Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Education Data, Research, and Evaluation in Nigeria (EDOREN)
Programme Value: initially £5,998,766 extended in 2016 to £6,788,336, and in 2017 to £9,638,292		Review Date: June 2017
Programme Code: 202643	Start Date: 11/03/2013	End Date: initially 10/03/2017, extended to 31/03/2018

Summary of Programme Performance
Year	2014	2015/16	2016/17
Programme Score	A	A	A
Risk Rating	medium	medium	Low

Summary of progress and lessons learnt since last review

EDOREN has met or exceeded the majority of output-level milestones over the past reporting year. The programme has carried out large-scale research and evaluation work for all four DFID Nigeria education programmes (GEP3, TDP, DEEPEN, ESSPIN), and delivered independent thematic research, support and capacity strengthening to Nigerian education research, policy making, and data-gathering activities, as well as a wide range of derived knowledge products to serve the Nigerian education sector. Work done has been of consistently good quality and EDOREN has effective partnerships with its stakeholders including DFID education programmes, government and the education research community in Nigeria. The Programme engaged well with the recommendations from the 2016 Annual review. Specific responses to the recommendations from the last Annual review are set out in the Output sections below.
The future of EDOREN was not clear at the time of the last Annual Review. In April 2017, it was eventually clarified. Following the outcome of DFID Nigeria’s Portfolio Quality Review, EDOREN will now end in 2018, not 2021 as originally intended. The decision to end the EDOREN programme earlier was not because of concerns about the Programme’s achievements over its lifetime, rather in response to a realignment of DFID Nigeria’s programme portfolio after a DFID wide assessment of programmes requested by UK Ministers.

The decision to bring forward the end of EDOREN to 2018 secures the value of the investments made, including research already in progress, and positions the DFID Nigeria education portfolio to deliver results beyond 2018. In the final year of the Programme, EDOREN will complete ongoing high quality impact evaluations for 2 DFID Nigeria education projects – TDP and GEP3; complete evaluation for the private education programme, DEEPEN, disseminate the findings of research on access to education and conflict in the North East and conduct collaborative research on disability issues in education. The research and evidence work done by EDOREN is a critical element of the DFID Nigeria education portfolio and has strongly influenced the use of evidence in all DFIDN education programming. Over the past year, EDOREN’s research has influenced the ongoing implementation of existing programmes and the design of the new Education in Emergencies programme which is part of DFID Nigeria’s new Humantiarian Transition programme, NENTAD, 2017. Research and evidence will continue to play a key role in good quality programming and DFID Nigeria will take forward successful elements of the EDOREN project in the design and implementation of a planned new education programme from 2018, PLANE (Partnership for Learning for All in Nigeria – in design).

EDOREN’s progress in terms of delivering high quality outputs is strongly evidenced in the Programme’s reporting and monitoring which has improved over the past year. This Annual Review finds that EDOREN has broadly appropriate capacity in terms of staffing although there are some concerns about staffing capacity, particularly in Abuja, in the final busy year of the programme. Governance and quality assurance are managed well in the Programme and there are strong relationships with key stakeholders to deliver at output level. The reduction in the timescale of the programme heightens the need to ensure delivery at the outcome level and the focus of the programme should be to continue to demonstrate this strongly. This is a timely moment to emphasise the importance of programming to ensure the sustainability of key initiatives and ensure that programme activities and the logframe are able to demonstrate efforts to enhance sustainability in the final year of EDOREN.

Summary of recommendations for the next year

Specific recommendations for each Output area are set out in the Output sections below.

The broader set of recommendations immediately below prioritise the cross-programme issues that are most important in the final year of the Programme and in recognition that there will be a Project Completion review, to be completed by end June 2018. The recommendations are for both EDOREN and for DFID.

In its final year, EDOREN must:
- Revise the programme risk register to identify risks to the sustainability of programme outputs and activities, and mitigating actions. (July 2017)
- Finalise the programme plan for sustainability and revise the logframe accordingly. The sustainability plan should be informed by the revised risk register and clearly set out where sustainability can be maximised in the Programme and what EDOREN should prioritise activities to March 2018 to enable sustainability. The plan should help EDOREN focus its engagement with other DFID programmes and external partners to enhance the sustainability of EDOREN objectives, maintaining the momentum of EDOREN work to date and taking opportunities to embed the use of evidence. The prioritisation emerging from sustainability planning should feed into the review of the logframe (August 2017)
- Prepare for the PCR including – (i) Systematically setting out evidence about the extent to which the Project has made progress towards or/and achieved higher level outcomes; (ii) ensure an indepth assessment of Value for Money (including efficiency and effectiveness), drawing from expenditure data and VfM analysis of other DFIDN (education) projects where required and drawing on perspectives from DFID HQ on VfM in Research programming – this will feed into the PCR (March 2018)
- Strongly consider additional day to day management, coordination and technical support for the Abuja based/in country team in the final 9 months of the Programme noting the volume of work to the end of the Programme – strong consideration should be given to engaging a national for this work (Sep 2017)
- Respond to the specifc output focused recommendations set out in the Output sections below (Mar 2018).

In the final year of the programme, DFID must ensure that:
- The EDOREN Logframe is appropriate for the focus on sustainability in the light of the shortened and more prioritised programme going forward (Aug 2017)
- EDOREN delivers on a more systematic approach to reporting on VFM in line with the recommendations on VFM in the Output recommendations and in the VFM section below (quarterly and by end March 2018)
- The emerging lesson learning from EDOREN about what works to improve research, evaluation, data generation and use and policy update are fed into DFID’s planned new education programme, PLANE (Dec 2017)
- The final PCR includes strong input from DFID HQ Research and Evidence division and takes into account the need to extract broad lessons for DFID, emerging from the conceptualisation and implementation of EDOREN; ensure that these lessons are shared more broadly across DFID (June 2018)

A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-205066/documents
DevTracker Link to Log frame:

Outline of the programme

EDOREN was planned as an eight year programme, contracted to OPM for four years to 2017. Following the outcome of the DFID Portfolio Quality Review (2017), the Programme was shortened by three years, meaning a final year for the programme in 2018. EDOREN aims to generate new evidence and understanding of how best to support equitable access and improved learning outcomes for Nigerian children. The project has two central objectives:

To embed research, evaluation and learning in DFID’s education sector support in Nigeria. This involves adding value to, and improving the performance of, DFID Nigeria’s current basic education sector portfolio; and informing DFID Nigeria’s education strategy by synthesising and interpreting the evidence and knowledge gained from current projects, EDOREN’s independent research, and relevant comparative research.

To enhance national capacities to generate and use quality educational data, research and evaluation for policy and strategy making. This requires all EDOREN activities, whether in support of the DFID Nigeria education portfolio or separately, to apply well-articulated approaches to the development of individual and/or organisational capacity. It also entails working with stakeholders and partners to increase both the demand for and the capacity to supply high-quality educational data for policy-making. This aim is underpinned by EDOREN support and initiatives for improved data collection and management across a range of stakeholder programmes.

The Theory of Change and logframe capture the objectives in two higher-level logframe outcomes:
1. Improved DFID education portfolio performance; and
2. Improved education policy development and implementation.

These higher-level outcomes derive from three intermediate outcomes:
- Outputs are used by DFID and DFID education portfolio programmes to improve portfolio design and implementation;
- Outputs are used by state and federal governments to improve education policy design and service provision;
- Education data collection and analysis in Nigeria is improved in key states.

Outputs to achieve these outcomes are grouped in four areas:
1. Evaluations, reviews and operational research studies for DFID Nigeria education programmes (delivered by worstreams 1-4, which are dedicated to supporting GEP3, TDP, DEEPEN, and ESSPIN, respectively)
2. Primary and secondary studies on key basic education issues in Nigeria (mainy workstream 5 thematic research oututs, but also Policy Impact workstream)
3. Education database, data tools, processes and data reviews (mainly workstream 6: EMIS, ASC, and database support)
4. Derived knowledge and dissemination products (mainly Policy Impact workstream, building on other workstreams’ outputs)

This is the third annual review of the EDOREN project since full implementation began, and the second since the establishment of EDOREN as a standalone project in June 2015.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The higher level outcome 1 in the Logframe is Improved DFID education portfolio performance and the higher level outcome 2 is Improved education policy development and implementation. EDOREN has made solid progress in taking forward activities which are contributing to the programme outcomes in both areas with evidence of progress towards achievement of outcome level indicators in both areas.

Activities over the past year demonstrating progress towards the delivery of higher level outcome 1 include EDOREN’s direct work carrying out high quality research and evaluation for DFID Nigeria education programmes which is influencing the modifications in implementation of those programmes. EDOREN’s work has directly influenced the design of DFID’s new Education in Emergencies programme, an element of the new DFID Nigeria Humanitarian Transition programme, NENTAD. EDOREN evidence and EDOREN Technical Assistance provided important inputs for the draft strategic case for DFID’s planned new education programme, PLANE. EDOREN also supported DFID, other education projects and government with using data for planning and for results reporting.

Activities over the past year demonstrating progress towards the delivery of higher level outcome 2 include the positive reception by stakeholders of EDOREN’s collaborative research work and evidence of use of the findings of that research in local government decision making for teacher recruitment. There was positive reception by stakeholders including the Nigerian research community and senior policy makers from state and federal level of EDOREN support to the Federal Ministry that enabled the 2nd Nigeria Annual Education conference. EDOREN has also supported capacity development for state and local data officers to use education data.

EDOREN has built strong relationships with all programmes in the DFIDN education portfolio and education government partners beyond at federal and state levels, amongst other development partners and with a range of Nigerian academic institutions.

Overall output score and description

The overall output score is A, outputs met expectation. This score is based on assessment of progress against milestones and logframe targets over the past year, the consistently good quality of outputs and positive indication of progress towards higher level outcomes, noting the risks associated with attainment of those outcomes in the reduced timeframe. Notably, the programme has been responsive in the midst of these changes including re-priorisiting activites in line with DFID needs and budget constraints. The programme has demonstrated commitment to gather evidence of progress towards outcomes by the end of the Project in 2018.

Key lessons and key actions

The programme logframe sets out appropriate indicators and sources of evidence to demonstrate delivery on outcomes. EDOREN’s overall theory of change remains credible, with the caveat that the initial plan for a longer programme would have enabled a longer time over which to demonstrate delivery on outcomes, particularly for Higher level outcome 2.
Given the unexpected time and capacity constraints faced by EDOREN, the programme should refresh the intermediate and higher level outcome milestones to 2018 in the logframe, informed by a review of the programme risk register and sustainability planning. The Programme will need more evidence to demonstrate delivery on those outcomes in the coming year.
Further reflections on key lessons are set out in the Output sections below.

Has the logframe been updated since the last review?

The Theory of Change and Logframe were significantly revised in 2015/16 in advance of the lasty Annual review. No substantial changes to the logframe were made during this past year (2016/17), except to recognise the revised end of Project date and accompanying output milestones as agreed with DFID in April 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Evaluations, reviews, and operational research studies for DFID Nigeria education programmes
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	60%
Risk revised since last AR?		Y (in line with new DFID risk scoring)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of evaluation products signed off by DFID evaluation review processes	GEP3 baseline report	Reports completed. / Very positive feedback from EQUALS on GEP3 baseline report. Follow up provided for TDP and DEEPEN baselines completed in previous year, including policy briefs. Dissemination ongoing on GEP3 baseline report
Number of other research studies in the context of DFID-N programmes signed off by DFID	TDP In-service training activities - Formative Research / TDP Teacher Supply and Demand Study / DEEPEN Public-Private Primary 4 comparison Study	Reports completed. Separate knowledge products not requested by programmes and no dissemination events carried out. Some technical issues still to be resolved with the DEEPEN P4 study before finalisation of report.

Key points

As in previous years, DFID projects were unanimous in their views of EDOREN’s demonstrated capacity to provide quality technical evaluation processes and reports. The past year has been characterised by improved ways of working between EDOREN and programmes, with greater clarity on the roles and responsibilities associated with survey preparation, implementation, reporting and dissemination. The feedback from the DFID Evaluation Quality Assurance team, EQUALS (formerly SEQAS) gave a stellar rating to the GEP 3 baseline report calling it the best baseline survey report ever reviewed by the unit.

Over the past year, EDOREN has worked well with projects to support them to understand and use the evidence generated from baseline reports, including those carried out in the 2015/16 period. EDOREN has also responded to ungoing demand from programmes to support with communication and dissemination of the findings from the baseline with stakeholders, including government. This has included development of presentations, policy briefs and jointly planning dissemination sessions with programmes. EDOREN engaged well with programmes to meet research needs emerging from the surveys and on specific other technical work emerging from the research. In the case of TDP, EDOREN supported TDP to respond to demand from state goverments to systematically look into teacher supply and demand and this has led to state governments now seeking to better plan for and manage their pipeline of teachers. In the case of DEEPEN, EDOREN supported the programme to better understand the implications of the baseline survey regarding how learning outcomes could be better supported, including investigating particular concerns around low levels of learning in numeracy in private schools primary grade 4.

While all DFID programmes were strongly of the view that EDOREN has delivered value for them over the past year, a number of concerns were raised which will need to be engaged with by EDOREN and also by DFID. These concerns include – (i) the fair amount of time taken from surveys being carried out to reports being produced – in the longest case, the GEP3 baseline, the total amount of time from survey (Nov 2015) to final report was 12 months (Dec 2016), (ii) the value for money of some high quality pieces of research work vis a vis the type of research and reporting required for policy makers to understand key issues and take action, (iii) the need to continue to build local capacity beyond data collection/ enumeration to expand the pool of quality nationals in data analysis and reporting (iv) the need for policy makers and Nigerian researchers to be more involved in the design and processes of high quality evaluations of DFID programmes, to support research uptake.

Summary of responses to issues raised in previous annual reviews

Output 1 recommendations from the last Annual review were responded to as follows:

- EDOREN capacity enhancement should include a stronger element of developing local data analysis and reporting skills – Done. EDOREN strongly responded to this recommendation with regard to the approach taken to conduct thematic studies – on conflict in the North East and on teacher effectiveness (see discussion on Output X below). In Output one, use of local capacity on analysis and reporting has been limited though there are clear plans to tackle this across all workstreams as the follow up evaluations for DFID projects take place in the final quarter of Quarter 4, 2017
- DFID to undertake a cost analysis of survey work – In progress. At the time of the AR, this work is in progress, following commissioning by DFID, with support from EDOREN
- EDOREN to develop a tool that projects can use to review outputs delivered by EDOREN - Done. the tool was developed but is not yet in use, feedback on the draft tool from DFID programmes is in process and will be used in the coming months as part of EDOREN’s efforts to demonstrate programme impact before the Programme end
- As recommended in the last Annual review, the logframe has been revised to remove the indicator associated with EDOREN’s support to Annual reviews, to reflect DFID SRO responsibility for completing reviews

Recommendations

Before the end of the Programme and with a view to – (i) reducing the amount of time taken to conduct data analysis for surveys, (ii) demonstrating ways of using national/local capacity more – beyond data collection/enumeration to also do more data analysis and reporting - EDOREN should re-look at the processes currently used in its research methods and consider adopting new approaches such as greater use of software tools to analyse qualitative data – this recommendation is also valid for Output 2

Before the end of the Programme and with a view to improving engagement and uptake of research findings - EDOREN should ensure greater involvement, in accountable ways, of key senior federal and state (FME, UBEC, data agencies) government officials in the planning, conduct and dissemination plans for the follow up surveys for GEP3 and TDP in Sep to Nov 2017 – this recommendation is also valid for Output 2.

As part of VFM reporting in the final year of the programme, benchmark EDOREN expenditure on surveys (including unit costs of data collection, analysis, reporting) with similar (where they exist) surveys carried out by other DFID Nigeria education (and other) programmes

In the final evaluation reports for DFID programmes to be submitted by the endof the Programme, EDOREN to reflect on the challenges associated with the Evaluation frameworks (TDP, GEP3 and DEEPEN) and provide lessons to inform future work on Evaluation frameworks that may better engage with the needs of key stakeholders and be adaptible to changing circumstances.
## C: DETAILED OUTPUT SCORING

Output Title	Primary and secondary studies on key basic education issues in Nigeria
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		Y (in line with new DFID risk scoring)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of studies signed off by DFID advisers	TR3: Thematic Research Study on Identifying, Recruiting, and Deploying Effective Teachers / TR4: Thematic Research study on primary school attendance in the wake of conflict in Borno	Both completed. / Follow-up studies and dissemination planned in mid- 2017

Key Points

EDOREN’s approach to delivering these two milestones have been innovative in demonstrating new ways of working. For the thematic research on teachers, EDOREN used a collaborative research and capacity strengthening approach which brought together research teams composed of academics in higher-instittuions and policy-makers in state ministris and SUBEBs, who had traditionally never cooperated on research issues. The approach led to new relationships and teams being formed across institutional and hierarchical divides as it deliberaterly included both junior and senior academics from federal and state universtities and institutes in Kano and Kaduna and from government institutions. The approach has been well received by stakeholders. In Kaduna state the team formed has continued to work well together beyond the initial remit of the study and has used the findings from the research in “live” policy decisions in the state, such as in implementing a revised approach to teacher recruitment in Kudan Local Government. EDOREN is in the process of following up the teacher effectiveness research, again using a collaborative approach and in addition, drawing on partnership with DFID programmes – PERL and TDP – to expand the scope of coverage of the research to include Jigawa, Katsina and Zamfara states. This research approach highlights the value of involving high-level officials as active partcipants in research design and where possible analysis, to enhance research uptake.

EDOREN’s second thematic research study, into primary school attendance in the wake of conflict in Borno, followed a two stage approach, the first of which involved collaboration with Girl Effect, which used teenage girls and young women trained through its Technology Enabled Girl Ambassadors (TEGA) programme to conduct structured data collection to examine parents’ and children’s attitudes toward primary school in the two communities the study focused on. This study was qualitative and was not designed to be representative of Borno or north-east Nigeria as a whole, but its findings are expected to be highly relevant to other urban and peri-urban communities in Borno that have experienced similar reductions in violence. EDOREN addressed the significant challenge of working in a very high-risk environment, in Borno by extensively training and guiding local researchers to work with a high level of independence. The resulting study has been reviewed by DFID, and dissemination will occur in July 2017. Even before dissemination, the key findings from the research have been shared by DFID with broader stakeholders and have informed the design of new DFID programming for Education in Emergencies in Borno and Yobe states.

EDOREN has strongly engaged with last year’s AR recommendation to engage more with national/local capcity in this Output, as the programme has balanced earlier concerns around a possible trade-off between having high-quality research and having strong local capacity. The approaches used for thematic research over the past year point to improved ways of carrying out research with the objectives of embedding the results of the research to achieve policy impact, in sustainable ways and considering gendered elements (use of TEGA). Lessons from these approaches should be captured by EDOREN to improve knowledge sharing and research practices more broadly.

Summary of responses to issues raised in previous annual reviews (where relevant)

Output 2 recommendations from the last Annual review were responded to as follows –

EDOREN to build opportunities to engage with stakeholders on research recommendations into government engagement approach and longer term communication plans, for example follow up with UBEC on the UBE reform work – Done. as set out above, EDOREN’s collaborative research on teacher effectiveness demonstrates better engagement with government and other stakeholders, including other DFID programmes, on research to support policy impact. While the UBE Commission itself did not demonstrate strong demand for further engagement with EDOREN, the programme has supported other key stakeholders who are key influencers of UBE including the World Bank which has engaged strongly with UBEC over the past year as the key government agency to deliver a planned new $611 million basic education programme using results based financing. EDOREN’s plans in the current year to support institutional exchanges of staff within government departments – supporting academics to work in policy environments for example – will aid these engagement efforts.

Recommendations

See recommendations (i), (ii) and (iii) under Output 1 above as they are relevant under Output 2, as these recommendations are relevant for planned Output 2 thematic research on disability in basic education.

Engage with DFID and other education projects to ensure that the value of the thematic research on teachers is maximised in DFID education and governance projects.

## C: DETAILED OUTPUT SCORING

Output Title	Education database, data tools, processes, and data reviews
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		Y (in line with new DFID risk scoring)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of data quality outputs completed (reviews, workshops with programme teams)	Target: 8 / (1) support for at least 3 workshops on improving quality and timeliness of 2015/16 Annual School Census (ASC) using Unesco Institute of Statistics software; (2) Support for 2015/16 joint validation survey (ESSPIN/GEP); (3) Dissemination of linked ASC data and school quality index (ISD), (4) Dissemination of Schools Intervention Database, (5) Capacity building on use of data for Local government and state planners; (6) Nigeria Education Data Survey Out of School Children report finalised OoSC report; (7) Kano and Jigawa EMIS workshop for LGA planners; (8) Kano EMIS Workshop for state planners on more advanced data use	All milestones delivered. / In addition, the team drafted a consolidated report on data initiatives (e.g. LEARN Nigeria, National EMIS) and participated in a range of data-related workshops and stakeholders’ meetings including those called by Federal government Education MDAs. / The team also provided strategic support to DFIDN on evidence and data to inform DFIDN new education programme, PLANE and DFIDN results reporting

Key Points

Achievements of milestones over the past year has demonstrated the value of EDOREN’s data work to DFID programmes and external stakeholders including other development partners and government. The Programme is routinely called in to provide external QA in a range of data areas, often with short notice, and has responded well. For example, the Programme responded very quickly to a request from the Federal Ministry of Eduction to support the finalisation of the Ministerial Strategic plan, 2016-19, including support on data, costing and monitory and evaluation. A key lesson learned over the past year has been the value of maintaining budget and workplan flexibility for critical short-term strategic support to partners.

Key achievements over the past year included capacity building efforts for state and local government officials in DFID partner states of Kano, Kaduna and Jigawa – to strengthen the use of data for planning at state and particularly at local government level, working in collaboration with the agenda of other DFID programmes, first ESSPIN (which ended in January 2017) and the TDP.

EDOREN worked collaboratively with UNICEF to support the external review of education data systems across Nigeria. This joint working has been an important way of demonstrating development partner collaboration on data. EDOREN has contributed to DFID’s thinking on data for the planned new education programme and has contributed to other development partners thinking, particularly the World Bank, on the data and monitoring and evaluation needs of its planned new $600+m Programme for Results. In response to broader stakeholder questions about Nigeria’s Out of School Children (OOSC) data, EDOREN produced a report getting under the skin of existing household data (the Nigerian Education data survey) to be able to set out in more detail what we know about OOSC numbers and patterns and what this means for policy in these areas.

Summary of responses to issues raised in previous annual reviews (where relevant)

Output 3 recommendations from the last Annual review were responded to as follows –

EDOREN to revise data section of Policy Impact Strategy, with a clearly articulated vision and consideration of capacity development needs – Done. A note on DFID Nigeria’s “data vision” with detailed sections on data issues in relation to EDOREN’s policy impact (PI) strategy and activities planned for the remaining duration of the programme, was delivered in Nov 2016. The support to cross local government and state staff on use of data across DFID partner states has been an important element of work drawing from this note.

EDOREN to put in place a mechanism to capture lessons learnt from data activities - Done. During the year under review EDOREN captured feedback from participants involved in the capacity building workshops on use of data for state and local government officials

Recommendations

Before the end of the Programme (March 2018), Output 3 to review the conduct of the ASC (annual school census) in states over the past 2 years, particularly reviewing progress in former Education Sector Support Programme in Nigeria (ESSPIN) supported states. The review should assess progress informed by the ASC activities of states and the National Education Management Information Systems (NEMIS) unit, the findings of the Association of Development of Education in Africa (ADEA) validation report 2016, the EDOREN Data note 2016, the ongoing work of UNICEF-GEP3 on ASC and support to school record keeping, and set against the opportunities of planned new World Bank funding to support data and M&E. The report should provide DFID with a set of recommendations for future work to support data in basic education

Before the end of the Programme, review progress on approaches in Nigeria to monitor learning outcomes, including those carried out by government agencies, by other development partners, by EDOREN and by the efforts to develop Citizen led assessments in Nigeria – in schools and in households, and provide recommendations for DFID’s future support on learning outcomes

Before the end of the Programme, consider the possibility and opportunities of doing specific work analysing expenditure on education within selected state systems to provide evidence on value for money in government systems

## C: DETAILED OUTPUT SCORING

Output Title	Derived knowledge and dissemination products
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		Y (in line with new DFID risk scoring)	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Percentage of planned communication processes delivered	100% of outputs set out in agreed policy impact workplan completed on time (including agreed contributions to DFID strategy) / 10% year-on-year growth of nigeriaeducation.org website hits	All milestones achieved (though not always on time) / All dissemination outputs delivered – of 70 outputs on June 2016’s plan, 25 pertained to years beyond March 2017 (in the expectation of EDOREN’s extension), 12 were obsolete due to changes in DFID programmes and DFID prioities and the remaining 33 were delivered. There is a plan for communications and dissemination work to the end of the Programme. / Overachieved on year-on-year growth of Nigeria-Education.org website traffic: 61%, from 15,868 visitors in the year to March 2016 to 25,853 in the year to March 2017.
Number of individuals participating in and demonstrably benefiting from capacity enhancement activities	20 Nigerian researchers trained on education research / 50 Nigerian government officials attending EDOREN dissemination workshops or meetings on education research	Achieved / 20 researchers in Teacher Study; 8 researchers trained in Conflict Study (not counting use of Girl Effect TEGAs); / Total number of state and local government participants at “Use of data” sessions in DFID partner states – 138.

Key points

This output is most focused on Policy impact and derives its achievements from work done across all other outputs. Over the past year, EDOREN has continued to maintain a growing database of relevant education research from its own work as well as external sources, and makes them publicly available on the website http://www.nigeria-education.org. EDOREN also supports http://www.naec.ng to redirect traffic pertaining to Nigeria’s Annual Education Conference (NAEC) to the relevant pages on Nigeria-Education. EDOREN tracks the programme’s dissemination outputs. Outputs include professionally design reports for dissemination, presentations, policy briefs, and blog posts, and are aligned with joint dissemination plans that exist with DFID’s portfolio of Nigerian education programmes. While all outputs planned were delivered during the review period, some products were delayed. Timelines will need to be managed better if EDOREN is to deliver on its ambitous plans to end March 2018.

EDOREN has been successful in establishing and embedding processes for the communication and dissemination of research. The support to the Federal Ministry for the Nigerian Annual Education Conference (NAEC) is notable and the November 2016 Conference drew the highest levels of engagement with the keynote address delivered by the Vice President of Nigeria. The Federal Ministry’s commitment to continuing the conference is demonstrated in the clear role of the Planning department in organising the Conference and a new budget line created to support the Conference in the Federal Ministry’s budget. Specific activities during the year, such as support to the Ministerial Strategic Plan, have strongly underlined the value of embedded work with key government agencies. EDOREN researchers or individuals working with EDOREN can be placed not just to deliver support, but simultaneously to gain information, engage in an ongoing working-level dialogue, and achieve recognition and impact for research. The EDOREN Fellowship programme in the final year of Programme involving interagency exchange of staff is designed to capitalise on this lesson while enabling collaboration between agencies.

EDOREN has demonstrated commitment to supporting Nigerian researchers over the past year, increasing the number of nationals carrying out research activities for the programme. While a minority of nationals are involved in data analsysis, much of the engagement of locals is limited to data collection/enumeration.

With regard to effective policy uptake, EDOREN has sought to move beyond “dissemination” to “engagement” over the past year through hands on workshops and in the effort to kick start a Community of Practice (CoP) following the National Conference. The latter effort was however not followed up adequately by EDOREN and stakeholders engaged with during the Review were not convinced that the CoP model was appropriate for the context. Beyond this, this review remains concerned that EDOREN’s dissemination strategy is not sufficiently targeted to achieve impact. Targeting should not be only related to audiences but specific results. DFID recognises that shifting policy is a long-term process, and it is understandable that much of EDOREN’s outreach and dissemination activities are focussed on developing relationships, getting evidence into the hands of policy-makers, building stakeholders’ capacity to understand and use evidence. However, given the reduced timeframe for this programme, EDOREN should maximise impacts by being more specific and explicit regarding the objectives of its outreach and dissemination activities in its final year.
In terms of internal communication and dissemination across DFID, DFIDN has an important advocacy role to play to support greater visibility of the EDOREN approach within DFID by sharing lessons with other country offices and with the DFID Research and Evidence division.

Summary of responses to issues raised in previous annual reviews (where relevant)

Output 4 recommendations from the last Annual review were responded to as follows –

EDOREN should identify more intentional opportunities to build capacity and strengthen engagement with government counterparts in FME, UBEC and the states, targeting key individuals/departments such as Planning and Research - Done. As set out above, strong relationships were built during the year under review, evidence by the successful National Conference and support to local capacity strengthening in states on use of data.

EDOREN should identify opportunities to utilise their research for further synthesis products/policy briefs to fill evidence gaps in “hot” policy areas, for example develop a series of policy brief from the UBE reform study and other evidence, on financing/accountability/anti-corruption in education – Done. The development of policy briefs, increasingly by Nigerian researchers, is now a standard feature of EDOREN’s continuously updated matrix of dissemination products; the planned Fellowship scheme will enable a direct pathway to interact with key organisations on a close and daily basis. Plans going forward will focus on the synthesis and secondary use of EDOREN results generated over the last four years

EDOREN should review indicator 4.3 and explore options to capture quality of capacity enhancement activities as well as participation – Done. The indicator has been revised to read “Number of individuals participating in and demonstrably benefiting from capacity enhancement activities”; in the year under review, EDOREN has intentionally supported capacity enhancement activities enabling nationals to present evidence generated by EDOREN support in local and international fora.

Recommendations

- EDOREN should be more explicit about the intended impact and results associated with its outreach and dissemination activities in its final year of operation
- To aid sustainability efforts, EDOREN to engage more with national/local capacity in software development, infographics and innovative advocacy groups, where appropriate – to promote awareness raising and dissemination of basic education evidence amongst influential citizen groups
- To further support the Nigerian research community and support sustainability – engage more proactively to share the raw data and findings of EDOREN research with post graduate researchers and academics in education research departments/faculties in Nigerian higher institutions
- EDOREN to support the Federal Ministry with appropriate approaches to follow up on the NAEC Conference after the event, in ways which promote and report on evidence uptake amongst key stakeholders and enhance accountability for use of evidence in planning and implementation processes in government systems

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

A significant majority of EDOREN’s budget (75%) goes towards output 1 – support to DFID programmes. Under this Output, the key cost drivers are the fieldwork costs for evaluations and other research. These costs include fees for enumerators and local researchers, transport and security, plus international fees. Within the international fees, the key costs drivers include the number of days associated with data analysis and reporting. Going forward, the Programme will attempt to manage this by increasing the amount of local input involved in data analysis and reporting. The rest of the EDOREN budget is split between output 2 on thematic research (12%), output 3 on data (8%) and the remaining 12% is to support policy impact and management.

VfM performance compared to the original VfM proposition in the business case

EDOREN keeps track of its costs to enable VfM indicators to be assessed. Over the course of the project, costs for similar work – e.g. initial baseline surveys and follow up surveys 2-3 years later (as currently being planned) have remained largely the same. Over the past year, budgets and costs have been monitored by DFID and prioritisation of activities by DFID has meant that savings were found against initial budgets, demonstrating strong value for money for DFID.

EDOREN’s VFM strategy is an effective articulation of OPM’s approach to VFM. Going forward there will be a strong need to demonstrate VFM systematically, including – (i) specific VFM indicators to provide comparative data against other research programmes in DFID, drawing on unit costs and other data (ii) the use of DFID’s Key Supplier Management performance indicators to assess the efficiency and effectiveness of programme delivery, (iii) improved reporting on VFM, including better qualitative evidence, in quarterly reporting by EDOREN. The approach to VFM going forward should be informed by the findings of from a review of VFM across all DFID Nigeria education projects which had recently begun at the time of writing this Annual Review.

Assessment of whether the programme continues to represent value for money

The reprioritisation of work in the final year of EDOREN and the reduction against planned budget has demonstrated efforts to enhance overall Value for Money for DFID.

On the management of costs, EDOREN benefits from a shared office with other OPM staff. Activities are planned where possible to align with other DFID programmes activities in states and costs sharing mechanisms are agreed with other DFID programme, for example when covering the costs of dissemination. The increased use of Nigerian staff and consultants has been a positive development over the past year, both from a capacity strengthening perspective and also from a VfM perspective.

EDOREN invoices are based on actual reimbursable costs and fees based on outputs agreed in advance with DFID. Payment by results is implemented whereby milestones are paid for when they are delivered and delays to delivery has on occasion meant corresponding delays of DFID payments until the milestone is delivered. Judging by the fee rates as agreed in the contract with DFID, the costs of surveys and research and the value emerging from EDOREN’s work as evidence by engagement with stakeholders during the course of this review, the evidence suggests that EDOREN continues to represent value for money.

Reporting on VfM beyond economy to better report on efficiency and effectiveness needs to improve in the project going forward. A thorough VfM assessment will need to be provided and included as an important input into the Project Completion review in 2018.

Quality of financial management

Expenditure on the programme is monitored and reported quarterly and in annual reports. Expenditure during the last year and over the lifetime of the project has been close to the budgeted figures. EDOREN has responded fairly well to DFID’s instruction to maintain monthly variances in expenditure against budget within a 5% margin in Q1 – Q3 and 2% margin in Q4, as well the directive to spend 90% of annual budgets by end of the third quarter, which has influenced the timing of key activities including survey work. In the last year of project implementation (current year) EDOREN will continue to strive towards improved financial reporting and in ensuring that invoices are in line with forecasts provided, or within an acceptably low variance.

During the preivious reporting year, the external audit firm, Baker Tilly conducted a comprehensive financial audit of OPM’s management of EDOREN, including a review of the asset register, and reported no “material findings”, i.e. no substantial problems of discrepancies. The 2016 financial audit is ongoing at the time of this Annual Review and recommendations from the final report will inform any improvements that need to be made before the Project closes.

Date of last narrative financial report	10 June 2015
Date of last audited annual statement	14 May 2015

E: RISK

Overall risk rating: Low

Overview of programme risk
The overall risk rating has been amended to low in recognition of DFID’s 4 (rather than the former 3) risk categories. As EDOREN is a research programme and not involved in day to day delivery of programming in states and local governments, the DFID SRO and Lead Adviser concluded that on balance a Low (rather than Moderate risk) was an appropriate overall risk rating for EDOREN (other DFIDN eduation programmes involved in supporting states to deliver education services are rated as Moderate risk). The programme risk register was updated during the course of the year and will be looked at again following the completion of this Annual review as it will be important to ensure that they key delivery and other risks to the end of the Programme are clearly set out and being mitigated.

In the light of the confirmation of the Programme timeframe being shortened by 3 years, the highest level risk in the risk register is associated with potential implications of the shortened programme on Programme impact - “Reduced EDOREN overall impact and long-term outcomes, due to insufficient continued engagement with important range of external stakeholders, including DFID state staff and other partners leading to an inability to embed results, maintain convening power, or influence decision-making.” In particular, the risk extends beyond EDOREN’s lifetime if no follow-up programme or activity continues beyond April 2018, highlighting the need for DFID to take seriously the value of the work currently done by EDOREN in planned future programming in DFID Nigeria.

Other risks highlighted the challenges of changes to evaluation plans, particularly for DEEPEN and Bridge in the light of budget constraints and broader DFID priorities, meaning that the original intentions for these surveys in terms of the levels of robustness of findings that can be reached in the replacement evaluation work will not be as strong as originally intended.

Outstanding actions from risk assessment

1. EDOREN and DFID to better set out any reputational risks and any safe guarding risks associated with Programme implementation, following this AR.
2. This Annual Review recommends that the EDOREN risk matrix is revised following this annual review to identify risks to the sustainability of programme outputs and activities, and mitigating actions (by August 2017). This risk assessment with a focus on sustainability will help inform the prioritisation of EDOREN’s final year activities.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

EDOREN has now completed its 4th year implementation phase (September 2013 - March 2017), during which time the project delivery plan has been adjusted in close cooperation with DFID. Adjustments have been made to take into account changed circumstances, emerging priorities and the new project structure. For example, the programme was designed for two 4 year periods with a review after the first 4 years in 2017. but the outcome of the DFID Nigeria Portfolio Quality Review outcome has meant that an extension is being sought for only one year (2017 – 2018), so the project will continue for a further year to ensure responsible exit.

The project faced a fair amount of uncertainty about it’s future since the last AR but is now clear that it will end in March 2018, following the outcome of the DFIDN Portfolio Quality Review (PQR). This does mean that EDOREN has it’s most ambitious year of activity to date and will need to be closely monitored to prioritise activities that enhance sustainability and learning beyond the life of the Programme, while continuing with high quality delivery in its final year.

Performance of partnership (s)

OPM’s consortium partner for EDOREN is the Institute of Development Studies (IDS) of the University of Sussex. IDS’s role has included knowledge management and dissemination aspects, but since 2016, has been re-defined more narrowly to focus on a core competence that OPM and the EDOREN office in Abuja cannot perform themselves, which is the technical maintenance of the EDOREN and Nigeria-Education.org websites. By increasingly using OPM’s own expertise and communication teams, as well as a further shift of activities towards Abuja, and local service providers, EDOREN has kept communication and dissemination costs down, and moved responsibility for dissemination closer to key stakeholders in Abuja.

DFID’s partnership with EDOREN is positive and DFID finds the Programme to have been flexible and responsive, particularly in dealing with the uncertainty associated with the Programme’s future and the need to reprioritise activities and reduce budgets, during the period under review. This review also found that working relationships between EDOREN and other DFIDN projects are positive and EDOREN proactively engaged well with the PERL(Governance) programme to support greater roll out of its research and policy impact agenda and as part of broader sustainability efforts. Protocols for ways of working between EDOREN and other programmes have been improved during the period under review and the Organisation structure recognising the role of Workstream leads responsible for interactions with Programmes, appears to be fit for purpose. Partnerships with the wider community, vary in intensity but also appear to be productive. EDOREN has intensified its relationships with State Ministries and SUBEBs and with Academic institutions over the past year – for the former recognising the need for partnership between DFID education and governance programmes in establishing effective engagement at state and local level.

Asset monitoring and control

All items belonging to the project are listed in an asset register, which is regularly updated. Asset reports are verified by Country Director. Asset monitoring is undertaken by DFID at least twice a year and is also an element included in the financial audit exercise. During the reporting year under review, the external audit firm Baker Tilly conducted a comprehensive financial audit of OPM’s management of EDOREN, including a review of the asset register, and reported no “material findings”, i.e. no substantial problems of discrepancies. The 2016 financial audit is ongoing at the time of this Annual Review and recommendations from the final report will inform any improvements that need to be made to improve asset monitoring and control.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The Partnership Principles were not considered within the project business case. In September 2014, DFID Nigeria conducted an assessment of the Federal Government of Nigeria commitment to the Partnership Principles which reconfirmed the UK’s declared policy that no UK aid money should go directly to the Government of Nigeria: as an anti-corruption measure and to avoid substituting for the country’s own resources. EDOREN is consistent with this policy. As the programme is delivered directly by an implementing partner with no funding through government channels, the Partnership Principles are not relevant for the direct management and monitoring of this project.

H: MONITORING & EVALUATION

Evidence and evaluation, and Monitoring progress throughout the review period

EDOREN does not have a formal evaluation. Monitoring takes place through the logframe and policy impact assessment tools, as well as quarterly reporting to DFID where progress against milestones is determined and payments for milestones approved when evidence of their being met is demonstrated to DFID. In line with recommendations from the last AR, EDOREN developed a tool to receive feedback from stakeholders on its research process, outputs, and use. EDOREN has produced a detailed study (currently in draft) on EDOREN’s capacity strengthening effects and strategy, evidencing significant progress in involving local stakeholders.

EDOREN intends to undertake further case studies of its impact during the current (final) project year, to gather and use case studies to support reporting and evidence of achievement of outcomes.

In the final year, DFID and EDOREN will need to engage more closely with research teams at DFID HQ. DFIDN recognises the uniqueness of the EDOREN project – having a standalone research and evaluation project on education in country – and is keen to share lessons with other Research programming and also learn lessons as to what works to support research, evidence and data efforts and achieve policy impact in developing country contexts. The thinking around this should inform EDORENs Sustainability Plan (to be completed August 2017).

The annual review process

This annual review was carried out in June 2017, led by the DFID Nigeria education adviser, supported by 10% support from the DFID HG Education Research team, the SRO/Team Deputy programme manager and the Programme Officer from the DFID Nigeria Human development team. The Terms of Reference for the review focused on assessing the extent to which EDOREN met the recommendations from the last Annual review, assessing overall progress to date and providing recommendations to help EDOREN exit responsibility. The latter included considerations regarding sustainability and lesson learning. The review involved a document review of reports produced over the reporting year, engagement with the Programme’s self-assessment of their delivery against plan, meetings with the EDOREN team in country and in the UK, and discussions with stakeholders from government and from other DFID projects.