Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Khyber Pakhtunkhwa Education Sector Programme
Programme Value: £283.2 million		Review Date: September 2017
Programme Code: 202328	Start Date: August 2011	End Date: July 2020

Summary of Programme Performance
Year	2012	2013	2014	2015	2015	2016	2017
Programme Score	C	B	B	A	A	A	A
Risk Rating	High	High	High	High	High	Major	Major

Summary of progress and lessons learnt since last review
DFID’s Khyber Pakhtunkhwa Education Sector Programme (KESP) supports the Government of Khyber Pakhtunkhwa (GoKP) to deliver better quality education for more children across the province of Khyber Pakhtunkhwa (KP) in Pakistan. In particular, it aims to improve learning outcomes for all children, with an increasing focus on girls and marginalised groups. DFID does this by providing sector budget support (SBS) to the GoKP’s Elementary and Secondary Education Department (E&SED) to finance the provincial Education Sector Plan (ESP), and technical assistance (TA) to the GoKP through Adam Smith International (ASI) to help implement their reform agenda linked to the ESP. DFID also funds IMC Worldwide, an international development company, operating under the brand name Humqadam in Pakistan, to construct and rehabilitate school infrastructure.
This has been a strong year for education in Khyber Pakhtunkhwa. E&SED has demonstrated increased capacity, with particularly impressive progress made on public financial management (budget execution) and in some other specific parts of the department, such as the Independent Monitoring Unit (IMU). Initiatives developed this year include the School Improvement Framework, an Equity Strategy, a Teacher Induction Programme, a revised Continuous Professional Development Strategy for teachers, and the Out of School Children Census (OOSC). Success next year will be contingent on the implementation and monitoring of these pieces of work and on maintaining momentum for education reform through a likely to be eventful 12 months in domestic politics.

This year, four of the five outputs score an A, with the school infrastructure output again scoring a B. Challenges to both government and directly-contracted construction remain in terms of quality and of pace, but underneath this is a 580% increase on last year’s classroom completions by IMC Worldwide which needs to be further built on to meet the remaining milestones and targets.

Summary of recommendations for the next year
The recommendations below relate to the detailed analysis of the outputs scored in section C.

More effective teachers
1. Lessons learned from the School Quality Management Initiative (SQMI) pilot should be used to inform future scale-up.
2. The target for teacher attendance rate can be raised to a minimum of 90%.
3. An assessment strategy should be developed by ASI to streamline the current assessment policy and practices for grades 2, 5 and 8.
4. The TA and DFID teams should increase efforts to influence E&SED and GoKP for the formal approval and implementation of the new terms and conditions for teachers.
5. Teacher assessments (content knowledge and competency surveys) should be conducted earlier to feed into professional development activities which then need to be aligned with budget planning timelines.
Better schools and facilities
1. Output indicator 2.1 should be revised to measure the completion of work in schools and should set more stretching targets.
2. The 70:30 ratio (girls’ to boys’ schools) in indicator 2.2 will not be met because E&SED will now address missing facilities in all schools. It can be replaced by % of girls’ schools provided with missing facilities.
3. The Third Party Validation (TPV) should be reappointed to assess the quality of construction by Parent Teacher Councils (PTCs); and the use of non-technical PTCs to deliver missing facilities should be reviewed.
4. DFID should consider expanding the indicators under this output to capture infrastructure other than classrooms (toilets, exam halls, laboratories etc.)
Better (equitable) access to education
1. All stipends should be disbursed within the academic year, in particular in grade 10 after which girls complete school.
2. E&SED could consider a significant scale-up of the voucher programme with more stretching distribution and redemption rates. The capacity of EEF improved last year largely due to the new senior management team after restructuring supported by ASI and this could be further developed.
3. ASI should help EEF continue to improve the Girls’ Community School (GCS) model, including the teaching and learning and facilitating the girls’ transition to middle and secondary schooling.
4. The recommendations and options in the Equity Strategy should be implemented swiftly and monitored closely to assess their impact.
Good governance and management
1. For output indicator 4.1 the yearly target should be brought in line with the indicator and should try to capture the effectiveness of GoKP’s Online Action Management System (OAMS).
2. The target for school supervisory visits by district education staff should increase the coverage of schools and capture the outcome.
3. Delays in procurement processes have been affecting the timely delivery of some activities. ASI should provide TA for improving E&SED’s procurement systems and processes to help build the department’s procurement capacity.
4. Since all districts in KP have developed District Education Plan (DEPs) in line with the ESP, E&SED can focus on monitoring progress of their implementation. DFID should consider including some DEP targets under this output.
5. With more development funds going to districts under the local government system, there is a need to link DEPs with districts’ development budgets and build the capacity of district education staff to design and implement education related development schemes under the DEPs
Effective and efficient technical assistance
The DFID team should reassess this output once DFID’s new process for supplier management is finalised. If it is retained, the team should set clear and measurable expectations, and consider whether to add an indicator covering IMC’s performance.
Value for Money and financial performance
1. By December 2017, DFID should conduct a revised cost-benefit analysis, providing more accurate net present value estimates and a clearer assessment of Value for Money (VFM).
2. By December 2017, DFID should revisit the underlying Theory of Change to ensure that it is structured to best lead to the intended outcome.

A. Introduction and Context
DevTracker Link to Business Case:	Business Case: / http://iati.dfid.gov.uk/iati_documents/3745014.odt / Addendum to the BC: / http://iati.dfid.gov.uk/iati_documents/5064370.odt
DevTracker Link to Log frame:	2011-2015 log frame: / http://iati.dfid.gov.uk/iati_documents/5004175.xlsx / 2016-2020 log frame: / http://iati.dfid.gov.uk/iati_documents/5558320.xlsx

List of Acronyms

ADP	–	Annual Development Plan
AKRSP	–	Aga Khan Rural Support Programme
ASDEO	–	Assistant Sub-Divisional Education Officer
ASI	–	Adam Smith International
CBA	–	Cost Benefit Analysis
CPD	–	Continuous Professional Development
C&W	–	Communication and Works Department
DEP	–	District Education Plan
DMO	–	District Monitoring Officer
E&SED	–	Elementary and Secondary Education Department
EEF	–	Elementary Education Foundation
EMIS	–	Education Management Information System
ESP	–	Education Sector Plan
EY	–	Ernst & Young
GCS	–	Girls’ Community Schools
GoKP	–	Government of Khyber Pakhtunkhwa
HSS	–	Higher Secondary Schools
IMC	–	IMC Worldwide
IMU	–	Independent Monitoring Unit
JRF	–	Joint Review Framework
KESP	–	Khyber Pakhtunkhwa Education Sector Programme
KP	–	Khyber Pakhtunkhwa
KPI	–	Key Performance Indicator
KSM	–	Key Supplier Management
M&E	–	Monitoring and Evaluation
MIS	–	Management Information System
NER	–	Net Enrolment Rate
OAMS	–	Online Action Management System
OOSC	–	Out of School Children
PEAC	–	Provincial Education Assessment Center
PESP II	–	Punjab Education Support Programme II
PKR	–	Pakistani Rupee
PPA	–	Partnership Principles Assessment
PTC	–	Parent Teacher Council
SBS	–	Sector Budget Support
SCRP	–	School Construction and Rehabilitation Programme
SIF	–	School Improvement Framework
SLO	–	Student Learning Outcome
SQMI	–	School Quality Management Initiative
SRSP	–	Sarhad Rural Support Programme
STR	–	Student to Teacher Ratio
TA	–	Technical Assistance
TCS	–	Teacher Competency Survey
TPV	–	Third Party Validation
VFM	–	Value for Money

Outline of the programme
The intended impact of the Khyber Pakhtunkhwa Education Sector Programme (KESP) is to result in ‘more educated people in KP, making a positive social and economic contribution’. The outcome of KESP is ‘more children in school, staying longer and learning more’. This year, KESP directly supported 126,200 children to gain a decent education and indirectly benefits all 4.27 million children of school age (5-16) in government schools in KP. It also works to enrol many of the 1.5 million out of school children[1] in KP, with an increasing focus on girls. KESP contributes towards the fourth objective of the UK Aid Strategy: tackling extreme poverty and helping the world’s most vulnerable.
[1] Elementary and Secondary Education Department province-wide census of children aged 0-17 years
The three components of KESP have a total value of £283.2 million:
1. £181.2 million SBS to the GoKP on the basis of progress against the Joint Review Framework (JRF).
2. £42 million to fund TA to the GoKP to support delivery of the JRF, underpinned by the GoKP’s 2015-2020 Education Sector Plan (ESP), provided by Adam Smith International (ASI).
3. Up to £60 million for the construction and rehabilitation of classrooms, toilets and other facilities in government schools, implemented by IMC Worldwide (IMC), acting as Humqadam in Pakistan.
Through a Delegated Cooperation Agreement with the UK, the Australian Government is contributing AU$63.85 million (approximately £41.3 million), of which AU$32.15 million is allocated to SBS and AU$31.70 million for school construction and rehabilitation.
The performance of KESP has improved over its lifespan, scoring a C in 2012, Bs in 2013 and 2014, before As in 2015 and 2016. Last year’s review found that four of the five outputs’ milestones had been fully met or exceeded, with challenges remaining in the school construction component of output 2.
GoKP clearly prioritises education within its policy planning, with attention being paid at the highest levels of the government to the implementation of the ESP and increasing budgets for education to meet its ambitious targets. The ESP has ten core policies, organised into four policy areas essential to delivering better education outcomes for children. These are: more effective teachers; better schools and facilities; every child’s right to education; and good governance and management. DFID has restructured the programme log frame around these same four areas and agreed milestones to 2020 with E&SED. This and the fact that DFID has changed its risk measurement system mean that all the output weightings and risk ratings have changed since last year. See section C for new ratings and section E for risk.
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Indicator(s)	Baseline/earliest milestone available	Milestones	Progress
Indicator 1: Net enrolment rate[2] (NER) (primary, middle and high) by: / (i) whole eligible population; (ii) girls / (iii) boys / Source: Education Management Information System (EMIS)	2013 baseline / Primary Total: 48% Girls: 44% / Boys:52% Middle & Secondary Total: 20% Girls: 15% / Boys:25%	Primary / Total: 50% / Girls: 46% / Boys: 52% / Middle & Secondary / Total: 22% / Girls: 17% / Boys: 26%	Primary / Total: 48% / Girls: 45% / Boys:51% / Middle and Sec. / Total: 21% / Girls: 17% / Boys: 24%
Indicator 2: Out of school children at Primary and Secondary level	2012 baseline[3] / Primary: 2,838,847 / Girls: 1,250,736 / Boys: 1,588,111 / Secondary: 1,032,733 / Girls: 374,088 / Boys: 658,645 / Total: 3,871,580 / Girls: 1,624,824 / Boys: 2,246,756	OOSC census baseline to be established / 05-09 years / Girls: / Boys: / 10-17 years / Girls: / Boys: / Total: 05-17 years / Girls: / Boys:	OOSC Baseline established[4] / Primary: 624,650 / Girls: 410,969 / Boys: 213,681 / Secondary: 894,721 / Girls: 603,450 / Boys: 291,271 / Total: 1,519,371 / Girls: 1,014,419 / Boys: 504,952
Indicator 3: Student attendance rate by gender (government schools)[5]	Baseline May 2014 / Total: 73% Girls: 72% Boys: 73%	Total: 77% / Girls: 76% / Boys: 78%	Total: 77% / Girls: 75% / Boys: 79%
Indicator 4: Student learning outcomes in early grades by subject (public sector schools)	2016 baseline from PEAC[6] / English 42% / Urdu 40% / Maths 51%	PEAC: / English 42% / Urdu 40% / Maths 51%	Grade 2 PEAC: / English: 37% / Urdu: 40% / Maths: 44%
[2] Net Enrolment Rate refers to the number of students aged 5-9 years that are enrolled in a primary school, divided by the number of children in the age group for that level of education.
[3] Annual School Census - EMIS and OOSC census
[4] Elementary and Secondary Education Department province wide census of children aged 0-17 years
[5] Calculation: Total attendance in school level/ total enrolment in school level measured over the 10 months schools are open.
[6] The Provincial Education Assessment Centre (PEAC) grade two assessment measures average scores by subject on key Student Learning Outcomes (SLOs) for English, Urdu and Maths. PEAC data is a standardised test and is comparable over time.

While outcome indicators remain largely on-track, further work is required to ensure equitable achievement of the programme outcome in terms of attainment by gender and by subject. The Net Enrolment Rate (NER) (percentage of eligible children who are in school) at both primary and secondary is marginally off-track, though concerns around the quality of this indicator have led to an indicator relating to out of school children being added following the last annual review. The NER has continued to be measured this year whilst the baseline for out of school children was established, though this will be removed from the log frame now that the baseline is in place. The milestone for indicator 3 has largely been met, though achievement against the milestone for boys has been better than for girls. While the milestone for indicator 4 has been met for Urdu assessment, performance in English and Maths has been less positive and further efforts are required to get back on-track.
It will be important for the DFID team to work with GoKP and ASI to test the Theory of Change and ensure that the programme is working to deliver outputs that will lead to the intended outcome.

Overall output score and description

Overall, KESP scores an A this year. Each output scores an A except output 2, which scores a B.

- Output 1 aims to increase the effectiveness of teachers by: a) improving the student-teacher ratio to reach an optimal ratio in every government school; b) supporting districts to deliver Continuous Professional Development (CPD) to teachers; c) establishing the proportion of teachers achieving the minimum competency and increasing this over the life of the programme; and d) increasing the daily attendance rate of teachers in school.
- Output 2 aims to: a) improve schools through the provision of missing facilities (toilets, boundary walls, electricity, and drinking water) via the E&SED and b) rehabilitate schools, providing additional classrooms, through a separate DFID-managed contract with Humqadam.
- Output 3 aims to increase the enrolment and retention of girls and other marginalised children by: a) providing a monthly bursary (known as a stipend) to all 10-16 year old girls in government schools; b) offering free places (through a voucher scheme) at low-fee private schools for children in areas with insufficient government schools; and c) increasing and improving girls’ government schools and creating local community-run schools for girls (GCS) in remote areas.
- Output 4 aims to improve governance and management in the E&SED by: a) ensuring the Independent Monitoring Unit (IMU) conducts monthly monitoring visits to as many GCS and government schools as possible and collects reliable data; b) increasing the number of schools visited by district education staff every month for school supervision; c) supporting districts to develop and implement their own District Education Plans; and d) supporting the E&SED to achieve a high budget execution rate each year.
- Output 5 aims to provide effective and efficient TA which provides a high quality service to the GoKP to drive the necessary reforms to the education system, and provides timely and quality information to DFID about the progress of reform. This is provided through ASI.

Key lessons
1. The online action management system piloted in two districts did not have the desired impact when it was rolled out to all districts. The challenges of working at scale should be assessed and addressed before roll-out and targets will need to be realistic when pilots are scaled-up.
2. Key Performance Indicators (KPIs) need to be defined clearly to avoid confusion. They should be mapped over each 12 month period to assess progress and impact.
3. A hybrid contract with ASI, based on KPIs, helped the team to effectively manage them and improved the TA's performance this year.
4. Due to successful influencing by DFID and ASI, GoKP allocated a block amount of money to implement options in the Equity Strategy before it was finalised. This should avoid implementation gaps that are common in instances where the government develops policies first then seeks funds to implement them later.
5. DFID encouraged the TA to think more strategically. This led to linking up isolated activities and processes, which will help to achieve the outcome level objectives of the programme.
6. DFID has renegotiated the contract for school construction and rehabilitation with IMC Worldwide to set realistic targets, based on construction rates that have been tested in the market, and to introduce an element of output-basis to IMC’s payments.

Key actions
1. The KESP TA should develop an enrolment strategy to reduce the large number of out of school children identified through the recent OOSC census. This includes girls, children with disabilities and other marginalised groups.
2. By December 2017, DFID should revisit the underlying Theory of Change to ensure that it is structured to best lead to the intended outcome.

Has the log frame been updated since the last review?
The log frame has been adjusted since the last annual review and was approved in April 2017. This was done to align it with the Theory of Change and Joint Review Framework (JRF). Milestones were also added for the outer years.

## C: DETAILED OUTPUT SCORING

Output Title	More effective Teaching and Learning
Output number per LF		1	Output Score	A: Met Expectation
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1 % of primary schools with required Student Teacher Ratio (STR)	65%	A: Met expectation / 65%
1.2 # of districts implementing school based Continuous Professional Development (CPD) in at least 50% of the schools	4 districts implementing school based CPD in 50% of the schools	A+: Moderately exceeded expectation / 4 districts implementing school based CPD in 59% of the schools
1.3 (a) % of content knowledge exhibited by the primary school teachers in Science, English and Maths / (b) % of primary school teachers meeting teacher competency criteria	(a) Content Knowledge / English 44% / Maths 42% / Science 31% / (b) Teachers' Competency 25%[7]	Establishing new baseline – not scored / (a) Content Knowledge / English 40% / Maths 47.5% / Science 40% / (b) Teachers’ competency 49%
1.4 Teacher attendance rate	87%	A: Met expectation / 87%
1.5 Availability and use of assessment results/data	N/A	N/A
[7] 25% teachers’ competency scores are above 55%.

Key Points
This output achieved its targets. It assesses the Teaching and Learning work stream of the ESP, which focuses on improved recruitment and training of teachers. These are crucial to improving student learning outcomes. KESP is working on the improvement of content knowledge, competencies and pedagogical skills of all teachers in the province. New teachers’ terms and conditions have been developed and approved by E&SED, and are awaiting approval from the Law Department and KP Provincial Assembly. The reforms to teachers’ terms and conditions are an important building block for wider reforms to how teachers are recruited, trained and managed across the province. The School Quality Management Initiative (SQMI) has been piloted in two districts and will be launched in the whole province in 2017/18. It will collect data on student learning and teacher classroom practice that will be fed into the School Improvement Framework (SIF).

Indicator 1.1: % of primary schools with required Student Teacher Ratio (STR)
The output indicator target of 65% has been achieved. Progress is being made towards attaining the optimal student teacher ratio (OSTR) (40:1) by redeploying surplus teachers (rationalisation) and recruiting more teachers. An improved STR should increase the contact time between students and teachers and ensure schools have a dedicated teacher for each grade. It should also lead to improved student learning outcomes. Schools are not universally understaffed; in some cases the ratio is well below 40:1. GoKP has responded with a teacher ‘rationalisation’ exercise to spread teachers across schools and transfer orders have been issued by E&SED. There were 70,876 teachers in June 2016 and the number has now risen to 76,688 in June 2017. A total of 3,684 teachers were redeployed under teacher rationalisation. There are now 13,084 schools out of a total of 20,126 schools with the right STR. E&SED has hired 9,861 teachers through an improved National Testing Service (NTS) screening test; new teachers scored higher than the non-NTS teachers in a recent assessment.

Indicator 1.2: # of districts implementing school based CPD in at least 50% of the schools
This output indicator target was revised down during the year and has been slightly exceeded. The Continuous Professional Development programme (CPD) is currently the only intervention in the province related to teacher professional development. In November 2016, a review revealed that there were issues in the implementation of the CPD programme. It found that targets for the numbers of schools where CPD would take place were unrealistic and should be revised downwards from 80% to 50% due to the scale and size of the programme, with consequent challenges in monitoring, as well as the quality of supervisors and head teachers. A new CPD strategy was developed with TA support to increase its effectiveness. The revised model will be piloted in two districts in September and a successful model scaled up to all districts by August 2018. Closely linked to this is the restructuring of two important teacher professional development institutions: the Directorate for Curriculum and Teacher Education and the Provincial Institute for Teacher Education.

Indicator 1.3	(a) % of content knowledge exhibited by the primary school teachers in Science, English and Maths
(b) % of primary school teachers meeting teacher competency criteria

The aim for this year was to establish a new baseline for this indicator, which has been achieved. It assesses teachers’ content knowledge and core competencies which are pre-requisites for improved student learning. It was agreed that the surveys for two years (2015/16 and 2016/17) will serve as baselines for both the teacher content knowledge and teacher competency surveys because this year a more representative sample and rigorous methodology were used.

The teacher content knowledge assessments conducted by the Provincial Education Assessment Center (PEAC) in 2016/17 used a representative sample of 1,442 teachers from 835 schools. The sample was provincially representative with the teacher as the sampling unit. The assessment tests teachers’ content knowledge in core subjects. Teachers’ scores were 40% in English, 47.5% in Maths, and 40% in Science, showing a slight decline in English, but improvements in Maths and Science.

The teacher competency survey (TCS) assesses teachers on a range of pedagogical skills (11 competencies) through classroom observation. The TCS was conducted with a representative sample of 1,875 teachers from 974 schools (574 schools in CPD districts) in four districts[8]. Competency scores in CPD districts were comparatively better than scores of non-CPD districts, showing an overall increase from 42% in 2016 to 49% in 2017. These results indicate that most teacher competencies and content knowledge are poor, reflecting weaknesses in the existing teacher education programmes. A newly designed, intensive induction programme, to be implemented from September 2017, will be mandatory for new teachers.
[8] The sample for both years was provincially representative and was randomly drawn separately for both years. The size of the sample determines the accuracy of the findings.

Indicator 1.4 Teacher attendance rate
The output indicator target of 87% has been achieved. Teacher attendance has increased by two percentage points from last year. The target was reduced from 90% to 87% because the pilot was being rolled out to all districts. Teacher attendance is measured through the Online Action Management System (OAMS) by the Independent Monitoring Unit (IMU). The OAMS was piloted in two districts last year and scaled up to all districts in December 2016. Incremental disciplinary actions are taken by the district staff as a result of the information generated: one absence results in deduction of one day’s salary, a second in the removal of a year’s pay progression, and a third in dismissal. The scale-up is not showing the same results as the pilot. This could be due to the lack of provincial pressure for districts to carry out actions despite them being automatically issued. The TA team is undertaking further investigation into these trends.

Indicator 1.5 Availability and use of assessment results/data
This indicator will measure both availability of assessment data for grades 2 and 5 and the use of assessment data. It could not be scored this year because we first needed to establish a new baseline to measure the availability of data. A new baseline was needed for grade 2 because the sample size was increased based on lessons learned from the previous year. A baseline was established for grade 5[9].
[9] The results were: Grade 2 – English: 37%, Maths: 44%, Urdu: 40%; Grade 5 – English: 33%, Maths: 13%, Science: 24%

The sample grade 2 and universal grade 5 assessments comprehensively tested students against student learning outcomes in KP. A compendium of errors on the results was developed which included remedial activities and this was disseminated using mobile text messages to teachers and school administrators. It is also publicly accessible on E&SED’s website.

Future milestones will measure the number of schools and teachers who will benefit from feedback on teaching practices for improving weak areas in student and teacher assessment linked to the availability and use of data. This has been a key achievement of DFID’s TA supporting E&SED as prior to DFID’s support there were no such assessment systems.

Summary of responses to issues raised in previous annual reviews

Recommendation 2015/16 Annual Review	Response
E&SED should increase the pace of teacher transfers from schools with surplus teachers to those without enough. They should set a suitably stretching target for the proportion of schools with the optimal student-teacher ratio for next year.	The pace of teacher transfers could not be increased as envisaged due to the national census. The target for OSTR was increased from 55% to 65%.
E&SED to target professional development on weaknesses identified by the annual teacher and student assessments and monitor whether or not the performance of teachers is improving in these areas.	This is being done and both teacher content knowledge and teacher competency surveys for two years have been taken as baselines. This year larger sample sizes were taken and the methodology was also revised.
E&SED should use the Online Action Management System (OAMS) connected to the IMU data to hold teachers to account for their attendance, aiming for a 90% minimum attendance rate next year.	The OAMS was used to track teacher attendance and 87% results were achieved - reasons are cited above for why the target of 90% was revised downwards.

Recommendations

1. Lessons learned from the SQMI pilot should be used to inform future scale-up.
2. The target for teacher attendance rate can be raised to a minimum of 90%.
3. An assessment strategy should be developed by ASI to streamline the current assessment policy and practices for grades 2, 5 and 8.
4. The TA and DFID teams should increase efforts to influence E&SED and GoKP for the formal approval and implementation of the new terms and conditions for teachers.
5. Teacher assessments (content knowledge and competency surveys) should be conducted earlier to feed into professional development activities which then need to be aligned with budget planning time.

Output Title	More and better school buildings and facilities
Output number per LF		2	Output Score	B: Moderately did not meet expectation
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 # of schools upgraded and construction work started for new schools (girls 70%: boys 30%)	Girls: 31 (28 primary to middle schools+3 middle to HSS) / Boys: 23 (20+3)	A+: Moderately exceeded expectation / Girls: 34 (29+5) / Boys: 28 (24+4)
2.2 % of schools provided missing facilities	60%	B: Moderately did not meet expectation / 62% or 16,151 schools provided with all missing facilities, however the quality of 38% was below expectation
2.3 # of primary and HSS classrooms rehabilitated through SCRP	a) Primary total: 489 / (girls 201; boys 288) / b) HSS total: 505 / (girls 138; boys 367)	B: Moderately did not meet expectation / a) Primary total: 482 / (girls 162; boys 320) / b) HSS total: 372 / (girls 60; boys 312)
2.4 # of new classrooms built in primary and HSS through SCRP	a) Primary total: 155 / (girls 72; boys 83) / b) HSS total: 212 / (girls 72; boys 140)	C: Substantially did not meet expectation / a) Primary total: 98 / (girls 49; boys 49) / b) HSS total: 114 / (girls 31; boys 83)

Key Points
This output works on the construction of additional classrooms; the rehabilitation of existing schools and classrooms; and the provision of missing facilities which are required for the basic operation of a school i.e. water supply, toilets, electricity, and boundary walls. Indicators 2.1 and 2.2 are implemented indirectly through GoKP, while 2.3 and 2.4 are contracted directly by DFID through Humqadam.

2.1: Number of schools upgraded and construction work started for new schools (girls 70%: boys 30%)
One of the milestones for this indicator was met and the other was exceeded. The indicator tracks the number of schools E&SED is constructing or upgrading under its Annual Development Plan (ADP). Milestones for upgrading schools were narrowly exceeded, and for the construction of new schools, the milestone was exceeded as work was completed, not just started, on the required number of schools.

The 70:30 (girls to boys) ratio was not met for the current year, though it was met in aggregate for the last three years. Overall the government’s allocation and spend on school construction was promising: last year £48 million was allocated, but over the year, this rose to a final spend of £66.5 million.

2.2: Percentage of schools provided missing facilities
Indicator 2.2 measures the percentage of schools that are provided with water supply, toilets, electricity, and boundary walls. E&SED is implementing this from its non-salary budget and is supported by ASI. Although the number of facilities provided met the milestone (62% against a milestone of 60%), this indicator scores a B as quality in 38% was found to be below expectation. Conditional grants are disbursed from E&SED to PTCs according to approved school implementation plans, who then procure materials and services. ASI has helped E&SED develop a costed three year plan (£123 million) for the provision of all missing facilities. To address gender disparity, all missing facilities for girls’ schools will be providedin 2017-18. The 70:30 ratio was not met this year; this has less significance in future years given the new target to provide all missing facilities over three years.

Associates in Development were contracted as third party monitors until October 2016 to assess the quality of works. Their final report, covering 6058 schools, found 52% facilities had design deviations and 38% had poor quality workmanship. It found corrective action was required in a significant number of schools, though E&SED contest this.

2.3: Number of primary and HSS classrooms rehabilitated through SCRP and 2.4: Number of new classrooms built in primary and HSS through SCRP

The £163 million School Construction & Rehabilitation Programme (SCRP) operates in both KP and Punjab. The KP component is £70.76 million and is co-funded by the Australian Government which contributes around £18.1 million. SCRP, operating under the brand name Humqadam, is implemented by IMC Worldwide (IMC). Humqadam provide new and rehabilitate existing classrooms, toilets and other facilities. They also engage with and train members of the local community of each school, aiming to increase their sense of ownership of the infrastructure.

Following challenges outlined last year, DFID and IMC renegotiated the contract for this work, resulting in a £9 million reduction to the budget for work in KP. DFID has third party validation in place to monitor quality and pace of construction: this has proved to be a very useful tool in highlighting and remedying ongoing challenges with quality and pace.

Challenges with GoKP characterised part of the year, with a halt on construction in all schools ordered for several months by GoKP due to some differences in the dimensions of classrooms being constructed by Humqadam and GoKP guidelines. This affected their ability to complete the target number of classrooms. After a series of meetings, DFID-GoKP-Humqadam coordination and communication have been greatly improved since May 2017 and progress is now back on-track.

Indicator 2.3 reports the number of completed rehabilitated classrooms, mostly in Higher Secondary Schools (HSS), where DFID has committed to carry out rehabilitation and construction in 202 HSS across KP. Humqadam missed the milestone, completing 86% of the required number. Progress has improved considerably over previous years, but will require further improvement to meet final targets. Given the better relationship with GoKP, the external circumstances are now in place for this to be possible.

Indicator 2.4 reports the number of new classrooms constructed. The annual milestone for completions was only 58% met. The shortfall can be attributed in large part to the challenges described above, as well as uncertainty on the number of primary school classrooms that could be constructed within the overall contract with DFID, given the renegotiation that took place over the year. It is likely that the budget for primary school construction will be fully utilised over the next 12 months to reach the final target of 375 classrooms. Any savings on the HSS are to be reallocated to more new girls’ primary school classrooms.

DFID developed a VFM framework in July 2017 to monitor costs and other metrics to ensure VFM against the original business case and plans to carry out a comprehensive review of this component’s performance by February 2018.

Summary of responses to issues raised in previous annual reviews

Recommendation 2015/16 Annual Review	Response
DFID should continue close management of Humqadam, including producing new milestones and a realistic and detailed work plan for the remainder of the programme.	DFID has further scaled up management of SCRP since last year, adding an infrastructure adviser to the team. TPV is in place and a new overall work plan is in place for the revised scope of work but Humqadam must now submit a detailed work plan.
Humqadam should confirm the girls to boys ratio of primary schools for future phases of construction. If this is below 70:30, Humqadam should provide options to meet this ratio so that enough girls’ facilities are provided.	With the revised budget, limited scope exists for building additional primary classrooms to meet this target. As such, Humqadam have committed to using all savings from the programme to build more girls’ primary school classrooms.
The definition of output indicator 2.1 needs revision. Currently it only captures the release of funds to PTC accounts for building missing facilities (toilets, boundary walls, electricity, water and additional classrooms) and does not measure the actual construction of facilities contracted by the PTCs – this should be measured next year.	Following the recommendation, the results reported against this indicator are completion of missing facilities and not disbursement of funds.

Recommendations
1. Output indicator 2.1 should be revised to measure the completion of schools, and should set more stretching targets.
2. The 70:30 ratio (girls’ to boys’ schools) in indicator 2.2 will not be met because E&SED will now address missing facilities in all schools. It should be replaced by % of girls’ schools provided with missing facilities.
3. The Third Party Validation (TPV) should be reappointed to assess the quality of construction by Parent Teacher Councils (PTCs); and the use of non-technical PTCs to deliver missing facilities should be reviewed.
4. DFID should consider expanding the indicators under this output to capture infrastructure other than classrooms (toilets, exam halls, laboratories etc.)

Output Title	More (equitable) access to education
Output number per LF		3	Output Score	A: Met expectation
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 % of stipends disbursed to girls in Grades 6-10	95%	A: Met expectation / 95.8%
3.2 Number of vouchers distributed and % redeemed	Distribution: 30,000 / Redemption: 55%	A++: Substantially exceeded expectation / Distribution: 30,310 / Redemption: 81%
3.3 # of Girls Community Schools established	300 Girls Community Schools established	A: Met expectation / 300 Girls’ Community School established

Key Points
This output has achieved its targets. According to the recent out of school children census, there are approximately 1.5 million out of school children in KP, two-thirds of whom are girls. The provincial government is responsible for providing free and compulsory education to all children between 5 and 16. This output is focused on increasing access to schools through the establishment of Girls’ Community Schools and the provision of conditional cash transfers for children to continue their education. An Equity Strategy was developed to identify who is excluded from accessing and obtaining a quality education in KP, and why. This included costed options to address the barriers identified in the first stage.

3.1: % of stipends disbursed to girls in Grades 6-10
The milestone of 95% for this year was met. The stipends aim to improve girls’ enrolment and access to school by providing grants to cover the costs of transport, uniform and stationery. An annual grant of PKR 2,400 (£17) is provided to girls in grades 6-10 to help them attend middle and high schools. In 2016/17, a total of PKR 1,048.16 million (£7.7 million) was released for stipends, out of which 95.8% was disbursed. The timing of disbursement remains a challenge; in previous years, this was not complete until after the end of the academic year for which they were intended. The disbursement speed has improved, and all stipends were disbursed before June this year. Nevertheless, further improvements are needed so that girls receive their stipend before the beginning of the academic year (March) and before the start of the second term (September) to make sure the stipends are providing maximum VFM. The Finance Department has agreed to incorporate this programme into the recurrent education budget, which will help to reduce such delays and make the initiative sustainable.

From next year, E&SED has merged the main stipend programme with the separate programme in low-NER districts as the latter was not having an impact on enrolment or retention. E&SED has also increased the annual stipend amount to PKR 6,000 (£43) for girls in grades 9 and 10 in the areas where dropout rate and cost of education are higher.

3.2: Number of vouchers distributed and % redeemed
The milestone for distribution was met and the milestone for redemption was significantly exceeded. This intervention, implemented through the Elementary Education Foundation (EEF), enrols out of school children in low-fee private schools to get a decent education. EEF is a semi-autonomous institution of the GoKP which focuses on developing public-private partnerships to provide access to schools for remote, marginalised and out of school children. EEF’s voucher scheme started as a pilot in Peshawar in 2014/15, when 800 vouchers were distributed, of which 56% were redeemed. The scheme significantly scaled up in FY 2015/16 to 30,000 vouchers distributed and 51% were redeemed.

This year EEF engaged a private firm to undertake beneficiary identification and distribute vouchers. However, EEF later terminated the contract as the selected firm underperformed. To avoid further delays, EEF took on direct implementation. Assisted by continuous capacity building and support from ASI to mobilise EEF’s field staff, 81% of vouchers were redeemed this year, a marked overachievement against the milestone of 55%.

3.3: # of Girls’ Community Schools established
The milestone for this indicator was met. It tracks how many new girls’ schools have been built or expanded – both government schools and GCS. EEF establishes GCS to promote access to education for girls and their brothers from areas that do not have a government school within 1.5km of their homes. The model is a one-room school donated by the community with a teacher from within the community. GoKP provides teacher salaries, free textbooks and teacher resources. At the end of June 2017 there were 1,736 GCS throughout the province providing education to 86,176 children (56,708 girls and 29,468 boys). ASI has developed a Management Information System (MIS) to manage site selection; feasibility for establishing a school; enrolment; attendance; and information on teachers that includes their names, contact details, length of service, date they began their current posting and training they have received.
Summary of responses to issues raised in previous annual reviews
Recommendation 2015/16 Annual Review	Response
E&SED should consider options to track the disbursement of the stipends to girls rather than measure funds disbursed, and begin doing this. It should be tracked within the academic year to monitor when girls receive the stipend	ASI developed a tracking dashboard for E&SED to identify the specific reasons for delays in disbursement. The dashboard improved the Provincial Coordinators’ ability to drive disbursement of the stipends.
In the short term, E&SED should improve the management of the stipends programme by implementing the new operational manual and conducting at least monthly monitoring field visits with ASI. DFID should commission TPV of the stipends programme to check if the controls have improved after implementing the operational manual, and verify how many girls report having received the stipend.	ASI lobbied E&SED to increase the provincial coordinator office’s staffing for monitoring visits. This resulted in an increase in monitoring visits from 14 last year to 128 in FY 2016/17. / DFID has received the draft TPV report which will be finalised by end September.
E&SED should decide whether or not to continue the stipends programme, and implement whichever intervention(s) would achieve maximum impact on enrolment for girls.	E&SED has merged the two stipend programmes and from this year there will be a single stipend programme in the province.
E&SED should consider how to improve the capacity of the EEF rapidly so that a successful scale-up of the voucher programme can be achieved, with more stretching distribution and redemption rates. E&SED should help the EEF address their underspend and their lack of staff.	The capacity of EEF has improved slightly and spot checks conducted by ASI found 92% accuracy in the identification of OOSC for vouchers.
ASI should help the EEF think about improvements to the GCS model, including improving the teaching and learning and facilitating the girls’ transition to middle and secondary schooling.	ASI supported EEF to develop guidelines for staff to conduct feasibility and establish GCS. The guidelines resulted in improving staff’s capacity. Ongoing support is required for EEF to continue improving the GCS model.

Recommendations
1. All stipends should be disbursed within the academic year, in particular in grade 10 after which girls complete school.
2. E&SED should consider a significant scale-up of the voucher programme with more stretching distribution and redemption rates. The capacity of EEF improved last year largely due to the new senior management team after restructuring supported by ASI and this should be further developed.
3. ASI should help EEF to continue to improve the GCS model, including the teaching and learning and facilitating the girls’ transition to middle and secondary schooling.
4. The recommendations and options in the Equity Strategy should be implemented swiftly and monitored closely to assess their impact.
Output Title	Good governance and management in the education sector at all levels (Provincial, District and School)
Output number per LF		4	Output Score	A: Met expectation
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 % of actions taken against absent teachers	OAMS launched in two districts / OAMS scaled up in all districts / Baseline to be established by June 2017	A: Met expectation / OAMS launched in two districts; Mardan and Peshawar / OAMS scaled up in all 25 districts and a baseline established
4.2 % of schools visited by district education officials every month for school supervision	30%	A+: Moderately exceeded expectation / 36%
4.3 # of districts developing and implementing costed district education plans (DEPs)	25 DEPs successfully implemented	B: Moderately did not meet expectation / 20 DEPs successfully implemented
4.4 Budget execution rate (non-salary recurrent and development)	Non-salary: 95% / Development: 90%	A+: Moderately exceeded expectation / Non-salary 97.7% / Development 99%

Key Points
This output aims to capture improvements in governance structures and management practices at provincial, districts and school levels.

4.1: % of actions taken against absent teachers
The milestone for this indicator was met. The Online Action Management System (OAMS) is an automated system which uses IMU data to issue instructions to district education staff to take corrective measures. OAMS was piloted in two districts in September 2016 and led to a decrease in unauthorised teacher absences from 20% to 7% in Mardan and from 18% to 12% in Peshawar in three months. Following this success, the department launched OAMS in all 25 districts of KP in December 2016. This has resulted in a 2% increase in teacher attendance from 85% to 87%. OAMS records and tracks disciplinary actions initiated against absent teachers. Out of a total of 9290 actions initiated by 30 May 2017, 2474 were completed, setting a baseline for subsequent years of 26.63%.

4.2: % of schools visited by district education officials every month for school supervision
The milestone for this indicator was met. Although IMU monitors carry out school inspections every month, it is the mandate of education district officers (EDOs) and other district based staff of the education department to visit schools, take corrective actions, and flag school level issues and needs to district administration. This was a neglected area but over the past three years, there has been a small improvement. The percentage of schools visited by district education staff every month has increased from 26% in 2014/15 to 34% this year.

4.3: # of districts developing and implementing costed District Education Plans (DEPs)
The milestone for this indicator was missed. Timely completion and roll-out of all 25 district education plans (DEPs) was a significant challenge. The education department revised the DEPs and introduced new performance indicators that focus more on outputs and are in line with the Education Sector Plan (ESP). As of June 2017, 20 out of 25 districts had achieved the target of meeting 80% of their milestones. The department plans to further revise DEPs for the next year in light of the data from the OOSC census which is now available.

4.4: Budget execution rate (non-salary recurrent and development)
The milestone for this indicator was exceeded. This indicator focuses on execution of non-salary recurrent and development budgets – important measures of overall performance of E&SED. The development budget allocation was increased from PKR 15.9 billion to PKR 18.2 billion. In the financial year 2016/17, the execution rate against the original allocation for the development budget is 114% and 99% against the revised budget. The Finance Department imposed an austerity cut on the non-salary budget and reduced it from PKR 13.24 billion to PKR 9.44 billion. The execution rate for the non-salary budget is 69.6% against the original allocation and 97.7% against the revised budget.

Summary of responses to issues raised in previous annual reviews

Recommendation 2015/16 Annual Review	Response
Supervisory visits to schools by district education officials and their follow-up are critical for improving school performance. E&SED should improve the frequency and rigour of the supervisory visits in the context of planned reforms to the school monitoring system.	There has been an improvement in terms of frequency of supervisory visits but the target is still not very ambitious.
E&SED should focus on measuring districts’ performance against the teaching and learning targets set in the district education plans. ASI should work with E&SED to further improve district officials’ skills to achieve these more challenging targets.	E&SED revised this year’s DEPs which now have more output level indicators and are in line with the ESP. ASI assisted E&SED to revise the DEPs and conducted training workshops for district staff.

Recommendations
1. For output indicator 4.1 the yearly target should be brought in line with the indicator and should try to capture the effectiveness of the OAMS.
2. The target for school supervisory visits by district education staff should increase the coverage of schools and capture the outcome.
3. Delays in procurement processes have been affecting the timely delivery of some activities. ASI should provide TA for improving E&SED’s procurement systems and processes to help build the department’s procurement capacity.
4. Since all districts in KP have developed District Education Plan (DEPs) in line with the ESP, E&SED can focus on monitoring progress of their implementation. DFID should consider including some DEP targets under this output.
5. With more development funds going to districts under the local government system, there is a need to link DEPs with districts’ development budgets and build the capacity of district education staff to design and implement education related development schemes under the DEPs

Output Title	Effective and efficient technical assistance (TA) provides a high quality service to the GoKP and timely quality information to DFID
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
5.1 Quality and timeliness of programme delivery	Key Supplier Management Score of 4 (Delivery criteria being efficiently and effectively met in line with contractual and customer expectations.)	B: Moderately did not meet expectation / Performance assessed as equivalent to a Key Supplier Management Score of 3
5.2 System/institutional strengthening, capacity building and innovation	4 (as above)	A: Met expectation / Performance assessed as equivalent to a Key Supplier Management Score of 4

Key Points
This output was added to the log frame in 2016 to specifically assess the performance of Adam Smith International (ASI), given their importance to the success of KESP, in addition to the output milestones and the performance of partnerships section which indirectly measure the TA’s performance.

Under DFID’s former approach to Key Supplier Management (KSM), the DFID programme team held six-monthly meetings with ASI to assess their progress against six indicators. These included quality and pace of delivery, financial management, client relationship management, and continuous improvement and innovation. However, the KSM process has been under review at the global level, so the most recent KSM took place in July 2016, prior to the 12 months being assessed in this annual review. As such, the assessment for this output is being conducted separately, based on the programme team’s experience in the year and on the feedback on and evidence presented by ASI for this annual review.

5.1: Quality and timeliness of programme delivery
This milestone was not met. In the annual review meetings with government, stakeholders generally expressed satisfaction with ASI’s performance, including on the outputs provided but of the 16 KPIs, two important reports, the Inception Report and the Equity Strategy were delayed as they required further work.

On financial management, quarterly forecasts had variances of up to 40% in the first six months of the new contract, well above targets. Following continuous feedback from DFID and improvements in ASI’s processes, this has come down over the second half of the year to below the target of 5%.

  1. System/institutional strengthening, capacity building and innovation
This milestone was met. This year has been marked by notable improvements in E&SED’s capacity as described earlier in this review, for example allowing for full budget execution in 2016/17. There has been a shift to the GoKP playing more of a leading role, in line with ASI’s approach of moving from substituting, to supporting, to strengthening and finally to self-sustaining. For example the IMU demonstrated impressive capacity and near full autonomy. In other areas, ASI retains a more active role in capacity building. For example, in reviewing the girls’ stipends programme, ASI provided a series of recommendations to improve the efficiency of stipends and assisted E&SED’s monitoring, leading to a tenfold increase in monitoring visits.

ASI has clearly taken on board feedback from DFID in previous reviews on the level of innovation in their approaches to TA. They have made good progress on the 2016 Innovation Paper activities, though delivery is still more of a driving force than innovation. Some examples of innovative activities include the School Quality Management Initiative, which is currently in the pilot phase and will equip Assistant Sub-Divisional Education Officers (ASDEOs) with tablets to collect quality-level data on classroom observation, syllabus pacing, and student assessments.

Summary of responses to issues raised in previous annual reviews

Recommendation 2015/16 Annual Review	Response
DFID and ASI to decide how system strengthening, continuous improvement and innovation can be measured more objectively, taking into account E&SED’s desire for sustainability. All parties should agree on what constitutes an innovation, which may include completely new ideas, but also ideas that are new in KP but may been implemented in other parts of the country or in other similar contexts	There were a number of discussions on system strengthening and innovation with ASI and E&SED throughout the year which embedded better understanding of DFID’s expectations.
ASI should significantly improve the capturing of lessons learnt on KESP to provide a strong evidence base for any changes in the approach to existing programme interventions as well as the design of any future programme interventions.	ASI conducted a lesson learning exercise for the education voucher scheme. Lessons learned were incorporated resulting in increasing the voucher redemption rate from 55% to 81%.
ASI should share lessons learnt across their other Pakistan programmes and with Humqadam (school infrastructure partner) to maximise the potential for systematic reform in KP, in particular, with regard to the conditional grants programme and the use of PTCs (see output 2.1). ASI and Humqadam should discuss in particular barriers to increasing girls’ schooling facilities through the infrastructure component (output 2.2).	ASI can still do more to share lessons across their programmes inside and outside Pakistan, as well as from other DFID programmes. / ASI and Humqadam have had a few discussions over the course of the year, but this needs to be more systematic. A discussion on the use of PTCs has been scheduled but has not yet taken place.

Recommendations
The DFID team should reassess this output once DFID’s new process for supplier management is finalised. If it is retained, the team should set clear and measurable expectations, and consider whether to add an indicator covering IMC’s performance.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Sector Budget Support to E&SED (64% of KESP budget): In FY 2016/17 DFID disbursed £20 million in sector budget support (SBS), which formed 2.95% of E&SED’s budget, exclusive of the Annual Development Plan. DFID’s funds to E&SED are not earmarked to specific expenditure lines but rather specified in the grant agreement as contributing to the priority areas agreed in the JRF. Recurrent salaries, mostly teachers’ pay and benefits, account for 74%[10] of budget. The remaining 26% of expenditure was via the non-salary (9%) and development (17%) budgets. Excellent performance was exhibited in budget execution rates, with 98% and 99% for non-salary recurrent and development budget respectively, against the revised budget.
[10] Total budget expenditure was PKR 106.1bn, representing 98% of the revised budget and a 1.8% increase from FY15/16 (a real decrease).
School construction and rehabilitation through Humqadam (21% of KESP budget): Previous annual reviews have documented the reduction in output and outcome expectations[11]: unit cost increases have reduced the number of classrooms that can be constructed/rehabilitated with the available funds. Underperformance in 2015, captured in last year’s annual review, also resulted in a contract renegotiation between DFID and IMC that reduced the funds available in KP from £80 million to £70.76 million. Nevertheless, pace this year and the ratio of spend on construction to other expenses improved markedly, signalling a shift from a period dominated by problems, planning and design to a period of implementation. This is most clearly evidenced by a 580% increase in the completion of works year on year: 2016 saw the completion of 19 new and 127 rehabilitated classrooms; 2017 saw 212 new and 754 rehabilitated classrooms.
[11] Unsuitability of building modalities, material and construction cost inflation and GBP depreciation have all contributed to classroom unit cost estimates almost trebling against original business case.

Technical Assistance to E&SED (15% of budget): In FY16/17, £6 million was spent on resourcing technical expertise to support governmental reform. The majority of this cost was due to salaries, with the expenses ratio reduced slightly from the previous year. Overall, TA performance was judged to meet expectation, with timeliness of outputs usually satisfactory, and quality generally meeting expectations.

VFM performance compared to the original VFM proposition in the business case

The KESP business case was written in 2011. As has been noted in previous annual reviews, the original way in which VFM was calculated does not hold any more[12]. The original assessment assumed KESP would support a larger number of students than it does, and that it would increase wages for people receiving an education more than it has. However, some other areas were underestimated.[13] To provide clarity on the VFM performance of the programme, a new cost-benefit analysis (CBA) should be undertaken.
[12] KESP’s first annual review noted the difference between reality and the assumptions embedded in the earlier Education Sector Plan, which overestimated state capacity to increase enrolment and was un-costed at the time of writing the business case. It became clear that adequate funding, or indeed planning, was not in place to secure the expected results.
[13] This includes using a discount rate (a calculation that places less value on benefits that are further in the future) that is higher than DFID would normally use (12% rather than 10%) and, due to the business case extension, some students will benefit from up to eight years of schooling rather than three.

Separately, over-optimism in terms of Humqadam’s construction costs outlined in the business case has been documented in previous reviews. The VFM proposition in absolute terms will not be met, although relative VFM is confirmed by comparison with GoKP-led infrastructure works. Hard data on final GoKP construction costs are difficult to source but anecdotal evidence from the Communication and Works Department (C&W) suggests 2017 classroom construction costs of around PKR 3,000 per square foot, some 20% higher than Humqadam’s confirmed final costs of around PKR 2,500 per square foot in primary schools. In the rehabilitation of the Higher Secondary Schools (HSS), C&W is spending PKR 35-95 million per school, in comparison to PKR 25-35 million through Humqadam. DFID should continue to benchmark against GoKP and begin benchmarking against other development partner construction.
ASI has generally performed well, with their outputs largely well-executed and capacity building efforts appreciated by GoKP. However, some KPIs were missed due to suboptimal products indicating that greater VFM can be attained, reducing the input hours required to attain sufficient quality outputs.

Assessment of whether the programme continues to represent value for money
The programme’s VFM performance is captured in a VFM Framework and in regular VFM reporting. This year’s SBS means that DFID directly supported 126,200 students through a year’s schooling in the public system. This represents a unit cost[14] of PKR 20,600 (£158) per annum, similar to unit costs in Punjab. DFID’s TA also contributed[15] to 24,900 students using vouchers to enrol in EEF-run schools.
[14] This clearly varies by total expenditure, if GoKP managed a 100% budget expenditure rate (desirable) then unit costs would have increased.
[15] Supporting the design and implementation of the voucher system.

There are now 4.27 million students enrolled in KP public schools taught by 132,250 teachers (increases of 343,000 and 13,000 respectively since 2012/13). These teachers spend more time in the classroom (teacher attendance rates increased to 87%, up 2%), their content knowledge[16] is generally improving, and their overall performance is improving. Student attendance increased (by 1%) to 77% overall[17]. However, student outcomes[18] have actually deteriorated in English and Maths and flat lined in Urdu (a review into this is being undertaken). This may be as a result of a time lag in improving outcomes due to a change in the methodology of assessments away from rote-based testing. It’s clear that there is ample room for improvement in both enrolment, student and teacher attendance, and we should expect better outcome gains as these factors improve. However, the slow progression (and potential regression in outcomes) of the major effectiveness indicators should prompt the programme to evaluate whether we are witnessing a lag between inputs and expected outcomes, or whether our theory of change contains assumptions that are not borne out in reality. On school construction, each new classroom increases aggregate capacity by 40 students per year, and each rehabilitated classroom directly improves the learning environment for 40 students per year[19]. Other facilities such as toilets, examination halls and laboratories improve the learning environment for all children in the school and are likely to improve retention. More in-depth analysis is required, but initial surveys[20] suggest that enrolment increases with classroom provision.
[16] Average test scores improved for Maths (up 5.5%), Urdu (up 12%) and Science (up 9%) but decreased for English (down 4%)
[17] Girls attendance rate is lower at 75%, but increased by 2% from last year.
[18] As measured by testing sample of 12,289 students.
[19] Assuming a student to teacher ratio of 40:1.
[20] VFM of Conditional Grants study; IMU data collected on sites in which IMC work has completed.

Recommendations
By December 2017, DFID should conduct a revised cost-benefit analysis, providing more accurate net present value estimates and a clearer assessment of VFM.

Quality of financial management
KESP involves payments to the GoKP, ASI and IMC; DFID measures the financial management of all three partners, but has less control over the GoKP’s financial management.

Public financial management by the GoKP
DFID has regularly raised the importance of countering fraud and corruption with E&SED, ASI and IMC. They have been responsive and the GoKP is open to DFID’s and ASI’s support in improving financial controls in all areas. DFID’s emphasis on prevention of fraud and KESP’s focus on strengthening internal control mechanisms have resulted in a fully functional and effective Internal Audit Cell. The Cell has successfully implemented its Annual Internal Audit Plans for two successive years i.e. FY 2015-16 and 2016/17, which, among other things, presented technical and strategic proposals to strengthen internal controls and mitigate identified risks. Addressing internal audit observations not only helped the Department improve compliance with GoKP’s financial regulations, but have also helped improve its procurement system.
DFID’s grant agreement requires Annual Audited Statements from the Auditor General of Pakistan confirming that DFID’s grant has been used for the intended purpose. Since the start of KESP there have been delays in receiving audits and there have not been comprehensive audits of all of DFID’s SBS contributions, despite a request to the Economic Affairs Division and the Auditor General’s office for these. Audit reports from the Auditor General covering the period FY 2014/15 pertain to specific spending units and did not find any misappropriation.
To compensate for previous gaps in audits, DFID commissioned Ernst and Young (EY) to conduct a third party audit of DFID’s SBS funds disbursed to the GoKP. EY were asked to establish whether DFID’s funds had been used in accordance with the conditions in the grant agreement and establish whether there was any evidence of losses of any kind. The audit reports for FY 2012/13 and FY 2013/14 were finalised in April 2016. No instances of misuse of funds or fraud were found. EY found some weaknesses in the financial management and control mechanisms of the various spending units it examined and made recommendations for E&SED. The audit reports for FY 2014/15 and FY 2015/16 will be available by October 2017 and will assess the extent to which previous recommendations have been addressed.
Financial management of TA provided by ASI
ASI spent 18.7% of the programme budget in the first year of the new contract. ASI have improved their financial management this year; the monthly rolling forecast variance has remained at an average of 3.06% during the first year of the new contract which started in August 2017. There were a few months during the start of phase 2 of KESP TA when ASI struggled with the forecast; variance from forecasts went up to 40% in January due to challenges associated with recruitment and consortium partners. ASI’s planning, however, improved after introducing a new forecasting and financial management tool. The forecast variance has improved significantly in the last quarter of the year. DFID will work with ASI to align the forecast with the work plan to improve planning and financial management. ASI’s quality of financial management is captured in the output indicator 5.1 score.

Financial management of school infrastructure component, provided by Humqadam
In 2016/17, DFID released £11.01 million to IMC to implement the school construction component. Of this total budget, £3.59 million was paid for fees and expenses of IMC staff and the district teams and the remaining £7.41 million was spent on construction works. The Australian government also contributed £0.86 million to the overall capital works budget for the year. Payments to IMC are made monthly in line with work plans and forecasts agreed at the beginning of the financial year. This year IMC has shown significant improvement in financial forecasting. As of 30 June 2017, IMC achieved more than 95% of their forecast for fees and expenses. For capital works, IMC’s monthly spending was mostly in line with their forecast for the first three quarters, although there was underspend in the last quarter. This variance is primarily because of delays by the GoKP in approving construction designs for the next round of construction.
Date of last narrative financial report	FY 2014/15 for SBS, July 2017 for TA
Date of last audited annual statement	FY 2014/15 for SBS. FY 2015/16 for TA

E: RISK

Overall risk rating: Major
DFID and ASI have quarterly discussions focusing on DFID’s and ASI’s risk registers. Mitigation strategies are identified and agreed in these meetings and the risk register is updated. The KSM process also measured the supplier’s identification and control of risk, and this has helped ASI improve their timeliness in communicating risks to DFID, allowing for better mitigation. DFID and Humqadam have quarterly discussions of their risk register through the quarterly progress report process. Last year KESP was rated as ‘major’ risk, which remains the same this year. 40% of the programme’s outputs are rated as having major risk (the others moderate) and the risk areas detailed below still pose a major, but not severe risk.

Overview of programme risk
The overall risk environment remains similar to last year, but with some improvements:
Security: Although there have been no major security incidents, security continues to be a major risk both to DFID’s ability to monitor the programme and to the ability of children to attend school, thus affecting the overall education outcomes. E&SED has begun focusing on building boundary walls in schools in all 25 districts through conditional grants. Construction of boundary walls and installation of security measures have improved school security. However this has not been completed in all 25 districts and schools; and thus poses a security threat. Security presents particular challenges to DFID’s ability to monitor directly – several field visits were cancelled at short notice over the year due to not receiving permission to travel from Government of Pakistan.
Conflict and humanitarian crisis: There was no major natural disaster reported this year. However the province is vulnerable to natural disasters including floods and earthquakes. The ongoing security operation in FATA bordering with Peshawar has a direct impact on the programme. Natural disasters and conflict from surrounding areas affect delivery and remain a major risk to KESP. ASI has mapped the existing emergency response processes in the province.
Fiduciary risk: Although there was no fraud and corruption case reported last year, fiduciary risk remains major in KP due to the weak government capacity and controls. DFID commissioned third party audits to ensure that there has not been systemic fraud or corruption in the activities under KESP. However, fraud and corruption risks remain until controls are improved and universally applied. Under Humqadam, we have closer scrutiny of the fiduciary risks associated with the construction sector, and IMC have measures in place throughout procurement and construction to mitigate risks. DFID has discussed the highest risk areas of fraud and corruption with E&SED at Quarterly Steering Committees and regularly follows up on audits to encourage E&SED to address recommendations. The TA team is helping E&SED improve financial controls through the audit cell embedded in the department.
Delivery Risk: There is a risk that Humqadam’s delivery is slowed down by government processes or by underperformance of their subcontractors who carry out the construction work. This can lead to delays and additional costs to DFID. To mitigate this risk, over the past year, Humqadam has reduced the number of schools included in individual contracts awarded, as well as reviewing their pre-qualification process. They have also enhanced their field monitoring and regularly track the performance by using a sophisticated MIS system, to which DFID and government have access. IMC links past performance of their subcontractors to the assessment of their potential for future contracts, rewarding good performance and excluding contractors that have underperformed.

Outstanding actions from risk assessment
Due to the current political situation in Pakistan, DFID should continue to monitor the risk associated with elections. There could be early elections, which might result in a change of government and leadership of the civil service in KP. DFID currently assesses that education is likely to remain a priority in KP and a fundamental change of approach is unlikely. ASI is seeking to institutionalise the reforms, aiming to lead to their sustainability. DFID’s ‘Transforming Education in Pakistan’ programme works to influence the four provincial and federal Pakistani governments and political parties to maintain a focus on education.

Recommendation
1. DFID should continue to support E&SED to undertake proactive mitigation of the security threat to schools.
2. DFID should continue to scrutinise all audits carefully and push for rapid follow-up where any problems are identified. DFID should proactively publish results and success stories in UK and Pakistani media.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
In terms of performance against the log frame, progress is broadly on-track. On indicator 1, the actual enrolment rate is 48% which is slightly lower than the expected 50% enrolment rate. For output indicator 3.1, the girls’ stipend in grades 6-10 was achieved but there have been delays in the disbursement of money to the beneficiaries. For improvement on this, a more thorough due diligence of beneficiary data is required so that the money can be disbursed in time. On indicator 2.1 the new schools construction asked for a 70:30 ratio of girls’ schools to boys’ schools; DFID is still in discussions with the government to address the supply issue and this may need a change in log frame target before the next annual review.

Performance of partnerships
The dominant partnership in this programme is between DFID and GoKP, of which most importantly E&SED. DFID assesses this partnership to be strong and mature, with mutual understanding and common objectives underpinning work at the official level, up to the Secretary and the Minister. Continuity on the side of E&SED over the past year has helped in this, as previous years have seen changes, especially at the Secretary level, requiring relationships to be re-forged. ASI’s relationship with GoKP has improved substantially in the last year, partly attributable to the appointment of a new ASI government liaison person.

ASI’s performance is assessed in output 5, so the detail is not repeated here. Overall, their performance has improved over the year, but there continues to be room for improvement in the quality of reports and forecasting. During the year, Agha Khan Rural Support Programme (AKRSP) left their consortium. There are no signs to date of this negatively affecting delivery.

IMC Worldwide’s performance has improved over the period being assessed in this annual review. They have made significant gains to the pace of construction, as well as the management of the programme through their Management Information System and several human resource changes following the February 2017 contract amendment. The speed of decisions has improved, but bottlenecks continue to appear with considerable burden placed on the Team Leader and Infrastructure Director in particular. Work must continue to ensure costs are kept to the right levels and that quality is ensured.

Previous annual reviews have highlighted the need for greater collaboration between ASI’s Punjab Education Support Programme (PESP) II and KESP TA teams, as well as between ASI and IMC. These interactions should focus on lesson learning, improving coordination and increasing value for money by avoiding any duplication of efforts.

Asset monitoring and control
ASI and IMC manage and monitor assets through asset registers and physical tagging. Updates on asset management are part of ASI and IMC reporting to DFID, and the most recent updates were received and reviewed in July 2017 for ASI and in August 2017 for IMC. Assets were reported to be in place and in good condition. The annual review team looked at how assets are procured, the processes followed, and documentation of the procurement process, and spot checked the procurement process and documentation in place. The review team also randomly selected 15 different line items for physical spot checks to verify ASI’s and IMC’s assets, and all assets were found to be in place and appropriately tagged. Over the next year, DFID will conduct physical spot checks of assets on a quarterly basis.

G: CONDITIONALITY

Update on partnership principles
The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division at the federal level and text is shared every six months. The PPA was discussed most recently in December 2016 during our Bilateral Assistance Talks. The PPA sets out the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

DFID Pakistan’s assessment is that the government is demonstrating a credible commitment to the four principles. DFID can therefore continue to plan and deliver sizeable programming on-budget. Progress towards the SDGs and poverty reduction is proceeding, albeit slowly, given the challenges. Progress on human rights is mixed. On public financial management and anti-corruption the direction of travel is broadly neutral, with some improvements in the areas of transparency on budgets, progress on audit and procurement, more openness on corruption and an appetite to tackle this at the highest levels. Elite capture and its influence are often cited as a concern.
In line with this assessment, two thirds of KESP’s budget is allocated to SBS to the Government of Khyber Pakhtunkhwa, with the remaining third split between two international consultancy contracts. The portion spent through SBS is conditional on progress against the GoKP and DFID-agreed Joint Review Framework, and is underpinned by strong political commitment to continued education reform in KP.
H: MONITORING & EVALUATION

Evidence and evaluation
An evaluability study of the programme was commissioned in 2016 through DFID’s Specialist Evaluation and Quality Assurance Service to determine the feasibility of an evaluation. The study recommended a performance evaluation to examine KESP’s overall contribution to the outcomes; an annual process evaluation to better understand the quality of implementation and enable lesson learning; and specific topic-based studies. Following this, DFID procured an organisation to take this work forward, awarding a contract in May 2017 to Ecorys. The recently-completed inception report sets out the purpose, nature and scope of the evaluation; the technical approach and methodology; the dissemination and uptake strategy; and overall management of the evaluation. The implementation phase will start in September 2017 and will provide a rich resource of information to help improve programme performance and assessment.
A number of evidence assessments have been delivered by the TA team to date, including the Equity Strategy, assessment of CPD strategy, and conditional grants assessment, each of which influenced the government’s understanding of the issues and led to changes in policy or process. For example, recommendations from the Equity Strategy have been adopted by the government, as well as the recommended scale-up of budget to support achievement of the strategy’s objectives. DFID has observed that government counterparts respond positively to evidence generation and have made more requests for data and evidence than previously. This suggests the provincial government has a continued commitment to education, which is an important assumption in the programme theory of change.
Monitoring progress throughout the review period
The DFID programme team monitors performance of the programme through a number of mechanisms. Regular field visits to schools and district education staff enable the team to understand the situation on the ground including: the quality of teaching in classrooms; use of conditional grants to improve school facilities; district use of data and evidence, including IMU data; and the quality and pace of school construction and rehabilitation. It also allows the team to understand community engagement under the school construction and rehabilitation component and to monitor the wider coordination of agencies across the province, both of which are difficult to understand remotely.
Delivery is regularly assessed throughout the year, with the programme team meeting ASI and Humqadam regularly as part of routine programme management. In recent years ASI has improved its monitoring and evidence framework, which has improved technical meetings and led to a much stronger focus on evidence. This focus has more effectively identified barriers to progress and serves as the basis for a useful dialogue on required reforms. VFM metrics are now firmly established, with regular discussions taking place to ensure the programme continues to represent value for money. A number of management information systems (MIS) have now, or are imminently, being developed by the ASI TA team for GoKP. These systems ensure data is more accessible to programme stakeholders, including DFID. The Humqadam MIS is used by DFID to monitor physical progress at the provincial level as well as right down to the school level, with site inspection reports and photos of physical progress, as well as construction planning documents available for review.
The government monitors the performance of the programme through the Independent Monitoring Unit (IMU), based within E&SED. The IMU collects data from every school in the province on a monthly basis against a headline set of indicators. These data undergo quality assurance and validation, before presentation at the provincial level at monthly meetings with the Secretary E&SED. Steering Committee meetings chaired by the Deputy Commissioner are held at the district level on a monthly basis. These meetings are underpinned by IMU data and presented by the District Monitoring Officer (DMO). These provincial and district processes ensure areas of underperformance are identified and immediate action can be taken in response to issues.
This annual review process was undertaken by the Deputy Head of Basic Services Group in DFID Pakistan, and involved a core team, an Economist, and the Statistics Adviser, as well as field trips to Peshawar and Swabi and a number of meetings with government and implementing partners.