Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Burma Accelerated Reform Facility (ARF)
Programme Value: £15m		Review Date: 30 September 2017
Programme Code: 203601	Start Date: 16 August 2012	End Date: 31 December 2020

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A	A
Risk Rating	Low	Low	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

The reform process remains complex and unpredictable. The Accelerated Reform Facility (ARF) enables rapid responses in Burma’s highly fluid operating environment and ARF projects have continued to deliver results though some impacts will become apparent only in the medium term. Results will come both in areas directly covered by the projects and indirectly by supporting and influencing results in other areas. The approach, and therefore the ARF, remains valid. The ARF has also demonstrated success in piloting projects that has been and to be taken over by larger, sectorally focussed DFID Burma programmes where they complement and reinforce other interventions. Overall the ARF is proving to be valuable and necessary mechanism in enabling DFID to provide quick support to the reform process.

Summary of recommendations for the next year

DFID Burma should continue to draw on the ARF as a tool for supporting reformers.

DFID Burma should also keep the new approval processes for the project (instated in July 2016) under review and if possible should try to revert to the original approval process to ensure the ARF’s ability to respond rapidly is not adversely affected.

An overall logframe has to be updated when we receive a finalised results framework from the Proximity Design project by 30 September 2017. There should be a continued discussion with the evaluation and result adviser how to best capture the performance of the programme.

The ARF risk matrix need to be reviewed and updated to relect DFID’s new risk management framework.

In addition we have the following project-specific recommendations:

Technical Assistance for Public Private Partnerships – TA for PPPs

This project is coming to an end on 31 December 2017. We are not planning for an extension. Public Private Parnership technical assistance is still required to have and implement across the government’s ministries. This annual review suggests to support a wider level PPP technical assistance to Government of Myanmar for a meaningful implementation which can contribute the provision of effective public sector services.

Rangoon General Hospital Reinvigoration - RGHR

The project has received leadership support from the Health Minister U Myint Htwe, and State Counsellor Daw Aung San Suu Kyi, they are informed the progress of the project. The Masterplan of the Rangoon Genral Hospital have developed and presented to the Minister, who was excited by the work done. The ministerial team immediately identified ways in which the Ministry could work with the charity to make further improvements in the Hospital. There will be an ongoing need for funds and human capital. In anticipation of these needs, DFID should continue its support to implement the findings and action plans in the Master Plan through key pillars – continuing supporting the Masterplan operationalization, renewal of the physical fabric of the Hospital, providing medical education, and building capacity for a digital medical record system.

Myanmar Centre for Responsible Business – MCRB

As the MCRB has now moved under DFID Burma’s Business for Shared Prosperity (BSP), recommendations are not included in this annual review. They are captured in the BSP one instead.

English for Education College Trainers – EfECT

- DFID Burma should continue to support Education in Burma in a more systemic and sustainable way under a committed plan for education. Last year’s annual review recommendation was that there should be a second phase of English for Education College Trainers (EfECT) from July 2017, funded through DFID Burma’s planned new education programme. We are addressing that through the new education programme though it will be broader than EfECT and would not be a mere continuation of EfECT. In the new programme, DFID Burma should tie in the English support to wider areas of teacher education reform such as continuous professional development and curriculum reforms.
- There should be a medium to long term plan of teacher education in the form of a collective government and development partner plan, building on the work of EfECT in Educational Colleges, whose outreach could be felt in state schools and non-state sector as well.

Knowledge for Nation Building

- DFID should request from Proximity detail on its theory of change to clarify the flow of logic from activities to outputs to contribution to outcome and ultimate impact – by 18 September. The project logframe should be updated as soon as possible thereafter – by 30 September. If, by 31 October, DFID has not been satisfied with the proposed revisions to the results approach, then it should consider an early closure of the project by 31 December 2017.
- DFID should request more information from Proximity at an early stage in the planning of study tours to ensure maximum utility of the visits and appropriate fit with an (update) ToC.
- Proximity and DFID should finalise the Delivery Chain Mapping and revised budget plan as soon as possible, and complete an updated project risk matrix by the end of September.
- Each quarterly progress report needs to report on progress on results (as per a revised logframe) and must include information on how the work promotes gender equality and beneficiaries feedback
- DFID should quickly review the advance funding modality to Proximity’s sub-partner, Harvard. More detail is needed from Proximity prior to each advance payment. With reference to the Theory of Change, Proximity/Harvard need to explain the rationale for the work proposed. A costed work plan of activities should also be provided to DFID prior to funds being advanced to Harvard. DFID should review the proposed and provide comments or non-objection within a reasonable period agreed with Proximity (e.g. 10 working days).
- Within DFID, it is recommended that the SRO and programme Manager are in the same team, subject to a revision to ARF’s own update of its purpose and results framework. It should be considered whether this work would best fit in the Governance, Humanitarian and Peace team, rather than in Inclusive Growth and Livelihoods.

Joint DFID-AustralianAid Liasion Office

DFID’s co-located Nay Pyi Taw (NPT) office (with DFAT) needs to significantly enhance capacity and engagement with local engagement partners. As a result, it is recommended that DFID seeks to develop and open an independent office in NPT. This will not only improve visibility for DFID NPT, demonstrating the seriousness of our commitment to development in Burma (and recognition of NPT as a key centre for government and development partners), but also significantly reduce the reputational issues of the current office base and drive value for money savings through lower costs. This would still be funded uner the programme – ARF comprising a key asset in ensuring the necessary engagement in Nay Pyi Taw with government and implementing partners.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Link
DevTracker Link to Log frame:	Link

Outline of the programme

The DFID Burma Accelerated Reform Facility (ARF) was set up to provide up to £5 million between September 2012 and April 2014 for DFID Burma to be able to respond quickly to opportunities, created by the reform process, to support interventions that catalyse, foster and deepen reform in Burma.

The MoS approved (EDRM 4322226) a further £10m and extended the ARF until the end of the December 2016 based on the success of some of the initiatives funded under the ARF and the further opening of reform space, particularly in relation to the peace process in 2013. In 2016, the project was extended on a no-cost basis to the end of 2020 by the Head of Office on the basis that opportunities to support reform were continuing to present themselves in Burma. In July 2016 the MoS approved the reallocation of £5m earmarked in the 2014 extension for supporting the peace process for use under any of the ARF’s focus areas (EDRM 5514046).

The ARF focuses on six strategic pillars with the aim of helping create a better governed, more peaceful & prosperous Burma that uses its increased wealth to reduce poverty. These include the five new pillars agreed by the Secretary of State in the revised Operational Plan in 2012 and one additional pillar focused on better coordination and improved aid effectiveness:

1. Good governance and public financial management
2. Promoting responsible investment
3. Improving transparency, accountability and the rule of law
4. Strengthening the work of Parliament
5. Helping the process of ethnic reconciliation
6. Better coordination and aid effectiveness

The original criteria were updated and added to in line with the Smart Rules and Gender Equality Act 2014. Projects funded under the ARF all must meet the following criteria to ensure maximum value for money:

- The likelihood that the proposal will be transformational
- Complementarity with actions by other actors, including centrally or regionally funded DFID initiatives, and with other DFID Burma programmes
- Value for money, in terms of unit costs, input/output coefficients or other indicators appropriate to the intervention in question
- Delivery of tangible results within 18 months
- Key risks to DFID/UK
- Compliance with the International Development Gender Equality Act 2014 with a distinct section headed “Gender Equality”
- The DFID programme management implications of the proposal (including the management of DFID financial resources)
- Where relevant, the likelihood that the proposal will create further opportunities to deliver against the six areas in future

The following projects have been funded since the last annual review:

Table 1: Components under the ARF which are covered in this Annual Review

Component	Project Description	Start Date	End Date	Amount / approved / £	Drawdown Submission EDRM
203601-106	Joint Liaison Office in Nay Pyi Taw	16/08/2012	30/06/2018	272,000	4703384 (Letter of Agreement)
203601-107	Myanmar Centre for Responsible Business	11/02/2013	31/10/2016	1,786,308	4466484
203601-113	English for Education College Trainers (EfECT)	20/08/2014	19/02/2017	2,971,492	5528986
203601-114	Technical Assistance to Myanmar for Public Private Partnership Framework Development - Implementing by Asian Development Bank	01/05/2014	31/12/2016	1,026,000	4463660
203601-116	Rangoon General Hospital	05/12/2014	30/06/2016	1,475,000	4730157
203601-117	Supporting a more inclusive political settlement: Knowledge for Nation Building	July 2015	June 2018	2,000,000	5022007

Table 2 : Results Chain

Impact: A better governed, more prosperous Burma that uses its increased wealth to reduce poverty.
Outcome: Short term results that strengthen long term reform in the ARF focus areas.
Outputs: / Better governance and public financial management / More responsible investment / Improving transparency, accountability and the rule of law / Strengthened Parliament / Helping the process of ethnic reconciliation / Better donor coordination and aid effectiveness.

An overall results framework was developed over the last year based on the detailed results which are used to monitor and report on progress for each project.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The purpose of this intervention is to opportunistically finance interventions that arise in the fast-paced changing peace context to maximise the potential benefits opened up by political reform. It will do this through financing strategic and catalytic interventions which are independent and discrete so do not necessarily contribute to result in a single outcome. The logical framework has idenditifed the strengthening of long term reforms in the various output focus areas, and these are reflected in Section C.

Overall output score and description

Output	Description	Impact Weight (%)	Output performance
1	Better Governance and Public Financial Management	35%	A (Outputs met expectation)
2	More Responsible Investment	30%	A (Outputs met expectation)
3	Improving Transparency, Accountability and the Rule of Law	0%	(No activity under this output since the last Annual Review)
4	Strengthened Parliament	0%	(No activity under this output since the last Annual Review)
5	Helping the process of ethnic reconciliation	25%	B (Outputs moderately did not meet expectation)
6	Better donor coordination and aid effectiveness	10%	A (Outputs met expectation)

The overall output score is A (overall outputs met expectation). The impact weightings reflect expenditure and the number of components per output.

Key lessons

The ARF continues to be an effective vehicle for supporting Burma’s reform process and key reformers within it. It has played a useful role in piloting successful work that has been and will soon be taken over by DFID Burma’s larger sectorally-focussed programmes, notably the MCRB project which has already transferred to the Business for Shared Prosperity (BSP) programme, and EfECT too is expected to transition to DFID Burma’s new education programme in mid-2017. RGHR, Proximity Design and the Joint Liaison Office have all been extended. This provides some demonstration of the ARF’s success. Some new projects have been proposed and further work is required to bring some or all of these to fruition. The new approval processes for the project instated in July 2016 could slow down the ARF’s ability to respond to reform opportunities and should be kept under review.

Key actions
- DFID Burma should keep the new approval processes for the project instated in July 2016 under review and if possible should try to revert to the original approval process to ensure the ARF’s ability to respond rapidly is not adversely affected.
- Audit reports need to be uploaded on AMP (and vaulted if not already done), we need annual audit statements for each component unless, for example, they are covered by a framework agreement with a multilateral. The historical audit record also needs to be updated on AMP, including for closed components.

Has the logframe been updated since the last review?

Yes. Logframe and results framework are updated when projects are ended and when new projects are added to the outputs.
## C: DETAILED OUTPUT SCORING

Output Title	Better Governance and Public Financial Management
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		N/A. Last year’s risk rating assessed at the overall programme level.	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (July 2017)	Progress (July 2017)
Developed a framework for international competitive bidding for facilitating public-private partnership (PPP) investments in Burma targeting the electric power sector	1	Completed. All the documents constituting the elements of the PPP framework were prepared and transferred to the Ministry of Electricity and Energy (MOEE).
Delivered evaluation support for 300 MW rental power plant in Yangon	1	Completed
Delivered assistance in managing Power Purchase Agreement (PPAs) through training of staff of the Electric Power Generating Enterprise in best practice of PPA management	1	Completed
Conducted a study on infrastructure sharing for the use of the public infrastructure for private business, such as use of existing rights-of-way of a transmission line for fiber optic cable for telecom business	1	Completed
Presented a proposed institutional design, management of PPPs and options for management of PPP projects at national level	1	Completed
Presented a proposed institutional design and management of public-private partnership (PPP) proposed and the options for management of PPP projects at national level recommended	Structure for management of PPP projects were proposed	Completed. Institutional structure for managing PPPs project at national and ministerial levels; and structure for financial risk assessment and management of PPPs project were proposed.
Developed a roadmap for privatisation of Yangon and Mandalay Electricity Supply Boards (YESC and MESC) and presented it to Ministry of Electricity and Energy	0	Implementatin is underway. The first consultation workshops with YESC and MESC were held separately in August 2017. The final report will be submitted by November 2017.
Rangoon General Hospital development Masterplan is agreed and implemented	1	1
Improved utilities, maintainance & waste management, medical records system and fire safety of the Rangoon General Hospital	Evidence of hospital safety	It is an ongoing process starting from the safety plan reviewing, consultation, updating the plan and implementation.

Key Points

Two projects operated under this output in the last 12 months. These complement other work in the DFID Burma portfolio, in particular the Public Financial Management programme, infrastructure development through InfraCo Asia, and the health sector strengthening through the 3MDG fund. This output is scored ‘A’ as progress of the components under this output is meeting expectations.

1. Technical Assistance for Public Private Partnership (PPP) Framework Development
[ £1,026,000, 01 May 2014 – 31 December 2017, Asian Development Bank ]

Only 33% of households in Burma get access to electricity with a substantial variation of electrification rate in Yangon at almost 80% and the average rate in the rural areas is as low as 16%. Government of Myanmar targets of 100% electrification by 2030. The government has a limited administrative and technical capacity, and budget to implement a full coverage of electricity access across the country. The Ministry of Electricity and Energy (MoEE) being a regulator as well as a service provider creates a challenging enabling environment for private investors.

Deloitte India is contracted by ADB to deliver the outputs of i) design a framework for international competitive bidding for facilitating public-private partnership (PPP) investments in Burma targeting the electric power sector; ii) apply the framework to real business by proposing a list of potential projects and applying the international competitive bidding (ICB) methodology; iii) propose an institutional design and management of PPPs; and iv) recommend the options for management of PPP projects at national level. Output number (ii) was not fully delivered due to slow take up by the Ministry. It takes time for the MOEE to realize the full usefulness of the draft framework and apply it. Due to this reason the output was modified to include the following three components. All these additional outputs are completed.

1. Evaluation support for the Yangon 300 MW rental power plant
2. Assistance in managing Power Purchase Agreements (PPA) by providing training of staff of the Electric Power Generating Enterprise in best practice of PPA management ; and
3. Conducting a study on infrastructure sharing which is to understand the use of public infrastructure for private business. One of the tasks was to analyse the use of existing rights-of-way of a transmission line for fiber optic cable for telecome business

An additional output to deliver the corporatisation roadmap of YESC and MESC was approved by DFID and the project life was extended until December 2017. ADB contracted the Deloitte team for this. Delloite had consultation workshops with YESC and MESC in July 2017. Along with inputs from those two boards, the Deloitte will be conducting gap analysis and will be conducting further extensive consultation workshops before October. The final roadmap is expected to be submitted to MoEE in November.

The centrally managed “Cities and Infrastructure for Growth” (CIG) programme will hopefully plan interventions to implement some of the components of corporatisation roadmap.

Summary of responses to issues raised in previous annual reviews (where relevant)

The Annual Review in 2015 noted that there may be scope for DFID Burma to support wider PPP reform under the Business for Shared Prosperity programme. Due to the government transition in 2016, there was a series of restructuring government ministries and the changes in leadership led to the delayed in further discussion. The last Annual Review recommended a six month no cost extention and DFID Burma approved a year no cost extension to allow ADB to fully deliver the above mentioned outputs.

Recommendations

The project is coming to an end on 31 December 2017. We are not planning for an extension. Public Private Parnership technical assistance is still required to have and implement across the government’s ministries. This annual review suggests to support a wider level PPP technical assistance to Government of Myanmar for a meaningful implementation which can contribute the provision of effective public sector services.

2. Funding Project Management of Restoration and Reinvigoration of Rangoon General Hospital.
[ £1,475,000, 01 Septmember 2016 – 31 December 2017, Jersey based Charitable Trust ]

Background Information

DFID has provided £1,475,000 over 16 months (September 2016 – December 2017) to the Rangoon General Hospital Reinvigoration Charitable Trust (RGHR), to fund engineering and architectural assessments and oversight for the renovation of the Rangoon General Hospital (RGH) building- Reinvigoration of Rangoon general Hosptial- Phase II. DFID funds will also contribute towards the finalisation and adoption of a master plan for the hospital’s development itself and for broader medical care in Rangoon. Under the project for the reinvigoration of the Rangoon General Hospital (RGH) there are a range of benefits which contribute to the overall ARF objectives:

1. Hospital buildings are safe for patients and staff
2. Clinical and other professional skills have been upgraded
3. Medical equipment is well functioning
4. Continuing Professional Development plans for RGH staff are developed, implemented and monitored.
5. Hospital Development Masterplan is agreed and implemented.
6. Coordinating body for hospital care across Yangon is convened.

RGHR have identified certain essential core deliverables which have been agreed with Hospital management. RGHR and its partners (including Article 25) will provide the engineering and architectural advice and expertise to enable Burmese partners to deliver on these critical improvements, and we will provide the training and advice that will make these changes sustainable. And the preliminary work on the Masterplan has reinforced the urgency of these works for all RGH users.

Key achievements in Reinvigoration of Rangoon general Hosptial- Phase II include:

- Approval of the Masterplan by the Ministry of Health: The Minister of Health finally approved the Masterplan on 24th January 2017. The masterplan has particular implications for programme management and budget planning inside the Ministry. The Masterplanning process has raised strategic challenges for the Ministry of Health which extend well beyond the boundaries of RGH. These recommendations raise the need for wider reform in Myanmar, which understandably warranted careful consideration by the Ministry of Health.
- Improved Utilities: Hygiene Improvement in the Hospital, including a specialist’s input on hand hygiene. Services Engineers’ accelerated works on water, electric and waste water. Cost Management Quantity Surveyor to support Ministry of Health budget management in Masterplan implementation, particularly Utilities implementation. The Ministry has recently show it values our support in their internal budget management discussions.
- Maintenance & Waste Managemen: Skills for accelerated maintenance improvement. This is considered a significant problem on the site and needs to be addressed.

Medical Records System: Beverley Bryant, who is now Head of NHS Digital recruited in late August 2016, a part time programme leader Edward Reid (“ER”) on a pro bono basis, who has been supporting a full scoping, working alongside the previously advised Koe Koe Tech (“KKT”), to ensure successful implementation of what is a complex and unproved concept by KKT. Our concerns around delivery, security and data protection have been mitigated by this recruitment and ER has made three visits with a final phase scoping visit and meeting scheduled for the end of this month. A Service Agreement has been entered into by RGHR with KKT and a route to funding is being implemented. Scoping work is also being undertaken in the Yangon Women’s Hospital and the project will also include work on the impact of medical records at a primary care facility. This is in line with the Minister of Health's request to the charity to achieve a prototype that is suitable for rollout across medical facilities throughout Burma.

Fire Safety: Development of a fire safety strategy for the main building, Oxyen building, Medical store and Cancer center was completed.

Architectural site support and design analysis for Oxygen building and medical store building for efficient and safe: Ongoing process-the structure of these buildings will be thoroughly analysed in order to design the most efficient method of stabilising the structure.

Visititing Professorship Program: A number of visits have carried out for radiation oncology, medcial oncology and surgical oncology, that resulted in the establishment of PET-CT services, Cyclotron genearation, and IAEA certification of oncology services.

Campus Seismic Stability: A seismic assessment has been carried out and has identified buildings on the campus that represent a serious risk of collapse, a threat to life and a threat to the functioning of the hospital. The Disaster Risk Management Plan has been reviewed for update.

Louvres: The hospital’s relatively cool internal environment depends on the flow of natural ventilation through the external windows. This removes the need for costly air conditioning which RGH would never be able to afford. These windows are routinely covered in plastic sheeting during the rainy season so the installation of appropriately designed louvres is needed to keep the rain out while permitting ventilation. This requires sensitive design to match the heritage qualities of the original hospital building. To date, the costed plan for this design was developed for presented to management committee.

Key achievements in Architectural work include:

Cancer Car Center: Assessemet visits were carried out by radiation engineers and recommedaiton outlined for overflow of medical waste, lead shield quality, designated technician for radiation and imaging services.

Architectural site support and design analysis for 12 story building: The original 12 story building was redegined to 5 story building and that needs on going structure analysis and intensive redesign exerceis in order to make safe and usable hospital building.

Summary of responses to issues raised in previous annual reviews

The previous review recommended continuing DFID’s support to allow flexibility in the activities and outputs for which our funding is used, providing it continues to contribute to the overall outcome of the reinvigoration of RGH. The programme has taken full and beneficial advantage of this flexibility – adapting activities and initiating new ones to maintain progress and maximise impact. With the reduction in political sensitivities after the election, a considerable part of the major works for a detailed masterplan and renovation works of RGH Main Building have been completed, and some minior activities are in progress.

Recommendations

- The Masterplan presented to the Ministry has reaction to other cabinet ministers. The Union Minister of Education, Professor Myo Thein Gyi, immediately asked for a similar piece of work to be done for Yangon University. The model of sustained engagement and knowledge transfer between a UK and a Burmese team has worked, and can be extended.
- The Masterplan for the RGH site is a document of long term significance. The work we are doing now represents only the most immediate steps that have to be taken to make the site safe. Some of the issues raised in the Masterplan will require urgent and sustained effort, supported by the kind of expertise that the ARF funding has been able to bring to the Hospital. Therefore, there will be an ongoing need for funds and human capital. In anticipation of these needs, DFID should continue its support to implement the findings and action plans in the Master Plan through key main pillars - supporting the renewal of the physical fabric of the Hospital, providing medical education, and building capacity for a digital medical records system.

Output Title	More Responsible Investment
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N/A. Last year’s risk rating assessed at the overall programme level.	Impact weighting % revised since last AR?	Yes (35%)

Indicator(s)	Milestones (July 2017)	Progress (July 2017)
Support responsible business behaviour in target sectors through Myanmar Centre for Responsible Business (MCRB)	One new SWIA and 1 neew briefing paper / Updated business guide to Human Rights in Burma / Four submissions to governments on specific policy/legal reform	Drafted a mining Sector-Wide Impact Assessment (SWIA), highlighting the actual and potential impacts of the sector with clear recommendations for government, civil society and businesses. Published a briefing paper on Children’s Rights and Business in May, to provide foreign and Myanmar companies with guidance on how to apply the ten ‘Children’s Rights and Business Principles’, developed by UNICEF, the UN Global Compact and Save the Children, within a local context. / Continued to provide (free) initial advice to foreign investors about the business and human rights landscape in Myanmar; and / supported a variety of other donor-funded programmes in activities that link to the MCRB’s objectives, including several funded by DFID (e.g. support to the BIF programme’s Doing No Harm Toolkit on tourism, and to the BSP’s corporate governance activities delivered through the IFC). / Worked with a variety of private sector and NGO/CSO partners to make seven submissions on policy reform to government, covering: investment regulations (x2), mining regulations, Environment Impact Assessments (x3), and privacy.
Improved the English language proficiency of Teacher Educators (TEs) in Burmese State training colleges	90 % of Teacher Educators (TEs) show improvement on end of course SLGV test	86% of Teacher Educators (TEs) show improvement on end of course SLGV test (progress until April 2017)
Improved awareness and understanding of effective interactive classroom teaching and learning methods for Teacher Educators (TEs) in Burma	75% of Teacher Educators (TEs) show increased scores in test of understanding of methodology and pedagogical practice complete / 75% Teacher Educators (TEs) show increased ability to critically reflect on their teaching	92% of Teacher Educators (TEs) receive 50 hours of Mastertrainer classes at end of Bridge project (progress until April 2017) / 63% of Train the Trainer (TTT), English Methodology Trainer (EMT) and English Proficiency (EP) Teacher Educators (TE.s) completed 100% of their portfolios. / 76% of Train the Trainer (TTT) Teacher Educators (TE.s) completed 80% of their portfolios / 79% of English Methodology Trainer (EMT) Teacher Educators (TE.s) completed 80% of their portfolios / 79% of English Proficiency (EP) Teacher Educators (TE.s) completed 75% of their portfolios (progress until April 2017)
75% of Teacher Educators' (TEs) classes observed demonstrate application of effective interactive classroom teaching and learning methods in training student teachers	75% of Teacher Educators (TEs) show observed improvements in competencies 2 (questioning) and 3 (interactive classroom management)	In Train the Trainer (TTT) from baseline to end of course observations there was a higher percentage of score 3 across 100% of competency indicators. In English Methodology Trainer (EMT), from baseline to end of course observations there was a higher percentage of score 3 in 10 out of 13 competency indicators
75% teacher educators show more effective use of resources to support learning in the classroom	75% of Teacher Educators (TEs) show observed improvements in in competency 4 - resources	74% of English Methodology Trainer (EMT) Teacher Educators (TEs) and 70% of Train the Trainer (TTT) Teacher Educators (TEs) show improvement in developing, adapting and using resources

Key Points

Two projects operated under this output in the last 12 months. These complement other work in the DFID Burma portfolio, in particular the links between education and skills in the Business for Shared Prosperity business case and DFID Burma’s planned expansion of its education programming. Overall, outputs moderately exceeded expectations and so are scored ‘A’.

1) Myanmar Centre for Responsible Business - MCRB
[£1,786,308, 11 February 2013 – 30 September 2016, IHRB/DIHR]

The MCRB has met expectations for the annual review period.

In 2013, DFID Burma provided £600K to the Institute of Human Rights and Business (IHRB) to set up the MCRB in partnership with the Danish Institute for Human Rights (DIHR) and local partners. The centre was opened in August 2013 and has been led since then by former UK Ambassador to Burma, Vicky Bowman. Additional donors have since joined DFID and have begun providing funding (Switzerland, Netherlands, Ireland, Norway and Denmark). The aim of the centre is to promote responsible business in Burma and to provide practical advice to Government, business and civil society on what responsible business means in reality.

This has been a year of transition for the Myanmar Centre for Responsible Business in terms of DFID funding it. The organisation received its final payment via the ARF in December 2016. At DFID Burma’s request, it subsequently began discussions with the office’s DaNa Facility (part of its Business for Shared Prosperity programme) as a direct grantee. DaNa and the MCRB have subsequently carried out its own due diligence, signing a grant agreement in early July 2017 which will mean funding is no longer channelled through the ARF.

During this period, the UK has continued to fund around half of the MCRB’s activities. This has dropped in the second half of the period due to a pause in payments whilst the organisation has moved from the ARF to DaNa/BSP. However, the assurance of future DFID funding, albeit via a different route, enabled the programme to continue with activities it could not otherwise have undertaken. Subsequent payments from DaNa will be structured to cover any shortfall caused by this transition.

The MCRB has continued to make good progress throughout the annual review period, including:

Providing practical advice and evidence on responsible business:
- Published a briefing paper on Children’s Rights and Business in May, to provide foreign and Myanmar companies with guidance on how to apply the ten ‘Children’s Rights and Business Principles’, developed by UNICEF, the UN Global Compact and Save the Children, within a local context; and
- Drafted a mining Sector-Wide Impact Assessment (SWIA), highlighting the actual and potential impacts of the sector with clear recommendations for government, civil society and businesses.

Driving policy reform to promote responsible business in an inclusive way:
Worked with a variety of private sector and NGO/CSO partners to make seven submissions on policy reform to government, covering: investment regulations (x2), mining regulations, Environment Impact Assessments (x3), and privacy.

Providing support to flexible support to improve attitudes to responsible business:
    - Continued to provide (free) initial advice to foreign investors about the business and human rights landscape in Myanmar; and
    - Supported a variety of other donor-funded programmes in activities that link to the MCRB’s objectives, including several funded by DFID (e.g. support to the BIF programme’s Doing No Harm Toolkit on tourism, and to the BSP’s corporate governance activities delivered through the IFC).

Summary of responses to issues raised in previous annual reviews

Last year’s annual review set out nine recommendations for the MCRB. Progress has been made against all of these:

1. Complete: ARF funding has now ceased and the MCRB has moved under the BSP.
2. Complete: MCRB’s work on core international standards has continued, as has awareness raising activities.
3. Ongoing: MCRB continues to target large Asian and Burmese businesses through its advocacy, although this remains just one component of its work.
4. Complete: MCRB has worked closely with a range of development partners on improving the business environment, including significant engagement with the consultation process around the new Investment law (led by the IFC).
5. Complete: MCRB continues to support new organisations to set-up, and is seeking opportunities to engage further with the SME community.
6. Complete: MCRB has facilitated multi-stakeholder dialogue at subnational level, including a tourism conference in Bagan.
7. Ongoing: MCRB has continued to prioritise the development of Burmese staff.
8. Complete: MCRB has proven itself to be an adaptive organisation, able to both push ongoing strategic work as well as to respond quickly to ad hoc requests from government and businesses.
9. Ongoing: Ensuring continued funding from other donors remains a priority going forwards.

Recommendations

N/A – As the MCRB is no longer under this programme. Direction for the BSP programme, which now funds the MCRB are provided in its own annual review.

2) English for Education College Trainers – EfECT
[£2,971,492, 20 August 2014 – 31 October 2017, British Council Rangoon]

There are four key outputs for the EfECT project which will help support the achievement of the overall
ARF objectives. These are:

- improved English language competence for all Burma’s state teacher trainers and, indirectly, the teachers they train
- improved teaching methodology competence, for teachers and teacher trainers
- improved access to, and an understanding of how to use, teaching resources from the UK
- improved training methodology competence

During her September 2016 visit to London, the Burmese State Counsellor Daw Aung San Suu Kyi noted that English language training was vital, and she recognised the excellent work that the British Council was already undertaking in this area. She believed that English was the language of IT – and therefore the language of the world – and so it was vital that young people had a good grasp of the language by the time they reached High School. Burma was also considering making English the language for instruction in their universities. In addition, she wanted to improve the language ability of civil servants, particularly those working in the trade and finance ministries.

DFID Burma has strengthened its partnership with the British Council to use EfECT to engage more effectively on strategic issues at the national policy level, and liaised with other donors working in teacher education to streamline activities where possible.

The EfECT project is being implemented in the 20 Education colleagues, 2 universities of Education and the university for the development of National Races in all States and Regions of Burma in the second year of the project. It has been largely successful and an exemplary project in many ways. It was characterised by several strengths in design, delivery, management and evaluation and these strengths allowed it to respond productively to several challenges that arose. The EfECT project was extended without cost from Sept 2016 to Oct 2017. The bridge phase originally planned to run from Sept 2016 to June 2017 was extended to Oct 2017 to minimise the gap between the end of EfECT and the start of DFID’s new education programme.

During the Bridge extension, key achievements include:

- Registers set up for additional 35 hours of instruction during Bridge. Bridge baseline English Speaking, listening, grammer and vocabulary (SLGV) test of interactive communication set up. Teacher Educators’ confidence in using English were improved according to the unanimous feedback from the monitoring visits done in June 2017. The feedback included linking the increased level of proficiency to a standardised and recongnised accreditation for better motivation of teacher educators.
- The direct trainer support to the Colleges ended in July 2017 and the programme has now entered a close down/transition period until Oct 2017. External evaluaitons of the extensions are to be available in Sept 2017.
- A project closure review is planned and will be completed by November.
- During the last year DFID Burma has recruited two education advisers. This has enabled stronger monitoring and technical support to the programme.

Summary of responses to issues raised in previous annual reviews
The last Annual Review recommended a second phase of EfECT from July 2017, funded through DFID Burma’s planned new education programme and DFID Burma has planned to fund this programme under the new education business case through competitive tendering process starting from Year 2018/19. During this interval 2017/18, the response to provide short term technical assistance is placed as a platform of new programme.

Recommendations

- EfECT Burma UK Partnership of Education (BUPE), the new education programme of DFID from 2017 to 2022, will take in these considerations in designing the programme, choice of suppliers and implementation. BUPE will take in the work done by EfECT and adopt a broader address to the education reform which is not only strategic for the UK but also systemic for Burma. It is recommended that the British Council and DFID, before the new programme starts, have more consultations with the Ministry of Education (MoE), development partners, colleges and schools to define a coordinated path for BUPE which is linked well to the nation’s reform goals.
- DFID Burma needs a more sustainable approach, more integrated programme into the state’s system and more robust monitoring and evaluation. In the new programme, there should be more coordination and extensive discussions with the MoE, development partners and participants so that the programme does not stand out as an external programme. The monitoring should be strong from both the supplier and DFID side taking in recommendations from annual reviews into adapting the programme. The information coming from the colleges could have been better managed and responded.
- DFID Burma should have more involvement in the strategic oversight of the programme which has been challenging in EfECT due to the nature of partnership funding and response made fast without much chances to bring in stakeholders for discussion and buy in. There is a programme board where DFID was not part of in setting strategic directions. If there were more DFID involvement, the extension could have been planned differently laying the ground for smooth transition. DFID could have been stronger in managing the process in terms of regular discussions, monitoring on stakeholder management and outreach/impact of the progamme. DFID should have encouraged the British Council to do more stakeholder engagement in planning the extension or involved the trainers more.

Output Title	Improving Transparency, Accountability, and the Rule of Law
Output number per LF		3	Output Score	NA
Risk:		N/A	Impact weighting (%):	0
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

No projects were active under this output in the review period. Support for the Extractive Industries Transparency Initiative (EITI) project is being taken forward by DFID’s Public Finncial Management programme.

Output Title	Strengthened Parliament
Output number per LF		4	Output Score	NA
Risk:		N/A	Impact weighting (%):	0
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

No projects were active under this output in the review period.

Output Title	Helping the Process of Ethnic Reconciliation
Output number per LF		5	Output Score	B
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N/A. Last year’s risk rating assessed at the overall programme level.	Impact weighting % revised since last AR?	Yes (15%)

Indicator(s)	Milestones (July 2017)	Progress (July 2017)
Key leaders from the main target groups to participate in senior leadership programs and exposure visits	TBC (Proximity Design will update its theory of change to clarify the flow of logic from activities to outputs to contritubiton to outcome and ultimate impact by 30 September. The milestone will be updated by 31 October.)	N/A
Feedback from targeted leaders on how they value project research and see its relevance to upcoming policy decisions	ditto	N/A
Evidence of increased understanding of approaches to sectarian conflict during democratic transitions in an international context	ditto	N/A

Key Points

Only one project has been active under this output since the last Annual Review (Knowledge for Nation Building). Whilst it has delivered significant pieces of work and there is early evidence of changing mindsets and increasing understanding, there have been considerable concerns about project management. Some of these appear to be being addressed, others are still outstanding. Hence the output score of ‘B’, borderline C because of the weakness in results tracking systems.
Knowledge for Nation Building
[£2m, 01 July 2015 – 31 June 2018, Proximity Designs]

Human-resource constraint still remains in the Proximity project team and the partner tried to respond to the DFID requests on Accountable Grant amendment, result framework, delivery chain and risk register with limited staff numbers. The partner could not implement the activities as planned and some activities have been delayed eg. research trip and study trips to Indonesia. The further changes required are summarised in the recommendations below.

The Proximity results framework has updated in mid-2017 based on the discussion with the Proximity team leader and DFID team . The revised framework sets out three components and fifteen immediate outcome statements and most attention to research, engagement with local key stakeholders and senior leadership programme. However, the logframe needs more work to clarify activities, relative to outputs, relative to outcomes. In the absence of SMART indicators, this review assesses that there is tentative emerging evidence of some success with components, particularly given the impressive participation in Proximity-facilitated study tours. It recognises the unimaginable set-back caused by the dreadful murder of U Ko Ni as he returned to Yangon airport in January 2017 from the most recent exposure visit to Indonesia

Component 1: Local Research and Analysis of Priority Issues

Verdict: Sittwe trip in December 2016 produced a short memo on Rakhine: “Rakhine State – In Need of Fundamental Solutions". With the lessons and success of the January trip to Indonesia, the memo into a short paper was developed and have continued to make edits and updates to the paper as of February 1, 2017. Proximity continued refining two previously published papers. “A Grand Bargain: What It Is and Why It Is Needed” and “Rakhine State Policies: Considerations for the New State Government”. These papers are overviews of themes or attempts to bring together multiple issues, rather than deep dives or serious academic research. They are relevant to the interests of stakeholders but their quality is medium. They have since clarified their position with senior figures in the group, who now better understand the options they were presenting, but there was some reputational damage to Proximity. The reports have been prepared in Burmese language with stakeholders commending the quality of translation.

Component 2: Engagement and Dialogue with Key Stakeholders on Facts and Findings

Verdict: The team seems to have made progress in developing relationships with senior members of the Military, the new government and ethnic leaders. Through their research outputs and workshops Proximity seems to have gained credibility with a number of the groups and this has led to calls for follow up policy support. Finding high quality technical translation is a key challenge in Burma but feedback from stakeholders has been very positive about this, including a request for Proximity to provide translation at a military workshop.

Component 3: Senior Leadership Programs - Exposure/Study Trips to Indonesia

Verdict: Proximity conducted three study visits so far and the last trip was Senior Leadership Program in Jakarta and Ambon (Maluku Islands), Indonesia in late January 2017. Proximity Designs took a group of 21 Myanmar leaders from the national, Rakhine state and local community levels to Indonesia, to learn about its democratic transition, its violent religious conflict in Maluku province and a peaceful resolution to the conflict. In Maluku, the group heard firsthand, the stories of how both Muslim and Christian leaders came together to end the violent conflict. Their time in Indonesia culminated in the Muslims (national and from Rakhine state), Rakhine state Buddhists parliamentarians belonging to the Arakan National Party, military and security officials, and NLD government officials being able to discover common ground among themselves and compromise.

Sample stakeholder feedback reported by Proximity makes clear that participants in the visits developed increased understanding of opponents’ positions and the factors affecting their ability to move the peace process forward.

Key lessons

- The importance of skilled programme management - Proximity hasn’t filled up this skill gap and so they have taken time to respond to DFID requests on management matters.
- Difficulty of measuring project progress in the absence of SMART indicators – Proximity provided a revised result matrix in mid-2017 but, while it sets out components and outcomes, it needs to be clearer about activities vs outputs vs outcomes and include indicators and milestones.
- Staff capacity is needed to underpin delivery - Limited Human Resources in the project team hasdirectly affected the project implementation and made it difficult to deliver as planned.
- Importance of a robust Theory of Change – A ToC is needed to support periodic review and challenge of the project strategy from the team and the SRO. A revised strategy and ToC will need to be presented at the next 6 monthly senior strategy meeting, in October.
- Regular dialogue is essential - Regular informal meetings are also important to gauge project progress and build trust. Participation from DFID to project activities is also important to provide the technical inputs and then DFID could ensure more frequent engagement with proximity team.

Summary of responses to issues raised in previous annual reviews

When the ARF was extended by £10m in 2014, £5m of this was earmarked for support to the peace process and a further £1.5m to promoting ethnic reconciliation. The approval of DFID Burma’s new Peacebuilding Programme (EDRM 5289920) meant that these funds were no longer required for these purposes under the ARF. Following this, Ministerial and Head of Office approval (EDRM 5513989 and 5514046) was obtained to reallocate these funds for use under any of the ARF’s output areas.

Recommendations

- DFID should request from Proximity detail on its theory of change to clarify the flow of logic from activities to outputs to contribution to outcome and ultimate impact – by 18 September. The project logframe should be updated as soon as possible thereafter – by 30 September. If, by 31 October, DFID has not been satisfied with the proposed revisions to the results approach, then it should consider an early closure of the project by 31 December 2017.
- DFID should request more information from Proximity at an early stage in the planning of study tours to ensure maximum utility of the visits and appropriate fit with an (update) ToC.
- Proximity and DFID should finalise the Delivery Chain Mapping and revised budget plan as soon as possible, and complete an updated project risk matrix by the end of September.
- Each quarterly progress report needs to report on progress on results (as per a revised logframe) and must include information on how the work promotes gender equality and beneficiaries feedback.
- “DFID should quickly review the advance funding modality to Proximity’s sub-partner, Harvard. More detail is needed from Proximity prior to each advance payment. With reference to the Theory of Change, Proximity/Harvard need to explain the rationale for the work proposed. A costed work plan of activities should also be provided to DFID prior to funds being advanced to Harvard. DFID should review the proposed and provide comments or non-objection within a reasonable period agreed with Proximity (e.g. 10 working days).”
- A results framework has been developed by Proximit dated 25 July 2017, which DFID is now reviewing. It will give the proper feedback on this framework as soon as possible.
- Within DFID, it is recommended that the SRO and programme Manager are in the same team, subject to a revision to ARF’s own update of its purpose and results framework. It should be considered whether this work would best fit in the Governance, Humanitarian and Peace team, rather than in Inclusive Growth and Livelihoods.

Output Title	Better donor coordination and aid effectiveness
Output number per LF		6	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N/A. Last year’s risk rating assessed at the overall programme level.	Impact weighting % revised since last AR?	Yes (15%)

Key Points
DFID’s Nay Pyi Taw-based office, co-located with the Australian Department of Foreign Affairs & Trade (DFAT) has continued to demonstrate strong capacity for engagement with government and implementation partners based in the capital. As well as 1.5 FTE staff shared with DFAT, DFID has recruited a dedicated A2(L) Governance Adviser to drive forward the technical work of the office, as well as an A2 Head of Liaison Office to manage office performance, enhance capacity and maximise linkages into Nay Pyi Taw-based partners. A key lesson of the past reporting period has been the need to further build-up our presence in the Burmese capital, whilst clearly delivering value for money, and as a result DFID will be de-linking from our present contract with DFAT on co-location from November 2017 to seek our own premises.

Summary of responses to issues raised in previous annual reviews

Last year’s reviews recommendations and actions taken:

DFID Burma should further consider how they can maximise the value they get from the NPT team. Teams reviewed how the NPT team could best support them. With two full time DFID staff based in NPT, better engagement and relationships have been built with the Government ministries as well as with the partners.

The NPT team should continue reporting on government and parliamentary activity and the DFID Burma team should consider commissioning more such reports as required. This has continued with regular updates on: new ministries during the new government’s reorganisation of the machinery of government; ministerial appointments; and parliamentary business. We will ensure that this carries on after de-linking with the DFAT office.

DFID Burma should consider options for the liaison office once the current agreement with the Australian Embassy expires in June 2016.
Agreement was reached with the Australian Embassy to extend the current agreement to June 2018. In addition, DFID Burma has now 2 permanent staff based in Nay Pyi Taw and with a plan to employ an administrative staff after de-linking from DFAT.

Recommendations

DFID’s co-located Nay Pyi Taw (NPT) office (with DFAT) needs to significantly enhance capacity and engagement with local engagement partners. As a result, it is recommended that DFID seeks to develop and open an independent office in NPT. This will not only improve visibility for DFID NPT, demonstrating the seriousness of our commitment to development in Burma (and recognition of NPT as a key centre for government and development partners), but also significantly reduce the reputational issues of the current office base and drive value for money savings through lower costs. This would still be funded uner the programme – ARF comprising a key asset in ensuring the necessary engagement in Nay Pyi Taw with government and implementing partners.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The cost driver of each project were different. The reimbursable fee rate and operational cost hasn’t been varying significantly when it compares to the original grant agreements and contracts on each project.

Examples include:

- TA for PPP – as a technical assistance project, the majority of the expenditure goes on consultants’ fees and for the capacity building activities.
- RGHR – as a technical support to Governement for implementation of renovation of Rangoon General Hospital project, the majority of the costs goes on consultants’ fees to provide technical assistance to improve the safety of hospital campus against the risks of disaster, earthquake, typhoon, fire.
- For the MCRB, the key cost drivers remain human resource costs, with salaries benchmarked against relevant positions elsewhere. Rent in Yangon is the other main cost.
- EfECT project’s key cost drivers are costs associated with the EfECT team (84%), development of Foundation in Teaching (FIT) materials (2%) and admin (13.5%).
- The Knowledge for Nation Building project’s key cost drivers are costs associated with the Harvard research team contract cost (57.18%), local research cost (1.3%), the immersion trips to Indonesia (17.26%), and Proximity staff cost (21.16%) and Office running cost (3.1%).
- The Joint DFID-Australian Aid Liaison Office’s principal costs are the office lease agreement and contract staff salaries. Staff salaries are benchmarked to local rates and a new, lower cost 2 year lease was signed in June 2016. DFID will de-link with the DFAT in November 2017 to have an independent office resulting in more savings from the rental as well as the staff costs.

VfM performance compared to the original VfM proposition in the business case

Overall VfM has been firmly shown in every project funded to date under the ARF – projects that have been completed have mostly delivered against their objectives within or below the original costs set out in their financial plans.

Every drawdown submission for funding from the ARF is assessed against the criteria set out in the original ARF business case. These criteria were strengthened further during the £10m cost extension approved by the Minister of State in 2014 and by the addition of a requirement to demonstrate how projects will comply with the International Development Gender Equality Act 2014.

Assessment of whether the programme continues to represent value for money

A key element of the ARF’s delivery of value for money is the significant amount of staff time saved by being able to write concise project proposals for small interventions rather than full Business Cases. This addressed DFID’s objective to be able to rapidly respond to the opportunities that arise unpredictably in Burma’s reform process. A new project proposal instated in July 2016 could adversely affect this equation and its impact will be kept under review.

ARF projects that have been completed have mostly delivered against their objectives within or below the original costs set out in financial plans, indicating effieiency.

Effectiveness is harder to measure as it is not possible to estimate exactly how much of an impact the projects have had on the reform process as there are too many possible contributing factors. However they are achieving outputs in areas that are key for reforms and have provided DFID with a mechanism to respond quickly to opportunities to support the reform process. The completed projects have all delivered against some or all of the criteria set for the ARF and those not yet completed appear to be well placed to do so.

Specific examples of value for money in ARF projects include:

MCRB - The MCRB continues to represent good VfM for DFID, especially given its efforts to recruit and develop Burmese nationals. All printed material is translated and produced locally. A key issue going forwards is ensuring the institution continues to receive funding from a range of donors.

EfECT – Negotiations on proposals considered economy, efficiency and effectiveness in the bridge extension. British Council Myanmar can drive the optimal use of available resources to achieve intended outcomes and the beneficiaries have so far reported satisfaction with English classes, interactive classroom management, training activities, teaching practice sessions with FIT materials and pedagogy which is implemented by British Council Myanmar in 20 education colleges across Burma. A detailed VfM assessment will be conducted as part of the Porject Completion Review.

Knowledge for Nation Building - Regarding to the project nature, measurement of the project outcome and output results is not easy as project activities are sometimes behind the schedule due to the political situations. According to the revised result framework, the achievement can be measured against output and outcome target in next year Annual Review. VfM performance of the project is also not vividly like last year Annual Review and so SRO and Programme Manager have reviewed the contract management on Harvard team and ensure that each single payment on contracts must have to be made based on the satisfactory of lead of the Proximity by reviewing the delivery report of contractee. After VfM training organized by DFID in July 2017, Proximity understood the need to be more structured and presentable in how they assess our desired outcomes and impact. Furthermore, Proximity has proactively taken up, upon DFID’s recommendation, the process of Strategy Testing for our internal annual reviews of our projects and areas of policy focus together with our partners. This is a process of continuous improvement and we would appreciate any and all support we can get from DFID and other implementing partners. However DFID will continue the discussion on the high return from low cost. Eg. a)The Harvard researchers’ costs are larger than anticiapted - the scope for savings is being investigated and it may be possible to reduce the number of trips they make to Burma, though there are risks that this would undermine progress against the outcomes to the extent that it counteracts the cost savings; b) DFID lead will look at the contractor’s report on project activities before making the payment; and c) DFID Lead will review quarterly progress report and give the feedbacks in time and DFID let proximity knows that payment will be made based on the satisfaction of quarterly report.

Quality of financial management

The ARF programme is overall assessed as having a good financial management except EfECT programme. Strong financial and reporting arrangments have been put in place for each project and due diligence assessment hav been made and the financial and management arrangements for each project reflect these assessments.

Examples of financial management within the ARF’s current projects include:

MCRB – MCRB funding is held and administrated by IHRB which has fiduciary responsibility to donors. Funds are then transferred from the UK to Yangon for local spending, as appropriate. Expenses outside of Burma are dispersed by IHRB to DIHR and partners or service providers. This arrangement works well and reflects MCRB’s respective legal statues in the UK and Burma.

The MCRB has an anti-corruption code of conduct which can be found here- http://myanmar-responsiblebusiness.org/pdf/Anti-Corruption-Code-of-Conduct.pdf. The purpose of the MCRB Anti-Corruption Code of Conduct is to ensure and support behaviour and working ethics characterised by high standards of personal and organisational integrity, both internally and with partners.

Knowledge for Nation Building – Financial management has been good to date but there is a room to improve in contract management . Spend tends to vary from forecasts, as was anticipated in the draw down submission due to the nature of the project. DFID Burma is kept informed of expected variations and we are working with the Proximity Designs team to improve planning and financial forecasting.

EfECT – The project could have considered the opportunity costs better especially for the underspend. There should be stronger financial management and budget forecasting as the supplier consistently overforecast on spend.

The quality of the financial reports under this programme are not always accurate with detail specification of operational activities. As the EfECT programme will end in October 2017, the impression of financial management will highlight in details with the relevant recommendations in Project Completion Review. The British Council Myanmar needs to strengthen giving the assurance of financial oversight and budget forecasting with best estimated spend for programme activities. Justifications are provided for the underspend figures in their quarterly reports accordingly – however, the possibility of underspend should be consistently escalated.

E: RISK

Overall risk rating:

Currently risk rating of moderate has not changed since the last Annual Review. However, individual projects vary from moderate (the TA for PPPs, RGHR, MCRB, EfECT, Joint Liaison Office) to major (Knowledge for Nation Building).

Overview of programme risk

The elections in November 2015 and the transition to the new Government in April 2016 proceeded smoothly and the reform process remains on track but there remains potential for disputes between the Government and the military to stall or even reverse the reform process – this might dramatically limit the ARF’s scope to support projects. Increased conflict in border areas is another risk that could affect implementation of those projects that operate across the country (e.g. EfECT). There is little that can be done within the ARF itself to mitigate these risks (though some, such as Knowledge for Nation Building work directly to minimise the potential for conflict) – other programes across the DFID Burma portfolio address the sources of tension and conflict (e.g Peacebuilding, Humanitarian, and Democratic Governance).

The risk that the interventions would not be strategic has not materialised as all of the interventions are in areas that remain key parts of the DFID Burma programme.

The programme management implications have been included as one of the key ARF funding criterias to assess the returns against the management burden. Each project has its own dedicated programme manager with a separate programme manager having oversight across the whole ARF. No programme manager manages more than one ARF project so the workloads is spread across the team, minimising the impact on individuals.

None of the projects under the ARF are funding Government currently and therefore risks related to the Government’s ability to manage interventions are not generally an issue.

A new operational risk is the change to the ARF project approval process in July 2016. The ARF is explicitly intended as a rapid response facility and was conceived and approved as a programme under which authority to approve projects would be delegated to the Head of DFID Burma. The new procedures potentially add substantial time to the approval process and could therefore slow down the ARF’s ability to respond to support reform opportunities. This risk should be kept under review and if possible, should try to revert to the original approval process to ensure the ARF’s ability to respond rapidly is not adversely affected.

Outstanding actions from risk assessment

The ARF risk matrix need to be reviewed and updated to relect DFID’s new risk management framework.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

As outlined above, the projects under the ARF are largely on track to deliver their objectives within agreed timeframes, though the TA for PPPs required a no-cost extension to compensate for delays cuased by government focus being elsewhere in the run up to the elections and during the transition to the new government and the EfECT programme required £620,000 cost extension from September 2016 to June 2017 for the bridge period to develop DFID Burma’s education strategy in the context of a new administration under the National League for Democracy (NLD) and emerging educational reforms. The no-cost extension until 31 October 2017 was required for the project closure period to ensure good quality exit procedures and completion.

Performance of partnership(s)

There are co-funders in a number of ARF projects including the MCRB, the EfECT and the Nay Pyi Taw Liaison office. Generally, these are working well but there is more room to improve partnership in EfECT programme.

EfECT – The British Council is the co-funder in EfECT progrmame. There were changes in management/project director during extension period from a full time director to a director who is engaged in the core British Council’s activities and can’t devote more than one day a week to EfECT. In addition, the director departed earlier than the original plan to stay until September.

MCRB – The MCRB is also funded by the governments of Norway, Switzerland, Denmark, the Netherlands and Ireland. The UK continues to contribute roughly one half of funding, although payments are ‘lumpy’ across donors so this may not be representative of some specific periods. Relationships with other donors are going well, and they have been receptive to DFID’s change of funding channel for the MCRB.

Knowledge for Nation Building – Partnership with DFID and Proximity is now going smoothly and we should keep this momentum going by doing regular quarterly meeting with the partner. DFID’s project lead has also provided more time and has participated in some project activities and provided timely feedbacks to the partner. Partnership between Proximity and project key stakedholers such as Government, military and ethnic group has been good so far except some activities were delayed in implementation due to not getting approvals in time from the Government and the military.

Asset monitoring and control

The partners have been informed a new asset register policy in DFID through issuing the new accountable grant to record the asset above £500. According to the MoU and Accountable Grant arrangements, audits will be conducted on the projects and the auditor will also perform a physical check on the assets.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Until now, DFID Burma does not provide any budget support or direct funding to Government, in line with the policy agreed by Minister of State Alan Duncan in response to DFID’s submission of 31 March 2014.
Subsquent reviews have found that no change was required to the principles approved by the Minister of State. These state that DFID:

1. Should continue not to provide funding directly to the government, but should allow selected programmes and multi-donor bodies funded by DFID to fund government subject to rigorous controls and oversight by trusted international agencies.
2. Should allow inclusion of government representatives on oversight bodies for selected DFID-backed programmes, where the counterpart departments have demonstrated themselves to be pro-reform
3. Should continue to fund technical assistance to pro-reform government bodies directly and through organisations that we fund.
4. Should monitor for severe deterioration in human rights or governance, and be prepared to change our position should either arise.
These principles are reviewed as part of our continued analysis of major events and through our programme work at appropriate milestones.

H: MONITORING & EVALUATION

Evidence and evaluation

The reform process faces risks but has proceeded smoothly over the last year and is ongoing. It is important that DFID continues to explore opportunities to provide support to the reform process. DFID Burma should also continue to be flexible in interpreting how support to reforms might help deliver against the ARF objectives, and be prepared to accept that some reforms will contribute indirectly and in the longer term to these objectives.

Projects funded by the ARF undergo monitoring and evaluation. Examples include:

TA for PPPs – ADB will inform DFID of any review missions undertaken by it related to the Grant, and provide to DFID a report setting out the main findings or results of such mission. ADB will invite DFID to join TA review missions, including supervision mission and the mid-term review during the implementation of the TA and upon its completion.

MCRB – An external Mid-Term Review of the MCRB took place in 2015, confirming that “the MCRB has more than lived up to its original mandate, and that its aims and objectives remain valid”. Online stakeholder reviews by the MCRB have continued to support this, with significant numbers of businesses confirming that the MCRB is a key source of information on responsible business for a variety of stakeholders.

EfECT – External evaluations of the extensions are to be available in October 2017.

Knowledge for Nation Building – Evidence of outputs are collected systematically and are easy to verify. Evidence of performance against outcomes is more subjective and is harder to verify. To ensure these assessments are evidence-based, the results framework has been revised to be in line with the revised ToC. To further ensure rigorous monitoring, the project’s evaluation strategy will be discussed over the next 3 months and will include an independent evaluation.

Monitoring progress throughout the review period

The review is based on analysis of documents delivered, regular conversations with project staff and beneficiary feedback, where available. Evaluaitons have been conducted and planned for certain individual programes such as the MCRB, EfECT and Knowledge for Nation Building.

Use of DFID branding

ARF projects use the DFID/UKaid branding in accordance with the guidance. Examples include:

UKAid branding was used throughout the TA for PPPs project. ADB published DFID’s funding support to the project on their website explicitly.

The UKAID logo is included on the MCRB website homepage, in its publications and on signs at its office and events.

The DFID-Australian Aid Joint Liaison Office is clearly branded as such with a signboard outside the office, including the latest UKaid logo. All written communications from the office team are also marked as being from the ‘Australian Aid – DFID Joint Liaison Office’.