Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	30th September 2017

Title: Programme for the Promotion and Protection of Women and Children’s Rights in Zambia
Programme Code: 203428	Start Date / 12th March 2013	End Date / 30th June 2017

Summary of Programme Performance

Year	2013	2014	2015	2016	2017 (AR)	2017 / (PCR)
Programme Score	A	A	A	A	A	B
Risk Rating	Medium	Low	Low	Minor	Minor	Moderate

Financial Position

Original Programme Value	£2,337,500
Extensions/ amendments	2013 extension of £50,000, bringing total programme value to £2,387,500
Log-frame revisions (with dates)	February 2013 / March 2014 / February 2016 / July 2017
Total programme spend	£2,348,815.28

Follow up actions required following closure

- A number of unmet milestones may be completed using UNDP resources in the next 6 months. DFID Zambia should continue to monitor the programme in order to ensure the quality of activities and the sustainability of achievements. UNDP are commissioning an evaluation in October and it will be important for DFID to engage in this process and share lessons learnt.
- DFID Zambia should begin financial close out with both partners. This will entail making a final payment to VSO, and ensuring the return of unspent funds and asset disposal with UNDP. As the UNDP contribution to the programme does not end until December 2017 these processes will need to take place in 2018. This project completion review should be updated following the full financial closure.
- The DFID Zambia team should discuss with UNDP opportunities to document the successes of the programme not captured in the logframe, particularly if there is a method for documenting the changes in national discourse and national development planning.
- The Senior Responsible Owner (SRO) should share learning from this programme with DFID Zambia colleagues also implementing technical assistance programmes, and use this as the impetus for thinking about better ways to monitor the impact of these programmes.
- This programme has generated a number of lessons for DFID Zambia in terms of programme management. These should be shared widely to ensure lessons learnt can be built upon to improve the management and outcomes of other programmes.
A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204075/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204075/documents

Outline of programme and what it has achieved

In Zambia, discrimination against women and girls cuts across economic, political and socio-cultural boundaries. At the time of this programme`s inception (2012) Zambia ranked 136th out of 148 countries on gender inequality[1]. This high level of inequality has hindered the country’s development efforts and ability to support all its citizens to access and benefit from economic development.
[1] 2012 Gender Inequality Index, United nations Human Development Report

To support the Government of the Republic of Zambia (GRZ) to reduce gender inequality and discrimination against women and girls, DFID Zambia allocated £2,387,500 over four years (2013-2017) to provide flexible technical assistance (TA) and strengthen capacity of the Ministry of Gender (MoG).

The programme was made up of three components:

Direct support for the implementation of the GRZ Programme for the Promotion and Protection of Women and Children`s Rights (PPPWCR), managed by UNDP and focused on four themes of: legislative reform, economic and social empowerment, political representation and strengthened coordination.

The Gender Equality Fund (GEF) – used to provide training[2] to build the capacity of MoG staff, Permanent Secretaries and gender focal points from across government ministries ministries.
[2] Three types of training were delivered: gender analysis skills development, strategic leadership development and team building, mentoring and coaching

The Gender Institutional Strengthening Support Project (GISSP) implemented by Voluntary Services Oversees (VSO) from 2015-2017. VSO placed three volunteers at the MoG to work alongside staff to build systems and staff capacity in Results Based Management Systems (RBMS), Management Information Systems (MIS); and Planning.

Together these activities were expected to deliver the programme outputs:

- Ministry of Gender delivers effective leadership, coordination and monitoring of action to improve gender equality
- Priority line ministries implement gender responsive policies, planning and budgeting
- Coordinated action to domesticate the Convention on Elimination of all forms of Discrimination Against Women (CEDAW) and implement the Anti-Gender Based Violence Act
- Communication strategy promotes positive gender norms and increased awareness of laws and policies
- Implementation of a strategy to increase women`s representation in decision-making positions

The programme theory of change assumed these outputs would deliver the programme outcome of an ‘enabling environment for the legal, political, economic and social empowerment of women in Zambia’ which in turn would contribute to the impact of ‘reduced gender inequality in Zambia'.

Key achievements

There has been significant improvement in gender equality in Zambia during the period of this programme, as evidenced by both impact indicators having been exceeded. Between 2012 and 2015 the Gender Inequality Index in Zambia improved from 0.623 (2012) to 0.526 (2016), moving its rank from 136 out of 148 countries to 124 out of 159. The percentage of Zambians aged 18 and above that attach equal importance to women and men has increased from 44.8% in 2011 to 67% in 2016. Whilst these changes are not fully attributed to the programme, findings from this review suggest the programme has made a number of positive contributions towards improving gender equality, such as the increased leadership and improved discourse on gender across the GRZ and work with traditional leaders, and these have contributed and will continue to contribute to this positive trend. Key achievements include:

Increased discourse and leadership within government to promote gender equity and equality, as evidenced by:
- Gender embedded in the 7th National Development Plan (NDP) (2017) with the integration of gender indicators throughout the NDP rather than being a standalone pillar. Speeches from senior government officials emphasised the importance of gender equality in national planning, and the MoG engaged line ministries to develop a strategy for tracking gender progress across the pillars of the NDP.
- Commitments to increase women’s political participation – the MoG collaborated with the Zambia National Women’s Lobby (ZNWL) and the NGO Coordinating Council (NGOCC) to implement the ‘Count Her in Strategy’ which resulted in political parties signing a Joint Declaration outlining their commitment to increase the adoption of women candidates, although this commitment was not fully met.
- The inclusion of a gender component in all cabinet ministers’ performance management forms, instigated by the President.
- The creation of a Committee of Permanent Secretaries (chaired by the Secretary to the Cabinet) to discuss gender issues was a strong indicator that the government was committed at the most senior civil servant level to a cross departmental approach to gender equality. Until the 2016 general election, this committee met annually.

Legislative standards better support the rights of women
- Enactment of the Gender Equity and Equality Bill (2016) following several years of work to define the legislative standards and institutional framework to increase gender equity in Zambia.
- Establishment of the Gender Equity and Equality Commission, through the revised Constitution and Gender Equality and Equity Act. The organisational framework for the new commission has been submitted to the Cabinet for approval, and it will have the power to hold line ministries to account, complementing the coordination, advocacy and lobbying role the MoG will retain.
- Improved legal services for victims of gender based violence, evidenced by the establishment of 2 fast track courts for Gender Based Violence (GBV) victims and draft revisions to the penal code and criminal procedure code.

Improvements in data collection and communication to inform policy and practice
- New systems are developing to generate national evidence to improve policy and practice. Three national gender status reports (2011, 2012-2014 and 2015-16) and two gender perception surveys have been completed by the MoG. This reflects increased capacity to collect, analysis and publish data to inform policies that impact on gender equity. The MoG should now focus on improving data quality and the consistency with which data is submitted and reports are published.
- Development of an internal working paper by the MoG on key issues such as collection, processing and production of sex disaggregated data to inform policy development and decision making based on its participation at the 2016 Commission on the Status of Women(CSW). These working papers provided inputs into major state policy pronouncements and directives. An example being the Presidential directive to the Ministry of National Development and the Ministry of Gender to ensure that all ministries and provinces integrated gender into their budget plan.

Challenges
Despite these achievements, the programme has faced a number of challenges, particularly during the later stages of the programme. Key challenges per programme component are outlined below.

Direct support for the implementation of the PPPWCR implemented by UNDP

Lack of commitment from the MoG to prioritise its mandate of coordination and advocacy
- An agreed milestone target for the programme was to create a communication strategy that would enable MoG to carry out sustained and strategic activities on priority policy areas. However, despite annual review recommendations for the need to accelerate progress to deliver this strategy, the MoG prioritised short-term activities that raised their profile and visibility, such as large commemoration events in support of specific gender related days.
- MoG was able to attract resources from other donors drawing it further into implementation of activities. The prioritisation of the MoG on these budget generating activities meant that their cross government influencing role was neglected, for example gender audits of priority sectors were not used effectively to advocate for change in line ministries.

Lack of government budget and resources for sustained capacity building
The MoG has been underfunded throughout the programme period. On average, less than half of the allocated budget is received, for example in 2014 only 26% of allocated budget was disbursed. The lack of human and financial resources resulted in trade-offs between the day to day running of the ministry and delivering PPPWCR objectives, of which the former was often prioritised.

Outputs requiring action and input from other line ministries were too ambitious
It was recommended in PPPWCR annual reviews that a system should be put in place to compare percentage of budgets allocated by ministries to percentage of budget expended in order to measure improvements in gender responsiveness. This target was not met and there was limited evidence of the quality of Gender Responsive Budgeting (GRB) in line ministries, in a large part because the programme overestimated the capacity and power of the MoG to compel line ministries to respond to their requests for this information.

Failure of the programme to respond to contextual changes:
- Institutional capacity, high staff turnover and restructuring of the MoG - The Ministry of Gender and Child Development was established in March 2012. As a new Ministry, at the time of programme inception all staff were director level. These staff were committed to the PPPWCR but were then moved to other ministries. The Ministry underwent restructuring in 2015, which alongside increasing staff turnover, reduced engagement, institutional knowledge and coherence of projects and plans to implement the PPPWCR. Engagement improved in late 2016 under the new Director of Planning, however this came too late to get the programme fully back on track.
- Insufficient UNDP resources allocated to the PPPWCR - the impact of the above changes in context were compounded by the lack of a dedicated staff member at UNDP to work on the PPPWCR. It had been assumed this work could be achieved through MoG staff, however a dedicated staff member would have improved the responsiveness of the programme to the context and increased the pressure applied on the MoG to deliver PPPWCR outputs on time.
- DFID engagement with the PPPWCR - staff turnover and competing priorities in DFID meant the logframe increasingly diverted from the activities the programme came to focus on, and there were insufficient efforts to improve partner monitoring and measurement of outputs and outcomes, resulting in difficulty assessing programme performance. Although two versions of a value for money framework were developed and reported against in 2015, 2016 and 2017, the lack of clear targets did not facilitate a thorough review of whether the programme was improving value for money. These lessons have been learnt, and DFID Zambia is currently improving mechanisms for monitoring annual review recommendations, updating logframes, value for money frameworks and delivery plans to ensure stronger programme management.

In February 2017, the annual review team requested a 6 month no cost extension to allow UNDP to catch up on delays in implementation caused by the election period (August 2016), however this was not approved by DFID Zambia due to the lack of evidence of improved performance and ability to deliver the agreed outputs during the extension.

Gender Equality Fund

Technical assistance provided has been well received but there was no measurement of outcomes and impact.
Training delivered through the GEF was carried out successfully and feedback from those interviewed was very positive, however there was no measurement of how the participants had retained what they had learnt, or been able to apply it.

Provision of training not sustainable
The programme assumed that intensive training during the early years of the Ministry would build a base level of capacity that could then be sustained through routine training and on the job learning. Currently the MoG does not have the resources to provide this training and therefore remains dependent on donor support.

The Gender Institutional Strengthening Support Project (GISSP)

Evidence analysed during this review suggests that the GISSP failed to achieve its objectives and should have been significantly amended at an early stage of programme implementation. Challenges faced included:

Identifying volunteers with appropriate skillset – there were significant delays in the recruitment of volunteers that had the skillset required to fulfil the needs of the Ministry. This reduced MoG engagement with the volunteers when they arrived, and reduced the consistency of the capacity building support provided.

No monitoring or evaluation of project outcomes – it is difficult to measure the success of the GISSP as no system was put in place to measure improvements in individual or institutional capacity. VSO assumed that if outputs were achieved then so were the intended outcomes.

No output in the logframe for the GISSP component of this programme – whilst DFID met with VSO regularly throughout the programme period, the GISSP output was not included in the programme logframe until 2017. This meant that this component of the programme wasn’t monitored systematically through DFID`s annual review process.

Volunteers carried out ‘gap filling’ tasks rather than carrying out their advisory and capacity building role – despite recommendations in the PPPWCR mid-term evaluation, volunteers continued to fill MoG staffing gaps, for example by representing the MoG at meetings or proof-reading speeches. This delayed the delivery of GISSP workplan objectives.

Insufficient MoG engagement – a single tripartite meeting between the volunteer, VSO and a MoG representative was carried out before the volunteer placement, which informed the terms of reference for the volunteer placements. No additional meetings between the 3 stakeholders took place and this appeared to lead to a lack of communication between VSO and the MoG and a misalignment of expectations.
## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The intended outcome of the PPPWCR was ‘an enabling environment for the legal, political, economic and social empowerment of women in Zambia’. The four outcome indicators used to measure progress towards achievement of this outcome were not met.

Outcome Score: B, outcome did not meet expectations

Indicators	Baseline (2012)	Target (June 2017)	Progress
1.1 Number of laws revised to conform to CEDAW provisions (cumulative)	0	5	Not achieved - 3 / The programme has supported work on seven pieces of legislation, which would exceed the programme target. However, only three laws have been enacted (the Gender Equity and Equality Act (2016), Employment (Amendment) Act (2015) and Articles 8, 9, and 231 of the amended constitution), four have been (re)drafted and are pending submission to Parliament: the Anti-GBV Bill, Penal Code, the Criminal Procedure Code, Child Code Bill, Marriage Bill
1.2. % newly allocated state land allocated to women	27% (2014)	35%	Not achieved – 32% / Whilst the target has not been met, the percentage of women accessing land has continued to increase from 27% in 2014, 28.3% in 2015, and 29.6% in 2016 to 32% in 2017.
1.3. % women in decision-making positions in the civil service	PS: 19% / Director: 23% / Dep Director: 43%	PS: 26% Director: 37% / Dep Director: 47%	Not achieved - PS 24%; Director and Dep Director data not available. / 2017 data for director and deputy director levels is not available; however 2016 figures of 33% and 28% respectively were not on track to meet the target.
1.4 Number of operational Anti-GBV user-friendly and fast track courts	0	6	Not achieved - 2 / 2 courts are fully operational, equipment has been procured for an additional 4 courts and training has taken place, however construction work has delayed the launch of these courts until October 2017.

Despite not meeting the target of 5 laws revised (e.g. enacted) to conform to CEDAW provisions, progress towards improving the legal environment for women and girls has been very positive, with three key pieces of legislation enacted and four in the process of being amended to better conform to CEDAW and the Convention on the Rights of the Child. These include:
1. The signing of articles 8, 9 and 231 in the constitution, which outline the values and principles of gender equality.
2. Drafting and enactment of the gender equity and equality bill, which includes key issues from CEDAW and the SADC protocol on Gender and Development.
3. Drafting and submission of the Marriage Bill to the Ministry of Justice (MoJ). UNDP and the MoG had indicated that it would be enacted in this parliament however progress has halted due to the contradiction between this Bill and Article 23 of the constitution.
4. Drafting of the Child’s Rights Code Bill. Before the Child Development mandate was moved from the Ministry of Gender and Child Development they drafted this Bill which aims to domesticate the CRC provisions in their entirety. The Zambia Law Development Commission (ZLDC) reported that this bill is currently being finalised.
5. By the end of 2016 amendments to the Penal Code and Criminal Procedure Code had been drafted to include Gender Based Violence (GBV) penalties. This code will provide for an increased remit for the Fast track GBV courts and reinforce the commitments under the Anti-GBV Act. The code has been submitted to the MoJ and is expected to go to Parliament for the 1st reading at the end of 2017.

The programme also contributed to the establishment of a Gender Equity and Equality Commission and the engendering of the 7th National Development Plan.

In relation to state allocation of land, progress has been positive. The MoG completed a gendered lands assessment that resulted in the Minister of Land issuing a policy statement in 2013 declaring that 40% of newly allocated state land will be issued to women. Following continued delays with the National Land Policy, MoG advocated for a second policy directive which was issued in 2017 declaring that 50% of land allocation will be to women. The MoG and UNDP subsequently commissioned a land audit of councils to assess how they are implementing this directive and recommend steps to increase provision of land to women. In addition to state allocated land, the programme has also worked closely with Chiefs to increase access to customary land for women. Allocation of customary land is extremely difficult to measure, but specific examples of progress include two Chiefs implementing a 50:50 land allocation principle, with one also introducing customary land certificates. The number of women issued with land ownership certificates has increased in one Chiefdom from 19 in 2015 to 50 in the 2017.

Despite the commitment from the MoG to provide an update in April 2017 on the percentage of women in decision making positions across the civil service, no data has been received for Director and Deputy Director level and quarterly reporting has not begun. The Public Service Management Division (PSMD) has shared the database of public service commissions with MoG for analysis, but this is not yet complete. Data from 2017 for Permanent Secretaries has actually shown a decline from 28% in 2016 (exceeding the end of programme target) back to 24%. Data for 2016 for Directors and Deputy Directors did not meet targets, with almost no improvement from baseline

Progress on establishing fast track courts has been strong, however this has moderately not met the end of programme targets as the 6 courts will only become operational in October 2017. Courts in Lusaka and Kabwe are functioning well, equipment and training of staff in Ndola, Chipata, Choma and Mongu has been done and construction work is being finalised ahead of the courts launch in October.

Lessons learnt and how these have been shared

The key lesson for DFID is the importance of ensuring robust monitoring systems are in place and implemented. Targets and milestones in the logframe for this programme did not accurately measure progress against the defined outputs and the outcomes. Many milestones were poorly defined and some components of the programme (e.g. GISSP) did not have a logframe output until the last year of the programme.

Recommendations:
- In future, DFID should work with partners to ensure the indicator milestones and success criteria are clearly defined and measureable, that outputs and outcomes remain aligned to the programme theory of change and that milestone targets continue to measure the defined output.
- Output targets should be under the control of the implementing partner and be stretching yet attainable. These targets should be agreed by all parties at the outset.
- Value for money indicators covering all major programme activities should be set with appropriate targets and monitored regularly throughout the programme.
- As measurement in capacity building programmes is challenging, process indicators should be included where possible to demonstrate how the programme has contributed to achievements.
- To ensure future programmes remain relevant and aligned to the needs of key stakeholders and beneficiaries, DFID should ensure there are reviews of the programme context and that these feed into logframe amendments and changes in programme design.
- DFID should align timeframes with partners in joint programmes. The 6 month difference between the end of DFID financing and UNDP financing has caused problems in terms of reporting but also delayed activities, with UNDP incentives aligned for completion in December.

Recommendations for UNDP:
- UNDP’s approach of providing the MoG with sector specialists at key events, such a workshops to revise national plans, policies and legislation, worked well to build MoG capacity and maintain the quality of outputs that the MoG contributes to. This approach should be recommended for inclusion in any future programmes.
- UNDP should ensure that there are sufficient staff resources to support the MoG (or other Ministries) and ensure activities remain on track and relevant to programme objectives. In future programmes delays and challenges should be communicated to donors early and, where required, alternative objectives should be proposed. This proposal should be made in advance of target deadlines.
- UNDP should ensure that the targets they set are under their control and measureable. It should be agreed at the outset what evidence is required to demonstrate success, and systems should be put in place to collect this data. UNDP reports should be better aligned to these outputs and outcomes.

Recommendations for VSO:
It is not recommended that this model is used again to support capacity building within a government ministry, however if a similar approach is applied in the future, lessons from the GISSP have generated the following recommendations:

- There should be good initial and ongoing engagement with the Ministry to ensure there is demand for TA, and an enabling environment for the successful delivery of outputs.
- TA roles need to be outcome focused and sustainability of their contribution needs to be considered from the outset. This may mean focusing on small scale systems/process improvements, rather than ad-hoc individual capacity building.
- High level support from DFID/other donors is required to improve engagement and leadership from senior staff at the respective ministry. Unlike VSO, donors have the power to push the ministry to take action on specific issues/challenges.

## C: DETAILED OUTPUT SCORING
Output Title	Ministry of Gender delivers effective leadership, coordination and monitoring of action to improve gender equality
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)	Baseline (2012)	Target (June 2017) 06/17)	Progress
1.1 Number of functional working groups for coordinating gender programmes and strategies that include all relevant stakeholders including civil society other line ministries, traditional leaders	1	All 7 committees meet the required standard of meetings as set out in their ToRs	Target not met: / 11 committees were established and meeting, however MoG/UNDP were not able to provide any evidence that they are meeting as per their terms of reference.
1.2 National gender M&E plan and system established and implemented	Draft M&E plan, 31% of indicators without baseline	20 (91%) MPSA-Ministries, provinces and spending agencies submit data on core indicators in the national gender M&E plan	Target met: 22[3]
1.3 Annual publication and dissemination of National Gender Status Report	No report published in 2011	2015 report produced and disseminated to key stakeholders	Target not met: 2015 - 16 report has been drafted and validated by stakeholders but not yet printed or disseminated.
1.4 Gender Equality Fund used for training and capacity building of MGCD and gender focal points	No training and capacity building plan	2016 target - Gender Equality Fund used to develop capacity of gender focal points (i.e. Directors of Planning) in priority line ministries and 70% of gender analysts and directors in MGCD trained	Target exceeded: / GEF has been used to train more than 90% of Directors, Assistant Directors, gender analysts and gender focal points. / No target for 2017
[3] These are: Ministry of National Guidance and Religious Affairs, Ministry of Fisheries and Livestock, Ministry of National Development Planning, Ministry of Foreign Affairs, Office of the Vice President, Parliament, Ministry of General Education, Ministry of Higher Education, Ministry of Health, Ministry of Community Development and Social Services, Ministry of Labour, Ministry of Local Government, Ministry of Agriculture, Ministry of Justice, Ministry of Chiefs and Traditional Affairs, Ministry of Home Affairs, Central Statistics Office, Ministry of Gender, Public Service Management Division, Ministry of Commerce, Trade and Industry, Ministry of Lands, Ministry of Transport and Communication

Key Points

Under this output, the Ministry of Gender is to deliver effective leadership, coordination and monitoring of action to improve gender equality. This focuses on delivering gender training, engaging with other Ministries, supporting Ministries, Provinces and Spending Agencies (MPSAs) to submit gender related data into national monitoring and evaluation and producing national gender status reports.

Eleven cross government committees have been established, four more than the programme target, and MoG/UNDP have reported that most are functional. However, no system was put in place to monitor and measure the actions or outputs from these meetings so it is not possible to assess each committee`s contribution to output 1. For some committees (e.g. the Programme Implementation Technical Committee (PITC), Gender Statistics Committee etc.) it is clear that they discuss gender and contribute to PPPWCR objectives, however for others, it is unclear how what contribution they have made or what the role of the MoG was in setting them up.

In the past year the gender statistics committee has been meeting regularly to produce gender status reports and develop a data collection tool for GBV. The MoG has met all line ministries during the period under review to mainstream gender in the 7NDP however these activities are not sufficient to say that the output indicator has been met. The MoG plans to revisit these working groups and realign them with the Cluster Advisory Groups (CAGs) established under the 7NDP.

The target for output indicator 1.2 was met. UNDP and the MoG report that data has been submitted against national gender indicators from 22 line ministries, however the system for data collection requires further strengthening. The MoG indicated that a new system would be in place to enable quarterly reporting of data against gender indicators by June 2017, however this target has not been met and data quality remains poor. The revised National Gender Policy specifies that all partners are responsible for collecting and submitting sex-disaggregated data, however a number of line ministries have not provided data that is disaggregated by sex.

The target for indicator 1.3 was not met. MoG has repeatedly struggled to achieve the output ‘Annual publication and dissemination of National Gender Status Report’. The 2011 gender status report was published in 2013, due to ongoing backlogs a decision was made to combine the 2012, 2013 and 2014 reports into one publication, the resulting 2012 – 2014 was published behind schedule in 2016. Progress on the combined 2015-2016 report has been more positive, it has been drafted and validated and is due to be printed and disseminated in September 2017. Any future support should focus on a more realistic target of a biennial report being produced on schedule.

Summary of responses to issues raised in previous annual reviews

Recommendation: Consider the possibility for additional work with new MPs and Ministers under the Gender Equality Fund and agree an appropriate end of programme logframe target.
Progress: It was agreed that UNDP has sufficient remaining budget within the main programme that would be made available to support a gender orientation of newly elected Parliamentarians and Ministers, and newly appointed Permanent Secretaries.

Recommendation: Include an output indicator reflecting the VSO component.
Progress: Done, this is now output 6.

Recommendations for future programmes

Future programmes should develop tools for monitoring the quality and content of processes rather than focusing on quantitative assessments. This should include, where appropriate, incorporating a robust evaluation to build the evidence base on what works to build institutional capacity within government to mainstream gender.

Output Title	Priority line ministries implement gender - responsive policies, planning and budgeting
Output number per LF		2	Output Score	C
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline (2012)	Target (June 2017)	Progress
2.1. Priority ministries demonstrating increased gender planning	No guidelines for gender responsible budgeting	Assessment undertaken to review line ministry programmes that are gender responsive[4]	Target moderately not met – an assessment has been undertaken but it was significantly delayed, only a preliminary report has been produced and the full findings are not yet known
2.2. % (number of line ministries) that have operationalised gender-responsive budgeting tools	11% (2 Line Ministries) have gender responsive budgets	91% (20) Line Ministries have operationalised gender responsive budgeting tools	Target not met – the assessment has not been finalised and therefore information is not available
2.3. % (number of line ministries) reflecting expenditures on gender programmes	2	68% (15) line ministries	Target not met - the assessment has not been finalised and therefore information is not available
[4] Priority Ministries: Lands, Education, Health and Agriculture

Key Points

This output relates to the MoG’s provision of targeted capacity building and support to priority sector ministries (Lands, Agriculture, Education and Health) to take forward the recommendations of sector gender audits and to develop and implement gender-responsive policy, planning and budgeting across all Ministries. The assumption is that improved gender-responsive planning and budgeting will improve opportunities and services for women and girls in the areas of land ownership, agricultural productivity, education and health.

It was initially intended that progress against output 2 indicators would be measured through analysis of the proportion of budget allocated to strategic gender activities as reflected in the national finance report. UNDP and MoG were not able to put in place a mechanism to assess this systematically, and instead it was agreed that the Zambia Institute for Policy and Research (ZIPAR) would be hired to carry out an independent assessment of line ministry progress against each indicator. The deadline of June 2017 for completion of this assessment was not met. A preliminary report has been drafted but the assessment is still not finalised.

Despite this assessment not being completed, there is evidence that the priority ministries have improved their gender responsive programming. For example, the Ministry of Agriculture has marginally improved its targeting of women in the implementation of the Farmer Input Support Programme (FISP). The number of beneficiaries increased from 16.1% female headed households in the 2008/9 season to 17.7 % in the 2013/2014 season.

In 2017, the Ministry of Education started allocating resources for procurement of sanitary pads to be distributed to girls in schools. This builds on other efforts such as the re-entry policy of girls in schools, and has contributed to an increase in school girls re-admitted after becoming pregnant, between 2011 and 2014 primary readmissions rose by 4% and secondary readmissions by 114%. The Gender Parity Ratio of girls to boys completing secondary school education improved from 0.78 to 0.82.

The programme also supported the gender audit of the Ministry of Health and the implementation of recommendations to enhance gender responsive programming.

The 2016 targets for indicators 2.2 and 2.3 were exceeded with 17 line ministries having gender-responsive budgeting and expenditure, however this information has not been subject to an assessment of the quality of budgeting and the type of expenditure and therefore this review has concluded that there is no evidence that these targets have been met. The 2018 budget circular issued to all spending departments in September 2017 included a request that Gender Focal Points form part of the budget committee within Ministries, which is an example of the change in priority being afforded to gender budgeting at the highest levels of GRZ.

Whilst the forthcoming assessment will be useful in determining the level of gender budgeting and expenditure in key ministries, and could potentially be used for future advocacy, it does not satisfy the objective of the output in relation to MoG’s enhanced coordination and monitoring of national gender initiatives.

Summary of responses to issues raised in previous annual reviews

Recommendation: UNDP and MoG to prioritise 2016 and 2017 budget analysis in advance of the Committee of Permanent Secretaries meeting and present this as an input for discussion.
Progress: The budget analysis has not been presented as it is not yet complete and the committee of permanent secretaries have not met since 2016.

Recommendation: DFID to explore with UNDP what training to new Ministers is required and whether funds can be reallocated from within the programme to support this activity.
Progress: Funds were reallocated within the programme budget to train new Ministers. The President requested to join the training, resulting in extensive security and protocol requirements that delayed the training. UNDP intend to conduct this activitiy in October 2017.

Recommendations for future programmes

Ministries of Gender (or their equivalent) are often one of the weakest or newest ministries of government. Expectations of their impact on other ministries should therefore be modest and measureable to enable monitoring of progress and reallocation of resources if necessary. Rather than setting cross-government objectives, the focus should be on building the capacity of particularly relevant or powerful line ministries (e.g. the Ministry of Education or Ministry of Finance) and strengthening their partnership with the MoG (or equivalent).

A detailed needs assessment of the relevant ministry/institution should be carried out to improve understanding of the capacity building support that is required and what is achievable with the systems and resources available. The assessment should inform programme design and ensure realistic targets are set.

DFID should increase its level of oversight and engagement with partners to ensure annual review recommendations are actioned. When these recommendations cannot be completed, there should be clear written justification and alternative actions should be proposed. Working with a government ministry with low capacity is challenging, and this requires DFID to increase its engagement and/or adopt more flexible management tools. The introduction of key performance indicators (KPIs) and/or results based financing could improve value for money and performance.

Output Title	Co-ordinated action to domesticate CEDAW and implement the Anti-GBV Act
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline (2012)	Target (June 2017)	Progress

3.1 Strategy to review and revise constitution and laws to conform to CEDAW provisions developed	Gaps in constitution and legislation identified	Gender Equity and Equality strategy developed for implementation	Target met / The strategy to implement the Gender Equity and Equality Act is being implemented. The MoG has drafted ToRs outlining the role of the MoG versus the commission, and an organisational framework for the commission has been submitted to the cabinet for approval.
3.2. % (number) of traditional leaders trained in CEDAW provisions and the Anti-GBV Act	230 gazetted traditional leaders, none trained	65% (150) traditional leaders trained	Target substantially exceeded: 270 traditional leaders have been trained (94%)
3.3 Fast track courts for cases of GBV piloted	-	Fast Track Courts evaluated and plan in place to roll out fast track courts to other districts	Target met / The evaluation of the fast track courts has been completed. Refurbishment / construction of four additional courts is ongoing, equipment has been procured and training of staff completed.
3.4 Strategy implemented to increase women’s land ownership	No strategy in place	Review gender and land strategy	Target not met / The gender and land strategy has not been agreed.

Key Points

Under this output, the MoG was expected to engage effectively with relevant legal, judicial and political bodies in order to establish a legal and regulatory framework that protects the rights of women and girls. This includes working in partnership with the Ministry of Justice to facilitate the domestication of CEDAW and the implementation of Anti-GBV Act, as well as establishing fast track courts (FTCs) to improve legal services available for GBV survivors.

Over the course of the programme MoG have drafted and consulted widely on the Gender Equity and Equality Bill, conducted advocacy meetings and trainings to support the passing of the legislation and are now implementing the strategy to operationalise the Act. A terms of reference for the roles and responsibilities of the Gender Equity and Equality Commission has been drafted and an organisational framework was submitted to Cabinet Office for approval. These documents will be fundamental to the alignment and coordination of the two institutions, and their overall success. Importantly, unlike the MoG, the Commission will have the power and authority to hold ministries to account on gender related activities.

Since 2014 270 traditional leaders have been trained in legislative frameworks for gender equality, exceeding the indicator 3.2 target of 150[5]. It is difficult to establish the overall impact of this training given the lack of data available on decisions made under customary law, but UNDP report that individual Chiefs trained under the programme have increased their land allocation to women, adopted measures to reduce child marriage in their chiefdoms, and become advocates for gender equality.
[5] The target of 150 was exceeded in 2016 (156 trained). At that point a revised target should have been agreed for the last year of the programme to capture increased ambitions in engaging with traditional leaders.

Since 2014 the programme has supported the development of a framework for the creation of fast track courts, piloting of the approach and establishing the first ever fast track courts in Africa. The roll out of 4 additional fast track courts has progressed well. Venues have been identified, equipment has been procured, staff are being trained and construction is expected to be completed in October 2017. The MoG continues to work with the MoJ, ZLDC and other stakeholders to ensure the appropriate legal framework is in place to permit the use of special equipment in trials.

Meanwhile, the evaluation of the court pilot was completed. Findings indicated that the courts were an efficient way of delivering justice for survivors of GBV, for example conventional courts took up to 2 years to hear GBV cases while the two fast track courts heard most of the cases within a month, with the longest case taking 72 days. However, before the model is scaled up a sustainability plan needs to be developed to ensure the expensive equipment that has been installed in the courts can be maintained after donor funding ends. These findings are being incorporated into the roll out plan, for example increasing the training to local court officials to ensure they are able to fully operate and maintain specialist equipment and training a broader pool of magistrates to mitigate against high staff turnover.

During the PCR meeting, the MoG Director of Planning reported that the gender and development directorate (GDD) were attending a government workshop to review the government land policy, and that a gender expert with land expertise was also attending to ensure that the new policy is gender sensitive. The programme enabled MoG to support the revision of this policy, incorporating land provisions from CEDAW, the AU and SADC gender protocols. Other notable achievements in relation to women’s land ownership have been made, as noted in the outcome section above this includes a 2017 policy directive declaring that 50% of land allocation will be to women and advocacy for greater customary land allocation to women. However, the national land policy in Zambia has faced long delays and is a highly politicised issue, whilst the workshop is a positive step towards achieving a gendered land policy; this target cannot be considered met.

Summary of responses to issues raised in previous annual reviews

Recommendation: Incorporate UNDP’s Fast Track Court outcome indicator into the DFID logframe, including data on performance measured by throughput of cases.
Progress: The fast track court indicator was added in 2017 but there is no additional indicator to measure performance by throughput of cases.

Recommendation: UNDP and MoG to ensure findings of evaluation on Fast Track Courts are widely disseminated, in Zambia and internationally, to inform best practice and future roll out of fast track courts in the next 4 provinces
Progress: The evaluation report has been completed however it has not been disseminated. Printing and dissemination to direct stakeholders has begun, formal dissemination at provincial level is expected to take place in October and November to coincide with the launch of new courts and 16 Days of Activism.

Recommendations for future programmes

As recommended in the evaluation of the fast track courts, future programmes that fund improved legal services for GBV victims and survivors should develop a sustainability plan to ensure the procurement and maintenance of any infrastructure and equipment can continue after donor funding ends.
To avoid legal challenges, programmes should also ensure that this equipment and infrastructure is appropriate and orientated to the rules of court, or seek to revise these rules where they are not aligned.

Output Title	Communication Strategy promotes positive gender norms and increased awareness of laws
Output number per LF		4	Output Score	C
Risk:		Minor	Impact weighting (%):	5
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes – following 2016 and 2017 annual review recommendations this weighting was reduced from 20%

Indicator(s)	Baseline (2012)	Target (June 2017)	Progress
4.1 Number of radio programmes produced on community and commercial radio stations (cumulative)	70	No target set as the activities were suspended pending development of the new communications strategy	Original programme target (350) exceeded: 509
4.2 Number of TV programmes on gender equality produced / and aired (cumulative)	25		Original programme target (125) not met: 101
4.3. Number of journalists trained in gender/child responsive reporting (per annum)	0		The milestone of 60 journalists trained up until 2016 was met with 76 trained.
4.4 Film dealing with gender equality issues produced and aired	0		Two films and a TV series were produced and aired.
4.5 National Gender Perception Surveys conducted and disseminated and feed into gender strategy		Assessment of the gender strategy conducted and action plan developed	Target not met: / The review of the National Gender Strategic Plan began in June 2017.

Key Points

In 2015/16 a MoG review revealed that communications activities under a number of programmes were not fully aligned and risked overlap and duplication of effort. The Programme Implementation Technical Committee (PITC) agreed in 2016 to suspend activities under 4.1 – 4.4 whilst the MoG communication strategy was being reviewed and a new strategy developed.

Despite repeated recommendations from DFID for the MoG and UNDP to accelerate progress, a communication strategy has not been developed. Procurement regulations within UNDP hindered the original contracting of a consultant to support this activity, but this issue was resolved in early 2017 and there has still been limited progress. At the time of this review, the MoG Director of Planning reported that a consultant had been hired and is undertaking scoping activities including stakeholder consultation; however drafting of the strategy has not yet begun.

In the period prior to suspension of communications activities, milestones related to training of journalists, production of radio and TV shows and films had been met. An independent assessment of their impact has not been commissioned, and therefore it is not possible to attribute changes in attitude to these activities. The National Gender Perception Survey finalised in 2016 did demonstrate a positive change in attitudes, and it can be assumed that the widespread dissemination of communications material may have had at least a small effect on this shift.

The target for Indicator 4.5 refers to the National Gender Strategy, however milestones over the course of the programme have related to the production and dissemination of the National Gender Perception Survey. A review of the national gender strategy began with an inception meeting in June 2017, the review is expected to be completed in October 2017 and an action plan will then be developed.

Summary of responses to issues raised in previous annual reviews

Recommendation: UNDP to closely monitor the development of the communications strategy and ensure it stays on track (June 2017)
Progress: A consultant has been hired and is undertaking scoping activities. Drafting of the strategy has not yet begun.

Recommendation: MoG to organise a validation workshop for the National Gender Perception Survey and disseminate the report (March 2017)
Progress: Validation of the survey has taken place but printing and dissemination has not yet started.

Recommendation: MoG to convene a meeting with the Cooperating Partner’s Gender group to review the final communication strategy and encourage greater coordination amongst donors seeking to support the MoG (July 2017)
Progress: As above, the communiation strategy has been delayed and therefore this meeting has not taken place.

Recommendations for future programmes

DFID should ensure all future logframes are regularly reviewed to ensure metrics continue to measure the output indicator, and that outputs remained aligned to the programme theory of change.

Output Title	Strategy to increase women’s representation in decision making positions implemented
Output number per LF		5	Output Score	B
Risk:		Minor	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator	Baseline (2012)	Target (June 2017)	Progress
5.1 Committee of Permanent Secretaries implementing the strategy to engender the public service	-	Evaluation of the implementation of the strategy takes place and lessons learned highlighted in evaluation report	Target not met. / MoG developed a Terms of Reference for the review of the strategy to engender the public service, have met with PSMD and received initial data on women in public service.
5.2 Number of parliamentarians sensitised on the 50/50 SADC Protocol (cumulative)	50	150 cumulative	Target moderately not met. 143 parliamentarians were trained; however additional training is scheduled to take place once Parliament starts sitting again in mid-September.
5.3 Campaign to increase votes for women takes place	-	2016 target - Launch the 2016 vote for women campaign & implementation of some key activities	Target met / The Count Her in Strategy was launched with accompanying advocacy and communications events. / No 2017 target as there was no election.

Key Points

This output aimed to increase women`s participation in senior leadership positions in politics and public service by supporting the MoG to engage with senior civil servants to develop a gender strategy for the public service. This involved working with political parties and the public service to increase the adoption and election of women candidates, and with relevant parliamentary structures to increase knowledge on gender related issues.

Under this indicator, a key achievement was the creation of the committee of Permanent Secretaries which met annually until the 2016 election, and was chaired by the Secretary to the Cabinet. Through this Committee the strategy to engender the public service was adopted leading to the development of the ‘Gender Equality Seal Certification Programme in the Public Service[6]’. This was a strong indication of political commitment and senior civil servant leadership to engender the public service, however since the 2016 elections this committee has not met. MoG has written to the Secretary to the Cabinet requesting that the Committee is reconvened, but at the time of writing this meeting has not been scheduled.
[6] The certification programme aims to reduce gender inequalities in the work place, promote good labour practices and strengthen the oversight role of the Ministry of Gender.

MoG developed a terms of reference for evaluating the Committee and strategy, and this activity was included in the 2017 workplan, however as the 7NDP gained momentum UNDP and MoG decided to prioritise forward looking work, engaging the Ministry of National Development Planning to develop a conceptual framework for monitoring gender across Cluster Advisory Groups. As a result the evaluation of the strategy to engender the public service was delayed.

The MoG made significant progress against output 5.2. By February 2017, 143 parliamentarians had been sensitised to the 50/50 the Southern African Development Community (SADC) protocol on gender and development, just below the target of 150. DFID agreed for UNDP to use unspent funds to train new Ministers and MPs elected following the 2016 general elections. The training for MPs is due to take place once Parliament is back in session. The President has requested to attend the Ministerial training, which is a significant achievement for the programme but has also caused delays due to scheduling, logistics and security requirements. A venue for the Ministerial training has now been agreed and is likely to take place in October. This will provide the opportunity to update officials on the amendments that were made to SADC protocol to ensure it is aligned to the Sustainable Development Goals (SDGs).

Summary of responses to issues raised in previous annual reviews

Recommendation: UNDP to support MoG in continuing to gather lessons about the work of the Committee of Permanent Secretaries and feed this into future workstreams and ensure the evaluation of the strategy to engender the public service is completed on schedule.
Progress: The evaluation has been delayed although initial engagement with PSMD demonstrates that MoG and UNDP are beginning to gather lessons about the engendering of the public service.

Recommendation: UNDP to document the experience of the Committee of Permanent Secretaries as an example of good practice for high level commitment to gender.
Progress: No evidence has been provided that the work of the committee is being monitored, recorded or shared.

Recommendation: UNDP to coordinate with other UN agencies supporting training of Parliamentarians on SADC protocols to ensure coherence and cost-effectiveness of training.
Progress: Given the interest of the President in this specific training, and the related security and diary issues, it was not possible to combine multiple trainings.

Output Title	Increased institutional and staff capacity to plan and manage information and results based management systems.
Output number per LF		6	Output Score	C
Risk:		Minor	Impact weighting (%):	15
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes [new output agreed in Feb 2017]

Indicator	Baseline (2015)	Target (June 2017)	Progress
6.1 High quality information available for the results Based Management System on Ministry of Gender, National Gender Policy (NGP) and National Child Policy	No system functioning	Capacity building of staff in relation to Gender Information Management System	Target not met / Appropriate metrics were not developed to measure capacity building and therefore this target is not met.
6.2 Improved planning, coordination and documentation of gender and child development programmes	No assessment of the Department of Information and Planning	Transition: testing – trainings and corrections	Target not met / Metrics were not developed to measure achievement of this output and the 2017 milestone is not measureable.

Key Points

This output aims to monitor progress of the Gender Institutional Strengthening Support Project (GISSP) implemented by Voluntary Services Oversees (VSO). This project aimed to strengthen the capacity of the MoG and its staff with provision of technical expertise, training, research, mentoring, and other capacity-building initiatives, as well as systems development. This was to be provided through the deployment of three volunteer advisors in the areas of: Results Based Management Systems (RBMS); Management Information Systems (MIS); and Planning. These advisors were based at the Ministry.

Reporting the exact achievements of the GISSP and measuring success against milestone targets has been difficult. Whilst DFID met with VSO regularly throughout the programme period, the GISSP output was not included in the programme logframe until after the 2017 annual review period. This meant that there was limited evidence available for analysis of this component of the programme.

The project was able to support the MoG to strengthen routine operations, for example facilitating the greater sharing of information and work planning and developing monitoring and evaluation guidance for MoG staff to use when undertaking field visits. The project also conducted an analysis of MoG’s planning model and developed a strategy to improve the planning department. It is important to note that VSO and MoG agree the project achieved more in the first six months when contracted local consultants were in place rather than volunteers. This brings into question the added value of the volunteer model in such circumstances.

As part of this PCR, the team met with VSO, the IT volunteer and the MoG director of planning. These meetings suggested that the GISSP did not achieve its intended objectives due to a wide range of challenges including:
- poor induction of volunteers to the ministry and lack of engagement of ministry staff with the volunteers due to poor initial involvement and high staff turnover.
- lack of resources allocated to the project within the MoG prevented implementation of strategies and plans developed by the volunteers.
- withholding of information and lack of access to internal systems from volunteers by ministry staff due to the competition between staff
- a requirement of volunteers to gap fill (e.g. attend meetings on behalf of the ministry and proof read) rather than carry out GISSP objectives
- the overlap between volunteer objectives and those of the newly launched World Bank Girls Education, Women Empowerment and Livelihoods (GEWEL), which included a component on institutional strengthening and systems building for the MoG

Summary of responses to issues raised in previous annual reviews

Recommendation: to incorporate an output for the GISSP.
Progress: a new output has been incorporated; however metrics were not clearly defined and as a result of this and the lack of evidence provided it has not been possible to score progress.

Recommendations for future programmes

DFID Zambia need to ensure that logframes remain aligned to the programme ToC and measure all activities that they believed are sufficient and necessary to achieve outcome targets.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The total spend on this programme has been £2,348,815.28 broken down as follows:

- Direct Support for the implementation of PPPWCR: £2,002,154
- Gender Equality Fund: £152,315
- GISSP: £94,385

An additional £99,960 was spent on designing the programme, the mid-term evaluation and one year of a DFID adviser overseeing the programme implementation.

A VfM framework covering the UNDP activities (direct support for PPPWCR and the GEF) was developed in 2014 and reported against in 2015 and 2016. This was then reviewed and a new framework agreed in July 2016 which has been reported against in August 2017. The framework tracks the 3 key items of expenditure (on training, media, and fast track courts) along the 3Es of Economy (both cost and quality), Efficiency and Effectiveness.

There were a number of attempts to improve economy over the course of the programme, for example the decision to pay direct costs for residential training rather than provide Daily Subsistence Allowance (DSA) and holding trainings in Lusaka to minimise costs. This was a difficult decision to implement, and caused strain on the relationship between UNDP and MoG, but was necessary to reduce the costs of the training and promote greater sustainability.

However, reporting on the ‘higher level’ Es such as the efficiency and effectiveness of training and media efforts by tracking their impact proved difficult as indicators were agreed after the majority of those activities took place. The final evaluation (October 2017) may be able to provide additional evidence.

Economy
VFM measure	Indicators	2017 update
A. Costs: / Does the programme achieve good prices and low costs in procurement? / Admin cost vs programme cost / B. Quality: / Media / Training / Fast track courts	Evidence of competitive bidding in the procurement of media, training and fast track court equipment / Number of audit findings raised on recruitment of consultants / % of budget /expenditure spent on administration. / Are the best formats used to reach the most people? Evidence of considering campaign reach in procurement decisions. / % of trainees who said training was good. Target: 80% / Evidence of decision making by UNDP on location of fast track courts of where needs are high.	UNDP procured the Fast Track Court Equipment under a Long Term Agreement (LTA). The LTA was obtained competitively across the UN, enabling PPPWCR to benefit from a bulk contract negotiation. There was no procurement for media in 2017. / The 2016 audit did not raise any issues on the recruitment of consultants / 13.8% (reduced from 15% last year) / According to the findings of the gender perception survey the majority of people preferred the radio as a means of information dissemination followed by television. This reflects the majority of activities and preferred channels used by the programme. / No trainings were undertaken in 2017 / The selection of the Fast Track Courts is based on the incidence of GBV cases, in particular cases of defilement, as per Zambia Police Reports

Throughout the programme consultancies for trainings have been a large cost driver. This was not the case in the final 18 months of the programme as the GEF closed in March 2016. UNDP did secure some savings over time, for example the unit cost per person trained fell from £764 in 2014 to £714 in 2015 through efforts to concentrate more training in Lusaka. Training reports and anecdotal evidence from MoG staff indicate that the training was highly beneficial, deepening their gender knowledge, increasing their ability to work as a team and improving senior management’s leadership skills. Gender focal points also reported to the review team that the training received was useful, however the recommendation to ascertain the impact of trainings will be taken forward in the end of project evaluation in October, and therefore cannot yet be reported on.

UNDP was able to reduce costs on several activities through the use of consultants or vendors with Long Term Agreements (LTA), and therefore benefit from lower rates negotiated on the basis of high volumes of procurement. This is particularly beneficial to PPPWCR, a relatively small programme, as it can leverage savings generated from UNDP’s much larger procurement programmes.

Administration costs for UNDP the programme fell over successive years, from 18% in 2015 to 15% in 2016 and 13.8% for the year to date. The final figure for 2017 will not be known until UNDP close out the remainder of their programme in December.

For VSO the key cost driver was volunteer allowances, travel and accommodation. These were set at the outset of the programme and are lower than similarly qualified staff salaries.

Efficiency
Media / Training / Fast track courts	Cost per person reached through media channel / Number of line ministries applying Gender responsive budgeting tools. Target: 20 / % of cases adjudicated within 30 working days.	No media programs implemented in 2017 / 17 (2016 achievement, exceeding the 2016 target of 15 line ministries) / 73%

Whilst no media programmes were produced in the last 18 months of the programme, reports from 2015 estimated that MoG was achieving cost-efficiency through media work, selecting the right channels of communication to achieve costs per person reached ranging from to $0.03 on community radio, $0.15 for community theatre and $1.42 in print media.

The final number of line ministries applying gender responsive budgeting is not yet known, pending the assessment discussed above under Output 2. In 2016 this target had been exceeded, demonstrating some positive evidence of efficiency.

Effectiveness
Cross cutting measures / Training	i). Increase in number of Zambians that attach equal importance to both men and women. / ii).Evidence from the end term evaluation on impact of training	Increased from 48.4% to 67% / The evaluation will take place in October 2017

The evaluation of the fast track courts found that they had significantly increased throughput of cases, increasing judicial efficiency and improving access to justice for vulnerable women and children. The longest case in the fast track courts took 72 days, which compares favourably to other courts where cases have gone beyond 2 years before adjudication. The conclusion of the evaluation was that FTCs are an effective way of delivering justice for survivors of GBV and should be scaled up across the country.

Unfortunately there is not currently any data to demonstrate whether the training has been effective, however this will be determined by an evaluation planned for October 2017.

Equity
The programme has gender equity at its core, as evidenced by the gender inequality index and National Gender Perception Survey – the programme has contributed to reduced inequality. During programme implementation, equity was prioritised through communications activities, with channels chosen to ensure outreach to more marginalised communities, particularly rural women.

VfM performance compared to the original VfM proposition in the business case

The business case did not include VfM indicators, but noted that there is limited evidence on the economic benefits of this type of investment for gender equality and women’s empowerment. It assumed that the benefits would justify the costs based on the likelihood of increased capacity of GRZ institutions to engage on gender issues, the medium to long-term impact on the Gender Inequality Index and the potential for an initial DFID investment to leverage additional resources, particularly additional interest from other CPs.

Assessed against these criteria the programme has delivered as expected – with a positive impact on the Gender Inequality Index and additional resources flowing to the MoG. There is also strong anecdotal evidence to suggest that GRZ institutions are more equipped and willing to engage on gender issues.

Unfortunately this programme has not contributed to addressing a core issue set out in the original VfM proposition – the limited evidence on the economic benefits of this type of programme. Future programmes should build this in from design, with a strong VfM monitoring framework to enable a more robust assessment of programme costs and benefits in the future.

Assessment of whether the programme represented value for money

Performance against VfM measures
The programme has generally performed well against the VfM measures set, with evidence of improved economy in procurement and delivery of training, reduced administrative costs, and improved efficiency and effectiveness in providing access to justice for vulnerable women and children. However, the lack of clear targets for VfM indicators and the lack of evidence about the impact of training has prevented a full assessment of whether this training was an efficient or effective way of increasing capacity within the MoG and other line ministries. The programme has not fully met its output or outcome targets, and therefore it as been a slightly less efficient and effective programme than originally envisioned.

Results

The programme has exceeded targets on its two impact indicators, and whilst none of the outcome targets have been met there has been significant progress on legislative equality, with a positive trajectory on land allocation and very strong steps to improve access to justice for survivors of GBV. The programme has demonstrated its effectiveness in influencing legislative reform, engaging on the revision of more pieces of legislation than planned. As a result of capacity building and institutional strengthening funded through the programme, there is at least a perception that MoG’s capacity has improved greatly, however there is not yet robust evidence to support this.

Theory of Change
An assessment of the theory of change is included in the monitoring section below. In summary, this theory assumed that only government is able to bring about the policy, legislative and economic change to address structural barriers to gender equality, increased MoG capacity will enable them to provide effective leadership and coordination and build the capacity of other ministries, and funding and technical assistance will increase MoG`s capacity.

At this stage the available data suggests that supporting the MoG has resulted in significant policy and legislative reforms, and increasing land allocation does indicate the beginnings of some economic change. There is insufficient evidence to determine whether training did increase MoG’s capacity, however stakeholders spoken to during this review stated that capcity had increased over the course of the project.

Whilst not a direct objective of the programme, DFID support has enabled the MoG to leverage support from other donors. When the programme began, DFID and UNDP were the only donors providing support to the MoG, and the end of this review Sweden, Ireland, USAID and the World Bank are all provided supporting, with the EU and GIZ expected to begin supporting them soon.

This programme has contributed to reduced gender inequality in Zambia, and these results still justify the costs of the programme and it has represented good value for money. However, this could have been improved through the refocusing of the programme in areas where there was greater traction.

Recommendations for future programmes

When programmes change focus or add new components and activities, DFID should ensure that VfM indicators and targets are also updated to cover all key activities and steps in the theory of change. These should be discussed with implementing partners and reported on a regular basis.

DFID Zambia should work with UNDP to ensure that the evaluation terms of reference includes assessing the effectiveness of training undertaken during the programme..

Quality of financial management during programme

Financial management has been strong throughout the programme, with the risk of funds not being used as intended considered low as both UNDP and VSO had strong financial management systems.

Funds were disbursed to UNDP 6-monthly in advance, through a Contribution Arrangement. VSO received payments on a quarterly reimbursable basis, through an Accountable Grant. Forecast management was generally strong in both partners, with the exception of the first half of 2016 when delays in agreeing the workplan followed by national elections resulted in an underspend by UNDP.

However, with the delayed implementation of some activites in UNDP there has been an underspend in the last months of the programme. With UNDP support for MoG continuing until December 2017, the final closure of accounts and retiring of DFID funds will be completed in early 2018.

All activities with VSO have been completed and their reporting indicates an underspend of £369. The final disbursement will be made less the indicated underspend.

Date of last narrative financial report	UNDP: 31/08/17 / VSO: 04/08/17
Date of last audited annual statement	UNDP: 10/06/16

E: RISK

Quality of risk management over the life of the programme

The risk rating for the majority of the programme was low/minor. This was raised to moderate in March 2016 in anticipation of the Zambian General Election. This was lowered after election was complete and MoG was able to refocus on programme delivery, however in February 2017 the risk was again increased to moderate reflecting an increased delivery risk, with UNDP and the MoG having been unable to complete a number of processes to schedule.

This delivery risk was realised, and subsequently managed through increased engagement with UNDP and MoG, including regular meetings to update on the progress of a prioritised action plan. These meetings did improve communication, and programme delivery has improved, but not sufficiently to get back on track with expected outputs.

The risk of an increasing number of donors allocating funding for different programmes was highlighted in 2015, causing concern risk that MoG would be overwhelmed and therefore not be able to deliver on the PPPWCR commitments. DFID has worked with other donors through the CP Gender group to encourage a more coordinated approach to support. This has been somewhat successful, with increased engagement between CPs and leadership within the MoG, but it has not been sufficient enough to refocus MoG on its core mandate of coordination and advocacy.

The main risks for the programme are summarised below.

		Impact
		Insignificant	Minor	Moderate	Major	Severe
Likelihood	Almost Certain
	Likely				6. Delays in implementing activities reduce effectiveness and sustainability of the programme
	Possible			1. Understaffing and lack of capacity in MoG 3. Priority ministries not demonstrating increased gender planning and budgeting

	Unlikely			2. Traditional leaders resistant to social norms change / 4. Political interference / 5. Corruption and fraud
	Rare

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The programme has fallen behind the planned timeframe for a number of outputs. Activities were often delayed, and even with increased oversight in the final stages of the programme a number of deadlines were missed, with workshops and consultancies being cancelled or postponed.

UNDP will be continuing their support to MoG through PPPWCR until December 2017, and there is a possibility that a number of outstanding activities will be completed during this time, however these will still be substantially delayed.

The Gender Equity Fund performed well against its timeframe, exceeding the scope of its activities on schedule. This was a much more demand driven fund, and the support provided was rated very highly from MoG staff. This can provide lessons for future provision of technical assistance, particularly the need to align with institutional priorities and incentives.

Performance of partnership

DFID maintained a good working relationship with MoG, UNDP and VSO. However, with both MoG and VSO very high levels of staff turnover reduced the quality of the partnership, with new relationships having to be established and a loss of institutional memory, momentum and programme support.

The relationship with UNDP is strong both bilaterally and through engagement with the CP Gender group. They are a responsive partner, but the lack of a dedicated member of staff implementing PPPWCR did lead to delays.

The relationship between UNDP and MoG suffered a setback in the middle of programme implementation. This was related to personality clashes in the two organisations, and was overcome when the programme lead in MoG was changed, however this did cause further delays to the programme. DFID intervened to establish the cause of the conflict and to mediate between the partners, however in future programmes this should be done earlier to avoid escalation.

Asset disposal and value obtained by DFID

The programme purchased one vehicle and some office equipment. UNDP maintains an asset register, the vehicle is based at the MoG and log books are maintained and reviewed to monitor its use. It is proposed that these assets are handed over to the MoG for their continued use after the programme closure. A submission and request from MoG will be submitted to the Head of Office in October to formalise the transfer of assets.

G: CONDITIONALITY

Partnership principles assessment

Whilst this programme did not provide direct financial aid, it worked very closely with MoG and provided financial and technical assistance through UNDP. DFID’s relationship with GRZ is assessed against continued commitment to four partnership principles. These principles are assessed at least annually and the last assessment was last conducted in January 2017.

The assessment specifically looked at gender, and concluded that whilst gender inequality remains high, there have been signs of progress with the passing of legislation and Zambia taking a leading role within the African Union on the need to end child marriage.

Commitment to poverty reduction and the Sustainable Development Goals (SDGs):
In general, policies on poverty reduction and basic service provision have not been supported by consistent funding by GRZ. Overall, social sector spending has appeared a relatively low priority of past governments, but modest signs of pro-poor investment observed in recent years in the increasing government support to the scale up of Social Cash Transfers have been confirmed.

Commitment to human rights and other international obligations:
There is a general commitment to human rights; however this is not applied consistently. Whilst civil and political rights have previously been largely respected, in the run-up to the general election in August 2016 the opposition faced significant challenges in exercising its freedoms of assembly and expression.

Commitment to strengthening public financial management:
Commitment to strengthen financial management and accountability is moderate. It has been weak on tackling the budget’s lack of credibility; though the new Government’s bold economic reform programme could signal a shift. There is some commitment to fight administrative corruption but few examples of successful sanctions against senior political figures.

Commitment to strengthening domestic accountability:
Commitment to domestic accountability is moderate. Elections have been largely credible and civil society operates freely, but the media is largely state-controlled (even if not state-owned) and there is little scope for dissenting views. Online and social media is more diverse. Outside of elections there are few effective mechanisms to hold government to account.

H: MONITORING & EVALUATION

Evidence and evaluation

Despite providing valuable insights and recommendations to help shape and improve the programme, the PPPWCR mid-term evaluation was a review rather than an evaluation and therefore was not able to generate rigorous evidence about what works to deliver this type of programme. In order build the evidence base, a robust evaluation should be embedded into future programmes.

The PPPWCR theory of change assumed that the programme outputs would provide an enabling environment for the legal, political, economic and social empowerment of women which in turn would contribute to the impact of reduced gender inequality in Zambia. The original assumptions underpinning this causal chain included:

1. Only government is able to bring about the policy, legislative and economic change to address structural barriers to gender equality.
2. Only government is able to ensure that sector ministries deliver gender responsive programmes
3. Changing deeply entrenched social norms takes time and will require the MoG to work with a wide range of partners, including civil society, the media, and traditional and religious leaders. A communication strategy will be central to this.
4. Funding and technical assistance will increase MoG`s capacity
5. Increased MoG capacity will enable MoG to provide effective leadership and coordination, build capacity of other ministries, civil society and the media to address gender issues, and ensure effective oversight, M & E and reporting of gender equality action.

Without a rigorous evaluation, it is not possible to say confidently whether these assumptions were supported by the results of this programme; however the data collected and reviewed during the PCR process suggest:
- Assumption 1 is supported by the results of this programme; supporting the MoG to lead on legislative and policy change resulted in major legal reforms including the domestication of CEDAW, and one of the main reasons that the GISSP failed to build sustainable capacity was due to the lack of buy in, support and leadership from the MoG.
- Assumption 2 is supported by the findings of this review, however the word ‘government’ should be changed. The PPPWCR demonstrated that some ministries (e.g. the MoG) do not have the power or influence to drive changes across government. An alternative assumption for future programmes is: ‘Only line ministries themselves or senior government officials (PS`, Ministers, the President) are able to ensure that their ministry delivers gender responsive programmes’.
- Assumptions 3 cannot be assessed as the communication strategy was not developed and in-depth evidence on social norm change is not available.
- There is insufficient evidence to determine whether assumption 4 remains justified, however, anecdotal evidence reported by stakeholders consulted as part of the PCR suggests that the MoG’s capacity did increase over the course of the project. The fact that the MoG has been able to attract additional donor financing in the last two years also suggests there is an impression of increased capacity to manage resources.
- There is some evidence that assumption 5 remains justified, as evidenced by the increased discourse and leadership on gender observed within the MoG, and at PS and parliamentary level. The lack of progress made on the communication strategy and coordination with other line ministries suggests that the level of capacity building provided through the programme was insufficient to overcome competing priorities and build systematic change.

Monitoring progress throughout the programme

A Programme Implementation Technical Committee (PITC), chaired by the Permanent Secretary of the Ministry of Gender is responsible for oversight of the PPPWCR. The PITC comprises DFID, UNDP, PS MoG, Directors and Deputy Directors from MoG, Central Statistics Office, Zambia Police Victim Support Unit, National Assembly, representatives from priority line ministries and also includes Civil Society Organisations and NGOs working in the Gender Sector.

The PITC is supposed to meet on a quarterly basis to review progress, determine the strategic direction of the programme, and ensure a focus on results, however, the PITC last met in October 2016. A meeting was scheduled for February 2017 to approve the annual workplan, however due to competing pressures the MoG consulted PITC members electronically and approved the workplan without a physical meeting. The second quarter meeting was repeatedly postponed due MoG and UNDP engagement in the 7NDP development. This was rescheduled for August but was again cancelled due to competing commitments amongst partners. It is now unlikely to take place before October 2017. DFID, UNDP and MoG have held several meetings to discuss progress over the last year, but the failure to hold a formal PITC is a demonstration of the competing demands of the MoG and the lack of prioritisation given to PPPWCR.

MoG submits quarterly progress reports to UNDP, who submit annual reports to DFID. The UNDP reports provide an update against their annual work plan and their DFID logframe targets. In addition, DFID had met with UNDP quarterly in advance of the PITC meeting to monitor progress towards expected results and since March 2017 has met with them monthly. These reports are useful in monitoring programme activities but are not fully aligned to DFID’s logframe. In future, a clearer reporting template and monitoring framework would strengthen oversight and ensure incentives are aligned with implementing partners.

VSO submits a quarterly report to DFID, reporting against their quarterly workplan. The quality of these reports has not been sufficient to monitor progress and this is linked to a lack of clear, measurable outputs and an agreed methodology to measure success. It is essential that in future programmes DFID agree a clear monitoring framework with all implementing partners, especially when activities or components are added later in the programme lifecycle.

The Annual Review was jointly conducted by a Social Development Advisor from the Health Research Team, the PPPWCR SRO, and the DFID Zambia Social Development Adviser. As outlined in the PCR ToRs, the review process included:
- Meeting with representatives from the MoG, other line ministries, ZLDC, UNDP and VSO, including the volunteers deployed within the Ministry, to try and collect evidence of programme progress, successes and challenges that could generate learning for future programmes.
- Visiting the Kabwe Fast Track Court and meeting with the magistrates and prosecutors working there.
- Carrying out a desk based review of key programme outputs and monitoring documents (such as annual and quarterly partner reports, DFID annual reviews, the gender perception survey, the JPGBV Fast Track Court evaluation, and the 2014-15 national gender status report) .