Annual Review - Summary Sheet

Title: Kenya Extractives Programme (K-EXPRO)
Programme Value: / Initial: £24,000,000 / After the 2017 Portfolio Quality Review (PQR): £6,355,450		Review Date: September 2017
Programme Code: 204339	Start Date: 30/09/2015	End Date: / Initial: 31 March 2020 / Post PQR: 31 October 2018

Summary of Programme Performance
Year	2016	2017
Programme Score	B	A
Risk Rating	Major	Major

This is the second annual review of K-EXPRO. Since the first annual review, a DFID-wide Portfolio Quality Review (PQR) process resulted in K-EXPRO being reduced in size and scope from £24m to approximately £6.35m. The PQR process happened at a point when the project’s inception phase was ongoing and hence a two month extension of the inception phase was granted to adapt the inception findings to the PQR outcome. The key strategic implication of the PQR outcome was the reorientation of the programme away from mining to focus more on oil (as well as gas to a lesser extent) and with a clear focus on northern Kenya. K-EXPRO is implemented by:
1. A consortium led by Oxford Policy Management (OPM) which manages grants and technical support to government institutions and non-state actors (including Strathmore University), as well as provides a coordination role across the programme implementing partners.
2. The World Bank which implements a multi-donor trust fund – the Kenya Petroleum Technical Assistance Project (KEPTAP) – which is supported in part by K-EXPRO.
3. The UNDP which, for the past year, has run an advisory facility to the Ministry of Mining supported by K-EXPRO (although next year, in the final year of the programme, the remainder of the advisory facility will be managed by OPM instead).

Summary of progress since last review
The programme is on track, delivering against outputs in a revised logframe reflecting the reduced size and scope of the programme. The last 12 months mainly featured the programme’s inception phase (November 2016 to June 2017) and implementation began in July 2017 in the run up to the Presidential election in Kenya. Some key achievements this year organized by the three logframe outputs include:
1. Increased capacity of local businesses to benefit from supply chain opportunities linked to the emerging oil and gas sector
  1. Undertaking supply/demand gap analysis to determine priority sub-sectors for Small and Medium Enterprise (SME) support from the World Bank implemented Petroleum Business Opportunities (PBO) initiative.[1]
    [1] Priority sub-sectors for support from the PBO over the next year include: (1) civil engineering and construction; (2) cement production; (3) maintenance – mechanical and electrical; (4) well services; and (5) steel manufacturing.
  2. The first of a number of ‘local content exchanges’ were carried out to raise awareness and interest amongst local businesses, oil executives and policy makers on the challenges and opportunities for Kenya in building local supply chains. The events were well received and publicised through briefing notes disseminated in local print and on social media.
  3. A Joint Ventures and Strategic Partnerships training was organised for local businesses by the World Bank, with K-EXPRO and industry funding (Africa Oil and Tullow Oil). This was supplemented by a Business-to Business networking event in Nairobi where international oil companies met with local companies wishing to do business with the sector.
2. Increased county and community level influence on policy, systems and practice to reduce conflict and investment risk in oil and gas sector
  1. Undertaking two Political Economy Analyses (PEAs) during inception that have been fundamental to scoping out issues and identifying suitable projects and partners to work with at the county and community level. Particularly important when engaging stakeholders in Turkana has been trying to understand local power dynamics and how decisions are made.
  2. The Extractives Baraza delivered two ‘fireside’ chats with key policymakers, industry and civil society in Nairobi to discuss pertinent issues in the extractives sector as a mechanism to raising county and community issues at a National policy level.
  3. International Alert were supported to publish a paper to bring attention to conflict risks and extractives and the impacts on communities in Kenya.
3. Improved policy, systems and practice at the national level through coordinated extractive sector support
  1. The Ministry of Mining was able to finalise a number of key regulations required by the Mining Act 2016 and start putting into effect the legislative changes, including policy advice on formalising Artisanal and Small Scale Mining, and helping set up the Mineral Rights Board.
  2. Significant progress was made by the British Geological Survey (BGS) technical support to the Ministry of Mining’s Directorate of Geological Survey towards the establishment of the National Geodata Centre with funding through DFID’s GREAT for Partnerships Centrally Managed Programme (CMP).
  3. Civil society efforts to raise interest in addressing oversight challenges in extractives sector governance were supported through two Extractive Sector Forums and with the Extractives Baraza developing a ‘Transparency Scorecard’ for Kenya.

This past year of inception (nine months) and implementation (three months) has been critical in laying the foundations supporting reform of the sector and pathways to build stronger institutions over the next full year of implementation. With a strong focus on sustaining the efforts of local delivery partners, many of these initiatives will be handed over to others, phased out or wrapped up upon completion, during the course of the next (and final) year of K-EXPRO.

Summary of lessons learnt since last review
1. The PQR process has been challenging – both in terms of transaction costs for DFID as well as challenges for each of our implementing partners. Proactively managing key stakeholders was instrumental for managing risks associated with the PQR process and for the effective design of residual programme activities. Permitting a short inception phase extension in order to re-focus activities prior to implementation helped the team more easily adapt to the PQR outcome.
2. Through a partnership with the World Bank, DFID has also been able to capitalise on their convening power and so maintain a significant degree of influence despite the reduction in the scale of K-EXPRO.
3. The contested, and currently ongoing, Presidential election is likely to further increase the complexity of political dynamics concerning oil in northern Kenya. Regular and applied political economy analysis at both the national and county levels will be critical in informing and helping activities to adapt during the remainder of the programme.

Summary of recommendations for the next year
1. With the programme ending in October 2018, put in place (as a matter of urgency) clear sustainability or exit plans to ensure a smooth transition. This will include exploring financial sustainability options for the Extractives Baraza website run by Strathmore University.
2. Focus efforts on ensuring the uptake of knowledge/materials generated through the programme translate into positive contributions to policy, systems and practice.
3. As the advisory facility to the Ministry of Mining is being transitioned from UNDP to OPM, and phased out by March 2018, there is ever greater need for the advisers to develop clear transition plans and strengthen competency transfer.
4. Continue strong engagement between the K-EXPRO project delivery team and the DFID Centrally Managed Programmes (CMPs)[2] to ensure a clear understanding of the K-EXPRO support role in their projects’ execution and collaborative engagement with Government.
  [2] Comprising: 1. Sills for Oil and Gas (SOGA); 2. Releasing the Transformational Potential of Extractives for Economic Development Programme (RTPEED), 3. GREAT for Partnership; Africa Legal Support Facility (ALSF); and 5. East Africa Research Facility (EARF).
5. Continue conducting regular political economy analyses for timely safeguards to be instituted where necessary during the next delivery cycle.
A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204339/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204339/documents

K-EXPRO was originally designed to comprehensively focus on emerging petroleum and mining industries in Kenya by providing four main forms of support:
1. Support to build institutional capacity within national and county level government institutions, with transparency, accountability and environmental protection as priorities.
2. Support to organisations at the national level to advocate for a better business environment in the extractives sector.
3. Support to enhance county level dialogue and local development discussions, including with women and youth.
4. Support to promote a pragmatic approach to “local content”[3], by focusing on the capacity of the domestic private sector to capture foreign direct investment related to extractives.
  [3] The share of inputs in the production process (jobs, materials, equipment, capital) that come from local sources rather than being imported, i.e. the share of the investment that boosts local economic development

A fifth component was to provide regular updates on stakeholders involved in the extractives industries where political and economic sensitivities are extremely high. The component would provide insights to adapt the programme, reduce risks and maximise results.

The programme however experienced significant change in May 2017 during the DFID Portfolio Quality Review (PQR) process which resulted in a major reduction of scope, timeframe and programme value. The programme will now be delivered in a period of 15 months down from four years and funding reduced to approximately £6.35m, approximately 75% less than the funding originally approved for the project in 2015. Although particularly challenging, both for DFID and its partners, the PQR process happened when the project’s inception phase was still being carried out and so a short two month extension to the inception phase was permitted in order to re-assess and focus proposed activities in line with the PQR outcome. The key strategic implication of the PQR outcome was the eventual reorientation of the programme away from mining to focus almost exclusively on oil (as well as gas to a lesser extent), with a clear northern Kenya geographical target.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Expected Outcome: A better enabling environment for business, strengthened governance, and a localised and inclusive approach to community development in extractives sectors.

The initial logframe had five output pathways to achieve the outcome, over a four year period. The programme has now been reduced to three output work streams and it will be challenging for those to successfully achieve this outcome; which will be evaluated in the final Project Completion Review.

Outcome Indicator 1 – 54/100 in the Policy Perception Index (Petroleum) of the Fraser Institute’s Global Petroleum Survey

The Policy Petroleum Index (Petroleum) for 2016/17 is set to be released after this review (December 2017). However, there have been some changes in the Kenyan petroleum sector which could result in index score improvements for Kenya. The ‘improved quality of geological databases in the sector’ metric may improve for Kenya given modernisation of the Kenya geological database by the National Oil Corporation (with some support from KEPTAP); and the National Geodata Centre being set up with support from the British Geological Survey (BGS) under the GREAT For Partnerships CMP and K-EXPRO. Both initiatives should improve the quality and ease of access to geological information across the wider extractives sector.

Outcome Indicator 2 - Significant changes in extractive sector policy, systems and practice supported by K-EXPRO.

In addition to the five full time technical advisors in the Ministry of Mining, K-EXPRO placed a short-term advisors in the Ministry of Mining to support the development of mining regulations which have been finalised following an extensive consultation process. In addition, the Minerals Rights Board was also set up with backstopping from K-EXPRO technical advisors . The supportive role of the technical advisors has resulted in improved relationships between industry and policy makers in the national government and a generally more open perception of the Ministry of Mining due to increased transparency and use of social media to share developments in the sector.

Overall output score and description
The overall programme performance for the period was assessed as an ‘A’ (met expectations) against the July 2017 revised logframe with the following output scores:

Output	Description	Score	Weighting
1	Increased capacity of local businesses to benefit from supply chain opportunities linked to the emerging oil and gas sector	A	35
2	Increased county and community level influence on policy, systems and practice to reduce conflict and investment risk in oil and gas sector	A	35
3	Improved policy, systems and practice at the national level through coordinated extractive sector support	A+	30

Has the logframe been updated since the last review?
Yes. The logframe was updated in mid-July 2017 to reflect the reduced ambition and resultant change in focus necessitated by the PQR outcome as follows:
1. Three of the Outputs were removed (i.e. Institutional Strengthening, Transparency and Social Accountability, and the cross-cutting Stakeholder Mapping);
2. Two of the Outputs amended to accommodate the reduced scope and ambition (County Engagement and Private Sector Development / ‘local content’); and
3. A new Output introduced to capture elements relating to the early closure of K-EXPRO including the increased use of DFID CMPs to support Kenyan institutions.

## C: DETAILED OUTPUT SCORING

Output Title	Increased capacity of local businesses to benefit from supply chain opportunities linked to the emerging oil and gas sector
Output number per LF	Output 1	Output Score	A
Risk:	Major	Impact weighting (%):	35%
Risk revised since last AR?	Yes	Impact weighting % revised since last AR?	Yes
Indicators	Milestones	Progress
1.1 SMEs with improved business skills, linkages, finance and information	Supply/demand gap analysis that informs choice of five sectors and approach to supporting SMEs; / Feasibility study of potential oil/gas-related business models for northern Kenya completed.	Met expectation: A / Supply/demand gap analysis undertaken and informed initial choice of five sub-sectors jointly by industry and government; / Feasibility study completed by Rebel Group and policy note in development.
1.2 Quality learning materials and knowledge products on key sectoral and operational issues produced and disseminated and taken up by key stakeholders in policy, systems and practice	1	Moderately exceeded expectation: A+ / Achieved: 3 / A local content exchange was carried out on 4 July by the World Bank. Briefing notes published and disseminated on social media (LinkedIn, Twitter and Facebook), in local print media (Nation Media) and uploaded onto the Extractives Baraza website[4]. Continued tracking of usage will take place through google analytics. / A Joint Ventures and Strategic Partnerships training was organised by the World Bank, with K-EXPRO and industry funding (Africa Oil and Tullow Oil). This was supplemented by a Business-to Business event in Nairobi where international oil/gas companies met with Kenyan companies wishing to participate in the sector. / The Rebel Group (K-EXPRO consortium member) produced a research note on initiatives to develop SMEs in the oil sector.
[4] http://extractives-baraza.com/events/kenya-local-content-exchange-meeting

Key Points
- This Output’s weighting was increased in the revised logframe, from 20% to 35% (previously captured under Output 4) as a result of the reduced scope of K-EXPRO.
- Output 1.1:
  - The rationale for interventions is to help Kenyan SMEs and entrepreneurs, in particular those from the impacted areas in northern Kenya, take advantage of economic opportunities arising from oil sector investments so as to broaden the potential economic and developmental impact of oil sector investments.
  - The five priority sub-sectors for SME support identified through the supply/demand gap analysis comprise (1) civil engineering and construction; (2) cement production; (3) maintenance – mechanical and electrical; (4) well services; and (5) steel manufacturing
Output 1.2:
  - The Extractives Baraza – currently funded by K-EXPRO, is an online platform that impartially promotes knowledge, transparency and evidence-based stakeholder dialogue on the extractives sector in Kenya. Its ultimate goal is to enhance citizen participation and engagement in the governance of Kenya's extractives sector. Discussions are ongoing with other donors (i.e. World Bank and the Finish Government) to explore options for additional future funding to the Extractives Baraza, including after the end of K-EXPRO.
  - Quality assessments of the learning materials and knowledge products is ongoing and determined in discussion with OPM in quarterly reviews of the delivery plan and with the World Bank during the six-monthly review missions.
Overall, the foundations laid in this first year will enable 30 SMEs to be directly supported next year to grow and employ more people due to improved business skills, linkages, finance and information relevant to the oil and gas sector. The specific support provided will be designed so as to be catalytic for the SMEs and not require on-going support beyond the life of the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Make sure a pipeline of relevant private sector partnerships is planned and implemented for both the DFID Skills for Oil and Gas Africa (SOGA) programme and the World Bank Kenya Petroleum Technical Assistance Project (KEPTAP) Petroleum Business Opportunities (PBO);
  - SOGA: The Advisory Committee meetings have consistently included the private sector; and a private sector partnership agreement focusing on supporting SMEs in Turkana has been agreed (with Kenya Federations of Master Builders, Shell and ‘Invest in Africa’, a Tullow Oil initiative).
  - KEPTAP-PBO: Numerous private sector partnerships have been established under PBO and co-financed by industry, including the joint venture training and local content exchanges.
- Make sure that a strategic fit for both SOGA and PBO is maintained with sufficient steer provided by GoK and by key international investors through respective governance arrangements
  - Government and industry representatives have actively participated and financially contributed to PBO events, and SOGA Advisory Committee meetings, including engagement by the Permanent Secretary of Petroleum. This remains instrumental in shaping the strategic focus and effective progress monitoring (particularly evident during the World Bank missions to help shape the direction of PBO’s work programme).
- Confirm the output description as revised in June 2016 and make sure that OPM team delivers a convincing update of indicators, milestones for outer years and risk rating, supported by sound baselines and thorough Political Economy Analysis (PEA) performed during the inception (by May 2017).
  - During the first phase of inception (November 2016 to April 2017) the OPM team commissioned consultants to conduct macro and industry level PEA that helped inform the revised logframe.

Recommendations
1. With the programme ending in October 2018, put in place (as a matter of urgency) clear sustainability or exit plans to ensure a smooth transition. This will include an early handover of remaining advisory facility support from the UNDP to OPM, and exploring financial sustainability options for the Extractives Baraza website run by Strathmore University.
2. Focus efforts on ensuring the uptake of knowledge/materials generated through the programme translate into positive contributions to policy, systems and practice.

Output Title	Increased county and community level influence on policy, systems and practice to reduce conflict and investment risk in oil and gas sector
Output number per LF	Output 2	Output Score	A
Risk:	Major	Impact weighting (%):	35%
Risk revised since last AR?	Yes	Impact weighting % revised since last AR?	Yes
Indicators	Milestones	Progress
2.1 Key community and county issues that are integrated into national and county-level debate	Mechanism to deliver constructive dialogue forums involving senior government officials, civil society and industry representatives initiated.	Moderately did not meet expectation: B / Mechanism for addressing conflict risks associated with oil and impacted communities in Turkana designed and ready for implementation in partnership with Trocaire and other stakeholders who will sustain it after the end of K-EXPRO. The initiation of this mechanism was delayed by the 2017 Kenya General elections. / Progress transforming the previous Information Centre for Extractive Sector (ICES) to the ‘Extractives Baraza’. Including a more interactive website, active social media campaign and more buy-in from industry and government (including the set up of a Steering Committee chaired by the National Treasury to ensure good governance and the required government support).
2.2 Quality learning materials and knowledge products on key sectoral and operational issues produced and disseminated and taken up by key stakeholders in policy, systems and practice	1	Moderately exceeded expectation: A+ / Achieved: 3 / Two events brought together industry, policy makers in government, civil society and community representatives to discuss key industry issues in an informal context (‘fireside chats’) held by the Extractives Baraza; along with frequently asked questions (FAQs) on the extractives sector published in the Nation Media group[5]. OPM and their consortium implementing partner (Strathmore University) will be tracking when and how these initiatives translate into change and progress reported against the quarterly delivery plan. / OPM contracted International Alert to conduct and publish an analysis of conflict and extractives development in Kenya.[6] / A draft discussion paper on waste management issues in northern Kenya was also produced by OPM and disseminated to industry to increase investor understanding and interest.
[5] http://extractives-baraza.com/resources/faqs/faqs-and-answers-on-compulsory-land-acquisition-in-kenya
[6] http://www.international-alert.org/tags/kenya

Key Points
- Output 2 interventions seek to support county representatives and communities to better understand, and be able to provide, meaningful, free and informed consent to oil projects. It also aims to help re-dress negative perceptions that some individuals have within communities, minimize ‘blockers and spoilers’ of oil investments, reduce conflict risks and ultimately increase the potential for local job creation opportunities from oil.
- Overall, the foundations laid in this first year will enable key policy issues on critical infrastructure projects to be integrated into national and county level debates next year in order to influence policy change beyond the life of the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Review with OPM proposals for support on Artisanal and Small scale Mining (ASM) in at least two Counties and start implementation by March 2017.
  - OPM and DFID reviewed a number of proposals to support ASM, leading to a short deployment of consultants in the Ministry of Mining to establish a national ASM technical committee in compliance with the provisions of the Mining Act 2016. The consultants helped in the development of a draft national ASM strategy which is now awaiting multi-stakeholder validation prior to implementation. In this regard, K-EXPRO has put ASM formalisation on a firm footing for the Ministry of Mining to start its operationalisation.
- Commit the K-EXPRO service provider to review lessons from the Turkana community engagement pilot previously funded under the DFID Kenya Extractives Industry Development Programme KEIDP and use them to propose a follow up engagement by June 2017
  - K-EXPRO via OPM used the inception period to investigate more deeply the political economy context of Turkana and has strived to build and nurture relationships and trust with various actors in the region. This was critical for making decisions on which partners to work with and allowed time for engaging with relevant stakeholders in Turkana including senior county government officials, industry and CSOs to gauge any potential reputational risk of working with the various actors. In the revised work plan signed off at the end of June 2017 it was agreed that Trocaire were best placed to deliver activities through their partners who have a clear understanding of local dynamics within the oil sector, particularly around public participation, conflict and natural resource rights.
- Review the Output description as revised in June 2016 and make sure that OPM team delivers a convincing update of indicators, milestones for outer years and risk rating, supported by sound baselines and thorough political economy analysis performed during the inception (by May 2017).
  - During the inception phase (November 2016 to April 2017) the DFID and OPM teams revised and updated the logframe with indicators and milestones to align with the new programme end date of October 2018.

Recommendations
n/a

Output Title	Improved policy, systems and practice at the national level through coordinated extractive sector support
Output number per LF	Output 3	Output Score	A+
Risk:	Major	Impact weighting (%):	30%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	No
Indicators	Milestones	Progress
3.1 Access to credible and relevant information on extractives policies, systems and practice	Robust pathway for public outreach and education on extractives successfully launched.	Moderately exceeded expectation: A / A ‘Transparency Scorecard’ was developed by the Extractives Baraza with support from OPM and the Natural Resource Governance Institute (NRGI) to increase international interest and oversight in extractives governance in Kenya. This initiative is an attempt to tap into broader media and investor interest in NRGI’s transparency benchmarking which provides a 50 country index (of which Kenya as an exploration player is not yet included). NRGI is partly funded under DFID’s Releasing the Transformational Potential of Extractives for Economic Development (RTPEED) CMP. / Two Extractive Sector Forums held in 2017 through the Extractives Baraza brought together government, industry and civil society to discuss key policy issues. / The revamped and interactive Extractives Baraza website is in place and with regular newsletter distribution (this has dramatically increased the reach of the platform).[7]
3.2 Managed hand-over and transition of K-EXPRO supported interventions, including to DFID’s Centrally Managed Programmes (CMP) and/or other partners	2 instances of successful leveraging of effort among CMPs and with K-EXPRO.	Moderately exceeded expectation: A+ / Achieved: 4 / Significant progress made by BGS technical support to the Ministry of Mining Directorate of Geological Survey towards the establishment of the National Geodata Centre with funding through DFID’s GREAT for Partnerships CMP; the timelines were however affected by the 2017 Kenya General elections, continuation of initiatives now expected in November 2017. / Africa Legal Support Facility (ALSF) drafted a model mining agreement which was shared with the Ministry of Mining for endorsement. / The East Africa Research Hub funded a policy brief on ASM (written by PACT) that was used by the Ministry of Mining to inform Treasury budget allocations. / Extractives Hub (funded by RTPEED) drafted a policy note providing an overview of reform options and potential pathways for Kenya’s sustainable mining fiscal review processes.
3.3 Progress of legacy interventions (competency transfer in Ministry of Mining and establishment of National Sovereign Wealth Fund (NSWF))	Evidence of (i) satisfactory competency transfer from advisors in Ministry of Mining; and (ii) high level strategic advice (based on robust analysis) provided to GOK to inform the NSWF Bill.	Met expectation: A / Some competency transfer from the five technical advisors embedded within the Ministry of Mining, though more needs to be done. / A World Bank multi-sectoral team provided strategic advice to the National Treasury to inform the NSWF Bill.
[7] Google analytics indicates a significant increase on the use of the EB platform by different users. In the first quarter, EB had a total of 2,155 sessions, 1,031 users and 7,586-page views. This increased to 5,178 sessions, 3,165 users and 12,653-page views in the second quarter

Key Points
- Output 3 is aimed at coordinating extractives sector support, in particular leveraging DFID’s research hub and five DFID Centrally Managed Programmes (CMPs).[8] This aims to achieve greater value for money through more engaged local oversight as well as drawing on CMPs more where K-EXPRO no longer has funds to work. A measurement challenge is clearly defining the value add by K-EXPRO to the on-going work of the CMPs.
  [8] Comprising: 1. Sills for Oil and Gas (SOGA); 2. Releasing the Transformational Potential of Extractives for Economic Development Programme (RTPEED), 3. GREAT for Partnership; Africa Legal Support Facility (ALSF); and 5. East Africa Research Facility (EARF).
- With respect to the advisory facility to the Ministry of Mining, there were significant challenges in integrating the UNDP managed technical advisers, though things have improved and the ministry counterparts report greater satisfaction and closer working relationships now. By raising productivity in the ministry and interaction with industry, the advisory facility seems to have contributed to improved staff morale and proactivity – most notably, the five advisers’ inputs in the development of the Mining Act 2016 and the accompanying 14 implementation regulations.
- Overall, the foundations laid in this first year will enable greater civic engagement through 10,000 people being able to access credible information on extractives policies and projects next year. The Government will be able to design a National Sovereign Wealth Fund drawing on both technical advice as well as being held more to account by the higher levels of civic engagement.

Recommendations
1. As the advisory facility to the Ministry of Mining is currently being transitioned from UNDP to OPM, and phased out by March 2018, there is need for the advisers to develop clear transition plans and strengthen competency transfer.
2. Continue strong engagement between the K-EXPRO project delivery team and the DFID Centrally Managed Programmes (CMPs)[9] to ensure a clear understanding of the K-EXPRO support role in their projects’ execution and collaborative engagement with the Government of Kenya.
  [9] Comprising: 1. Sills for Oil and Gas (SOGA); 2. Releasing the Transformational Potential of Extractives for Economic Development Programme (RTPEED), 3. GREAT for Partnership; Africa Legal Support Facility (ALSF); and 5. East Africa Research Facility (EARF).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The key cost driver for OPM in this review period has been costs associated with programme set up (76%). This included establishment of the programme office in Nairobi, recruitment of the core team and development of programme operations, finance and procurement, and grant manuals. Programme scoping work (24%) related to the design of interventions for the implementation phase was the second largest cost. Disbursement of grants is expected to form the major part of the interventions in the coming year.

VfM performance compared to the original VfM proposition in the business case
It is anticipated that the service provider management costs over the lifetime of the programme will increase from 11% anticipated in the Business Case to approximately 17%. This percentage increase in management costs is in a large part due to the significantly smaller total size of the programme now.

The programme implementation phase started in July 2017 and hence it is too early to make strong judgements about some areas of VfM, particularly at the effectiveness level. K-EXPRO has demonstrated some good evidence of VfM at the economy and efficiency levels as follows:
1. Economy: OPM’s average international flight unit costs have been revised downwards to £750 as compared to the budgeted amount of £1,100. OPM also saved office costs by subletting from their partner WYG as opposed to leasing and furnishing - Office furnishing had been budgeted at £30,000 whereas only £17,642 had been spent. Overhead charges by UNDP on the advisory facility will also be done away with by transitioning the management of the advisers to OPM.
2. Efficiency: Most notably, the options chosen in the implementation phase are strategically informed by scoping studies and are responsive to the peculiarities in the operational context and based on lessons learned from KEIDP and other extractives programmes. The interventions are delivered mainly through local partners (of the funding managed by OPM around 80% is in the form of grants, the rest in technical assistance) who have a sound understanding of the issues to be addressed and are well grounded in the target areas and hence have earned community goodwill.

Assessment of whether the programme continues to represent value for money
The programme is assessed as delivering satisfactory levels of VFM. Given the smaller size of the programme, the proportion of spend by OPM on start up costs has been high. Savings were made on office running costs, international travel and IT costs. The PEA findings remain instrumental in delivering an efficient and effective programme over time cushioned against political risks and scanning opportunities to better delivery. Review mechanisms have been instituted and the quarterly KEPTAP missions in particular have been effective in maintaining programme momentum with partners.

Quality of financial management
The programme is on track with disbursements. The programme had spent 52% of its PQR adjusted budget at the time of this review. K-EXPRO’s current budget balance is approximately £3m, of which £1.7m is forecasted to be spent by March 2018 with the remainder by October 2018. With respect to the 3 main implementing partners:
1. OPM: spending performance was extremely accurate during inception, with a variance of only 2% compared to the forecast shared with DFID. The team has been transparent in their financial reporting, including the timely issue of credit notes when billing errors were identified.
2. UNDP: payments are ceasing in part over delivery concerns, and the responsibility for the remaining advisory support to the Ministry of Mining transfering to OPM from late 2017 onwards.
3. World Bank: The KEPTAP funding commitment after the PQR outcome was fully disbursed by the time of this review.

As lead contractor of a consortium, OPM has developed robust programme financial, grants and operations management manuals drawing on lessons from OPM’s other DFID-funded projects such as GOGIG (Ghana), MUVA (Mozambique) and FOSTER2 (Nigeria). The manuals serve as a reference point to ensure that a) correct procedures are followed; b) full accountability and transparency are maintained; and c) strong internal controls are implemented.

Date of last narrative financial report	23 August 2017
Date of last audited annual statement	See comments below

1. OPM: OPM has plans to conduct audits on its downstream partners with whom grant agreements have been finalised. OPM conducts comprehensive due diligence assessments on these grantees before agreeing the grant commitments in line with their contractual obligations to DFID. The due diligence assessments reflected general compliance with statutory audit requirements. Specifically, an audit has been carried out on the Information Centre for Extractive Sector (ICES) – which has since been transformed into the Extractives Baraza – the report is currently being finalised by the audit consultant.
2. World Bank and UNDP: K-EXPRO relies on the standard World Bank and UNDP fiduciary risk assurances which DFID has agreed to institutionally.

E: RISK

Overall risk rating: Major

Overview of programme risk
There has been a regular review of risks to the programme. K-EXPRO’s overall risk rating of ‘major’ has been assessed as not having changed since the last annual review. The main risks identified in the Business Case remain, and comprise:
1. DFID being associated with any future corruption allegations or with environmental damage;
2. The risk that the programme is implemented in the context of conflict, whether violent conflict in the field, or political economy tensions within national government and between national and county levels, or within local governments themselves;
3. The risk that there will be a lack of coordination from the Government of Kenya in terms of support initiatives, both government and donor-driven and finally; and
4. A disproportionate risk associated with low quality, unevenly delivered or late delivery of technical assistance.

In addition, over the course of the year there were many risks associated with the PQR process and reduction in programme size and scope – in particular reputational risks. These were mitigated through proactive management of key stakeholders, though some residual risks remained given high stakeholder expectations when the programme came on stream. There were also risks associated with the Kenya elections 2017 and a slow down of delivery, which has been managed. Overall, the team does not assess the risk level to have increased beyond ‘major’ this year.

OPM has set up internal control systems (audits, due diligence, spot checks on partners) to manage fiduciary risks associated with its grant-making and service providers for the delivery of individual interventions. Pre-funding due diligence assessments are undertaken on potential downstream partners. OPM is required to follow up any concerns identified in due diligence assessment to ensure these are effectively and timely managed.

Outstanding actions from risk assessment
The programme risk register has been updated following transition from the inception phase to implementation phase.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme was reported as having experienced considerable implementation delays during the 2016 Annual Review owing to the extended time taken to recruit the programme’s main implementing partner (OPM). The transition from inception phase to implementation phase in the period under review was further affected by the PQR process. Some of the proposed interventions were caught up by Kenya election risks and hence started late. This included the sign-off of grant agreements with downstream partners. OPM’s billing has been timely and follows an agreed schedule, which had transitioned to monthly at the point of this review. The financial reports that accompany invoices are sufficiently detailed to support various analysis and decision making.

The OPM contract was premised on a Payment by Results (PBR) model during the inception phase, this was however changed following the PQR outcome and a consensus reached between DFID and OPM that the PBR format no longer presented good value for money, especially as regards to the disproportionate administration time required to apply it. The strategic advisory facility to Ministry of Mining, KEPTAP support and funding for the Extractives Baraza (now managed by OPM) are on track and reporting early successes.

Performance of partnerships
OPM was proactive in communicating to DFID implementation progress and challenges, including the recent Kenya election risks that affected the signing of grant agreements with some downstream partners. The OPM team leader has built relationships with other DFID and non-DFID extractives programmes that are complementary and likely to enhance K-EXPRO objectives. OPM diligence and commitment is demonstrated by the close working relationship with DFID to deliver the logframe and delivery plan. OPM continues to apply the outputs from its monthly political scans to adapt the programme to external factors identified. OPM has applied lessons learnt from managing similar programmes in Nigeria and India to enhance VFM achievements, including the employment of a director who is involved with the two programmes to share lessons and delivery inputs. DFID enjoys a good working relationship with the World Bank through KEPTAP, which is especially valuable for fostering relationships with the Ministry of Energy and Petroleum, and industry stakeholders. The partnership with UNDP has experienced challenges with reporting timelines though overall the deployment of skilled advisers to the Ministry of Mining has significantly improved the ministry’s capacity.

Asset monitoring and control
In the coming year, DFID will verify programme assets, review the strength of the due diligence procedures applied on downstream partners and assess the risk management safeguards in place, including in the management of fiduciary and corruption risks. Delivery partners and their respective downstream partners are expected to maintain asset registers as provided for in their contracts/agreements with DFID. OPM will conduct half yearly general verification checks on their processes partners, including on asset management.

G: CONDITIONALITY

Update on partnership principles
The programme works in close partnership with the Government of Kenya, with an increasing focus at the county level. All support towards government is through technical assistance and no funds are channelled through government accounts.

H: MONITORING & EVALUATION

Evidence and evaluation
There is no formal mid-term evaluation planned for the programme owing to the limited delivery time available post-PQR decision. OPM however are implementing a simple and effective Monitoring and Evaluation system to track performance, highlight challenges and feed them back into the planning process to ensure better results. This is aimed at telling a holistic story of the interplay between Inputs, Outputs, Outcome and Impact – within the complex environment that K-EXPRO operates. As mentioned earlier, the regular political economy analysis will also greatly help in identifying factors in the environment with likely potential to impact the programme delivery, and relevant and timely mitigation measures put in place to manage.

Monitoring progress throughout the review period
The programme team at OPM and DFID is well-coordinated, with regular meetings to assess programme intervention models and progress. The team is currently looking at lesson-learning with similar projects in other countries that would be of benefit to the programme. The advisory facility to the Ministry of Mining is reviewed via regular quarterly review meetings where adviser inputs and outputs are assessed by the Ministry of Mining, DFID (including OPM) and UNDP; corrective actions are identified and agreed in these meetings. Effectiveness of capacity transfer was identified as still lagging in the May 2017 review meeting and the advisers advised to explore ways to enhance closer working and inputs from their Ministry of Mining counterparts. The Ministry of Mining has expressed satisfaction with the outputs of the advisory facility thus far as has sections of industry.

The KEPTAP programme is reviewed on a quarterly basis via the World Bank review missions and aid memoires produced that account for the project’s progress and lessons learnt through delivery. DFID and the OPM team have also participated in field visits to Turkana, sometimes jointly with other DFID Kenya programme teams, to assess the relevance of the programme and appropriate interventions to implement. The OPM Operations Coordinator works across the programme to support all programme management functions as required, but with a clear focus on process compliance, and programme monitoring and learning.

The annual review process
This annual review was undertaken by Linet Otibine (Programme Manager, Sustainable Economic Development, DFID Kenya) and Ian Mills (Head of Sustainable Economic Development, DFID Kenya) with inputs from OPM. The report has been quality assured by the Accountability and Results Team in DFID Kenya.