Annual Review - Summary Sheet

Title: Livelihoods and Food Security Trust Fund (LIFT) for Burma
Programme Value: £152,060,000		Review Date: 21/08/2017
Programme Code: 201239	Start Date: 31/12/2009	End Date: 31/03/2019

Summary of Programme Performance
Year	2010	2011	2012	2013	2014	2015	2016	2017
Programme Score	70	A	A	A+	A+	A+	A+
Risk Rating	H	M	M	M	M	M	Mod

### Summary of progress
Decades of economic mismanagement, conflict and international isolation has left Burma one of the poorest countries in the region, although the abundance of its natural resources and strategic location means it has the potential to be rich. One in three people live below the poverty line and one in three children under five are stunted. Rural areas account for 70% of Burma’s poverty, whilst agriculture employs around 54% of Burma’s workforce and generates 29% of GDP. Migration and off-farm work are increasingly popular livelihood strategies for rural households.

The Livelihoods and Food Security Trust (LIFT) is a multi-donor trust that promotes resilient and inclusive growth in Myanmar. It achieves this by enabling poor women and men to ‘step up’ into commercial value chains, ‘step out’ of marginalised farming into more profitable off-farm jobs, and ‘hang in’ by using agriculture as an affordable safety net. Improved nutrition and reduced stunting are critical themes for all LIFT activities, as are the themes of resilience, gender and social protection. DFID is the largest contributor to the fund, which has received contributions from thirteen other government donors and one private entity.

This is the seventh annual review of LIFT. It has moderately exceeded expectations (A+) for the fourth year in a row, even with substantial increases in ambition. This review assesses the performance of the LIFT project portfolio against the new 2015-2018 logframe, and progress against the overall strategic direction set out in 2014-18 LIFT strategy. The review is informed by the 2016 LIFT tracking survey, an Independent Interim Review, the LIFT Annual Report 2016, aggregated data from implementing partners and meetings with a range of stakeholders including a field trip that involved meeting various beneficiary groups.

### Key programme achievements
LIFT is achieving results at a vast scale. It aims to reach 7.2 million people by the end of 2016. This is roughly 20 percent of Myanmar’s rural population. The programme has met or exceeded 25 of its 27 output indicators in 2016. Scale-up has been orientated around LIFT’s geographic and thematic programmes and includes significant cross-cutting results for nutrition and resilience. Growth in people reached has been particularly driven by LIFT’s financial inclusion activities. To date LIFT’s headline results include:
- an estimated 2.2 million people living in households with increased incomes;
- 2.3 million people living in households with increased assets;
- 2.3 million people with strengthened resilience; and
- over 325,000 households with improved diets.

LIFT continues to adapt its activities to keep pace with the rapid speed of rural transformation. LIFT-funded research[1] underlines how quickly parts of the rural economy are changing. This includes the uptake of tractors, harvesters and other machines that enable some households to ‘step up’, as well as migration to urban areas as others opt to ‘step out’. LIFT’s 2014-18 strategy, which included substantial DFID-input, has provided a clear framework to guide the programme’s activities in response. For example, the broadening of focus to include private sector entities has enabled LIFT to support evolving livelihood strategies. The ability of the fund to regularly open new grant windows, three were launched in 2016, has also aided its ability to remain nimble. This is partly enabled by donors trust in the fund management office (FMO) and a preference against earmarking contributions.
[1] See M. Thida Win and A. Mya Thinzar (2016), Agricultural Mechanisation and Structural Transformation: Ayeyarwady Delta.

In 2016 LIFT supported 56 Microfinance Finance Institutions (MFIs), providing low-interest loans to nearly 1.6m clients, 94% of whom were women. Disbursements from these institutions totalled $420m, reaching 15,300 villages. Myanmar’s economy remains severely credit-constrained[2], and LIFT therefore supports access to rural financial services across all four of its geographic programmes.
[2] See: World Bank (2017), Myanmar Economic Monitor: December 2016.

LIFT leveraged significant capital from the private sector to amplify its impact. LIFT has expanded its financial inclusion programme to support a new agricultural hire purchase programme. By leveraging $43m capital from Yoma Bank (five times LIFT’s contribution), LIFT has improved the terms on which farmers can access mechanical farm services. At the end of 2016 this had facilitated 3,000 new lease contracts with a total value of $56m. LIFT also opened a Currency Exchange and Hedging Window to protect foreign investors in Myanmar’s MFI sector from exchange rate volatility. A LIFT subsidy of $10m was able to leverage $70.6m of foreign direct investment (FDI) from institutional investors, providing access to financial services for up to 350,000 clients.

The fund has expanded its engagement with local entities across the country. An increasing proportion of funds are now managed by local groups. LIFT signed 24 new contracts in 2016, of which nine were with national NGOs and four included national sub-implementing partners (sub-IPs). In particular, the fund increased its engagement with civil society by opening three small grants windows, in the Delta, Dry Zone and Uplands. These are for township-level civil society organisations (CSOs) that work on livelihood system strengthening with other local actors.

A constructive relationship between LIFT’s Fund Board (FB) and Fund Management Office (FMO) drives continuous improvement. An active FB, that is empowered to also make decisions between meetings, ensures that LIFT’s work remains in line with emerging priorities of the Government of Myanmar (GoM) and donors. A number of interviewees singled out DFID’s role as chair of the FB as a key driver of continued improvement.

LIFT has improved its engagement with government, including by inviting it onto the FB. In March 2016, LIFT’s donors agreed to invite the newly-formed Ministry of Agriculture, Livestock and Irrigation (MOALI) to join the FB. MOALI is now a full FB member and participated in discussions regarding the future of LIFT. This has been achieved without slowing processes down, by recognising the varied interest government has in parts of the programme. In cooperation with USAID and the EU, LIFT has also established an agriculture policy unit in MOALI, which has helped develop and implement a new Agriculture Development Strategy.

The fund has continued to improve the nutrition of women, men and children. In 2016, LIFT expanded its nutrition and water and sanitation activities. Whilst results under the related output are progressing slower than others, the programme has successfully begun a range of new interventions across the country. In 2016, LIFT delivered 45,936 cash transfers to 9,125 beneficiaries, and 55,000 households participated in health and nutrition training sessions. LIFT also continued to improve the resilience of rural households and support social protection interventions. Survey evidence shows that households who received LIFT-funded agricultural training were four times as likely to increase their crop yields and twice as likely to increase their incomes. LIFT also continued to support vulnerable populations including the elderly. For example, a social protection project in the Dry Zone has strengthened community mechanisms for addressing problems that the elderly dace and has assisted the government to implement social protection plans.

In 2016 LIFT improved its approach to Monitoring and Evaluation for Accountability and Learning (MEAL). The fund increased its MEAL resources, enabling projects and programmes to refine their Theories of Change (ToC) and develop new evaluation and learning questions (ELQs) to structure learning. LIFT also influenced policy on rural transformation through the production of a range of new evidence. In 2016, the programme supported 49 policy-orientated events and published and disseminated 49 publications to stakeholders.

LIFT has continued to provide a focus on cross-cutting priorities, including working in conflict-affected areas and, to a lesser extent, gender equality. In 2016 the fund developed a new gender strategy and action plan, and allocated funding to its implementation. LIFT also expanded its work into the conflict-affect areas of Kayin, Kayah and Tanintharyi with new partners and stakeholders, alongside completing various conflict-assessment missions. In spite of the challenges in Rakhine, the programme expanded its work to cover 14 out of 17 townships.

LIFT continues to provide good value for money. UNOPS’ role as FMO enables LIFT to convene a range of donors and parts of government that other programme struggle to reach. There are also increased examples of cross-working between LIFT and other UNOPS managed funds (e.g. 3MDG, Global Fund).
### Key challenges and lessons
Working with the GoM has proven more complex than expected. Whilst LIFT has developed constructive relationships with government, the fund may have demonstrated optimism bias about the speed with which the new government would begin implementing reform. Decision-making has been particularly slow, and capacity building support often delayed. Whilst the fund has various positive examples of constructive engagement with government, these have taken more time and resource than was envisaged. This issue is likely to continue without scale-up of capacity building, including through targeted technical assistance.

Whilst LIFT has had significant success in influencing policy, it could do more to ensure holistic policy support across the fund. This might include incentivising all programme staff to prioritise their policy influencing role, and providing a more permanent policy presence in the Nay Pyi Taw to support coordination alongside longer-term capacity development for the GoM ministries.

Implementation of a cross-cutting focus on gender equality and women’s empowerment has been slow. Whilst LIFT is now implementing a comprehensive gender strategy, this was developed much later in the programme’s lifecycle than would be expected, limiting the impact it will have.

A lack of resources allocated to knowledge management has impeded the impact of LIFT’s strong MEAL and communications activities. More could be done to ensure lessons across project activities are drawn together cohesively to influence government policy and future fund direction. It is not easy to discern what LIFT’s research and MEAL activities tell us about the overall shape of rural transformation in Myanmar, as described by the 2014-18 strategy (against ‘step up’, ‘step out’, ‘hang in’).

LIFT has not publicised the lessons it has learnt from failure. LIFT has typically adapted quickly where things have not gone to plan. However whilst internal documentation and communities of practice (CoPs) demonstrate how the fund shares these lessons internally, less is made public for an external audience. For example, LIFT’s 157 page Annual Report 2016 does not include any clear focus on where things went badly.

It is difficult to isolate the impact of the various types of activity LIFT is implementing. The vast outreach of the financial inclusion activities is commendable, and the fund has adapted its survey approach to better understand results in ‘financial inclusion only’ areas (as opposed to those also receiving other LIFT interventions). Whilst output-level data and qualitative reports, supplied by IPs, show that LIFT’s other activities are also going well, it is difficult to unbundle the relative impacts of these activities in the survey data. Next year’s household survey should be able to shed more light on this.

LIFT is no longer the only donor programme in the agriculture space. Additional projects and programmes with a direct or indirect focus on rural transformation are growing quickly, a sign of the success the fund has had in demonstrating the impact of its rural transformation activities. LIFT is still the largest, but needs to remain open to challenge from others to help grow a diverse group of actors supporting the sector.

The risk environment in which LIFT operates has changed. This includes sustained conflict in Kachin and Shan states, and increased conflict in Rakhine, continuing to restrict activities supporting particularly vulnerable populations. The outbreak of violence in Rakhine in October 2016 caused particular delays in activities being implemented by LIFT’s IPs. Other new risks include the increased proportion of LIFT funding managed by local entities, and possible delays caused by changes in the GoM’s approach to aid programmes.

LIFT’s new Value for Money (VfM) guidelines and metrics need another year before providing full detail on efficiency, economy and effectiveness. Nonetheless, there are increased examples of UNOPS providing cross-fund working, demonstrating the effectiveness of co-located programmes.

### Actions on previous recommendations
LIFT has taken partial or complete action against all 17 recommendations from last year’s review. Responses taken are summarised in Annex 2. The fund has made substantial progress in responding to recommendations on raising LIFT’s profile across government, retaining funding flexibility, monitoring partner implementation and improving cross-programme coordination.

Activities requiring an ongoing focus from the fund are:
- actively engaging the GoM on what support it needs on rural transformation post-2018;
- implementing the new VfM guidelines to provide a detailed assessment in next year’s annual review; and
- better aligning knowledge management with LIFT’s policy work.

### Priority activities for the next year
This section provides general and cross-cutting recommendations. Additional output-specific recommendations are included in section C below.

LIFT to continue to actively engage the GoM and other development partners on what the future of LIFT should look like post-2018 and how policy reform can support rural transformation. Better articulation of LIFT’s policy priorities and the deployment of a policy adviser in Nay Pyi Taw would support this.

LIFT to prioritise the rollout of the Gender Action Plan and the scoping study on climate change adaptation. The former will also require LIFT to develop its understanding of how women’s empowerment in relation to the expanding private sector programme (i.e. microfinance interventions have had a strong outreach to women, can this be emulated with the support for Yoma Bank on mechanisation?)

LIFT to draw together its activities on improving working conditions and combatting human trafficking. In addition to addressing these crucial issues for Myanmar, LIFT should also be able to demonstrate how it is responding to the UK’s agenda on modern slavery.

LIFT to improve its knowledge management processes to ensure lessons learnt across projects and research activities fully influence GoM policy and future direction of the fund. This is likely to include ensuring a full-resourced knowledge management position, and prioritising development and dissemination of LIFT’s legacy paper series. Mapping this evidence against LIFT’s 2014-18 beneficiary framework may be a useful activity.

LIFT to better publicise lessons it has learnt from failure, including in the next annual report. These could also emphasise to other how a ‘nimble’ fund is able to operate effectively in a changing risk environment.

LIFT to prioritise comparative analysis of the impact of LIFT’s activities across its two ‘tiers’ of activity. Analysis of the next household survey combined with LIFT’s other sources of evidence should enable the fund to better isolate, or estimate, the impact of various activities. For example, how much of LIFT’s results are driven by financial inclusion and are there positive interaction effects where financial inclusions and other activities are provided in the same areas?

LIFT to better communicate its innovative activities in working with the private sector to the GoM and to other donors. As a pioneer in this area, the fund has the responsibility to shape future work engaging the private sector in the country’s rural transformation.

LIFT to ensure it provides the space for other stakeholders in the rural development sector to engage with its projects and challenge strategic focus. The fund could do more to acknowledge where it has learnt lessons from failure or external challenge. A simple shareable database or ‘MIS’ of existing projects including their locations and cross-cutting themes could make it easier for other partners to engage with LIFT.

LIFT to keep a close eye on its civil society activities, to ensure they provide responsive investment and support as needed. The fund’s welcome expansion in the use of local entities needs careful monitoring to ensure capacity development is provided hand-in-hand with increased financing.

DFID and LIFT will work together to ensure the Fund continues to deliver VfM through the assessment of new FMO and programmatic VFM indicators outlined within LIFT’s VFM guidelines and the dissemination of VFM best practice examples.

1. DFID to prioritise the design of a successor programme. LIFT has achieved significant success in supporting rural transformation in Myanmar, but this work is not complete. Planning for a future phase has begun, in collaboration with the GoM and other donors. This remains an urgent priority for DFID Burma.
A. Introduction and Context

DevTracker link to business case, logframe:	https://devtracker.dfid.gov.uk/projects/GB-1-201239/documents

### Outline of the programme
LIFT was launched in 2009 as a multi-donor trust fund, primarily in response to Cyclone Nargis. It also had the aim of improving progress against Millennium Development Goal 1 (eradicating extreme poverty and hunger).

It is now the largest aid multi-donor trust fund operating in Myanmar. Originally established as a five year fund, LIFT has been extended twice with grants now running until end June 2019. At the end of 2016 LIFT was supported by fourteen donors and one private company[3], of which DFID is the largest contributor.The fund is governed by a Donor Consortium and a FB, and managed by UNOPS. In 2016 overall delivery was $59m, 89% of which was provided to implementing partners (UN agencies, INGOs, LNGOs and research institutions). The programme currently has 71 live projects. By the end of 2016, the UK had made commitments equivalent to 49.7% of fund value, thus is able to claim that proportion of programme results.
[3] Donors include Australia, Denmark, the European Union, France, Ireland, Italy, Luxembourg, the Netherlands, New Zealand, Switzerland, Sweden, the United Kingdom and the United States of America. The Fund’s first private sector donor, Mitsubishi Corporation, joined in 2015.

LIFT has adapted its approach over time in response to the pace of economic transformation and reform. In 2014 the FB agreed to extend LIFT until 2018, contingent on implementation of an inclusive rural growth strategy, a new Theory of Change (ToC and an updated logframe to reflect the changed operating context. The UK was highly influential in the development of the strategy to ensure alignment with DFID’s approach to rural transition. In 2014 LIFT redefined its direction through the publication of a new LIFT strategy, developed in partnership with government and partners (http://www.lift-fund.org/strategy).

LIFT’s strategy promotes resilient and inclusive growth in Myanmar by enabling poor women and men to:
- ‘step up’ into commercial value chains;
- ‘step out’ of marginalised farming into more profitable off-farm jobs; and
- ‘hang in’ by using agriculture as an affordable safety net.
This approach is aimed at supporting rural transformation by providing new knowledge and technologies, facilitating access to finance and markets, and developing new agri-business opportunities with the private sector. Projects are divided into four agro-ecological zones: the Delta, the Dry Zone, Rakhine State and the Uplands, and three thematic areas: migration, financial inclusion and civil society strengthening. Improved nutrition and reduced stunting is a critical theme for all LIFT activities, as are the themes of resilience, gender and social protection.

The Annual Review period was the first full year of implementation under the new strategy. Substantial new funding in 2015 established a range of new projects for all geographic and thematic programmes.

### What are the expected results?
A detailed logframe is available on the UK’s DevTracker. Overall headline anticipated results to 2018 include[4]:
[4] Note, these are overall LIFT results of which DFID can claim 49.7% of based on its proportion of funding to date.
- 364,119 households with increased income;
- 1,766,394 people whose resilience and ability to cope has improved;
- 474,190 households with an increase in food security by at least one month (per year); and
- 13 public sector rural development policies influenced.
Progress against these is summarised in the next section.

Over seven years LIFT has achieved substantial results at the outcome and output level, and continues to deliver a high proportion of DFID Burma’s results. The programme has helped to exceed two DFID Operational Plan headline results: “the number of women reached with access to financial services as a result of DFID support” and “the number of people reached with nutrition support”. For instance, women represent 94% of LIFT-supported microfinance clients (1,532,961 women in total, 761,882 UK attributable). LIFT also contributed to three headline DFID Results Framework results for DFID Burma: number of people with sustainable access to clean water and/or sanitation through DFID support; number of people with access to financial services as a result of DFID support; and number of people reached with nutrition support (under 5 + pregnant women +women breastfeeding). Full details of LIFT’s performance against these criteria are provided in Annex 3.

### What is the context in which UK support is provided?
Decades of economic mismanagement, conflict and international isolation has left Burma one of the poorest countries in the region, although the abundance of its natural resources and strategic location bordering China and India means it should be rich. One in three people live below the poverty line and one in three children under five are stunted (higher in marginal and conflict affected areas). Rural areas account for 70% of Burma’s poverty.

In 2011, Burma began to emerge from decades of isolation and military rule, initiating economic and political reforms. Growth is estimated at around 7.5% for 2017/18 driven mostly by new investments in manufacturing, showing a positive and gradual move away from extractives.

The NLD-led Government has prioritised inclusive rural growth, with particular emphasis on rural job creation, land reform (reclamation and restitution) and improved nutrition. Capacity within Government is low to deliver on major reforms, and Government has looked to the UK both bilaterally (on nutrition) and multilaterally (through LIFT) to help them deliver tangible progress.

Agriculture employs around 54% of Burma’s workforce and generates 29% of GDP. Restrictive government policies, underinvestment in crop research and extension, and a bias towards rice have all contributed to productivity levels half of the South-East Asian average. The story is similar for other crops, except beans and pulses which have thrived away from government interference. The private sector is almost absent in agriculture.

Farmers face huge credit constraints and many rural households are landless. The unmet demand for rural credit is estimated at $3bn. The Myanmar Agricultural Development Bank provides seasonal credit of $150 per acre for rice. Most people rely on informal credit at high interest rates and the growing micro-finance sector (with lower interest rates, but limits on borrowing amounts). Half of rural households are landless, and these households account for over half of poverty cases. For those with land, tenure remains insecure especially due to conflict.

Myanmar is in the top ten countries globally most at risk from climate change. Cyclone Nargis killed around 140,000 people and destroyed assets in value of 20% of Burma’s GDP in 2008. A similar scale cyclone in Bangladesh killed 130 people. In August 2015 flooding in Burma affected 1.5m people and 6% of arable land.

Landlessness, climate change, low incomes, and economic opportunities elsewhere are driving outmigration. There are 4m Burmese migrants in Thailand remitting around $960 annually and millions in China, Singapore and Malaysia. Migration is usually an opportunity but for some it is an escape from persecution. There are many risks including slavery and sex trafficking, with women migrants particularly vulnerable to abuse. For most, migration is toward internal opportunities in the rural economy (e.g. 40% households include someone working off-farm).

B: PERFORMANCE AND CONCLUSIONS

### Annual outcome assessment
LIFT’s Theory of Change sets out the programme’s vision, goal and purpose (see Annex 4):
- Vision: In 2018, LIFT is a collective and influential voice for innovation and learning, and provides a platform for innovation and learning, and provides a platform for enhanced policy engagement on resilient, pro-poor rural development.
- Goal: To contribute to the national goal of sustainably reducing the number of people living in poverty and hunger in Myanmar.
- Purpose: To strengthen the resilience and sustainable livelihoods of poor people in Myanmar.
To achieve these, the programme targets four outcomes, or ‘process-level outcomes’, as listed in the first column of Table 1. Progress against these is tracked across 11 outcome indicators, as shown in the second column.

Progress at the outcome level is measured using LIFT’s independent large-scale, representative household survey (biennial) and tracker survey (biennial; alternate years to household survey). For the current logframe, the 2015 household survey serves as the baseline and the 2016 tracker survey provides the follow-up. To ensure value for money, the tracker survey does not go into as much detail as the household survey. As 2016 is a tracker survey year, not all outcome indicators have been measured. However they will be next year. An Independent Interim Review (IIR), carried out of the programme in 2016, found the methodologies of both surveys to be reliable and satisfactory.

#### Table 1: Outcome Performance
Outcome	Outcome indicator	Milestone ‘16	Progress
1. Increased incomes of rural households	1.1: Number of households in LIFT villages with increased income	250,000	Milestone substantially exceeded / 491,164 households (196%)
	1.2: Percentage of households in LIFT villages below the poverty line	28%	Data collected biennially / NA
2. Decreased vulnerability of poor households to shocks, stresses and adverse trends	2.1: Number of households in LIFT villages with increased asset ownership	250,000	Milestone substantially exceeded / 522,233 households (209%)
	2.2: Number of households in LIFT villages with increased income diversity score	100,000	Data collected biennially / NA
	2.3: Number of people whose resilience and ability to cope has increased	1,135,000	Milestone substantially exceeded / 1,966,012 people (173%)
3. Improved nutrition of women and children	3.1: Number of households in LIFT villages with an acceptable dietary diversity score	250,000	Milestone moderately exceeded / 325,723 households (130%)
	3.2: Number of households in LIFT villages with 12 months of adequate HH food provisioning	500,000	Milestone met / 492,435 households (98%)
	3.3: % of moderately/ severely stunted children under 5 years in LIFT villages	28%	Data collected biennially / NA
	3.4: Proportion of children under 5 years with diarrhoea in the previous 2 weeks	19%	Data collected biennially / NA
4. Improved policies and effective public expenditure for pro-poor rural development	4.1: Number and type of public sector policy and programme changes supported by LIFT	8	Milestone substantially exceeded / 20 changes (250%)
	4.2: Number and type of changes in public rural development budget allocation/spending supported by LIFT	2	Milestone substantially exceeded / 5 changes (250%)

In 2016 LIFT met or exceeded the targets of all seven purpose-level outcomes for which data was collected. For outcomes 1 (increased rural incomes), 2 (decreased vulnerability) and 4 (improved policy) the available evidence suggests that LIFT is on track to substantially exceed the 2018 end of programme target. For outcome 3 (improved nutrition), LIFT is on track to at least meet its end of programme target, although progress is not as impressive as for the other outcomes. Where survey data was not collected this year, output data from IPs and qualitative evidence from interviews, a field visit and internal reports suggests that LIFT is on track to the other indicators.
### Overall output score and description
LIFT has received an overall review score of A+, moderately exceeding expectations. This is based on individual output scores (of A++, A+, A+, A+, B, A, A+ and A++) against challenging milestones in the new logframe, impressive performance against outcome indicators, substantial progress across most cross-cutting themes, clear evidence of leveraging increased investment from the private sector (through work with Yoma Bank and the Currency Exchange Hedging Window), and the overall impression of performance gained from the review (including the demonstrated ability of the fund to respond flexibly to new opportunities throughout the period). Quantitative logframe performance, collected through LIFT’s household and tracking surveys and IP data, is corroborated by qualitative data from stakeholder interviews (e.g,. another LIFT donor describing the FMO as “exceptional, the best levels of professionalism and quality I’ve ever worked with”), a field visit to three Delta programme projects and a desk review of programme documentation including the recent Independent Interim Review and individual project reviews and case studies.

Against its output milestones, LIFT has substantially exceeded expectations for increasing sustainable agriculture and farm-based production (output 1) and generation of policy relevant evidence on pro-poor development (output 8). It has not met expectations for improved nutrition, sanitation and hygiene practices (output 5). All other outputs have either moderately exceeded (outputs 2, 3, 4 and 7) or met expectations (output 6).

### Key lessons
Cross-LIFT lessons and recommendations are described on pages 3-4 above.
### Has the logframe been updated since the last review?
A new logframe and ToC were developed in 2015 (approved by the FB in October 2015) to align with LIFT’s 2014-18 strategy (developed the previous year). In late 2016, the logframe’s milestones, targets and output impact weights were revised to increase ambition and reflect direction of the fund (approved by the FB in May 2017). The targets of 10 indicators were increased considerably as a result of LIFT’s rapidly expanding financial inclusion programmes. For example, the target for households reporting increased incomes rose from 364,119 households to 520,000. The targets of the policy related indicators also increased substantially, due to a growing focus of FMO and IPs on policy support. For example, the target for policy changes increased from 13 to 25 and the target for policy-oriented events increased from 54 to 130.

LIFT’s current logframe consists of four purpose-level outcome statements, with two to four indicators assigned to measure each high-level outcome (see above). These 11 purpose-level indicators include measuring income levels, income diversity, asset ownership, resilience (including DFID KPI 4), food security, diet diversity, stunting and public and private policy and expenditure changes. The new logframe also consists of eight programme-level outcome statements, with two to six indicators assigned to measure each, which includes both outreach and outcome-types of indicators. The 25 programme-level indicators measure such things as use of improved agricultural practices, agricultural productivity, establishment of enterprises, use of financial services, awareness of women and children’s nutritional needs, child diet diversity, exclusive breast feeding, use of improved sanitation facilities and water sources, and policy-oriented events and publications.

To measure indicators more accurately and consistently, all purpose-level indicators are now measured by the LIFT Household Survey and Household Tracking Survey. The results of the programme-level indicators will have two sources: IP monitoring data mostly for the outreach-related indicators and LIFT surveys mostly for the outcome-related indicators.

This is the first Annual Review under LIFT’s new logframe. LIFT’s ToC (Annex 4) underpins both the logframe and current strategy.

C: DETAILED OUTPUT SCORING
NB: LIFT’s logframe and Theory of Change refers to ‘programme outcomes’ and ‘process outcomes’. To match with DFID’s Annual Review terminology, these are referred to as outcomes and outputs in this document.
Output title	Increased sustainable agriculture and farm-based production by smallholder farmers
Output number per LF	1	Output Score	A++
Risk:	Moderate	Impact weighting (%):	10%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
1.1: Number of LIFT households reached by advisory services	150,000	Milestone met / 163,898 households (109%)
1.2: Number of households in LIFT villages who trial or adopt improved practices, inputs and technologies	130,000	Milestone substantially exceeded / 265,755 households (204%)
1.3: Number of households in LIFT villages with an increase in productivity – crops only	130,000	Milestone substantially exceeded / 202,193 households (156%)

### Key Points
Overall output 1 has substantially exceeded expectations, scoring an A++.

Since 2010, 30 IPs have reached a cumulative total of nearly 164,000 households with advisory services (1.1), meeting the milestone. Of these, 32 percent were female headed households. In 2016, 10 IPs[5] have reached nearly 25,000 households, mostly in new programme areas. These included:
[5] Food Security Working Group (FSWG), Golden Plain, International Council for Research in Agroforesty (ICRAF), International Fertilizer Development Center (IFDC), International Rescue Committee (IRC), Link Emergency Aid and Development (LEAD), MercyCorps, Radanar Ayar Association, Save the Children, Terra des Hommes (TDH), and Welt Hunger Hilfe (WHH).
Golden Plain advised famers in the use of green manure fertilizer;
- Mercy Corps and East West Seed field teams organized farmer outreach and extension trainings in supply chain development that included seedling trays, plastic mulching and trellis netting;
- Mercy Corps and a private company, AWBA, provided technical assistance to farmers through demonstration plots, as well as through on-call services and a mobile app;
- Radanar Ayar Association trained farmers in seed and gram production through extension services;
- Terre des Hommes trained farmers in hydroponic systems, drip irrigation systems and pest management;
- TAG provided advanced bee keeping trainings to commercial bee keepers; and
- In the Tat Lan programme, IRC and Save the Children provided advisory services to farmers through on-call services and demonstration plots in seed production and multiplication, and in the production and use of natural fertilisers.
- An estimated 204,000 households trailed and/or adopted improved practices, inputs and technologies (1.2) in 2016. Meaning that overall 265,755 households have since the baseline, substantially exceeded the milestone. The 2016 estimate is based on extrapolating the percentage of households reporting trial or adoption in the tracker survey (15%) to the number of LIFT households[6]. The percentage was lower for female-headed households (10%) than male-headed ones (16%).
  [6] This agreed method for estimation is used for many of the other indicators throughout this section. The explanation is not repeated.
- An estimated 106,000 households increased crop productivity (1.3) in 2016, bringing the total number to 202,193 since 2015. This substantially exceeds the milestone. Forty-three percent of LIFT households surveyed reported having grown a major crop in the past 12 months, 19.5% of which reported an increase in crop productivity. The figure was significantly lower (13%) for female-headed households compared too male-headed ones (20%). One of the reasons for this is likely to be that female heads of households spend comparatively less time in the field conducting paid work and, instead, conduct more non-paid activities such as collecting water, cooking and caring for children.

### Summary of responses to issues raised in previous annual reviews
As recommended in last year’s annual review, LIFT revised its indicator targets to take into account allocated funding levels, severe weather events, and the baseline findings from the 2015 household survey. The FB approved these revised targets in May 2017.

### Recommendations
- LIFT to consider which partners (civil society, INGOs, private sector) are best placed to provide advisory services to households, to support the design of future funding windows.
- LIFT to prioritise comparative analysis of the impact of activities across its two ‘tiers’ of activity (i.e. areas receiving financial inclusion activities only vs. those receiving financial inclusion and other LIFT activities, such as advisory services).

Output title	Improved market access and market terms for smallholder farmers
Output number per LF	2	Output Score	A+
Risk:	Moderate	Impact weighting (%):	10%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
2.1: Number of LIFT households who are members of functional producer groups	54,000	Milestone met / 53,382 households (99%)
2.2: Number of LIFT households adopting new marketing practices	6,473	Milestone substantially exceeded / 10,868 households (168%)
2.3: Number of households in LIFT villages securing higher returns (profit) from agriculture activities	130,000	Milestone substantially exceeded / 185,674 households (143%)

### Key Points
Overall output 2 has moderately exceeded expectations, scoring an A+.

- In total just over 53,000 households receiving LIFT support were, or have, become members of functional producer groups (2.1) since the programme began. This meets the 2016 milestone. Of these, around 30 percent are female-headed and 7,762 households were recorded as members in 2016. This data is reported by IPs and aggregated by LIFT, including from: Mercy Corps (14,000 households), Oxfam (8,000 households), ActionAid (6,000 households), CESVI (3,500 households) and Proximity Design (3,000 households). The current methodology does not enable the programme to know the composition of the yearly total broken down by new or old members.
- An estimated 10,868 households have adopted new marketing practices (2.2), over 50% more than this year’s milestone. Between 2015 and 2016 there was a 7 percent increase in households reporting adoption. Male-headed households were around twice as likely to report the use of new marketing practices then female-headed ones.
Overall 185,674 households are estimated to have secured higher returns from agriculture (2.3) this year, exceeding the milestone by over 40%. In total, 14 percent of households reported higher returns during the period, typically from agriculture, livestock or fisheries. This included 15.6 percent of male-headed households and 7.1 percent of female-headed households.
### Summary of responses to issues raised in previous annual reviews
As recommend in the 2015 Annual Review, LIFT continued to measure 2.3 through the household survey, instead of using IP data, plus recalculated the relevant targets based on funding amounts, severe weather events, and the baseline findings of the 2015 household survey.

### Recommendations
- It is difficult for LIFT to maintain a clear understanding of the changes in producer group members overtime. The fund should consider whether additional data could be collected to support these numbers, e.g. through the household survey.
- LIFT to consider whether additional support targeted specifically at women-headed households is needed to complement existing activities under this output.

Output title	Increased and safe employment in non-farm activities for smallholders and landless
Output number per LF	3	Output Score	A+
Risk:	Major	Impact weighting (%):	10%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
3.1: Number of LIFT households supported in non-agricultural skills development	32,000	Milestone met / 33,065 households (103%)
3.2: Number of trained people who establish their own enterprises or become employed	80,000	Milestone met / 78,999 people (99%)
3.3: Number of households in LIFT villages with an increase in income from non-agricultural activities	150,000	Milestone substantially exceeded / 277,233 households (185%)

### Key Points
Overall output 3 has moderately exceeded expectations, scoring an A+.

A total of 33,065 households have received training or support in non-agricultural skills development (3.1) since 2010. This meets the 2016 milestone. Training and support has been provided through 21 IPs, and sixty-two percent of recipients have been women. 2016 was a particularly impressive year for this activity, as over half the results (18,000 households) were achieved in this period. The majority of support has been vocational training on themes including tailoring, hairdressing, mechanics and food processing. More recently, training has expanded to the introduction and expansion of apiculture (beekeeping).
A highlight has been Mercy Corps and Swiss Contact’s work on Technical and Vocational Education and Training under the Delta programme. This includes a programme to train rural landless individuals and households in non-farm employment. Priority occupations have included mechanics, carpentry, masonry, garment manufacturing and hospitality. The project aims to train 1,400 students in total.
- Nearly 80,000 trained people have established a business or become employed (3.2) since 2010, meeting the milestone. Forty-two percent of these were women. The most common enterprises established were small rice, pulse and cereal mills, fisheries, beekeeping, handicrafts, and weaving and woodwork. This data is reported by IPs, highest contributors include: MARC (51,867), UNDP (6,544) and PACT (3,165).
- An estimated 277,233 households in LIFT villages have increased their incomes from non-agricultural activities (3.3). This is 85% higher than the 2016 milestone, substantially exceeding it. This estimate is based on 17 percent of households reporting increased non-agriculture incomes in the 2016 tracking survey. The proportion was lower for female-headed households (13%) than male-headed ones (18%).
### Summary of responses to issues raised in previous annual reviews
NB: None of the remaining outputs had specific recommendations in the last Annual Review, in part due to the restructure of the logframe. A full list of responses to previous recommendations is included in Annex 2.
### Recommendation
LIFT needs to draw together its activities on improving working conditions and combatting human trafficking, to enable it to respond cohesively to the UK’s emerging agenda on modern slavery. This is likely to include contributing to the evidence base on child labour in agriculture.

Output title	Increased access to adequate and affordable financial services
Output number per LF	4	Output Score	A+
Risk:	Moderate	Impact weighting (%):	25%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
4.1: Number of LIFT MFIs financially self-sustaining	8	Milestone substantially exceeded / 12 MFIs (150%)
4.2: Number of LIFT households with access to financial services (active clients)	1,500,000	Milestone met / 1,635,932 households (109%)

### Key Points
Overall output 2 has moderately exceeded expectations, scoring an A+.

Twelve LIFT-supported MFIs are now considered financially self-sustaining (4.1), 50% more than 2016’s milestone. To be classed as sustainable, the institution must be covering operational costs by income after adjusting for financial costs and inflation. LIFT’s support for the Myanmar microfinance sector has been wide-ranging. In 2016 it continued to support 56 microfinance partners, including:
9 local microfinance organisations;
- 38 credit cooperatives;
- 8 international microfinance organisations; and
- 1 private bank.
LIFT’s support to these organisations varies, focused predominantly around financial assistance, with additional technical assistance where necessary. Now that LIFT has helped to generate a diverse microfinance market in Myanmar, there is a question as to how much additional support MFIs need going forward other than to particularly tricky areas (e.g. conflict affected ones) that whey would not otherwise prioritise.
Over 1,600,000 households have been provided with access to financial services (4.2), meeting the 2016 milestone. LIFT’s assistance to households through microfinance partners has grown rapidly since 2011, predominantly through access to loans. Ninety-four percent of clients are women, and almost 60% of LIFT-supported MFI staff. The fund’s microfinance support appears influential in helping rural households to ‘step up’ to new livelihood strategies including livestock, fisheries and aquaculture. In 2016, an increasing proportion of loans were disbursed for livestock (65%), almost twice as many as for crops (32%).
A field visit for this review observed first-hand a variety of new livelihood strategies adopted by microfinance recipients, including the purchase of trucks for rural households to diversify into transportation and the establishment of several village shops.
LIFT has also increased its engagement with the private sector, in ways not fully captured by the logframe, to deliver poverty reduction and improved resilience. These include:
- LIFT worked with Yoma Bank to establish the Agribusiness Finance Programme in January 2016. This involves LIFT providing a $9m partial risk guarantee to reduce Yoma’s exposure to the risk of delinquent hire-purchase loans (leveraging $43m from Yoma; five times as much as LIFT’s contribution). This has enabled Yoma to offer more attractive hire-purchase loan terms, such that almost 3,000 rural small and medium businesses were financed for the purchase of tractors, combine harvesters and transportation vehicles. The actual impact is much larger as almost all of these businesses rent out their machinery to other farmers. It is estimated that tractors financed by the programme are providing land preparation services to 64,884 households, and financed combine harvesters are providing services to 16,214 more. The economic impact on these households is substantial. For example, the estimated cost savings of using these tractors instead of draught animals is $423,000 for one growing season. In addition, the estimated cost savings for using the combine harvesters instead of manual labour is $1,561,800.
- In partnership with The Currency Exchange, LIFT opened the Currency Exchange Hedging Window to foreign direct investors in December 2016. This enables institutional investors to lend in MMK to Myanmar’s MFI sector with protection from exchange volatility. A LIFT subsidy of $10m was able to leverage $70.6m of foreign direct investment from institutional investors. This reached 14 MFIs, eight of them new to LIFT, providing access to financial services for up to 350,000 clients.
### Recommendations
- LIFT to revisit the additionality of its support to MFI institutions, now that the sector is thriving in most parts of Myanmar (and the additional social returns to increased donor support are falling). Going forwards, it may be more appropriate for the programme to limit its support to MFIs expanding into conflict-affected or remote areas, alongside expansion of the currency hedging window.
- LIFT to update its logframe to better capture its private sector work, for example including indicators on the amount of funding leveraged for banks to support rural small and medium businesses. As activities switch to this type of support, careful attention to gender disaggregation will also be needed (as it may be a lot trickier to reach women and women-led businesses than it has been with MFI support).
- LIFT to consider expanding the Agribusiness Finance Programme to other banks, to minimise potential market distortions. Supporting second movers to follow in Yoma’s lead could help to drive systemic change across the rural finance sector (as opposed to one pioneer bank operating in isolation with donors).

Output title	Improved nutrition, sanitation and hygiene practices
Output number per LF	5	Output Score	B
Risk:	Moderate	Impact weighting (%):	10%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
5.1: Number of LIFT households reached with nutrition sensitive information	150,000	Milestone moderately not met / 127,844 households (85%)
5.2: Number of people with awareness of the nutritional needs of women and children *	60,000	Data collected biennially / N/A
5.3: Number of children 6-23 months with “acceptable” dietary diversity *	18,000	Data collected biennially / N/A
5.4: Number of infants (0-5 months of age) who received only breast milk in previous 24 hours *	30,000	Data collected biennially / N/A
5.5: Number of households in LIFT villages using safely managed sanitation services	225,000	Milestone met / 219,850 households (98%)
5.6: Number of households in LIFT villages using safely managed and protected drinking water services	220,000	Milestone substantially not met / 165,844 households (75%)

* Only measured in biennial Household Survey (due next year)
### Key Points
Overall output 5 has moderately not met expectations, scoring a B.

- LIFT has reached nearly 128,000 households with nutrition sensitive information (5.1) since 2010. The programme has moderately not met the milestone, achieving 15% less than expected. Underachievement is predominantly due to the delayed start-up of LIFT’s newer nutrition projects (e.g. nutrition activities in the Uplands were re-calibrated to make way for emerging GoM priorities) and because of recent logframe changes that include an increase in ambition. Further, the social marketing outreach of some related activities, such as fortified rice distribution, has not reached as many rural households as hoped due to an initial focus on supermarkets in urban areas.
- Nonetheless progress in 2016 was considerable, with 55,000 households participating in health and nutrition training sessions and 7,000 receiving maternal and child cash transfers (MCCTs). The majority of outreach has been health and nutrition training sessions, which have evolved throughout the programme to focus predominantly on nutrition (as opposed to general health). Seventy-four percent of all participants have been women. The most active IPs under this output are IRC in Rakhine, Help Age in the Dry Zone, and Save the Children (through MCCTs) across the Dry Zone, Delta and Rakhine.
A field visit carried out for this review observed how enthusiastic many new mothers in the Delta are about the nutrition sensitive information they have received. These sessions appeared to be successfully convincing mothers to change what they fed new-born babies (e.g. several mothers spoke passionately about how much healthier and more energetic their most recent children are compared to older siblings who were born before nutrition information had been provided). Nonetheless, superstitions held by many older members of the community remain difficult to shift.
As 2016 was a tracker survey year, data for awareness of nutritional needs (5.2), children with ‘acceptable’ dietary diversity (5.3), and infants who received only breast milk (5.4) was not measured. It will be collected in 2017 as part of the full household survey. There is indicative evidence that decent progress has been made against these milestones due to the reach of LIFT’s nutrition awareness and MCCT activities in 2016, which drive progress under these outputs. Although given the moderate underachievement on output indicator 5.1, active monitoring of these activities will be necessary this year. The preliminary findings of the mid-term review of the Legacy MCCT project in the Dry Zone suggest these activities are progressing well.
- In June 2016 LIFT organised a high-profile event in Labutta to launch the Bright SUN nutrition project that features MCCTs. This successful launch included senior officials from the National Nutrition Centre, the Department of Social Welfare, local and regional governments and the press.
- In addition, the LIFT-funded PATH project received approval from Myanmar’s Food and Drug Authority for its fortified rice kernels as well as for three fortified rice production facilities. Fortified rice is now distributed through 28 supermarkets and 218 retailers in Yangon and Ayeyarwady regions.
- An estimated 219,850 households in LIFT villages are using safely managed sanitation services (5.5), meeting the 2016 milestone. This estimate is extrapolated from the 11 percent increase in households reporting the use of such services between 2015 and 2016. The proportion is slightly higher for female-headed households (13%) than male-headed ones (11%).
- Just over 165,000 households in LIFT villages are estimated to be using safely managed and protected drinking water services (5.6). LIFT achieved only 75% of the milestone, which, as above, is be due to delays in the some projects providing nutrition-sensitive information and recent increases in milestone ambition. The estimate is based on a two percentage increase in households reporting their use in the tracker survey. The proportion was higher for female-headed households (2.9%) than male-headed ones (1.7%).
### Recommendation
- LIFT and the FB to pay close attention to progress under this output, to establish whether the current underperformance against milestones is simply the result of delayed projects or a result of more systemic issues with LIFT’s ToC. Close attention should be paid to whether nutrition sensitive information is actually leading to the behaviour change expected.
- Social marketing activities to ensure adequate focus to the ‘bottom of the pyramid’ to ensure impact on the nutrition of poorer rural households, alongside sales in urban supermarkets that support financial sustainability.
Output title	Safeguarded access to and sustainable use of natural resources for smallholders and landless
Output number per LF	6	Output Score	A
Risk:	Major	Impact weighting (%):	10%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
6.1: Number of LIFT villages where common property resource management is taken up	370	Milestone substantially exceeded / 609 villages (165%)
6.2: Number of households in LIFT villages benefitting from protected/ managed natural resources	45,000	Milestone moderately not met / 38,846 villages (86%)

### Key Points
Overall output 6 has met expectations, scoring an A.

Over 600 villages have taken up common property resource management (6.1), substantially exceeding the 2016 milestone of 370. This is based on extrapolating the percent of interviewed villages that reported that they were implementing a new type of resource management (30%) in the tracking survey. The majority of this progress was in 2016, when 468 villages are estimated to have taken it up. IPs contributing to these results include Better Life Organisation, Save the Children, ICRAF (World Agroforestry Centre) and the International Rescue Committee, who are working with villages on community forests, wind break plantations, grazing lands, mangroves, wild fisheries, watersheds and embankments.
A particular highlight has been Save the Children’s work in Rakhine, where the project has worked with communities to establish 130 miles of embankments and over 70 sluice gates to protect 26,000 acres of paddy land from salt water intrusion and monsoon flooding.
Another example is ICRAF’s ecosystem conservation work in Chin and Shan which has included establishing demonstration plots of nitrogen-fixing trees.
Nearly 39,000 households in LIFT villages are estimated to be benefitting from protected and/or managed natural resources (6.2). This is 86% of the 2016 milestone, which is therefore moderately not met. However, only 932 additional households are estimated to have benefitted, a surprisingly low percent increase given LIFT’s progress under the indicator above. The logical reason for this could be that there is a substantial lag time between natural resource management being adopted and the surrounding community experiencing the benefit. Nonetheless, this assumption requires testing and close attention should be paid to this activity in the coming year.

### Recommendations
- LIFT and the FB to pay close attention to whether the number of households reporting to have benefitted from natural resource management begins to respond to activities or not. Whilst current underperformance for this indicator may be the result of a lag before the impacts are felt, it could also be evidence that some of the assumptions underlying LIFT’s ToC for this theme are incorrect.
- LIFT to ensure its activities under this output are fully represented in its climate adaptation strategy.

Output title	Strengthened capacity of communities, government, CSOs and enterprises to support food and livelihoods security
Output number per LF	7	Output Score	A+
Risk:	Major	Impact weighting (%):	15%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
7.1: % of LIFT funds managed by national entities	20%	Milestone substantially exceeded / 39% national entities (+19ppt)
7.2: Number and type of local groups and institutions supported to promote food and livelihood security	1,800	Milestone moderately exceeded / 1,972 groups and institutions (110%)

### Key Points
Overall output 7 has moderately exceeded expectations, scoring an A+.

In 2016, 39%, or $23m, of the total LIFT budget was managed by LIFT entities (7.1). This substantially exceeded the milestone, nearly doubling it, and is a substantial increase from the 14 percent in 2015. A major focus of LIFT’s new strategy is the strengthening of local capacity, including of government, CSOs and private enterprises. During the review period, LIFT signed 24 new contracts, of which 9 were directly with national NGOs and four included national sub-IPs. Other progress in engaging with local entities included:
- the opening of three small grants windows, in the Delta, Dry Zone and uplands, for township-level CSOs that work on livelihood system strengthening with other local actors; and
- the design and tendering of a strategic civil society partnerships facility, through which three organisations (the Food Security Working Group, the Gender Equality Network, and Land Core Group) will act as strategy partners to strengthen civil society beyond their own organisation.
Engaging with civil society and developing the capacity of key delivery organisations is an important part of ensuring the sustainability of LIFT’s activities. A critical question going forwards will be how much resource LIFT has available to support capacity development alongside this, and whether this element of the programme might be more efficient if tendered out to others (large CSOs, INGOs or the private sector).
Since the start of LIFT, 1,972 local groups and institutions have been supported to promote food and livelihood security (7.2). This moderately exceeds the 2016 milestone. This data is reported by IPs, and a sharp increase has been reported in 2016 due to a broadening of the definition of ‘local groups and institutions’ to include groups such as village organisations, producer and marketing groups, mother-to-mother support groups, and savings and loans groups. The IPs supporting the largest number include the Tat Lan programme (477 groups), Save the Children I the Bright SUN programme (262 groups), Mercy Corps (169 groups) and Action Aid-SEDN (120 groups).

### Recommendation
- LIT to closely monitor the results, management costs and due diligence aspects of its scale-up in funding to local entities. This should enable the fund to take a view on whether different modalities are needed to deliver scaled-up support to civil society.
- LIFT to pay close attention to its civil society activities, to ensure they provide responsive investment and support as needed. A flexible approach may be necessary where given groups need additional support in addition to any scale-up in funding.

Output title	Generation of policy-relevant evidence regarding pro-poor development
Output number per LF	8	Output Score	A++
Risk:	Minor	Impact weighting (%):	10%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	Yes

Indicators	Milestone	Progress
8.1: Number of LIFT-supported policy oriented events organised.	70	Milestone substantially exceeded / 103 events (147%)
8.2: Number of LIFT policy-oriented publications published and disseminated to stakeholders	40	Milestones substantially exceeded / 49 publications (123%)

### Key Points
Overall output 8 has substantially exceeded expectations, scoring an A++.

LIFT has now supported 103 policy orientated events (8.1), nearly 50% more than this year’s milestone. Almost half of these (49) were convened in 2016, of which 47 were organised by IPs and two by the FMO. Highlights include:
The ILO project held consultations with parliamentarians (including the Committee on Local and Overseas Employment, International Relations Committee, and Women and Children Committee) on labour migration management in Nay Pyi Taw. These increased awareness and capacity on migration.
- An IOM-led research project conducted sixe pre-study consultation workshops in Shan State, Mandalay Region, Rakhine State, Ayeyawady Region, Yangon, and Nay Pyi Taw.
- Under the Strengthening Civil Society programme, the Gender Equality Network organised several policy events, including a workshop on Prevention and Protection of Violence Against Women Law.
LIFT partners also organised several high level consultations concerning household and community resilience and land tenure policy (Land Core Group), in which Union and State/Regional officials and LIFT Fund Board members participated.
LIFT’s IPs have published and disseminated 49 policy-orientated publications to stakeholders (8.2). This is twenty-three percent more than 2016 milestone. These are all available on LIFT’s website, which averaged 150 user sessions per day in 2016. LIFT has a clear strategy for disseminating its own publications, but it leaves IPs to disseminate their own work. Publication highlights from 2016 include:
LEARN (Save the Children) published a two-part report concerning undernutrition in Myanmar: A Critical Review of Literature and a Secondary Analysis of LIFT 2013 Household Survey Data. ILO published an Analysis of the Myanmar Law Relating to the Overseas Employment from 1999.
- ILO published an Analysis of the Myanmar Law Relating to the Overseas Employment.
- In the area of financial inclusion, LIFT published Smart Money Management: A Basic Financial Literary Booklet. Micro-credit Ratings International Limited also published LIFT microfinance projects evaluations as well as a study Cooperative Approaches to Farmer Organisations and Cooperatives in LIFT Partner Projects.
- GRET also published several reports, including a land tenure study: Land Dynamics and Livelihoods in Peri-Urban Yangon: the Case of Htantabin Township. The Land Core Group also commissioned a land tenure rapid assessment in Pyapon and Maubin townships in the Delta.
LIFT’s FMO also supported several important publications. Michigan State University, in collaboration with the Center for Economic and Social Development and the International Food Policy Research Institute, published six analytical reports concerning the dynamics of rural transformation, agriculture development, land tenure, and migration. Further, the World Bank was supported to publish an Analysis of Farm Production Economies.
Overall LIFT has had significant success in influencing policy across a variety of thematic areas. This is partly driven by its ability to respond flexibly to emerging policy priorities through tweaking the focus of new grant windows but also due to its use of targeted technical assistance with support from its network of advisors within government and from the FB. LIFT has:
- placed advisors in Government, including substantial technical assistance supporting the Department of Rural Development in its bottom up village development planning, and consultants to support the Agriculture Policy Unit;
- funded policy and research engagement in Nay Pyi Taw through MSU, complemented by FMO staff providing intensive advice (for example in the development of the Global Agriculture and Food Security Program);
- networked and leveraged the advisors placed in Nay Pyi Taw by other donors, such as the EU’s advisor working on land issues; and
- used the FMO’s policy unit, of one international and one national staff, to support coherence across these activities (based in Yangon with c.40% time spent in NPT).
Nonetheless, the review observed that LIFT could do more to decentralise policy support from a number of key positions to incentivise all key programme staff to think more holistically about their policy influencing role, in addition to their focus on programme management. A lack of a more permanent policy presence in the Nay Pyi Taw may also be limiting policy coherence in some areas.

### Recommendations
- LIFT to incentivise all senior programme staff to engage in strategic policy influencing.
- LIFT to prioritise development of its delayed policy engagement strategy, enabling it to better capture the range of current work and interactions with government, as well as to provide guidance on how to take an increasingly strategic approach in future. In collaboration with other UNOPS funds, LIFT should also use this as an opportunity to decide how to strengthen its policy presence in Nay Pyi Taw.
- LIFT to prioritise resources to ensure systematic knowledge management (see Section H), with a view to set strategic direction for any future phase the programme. To support this, LIFT might consider mapping the evidence base against LIFT’s rural transformation strategy, i.e. against the narrative of ‘stepping up’, ‘stepping out’ and ‘hanging in’, and using this to inform the relative size and of future windows.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
### Key cost drivers and performance
Key cost drivers relate to the procurement of goods and services from implementing partners through grants and non-grant support for the delivery of projects. At the Fund Management Office the cost drivers are the administrative costs of managing the fund, including from the salaries of staff, travel and expenses, and other associated costs.

#### Table 2 – LIFT expenditures for the year 2016 (US$)
Activity	Budget	Actual	Progress
Grants & Supports
Grants to implementing partners	51,019,346	46,185,885	(4,833,461)	-9%
Non-grant supports	5,962,739	6,025,222	62,483	1%
Research	1,988,838	1,469,783	(519,055)	-26%
Operation of the Fund Manager’s office	4,403,718	4,139,625	(264,093)	-6%
Support to the Fund Board	17,135	13,292	(3,843)	-22%
Facilities and administration	1,225,459	1,126,843	(98,616)	-8%
Total	64,617,235	58,960,650	(5,656,585)	-9%

In 2016, 88.6% of LIFT expenditure was programme implementation, 2.5% on research, and 9.0% on the Fund Manager’s office, support to the Fund Board, and facilities and administration. This represents a slight increase (2.2 ppt) in the proportion of total expenditure since 2015 (though is a decrease from 2014), driven largely by increases in expenditure within the Fund Manager’s office. This is in spite of an 8.5% decrease in total expenditure from 2015 to 2016.

LIFT has identified cost drivers and controls in all of its 37 projects. LIFT requires all of its projects to follow stringent procedures that include requiring the use of recognised public procurement procedures, and benchmarking salaries and travel against other projects and with market prices in Burma.

### VfM performance compared to the original VfM proposition in the business case
The original business case outlined VfM across four domains: intervention design; outreach; selected outcomes overall and for specific interventions; and use of VfM results.

On intervention design, the LIFT Value-for-Money guidelines outline robust appraisal mechanisms that can incorporates cost-benefit analysis, comparison with alternative approaches and designing M&E systems at setup. In 2016, 31 out of 37 (84%) projects in the geographic programmes that were contracted or extended provided value for money considerations that utilised quantitative or qualitative approaches in their first and/or revised proposals that enabled FMO staff to conduct VfM assessments.

On VfM in LIFT’s outreach, the 2016 Annual Report outlines a cost per household reached of $36, or $8 per individual, which is below the $52 estimate set out in the business case and compares favourably against other programmes in the Philippines, Vietnam and China[7]. Disaggregating this information by three major programmes (agriculture production, maternal and child cash transfer, and microfinance) indicates the range of cost per beneficiaries for each area of intervention. LIFT, through its implementation of the VFM guidelines, should compare these respective costs against estimated benefits to consider outcome level value-for-money across the programme components.
[7] Benchmarks taken from Table 2, p27, Resilient and Inclusive Rural Growth business case.

#### Table 3 – VfM in LIFT’s Outreach by Select Programme Component for 2016
Programme Component	Number of Projects	Number of households reached 2016	LIFT expenditure 2016	Cost per household (USD)	Cost per Individual (USD)
Agriculture production	17	54,216	8,322,418	154	35
Maternal and child cash transfer (MCCT)	4	22,025	1,714,947	78	NA
Microfinance (active clients)	10	1,635,932	23,789,358	14.5	3.3

On selected outcomes overall and for specific interventions, progress on the log frame indicates that in 2016 LIFT met or exceeded its targets for 24 of the 27 outcome indicators. Compared against its original milestones for 2016, 491,164 households in LIFT villages have an increased income (versus 250,000 milestone); 1.966 million people have improved resilience (versus 1.135 million) and 325,723 households have an acceptable dietary diversity score (versus 250,000). Only for the indicator on adequate household food provisioning does LIFT marginally miss its milestone (by 2%).

On the use of VFM results in ongoing decision-making, the LIFT Value-for-Money guidelines outline implementing partner performance monitoring approaches. This includes expenditure tracking against budget, for which 81% of projects spent less than 90% of their planned budget and 43% of projects spent less than 70% for 2016, driven by a number of projects being in the inception phase or working in conflict affected areas. Other metrics will include progress against work-plan comparison of expenditure versus performance and potential for replication/upscale. LIFT also plans to conduct value for money assessments in eight projects to inform programme design and implementation.

### Assessment of whether the programme continues to represent value for money
The LIFT programme continues to represent value for money. In 2016, LIFT met or exceeded almost all of its original milestones for the year and delivered outreach at a cost below that expected by the original business case. It has also delivered VfM from its policy work on agriculture, which helped leverage increased foreign direct investment, and on nutrition and social protection, which led to increased budget allocations from government.

The programme has a robust set of value-for-money guidelines developed in November 2016 to draw from, though the initial reporting of a number of the metrics will not be complete until the 2017 LIFT Annual Report. The availability of these metrics, alongside the eight project specific value-for-money assessments, will enable a more comprehensive value-for-money assessment to be conducted for the next DFID Annual Review. LIFT should benchmark cost-effectiveness metrics defined in the VFM guidelines against comparator programmes to enable a stronger assessment of outcome level VFM across its various components..

The slight increase in the proportion of total expenditures being undertaken by the Fund Manager’s Office can represent value-for-money if it delivers VfM through its appraisal, monitoring and evaluation functions. The additional reporting set out in the value-for-money guidelines for the FMO will enable the next review to consider this in greater depth. Furthermore, while continued underspend against programme budget has not had an adverse effect on the delivery of results, the FMO should consider mitigating actions at appraisal and implementation stages to ensure continued value-for-money in the instance that further exogenous events continue to have an adverse effect on expenditure against planned budget.

Some of the value for money provided by LIFT is difficult to quantify. Two of the other donors interviewed for this review referenced the convening power of UNOPS as LIFT’s FMO as an integral part of the programme. In particular, there appears to be a strong benefit of having a UN agency as the implementer because it is able to play a facilitating role between donors and government that other organisations might be unable to achieve. There are also likely to be agglomeration effects of UNOPS running other large Myanmar funds alongside LIFT, including 3MDG, the Global Fund and the Joint Peace Fund. Examples include: weekly communications meetings between the funds to shape media narratives, a shared UNOPS coordinator based in Rakhine, the use of joint shared-services across the funds, and the development of cross-programme thematic expertise (e.g. on nutrition).

Quality of financial management
The most recent due diligence assessment (2015) found LIFT’s financial management system to be adequate for accountability. LIFT’s FMO has an experienced finance team and clear separation of duties. In January 2016, UNOPS introduced a new Enterprise Resource Planning system (OneUnops, based on aggresso), which allows a diversified Chart of Accounts to allow tracked and monitoring of expenditures in detail. Incoming funds are identified via accounts receivable entries which are requested at field level and monitored and managed at HQ level.

The LIFT finance department keeps the cash flow statement updated; this includes statements on the amount of grants to be issued and the expected cash inflows (from donors) for the current year and also coming years. LIFT provides regular and timely fund flow updates at Fund Board meetings, which allow donors to manage their contributions to the trust fund as necessary. LIFT also submits a detailed financial report annually and a certified financial statement.

LIFT-funded projects are audited on an annual basis. After an audit each IP prepares an audit action plan to address the audit findings. The 2015 FMO audit report had no observations. In terms of audits of implementing partners, 55 projects had their expenditures audited in 2016 with a total of ten observations rated as “high priority” by the auditors. As of August 2017, three of the “high priority” observations have been addressed and closed. For those remaining observations, the auditors have followed up during their audit of the IPs this year conducted in June-August 2017, audit reports are yet to be received.

LIFT’s forecasting and invoicing processes for DFID were accurate and efficient throughout 2016.

Date of last annual report	28/04/2017
Date of last audited annual statement	29/06/2017

E: RISK

### Overview of programme risk
Overall LIFT is judged to be moderate risk on DFID’s risk scale. The sheer size of the programme, including 71 live projects at present, allows it to maintain a portfolio of both higher and lower risk activities.

LIFT is operating in an environment in which the pace of economic change and (some) political reform is high, creating both risks and new opportunities. Much of the success of the programme therefore depends on its ability to adapt in response to the changing context. LIFT’s regular programming of new activities (i.e. launching of new competitive calls in geographic or thematic areas) allows it to be fairly nimble in this regard. Nonetheless there remain risks that poorly designed activities could exacerbate tensions, support the wrong groups and/or fail to deliver value for money. It is therefore likely that some activities will fail to deliver the results intended whilst others may have a greater impact than anticipated.

LIFT monitors and mitigates risk at three levels: individual project risks, predominantly the responsibility of the IP; geographic or thematic programme risks, the responsibility of the relevant FMO team; and cross-LIFT risks, which are regularly discussed between the FMO and the FB (every four moths). There are clear processes for escalating risks between each level.

LIFT’s current Risk Matrix includes risks categorised as stakeholder, operational, IP and programme risks. Headline risks include:
Stakeholder risks
- LIFT fails to support effectively the new Government of Myanmar
- Development partners fail to harmonise and align
Operating environment risks
- Political uncertainties undermine LIFT effectiveness
- Institutional policy development conflict with priorities supported by LIFT
Implementing partner risks
- Ineffective LIFT governance
- Weak technical capacity of FM and IPs
- Fraud and corruption
Programme risks
- Design of LIFT programmes
- Ineffective knowledge management
- Social and environmental consequences
- Delivery quality
- Sustainability of interventions
Each of these is broken down into specific sub-risks with clear mitigation plans, a risk owner and a timeframe for action. The sub-risk is also scored on a four-point scale. For example, the first headline risk listed above (on supporting the Government) is broken down into five distinct possible impacts and mitigation strategies, some owned by the FMO and others by the FB.

LIFT’s risk categories map closely to DFID’s risk framework, but not all categories are fully captured. Most of DFID’s seven risk categories are covered cohesively by LIFT’s processes, including external context, delivery, operational, fiduciary and safeguarding. Others, such as reputational risks, are closely monitored during FMO and FB discussions and through the design of new grant windows and other activities. Given the multi-donor nature of LIFT, full alignment with DFID’s risk terminology is not deemed necessary.

### Emerging risks and outstanding actions
In 2016 there were three main changes to the risk environment in which LIFT operates:
- An increasing proportion of LIFT funds were managed by local entities, including government, civil society organisations and private enterprises, as a result of LIFT’s strategy to increase efforts to strengthen local capacities. As described above, this included the signing of nine new contacts directly with national NGOs, and of another four contracts that include national sub-IPs. In 2016, LIFT also opened three new small grants windows for township level CSOs working on livelihood system strengthening with civil society, government and private sector actors. The increased focus on local entities brings its own operational and financial risks were new partners have lower capacity than other partners the programme works with. LIFT has maintained a close eye on the risks associated with this, including through careful due diligence processes, but will need to prioritise the development of a clear strategy for local actor support if it is serious about empowering these groups to deliver a substantial part of LIFT’s portfolio.
- Sustained conflict, despite the ongoing peace talks, impacted on the fund as it continued to expand into conflict-affected areas, including Kayin, Kayah, and Thantharyi. This has included working with new partners and stakeholders, and the programme has built on its 2015 work managing conflict-related risks to ensure adequate mitigation measures. LIFT also expanded its work in Rakhine, to cover 14 out of 17 townships, including new projects launched in Northern Rakhine (Rathedaung and Maungdaw). Rakhine continues to be an area of great need but immense difficulties, with new outbreaks of violence at the end of 2016 (and since) making the situation particularly complex and difficult. LIFT should continue to seek to share knowledge with other key stakeholders and government to mitigate where possible.
  - LIFT actively manages the risks of working in conflict-affected and post-conflict areas by consulting with a highly experienced Conflict Sensitivity Advisor, who has helped develop and implement a set of Conflict Sensitive Principles. In addition, this advisor has trained FMO staff in how to conduct conflict assessments, including written guidelines and several practical tools. The FMO used these principles and guidelines to further develop the Uplands programme, by conducting several conflict sensitivity assessments and engaging constructively with governments and ethnic armed groups.
- Another emerging risk is the capacity of the Government to coordinate donor programming in a constructive way. Whilst relationships with the Government of Myanmar have been positive across most of LIFT’s work, there is a risk that the GoM’s increased focus on donor coordination creates a bottleneck for approval of new activities. This is particularly pertinent in a country where decision-making remains highly centralised. LIFT’s FMO and FB should continue to closely monitor the development of the new Donor Assistance Coordination Unit and seek opportunities to assist it to become a constructive challenge function.
F: COMMERCIAL CONSIDERATIONS

### Delivery against planned timeframe
LIFT continues to exceed results on time in a challenging, and quickly changing, environment. The programme has met its targets in seven out of eight outputs, exceeding six of them. It has scored an A+ for the third consecutive year, in spite of a continued increase in logframe ambition. Against outcome milestones it is also on-track to exceed its end-of-programme targets.

### Performance of partnership
LIFT has clear processes in place to ensure due diligence of IPs awarded grants through windows, as well as of their sub-IPs. This includes careful due diligence assessments, and supplier (and sub-supplier) chain mapping.

The fund uses a ‘traffic light’ system to monitor the project management performance of all IPs. The results for the projects active in 2016 are summarised in Table 5. IPs received regular (biannual) feedback on how they are performing under each category, giving them the opportunity to improve project management if needed. Compared to 2015, the proportion of projects categorised as low risk has increased by eight percentage points.

Whilst LIFT provides regular project management performance assessments to IPs, it rarely has to intervene further to address poor performance. As LIFT increases the proportion of, potentially lower-capacity, local entities, it will need to ensure it can address weak programme management through both additional support and/or holding back payments if improvements are not forthcoming.

The FMO continues to have a productive relationship with IPs. Several IPs who were interviewed, commented on how they value technical input from FMO staff (e.g. in the co-creation of new financial inclusion activities). Others praised the clarity of terms of references for grant windows. One private sector company suggested that a clearer written-agreement at the start of new activities with businesses might make future partnerships easier.

#### Table 5 – Summary of risk assessment against project management process indicators
Indicator		Low risk (Green)		Medium risk (Yellow)		High risk (Red)
		Threshold	% Grants	Threshold	% Grants	Threshold	% Grants
1	Implementation rate	> 90% on track	38%	71 - 90% on track	24%	≤70% on track	38%
2	Annual expenditure	>90% spent	30%	71 - 90% spent	32%	≤70% spent	38%
3	Reporting timeliness	0 days late	77%	1 - 7 days late	21%	>8 days late	2%
4	Report completeness	100% complete	94%	71 - 99% complete	6%	≤70% complete	0%
5	Management controls	0 open observations	64%	1-3 open	20%	>3 open observations	16%
				observations
Overall rating 2016		49%		45%		6%
2015		41%		45%		14%
2014		51%		37%		12%
2013		48%		41%		11%
2012		32%		41%		32%

The relationship between the FMO and FB is an asset to the programme. Several FMO staff and FB members praised the role of DFID in particular, for steering the new strategy and providing continuous technical challenge. In 2016 the FB also included two external advisors: U Thant Myint U (political adviser) and Adam Burke (conflict).

Throughout 2016 LIFT also worked with other DFID programmes to share knowledge and support their activities. For example, it sits on the advisory committee for DFID’s Business Innovation Facility in Myanmar, and has provided support to DFID Burma’s DaNa Facility on how to run effective competitive grants windows in the country. It has also shown leadership in its engagement with 3MDG to enable greater collaboration on nutrition.

### Asset monitoring and control
LIFT’s operational guidelines clarify on the use, reporting and transfer of assets purchased by IPs. All assets purchased with LIFT funds are the property of the Fund unless a transfer of assets is formally approved. The FMO recognises the rationale of continuing to use assets for the intended purposes beyond the implementation period of LIFT funded projects and, therefore, allows the transfer of ownership to IPs (or appropriate NGO/CBO partners of IPs) upon project closure, if certain conditions are met and approved by the FMO.

IPs record all equipment on an inventory list with a description of the item, relevant serial numbers, location, purchase price and date, and a unique identification number. LIFT provides IPs with the required inventory list format. IPs report annually on their assets. The FMO also keeps an asset register for assets purchased for the FMO which is audited annually by the internal FMO audit.

LIFT FMO and IPs carry out a physical inventory check of LIFT inventory at least twice a year. The purpose of the physical inventory is to confirm that all of the assets are physically in the location they were assigned and are in good working condition.

Audits of IPs’ projects are conducted annually and focus on the areas of: effective, efficient and economical use of resources; reliability of reporting; safeguarding of assets; and compliance with applicable legislation. Inventory records are also audited.

### Communications and Visibility
LIFT uses the UK aid logo in-line with DFID’s co-branding guidelines for multi-donor funds. The LIFT Fund Manager has published the LIFT Visibility Guidelines at their website for the implementing partners to follow. The visibility guidelines detailed the use of the LIFT Donor Consortium logo (co-branded), examples of logo use, colour, size, positioning, etc. UKAID branding is mandated in DFID’s agreements with UNOPS.

Recognising DFID’s large contribution, LIFT’s ‘partners logo’ places the UK aid logo first. This review surveyed the branding on a variety of LIFT-funded documents, events and activities implemented by IPs. All were found to be in line with DFID branding guidelines. A recommendation for any future phase of LIFT, and sooner if possible, is to remove the logos of donors who are no longer contributing to the fund.

LIFT’s guidelines set out that IPs are required to publically credit all LIFT funded activities to the fund, and to donors where appropriate. This requirement is compulsory and includes:
- Providing visibility of the Fund will be through the display of the LIFT Donor Consortium logo (including the UKAI logo) at delivery sites, banners, backdrops, on assets, and through clearly crediting LIFT on all promotional materials.
- Display of the logo is accompanied by the words “funded by” to clearly mark the role of LIFT in the project.
- LIFT funding is mentioned in all public and press statements and media coverage.
- The Donor Consortium logo is present on either the cover or first page of any LIFT funded publication, research or study and an acknowledgment and disclaimer where all donors must be mentioned should be included as well.
G: CONDITIONALITY

### Update on partnership principles
No funding was provided directly to government in 2016, but this may change.

In 2016, the LIFT Fund Board and FMO began discussions with the Government of Myanmar’s Ministry of Social Welfare, Relief and Resettlement for a state-wide MCCT programme in Chin State. In addition to leading to direct results for women and children, this progressed LIFT’s strategic intent to nurture and invest in sustainable government-led and government-owned programmes. To manage the risks during this process, LIFT developed a specific ‘MCCT Chin LIFT Risk Management Matrix’.

In December 2016, the LIFT Donor Consortium approved the principle of providing finance directly to the government for a new government-run nutrition programme in Chin State. This is in line with the continued normalisation of relations with the Government of Myanmar, but represents a material change in the LIFT Operational Guidelines.

It was agreed that LIFT could provide funds to the government under the following conditions:
- Funds transferred to the government must be for activities with low budget complexity. For example, for the Chin programme, all the funds transferred are earmarked for beneficiary cash transfers to individual households.
- UNOPS must sign a Project Cooperation Agreement (PCA) for this activity with the respective Union level government department or ministry.
- Funds will be transferred only to a designated bank account established by the government for the project as described in the PCA.
- Funds will be transferred incrementally against an approved work plan.
- UNOPS will ensure substantial involvement throughout the process including the provision of technical support, spot checks that funds are used only for activities in the approved work plan, and in accordance with the terms of the PCA and UNOPS Financial Rules and Regulations.
- A grievance or complaints mechanism deemed appropriate by UNOPS is established for the project activities

H: MONITORING & EVALUATION

### Where an evaluation is planned what progress has been made?
A thorough Independent Interim Review of LIFT was carried out by Coffey in October 2016 (published in February 2017). This graded LIFT as ‘green’ or green/amber’ for all key performance questions and the analysis the report has been fed into this review. Key recommendations included:
- Programme coherence: Programme managers should work with IPs to increase the level of cooperation and coherence across their respective programmes.
- Gender: LIFT should review its internal resources to ensure that it has the resources required to meet the demands of the revised Gender Strategy and the related Gender Acton Plan.
- Governance: The LIFT FB should develop a decision-making framework that is able to specifically inform and evidence how and why key decisions about the use of LIFT’s remaining funding were made.
- Sustainable exit planning: The FMO should assume that the successor programme or Fund for LIFT period will require a procurement exercise. Therefore it is important that the FM should review its exit strategies and consolidate its institutional learning.
- Policy: LIFT should identify and prioritise specific policy areas that LIFT (or successor) wants to support.
- Government: LIFT should increasingly involve its counterparts from the GoM in strategy discussions and decision making processes at the FB level. LIFT should also expand its technical assistance to GoM to respond to immediate institutional capacity gaps, including at sub-national level where possible
- Successor design: LIFT should design the successor programme or fund during 2017. This task is urgent and should include outline a timeline and process where different options for the future are researched, presented, evaluated and eventually selected.
An independent end-of-programme review is also planned for early to mid-2019.
### Monitoring and evaluation process
LIFT’s strategy places a strong emphasis on learning and accountability through its Monitoring and Evaluation for Accountability and Learning (MEAL) framework. In order for LIFT to better measure its new strategy and expected outcomes, the MEAL Framework includes a revised logical framework and Theory of Change (Annex 4). LIFT measures achievements against its theory of change and logframe and generates evidence and learning through a series of longitudinal household surveys, a large-scale longitudinal qualitative panel study, implementing partner reported data, numerous thematic and special studies, and strategic learning events. The UNOPS annual audit of LIFT provides external assurance of how data is obtained, managed, collated and reported.

The framework aims to increase the capacity of LIFT and its partners to generate and use robust evidence both to measure and improve performance and to influence rural development policy and practice. Key features of LIFT’s new MEAL Framework include:
- A broadening and more intentional articulation of the purposes for LIFT to conduct M&E;
- The creation of a three-tiered MEAL framework (at project, geographic/thematic programme, and LIFT levels) that defines the scope and functions of MEAL at the overall LIFT, programme, and project levels;
- The development and use of theories of change at each level to generate consensus on the envisioned change process and to underpin a systematic approach to MEAL;
- A revised logical framework and the development of project measurement frameworks;
- The formulation of clear evaluation and learning questions (ELQ) at each level; and
- The reworking of some of the ways and methods LIFT uses to measure it achievements and to learn from its programmes and projects.

In 2016 the FMO continued to refine and implement LIFT’s new MEAL framework and the strengthen M&E capacity. Including:
- Implementation of the new MEAL framework, through: defining new logframe indicators and documentation, further articulation of evaluation questions and data sources, design of new IP reporting formats and a aggregation database, training sessions with IPs on reporting, and developing an M&E User’s Manual for IPs.
- Conducting M&E-related studies and evaluations, by: overseeing the LIFT 2015-16 Household Survey and 2016 Tracking Survey, launching final reports of the Qualitative Social and Economic Monitoring 5 series and a related migration study, designing and launching a series of studies to address LIFT-level Evaluation and Learning questions (on vulnerability and resilience, income and assets, relevance and sustainability), commissioning six end-of-project evaluations and one mid-term project review, and assisting the FB in commissioning and overseeing the LIFT Independent Interim Review.
- Strengthening IP M&E systems, by: drafting detailed guidelines for IPs to design their own MEAL plans, assisting IPs to develop their new MEAL plans (directly and through expert consultants), reviewing IPs plans to conduct baseline studies, and assessing the M&E systems of ten IPs including data collection and management procedures.

In addition to improving LIFT’s M&E systems, in early 2016 LIFT also helped launch the Myanmar Monitoring and Evaluation Association (MMEA). This is a professional association consisting of M&E practitioners from Myanmar NGOs, INGOs, UN organisations, academia, private consulting firms, and government agencies. It aims to promote a stronger M&E culture within the development sector and strengthen the capacity of M&E practitioners and government. In 2016, MMEA had a membership of over 50 individuals, met on a regular basis, and organised several M&E capacity development seminars on such topics as random control trials, theory of change model building, and the use of mobile technology in M&E data collection.
### Is there any new evidence that challenges the programme design, rationale of Theory of Change?
The assumptions underpinning the programme’s design remain relevant, and LIFT continues to maintain a degree of flexibility to alter direction in response to external factors. The Theory ToC (Annex 4) was updated alongside LIFT’s strategy in 2014/2015.

The evidence base around rural transformation, nutrition and financial inclusion is improving, in no small part due to support from LIFT. In 2016 LIFT-supported several rigorous studies, including:
- the World Bank’s Analysis of Farm Production Economics; and
- Michigan State University and IFPRI’s Off-farm Employment and the Rural Non-farm Economy around Yangon and Agricultural Mechanization and Structural Transformation in Myanmar’s Ayeyarwady Delta;
In addition, LIFT’s large-scale population-based household surveys were conducted by an independent, survey research firm, as is a random control trial of LIFT’s maternal and child cash transfer programme in the Dry Zone.

Evidence suggests that the pace of rural transformation, including mechanisation, is perhaps even faster than anticipated. LIFT’s ‘step up’ (e.g. Yoma Bank hire-purchase project) and ‘step out’ (e.g. its new migration projects) activities are well designed to respond.

It will be important that LIFT builds on the evidence base in the design of LIFT’s next phase. The challenge will be to weight the pillars appropriately. Stepping out will need to be a much bigger part of the programme to continue to support inclusive rural growth – and some work will be needed to persuade other donors into this space.

### How are programme lessons collected and shared? How does it contribute to the wider evidence base?
LIFT continued to generate and use robust evidence to improve performance and to influence policy and practice, as well as strengthening its systems to support learning. In 2016 this included LIFT has continued to generate a large body of context-specific evidence to inform future investments, policy discussions and development practices. These cover themes such as how to support the growth of the rural economy, increase resilience and improve nutrition. More detail on recent publications is included under output 8 above.

During the review period, LIFT was successful in using its learning to influence policy. For example:
- LIFT’s research on nutrition[8] and its experience in implementing MCCT projects shaped the proposal for a government-led, universal MCCT programme in Chin state.
  [8] LIFT has carried out research through its nutrition partner LEARN: Undernutrition I and II (2016) and random control trials on MCCTs have been carried out by the Rakhine Programme.
- LIFT’s has assisted the Department of Rural Development, in the Ministry of Agriculture Livestock and Irrigation, to establish bottom-up village based planning systems in Myanmar. The village based planning approach was developed through an iterative learning process and is an example of how learning has informed policy.
LIFT organised a series of meetings, workshops, seminars and studies through its work with the Agriculture and Rural Development Sector Group to contribute to the development of policy recommendations for the Ministry of Agriculture, Livestock and Irrigation on public expenditure and agriculture.
LIFT provided two technical experts alongside shared project learning to contribute to the development of the Rakhine State Government’s socio-economic development plan in 2016.

LIFT works to capture and share learning from its projects run by IPs. Field monitoring visits and project reports for the backbone of this, and include a focus on improving implementation. For example, field visits and discussions between stakeholders in the Dry Zone in 2016 led to changes in UN Habitat’s WASH project. Engaging communities in latrine building rather than the project team building them has improved sustainability of these activities.

In 2016 LIFT carried out a survey to assess how learning is used by IPs, eight-five percent said LIFT learning events had led to improved practices such as greater coordination between partners. An external assessment of LIFT’s knowledge management capabilities was also carried out in early 2016, and IIR picked up on similar themes. Key lessons from 2016 include:
- LIFT’s flexibility and adaptability to changing contexts is crucial to support learning and encourage uptake.
- More resource is needed for knowledge management (a full-time Knowledge Development Analyst was subsequently recruited in the second quarter of the year).
- LIFT could allocate more time and resource to self-reflection, to enable the capture of learning and to allow time to apply it to current and future strategy.
- Cross-working processes are required to ensure the programme does not develop into silos. The start-up of new communities of practice is a positive step.

LIFT’s communication strategy outlines how the programme intends to share knowledge with stakeholders, alongside objectives on consolidating its public image and promoting learning. The strategy was last updated in May 2015 and outlines nine key audiences, five key messages and eight communication channels of focus. In 2016 LIFT established a physical and digital learning library to support knowledge sharing, and updated its website to make learning more accessible. However, very few of existing communications or knowledge products show much focus on learning from failure. This is an area LIFT could step-up its focus on, perhaps including a spotlight on what has gone less-well (but has subsequently informed the programme) in the next Annual Report. Facilitating this may require the FMO encouraging a culture of recording activities that have not gone to plan, perhaps to be driven by the Fund Board by creating a constructive environment in which to discuss examples.

LIFT has designed and begun implementing a series of ‘legacy papers’ to consolidate evidence from across the programme. The legacy papers, to be written in 2017 and 2018, will draw together learning from narrative reports and mid/end-term evaluations to cross-reference and share findings that have not necessarily been shared outside of the programme. The first of these studies is on the lessons of the Tat Lan project in Rakhine. The second will tell the story of LIFT’s policy work with the Department of Rural Development on bottom-up village development planning.

Despite LIFT’s sophisticated MEAL activities and thorough communications strategy, more could be done to ensure lessons that are captured across project activities are drawn together cohesively to set strategy. LIFT should prioritise resource to ensure systematic knowledge management, with a view to set strategic direction for any future phase the programme (rather than viewing knowledge as products simply to be completed and immediately disseminated). To support this, LIFT might consider mapping the evidence base against LIFT’s rural transformation strategy, i.e. against the narrative of ‘stepping up’, ‘stepping out’ and ‘hanging in’, and using this to inform the relative size and of future windows. The geographic communities of practice are a positive step towards this. LIFT’s could also consider clearer sequencing of the dissemination of key documentation to enable increased impact on policy.

### Annual Review process
This Annual Review was carried out by a DFID Private Sector Development Adviser independently of the LIFT SRO. The reviewer had just completed a maternity cover in DFID-Burma and had had no prior involvement in the design or implementation of LIFT, therefore providing external challenge on the programme’s performance and objectives. The VfM section was written by DFID-Burma’s Assistant Economic and VfM lead.

The review included desk review of existing documents, interviews were held with a range of stakeholders, and a field visit to the Delta. Interviewees and meetings were held with:
1. LIFT Communications Lead
2. LIFT Financial Inclusion Programme Officer
3. LIFT Fund Director (current)
4. LIFT Fund Director (previous, including for review period)
5. LIFT Livelihoods and Food Security Specialist: Delta
6. LIFT Livelihoods and Food Security Specialist: Dry Zone
7. LIFT Livelihoods and Food Security Specialist: Migration and Rakhine
8. LIFT Monitoring and Evaluation Officer
9. LIFT Programme Officer 1: Delta
10. LIFT Programme Officer 2: Delta
11. LIFT Programme Support Officer
12. Implementing partner 1: PATH
13. Implementing partner 2: Yoma Bank
14. Implementing partner 3: PACT
15. Implementing partner 4: Save the Children
16. Implementing partner 5: Mercy Corps
17. Beneficiary group 1: PGMF microfinance recipient group in Phayar Lay Pine
18. Beneficiary group 2: Save the Children MCCT recipient group in Kyein Chaung
19. Beneficiary group 3: Save the Children MCCT recipient group in Kun Chan Kone
20. Beneficiary group 4: Mercy Corps-supported Farmer Producer Enterprise in Aung Phone
21. Fund Member 1 (and chair of Donor Group): European Union
22. Fund Member 2: USAID
23. DFID SRO for LIFT
24. DFID Programme Manager for LIFT

### Annex 1 – Acronyms

CoPs	Communities of Practice
CSOs	Civil Society Organisations
ELQs	Evaluation and Learning Questions
FB	Fund Board (of LIFT)
FDI	Foreign Direct Investment
FMO	Fund Management Office (of LIFT)
GoM	Government of Myanmar
IIR	Independent Interim Review
IPs	Implementing Partners
LIFT	Livelihoods and Food Security Trust
MCCTs	Maternal and child cash transfers
MEAL	Monitoring and Evaluation for Accountability and Learning
MFI	Microfinance Institution
MMEA	Myanmar Monitoring and Evaluation Association
MOALI	Ministry of Agriculture, Livestock and Irrigation
PCA	Project Cooperation Agreement
ToC	Theory of Change
VfM	Value for Money

### Annex 2 – Progress against recommendations from the last Annual Review

AR 2015 Recommendations	Actions taken in 2016
FMO needs to be actively engaging government on what the future of LIFT should look like, if at all, post 2018.	Response ongoing / In March 2016, after the election of the new government, LIFT invited the newly-formed Ministry of Agriculture, Livestock and Irrigation to join the Fund Board. The government accepted the invitation and is now a full Fund Board member and participates in discussions regarding the future of LIFT. / Whilst there have been extensive discussions at many levels on what the Government wants from LIFT; there has not been an explicit discussion with Government about the post 2018 agenda. The next phase of scoping study, consultations and strategy development will focus on this task / In addition, the Independent Interim Review of LIFT was tasked with soliciting the government’s ideas on the future of LIFT. The review team concluded that government officials appreciated LIFT for helping them to support poverty reduction goals at a time when it has been difficult for them to do this work by themselves.
FMO should seek to capitalise on LIFT’s current policy and evidence advantage with government leadership, and get the right technical and financial support to government and within government.	Response complete / Government designed a MCCT nutrition programme in Chin State based on evidence from LIFT-supported nutrition programming in other regions. LIFT now provides technical and financial support to DSW for the Chin programme. / LIFT engaged with the Financial Regulatory Department, the Central Bank of Myanmar and the Ministry of Planning and Finance to advocate for foreign direct investment in MFIs to be permitted. The result was the introduction of currency exchange hedging through The Currency Exchange Fund that enabled foreign investors to invest directly in Myanmar’s microfinance market. / LIFT support for HelpAge International activities on behalf of the elderly has led to a significant re-allocation of government for a national rollout of a social pension scheme for the elderly. / At the state level, LIFT provided technical support to help the Rakhine State government develop a 5-year development strategy.
FMO needs to be active on raising LIFT’s profile across government ministries now.	Response complete / FMO continues to actively maintain LIFT’s high profile across government ministries. For example, FMO is widely recognised within government for its close collaboration with the Department of Social Welfare in support of DSW’s MCCT programming in Chin State as well as DSW’s social pension programme. / FMO has achieved widespread recognition for its work on nutrition. This is illustrated by the State Counsellor’s visit to LIFT-supported nutrition projects in the Dry Zone where she announced that improving nutrition outcomes for young children was a national priority. LIFT support for fortified rice is also raising LIFT’s profile across a wide range of ministries and agencies. / The FMO is also actively increasing LIFT profile at the state/regional level. All four of LIFT’s geographic-focused programmes continually seek to establish, maintain, and expand LIFT’s profile at state and regional levels across all areas of programming. However, the essential point is not so much to maintain a LIFT profile but rather to promote government ownership of all programming.
FMO needs to capitalise on DAASK support and push multi-donor trust funds to seek out new donor funding.	Response complete / In 2016, the FMO received USD 13.5 million in new contributions to LIFT. Three existing donors made new contributions (Australia, Ireland, and USA). / Detailed discussions with Korea did not ledd to additional funding.
LIFT needs to retain sufficient funding flexibility to be able to respond quickly and flexible to government requests.	Response complete / LIFT maintains flexibility in a variety of ways: (1) money is attracted into LIFT steadily, such that it always has new money to be programmed and response to learning; (2) a highly functional board ensures quick decisions are made, including between meetings; and (3) LIFT has integrated the Government onto the Board without slowing things down, by recognising the varied interest government will have in parts of the programme (e.g. on one occasion, de-linking a problematic proposal from other to assist the Government’s review and approval process). / By retaining flexible funding in 2016 LIFT was able to respond quickly to government requests. For example, supporting the establishment of an agriculture policy unit in MOALI’s Department of Planning to support a new Agriculture Development Strategy.
Value for Money (VfM) needs to be more clearly assessed as part of the LIFT annual report	Response ongoing / LIFT VfM guidelines were developed in 2016, focusing on VfM at three levels (project, programme and LIFT FMO). A section on VfM was added to LIFT’s Annual Report 2016. / Going forwards, additional clarification from DFID-Burma’s VfM lead will help build on this to answer broader strategic questions about the costs and benefits of LIFT’s main delivery mechanisms.
FMO needs to appoint a senior Nutrition Advisor by end of December 2016.	Response ongoing / In 2016, UNOPS undertook two recruitment processes to identify a Nutrition Policy Specialist, for LIFT and for 3MDG; however, neither process resulted in an appointment. / In response it has agreed not to appoint a senior nutrition advisor, with policy support on the issue provided by the DFID SRO and UNOPS to provide a technical offiver for 3MDG and LIFT.
FMO Director needs to pay closer attention to staff performance and capacity, taking early action against underperformance within a probationary period.	Response complete / As part of the UNOPS new talent management framework, a set of new competencies were introduced which form part of the annual objective and target setting for each individual staff member. In 2016, all LIFT staff completed a performance evaluation process which is spread out over the year and requires the supervisor and supervisee to agree on expected results, conduct as a minimum a mid-year review and an end year assessment. The assessment also evaluates the supervisee on the competencies. There were no cases of underperformance or need for probationary period during 2016.
FMO Director needs to show more leadership on gender.	No longer applicable (new FMO Director) / During 2016 LIFT increased its commitment to gender equality and women’s empowerment. LIFT developed a new gender strategy and action plan in 2016 and allocated approximately USD 100,000 to support the strategy’s implementation and to fund studies and workshops and to employ gender experts. / In 2016, leadership on gender was assigned to the Programme Coordinator, who works with others in the FMO team including the Knowledge Management Analyst and the Gender Programme Officer from the Dry Zone programme.
FMO needs to map both downstream partners and undertake a procurement mapping exercise of direct and indirect partners before the end of the calendar year 2016.	Response complete / At the request of DFID and in preparation for an external audit conducted on DFID Burma by the National Audit Office, the FMO mapped the processes and procedures for fund-flow and contracting for partners and sub-partners in a presentation based on samples provided by DFID. LIFT also prepared a detailed overview showing all partners and their sub-partners. . In August 2017, DFID requested an update of some of the slides, which has been provided.
LIFT should continue to closely monitor partner implementation, supporting local partners.	Response complete / LIFT continues to closely monitor implementation partners with field visits, joint meetings, support on MEAL, and conducting mid-term reviews as necessary. Close relationships continue between IPs and FMO. / In 2016, LIFT provided extensive support specifically to local partners through the Strategic Partnership programme. The Financial Inclusion programmed continued to work with local MFIs and village cooperatives, with the goal of achieving operational self-sufficiency.
The DFID 2017 Annual Review should be conducted by DFID peers external to DFID Burma	Response complete / This review was completed by a DFID Private Sector Adviser doing a temporary maternity cover in DFID Burma, who has had no prior involvement in the design or implementation of LIFT.
FMO needs to finalise its new logframe targets by end December 2016.	Response complete / In 2016, FMO continued to revise its logframe indicator targets. They were finally approved by the Fund Board in May 2017.

FMO needs to place resilience more centrally within its learning agenda.	Response complete / Resilience was placed at the centre of LIFT’s revised theory of change and was firmly anchored within LIFT’s learning agenda in 2016. LIFT’s primary and overarching learning and evaluation question was finalised in 2016, which reads: “To what extent has LIFT contributed to strengthening the resilience of poor people in Myanmar?” To answer this question LIFT began a series of analytical, methodologically-robust studies in 2016 on LIFT’s contribution specifically to increased incomes and assets, decreased vulnerability and improved nutrition.
Knowledge Management needs to be better aligned with LIFT’s policy work.	Response ongoing / In 2016, LIFT recruited a policy specialist to assist in the articulation and development of LIFT’s policy agenda. LIFT also recruited a knowledge management analyst to support the capturing and communication of LIFT’s knowledge and learning. In 2016, the FMO started a policy community of practice amongst IPs to better understand and share the work that LIFT is doing on policy. Two CoP workshops were convened, which led to a categorisation of all of LIFT’s project and publications by LIFT’s policy areas. / The FMO also restructured the website to better communicate LIFT’s policy work. These changes will be made live on the website in 2017. / Nonetheless, several interviewees remarked that knowledge management remains an area LIFT should continue to develop in 2017 and beyond.
Better Feedback loops are needed for learning.	Response complete / Field monitoring visits and project reports are the backbone of learning at LIFT. They are used to improve the implementation of projects and programmes and provide feedback loops for learning. FOther important learning events with feedback loops included the COP meetings (mentioned above) and the debriefings and final reports from both project mid-term reviews and end-of-project evaluations. / LIFT carried out a survey to assess how learning was used by its partners in 2016 and to further improve feedback loops for learning. Eighty-five per cent of respondents said LIFT learning events led to changes in practices, such as greater coordination between partners and other projects.
Greater coordination across programmes is needed.	Response complete / In September 2016, LIFT hired a Programme Coordinator, who assesses the coherence across the programmes, generates and circulates information, and ensures that activities and sectors complement each other. They also aim to link results and information across LIFT’s various units, such as the Policy, M&E, Communication and Support units, in order to enhance overall coherence across LIFT’s portfolio.

### Annex 3 – LIFT contributions to DFID results frameworks

Operational Plan indicator progress

Indicator	Baseline	Expected Results by 2016 Target	Progress towards results at Dec 2016	% 2016 target
Number of women reached with access to financial services as a result of DFID support	0 (2010)	1,410,000	1,532,961 / (UK's attribution from LIFT is 761,882)	109%
Number of people reached with nutrition support	339,147 (2010)	2,200,000	2,166,714 / (UK's attribution from LIFT is 1,076,857)	98%

DFID Results Framework indicator progress

Indicator	Baseline	Expected Results by 2016 Target	Progress towards results at Dec 2016	% Change against 2016 target
Number of people with sustainable access to clean water and/or sanitation through DFID support *	0 (2010)	979,000	848,527 (UK’s attribution from LIFT: 421,718)	87%
Number of people with access to financial services as a result of DFID support*	0 (2010)	1,500,000	1,635,932 (UK's attribution from LIFT: 813,058)	109%
Number of people reached with nutrition support*	40,626 (2010)	660,000	610, 883 (UK's attribution from LIFT: 303,609)	93%

* Provisional results shown, methodology pending further DFID review

### Annex 4 – LIFT Theory of Change