Project Completion Review (PCR) - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	September 2017

Title: Building a Reliable Investment Climate in Kenya (BRICK)
Programme Code: 203348	Start Date: 19 March 2013	End Date: August 2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2014	2015	2016	2017
Programme Score	A	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

Financial Position

Original Programme Value	£12.5 Million
Extensions/ amendments	Cost extensions of £2.775M – total programme value £15.275m / £1.1M - July 2014 / £0.975M - April 2015 / £0.7M - Sept. 2015 / 30 March 2017 – no-cost time extension to 30th June 2017.
Log-frame revisions (with dates)	Two Revisions: / 1st– 29/12/2014 / 2nd – 30/12/2015
Total programme spend	£15.24M (ARIES figure as at 25 September 2017) / NB: IFC yet to establish final spend during their project closure procedures to determine the total refund to be paid back to DFID.

Follow up actions required following closure
1. DFID programme manager to work with IFC and KEPSA to finalise on their respective project financial reporting, ascertain any fund balances and ensure the payment of these back to DFID.
2. Key lessons from this PCR to be discussed with the IFC, prior to finalising any agreement for future investment climate work; DFID is already in advance discussions for the IFC to support similar work under DFID Kenya’s Sustainable Urban Economic Development Programme (SUED).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203348/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203348/documents

Context
According to Kenya’s Vision 2030, the country aims to attain middle-income status by 2030 through a robust development strategy delivering steady economic growth of about 10% annually. To achieve this, the Government of Kenya (GoK) is focusing on a sustained expansion of the private sector and sound governance of public and private enterprises. In consultation with the GoK, DFID and the Government of the Netherlands designed ‘Building a Reliable Investment Climate in Kenya (BRICK)’ programme. DFID and the Government of the Netherlands contributed £15.3m and US$3m (£2.2m) respectively towards the BRICK programme that was largely implemented under the title of the “Kenya Investment Climate Programme 2 (KICP2) by the International Finance Cooperation (IFC).

BRICK support was aimed at building the capacity of GoK through designing and managing modern reform processes and procuring world class reform advisers. The programme was anticipated to leave skills and knowledge about reforms vested in national/sub-national institutions’ staff. These reforms targeted revamping the deteriorating business climate in Kenya; addressing anti-competitive practices and lack of competition and poor market practices; improving the quality of infrastructure such as energy and transport.

BRICK aimed to achieve “a transformed business environment with lower regulatory burdens, in a more competitive economy with improved infrastructure.” This was to contribute to the impact of “an expanded private sector, which creates more jobs, particularly for the poor”. Most of BRICK’s funding was channelled through the IFC in the form of technical assistance and IT system improvements for parastatals, regulatory agencies and selected units within government. Smaller grants supported Kenya Private Sector Alliance (KEPSA) and the Kenya Agribusiness and Agroindustry Alliance (KAAA) to strengthen their institutional capacity and improve on their advocacy capabilities. The programme had four outputs as outlined below

Output 1: Reformed regulatory environment
Working with government agencies to improve regulatory reforms, and trade logistics at national and county levels. This was intended to improve; the ease of doing business in Kenya, investment policies and business taxation.

Output 2: Effective competition
Working with the Competition Authority of Kenya (CAK) to ensure effective competition in the manufacturing, tourism, agribusiness, seed reform and warehouse receipt system (WRS) and improving the competition policy.

Output 3: Effective environment for public private partnerships
- Working with Treasury and the Public Private Partnership (PPP) Unit to implement and strengthen PPP regulations, and increase the number of PPP transactions implemented in Kenya.
- Working with counties to increase the number of project concept notes for county PPP’s finalised and approved by the PPP committee. Working with PPP stakeholders to improve the number of laws, regulations and e-portals drafted to support renewable energy.

Output 4: Strengthened demand and evidence base for investment climate reform
- Working with the officials of the Government of Kenya (GoK) to be satisfactorily trained on private sector development.
- Working with KEPSA to ensure the organisation’s change management plan was drafted and implemented to make the institution fit for purpose.
- Working with stakeholders to improve private sector consultation in BRICK components and improving the quality and frequency of investment climate reports produced.

IFC managed the 4 outputs with 25 associated indicators from the period 2013/14 – 2017/18 as outlined in section B.

Summary of key results/achievements
Overall the business environment has been transformed in Kenya and regulatory burdens have been lowered while the competitive environment is improving through strengthened oversight of public and private sector institutions. For instance the single business permit system reduced the number of days it takes to register a business in Kenya from 21 days to up to 5 days.
The Companies Act, Insolvency Act and Competition Act have also been reviewed and strengthened. Through BRICK, Kenya’s regulatory environment has improved since 2013; there is evidence of effective competition through work being delivered by Competition Authority of Kenya (CAK).
GoK has established an effective environment for public private partnerships in Kenya; through KEPSA and KAAA there is strengthened demand and evidence base for investment climate reforms.

The key results of the programme are:

Improved business environment relative to Kenya’s peers
Kenya was assessed as one of the global top three reformers by the World Bank for the last two years, with an extraordinary change in the Ease of Doing Business Ranking from 129 in 2013 to 92 in 2016.
Administrative changes and enhanced government capacity
1. The Deputy President of Kenya launched the Ease of Doing Business (EoDB) Delivery Unit housed under the Ministry of Industry, Trade and Cooperatives (MoITC) in November 2014. This was followed by the hiring of IBM consultants to provide technical assistance to the EoDB Delivery Unit to complement services provided by IFC. The EoDB Delivery Unit became the convenors of doing business reforms at national and sub-national levels. The senior level political support that was facilitated by IFC has been instrumental for the GoK to navigate through all reforms.
2. An enabling PPP environment now exists with the development of sound legal and regulatory framework and a framework to measure fiscal commitments and contingent liabilities is in place. Over ten projects in the transport, energy, education, and health sectors, with an estimated compound capital expenditure (capex) of US$4-5 billion (£3-3.7bn) are under various stages of the PPP lifecycle. The programme embarked on the next stage of PPPs at the subnational level with a number of pilot transactions ongoing to create models that can be replicated in other counties.
3. Kenya’s ability to attract Foreign and Domestic Direct Investment (FDI and DDI) is enhanced as a result of investor management support to national and county institutions, and the completion of the Kenya’s first national Investment Policy.

Increased local and county government revenue and savings for business from automation
1. Online E-Business Permit applications have significantly decreased revenue leakage. According to the Auditor General’s (AG) Office, revenues have increased from £710 to £17,700 per day.
2. Saved the private sector over £57m in annual direct compliance cost savings due to ease of dealing with government bureaucracies. This figure is largely the value of time saved to businesses as a result of automated systems.
3. KENTRADE implemented the Single Window System for linking 31 government agencies to importers and exporters applying for permits. The Single Window System has resulted in increased revenue for KENTRADE and faster applications, quicker movement of goods by importers and exporters and improved governance in multiple agencies.
Increased protection for consumers
1. CAK has been supported by IFC to modernise the Kenyan merger regime that has led to a reduction of c. £500k in investor costs. CAK eliminated cartels in outdoor advertising through their whistleblowing initiative. CAK also investigated 4 supermarkets near matatu (Kenyan minibus) stops for price fixing arrangements, the shops were fined a combined £425k and saved consumers £510k per annum. CAK also regulated the single firm dominance in the telecommunications sector bringing in more competition within the mobile phone and mobile money transfer business saving consumers c.£44.4m.
2. An improvement in the Competition Law by CAK has seen an increase in the active legal firms from 4 to 26 advising clients on competition aspects.
Enhanced private sector voice
1. Kenya Private Sector Alliance (KEPSA) has made significant progress in redefining the changes required to create a more effective environment for investment and presenting the collective policy views of the private sector to the public and to the government of Kenya (GoK). KEPSA has ‘hosted’ Presidential Round Tables (RTs) among numerous other advocacy events at which investment policy challenges have been debated; actions agreed, prioritised and acceded to by the President, Deputy President, Cabinet Secretaries and other senior GoK officers publicly. KEPSA membership fees have increased from 20% to 35% of total financial resources.
2. DFID supported Kenya Agribusiness and Agro-Industry Alliance (KAAA) in rebranding itself to deliver value to its members and lead on reforms in the agricultural/agro-processing sector in its bid to achieve financial sustainability and strengthen its institutional capacity, working with the IFC. Through the IFC support, the alliance has recently partnered with the Ministry of Industrialisation, Trade and Cooperatives to lead the agro-processing component of the Kenya Industrial Transformation Program (KITP) mandate.

Key lessons & recommendations for the future
Importance of political buy-in and local knowledge
The high output level can be attributed to the strength of the programme team, and the choice of which interventions to pursue and change as well as their ability to seek stakeholder buy-in and commitment. Buy-in by all the relevant players in the delivery of business reforms is key for effective collaboration in their development and successful implementation.
Automation can be a very effective anti-corruption tool
While the objective of automating a number of government bureaucracies was to reduce the time and costs to businesses, a notable co-benefit was a significant reduction in revenue leakage as a result of reduced corruption and use of intermediaries. This is a useful case study for those looking to reduce corruption elsewhere in Kenya, albeit it should not be seen as a panacea.
Coordination across donors
Better and effective collaboration by players in trade logistics and in the development space would ensure both effective design, implementation and sustained results.
Working with private sector but need for sustainability
In any future investment climate work, the programme will need to intensify its engagement with the Kenyan private sector that could have the mandate and voice to deepen and support reform processes. Further analysis, including political economy analysis, is needed to determine if this is best done through the private sector associations such as the Kenya National Chamber of Commerce, KAM, KEPSA and KAAA.
Future work should have a greater emphasis on equity
This programme focussed on locations and sectors where results could be delivered and demonstrated. Given that many of these interventions are now proven to be effective and implementable, future work should give a greater emphasis to poverty and the demography of recipients in the design of the interventions and monitoring of results.
Selection of the right implementing partners
1. In general the consistency in IFC technical assistance was able to provide continuity in the absence of national and local government continuity. However, this was not always the case; the PPP unit did complain about the change in consultants over time and the delays this caused. Future programmes should focus on where such consistency in technical assistance is most important and prioritise accordingly.
2. DFID should give greater consideration to the procurement times, processes and abilities of implementing partners in investment climate programmes. For example there is need for quicker procurement of experts and systems to respond quickly to institutional requests. IFC experts are highly regarded as they have deep subject matter skills, knowledge and experience. However, there are instances when the lead times to procure an expert are long because of IFC’s internal procurement procedures. There are minor cases when these procurement hurdles have slowed intended institutional reforms. IFC’s procurement of IT systems has been rather slow, particularly for wi-fi and laptops which are fairly standardised products.
3. More consideration of the capacity of organisations and personnel to implement (e.g. Ministry of Industrialisation, KenInvest) should be given prior to the development of strategies and diagnostic analytics that depend on institutional capacity. Any future support reliant on such institutions, must be complimented with strong institutional leaders and reform champions that implement actions from the Board of Directors, executive management and staff
Further investigation needed of the theory of change, areas for improved monitoring and value for money indicators
1. For any future work, DFID should be less reliant on monitoring from the implementing partner with a greater use of independent monitoring. The SUED programme has already committed to a large independent monitoring and evaluation component.
2. The BRICK interventions have been critical for Kenya to leapfrog other countries on the EoDB. These regulatory reforms are considered fundamental in directing businesses towards Kenya as an investment destination. Further work is needed to see if the slow increase in Foreign Direct Investment (FDI) and investment more broadly is a reflection of the lag between reforms and investments, or if other factors continue to deter investment in Kenya. There is also a need to understand the linkages in more detail between investment, growth and job creation, from the sectors which the programme is directly intervening.
3. Linked to the above, DFID also needs to give further consideration of how compliance costs savings in Kenya would translate to higher investment from a variety of types of firms i.e., from micro and small to the large and across sectors which the programme is targeting. DFID should liaise with IFC to seek disaggregation of investment figures (by firm size, sector, etc.) that are to be collected beyond the life of the programme and build such a requirement into the monitoring and evaluation of any future investment climate work. The possibility of estimating attributable job impact figures should be explored again, although remaining mindful of the analytical limitations.
4. Further work should go into establishing whether comparable benchmark figures on cost-effectiveness are available and if necessary work with colleagues in other DFID offices to help establish such benchmarks.
5. In light of the above, a revised theory of change should be drawn up reflecting the lessons learnt from this programme in order to shape any future investment climate support.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Overall Outcome Assessment
Outcome Indicator	Baseline	Target December 2016*	Achieved/comments
1. Compliance Cost Savings to private sector (direct and indirect)	0	No target for 2016 / (US$87m 2019)	Achieved: US$81.4m (2016) / Expected to exceed target in 2019 (see below) / Score: A / Met expectations
2. Number of investment climate Doing Business reforms implemented at national (N) and county levels (C) (cumulative)	0	N:4 C:11	Achieved: N:11 C:21 / Score: A++ / Substantially exceeded expectations
3. Private sector investment generated ($m, cumulative) in PPP’s, Agribusiness, Renewable Energy and SEZ	0	US$ 30m / (US$220m by 2019)	Achieved: / Zero (2016) / $50m (2017) / Score: B / Moderately did not meet expectations
4. Number of sectors with at least one sector-specific reform to the regulatory framework or business practices	0	4	Achieved: 4 / Score: A / Met expectations
5. Number of PSD champions created in government (disaggregated by gender)	0	10	Achieved: 14 / (Male:10 Female:4) / Score: A+ / Exceeded expectations
6. Increase in revenue generated from tax	0	US$ 10m	C: / Indicator not measured following early end of component
7. Proportion of KEPSA's financial sustainability target achieved (%)	0	70%	Achieved: 35% / Score: C / Substantially did not meet expectations

* Logframe targets largely reflect reporting timelines of the IFC; reporting against June 2017 targets has not always been possible but shown where figures are available.
Outcome Indicator 1: Compliance Cost Savings to private sector (direct and indirect)
Results indicate that compliance cost savings of £56m[1]. These are estimated savings associated with activities such as registering a business and are largely a monetisation of time saved from dealing with government bureaucracies). Estimated savings in 2016 were already close to the target for 2019 and it is therefore very likely that the 2019 target will be met. The Attorney General’s office advised that more businesses are applying for permits through the single business permit, with less revenue leakage (funds going to government as intended); revenues have significantly improved from Ksh100k (£710) to Ksh2.5m (£17.7k) per day on average. This has also improved governance issues with less corruption and unnecessary queues in state institutions. There have been significant time savings as well. On trade logistics, significant progress has been made on the Kenya National Electronic Single Window System (KNESWS) and e-payment system, which is currently being deployed across 31 GoK trade related agencies. By 2016 a reported 40,000+ import declaration forms and over 13,500 permits were processed with the collection of around Ksh 500 billion (£3.54 billion) passing through the system; a good and transparent way of raising public revenues.
[1] KICP2 Impact Study Report (May 2016). As noted in section H, this figure, and a number of other indicators in the programme were estimated through IFC surveys. As such, there is a risk of bias, even if the methodology appears robust

Outcome Indicator 2: Number of investment climate Doing Business reforms implemented
Through the work of the BRICK national and sub-national reform component, the programme has helped to establish the e-Citizen's portal that has an excess of 5 million registered users, handles at least 400,000 transactions daily and has collected over US$ 23 million (£17m) in annual revenues. The Government of Kenya (GoK) successfully introduced three new business laws including a new Companies Law, Insolvency, and Business Registration Acts, all of which have passed through Parliament. At a sub-national level, the vast majority of the effort has focused on the introduction of automated, construction permit systems and single business permits that has seen improvements in revenues collected, reduction of time taken, and increase in compliance across four pilot counties namely Nairobi, Mombasa, Kisumu and Kiambu. For example, the Kiambu Electronic Development Application System (EDAMS) system led to a reduction in construction permit approval days from 3 months to 30 days on average. Revenue generated also surpassed targets, while unnecessary time-wasting queues have been eliminated at county offices.
Kenya significantly improved its ranking on the Ease of Doing Business (EoDB) index from 134 (2014) to 92 (2016) and was the top 3 reformer globally for 2 years in a row. Kenya is now among the top 5 economies in Sub-Saharan Africa where it is easiest to do business. This improvement in the ranking is largely due to the implementation of reforms to EoDB (WB, EoDB reports). The areas that have improved the most are procedures, time, cost and paid-in minimum capital to start a business; dealing with construction permits; registering property; and enforcing contracts – the majority of which are areas BRICK has supported.

Year	2009	2010	2011	2012	2013	2014	2015	2016
Ranking	95	106	109	122	129	129	113	92

Overall the programme has been able to embed into the GoK reform agenda, in a flexible and demand driven manner, developing sustained buy-in at senior levels of the political elite, both at national and county level and across multiple agencies.

Outcome Indicator 3: Private sector investment generated
Generated by PPPs, agribusiness, renewable energy, SEZ and investment policy.
Under the BRICK programme, GoK moved to a more coherent national investment policy and development of a number of other important policies such as the development of the SEZ law and development of an advance pricing agreement mechanism are other notable achievements for the programme.
By end of 2016, no investment had actually been generated, reflecting the slow start to the programme and the long lag in this indicator. IFC have since indicated that the investment policy and promotion support in the textile and apparel sector has helped to facilitate $40m (£30m) in new investments, and a further $10m (£7.4m, various sectors) in Kiambu, Nakuru and Uasin Gishu counties.
IFC are also reasonably confident that future targets will be exceeded; over ten projects in the transport, energy, education, and health sectors, with an estimated compound capex of US$4-5 billion (£3-3.7bn) are under various stages of the PPP lifecycle. Investment worth an estimated $54m (£40m) is expected to come in through the Kenya University accommodation PPP, and a further $83m (£61m) in the SEZs ($53m Pharmaceuticals in Athi River, $30m textiles). Clearly not all of this investment interest will materialise, but in a number of instances such as the Athi River Special Economic Zone (SEZ), the physical work has started, providing us with some reassurance. Given the expected over-achievement of the future target, this outcome has been scored a B, despite significantly missing the 2016 target.
In terms of high-level impact, Kenya’s inward Foreign Direct Investment (FDI) flows are low at 2.8% of GDP (for 2016) compared to 10.1% for East Africa and 7.1% for all Developing Countries, and declined from 7.6% in 2013[2]. FDI in Kenya is characterized by many small projects[3], which together with its inflows translates to an under-performance on FDI (in terms of geography, population size, natural resource endowments, and stage of economic growth). The slow response rate of FDI to investment climate reforms means it is unlikely that any effects of the BRICK programme are captured in these FDI numbers. More work (and figures for 2017) is needed to determine if future FDI figures are likely to rise as a result of BRICK, or if this points to an incorrect theory of change.
[2] UNCTAD FDI/MNE database - http://unctad.org/fdistatistics
[3] Kenya Investment Policy Project Phase 1 Report, January 2016 Produced by Oxford Intelligence, Ecorys and IBM
Progress with the Competition Authority of Kenya (CAK) was one of the programme’s flagship successes. Key achievements on competitiveness include reductions in the market concentration index, the reduction of anticompetitive practices and the adoption of competition regulations to increase market competition across a number of sectors.
Outcome Indicator 4: Number of sectors with at least one sector-specific reform to the regulatory framework or business practices
Kenya registered improvements in private sector investments, business competitiveness and achieved cost savings from energy audits in agribusiness, leather, textile, furniture, WRS, seeds & Pyrethrum. Achieving systemic change is difficult and takes time; the project should lead to these changes by 2019, but discussions about the parameters of the change have already started taking place. The sectors that recorded at least one sector specific reforms are increased competitiveness, WRS, agribusiness, seeds and pyrethrum. In the agribusiness sector, through the BRICK programme, GoK successfully implemented a warehouse receipts system (supported by a law on warehouse receipts) and a pilot that has already disbursed over US$ 38m (£28m) of financing. There is potential to increase trade in agricultural commodities and deliver reduced post-harvest losses for low-income farmers through system enhancement.
Outcome Indicator 5: Number of Private Sector Development (PSD) champions created in government
The component was designed to produce a critical mass of private sector development ‘reform champions’ who can ensure not only speedy implementation and sustainability of the reforms supported by the project, but also generate their own reforms. The target was mainly mid-level civil servants in the main agencies BRICK worked with, but also seek to develop reform champions in the political leadership, private sector and civil society
The introduction of the PSD champions’ is beginning to deepen the gains of BRICK further at government level. 14 PSD champions were trained against a target of 10. Although this outcome target has been met, there is need to train more PSD champions and deepen the capacity building and align PSD champions incentives to their expected outputs. The effects of having the PSD champions are starting to be felt in the Ministry of Industry, Trade and Cooperatives, and they should be underpinned by continual regulatory and system improvements supported by the political economy.

Outcome Indicator 7: Proportion of KEPSA's financial sustainability target achieved
KEPSA’s target was to increase non-donor funding from 20% of its budget to 80% by 2019. This required a change in culture which takes a lot of time. The target for 2016/17 was 70% while KEPSA assessed itself to have achieved 35%. Although this is a notable under-achievement, the 70% target was observed to be ‘ambitious’ in the 2016 review.

Output score and description
Overall, BRICK met or exceeded the milestone targets for all its outputs this year. Overall therefore, BRICK scored an ‘A+’ in the 2017 Project Completion Review.
Output Description	2014		2015		2016		2017
	Overall Score: A		Overall Score: A		Overall Score: A+		Overall Score: A+
	Score	Weight	Score	Weight	Score	Weight	Score	Weight
Reformed regulatory environment	A	60	A	30	A	30	A++	30
Effective competition	B	20	A	30	A+	30	A	30
Effective environment for public private partnerships	B	20	A	30	A+	30	A	30
Strengthened demand and evidence base for investment climate reform			A	10	A	10	A+	10

Key points:
The key point for DFID is the confirmation from ex-post evidence of the need for coalitions of reform champions to be supported to embed reform processes. This has provided justification for the approach of the programme and the core thinking laid out in the DFID Inclusive Growth Diagnostic (IGD) on reform. The use of KEPSA, KAM and KAAA as animators for reform coalitions made significant change contributions. Reforms can make faster headway if these techniques are deployed.
Summary of responses to issues raised in previous annual reviews
Sustainable capacity building and effective coordination were identified as key to the delivery of the programme in the 2014 AR. Hence, the programme embedded relevant personnel in the project delivery architecture, especially in the project Counties; and technical advisers in the Business Delivery Unit who provided technical inputs, capacity building, political scanning and project coordination.
The 2015 and 2016 ARs highlighted the need to convene joint discussions among all the trade logistics players (TradeMark East Africa - TMEA, KENTRADE, Kenya Private Sector Alliance - KEPSA and IFC) to explore options for better coordination in in the logistical development space. Such conversations took place, although coordination remains a concern.

Finally, the logframe was revised in 2014 and again in 2015 to align indicators to the Theory of Change and ensure their realism and measurability.
## C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	Reformed regulatory environment
Output number per LF		Output 1	Output Score	A++
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Target December / 2016	Achieved	Score
1.1 Capacity score of the Doing Business Unit of MoIED	n/a	6	6	A / Output met expectations
1.2 Number of web-based regulatory portals developed and fully transactional on Construction Permits (CP) Single Business Permits (BP),Investment Portals (IP) and e-citizen portal (e-CP)	CP[4]: 0 / BP[5]: 0	CP:2 / BP:3 / IP[6]:2	CP:4 / BP:3 / IP:3	A+ / Output moderately exceed expectation
1.3 Number of county officers satisfactorily trained (disaggregated by gender)	0	T:150	T: 641 M:393 F:248	A++ / Output substantially exceed expectations
1. 4 Number of reform memoranda drafted/ strategy action plans produced	0	2	13	A++ / Output substantially exceed expectations
1.5 Percentage of transactions of top 15 government agencies using the KNESWS for permit application	0	70%	100% / (Based on 2015. Figure for 2016 not available)	A++ / Output Substantially exceed expectations
1.6 Number of policies recommended for improvement or elimination	0	3	1 / Estimate based on 2016 review	B / Moderately did not meet expectations
1.7 Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance.	n/a	70%	90%	A+ / Output moderately exceed expectations
[4] CP=Mombasa, Kisumu and Kiambu.
[5] BP=Nyeri, Mombasa,Kisumu.
[6] IP=Machakos and Nyeri.

Key Points

Indicator 1.1 – the ease of Doing Business Unit EODB Unit is in place, has dedicated staff (4), staff have been trained by BRICK (including under reform champions component), and the unit is funded $1.2 million (£0.9m) annually from the national budget. It is effectively headed by the Principal Secretary with strong engagement from the Cabinet Secretary.
Indicator 1.2 - The development of web based regulatory portals exceeded the target and was mainly achieved due to the close working relationships between the IFC team and the national and sub-national officials. This success story had its own challenges; the biggest continuing challenges of IT systems/automation and public awareness. This included challenges in integration with other systems and a lack of public engagement with new technologies.
Important to the county governments were the three peer to peer learning sessions organised by the IFC in Kisumu, Mombasa, and a European trip which included Denmark, Finland and Estonia. The European trip looked at e-governance/e-portals legal frameworks, health management and how these countries roll through their entire system. This trip in particular may have contributed towards a push for further reforms in participating county governments, and demonstrated what a fully automated office and government could achieve in terms of efficiency and reliability.
One of the main benefits of business automation (not tracked in the logframe) has been a significant reduction in revenue leakage, with more revenues accruing to the counties and government rather than intermediaries. Mombasa County, for example, saw a 40% increase in revenues from business permits. However counties now view business permitting and other licensing as their primary source of revenue, which may reduce their focus on making the system work best from a consumer and business protection perspective.
Indicator 1.3 - IFC satisfactorily trained 641 county officers to support with county regulatory reforms. These officers continue to engage with the IFC staff and consultants who work using a remote management model rather than being embedded in teams. In Mombasa, Nyeri and Kisumu IFC seconded an officer who is based there supporting implementation of BRICK components.
Indicator 1.4 - 13 sub-national doing business reform memos were done for counties including 1 generic one that could be utilised by any other county outside the ones included in the survey. Additionally, three doing business strategies/ action plans were done at national level.
Indicator 1.7 - County and national government offices were highly complementary of the engagement of the BRICK project assistance. They do note however that there is still a need for further assistance in attaining the required hardware to equip all staff with the systems as well as a need for further training of staff to be computer literate. IT appears to be a problem not only for administrators, but also for users. Kisumu district were proactive with this and hired a number of university students for one week to go to various areas in the county to assist people in making their online permit business applications and renewals.
Embedding and sustaining ongoing IFC intervention work in counties requires engagement with the Council of Governors; this has already started.
Summary of responses to issues raised in previous annual reviews The previous review noted that the integration of the Kenya Revenue Authority (KRA) and Kenya Trade Network Agency (KenTrade) systems was not completed. This has now been resolved.
The previous annual review pointed out that although client satisfaction of MoITC was rated as ‘Satisfied’ with support from IFC and its quality; they continued to note an apparent lag in support due to experts working on a number of other countries. This issue was not raised by stakeholders in discussions for this review.
Recommendations for the future Further efforts are needed to ensure greater coordination between donors, particularly the IFC and Trade Mark East Africa (TMEA) on the single window/KNESWS project. This should focus on comparative advantage of the institutions. Where donors continue to operate in the same space, the possible harmonisation of donor funding applications should be considered, to reduce the administrative costs of recipients.
Output Title	Effective competition
Output number per LF		Output 2	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline 2010	Target / Dec 2016	Achieved	Score
2.1 (Manufacturing) Number of industrial sector action plans that meet quality criteria and are adopted by GoK (cumulative)	n/a	3	3	A / Output met expectations
2.2 (Tourism) Number of short-term tourism initiatives completed	n/a	1		C / Indicator not measured as component dropped
2.3 (Agribusiness) Number of laws and regulations drafted to support agribusiness (cumulative)	n/a	4	4	A / Output met expectations
(Seed Reform and WRS) / Number of farmers reached (disaggregated by Gender)	n/a	5,000	5,000	A / Output met expectations
2.5 Number of laws and regulations drafted to increase market competition (cumulative)	n/a	6	10	A+ / Output substantially exceeds
2.6 Whole Output (Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance (MoIED, MoEAACT, MoA, CAK)	n/a	100%	100%	A / Output met expectations

Key Points (limited as indicators broadly in line with targets and require no further explanation)
Indicator 2.1 – 3 sector strategies for textile and apparel, furniture and leather were done and endorsed by GoK, although as noted below, implementation has been limited due to a lack of capacity in government.

Summary of responses to issues raised in previous annual reviews
The previous review noted that tourism may have the capacity to alleviate poverty in remote and low income areas and regions in Kenya, with a recommendation to consider further support to the sector. Following the MTR in 2016, we discontinued support to the sector owing to competing priorities. Unfortunately the DFID logframe was not updated to reflect this change.

It was noted in the previous review that none, or only extremely limited work, should continue on any investment policy related work. IFC should withdraw from this until a commitment is provided from the Presidency or Cabinet Secretary MoITC to complete institutional reform on KenInvest and related bodies, and to empower KenInvest to implement its remit. Some reforms were undertaken and IFC continued to work with KenInvest to target implementation of an investor conference on specific sectors. A consultant was signed to support 5 pilot counties for investment promotion support and MoU’s has been established between KenInvest and 5 counties with tracking systems (3 of the 5 counties adopted the tracking system). There are 27 leads in the texapp tracker (designed to help counties with trade facilitation) and 7 investment commitments worth US$71.7m (£53m). However the capacity in KenInvest remains a challenge and progress in this area has been slow (e.g. the county investment handbook still hasn’t been finalised after four years).

Recommendations for the future

While political economy support from the GoK is necessary to deliver such changes, it is clearly not sufficient given the limited capacity in key institutions such as KenInvest. Any future support must be complimented with strong institutional leaders and reform champions that implement actions from the Board of Directors, executive management and staff.

Output Title	Effective environment for public private partnerships
Output number per LF		Output 3	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Target December 2016	Achieved	Score
3.1 (PPP) Number of PPP regulations (R) and Fiscal Commitment and Contingent Liability (FCCL) frameworks (F) drafted through adequate consultation (cumulative)	n/a	R:2 F:1	R:2 F:1	A / Output met expectations
3.2 (PPP) Number of GoK officials satisfactorily trained in the PPP Unit (disaggregated by gender)	n/a	14	153	A++ / Output substantially exceeded expectations
3.3 (PPP) Number of PPP transaction feasibility studies at national (N) and county (C) level completed and approved by PPP Committee	n/a	N: 4 C: 3	N: 4 C: 0	B / Output moderately did not meet expectations
3.4 (PPP) Number of project concept notes for County PPPs finalized and approved by PPP committee	n/a	5	0	C – Substantially did not meet expectation
3.5 (Renewable Energy) Number of laws, regulations and e-portals drafted to support renewable energy (cumulative)	n/a	3	1	C – Substantially did not meet target / [Component dropped in 2015]
3.6 (SEZ) Number of laws (L), regulations (R), site feasibility reports (F), market demand reports (M), developer requests for proposals (D) and investment targeting strategies (I) drafted to support investments in SEZs (cumulative)	n/a	L: 1 R: 3 / F: 2 M: 2 / D: 1 I: 1	L:1 R:11 / F:6 M:3 / D: 0 I: 3	A++ / Output substantially exceed expectations
3.7 (SEZ) Capacity score of the SEZ Authority.	n/a	4	3	B / Output moderately did not meet expectations
3.8 (Whole Output) Percentage of key counterparts reporting satisfied or very satisfied with BRICK assistance.	n/a	100%	100%	A / Output meets expectations

Key Points
PPPs (Indicators 3.1-3.2) - There are general challenges with bringing projects to close; with the county PPPs being slower paced than national PPPs hence the failure to deliver county level transaction feasibility studies. The process of updating and consolidating the project pipeline is still ongoing.
The implementation of a modular PPP training program, targeting all stakeholders and contracting authorities began in September 2015; approximately 150 government officials participated in the training modules. The Public-Private Partnership Unit, supported by an International Development Association (IDA - highly concessional World Bank loan) programme, recruited a communications firm to develop and implement a public awareness campaign on PPPs and, more specifically, on the government’s toll-road policy. Parliament enacted the national PPP guidelines whereas the county PPP guidelines are awaiting the attorney general’s endorsement for gazetting in the next year.
Governments in sub-Saharan Africa (Ghana, Nigeria, for example) have indicated they consider Kenya to be well ahead of other countries in the region on this path and in the case of Ghana have made a visit to review progress and learn from Kenya. IFC supported the Energy Regulatory Commission (ERC) with the implementation of e-portals that are now up and running.
3.4 - Seven new county proposals have been drafted and are undergoing technical review prior to tabling to PPP Committee for approval. However none have yet to be approved.
3.5 – Renewable energy- The ERC e-portal was supported and up and running in 2014. However this component was discontinued from BRICK in 2015 as it was felt that the programme had little added value in an already crowded donor space and that other DFID programmes (STARK+) could provide such support.
3.6 - The IFC team also supported the implementation of the SEZ Act, 2015. The IFC project team assisted GoK in drafting 11 related regulations to operationalise the Act. IFC also drafted the Administrative Procedures Order, which will guide the operations of the SEZ Authority once established. IFC also initiated the procurement of a firm to design the Kenya SEZ communications strategy.
3.7 - The SEZ board and authority have been created, although the acting CEO has yet to be confirmed, with allocated funding from the national budget. However there is not yet dedicated staff in the authority.
Summary of responses to issues raised in previous annual reviews
The previous review noted that Japanese and Chinese investments should be complimentary in developing countries. Opportunities to create synergies should be explored quickly for the good of Kenyan industrial development. This was partly facilitated through the presidential roundtables initiated through our support to KEPSA.
The previous review also highlighted the need for IFC’s continued support to the PPP law and regulations as beneficial in further enabling the PPP operational environment. A greater emphasis needs to be placed on getting projects to the financial market and market testing and getting to financial close. A strong pipeline with 70 PPP projects has been developed worth an estimated US$20 (£15bn) billion. Three PPP projects worth US$2.5 billion (£1.9bn) have recently reached financial close. IFC continues to liaise with Treasury and the PPP unit on strengthening the PPP law and regulations while highlighting the fiscal risks of PPP’s.
Recommendations for the future
It is critical to secure board supporter base to influence the GoK to reform the PPP law and associated regulations. This could be achieved by working more closely with businesses and having more review meetings and exchanges.
Attracting private sector participation is key in implementation of PPP projects however GoK officials need to understand the nature of risk sharing arrangements within PPP’s. The understanding of PPP structuring and risk sharing structures are well understood at national level but counties still need substantial capacity building.

Output Title	Strengthened demand and evidence base for investment climate reform
Output number per LF		Output 4	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Target Dec 2016	Achieved	Score
4.1 (PSD Champions) Number of GoK officials satisfactorily trained on private sector development (disaggregated by gender)	Plan in place for the period 2008-12	10	14 / M:10 F:4	A+ / Output moderately exceeded expectations
4.2 (KEPSA) Extent that a Change Management Plan is drafted and implemented to help make KEPSA 'fit for purpose'	n/a	Plan at least 70% implemented	Change management plan fully developed and adopted	A+ / Output moderately exceeded expectations
4.3 (Private Sector Consultation) Number of BRICK components for which private sector inputs have been received through adequate consultation.	n/a	9	9	Score: A / Output met expectations
4.4 (Investment Climate Diagnostics) Number of Investment Climate reports produced (P), formally launched (L) and rated as Satisfactory on average by targeted GoK agencies (S)	n/a	P:9 L:5 S:6	P:9 L:5 S:6	Score: A / Output met expectations

Key Points
KAAA to continue contributing to the development and sustaining of close collaboration between the public and private sector stakeholders in the Kenyan agribusiness sector supporting the MoITC as the agro-processing implementing partner in the KITP. KEPSA continues leading and proactively managing Public and Private Dialogue (PPD) efforts in strengthening the demand for reforms.
KEPSA developed and operationalized a balanced scorecard to monitor progress. The project supported the review and reorganisation of key staffing functions and that resulted in the attraction of high calibre staff into KEPSA. Staff capacity development was also done through training and brainstorming workshops aimed at aligning individual objectives with the organisation’s vision. KEPSA’s membership revenue increased by 13.5% between March and June 2016 only, signalling the successful application of the resource mobilisation strategy developed with support from BRICK. However as noted above, they have still fallen short of the original target on financial sustainability (35% self-funded vs 70% target).
4.3 - Private sector inputs were received (e.g. stakeholder consultation, workshops, formal feedback) for agri-business, SEZ, competition, trade logistics, regulatory reforms, investment policy and national and sub-national doing business work.
4.4 - While a number of high quality diagnostic reports have been produced, implementation has been slow due to a lack of capacity in Government. Any future work will need to give greater consideration of the capacity to implement prior to investment in diagnostic outputs.

Summary of responses to issues raised in previous annual reviews
MoITC has indicated that it is satisfied with the level of support that has been provided by IFC. MoITC requested DFID to extend reduced programme support from 31st March 2017 to 30th June 2017. The three month bridge was well received and serves to preserve gains of the 4 year programme.
The previous review also supported continued private sector participation in the relevant reforms capable of improving the business environment and leading to increased economic growth through the various PPD platforms KEPSA and KAAA lead on. Coalition of reform champions like KAAA and KEPSA are critical in ensuring programme success. These reform champions need to have a strong mandate and membership to drive their agenda. Realistic non-donor financing targets need to be set to motivate the institutions to improve in the long-run.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

1. Economy:
The composition of the IFC costs has been consistent throughout the program: consultants 37%; staff 31%; travel 12%; and administrative fees and expenses 9%.
As staff and consultancy costs formed such a large proportion (69%) of total costs, the wage rates of consultants was clearly a key cost driver, with the use of local vs international staff also an important determinant.

The share of local consultants’ days increased over the BRICK implementation phase, relative to the international consultants’ days, with no indication of a reduction in quality. SEZs (71% international in MTR) and Agribusiness (69%) made greatest use of international consultants, reflecting the limited local expertise in these areas. Aggregated figures for 2016 are not available, although they are likely to show an increased use of local consultants overall, with 80% of SEZ days now from local consultants.

Table 1. Engagement of local and international consultants in KICP II (IFC component)
Parameters	FY 2013	FY 2014	FY 2015
Number of days
Share of local consultants	68%	60%	75%
Share of international consultants	32%	40%	25%
Value
Share of local consultants	48%	46%	71%
Share of international consultants	52%	54%	29%

Mid-term review 2016.
IFC were unwilling to divulge their consultancy rates. However the MTR did estimate the following average rates, which suggests good economy for the programme, although more transparency is required to make a thorough assessment. Note the increase in local rates and reduction in international rates is most likely due to the shift of highly skilled jobs from international to local contracts.

Table 2. Comparison of daily fee rate of local and international consultants
Parameters	FY			DFID Kenya and Somalia (International) and PEAKS (local) Averages (2015)[7]
	2013	2014	2015	Long term rates		Short term rates
				Senior Consultant	Consultant	Senior	Consultant
Mean daily fee rate of Local Consultants (USD)	216	277	294	372		391
Mean daily fee rate of International Consultants (USD)	505	486	362	607	375	665	457
[7] From DFID K&S Consultancy Benchmark study (unpublished)

Mid-term review 2016

2. Efficiency:
IFC followed a number of good practices that demonstrate their efficiency. Firstly, wherever possible they required GoK contributions as a sign of commitment to ensure sustainability. For instance, for process automations, IFC required equipment and personnel inputs from the counties before committing any support and have only provided assistance to GoK agencies that have demonstrated sufficient demand for assistance. In many cases national and sub-national beneficiaries contribute between 20–30 percent of required personnel and equipment. This approach allowed IFC to have a wider reach of the BRICK program while giving beneficiaries a sense of ownership and control.
They also made good use of peer-to-peer learning across counties and from international best practice as a means of increasing efficiency; For instance Kentrade learnt about the single window system from Ghana before procuring the Tradenet system from Singapore. This helped speed-up the learning curve of Kentrade.
As noted in the previous review, IFC are charging a 5% trust fund administration fee, which is in line with DFID guidance. The budget agreed in the DFID-IFC MoU charges 10.5% of each component to programme management and supervision. However, were not willing to report on what this has been spent on, and so it is not possible to benchmark BRICK’s administrative costs against other projects. This poses a risk in terms of being unable to fully assess the value for money of the programme and any future work should look to agree transparency on admin and management charges as part of the MoU.

3. Cost-effectiveness:
The table below shows the respective benefits and savings against the respective cost inputs on a select number of project interventions. Note these are not comparable across the interventions given that some are transfers rather than benefits to the economy as a whole
Table 3. Benefits and savings vs. cost inputs on a select number of project interventions
Project Activity	Investment/ inputs (£)	Benefits/ savings (£) (Estimates)	Notes
National and sub-national reform and trade logistics	£3.2m	£53m / Benefit-cost ratio of £17:1)	Compliance cost savings largely accruing to business
Competition work	£740k	£7.4m / Benefit-cost ratio of 10:1)	Largely transfers from producers to consumers
Investment inputs (PPPs, SEZs, and Agribusiness)	£3.9m	£163m investments / Investment to cost ratio of 42:1)	Projected investments gains are highly speculative and it is not clear that all investment should be attributable to the BRICK programme

Unfortunately we have not identified appropriate benchmarks to see the cost effectiveness of BRICK interventions relative to other similar programmes, although this should be an important area of work for any future investment climate support. It is recommended that DFID Kenya work with DFID’s value for money network to see what benchmarks are available or can be developed in this area.
It should be noted that many of the key intended impacts around jobs and poverty reduction could not be monitored in a way that allowed any attribution to the programme. Such methods are not considered feasible in a robust manner, although DFID may want to explore further as to what is possible.

4. Equity:
The programme as a whole had an extensive focus on driving economic growth and employment. While some work focused on supporting sectors where female employment was high (e.g. textiles), the work did not generally consider demographics in determining the sectors to intervene. For example, the counties supported focused on where successes was most likely (local buy-in), and would deliver the greatest benefits. As a consequence the most prosperous counties were in effect supported. While this may have been necessary to deliver quick-wins and demonstrate benefits, for any follow-on work there should be much greater consideration of equity in the choices of which sectors are targeted and counties supported, and greater monitoring of the characteristics of the recipients.

The agribusiness component of the programme was designed to improve the well-being of small scale farmers and traders through increasing access to credit, quality and affordable seeds for these farmers and training. $38m (£28m) of financing for farmers was disbursed, although much of this was to larger farmers and traders. While some of the workshops were targeted at women and youth, women’s participation in capacity building workshops and training events has not increased.

VfM performance compared to the original VfM proposition in the business case
The results from the original business case and logframe have largely been met – most notably the private sector cost savings from improved government bureaucracies are in line with those expected in earlier logframes ($81.4m delivered compared to c.$80m in the original Business case and $50m in the 2014 logframe). The programme budget was increased, to increase county level PPP support and extend and continue the work of KEPSA. This latter funding was provided with an explicit objective of increasing the sustainability of KEPSA; this objective has not been achieved, although they have delivered on their remit as a strong voice for the private sector in driving regulatory reform.

Overall assessment of whether programme represented value for money
The programme as a whole appears to represent good value for money, with inputs delivered at relatively low cost and outputs and outcomes largely met. As shown in table 3, some monetisation of benefits was undertaken, with these substantially exceeding the costs.
The Theory of Change appears to be valid, although with the long lead time for impact figures, such an assessment cannot robustly be made for a number of years.

Quality of financial management during programme
DFID committed £15.3m to BRICK over four years of delivery, and of these funds 98% were utilised as reflected on ARIES and implementing partners’ financial reports at the time of this review. The project’s spending against forecasts was mainly tied to the disbursement schedule included in the contribution agreement. However, a lesson to be considered in future project implementation via International Financial Institutions (IFIs) would be the increased emphasis on justification and demonstration of need in reviewing disbursement requests. On financial reports and forecasts, the IFC response times were slow. This was partly due to IFC bureaucracies. Feedback was provided, although this issue was never fully resolved.
There were instances where IFC reported a slow burn rate on the project resources, partly owing to slow moving activities that are dependent on political will and resource availability (i.e. electronic infrastructure) to implement. As a result, the project reported a prepayment of about £1.3m in the 2016/17 financial year. IFC’s project spend in the last two quarters was slowed owing to the uncertainties in the run up to the Kenya General elections; although this effect was marginal.
IFC reported a fund balance of £575k as at 25 September 2017. The actual refund to DFID post project closure, currently projected as £250k, will be finalised in October 2017.
DFID channelled KAAA funding through KEPSA; which was a financial risk mitigation arrangement since KAAA was yet to establish an effective financial management function in its organisational structure. KEPSA and KAAA’s financial management was assessed as satisfactory, although the two organisations however reported running into overhead deficits.
KEPSA procured and installed a new finance system following a due diligence recommendation by DFID. KAAA also moved away from using workbooks to using Quickbooks for their financial management as recommended in a due diligence exercise. These resulted in financial monitoring and management improvements, leading to better and clearer reporting to DFID.
DFID worked closely with IFC, KEPSA, KAAA and the World Bank Externally Funded Output - (EFO) to develop reliable budgets, manage forecasts and promptly obtain spending updates while addressing any difficulties envisaged.
A spot check on KAAA recommended the recruitment of an auditor to discharge financial assurance functions in compliance with the statutes. Audit reports from KEPSA and KAAA were filed with DFID and all were unqualified signalling low fiduciary risk to DFID resources.
Overall, the project’s financial management was satisfactory and with regular fiduciary risk discussions during reviews and the active enforcement of whistle blowing policy by partners. No fraud and corruption cases were reported in the course of delivery.

Date of last narrative financial report	August 2017 – KAAA & KEPSA / September 2017 - IFC
Date of last audited annual statement	May 2017 – KEPSA - unqualified / August 2017, KAAA – unqualified / September 2017 – IFC (covering all trust funds) - unqualified

E: RISK (½ page)

Quality of risk management over the life of the programme
As in the preceding Annual Reviews, the project risk is still assessed as moderate
The project’s overarching risk register was collaboratively developed and managed by DFID and the respective implementing partners.
Political will and government financing were two of the most critical risks identified as some of the major risks with relatively high impact on the delivery of the programme. Some of the County reform projects i.e. the automation of systems i.e. investment portals were overly delayed due to political will issues and lack of resources by County governments to honour their commitment to the project. These were however managed through close discussions with high level government counterparts - i.e. county governors and the ministry of Industry, Trade and Cooperatives (MoITC) whose performance depended on the delivery of these reforms. The conversations ensured buy-in and commitment from the counterparts. The government counterparts were also actively involved in design and review discussions of the respective projects that benefitted them.
Risk was included as an agenda in the half yearly steering committee meetings between DFID, IFC and the Dutch government; and in the regular catch ups with KEPSA and KAAA. The Externally Funded Output – EFO to the World Bank was conditioned on the provision of monthly progress updates.
DFID conducted two and one spot check(s) on KEPSA and KAAA respectively to ascertain their operational strengths. Recommendation (s) from these reviews which have since been actioned by the two organisations included; the a) reorganisation and development of proper staffing structures and capacities in the organisations, b) separation of duties relating to procurement, c) development and implementation of whistle blowing policies on fraud and corruption and d) organisation strategy development to guide their operations to align with their respective visions.
Overall, the project’s risk management was satisfactory and with regular fiduciary risk discussions having taken place. No fraud and corruption cases were reported in the course of delivery.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The project end date was changed from 31 March 2017 to 30 June 2017 to honour a request from GoK to provide continued technical advisory support (via IFC) to the Business Delivery Unit and the counties whose systems were automated, and to operationalize the SEZ law that provided for the establishment of a SEZ board. While most of the project activities were substantially completed at the end of the project in June 2017, some work streams i.e. tourism and taxation were dropped along the way. This was to align the project to DFID priorities and in recognition of other donors’ programmes’ focus in these areas. This is reflected in the output section.
The IFC implemented activities experienced a slow start in 2013/14. Accelerated momentum was however observed in the following years due to increased political support (especially by senior government officials right from the MoIT Cabinet Secretary), and pilot county projects reporting good gains from reforms. These included increased revenue collections from system automations, and thus had other Counties yearning to adopt these reforms.
IFC’s strength in the delivery of Investment Climate reform work, especially in providing technical inputs on policy and strategy is recognised globally and hence a good partner in the delivery similar interventions. The fly in-fly out consultant model had some challenges as it limited the contact time with the clients and the procurement processes were relatively long.
Support to KEPSA and KAAA terminated as planned on 31 December 2016; while the EFO ended on 31 March 2017.
Performance of partnership (s)
The project was delivered through the following:
1. A contribution agreement with IFC
2. MoU with KEPSA, and which also covered the support to KAAA
3. EFO to the World Bank to bridge funding for technical support to the financial services sector
The reporting arrangement with IFC was half yearly and in line with the IFC reporting cycle. This was challenging (as highlighted in the ARs), especially in the timeliness of the reporting as regards the AR process. The respective component leads were however very responsive and even available for face to face catch up discussions with donors. DFID is in discussion with IFC to set up a new trust fund through which it will continue its support for SEZ development and County reforms. 80% local staff composition and coordination of results via an independent M&E consultants are some of the safeguards being explored to ensure effective capacity transfer; and to ensure timeliness, effectiveness and accuracy in results reporting.
The IFC project delivery team was composed of suitable experts who were well respected by their counterparts in the ministry and hence enhancing the credibility and demand for the project interventions by the client (government, both national and county). The procurement lead times were however described as lengthy owing to the extended bureaucracies applicable both at the World Bank and GoK.
It would be worthwhile to explore a synchronised reporting cycles and logframes in future for general projects with IFC/World Bank and DFID need to ensure the logframe is updated in a timely manner. The DFID logframe was not always updated in a timely manner, which in part may be due to having separate DFID and IFC logframes for the programme.
The IFC project activities were also co-financed by the Dutch government. DFID and the Dutch did not however have many close interactions on the implementation of the programme, due to the divergent interests in the project. Greater consideration should be given to the interests of co-funders in multi-donor trust funds to ensure there is added value from such co-funding.
DFID enjoyed mutually beneficial relationships with KEPSA and KAAA. With DFID financing, KEPSA operationalised the Presidential Round Tables (PRTs) in which DFID participates and is able to influence on reforms. KAAA chairs the agricultural sector group within the Kenya National Chamber of Commerce and hence strategically placed to advocate for players in the agribusiness and agro-processing space. Adherence to reporting timelines was however observed as a challenge with both organisations, which could be attributed to staffing and capacity constraints in the two organisations.
The monthly updates from WB were key in keeping the project team updated of the progress of the EFO outputs especially given its short-term nature.
There have been a number of changes in the DFID personnel managing this programme and this was raised as a concern by the implementing partner. DFID should give greater consideration to DFID staff continuity when determining the management structure.
Asset disposal and value obtained by DFID
The implementing partners maintained up to date asset registers for the assets purchased with DFID funding. The DFID project team will carry out the relevant asset disposal process with the respective partners and in line with DFID SMART Rules.
G: CONDITIONALITY (½ page)

Partnership principles assessment
In line with DFID’s partnership principles (last updated April 2017), this programme did not put money through Government systems and with all procurement undertaken by the IFC. However, noting the shared objective on reducing poverty and economic growth, this programme worked closely with the national and county Governments to deliver these goals.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Since its Inception, in March 2013, the BRICK programme has undertaken three Annual Reviews (all undertaken by DFID-Kenya staff). The respective recommendations were communicated and discussed with partners, especially to ensure ownership and collaboration in identifying and effecting the corrective actions.
Efforts went into strengthening the ToC, although it still appears not to clearly communicate the pathways to the project’s overall impact, especially on poverty reduction. It is recommended that a revised theory of change should be drawn up reflecting the lessons learnt from this programme in order to shape any future investment climate support.
An impact study commissioned by the DFID Kenya Sustainable Economic Development team in 2014 that reviewed selected programmes in its portfolio, including BRICK, highlighted gaps on the project’s focus on poverty reduction right from design. It however recognised that the challenge could be attributable to the national focus of the interventions.
IFC commissioned a Mid-Term Review (MTR) in 2016. By reviewing the programme, the M&E methodology and priorities, they were able to make a number of recommendations, although not all of these were taken up. A key element was the mention of the need to collect better qualitative data in order to analyse the actual impact of the programme on incomes. There is a need to collect data on the impact the programme is having and to make a comparison of progress with similar programmes. The information collected (through surveys by the IFC) has the risk of perhaps being too biased as it is collected in order to prove impact rather than looking at the whole picture. Any future support in this area should involve independent monitoring and evaluation. A new trust fund currently under discussion and through which continued support for SEZ and County reform work will be delivered by IFC incorporates closer working with an independent M&E firm to ensure effective results measurement, monitoring and verification.
Sustainability and consistency are areas that have been raised in the annual reviews as being potentially problematic, and it would appear at this stage that these are still areas of concern. Each county government is still operating independently and are not always collecting the same kind of data (such as number of jobs created, gender, age, mobility). More cohesion across the county governments in terms of practices and data collection would enable more effective evaluation of future investment climate support, especially on reforms. Although a number of reviews were conducted, there was no key central learning document or formalised approach to lesson sharing and this is again an area that could be strengthened in the future.
The IFC has conducted a number of surveys to assess the impact of their work, but the methodology does not seem to be consistent and the focus does not provide a full picture of the situation. It would be interesting to analyse the impact of the new Companies Act (2016) and the automation system on micro and small businesses which were functioning in the informal sector. When looking at the investment climate, it would be important to look at the impact of these new systems not only on revenue generation, but also on its impact on employment and the livelihoods of the poor.
DFID and IFC did not attempt to monitor job creation or poverty impact attributable to the programme as no robust method could be identified. However future support in this area should explore this area again, including what disaggregated sector analysis is possible.

Monitoring progress throughout the programme
As mentioned above, IFC formally reported results to DFID on a half yearly basis while KEPSA and KAAA reported quarterly and the DFID management team had continuous discussions with the respective teams on progress, to provide technical inputs and to review any risks affecting delivery.
Conversations were also included with the relevant stakeholders including government to get a sense of adequacy and satisfaction levels with the project interventions; these discussions were mostly ad hoc and on demand, and during reviews. Stakeholders interviewed by the review team expressed general satisfaction with the project. M&E experts formed part of the delivery teams in the respective organisations, and hence played the pivotal role of general project monitoring and results collation. Future work may wish to have a more formalised structure to receive more frequent feedback from key implementing partners.
Process of review
This PCR was led by independent consultants (IMC Worldwide) with reviews and support from the SRO, programme manager and IFC. It is based on a desk review of a number of reports and stakeholder meetings between 28 August and 8 September 2017.