Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme’s performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2016

Title: African Enterprise Challenge Fund / Research into Business Window Round 1 (RIB1)
Programme Code: / 201500	Start Date / 2009	End Date: 31st November 2015. Programme management responsibility for RIB 1 programmes moved from Research and Evidence Division (RED) to Africa Regional Division (ARD) on this date.

Summary of Programme Performance

Year	2012	2013	2014	2015
Programme Score	A	A	B	A
Risk rating	Low	Low	Medium	Moderate

The Financial Position

Original Programme Value	£12,500,000
Extensions/ amendments	Budget reduced to £5.2m in November 2011 to restrict funding to one window rather than three. This allowed the first round of funding to run forward for 5 years in order to test its effectiveness before committing further funds. The decision to reduce investment in this novel approach to getting research products into use reflected a decision to maximise DFIDs investment, concurrent with a shift in DFID’s key research priorities.
Log-frame revisions (with dates)	Logframe revised June 2015 to build in monitoring lessons and ensure all AECF funding windows had similar indicators
Total programme spend	£5.2m

Follow up actions required following closure.

Management of remaining RIB 1 programmes transferred to Africa Regional Department
(ARD) on the 1st December 2015. ARD is the lead for the overall DFID AECF portfolio.

Research and Evidence Division (RED) to continue to liaise with ARD on the management and
outcomes of the remaining RIB 1 projects.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:	2217858

Outline of programme and what it has achieved

Challenge funds use competition to encourage new ideas and innovations in development cooperation. Small and medium-sized enterprises, organizations, institutions and individuals compete by submitting their project proposals to the challenge fund. Although the proposals have to meet predetermined and fixed criteria, the applicants have great freedom in the design of their development solution. The winning proposals are supported financially though financing from the challenge fund must usually be matched by a certain percent of self-funding.

The African Enterprise Challenge Fund (AECF) was established in 2008. The Fund design addressed a critical constraint in African agricultural sectors: that many agribusiness initiatives cannot proceed without access to finance. By providing access to finance, the programme aimed to increase commercial private sector investment in agribusiness, to demonstrate new business models, and to create viable agribusinesses with a high development impact through creation of jobs, commercial linkages, and the provision of affordable services or goods to rural communities and smallholders in Africa. The fund was housed within AGRA a multiagency alliance formed in 2006 in response to a call from former UN Secretary-General Kofi Annan, who said the time had come for African farmers to wage a “uniquely African Green Revolution.” AGRA is led by Africans with roots in farming communities. It is dedicated to changing the reality of agriculture in Africa through increased productivity, jobs, livelihoods and food security.

The Fund channels its resources through a number of different themed ‘windows’ that have their own specific goals. These include new and innovative business ideas in agribusiness, rural financial services, renewable energy solutions and technologies for adaptation to climate change. Some of the windows were specific to particular countries or geographical areas.

The RED funded ‘Research into Business’ (RIB) window aimed to address a crucial challenge for rural Africa, how to get new agriculture technology, that has the potential to boost productivity and incomes, into widespread use with poor farmers in areas where markets do not function efficiently.

The RIB window had two key objectives. Firstly, getting new technologies into use at scale and secondly, it was designed to determine how effective business development grants directed to small and medium enterprises are as a means of increasing the commercialisation and uptake of agricultural technology by poor farmers.

RIB project proposals were appraised through an investment committee on a competitive basis. The window then provided successful businesses with a mix of grants and non-recourse loans (repayable grants). RIB carried out two rounds of competition. The first round in 2010, known as RIB1, was funded by DFID and funded nine business ventures. The second round in 2012, known as RIB2, was funded by the Australian Department for Foreign Affairs and Trade (DFAT) as part of their efforts to support private sector development in Africa.

The nine businesses funded through DFID support to RIB1 focused on the uptake of novel technologies, targeting new customers with new products and services including new seed varieties, livestock vaccines, new fertilizer formulations and aflatoxin-free groundnuts. Five of the nine businesses were start-ups and the other four, although already in business, were small businesses with annual turnover of less than US$1m. The full list of companies is set out in the table below, including summary details of their progress.

Overall the RIB1 projects achieved good results in terms of lessons garnered for challenge funds as a mechanism for getting new technologies into use, the total net benefit and the development rate of return. The latter being a ratio of development impact and funds disbursed. Targets on number of projects achieving high development impact (projects generating a total net benefit of $250,000 or more per annum) has also been exceeded. Five RIB1 projects have contributed to these results; Mediae total net benefit (TNB) $30,000,000, Brentec Investment TNB $4,094,642, Phoenix Limitada TNB $1,174,496 and Super Sires Genetics TNB $537,210. The window reached significantly higher numbers of households than originally envisioned, primarily through the efforts of the company Mediae. The project also achieved its benefits per household goal. The window has performed moderately in terms of commercial viability of the companies supported, with three of the nine firms showing profits so far.

RED initially allocated £12.5m in 2010 to commission three funding rounds of the RIB window. However, in 2011 the scope of RIB was limited to a single £5.2m investment round (RIB1). The decision to reduce investment in this novel approach to getting research products into use reflected a shift in DFID’s research priorities and the intention to balance investments with other UK Aid objectives. Australia's Department of Foreign Affairs and Trade (DFAT) subsequently invested $8.83m in the second round (RIB2), launched in 2012.

RIB1 formed part of a broader programme of funding to the AECF led by Africa Regional Department (ARD). This Project Completion Report relates to Round 1 of the Research into Business (RIB) window of the AECF as this was the DFID RED-funded component of the Fund.

Summary of progress and lessons learnt.
RIB 1 window
Company	Country	Objectives	Progress and lessons learnt.
Toguna Agro Industries	Mali	To develop a phosphate deposit and produce fertilizers using a newly-developed 'pelletizer' technique with fertilisers specifically produced for smallholders. Targeting over 60,000 farmers.	Activity disrupted by Boko Haram insurgency in northern Mali. Activity resumed but the civil conflict has yet to be resolved. Lessons identified on the need for thorough risk assessment and mitigation planning when supporting new ventures in possible conflict zones in DFID priority countries.
Brentec Investments Ltd	Uganda	Delivering Poultry Vaccine to Rural Farmers. To produce, distribute and sell a new poultry vaccine against Newcastle disease to 200,000 small farmers. The vaccine is thermostable which allows it to remain effective for 3 days after reconstitution rather than the 2 or 3 hour window for the products currently imported into Uganda.	Vaccine sales in rural areas are high with targets now being exceeded. Key lessons have been learned around the difficulty for new companies understanding and overcoming regulatory hurdles. Delays were caused when the registration and licensing of the vaccine took longer than expected after it was discovered there were no standards for registration of domestically produced poultry vaccine in Uganda or any other country in the region. These standards are now in place.
The Mediae Company Ltd	Kenya	Delivering new technical agriculture information to small-scale farmers, demographic groups and geographic areas that are not currently able to access conventional extension services using multi-media approaches. The project aimed to develop and test a model for these services that was able to build commercial viability.	The project exceeded all targets with well over 1 million households being reached through broadcast media. Its approach is being extended to Uganda and Tanzania. Mediae’s model has been copied by other commercial companies seeking to sell content aimed at small-holder farmers. Mediae has attracted funding from other donors to expand its work to other countries, targeting other sectors with demographic groups that are hard to reach with information.
BLGG Kenya	Kenya	To improve smallholder farmer livelihoods by using infrared spectroscopy for soil analytical services To introduce infra-red spectroscopy to deliver low cost soil and soil organic resource analysis. 70,000 smallholder farmers in Kenya targeted.	The project sold soil analysis services to approximately 10,000 farmers in Kenya. Farmers pay 1,300 Kenyan shillings for the analysis (about $12) if purchasing direct but less if through a 3rd party such as a co-op. The company plans to introduce a hand-held tester for soil samples that will reduce the cost to 500 Kenya Shillings. The company has specifically focused on reaching dispersed, rural populations and developing products that are designed to deliver soil testing to low income households. The company has been able to demonstrate the cost benefit gains to small farmers to promote sales.
Leldet Ltd	Kenya	To produce, distribute and sell improved seed in small packs for small farmers, particularly for crops not generally available through commercial outlets in Kenya and for crops that are valuable to poor farmers in drought prone areas. These are chickpeas, pigeon peas, cow peas, groundnuts and various sorghum varieties – red/white, forage/staple grain. 60,000 farmers targeted.	The project, ran into regulatory and supply chain problems. This was a start-up company which had assessed that there was strong demand from small-holders for seeds other than maize and wheat. This was true but Leldet had not adequately considered the need to comply with national seed regulations. The company had to work with the Kenyan government to pass their novel varieties through National Performance Trails required before the commercial release of all new seed varieties. This delayed progress. / Efforts to grow and sell crops other than maize and wheat have been limited by lack of resources. The company struggled to produce enough quality certified seed to supply and support stockists nationwide. Demand was high for these seeds, the market is strong, but their supply chain was not adequate.
Super Sires Genetics Ltd	Kenya	Using Embryo Production and Gender Selected Semen Technologies. To develop collaboration with Viking Genetics Ltd (Denmark) to launch an artificial insemination (AI) service targeting 8,000 small farmers using sexed-semen and embryo transplants to improve heifer quality and increase milk quantities.	The project generated total net benefit for clients but failed to meet ambitious sales targets in the competitive artificial insemination and embryo market. The project attracted further funding from DANIDA and has long-term commercial potential. Produced lessons on the need to invest in communications and long duration business plans as sales are likely to be slow and results not immediately available.
FAIM Africa Ltd	Rwanda	Plant propagation facility and tissue culture laboratory. To set up a nursery and install a top-of-the-range tissue culture (TC) laboratory near Kigali to produce high quality planting material for a wide variety of crops. 25,000 small farmers targeted.	Project failed to meet expectations, though it was profitable. The planned Tissue Culture (TC) lab was not built, as the company decided to focus on the market for advisory services rather than plant sales. Whilst turnover more than doubled from consultancy, slow sales of nursery products and mounting debts hampered company performance. / Lessons related to start-up companies requiring significant business support at inception to identify market opportunities and develop sustainable business plan.
Phoenix Limitada	Mozambique	Manica Seed Production and Processing (Phoenix Seeds) To set up a commercial farm hub and out grower agriculture business to grow and distribute new and improved seed varieties targeting over 130,000 Mozambican farmers within five years. Primarily Maize seed sales.	Company demonstrated a big increase in productivity for seed varieties purchased by commercial farmers who bought their seed products from the open market. However the project failed to meet sales growth targets after sales contracts with NGOs and government fell through. / Company found maintaining and managing direct sales forces difficult and costly and failed to appreciate that such teams are better than radio and shops when it comes to convincing small holder farmers unfamiliar with a product or give it a try
Klein Karoo	South Africa	To produce and sell new white maize hybrid varieties with high yield potential, high level of disease resistance, adaptability to sub-optimal growing conditions (e.g. drought tolerance, low fertiliser applications). 20,000 farmers targeted over 6 years.	Failed to meet expectations. Project closed before the contract end date for non-compliance with reporting requirements of the funding agreement. Fund manager requested repayment of funds. Lessons around complexity of loan provision across international borders and repayment mechanisms in case of defaults.

The theory of change for the AECF assumes that investing in the private sector supports the establishment of more sustainable African agribusiness sectors, as companies are supported to achieve commercial sustainability, in new markets and with new products. This is a model widely used in developed countries to support business start-up and expansion but is less well tested in developing countries, particularly in small-scale agriculture. AECF measures company performance against key quantitative indicators: turnover and profit; jobs created and wages paid; and, households benefitting and benefit per household.

The overall turnover of RIB1 projects almost doubled in 2014. However, as can be expected with all start-up companies, it was very challenging to become profitable and commercially sustainable. Only three of the nine companies became profitable during the life of the project. There were a number of reasons for this, including regulatory barriers or absence of enabling regulations, longer than expected lead times on setting up or building new facilities and some companies struggling with different models of generating sales and defining their route to market. These challenges show that, while there is demand for the outputs of agricultural research, patient capital and plenty of time is needed before a sustainable business can be built around commercializing the outputs of agricultural research. RIB1 and RIB 2 provided important lessons on the commercial difficulty facing a typical firm in this window. These included:-

1. Small businesses, particularly start-up businesses, have little flexibility to adjust their business plans and manage cash flow disruption caused by conflict and unforeseen bureaucratic obstacles. This fragility needs to be mitigated through particularly thorough risk analysis in advance of contracting. This analysis needs to be carried out jointly by the investment committee and the business with specialist advice drawn upon if necessary. (Lessons from: Mediae, Toguna, Leldet Ltd, Brentec, FAIM Africa Ltd, Phoenix Limitada)
2. Business mentoring is particularly important for start-up companies. Being able to predict and meet spikes in demand and having the flexibility to respond to changes in demand make a crucial difference in terms of commercial success and failure (Lessons from: Phoenix Limitada, Leldet Ltd, FAIM Africa Ltd )
3. Adoption of new technologies is particularly challenging for risk averse small farmers. The more expensive the initial outlay is for the farmer the greater the challenge. Relatively expensive technologies such as the sexed semen and embryo transfer products of SuperSires require adequate investment in extension and communications over time, to ensure farmers understand the potential benefits and risks associated with the technology (Lessons from Supersires, Phoenix Limitada and BLGG Kenya)
4. The challenges for funds to provide loans when the borrowers are small start-up companies, operating across borders and in an environment of weak regulatory enforcement are considerable. (Lessons from: Klein Karoo).

The project has significant successes in terms of getting outputs of agricultural research into farmers’ fields. Many of the technologies would not have got as far as they are did if not for AECF funding through RIB1. For example, hundreds of thousands of households would not have benefited from the extension provided by Mediae delivering new technical agriculture information to small-scale farmers, demographic groups and geographic areas that are not currently able to access conventional services using multi-media approaches. AECF’s investment in Mediae brought systemic change far beyond the costs incurred in supporting the extension mechanism. In Uganda, Brentec has saved the lives of millions of chickens belonging to over 30,000 smallholders. The birds died eventually after being sold for an average of US$8-10 each, not from Newcastle disease that renders them unfit for market or even for home consumption. Brentec has also brought registration of vaccines into Uganda protecting millions of smallholders, not just their customers, from substandard poultry vaccines.

Taking research to farmers through small companies is not easy, but ultimately could be more sustainable than through NGO’s and donations. As the RIB1 Window of AECF closed and AECF moves forward, opportunities exist to build on the lessons learned from successful rounds to continue to support innovative enterprises in sub-Saharan Africa.

Following establishment of AECF it was determined that some milestone indicators were not being reported by projects, as they lacked the facilities or the resources to collect the relevant information. For example it was found too difficult for businesses to report how many of their clients were poor (living on less than $2 per day) or female. In order to strengthen Monitoring and Evaluation (M&E) of all AECF windows, a study was undertaken in 2014 by Coffey International. This recommended that one-off studies be undertaken to disaggregate data and verify results. These studies have yet to take place, however in the interim the fund manager has relied on field visits to provide an indication of project impact.

Following the study and recommendations from past annual reviews, improvements were made by AGRA on financial management, the AECF logframe was also revised to create consistent nested logframes for each window, with both new and old metrics.

Recommendations

R1 When working on technology transfer, Challenges Funds should supplement financial input with business support and mentoring, which will help the enterprises develop to a point where they can seek commercial finance.

R2 Challenge fund start-up grantees need revised business models that limit the size of grants and loans until proven success and ensure provision of adequate collateral and/or co-funding through links to investment ready loan schemes.

Gender Equality Act 2014

The project was approved before the act came into force in 2014; however AECF as a whole is making progress in this area. AGRA commissioned a gender equity report, which, while providing reasonable analysis, produced limited practical material which could be incorporated into AECF’s processes. To resolve this, AGRA is now conducting a more specific review of its operations manual and other organisation development tasks.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment A

The AECF RIB window has 1 indicator for impact and 3 indicators against its outcome statement of “Agribusiness market systems have high development impact by working better for the poor in rural areas of selected African countries”. The projects funded by RIB1 made a contribution to achievement of the intended outcome. However, progress has been mixed, with some businesses substantially exceeding targets and others not meeting expectations. This result reflects the precarious nature of business start-ups. The table below provides a summary of progress against milestones.

Outcome Indicators	Milestones	Progress
Outcome Indicator 1: / Cumulative development impact: / (a) total net benefit (US$); / (b) total net wages (US$); / (c) development rate of return (DRR) = ratio of development impact (a + b) to funds disbursed (4.5f).	(a) 15.5m / (b) 3.5m / (c) 3.22	(a) 72.7m / (b) 4.3m / (c) 12.5
Outcome Indicator 2: / Cumulative (US$): / (a) grantee matched funding (sum of grantee: cash, in-kind, re-invested profits); / (b) third party funding (sum of actual third party: equity investments, loans, in-kind, supplier credit, grants from other funders, bank loans, bank overdrafts); and / (c) funding successfully facilitated by AECF Connect.	a) 15.5m / b) 9.8m / c) 1m	a) 11.6m / b) 10.9m / c) 0
Outcome Indicator 3: / Number of ongoing projects: / (a) bringing a new technology or business model; / (b) replicated by other market players in some way; or that have / (c) led to other systemic changes (regulatory, factor and other markets).	a) 7 / b) 7 / c) 7	a) 4 / b) 5 / c) 9

Key Points

The RIB 1 window has exceeded its targets for outcome indicator 1, especially for total net benefit, where the cumulative development impact stands at $72.7m, far above its $15.5m target. This result is primarily driven by the results of Mediae Trust, which has had impressive extension outreach figures and a business model that has been replicated by various other media outlets. The company has now expanded into Uganda and Tanzania. During the life of the project queries have been raised about how well the Mediae approach meshed with RIB’s Theory of Change because the company is not fully commercial but relies upon attracting continued donor support for much of its work. However the company has never made a secret of the fact that profit is not its ultimate goal and has continued to expand its portfolio of programmes.

The remaining 8 companies in RIB1 are fully commercial and achieved mixed results. Brentec and BLGG were the next most successful companies after Mediae. Field visits demonstrated that the performance of these innovative programmes was improving. In the case of Brentec, which sells thermostable vaccines against Newcastle disease, there was a clear growing demand for the product with sales of over 1,850,000 doses in 2015 and some anecdotal evidence of success in achieving wider regulatory change that will benefit market systems in the region. BLGG, which provides soil analysis via infrared spectroscopy to farmers in Kenya also appeared relatively successful having reached 10,000 farmers in Kenya. Conversely, at the other end of the spectrum companies such as Leldet and Klein Karoo did not meet their sales targets and appear unlikely to become commercially viable. Support to Klein Karoo has now closed as it failed to meet reporting requirements. .

The Development Rate of Return (DRR) is a measure of development effectiveness from a dollar of donor funds going into the projects. The DRR for RIB as a whole is 12.47, which implies that US$12.47 of development impact is delivered for every US$1 of funds disbursed. Mediae contributes a significant proportion of DRR as it estimated to have delivered US$47 of impact for every dollar of AECF money disbursed. This kind of impact is only possible through mass media project like Mediae able to reach a large population of farmers with information.

The window’s results against total net wages paid, also appears to be a success, with $4.3m in net wages achieved against a target of $3.5m. This indicator provides some evidence of company performance but does not provide evidence of impact for smallholder farmers. The redesigned M&E systems and verification studies as recommended by the Coffey International Study should provide improved appraisal of actual impact, including impact on poor farmers and female farmers.

RIB met expectations against outcome indicator 2, with a significant funding attracted from other sources including, in some cases, other donor funds.

RIB also met expectations in outcome 3 indicators, bringing a number of new technologies to market, some of which are now being replicated or leading to systemic changes. With regard to replication, Mediae’s model has been copied by a number of other media outlets. There is also some limited evidence that Brentec has brought positive systemic change in the market. Brentec’s experience of submitting a vaccine for registration highlighted issues with the registration system. East African Countries are now working to develop a more streamlined registration regime whereby drugs registered in one country do not need to go through the registration process other countries. This initiative is not solely due to the Brentec experience which merely highlighted the problem for policy makers within the East African Community.

Output Score and Description

RIB 1 and 2 outputs are listed in the below table. Overall targets were met for Output 3 and 4 and partially met for Output 1 and Output 2.

Overall, Output 1 partially met expectations. Some of the indicators (1.3-1.5) could not be measured as they relate to demographics, poverty and gender parameters that were beyond the capacity small businesses. This led to a review of M&E systems and the overall logframe for AECF. The verification studies for specific projects recommended by the M&E review have yet to take place. Targets were significantly exceeded for indicators related to the number of beneficiaries reached (1.1) and almost reached for the net benefit per household reached (1.2).

Overall, the commercial viability of the projects (Output 2) did not fully meet expectations. To date three of nine companies funded (33%) have reached profitability (2.1). The reasons for this have been assessed by the fund manager. Whilst the result is challenging for the project appraisal team and fund manager the expectation that 68% of projects would become profitable was, with hind sight, over ambitious. Significant challenges to meeting sales targets included regulatory barriers, construction delays and finding appropriate sales techniques for small rural communities. The fund manager has noted the lesson that technology introduction is particularly challenging for small start-up companies and requires mitigating measures. Furthermore the skill sets required to develop new technologies are quite different to the commercial skills needed to bring a new company to profitability. A lesson learnt is that the Fund Manager should undertake more detailed appraisal of business acumen before finalising contracts and provided business advisory support to the companies. The lack of profitability is reflected in indicator 2.2 with significant delays in the repayment of loans made to the companies. The fund manager continues to follow up on loan repayment.

Overall, progress against Output 3 has met expectations. Indicator 3.1 shows that 15 of the RIB1 (DFID funded) and RIB 2 (DFAT funded) projects remain in business. Indicators 3.2, 3.3 and 3.4 have all been achieved, reflecting the novel and innovative nature of the companies which the window supports.

Overall, progress against Output 4, which measures the performance of the fund manager in terms of the challenge fund selection and contracting process has also met expectations.

Taken as a whole, programme performance scores A, as it has met expectations.

Lessons and how these have been shared

The initial business case acknowledged the difficulties that may be faced when turning research product ideas into viable businesses. RIB-funded businesses have been faced with regulatory hurdles and high start up and running costs, which made it difficult for firms to become profitable within the 36 month programme period.

A lesson learned for future programmes, and already taken on board by AECF, is that there should be greater acknowledgement of how difficult it is for researchers to make the transition to business. The skills needed to raise funds, keep teams paid and motivated, reach commercially oriented clients and deal with uncertainty and slow moving regulatory agencies are different from those required in conducting research.

In future programmes, greater consideration should be given to whether businesses have or are able to obtain the necessary commercial skills and capacity required to lead a successful business. This consideration needs to take place at the appraisal stage and the fund needs to include facilities to support, where feasible, those businesses that have innovative ideas and technologies but show weak business acumen.

This learning also suggests a strengthened ‘Knowledge Management’ role within the fund. Knowledge management incorporates project monitoring and results measurement as well as evaluation and in-depth learning from the portfolio, plus the analysis of dissemination of that collective learning to different audiences. This lesson has been taken up by other DFID supported projects, for example the Agresults Initiative where an independent knowledge management organisation is contracted to review and assess the impact of projects co-funded with the private sector. The Agri-tech Catalyst funding scheme of the UK Government takes a similar approach.

The Coffey M&E Study suggested a number of improvements to AECF’s monitoring and evaluation (M&E). The lack of capacity to measure the poverty profile of beneficiaries was a concern, particularly as impact on the poor was a key objective of this programme; and is a criticism of challenge funds and private sector programmes more generally. An improved M&E system could track indirect beneficiaries and market system improvements.

However, the Coffey recommendations reflect that extensive results and monitoring practices covering every project may not necessarily represent value for money. Rather, it may be more economical to verify the results of the top quintile of programmes that represent the greatest number of results – although the appropriate strategy for monitoring and evaluation is very much dependent on programme context. While there are lessons to be learned in failure as well as success, it does not make sense to go through an expensive process to record the characteristics of a few beneficiaries. AECF is planning to introduce verifiable cases studies for selected projects. These verifiable case studies should also elucidate another challenge that arose during the funds progress; that of determining attribution when multiple funding sources are being used. Assessment of attribution requires more detailed monitoring and assessment of particular projects.

: DETAILED OUTPUT SCORING

Output Title	Business initiatives supported by the AECF generate development benefits with high outreach, in particular to: those in rural areas; very poor; women; and youth.
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 1.1 / Net number of primary beneficiaries benefitting from ongoing AECF funded projects, by year, expressed as number of: / (a) households; and / (b) people.	90,000 / 450,000	558,517 / 2,792,585
Output indicator 1.2 / Average net benefit per household / per year (US$).	66	65.04
Output indicator 1.3 / Percentage of direct primary beneficiaries that live in rural areas.	60%	Not available – no verification studies as yet
Output indicator 1.4 / Percentage of direct primary beneficiaries that are poor (i.e., earn less than US$2 per day).	50%	Not available – no verification studies as yet
Output indicator 1.5 / Percentage of direct primary beneficiaries that are women.	50%	Not available – no verification studies as yet
Output indicator 1.6 / Total Jobs created (FTE) through/in enterprises supported by AECF: / (a) men; / (b) women; and / (c) youth (18-35 years).	700 / 300 / (300) / = 1000	272 / 198 / 299 / = 470

Key points
The number of households benefitting from AECF RIB funded projects is 558,517; significantly exceeding the milestone targets set. This result is largely driven by the results of the Mediae Trust mass media extension work on small-scale agriculture.

In 2014, the University of Reading interviewed over 13,000 farmers contacted through Media to estimate the value of the changes farmers make as a result of extension messages. The report estimated that over 428,000 households in Kenya directly benefited after adopting a practice they learned. Maize farmers in the Murang’a area saw their yields quadruple after adopting the recommendations. Farmers were more likely to be more confident to try new things, and spend more money investing in their farms. The survey also focused on dairy farmers, the second highest sector where farmers adopt new practises. The estimated net increase in the value of milk produced in Kenya as a direct result of the Mediae Trust’s extension programme in 2013 was US$24.1 million. This is a US$37 gain for every US$1 spent on production of the extension effort, and a US$205 gain for every US$1 spent on dairy sections alone.

In the last project year Mediae benefitted 515,000 households. This is significantly higher than the 108,774 attributed to Mediae in 2014, as the 2014 figure only reflected households who made changes in maize, dairy or both enterprises and that were influenced through Mediae’s work. This approach, to take into account only those benefitting from improved maize and/or dairy practices, was deemed to be excessively conservative by the Fund Manager and it was decided that the full number of households benefitting, as calculated by the University of Reading, provided a more accurate picture of the Mediae’s extension impact. If the same approach had been taken in 2014 the number of households benefitting from Mediae would have been 428,000. The results for 2014/2015 are an estimated 20% increase based on the 20% increase in farmers reached in 2013-2014. No further verification of final figures has taken place and the Mediae project would be a key project for the verification studies proposed by the Coffey M&E study. Such a study could help examine attribution of change through mass media and the impact of extension messages on the poorest households and by gender.

Households benefitting from other RIB projects (1.1) make up slightly less than the 50% of the milestone for 2014, ranging from 1,270 households benefitting from Super Sires Genetics to 30,172 from Brentec Investments. Four out of the nine companies had no beneficiaries documented up to February 2015. This can be partly explained by poor market access.

The Fund Manager collects a range of data when preparing the AECF Window Progress Reports and during site visits. However the Fund Manager was unable to verify the results for two projects; it was not possible to visit Toguna Agro works sites to verify the results due to conflict in northern Mali and for BLGG the company has been selling advice therefore the Fund Manager noted that it has not been possible to verify if people had taken on the recommendations. However, one could assume that consumers would derive benefit as they were willing to pay for the consultancy service. No third party verification work, as recommended by the M&E study undertaken by Coffey International, has yet been undertaken for any other RIB1 project. The mechanism and funding for these verification studies is still being negotiated between AECF and funders. Verification studies would provide a more robust tool for formally obtaining and calculating information on the proportion of poor households reached and gender benefit (1.3 – 1.5).

Job creation figures (1.6) were 470, significantly less than the 1000 projected in the logframe. This figure does not raise major concerns as job creation was never expected to be a primary development benefit of RIB, as the emphasis was on creating increased income generation for farmers. The window achieved its target for average net benefit per household per year (1.2).

Overall the window did achieve significant results for the output objective of ‘Business initiatives supported by the AECF generate development benefits with high outreach, in particular to: those in rural areas; very poor; women; and youth’, however this output has been scored as high risk due to concerns relating to result measurement interpretation and lack of verification studies, particularly relating to the gender and income characteristics of beneficiaries and how to attribute impact. The programme has been scored A as it exceeded its central target.

Recommendations

R3 – Recommend that for any future projects, AECF should reassess the methodology for calculating the milestone targets for job creation.

R4 – the mechanism for verification studies be finalised and studies of the highest performing RIB1 projects be carried out if funds allow. The studies should particularly examine attribution of change, impact on the poorest and gender benefits.

## DETAILED OUTPUT SCORING

Output Title	The business initiative supported by AECF (and the products and services delivered through them), are sufficiently commercially viable that the associated development impacts are sustainable.
Output number per LF		2	Output Score	B
Risk:		Medium/High	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Output Indicator 2.1 / Ongoing projects that are profitable 36 months from date of contract: / (a) total number; and / (b) percentage	Year a) No. b) % / 2014 9 67.5% / 2015 10 62.5% / 2016 16 94.1%	2014 a) 3 / b) 33.3%
Output Indicator 2.2 / % repayable funds due for repayment / that are repaid. / (a) = cumulative total repayable / grants due (US$); and / (b) cumulative total repayable / grants repaid (US$), / (c) = percentage.	2014 / a) 1,069,000 / b) 962,100 / c) 90%	2014 / a) 1,069,000 / b) 0 / c) 0%

NB: Progress against milestones from Feb 2014 to Jan 2015 is based on the grantees reports submitted in February 2015 and verified between March and June 2015 by the FM.
Key points

The logframe target for 2014 was that 67.5% (6 out of 9) RIB companies were to be profitable 36 months from date of contract; however progress was significantly less at 33.3% or 3 of 9 companies. The RIB Portfolio report 2014 provides a number of reasons for this, including regulatory barriers, longer than expected lead times on setting up or building new facilities and some companies struggling with different models of generating sales and defining their route to market.

There is a possibility that in setting initial log-frame targets, there was a failure to recognise the substantial challenge of the slow pace of policy and regulatory change in Africa for novel technologies and the difficult transition for managers with a research background to manage commercial portfolios.

The Fund Manager has been engaging with RIB companies on promoting a more commercial orientation, which they assessed some companies to be lacking. In the last year Brentec Investments have revised their business model and their route to market by outsourcing their distribution, which they were previously doing themselves.

The theory of change for the AECF assumes that investing in the private sector delivers more sustainable results as companies will continue to implement project activities after the end of the formal project due to their profit incentive. For this to be achieved it is necessary for AECF investees to be commercially sustainable. The RIB portfolio turnover almost doubled in 2014 over the year before. The greatest turnover relates to Mediae whose extension efforts expanded into Tanzania and Uganda, plus Toguna who resumed production following armed conflict in northern Mali and FAIM. However, there remains a risk that a number of these companies, whilst still operational, will fail to eventually become profitable and commercially sustainable. The Fund Manager’s developed a red, amber, green colour coded risk rating system that included assessment of the business model and cash flow. The latest assessment listed 6 out of 8 projects as having an amber risk rating. The assessment carried out for Mediae, which is rated green, was done in the knowledge that this company would likely remain dependent on some form of grant funding for the foreseeable future.

RIB provided businesses with a mix of grants and non-recourse loans (repayable grants). RIB1 provides slightly more repayable loan than grant, with an average of 52% of total funding provided as repayable loans. The first loan repayments were due in 2014 with the logframe target set at 90% of loan repayments due (1,069,000) would be repaid. As yet, no repayments have been made. This has been attributed to slow business growth and lack of profitability. AECF continues to follow outstanding loans.

The anticipated deadline for loan repayments may have been over optimistic in the original programme design. Lessons learned are around focusing on prudent and realistic business planning and the role of the investment committee in scrutinizing and challenging proposals in areas such as realistic timescales of start-ups companies to move into profit.

Recommendations
R5- Agreement on how outstanding loans are treated in closed windows should be agreed by all donors funding AECF.

R6-The investment committee should focus on prudent and realistic business planning challenging in areas such as realistic timescales of start-ups companies to move into profit.

## DETAILED OUTPUT SCORING

Output Title	AECF identifies and supports business initiatives which generate sustained and significant positive development.
Output number per LF		3	Output Score	A
Risk:		Low/Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output 3.1 / Total number of ongoing projects.	13	15
Output 3.2 / Ongoing projects that are marked 3 or above on the AECF innovation scale: / (a) total number; and / (b) percentage.	10 / 75%	13 / 87%
Output 3.3 / Ongoing projects achieving high development impact: / (a) total number; and / (b) percentage. / High development impact: generates a total net benefit of US$250k or more per annum.	3 / 23%	5 / 33%
Output 3.4 / Ongoing projects where innovation is recognised: / (a) total number; and / (b) percentage.	5 / 38%	4 / 26.7%

Key points

Progress against the majority of Output 3 indicators has exceeded the logframe targets. The RIB Window seeks to support the commercialisation of new technologies by supporting businesses aimed at getting new technologies and outputs of agricultural research into farmer’s fields. As a result you would expect that most projects would be innovative and mark at least 3 or above on the AECF innovation scale. It should be noted that this innovation scale is applied to all AECF windows.

For 2014 13 RIB1 and RIB2 projects scored 3 or above on the AECF innovation scale exceeding the target of 10 projects. The basis on which projects are judged to be innovative is through demonstrating new business models that are replicable and can benefit the poor. All projects are replicable if companies can develop similar skill sets to take advantage of new technologies. To measure the rate at which the innovation of projects is recognised a new indicator was included in the revised log frame of June 2015; ‘ongoing projects where innovation is ‘recognised’: (a) total number; and (b) percentage’.

Targets on number of projects achieving high development impact (projects generating a total net benefit of $250,000 or more per annum) has also been exceeded. Five RIB1 projects have contributed to these results; Mediae total net benefit (TNB) $30,000,000, Brentec Investment TNB $4,094,642, Phoenix Limitada TNB $1,174,496 and Super Sires Genetics TNB $537,210.

RIB1 annual reports have raised queries over the capacity of the grantees to benefit the poorest farmers who may not be able to afford new technologies. To date it has not been possible to provide independent verification of poverty impact and gender benefits. However, information obtained from site visits provided examples of RIB1 projects reaching smallholder farmers with affordable new technologies. Brentec manufactures and sells vaccines against Newcastle disease, which affects chickens. The vaccine, marketed as ‘Kukustar’, is thermostable unlike alternative products on the market, allowing it to be transported and stored without the need for full cold chain infrastructure. This makes it easier for smallholder farmers to use, as poor storage and transport often means other forms of the vaccine are ineffective. Kukustar is also sold in small quantities (minimum dose 25 chickens), at a maximum price of 100 shillings (approx. $0.02) a dose. This is to target smallholders who on average have 18-31 chickens, and make up roughly 80% of Brentec’s customer base. Similarly, field visits revealed that SoilCares (formally BLGG) provides soil analysis services via infrared spectroscopy to farmers in Kenya, including individual farmers, NGOs and farmer co-ops (who provide the service to their members) and local government. They have provided soil analysis services to approximately 10,000 farmers in Kenya, about 8,000 of which received the service via a 3rd party (e.g. NGO, co-op). Farmers pay 1,300 Kenyan shillings for the analysis (about $12) if purchasing direct, but often less if through a 3rd party. Most farmers would like to pay less for the service, but savings realised by applying the right fertiliser and lime mix far exceed the cost. SoilCares has also developed a low-cost hand held spectrometer that will give smallholders clarity on soil nutrition requirements. When the hand-held tester is brought to the market, the price is likely to drop to circa 500 Kenyan shillings per test. Most beneficiaries are reported to be smallholders and the company is focusing specifically on reaching dispersed, rural populations and developing products (the hand-held testing device) that are designed to deliver soil testing to low income households.

Overall, this output has performed well against its milestones.

Recommendations

R7 – the mechanism for verification studies be finalised and studies of the highest performing RIB1 projects be carried out if funds allow. The studies should particularly examine attribution of change, impact on the poorest and gender benefits.

## DETAILED OUTPUT SCORING

Output Title	AECF identifies, selects, contracts and provides managed support to business initiatives.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output 4.1 / Cumulative number of: / (a) competitions closed; / (b) registrations completed; / (c) applications received; and / (b) eligible concept notes marked.	a) 2 / b) 2,000 / c) 200 / d) Target not set	2 / 1,276 / 549 / 386
Output 4.2 / Cumulative number of: / (a) full applications (i.e. business plans) submitted; / (b) approved; and / (c) approval rate.	450 / 30 / 7%	31 / 17 / 54.8%
Output 4.3 / Cumulative number of projects successfully contracted.	18	17
Output 4.4 / Cumulative number of contracted projects that closed before their original contract end date.	1	0 / (Klein Karoo is in the process of being closed and Leldet Ltd may also be closed.)
Output 4.5 / Cumulative project funding pipeline metrics: / (a) new funds available to projects (US$); / (b) funds committed to projects at IC stage, pre-contract signature (US$), / (c) % available funds committed; / (d) funds contracted to projects (US$); / (e) % available funds contracted; / (f) funds disbursed to projects (US$); and (g) % available funds disbursed	12m / 8m / 67% / 7m / 58% / 6m / 50%	12.59m / 11.06m / 87.8% / 11.05m / 87.8% / 6.17m / 78% (KPMG report June 2014)

Key points

This output has been scored an A, despite initial slow progress in contracting businesses to implement projects. Delays were caused as the original concept of relying on African Research centres to identify key project ideas to promote through RIB did not deliver results and very few projects were identified through this route. AECF had to resort to the more traditional technique of calling for proposals. Despite delays in getting RIB projects contracted, project funding pipelines have been met and in some cases exceeded.

As the RED funded RIB1 projects near completion there are still a few projects where funds are due to be disbursed. This has delayed the closure of projects and the ability of AECF to manage loan payments. In order to address this, DFID’s ARD have now taken over programme management responsibility for RIB 1 programmes including the recovery of loan repayments.

Based on the latest information provided by the Fund Manager, funding was still to be disbursed to;

1. Toguna Agro Industries, grant of $187,500, and a loan of $187,500 with a total of $375,000. Disbursements to Toguna were delayed due to civil unrest in Mali.
2. Leldet Ltd, a total of $222,847.00 (grant and loan combined) was still to be disbursed, however the Fund Manager recommend that this project be closed and no further disbursements made.
3. Phoenix Ltd, a loan of $400,000 was still due to be disbursed. The Fund Manager had noted that this company had become unresponsive, but with recent support from the specialist group AgDevco[1] in Mozambique the Fund Manager now has re-engaged with the project. The Fund Manager plans to continue monitoring this project to end of contract and review the loan situation at that time.
  [1] AgDevCo is a UK registered charity that invests its own funds and raises third-party capital to develop agriculture businesses that are profitable and deliver transformational benefits for rural communities.

Recommendations

A recommendation on the disbursement of funds is set out in R7.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The competitive nature of the AECF’s funding allocation process ensures funds are provided to the most commercially viable ideas that offer a large development impact. The competitive process includes five steps:-
1. Companies register for the Competition
2. Concept Notes submitted to the AECF
3. Shortlisted Concept Notes reviewed by the Investment Committee
4. Business Plans generated for approval
5. Projects approved for funding.

The management fees for the RIB programme overall reflect 17.21%.

VfM performance compared to the original VfM proposition in the business case

Whilst no specific measures on Value for Money were set when the programme was originally designed,
VfM indicators were subsequently agreed and progress against these has been tracked. Benchmarks were based on the AECFs oldest window (the General Window-GW) and two closely aligned but separate programmes: the Financial Deepening Challenge Fund (FDCF) and the Enterprise Challenge Fund (ECF). These programmes provided indicative benchmarks only as they are of a different duration and intensity of management to the AECF.

Assessment of whether the programme represented value for money

Private sector leverage is currently at a rate of 2.73, with $6,075,967 of AECF funds (grant and loan) being matched by $16,404,489 by the successful grantees. The RIB Window is performing well against this indicator.

The RIB business case suggests that 30% of businesses will fail. The current rate of businesses failing within the RIB1 Window is 11.1%

Effectiveness
The total development rate of return (DRR) reflects the development returns compared to amounts disbursed and the RIB DRR is at 12.47 which is significantly higher than the 6.96 benchmark. The total net development impact for RIB as a proportion of the value of cumulative funds disbursed including the Fund Manager, AGRA Fees and additional services is 8.25; therefore RIB is having a development rate of return several times that of the cost of implementing the window, indicating that benefits outweigh costs.

Overall
The RIB1 funding window closed and the last projects within it are coming to completion. Overall the development rate of return of RIB1 as a standalone window reflected value for money. Management costs were slightly higher than expected; however, overall RIB 1 and 2 costs of 17.21% for both windows does represent VfM when benchmarked against comparator organisations. Negotiations are currently ongoing, through ARD and AECF, for the Australia’s Department of Foreign Affairs and Trade (DFAT) to pick up any future management costs for the remainder of the duration of the remaining RIB 1 windows.

Quality of financial management

The quality of the financial management of the overall AECF portfolio by AGRA has varied over the programmes time frame. A financial due diligence (FDD) of the AECF was commissioned in 2014. The FDD identified some problems with AGRA’s accounting treatment of funds. AGRA subsequently invested in the capacity of their staff and has completed a reconciliation of the net cash position on each window. Donors are continuing to monitor the implementation of the FDD recommendations through the AECF Steering Committee.

DFID programme managers have been working closely with AGRA to ensure the quarterly reports they provide are accurate, confirming all expenditure to date and have realistic forecasts for the next quarter.

E: RISK

Overall risk rating: Moderate

Quality of risk management over the life of the programme

Initially the risks assessment in the programmes design was rated as low; however a detailed identification of risks and how they would be managed was included in the programmes design. This original assessment has been reviewed and updated each year and there have been no changes to programme risk since the last annual review.

Financial management

In 2015 an additional risk was added relating to financial management in AGRA as there were concerns about its capacity. The probability of this risk was identified as high because there had been a number of staffing changes and unfilled vacancies within AGRA and the impact was assessed as medium because donors can only disburse funds for the AECF if they can be confident in the robustness of the systems in place to manage those funds. This was a key risk facing the programme over its final year, and a financial due diligence of the AECF was undertaken in 2014.

Risks to projects and window management

The AECF assesses risks individually for each project and reports them internally within AECF on a quarterly basis. ARD has continued to assess any potential risks to the RIB-1 window through meetings with AECF, or as any risks are reported by the AECF, either by e-mail, semi- and annual reports, or through any such reports to the AECF Governing Council. Oversight of the eventual closure of the remaining RIB1 windows will be managed by ARD in collaboration with AECF and the remaining donor to RIB (DFAT).

Recommendations

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

RIB 1 has mostly stayed on track against the planned timeframe for the programme and on or above target for funds raised and disbursed (Output 4), with the only caveats being that there are a small proportion of disbursements still to take place, which will be undertaken by AECF under the guidance of the donor steering group

Performance of partnership (s)
The partnership performed adequately. However more work needs to be done to institutionalise AECF knowledge and experience beyond high level management, to increase longevity of AECF beyond current partners.

Asset disposal and value obtained by DFID

No assets were purchased under the RIB 1 window.

Reporting by the Fund Manager on DFID’s capital has improved over the final year of the programme, following the financial due diligence undertaken after the 2015 Annual Review.
G: CONDITIONALITY (½ page)

Partnership principles assessment

The partnership principles were not used in monitoring this project as it does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The mid-term evaluation of the overall AECF has been completed by Ecorys. The final evaluation will take place in 2018 and will be based on a continuation of the case studies already undertaken along with 10-15 quantitative studies using counterfactual based evaluation methods.

The mid-term evaluation of the whole AECF confirmed the generally positive development benefits of the AECF but raised concerns regarding the additionality and sustainability of some of the investments made by AECF. The MTR concerns and the other general findings from the final evaluation will be built into the design of a strategic framework for the next phase of the AECF.

AECF commissioned Coffey International to conduct a study into the AECF’s Monitoring & Evaluation systems in 2014. This study recommended a more robust approach to monitoring and results measurement. To address this AECF employed a team of six people focussed specifically on the M&E of AECF and developed a central M&E proposal, which suggested including further verification studies to disaggregate data and verify results on the top 25% of the projects within each window. The AECF Steering Committee has approved the proposal from the Fund Manager and negotiations for funding the studies are ongoing.

Monitoring progress throughout the review period

In 2015, standardised logframes were introduced across all the AECF windows to increase the usefulness of results reported, and enhance the comparability across windows. However this does mean that comparability with previous years is slightly more difficult (although all important indicators continue to be monitored within the new logframe).

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

Review Process

The review process was completed by Lesley Hamill (Research Manager, Agriculture Research Team, Research and Evidence Division) with technical support from an Independent Animal Health specialist Tim Leyland. Quality assurance provided by Alan Tollervey (Team Leader, Agriculture Research Team). The Review is based on an APR completed in October 2015 and undertaken by Heather Scott-Rankin Policy Advisor (ARD) and David King, (Assistant Economist MENA) and site visits conducted by Tim McNeill. (Private Sector Development Advisor, DFID South Africa).

A member of the review team also visited two AECF RIB funded projects in September 2015 with the Fund Manager.

The main sources of information for this Annual Review are:
- How to Note: Reviewing and Project Scoring.
- AECF Fund Manager Year 2013/14 Annual Performance Assessment
- Africa Agribusiness Window Annual Report (Quest 5276697)
- General Window Portfolio Report 2014 (Quest 4666542)
- AECF RIB Window Annual Report (Quest 4787098)
- AECF Annual Report 2013-2014 (Quest 4667612)
- Africa Agribusiness Window Business Case (Quest 3174657)
- Due Diligence Report by Nathan Associates (Quest 4153345)
- AECF Revised Logframe (Quest 2778881)
- 2013 AECF Annual Review (Quest 3470404)
- Analysis of GW, ZIM1, RIB1 projects 21092015
- RIB Portfolio Impart Report 2014 (Quest 5276693)
- Site visit report on Brentec and BLGG (Quest 5276699)
- KPMG Annual Report July 2014 to June 2015 (Quest 5276703)
- AECF RIB1 SSU report (Quest 5276706)

## Annex A: Actions from previous Annual Review

	Recommendations from 2014 Annual Review	Response
1.	RED should continue to engage and collaborate with ARD on the management of AECF on:- / Proposed logframe revisions recently submitted by AECF for assessment by DFID. The revisions proposed for the RIB log frame appear appropriate but work needs to be done on quantifying the milestones and ensuring they are in line with other windows.	The new logframe has been agreed, however further work to quantify the milestones is required. DFID have provided feedback on the milestones.
2.	Promote the dissemination of information about RIB1 projects particularly case studies and exposure of the research community to some of the lessons generated on the commercialisation of new agricultural technologies in Africa.	Some progress. A recent article in a Uganda newspaper provided information on RIB1 funded business Brentec describing how the product came to market. The University of Makerere also published an article after trialling the vaccine for a year.
3.	Strengthened monitoring systems and verification studies proposed for RIB1 need to be put in place projects by June 2015. These studies need to measure new indicators and associated milestones. The balance of RIB1 funds held by AECF should be utilised for this purpose. / RED will work with ARD to do a strategic review of the prospects for achieving delivery of the outcomes from AECF RIB from RED contributions. By June 2015.	AECF have proposed a central M &E proposal. This would respond to the 2014 Monitoring and Evaluation (M &E) study undertaken by Coffey International recommending that verifications studies should be undertaken to disaggregate data and verify results. Agreement to implement the central M &E proposal is still being sought. As a result this recommendation has not been delivered.
4.	The fund manager has to produce an analysis of AECF loans by March 2015.	Completed.
5.	Revised log frame proposals to Output 3; i) “Ongoing projects that are marked 3 or above on the AECF innovation scale: (a) total number; and (b) percentage”; ii)“Ongoing projects where innovation is 'recognised': (a) total number; and (b) percentage; iii) “AECF identifies and supports business initiatives with high potential to generate sustained and significant positive development impacts and which are innovative” should be adopted.	Completed. The proposed revisions were accepted.
6.	Indicators in the draft revised log frame that measure progress toward “Business initiatives supported by the AECF generate development benefits which with high outreach, in particular to: those in rural areas; very poor; women; and youth” (Output 4) should be accepted.	Completed. This is now Output 4.
7.	Revised output on “The business initiatives supported by AECF (and the products and services resulting from them), are sufficiently commercially viable that the associated development impacts are sustainable” (new output 3) should be rated medium risk for RIB.	Completed. Reflected as medium risk in last year’s Annual Review.