ESPA Logical Framework Reporting: Financial Year 2016-17

IMPACT: Sustainably managed ecosystems contributing to poverty alleviation.
Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources. [1] / Sources: / National, global and regional monitoring of SDG implementation, particularly: / SDG 1 (No poverty) / SDG 6 (Clean water & sanitation) / SDG 11 (Reduced inequality) / SDG 13 (Climate action) / SDG 14 (Life below water) / SDG 15 (Life on Land) and / SDG 16 (Peace, justice & strong institutions) / Global Environment Outlook 6 (UNEP) / Global Biodiversity Outlook (CBD)
[1] At Impact level, the ESPA programme will contribute to this process, but progress will depend on other processes. For this reason, no targets are provided as it would be impossible to attribute change to the programme. The overall success of the programme is thus measured at outcome level.

Outcome: To positively influence end users and decision makers through the generation of cutting edge evidence on ecosystem services, their value, and links to sustainable development.
Indicator	2013 Milestone	2015 Milestone	2017 Milestone	2018 Target	2013 Progress	2015 Progress	2017 Progress
O.1 / ESPA research outputs reflected in national, regional or international development policies and practice.	1	8	20	55	7	19	36
O.2 / Development activities or investments informed by or utilising ESPA research.	£2 m	£30 m	£40 m	£65 m	£16.3 m	£32.6 m	£54.6 m

Output 1: A high quality, multi/ interdisciplinary and extensive body of knowledge on ecosystem services, their dynamics and human use generated.
Indicator	2013 Milestone	2015 Milestone	2017 Milestone	2018 Target	2013 Progress	2015 Progress	2017 Progress
1.1 / Total number of journal articles attributed to ESPA projects.	20	100	200	375	66	138	292[2]
1.2 / Number of other research outputs (books, book chapters, briefing papers, conference papers, grey literature).	20	300	600	750	50 / (2014 = 104)	6 books / 19 book chapters / 312 other publications / 337 Total	11 books / 40 book chapters / 575 other publications + engagement publications / 626 Total
1.3 / Percentage of total journal articles published as open access.	25% since start of the programme.	50% since previous milestone.	70% since previous milestone	70% since previous milestone	50%	50% since 1/4/2013 / 50% since start of programme	63% since / 1/7/2016[3] / 59% since the start of the programme
1.4 / For each project that has published journal articles at least one is of a multi-/interdisciplinary nature.[4]	25% of total projects	60% of total projects	70% of total projects	80% of total projects	PPD 25% / PFG 83%	SRC 89% / PPD 86% / PFG 100% / ESPA-2011 100% / ESPA-2012 67% / ESPA-2013 100%	91% of total projects / SRC 89% / PPD 89% / PFG 100% / ESPA-2011 100% / ESPA 2012 100% / ESPA 2013 100% / ESPA 2014 / 100%
1.5 / External citations of ISI journal articles from ESPA projects in research publications.	2	600	5,000	7,500	322	1,689	5,611[5]
1.6 / Global average citation rates of journal articles from ESPA projects published from 2009 to 2015[6].	n/a	n/a	2009: 22 / 2010: 20 / 2011: 16 / 2012: 14 / 2013: 10 / 2014: 7 / 2015: 4 / 2016: 1 / 2017: 0.1	TBD	n/a	n/a	2009: 60 / 2010: 28 / 2011: 30 / 2012: 96 / 2013: 22 / 2014: 17 / 2015: 18 / 2016: 3 / 2017: 1
1.7 / Number of computer models and datasets (with URLs) produced to support decision-makers to deliver evidence-based policy and investment decisions.	ESPA Directorate provides guidance	5 new tools/ models/ f-works from ESPA projects	65 new f-works, methods, tools and models from ESPA projects: / 30 models / 15 tools and datasets / 20 methods/ f-works	80 new computer models and publicly available datasets	ESPA Directorate developed guidance	61 total including: / 27 models / 19 datasets	67 total comprising: / 34 computer models / 33 publicly available datasets
[2] Date extracted 1st September 2017, when the Researchfish import into the ESPA database was completed.
[3] 1/7/2016-31/6/2017
[4] The Directorate reviews each paper individually to determine whether it is multi- or Inter-disciplinary. A paper is deemed to be multi- or inter-disciplinary where: a) There is a dimension of natural and social science (economics, political science, social surveys etc) in the methodology or approach of the paper, or b) A conceptual papers discusses interdisciplinary science, particular from a new perspective informed by ESPA research.
[5] Date extracted 25th August 2017, when the Researchfish import into the ESPA database was completed.
[6] Compared with global average citation rates from environmental science in the same year, as reported by ISI/ Web of Knowledge

Output 2: Increased demand for and uptake of ecosystems for poverty alleviation research.
Indicator	2013 Target	2015 Target	2017 Target	2018 Target	2013 Report	2015 Report	2017 Report
2.1 / ESPA Directorate and researchers contribute evidence to national/regional/ international processes, panels and committees of policy relevance.	25	72[7]	110[8]	145	34	63	124
[7] Targets for indicators 2.1.2 and 3.3.1 aggregated
[8] Targets for indicators 2.1.2 and 3.3.1 aggregated

Output 3: Developing country researchers participate actively in ESPA research and their capacity is enhanced.
Indicator	2013 Target	2015 Target	2017 Target	2018 Target	2013 Report	2015 Report	2017 Report
3.1 / Percentage of academic papers attributed to ESPA with developing country authorship.[9]	55%	65%	65%	65%	62%	62%	59%
3.2 / Percentage of publications attributed to ESPA with a developing country lead author.	25%	35%	25%	25%	24%	26%	25%
[9] The Directorate classifies an ESPA researcher as developing country (or not) according to the institution they are affiliated with as listed as on the front page of the journal article in question. In line with the World Bank’s ‘List of Country and Lending Groups’ for country classification, the Directorate counts Low-income economies, Lower-middle-income economies and Upper-middle-income economies as ‘developing countries’.