Humanitarian Preparedness and Response Programme (HPRP)

Project Completion Review – June 2017

List of abbreviations

AFD	Armed Forces Division
CHASE	Conflict, Humanitarian and Security Department
CSSF	Conflict, Stability and Security Fund
DFID	Department for International Development
DREE	Disaster Response Exercise and Exchange
ECHO	European Civil Protection and Humanitarian Aid Operations
FD	Foreign Donation
GIS	Geographic Information Systems
GoB	Government of Bangladesh
GPS	Global Positioning System
HCTT	Humanitarian Coordination Task Team
HPRP	Humanitarian Preparedness and Response Programme
HSA	Humanitarian Staging Area
IMO	Information Management Officer
IMWG	Information Management Working Group
IOM	International Organisation for Migration
JNA	Joint Needs Assessment
JNA	Joint Needs Assessment
JRP	Joint Response Plans
LCG DER	Local Consultative Group for Disasters and Emergency Response
MAF	Mission Aviation Fellowship
MoDMR	Ministry of Disaster Management and Relief
NARRI	National Alliance for Risk Reduction and Response Initiatives
NGOs	Non-governmental organisations
OCHA	Office for the Coordination of Humanitarian Affairs
OCHA ROAP	Office for the Coordination of Humanitarian Affairs Regional Office in Asia & Pacific
PIC	Project Implementation Committees
SDR	Secondary Data Reviews
SHPR	Strengthening Humanitarian Preparedness and Response
UN	United Nations
UNDG	United Nations Development Group
UNDP	United Nations Development Programme
UNHCR	UN Refugee Agency
UNICEF	United Nations Children Fund
UNRC	United Nations Resident Coordinator
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme
WFP	World Food Programme

Project Completion Review - Top Sheet

Review Date:	June 2017

Title: Bangladesh Humanitarian Preparedness and Response Programme (HPRP)
Programme Code: 202660	Start Date: 30/06/2011	End Date: 31/03/2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2012	2013	2014	2015	2016	2017
Programme Score	A	A	A	A	A	A
Risk Rating	Low	Low	Low	Low	Moderate	Minor

This programme has supported 862,237 people with humanitarian relief assistance. It has also supported the humanitarian community to prepare for disasters and to build a robust evidence base for humanitarian action. The programme has supported Rohingya refugees with emergency food aid.

Financial Position

Original Programme Value	£20 million
No cost extension to extend programme end date from 31 Dec 16 to 31 March 17 / Cost extension in Sep 2015 to add £5m to the programme	£5 million
Log-frame revisions (with dates) / Log-frame 2012 (initial), Log-frame 2013 (refinements), Log-frame 2014 (refinements), Log-frame 2015 (updated after APR), Log-frame 2016 (updated in Sept 16 post APR)
Total programme spend	£24,765,307.78

Follow up actions required following closure

1. The DFID programme team should receive and review all outstanding project reports. The following project reports are due by the stated deadlines:

- Support to the United Resident Coordinator’s Office (financial), UNDP responsible, by 30 June 2017.
- Support to the International Organisation for Migration (IOM) for coordination work (financial and audit), IOM responsible, by 30 June 2017.

2. The DFID programme team should ensure that all relevant reports are stored in the correct archive and online locations, including DFID’s Aid Management Platform, in accordance with DFID’s guidelines by 30 June 2017.

3. The DFID programme team should communicate the important results achieved by the programme, for example through a press release or infographic distributed through social media by August 2017.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.DFID.gov.uk/iati_documents/3717152.odt
DevTracker Link to Log frame:	http://iati.DFID.gov.uk/iati_documents/5584917.xlsx

Outline of the programme and what it has achieved

DFID spent £24,765,307.78 to support humanitarian preparedness and disaster response in Bangladesh under this programme. The original programme value was £20 million. This was increased by £5 million in September 2015 to provide relief to Rohingya refugees from Burma and to respond to disasters while a new humanitarian programme was designed. There were three components to the programme:

1. Rapid response to disasters: £20 million for post-emergency relief and recovery work.
2. Institutional preparedness and logistical planning: £4.5 million for preparation work to help agencies to prepare for future disasters.
3. Building the evidence base: £500,000 to help build a robust evidence base for humanitarian action.

The expected impact and outcome were:

Impact: To save lives, alleviate suffering, maintain dignity and reduce risk amongst people affected by disasters in Bangladesh through direct humanitarian assistance and a better prepared humanitarian system.

Outcome: To improve the effectiveness of humanitarian response through direct delivery of appropriate assistance and promotion of strong coordination and logistical support.

The programme had four outputs:

1. Provision of emergency assistance and recovery support to households most affected by disasters;
2. Improved coordination and information management;
3. Logistical support for non-governmental organisations (NGOs) and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions;
4. An enhanced evidence base and better analysis for an effective disaster management response in Bangladesh, and globally.

Achievements

Rapid response to disasters

The UK used funding under this component to respond to disaster events. In 2011 when the business case was submitted to Ministers, the operational environment in Bangladesh meant that the UK could not provide support to Rohingya refugees. However, this changed following the release of the government of Bangladesh’s ‘National Strategy on Undocumented Myanmar Nationals’ in 2014, and the UK was able to provide support.

In total, the UK provided 862,237 people with humanitarian relief assistance following disasters:[1]
[1] For more details on results achieved by the programme, please see the detailed output scoring under section C.

- Floods in Northwest and Southeast Bangladesh, Oct - Dec 2014 and Aug - Dec 2015: 560,438 people
- Waterlogging in Southwest Bangladesh, Mar 2014 - Dec 2016 (2 phases): 62,300 people
- Tropical Storm Mahasen, Sep 2013 - Mar 2014: 72,405 people
- Food security and nutrition for vulnerable people in Cox’s Bazaar Dec 2014 - Nov 2016: 48,000 people
- Rohingya refugees, Apr 2015 - Dec 2016 (2 phases): 32,770 people

Institutional preparedness and logistical planning

This component strengthened the leadership and coordination capacities of the international system, focussing on humanitarian coordination, needs assessment and logistics preparedness. Since 2011, DFID made a series of investments to strengthen disaster preparation and coordination. Support to the Joint Needs Assessment (JNA) programme and the Logistics Cluster, which coordinates planning and logistics for humanitarian organisations in Bangladesh, were significant parts of this work. UK funding paid for humanitarian agencies to coordinate their humanitarian assessment work. The resulting assessments gave humanitarian actors and the Government of Bangladesh (GoB) a shared understanding of the impact of disaster events. This programme has also given disaster affected communities a voice in this process.

The UK supported the International Organisation for Migration (IOM) to coordinate humanitarian assistance for Rohingya refugees in Bangladesh. The UK funded a Humanitarian Affairs Adviser in the United Nations Resident Coordinator’s (UNRC) office, who further strengthened coordination by preparing joint response plans and supporting coordination between humanitarian actors.

Building the evidence base

Funding to the JNA programme has also improved the evidence base for humanitarian action. The JNA produced Secondary Data Reviews (SDR)[2] for disaster events including cyclones, river flooding and waterlogging. These reviews analysed the impact of disasters on different sectors, and have been used by humanitarian organisations to make contingency and response plans. The JNA helped embed a rigorous assessment process in the Bangladesh humanitarian architecture, increasing stakeholders’ ability to make evidence-based decisions. The project also supported research under a World Food Programme (WFP) project on adaptive early recovery from waterlogging. This research was used during project implementation and also to inform the new humanitarian programme, called Strengthening Humanitarian Preparedness and Response (SHPR).
[2] A compilation of key pre-disaster secondary information designed to improve the understanding of the impact of disasters.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The programme has achieved its outcome and has been rated A. All activities have been completed. A brief summary of progress against the outcome indicators follows:

Outcome Indicator 1: Disaster affected people assisted with shelter, food, nutrition, water/sanitation or early livelihoods recovery: 862,237 people were assisted. As the programme was established to respond to urgent and by their nature unpredictable disaster needs, it was not possible to predict the exact numbers of people to be assisted. Because of this unpredictability, no target was set at the start of the programme. DFID responded with resources as needed, in line with the principles laid out in the business case.

Outcome Indicator 2: Humanitarian Coordination structures active, timely performance during preparedness and response: The UK funded a coordinated needs assessment through the JNA programme. Financial assistance to the International Organisation for Migration (IOM) supported district and national level coordination for support to Rohingya refugee activities, which resulted in an improvement in the standard of assistance provided. UK support to the UNRC’s office through humanitarian advisory capacity supported coordinated response plans following disaster events. These were used by a wide range of humanitarian organisations in Bangladesh.

Outcome Indicator 3: Emergency response and recovery logistics maintained and strengthened: Via support to MAF, the UK has helped humanitarian agencies reach remote locations in Bangladesh and to do post-disaster aerial assessments. The UK’s support to the Logistics Cluster has strengthened disaster preparedness for a major seismic event.

Output Score and Description

The performance rating of this programme has been judged as A: outputs met expectations. No indicator targets were set for output 1 because it was not possible to predict the exact number of people to be assisted. A short summary of programme outputs is below:

Output 1: Provision of emergency assistance and recovery support to households most affected by disasters: Delivery of this output has been strong throughout the programme. Since 2011, UK funding has assisted 862,237 people with shelter, food, nutrition, water, hygiene and sanitation or early livelihoods recovery. See section C below for further information.

Output 2: Improved co-ordination and information management: During the lifetime of the programme, support to the JNA project, logistics cluster, and the UNRC’s office has strengthened the coordination of humanitarian systems in Bangladesh. As a result there is a much stronger shared understanding by all parties of how to plan and implement a humanitarian response effectively. For example, after floods in northwest Bangladesh in 2015, the UNRC led the humanitarian community in a coordinated response. This was followed by a joint needs assessment and the development of a joint response plan.

Output 3: Logistical support for NGOs and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions: Support to the Mission Aviation Fellowship (MAF), a seaplane service, improved access to remote regions of Bangladesh for a wide range of humanitarian organisations, facilitating assessment, delivery and monitoring of disaster responses.

Output 4: An enhanced evidence base and better analysis for an effective disaster response in Bangladesh, and globally: DFID supported six studies on the impact of disasters in Bangladesh. These analysed the sector-specific impact of natural disasters, and were used by humanitarian organisations in their disaster response plans. These reviews provided relief and development actors with valuable insights into the impact of cyclical disasters in Bangladesh. A strength of these reviews was that they were fully referenced and thus helped establish a robust evidence base for humanitarian analysis. The project supported research under the World Food Programme-led project on adaptive early recovery from waterlogging. This research was used during project implementation and also to inform the new Strengthening Humanitarian Preparedness and Response (SHPR) programme.

Lessons and how these have been shared

Lessons were shared with partners during wrap up meetings and also during assessments of proposals and were used to develop the new DFID humanitarian programme.

Key Lessons

Making our response more predictable: The humanitarian system in Bangladesh failed to address the recurrent nature of disaster risk. While the Government of Bangladesh has strong preparedness measures in place for some events, there is still scope for them to improve. For example, responses to disasters need to be quicker. A key lesson learnt has been for future DFID programmes to invest ahead of disasters to support early action. For example, DFID should agree trigger points for interventions, indicators for tracking results, and the structure of relief packages in advance. This lesson has been factored into the new humanitarian programme by placing a higher degree of decision-making in the hands of the relief community, under DFID oversight, leading to quicker responses.

Disaster Resilience – greater focus on preparedness, including of the government: A major lesson was that there was significant need to increase humanitarian preparedness investment. There is strong evidence from a DFID funded review of international evidence on post-emergency food aid that early procurement, as well as placing supplies in advance, can reduce costs by as much as 50%.[3] The pre-positioning of supplies, stronger engagement with GoB in preparedness activities, especially for major disasters, was found to be crucial. As a result of this learning, DFID has allocated £7.9 million to fund preparedness activities in the new humanitarian programme.
[3] Venton, C. Value for Money of Multi-year Approaches to Humanitarian Funding (2013)

Stronger focus on Monitoring and Evaluation: Evidence and learning has not been shared and applied systematically in this programme. In this programme, no resources were provided for overall monitoring and evaluation. While there was a component on evidence building, this was not coordinated. DFID has included a greater focus on evidence, learning and monitoring in the new humanitarian programme as a result.

Introduce a single point management system to streamline administration: Administration in this programme was a challenge. The programme funded 22 individual components, resulting in a heavy administrative and programme management burden. DFID’s new humanitarian programme has fewer components and will be delivered through a fund manager. DFID will therefore have more resources available for strategic engagement across the humanitarian sector, and the programme will have a greater capacity to scale up quickly in response to major disasters.

Greater degree of consultation in the business case design process: Stronger consultation could have improved coordination between humanitarian actors, as well as the targeting of interventions. In response, significant resources were used for consultation in the new humanitarian business case. The resulting consultative process included the UN, NGOs and the Government of Bangladesh.

Coordinated assessments: DFID support to the JNA meant that all needs assessments following disasters in Bangladesh from 2013-2017 were coordinated and involved all key humanitarian actors.

Joint response planning: Support to the UNRC’s office helped embed the findings of needs assessments into the coordinated response plans developed jointly by UN agencies, NGOs and the Red Cross.

Response to recommendations in the previous Annual Review

Recommendation	Action taken
1. Adjust the weighting of the Log-frame outputs to better reflect programmatic delivery over the implementation period (by October 2016).	Done. Log-frame updated.
2. Apply lessons learnt from the current program (HPRP) in the delivery of the new humanitarian program (SHPR) (by March 2017).	Done. See individual output areas for further details.
3. Communicate the important results achieved by the programme, for example through a press release or infographic distributed through social media (by March 2017).	This will be completed by 30 August 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Provision of emergency assistance and recovery support to households most affected by disasters
Output number from the log frame		1	Output Score	A
Risk:		Minor	Impact weighting (%):	70%
Risk revised since last Annual Review?		N	Impact weighting % revised since last Annual Review?	N

Indicator(s)	Milestones	Progress
1.1 Number of people receiving emergency food security assistance	None[4]	150,000 people received emergency food security assistance
1.2 Number of people receiving early livelihood recovery assistance	None[5]	379,495 people received early livelihood recovery assistance
1.3 Number of people receiving other forms of emergency assistance	None[6]	299,972 people received assistance as follows: / 2,250 households received shelter support; / 23,293 households (12,743 in 14/15 and 10,550 in 15/16) received water, sanitation and hygiene (WASH) support; / 34,303 households received unconditional cash transfers; / 9,600 households received a nutrition-related Monthly Subsistence Allowance; / 14,481 households received cash for work following Tropical Storm Mahasen in 2014.
1.4 No of registered Rohingya refugee receiving food and nutrition assistance	34,000	32,770 Rohingya refugees received food and nutrition assistance. The target was set at 34,000 based on UN Refugee Agency (UNHCR) data and the results are based on the actual uptake.
[4] Not included as it is difficult to predict size of response
[5] Not included as it is difficult to predict size of response
[6] Not included as it is difficult to predict size of response

Key Points

Since 2011, UK funding has assisted 862,237 people with shelter, food, nutrition, water, hygiene and sanitation or early livelihoods recovery through this programme. DFID funded NGOs and multilateral organisations to achieve this result.

In February 2014, the Government of Bangladesh launched the National Strategy on Myanmar Refugees and Undocumented Myanmar Nationals in Bangladesh to address the security, socio-cultural, economic, demographic, environmental, and humanitarian and image challenges resulting from the large Rohingya refugee population in Bangladesh. This enabled humanitarian assistance to be extended to refugees living in makeshift, non-registered settlements, as well as refugees living in the UN Refugee Agency (UNHCR) supported registered camps.

Indicators 1.3 and 1.4 were added in 2015 to better capture the range of humanitarian assistance provided by the programme, including to the Rohingya refugees. Indicators 1.2 and 1.3 did not have any milestones because they tracked responses to crises; the size and frequency of these could not be predicted in advance.
A key lesson learnt from the activities funded under this output was that while often good, in some cases DFID was unable to provide support in a timely manner following disasters. For example, in response to Tropical Storm Mahasen which occurred on 16 May 2013 the DFID supported NARRI[7] consortium (an NGO Consortium) programme commenced in early November, nearly 6 months after the storm had made landfall. Government of Bangladesh approval processes and staffing changes in DFID both contributed to this. DFID has worked to improve the predictability and timeliness of its responses to disasters as a result.
[7] National Alliance for Risk Reduction and Response Initiatives (NARRI) consortium, a group of international NGOs in Bangladesh who delivered responses for DFID in northwest, southeast and southern coastal regions of Bangladesh.

People affected by disasters have received very effective relief assistance through cash transfers. Cash transfers (Conditional, unconditional, multipurpose) helped people access resources that met their most important needs at that time. The modality of cash transfers used (by hand, mobile banking) depended on the context. Cash gave people the ability to choose what support to purchase in order to meet their own needs. Beneficiaries received cash safely and securely through mobile phone banking.

Gender

Under this programme, 146,173 women-headed households received post-disaster assistance. All the disaster relief interventions in this programme were overseen by community-level project implementation committees (PICs). The members of these committees were beneficiaries, and women were always represented. The role of the PICs was to steer and support the project at community level, and to act as a point of contact for beneficiaries.

Support to Rohingya refugees in unregistered camps targeted the needs of women, including pregnant and lactating women. This treated and prevented acute malnutrition with specialised nutritious food. The programme supported 32,770 people with food cards[8]. 17,368 beneficiaries were women and 15,402 were men. The cards could be exchanged for food with local market traders at pre-negotiated prices. As women are traditionally responsible for food preparation within the household, senior female household members were made primary holders of these cards. As cardholders, women were empowered to choose how they met their family’s food needs. The establishment of registered shops inside the camps allowed women to buy food with decreased exposure to the insecurity and potential violence associated with leaving the camps. The shops were open six days a week from 9am to 5pm. Women and elderly people purchased smaller quantities of food on a regular basis, and so no longer had to carry heavy loads. Follow-up analysis by the delivery partner (WFP) showed that the proportion of women able to exercise control over household decisions about food consumption increased from 41% to 61% during the programme. Services for Rohingya refugees were coordinated through camp “Block Committees,” consisting of refugees selected by their peers. 50% of the committee members were women.
[8] Foodcards are electronic voucher that provides food assistance by WFP to the Rohingya refugees in registered camps

Under an IOM coordination project for Rohingya refugees, supported by this programme, sexual and gender based violence risks, services and incidences were mapped. Awareness of these issues was raised in the community. Survivors of gender based violence had access to medical care and services in eight IOM-supported healthcare facilities in Cox’s Bazaar. A gender based violence hotline was set up and is still functional.

Summary of responses to issues raised in the previous Annual Review

Recommendation	Action Taken
As identified in previous Annual Reviews, improve the speed and predictability of UK crisis response.	DFID reflected this recommendation in the design of the Strengthening Humanitarian Preparedness and Response (SHPR) programme.

Output Title	Improved co-ordination and information management
Output number from the log frame		2	Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last Annual Review?		N	Impact weighting % revised since last Annual Review?	N

Indicator(s)	Milestones	Progress
2.1 Databases including a ‘3Ws’ (who, what, where) matrix, contact lists and other key data for every DFID-supported cluster	Humanitarian advisory support to the United Nations Resident Coordinator (UNRC’s) office: / Facilitate the provision of high quality needs-based impartial humanitarian assistance; / Support and strengthen in-country humanitarian fora and architecture; / Strengthen partnership among humanitarian actors.	Four Joint Needs Assessments and Joint Response Plans were completed, under the oversight of the Humanitarian Coordination Task Team GoB/inter-agency coordination forum) Consultations with partners were also held to review the humanitarian architecture in Bangladesh to make it more fit for purpose and the proposed revised structure is with GoB for review
2.2 Number of agencies trained to support implementation of a Joint Needs Assessment (JNA)	10 organisations / agencies have the capacity to lead coordination of a JNA	This target was achieved in 2014.

Key Points

Delivery of results against this output began in the second year of the programme. In the first year, significant staff time was spent in policy dialogue and on the establishment of new humanitarian coordination mechanisms in Bangladesh. This output helped humanitarian actors better respond to the needs of the people affected by disasters. Improved co-ordination meant that humanitarian activities were more strategic and attuned to the actual needs of the affected population. While this contributed to timely humanitarian responses, a key lesson from this work was that further improvements could be made. This output has contributed to:

Joints Need Assessment: DFID supported the Joint Needs Assessment (JNA)[9], which was a set of tools and methods for assessing humanitarian need. It was used by the Government of Bangladesh and the Humanitarian Coordination Task Team (HCTT). The HCTT was a group of representatives from humanitarian organisations that was hosted by CARE with technical support from ACAPS.[10] Staff members from 10 organisations were trained to lead a JNA in the first phase of the project, in 2012-2013. These trainings were refreshed in the consultation phase (2015-2016). Six ‘Secondary Data Reviews’ (SDRs)[11], compilations of pre-disaster secondary information designed to improve the understanding of the impact of disasters were also produced as part of this process. These considered six types of disaster event (cyclone, waterlogging, haor flooding, river flooding, flash-floods and landslides, and cold wave). In total, four JNAs were produced, and used to design four Joint Response Plans. These enabled agencies to design proposals based on prioritised needs, and were endorsed by the HCTT. A second phase of the JNA was planned but did not receive GoB approval and thus a consultation phase was designed to work with the GoB on their queries instead. A key strength of the JNA programme was that the relief community jointly contributed to a single assessment report. This ensured a shared understanding of how a disaster impacted people and communities so that the needs were clear and there was no duplication of support. Prior to the JNA, multiple scattered assessments were commonly produced. These failed to provide an overview of the scale and nature of disasters.
[9] A needs assessment is a tool used after any emergency to determine the main needs are following a disaster. A Joint Needs Assessment is a coordinated assessment following commonly accepted tools and methodologies to conduct the needs assessment.
[10] ACAPS is a non-profit, non-governmental project established in 2009 with the aim of supporting the humanitarian community with all aspects of humanitarian needs assessments.
[11] A compilation of key pre-disaster secondary information designed to improve the understanding of the impact of disasters.

Information Management Officer: A review by the Local Consultative Group for Disasters and Emergency Response (LCG DER) in 2012 identified information management as an area in which additional support was required. Additionally, ECHO’s[12] Humanitarian Implementation Plan for 2013 highlighted information management as the main challenge to Office for the Coordination of Humanitarian Affairs (OCHA’s) effectiveness in Bangladesh. DFID funded the secondment of an Information Management Officer to the UN Resident Coordinator’s Office for six months during the second half of 2013 to strengthen the information management capacity and skills of UNRC’s Office staff and the HCTT. The Information Management Officer was also responsible for coordinating the work of the Information Management Working Group, and led efforts to standardise information management-related procedures. The Information Management Officer supported the UNRC’s Office with mapping and humanitarian analysis in the humanitarian dashboard.
[12] European Civil Protection and Humanitarian Aid Operations

Humanitarian Affairs Adviser to the UNRC’s office: DFID funded a Humanitarian Affairs Adviser to the UNRC’s Office for two years from late 2015. This strengthened overall humanitarian coordination for preparedness and response. The Adviser became the co-chair of the HCTT in April 2016. Since then, the HCTT met 17 times, contributing to key humanitarian decisions in Bangladesh. For example, the HCTT produced a contingency plan for earthquake response in urban settings. This was used by development agencies in their disaster response planning. The Adviser also promoted civil-military coordination, for example by assisting the Office for the Coordination of Humanitarian Affairs Regional Office in Asia and the Pacific (OCHA ROAP) to organise a UK funded[13] UN Civil-Military coordination course from 19-23 March 2017. Finally, the Adviser supported IOM to prepare a contingency plan in response to the influx of Rohingya refugees from Myanmar in 2016. This included working on a UN Joint Response Plan to support Rohingya refugees and host communities in Cox’s Bazar.
[13] Funded from Conflict, Stability and Security Fund (CSSF)

Coordination for Rohingya refugees: The UK supported the IOM’s work in relation to undocumented Rohingya refugees. DFID funded a ‘Coordination Support Unit’ in Cox’s Bazar and a ‘3W’ (who, what, where) matrix showing the delivery of humanitarian services in areas hosting Rohingya refugees, along with the design of an online information portal. IOM completed a mapping exercise to assess the delivery capability of local Bangladeshi NGOs, which led to them write a capacity building roadmap. This was implemented in late 2016.

Summary of responses to issues raised in the previous Annual Review

Recommendation	Action taken
Under the UK’s next humanitarian programme DFID Bangladesh should continue to support humanitarian coordination structures, including the provision of personnel in the UNRC’s Office, with the aim of strengthening disaster preparedness and response activities in Bangladesh.	Done. This has been supported under the Joint UN Emergency Preparedness programme as part of the Preparedness pillar of the new SHPR business case.

Output Title	Logistical support for NGOs and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions
Output number from the log frame		3	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last Annual Review?		N	Impact weighting % revised since last Annual Review?	N

Indicators	Milestones	Progress
3.1 Proportion of Mission Aviation Fellowship flights taken by NGOs and other humanitarian or development actors.	Over 70% of Mission Aviation Fellowship flights are taken by humanitarian and development actors.	Cumulative total: / 71% of passengers were humanitarian and development actors. In total 174 NGOs have been served.
3.2 Number of customs officers in Bangladesh with increased awareness of customs processes – as related to humanitarian emergency supplies.	N/A	Not achieved. See ‘Key Points’ below for more information.

Key Points

This output supported a seaplane, which gave humanitarian actors access to remote areas. They used this to deliver support and survey the extent of damage after disasters. The logistics cluster helped humanitarian actors to respond to major disasters rapidly.

Mission Aviation Fellowship: DFID provided core support to an NGO called Mission Aviation Fellowship (MAF) to operate a seaplane shuttle service. This small aircraft can land on water in some of the most inaccessible parts of Bangladesh. This improves access to remote areas, including during disasters when roads are often blocked. MAF exceeded a target of 9,100 passengers, having flown 10,082 passengers in total. 71% of these were humanitarian and development workers. MAF commissioned an independent impact evaluation of its work. The evaluation found that MAF had made significant contributions to programme quality and had achieved good value for money. It had achieved this by reducing the need for remote management and by improving the development community’s ability to complete needs assessments, project management, monitoring, accountability, learning and advocacy work.

Strengthening the logistics cluster: DFID provided funding to WFP to strengthen the Logistics Cluster for emergency preparedness. There were four outcomes under the programme of which two were successfully achieved – Coordination & Information Management, and Geographic Information Systems (GIS) Capacity Building. Three Global Positioning System (GPS) trainings were held benefitting fifty-eight participants from twenty-one organisations in Bangladesh. This training produced officers who could gather and map data in disaster affected areas. These staff also helped to produce the Capacity Atlas, a document which listed the location of logistics infrastructure across Bangladesh and that has also been used extensively by stakeholders in the country. DFID support also made it possible for the national logistics capacity assessment to be updated. Both documents provided stakeholders with information for preparedness and response planning. We have shared the capacity assessment and Atlas with colleagues in London from the DFID CHASE[14] Operations Team.
[14] CHASE- Conflict, Humanitarian and Security Department in DFID

The remaining outcome areas, Custom Clearance Process for Emergency Relief Cargo and Military and Civil Defence Liaison, were not fully achieved. The concept of a “One Stop Shop” for customs clearance in emergencies was planned under this project. This was discussed with the Armed Forces Division (AFD) of the Bangladesh Army and the Ministry of Disaster Management and Relief (MoDMR). Due to a challenging political context during the project delivery period, WFP were not able to secure the government’s approval for this proposed activity. It was therefore postponed, and has now been included as a component in the new DFID humanitarian programme. The Logistics Cluster also trained more than 30 people from the Bangladesh Armed Forces as well as staff from humanitarian agencies in civil-military joint sessions. These led to greater understanding about civil military relations during disasters. However, a challenging political environment meant that it was not possible to support a Military and Civil Defence Liaison, another proposed component of this work.

Overall, this output has been rated A. Indicator 3.1 was just exceeded, and delivered consistently for the full five years of the programme. Indicator 3.2 was not achieved; however it was only active for a year and was a relatively minor part of the output.

Summary of responses to issues raised in the previous Annual Review

Recommendation	Action taken
Support for Mission Aviation Fellowship to continue to broaden its funding base to be less reliant on UK support in maintaining its service.	DFID has supported the Mission Aviation Fellowship to reach out to the donor community in Bangladesh. DFID Bangladesh will provide a reduced amount of funding to Mission Aviation Fellowship under the new humanitarian programme.

Output Title	An enhanced evidence base and better analysis for an effective disaster response in Bangladesh, and globally
Output number from the log frame		4	Output Score	A
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last Annual Review?		N	Impact weighting % revised since last Annual Review?	N

Indicators	Milestones	Progress
4.1 Number of reviews or studies commissioned to fill identified knowledge and information gaps in disaster planning and preparedness	Secondary Data reviews for 6 disasters / Humanitarian system wide review planned / Research on waterlogging issues	6 reviews completed in 2014 / The UK funded International Humanitarian Affairs Adviser to the UNRC's office initiated a review of the functionality of the Humanitarian architecture. / 6 research activities were undertaken which fed into the programme activities.

Key Points

This output was added in 2013. DFID supported a series of six Secondary Data Reviews (SDRs) in 2013-2014; through the Joint Needs Assessment project (see output 2). The SDRs investigated the sector specific impact of cyclones, flash floods and landslides, haor (wetland) flooding, river flooding, waterlogging and cold waves in Bangladesh.

The UK-funded Humanitarian Affairs Adviser to the UNRC's office also initiated a review of the functionality of the Humanitarian architecture. This review made recommendations, which have been presented to the Prime Minister’s Office, the Ministry of Disaster Management and Relief and the Ministry of Foreign Affairs for their review.

The project supported research under the WFP led project on adaptive early recovery to waterlogging. This was used during project implementation to identify key issues so that humanitarian actors could target their support more effectively.

Summary of responses to issues raised in the previous Annual Review

Recommendation	Action taken
Via the new humanitarian programme DFID Bangladesh should improve how it monitors and evaluates UK funded humanitarian activities in Bangladesh. This should include third party / independent monitoring. In addition, DFID Bangladesh through the new humanitarian program should also strengthen its approach to gathering feedback from beneficiaries to ensure their views are accounted for.	Done. The Monitoring and Evaluation for the new SHPR programme has been outsourced to a fund manager. A beneficiary accountability mechanism is being set up which will enable recipients of UK-funded humanitarian support to pose questions, raise concerns and report instances of fraud and corruption should they occur.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The Business Case for this programme notes that the key factors in ensuring maximum value for money for a humanitarian intervention are cost, speed and quality of response. The assessment below draws on the programme’s past annual reviews and on the reports from the 22 interventions it has supported.

Key costs

The highest proportion of cost in the programme has been for cash transfers, either directly or by using mobile phone technology. Cash transfers following disasters took place in 11 of the 22 interventions, totalling £12,071,128.21 (48% of the total budget). The second highest cost was the cost of relief materials[15] including food vouchers: £3,912,121 (16% of the total budget), followed by investment in disaster preparedness through systems strengthening and training: £2,684,385.00 (11% of the total budget). DFID Bangladesh’s Guidance on Measuring and Maximising Value for Money in Cash Transfer Programmes suggests an operational cost benchmark of 5-15% for cash transfer programmes. The 22 interventions in this programme had operational costs between 7-15%.
[15] WASH, Hygiene kits, seed support and food vouchers

Cost drivers

Cost drivers have varied across the 22 interventions in this programme. DFID has responded where possible to fluctuating cost drivers in order to maximise the benefits gained from the programme. For example, the DFID programme team has systematically worked with delivery partners to drive down costs and realise savings where possible. They have done this by scrutinising budgets, especially for staffing, training and office equipment. In one intervention responding to flooding in southeast Bangladesh, DFID made sure that delivery partners used staff that had already been used in a previous DFID intervention supporting Rohingya refugees. This reduced the cost of training. Under a NARRI consortium flood response in northwest Bangladesh programme, the team negotiated a £9,000 saving on logistics and personnel cost, which allowed the programme to reach a further 113 households within the budget. As part of the response to Tropical Storm Mahasen, DFID negotiated with the NARRI consortium to reduce overheads, including staff costs, which allowed for an increased number of beneficiaries to be targeted. Under a WFP implemented flood response in the northwest of Bangladesh, the initial proposal included 19% of the budget for direct operational costs. DFID successfully negotiated this down to 7.5%, without a reduction in the quality of the intervention. As a result, the intervention reached an additional 2,223 households with humanitarian aid, an increase of nearly 13%.

Exchange rate fluctuations through the lifetime of the programme decreased costs overall. DFID made sure that financial savings from these fluctuations were used to reach more beneficiaries. For example, in responding to Tropical Storm Mahasen, the NARRI consortium sought to deliver support to 11,500 households in Barguna and Patuakhali. By using an exchange rate gain of 9.5%, the consortium was able to exceed this target by about 25%, reaching 14,481 households in total.

Hartals (strikes) and insecurity related to political events caused major disruption to humanitarian operations in late 2013 and in early 2015. Hartals contributed to price inflation for staple foodstuffs and other essential supplies, as they resulted in travel restrictions, which reduced the supply of food. In response, DFID agreed no-cost extensions to affected interventions to ensure that work could be completed after hartals, to minimise the impact of price increases and travel limitations.

Partner actions to maximise Value for Money

DFID worked with delivery partners to maximise the value for money of humanitarian relief. For example, the NARRI consortium ensured that procurement, monitoring and evaluation activities used technology shared by all consortium members, which helped to drive down costs. When delivering the Tropical Storm Mahasen relief support, the NARRI consortium procured all items, including seeds, fertilizers and spades, through a central procurement system. The Consortium approach resulted in economies of scale through bulk purchasing of relief items. Framework agreements were also put in place during a response to flooding in the northwest for hygiene kits, improving the speed, quality and cost of the delivered relief. The DFID funded kits were procured centrally by Oxfam on behalf of the NARRI consortium members on the local market at a unit cost of £7.20. This cost compared favourably to the price of similar kits held by DFID in its central stockpile for humanitarian supplies in London. One key value for money benefit DFID observed when working with the NARRI consortium was efficient monitoring and evaluation. This was centralised with one representative undertaking monitoring and evaluation for the entire consortium. In the relief responses, the use of mobile phone-based systems to transfer cash to beneficiaries also resulted in good value for money, as this method meant that delivery agents avoided the banking charges associated with transferring funds into bank accounts. When responding to floods in the north west of Bangladesh, the NARRI consortium worked alongside the European Commission (ECHO). By working in this way, both parties benefitted from economies of scale and reduced costs.

The World Food Programme provided vouchers to Rohingya refugees to buy food. The price of food was negotiated each month centrally by the World Food Programme, to maximise their negotiating power and to minimise price spikes.
In general, we assess that DFID funded humanitarian activities in Bangladesh were of a good quality, an assessment supported by evaluations, end of project surveys and field visit reports from DFID’s interventions. For example, after Tropical Storm Mahasen in Barguna district, DFID met programme beneficiaries who had generated income of BDT 30,000 from the provision of BDT 500 of seeds, demonstrating the high quality of the seeds used. Food vouchers provided to Rohingya refugees in registered camps were very popular as reported by the WFP’s post distribution monitoring report, as they provided flexibility and choice, stimulated local markets and improved the position of senior women as they were primary card holders; all good evidence of a high quality intervention.

VfM performance compared to the original VfM proposition in the business case

The business case stated that cost, speed and quality of response would be the keys to maximising the value for money of the response .This section considers the economy, efficiency and effectiveness of the programme:

Economy: DFID ensured that the UN and the NARRI consortium’s administrative costs were kept to a minimum by negotiating to keep costs in line with those agreed in advance by DFID centrally. Management and administrative costs have all been within DFID guideline rates. The NARRI consortium centralised its procurement process to leverage bulk discounts where possible as did the WFP for its feeding operation for Rohingya refugees living in registered camps. The WFP undertook assessments of local markets and this enabled the organisation to develop an assistance package that was built on a rigorous appraisal of prevailing costs. The rate that the programme paid in cash for work followed the Government’s agreed rate and was applied uniformly to both men and women.

Efficiency: Emergency responses were built on rigorous needs assessments, thus targeting support to have the greatest impact on those in the most need. Partners successfully worked together to respond to disasters. They provided support that did not overlap with each other, they coordinated central administration and planning, and they learned from their shared experiences. DFID’s interventions were planned in coordination with other donors through the Joint Response Plan process, improving efficiency. This process helped to avoid overlap between interventions, and ensured that responses were based on robust appraisals of the inputs. The DFID funded JNA process also helped to improve the efficiency of donor interventions. Also, UN’s joint response to monsoon flooding in the northwest delivered integrated packages of shelter, nutrition, food security, sanitation and livelihood support. These packages addressed all priority needs with a single intervention, maximising the sustainable impact of the work. As discussed under section C output 1 above, a key lesson learnt from this programme was that DFID should focus on delivering a speedy response to disasters in all cases. DFID has worked to improve the predictability and timeliness of its responses to disasters as a result. A costing model developed by MAF demonstrated that, for three Dhaka-based staff making a field visit of four working days to a project site accessed through Barisal the MAF Southern Shuttle service was 35%, 25% and 68% more cost-effective than making the same journey by road, boat or helicopter respectively. These cost savings meant that a wide range of organisations could more effectively contribute support to disaster-hit regions.

Effectiveness: The programme has helped 862,237 people with shelter, food, nutrition, water, hygiene and sanitation or early livelihoods recovery support. There is evidence from a DFID funded report[16] that cash transfers are more efficient than other methods of delivering humanitarian aid. Across the 22 interventions supported by this programme, cash transfers were favoured for most of the emergency relief along with some in kind assistance such as nutrition and WASH. For the support to the Rohingya refugees, vouchers were used to provide support. Nearly £2.7m from this programme has been spent on preparedness measures while a majority was spent on humanitarian response as envisioned in the Business case. This investment in preparedness helped improve the effectiveness of the remaining funds. Project implementation committees were set up to involve the community in these works, which continued beyond the life of the programmes, providing a link between communities and local government. For example, in the Joint UN Flood Response programme in North West Bangladesh these committees acted as community leaders to deal with different social challenges. These challenges included repairing and maintaining earthworks after floods and establishing links with local government institutes for various services such as securing relief during disasters. The communities had access to training and information from the local government during the project and once the project was over, they had access to support from this source. Additionally, a MAF-commissioned report demonstrated that there were clear value for money benefits organisations could realise by using its charter and shuttle service.
[16] http://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/9828.pdf

Assessment of whether the programme represented value for money

While there were some challenges for DFID in providing a speedy response, the cost and quality of interventions was good and overall the evidence above suggests that the programme delivered fair to good value for money.

Quality of financial management during the programme

The financial management of the programme has been robust. The programme team were in close contact with each partner to ensure that forecasts were realistic and that spend vs forecast variance was within acceptable limits. Budget adjustments were only approved by DFID where they were based on robust justifications. The DFID programme team ensured that all reports including audit reports were received in a timely fashion. Reports from two components will be received after this document is completed (see page one). When projects had cost extensions (five cases in this programme at component level), these were validated with evidence of need before being approved by DFID. Twelve time extensions were approved at component level to ensure delivery could still be completed despite periods of political unrest.

Audit reports from NGO partners have not identified any major issues. The WFP does not conduct annual audits; rather they complete country level audits. The last of these was completed in 2013 and it was marked satisfactory. The WFP provided annual Standard Project Reports that gave progress updates on activities and financial statements; these did not identify any major areas for concern.

Date of last narrative financial report	See page one for details of reports still pending
Date of last audited annual statement	See page one for details of reports still pending

E: RISK

Quality of risk management over the life of the programme

The following risks were identified in the business case and monitored during the lifetime of the programme by the DFID team.

a. A lack of political support and a weak government-led response to disasters, which could include a failure to acknowledge disasters or the scale of need: This risk was managed through DFID’s support to a system-wide review of the humanitarian sector. This was coordinated by the Humanitarian Adviser posted in the UNRC's office.

b. FD6[17] approval from the Government of Bangladesh to be received within agreed timeframe: In order to manage this risk, the Local Consultative Group for Disasters and Emergency Response (LCG DER) convened a working group chaired by OXFAM to support the approval process. DFID provided a letter of support to enable NGOs to apply for funding, where requested. In particularly contentious areas like the Chittagong Hill tracts, DFID supported partners by providing letters of support, and with advocacy with the Ministry of Disaster Management and Relief and the Non-Government Organisations Affairs Bureau, which is the body that provides the approvals. DFID also supported partners when withdrawing and focusing on other areas was necessary.
[17] FD6 approval is required by the Government of Bangladesh for any international funds to be spent by NGOs in-country.

c. Inability to support Rohingya refugees in a timely manner: DFID mitigated this risk by working closely with other UK government departments on the issue. DFID was part of the Inter-agency Coordination Group for Cox’s Bazaar, which coordinated assistance to Rohingya refugees. A joint visit to the Rohingya refugee camps in Cox’s Bazaar by High Commissioners of 3 missions (UK, Australia and Canada) was also held early this year to discuss these issues.

d. Fiduciary Risk: DFID informed all partners of its zero tolerance approach to corruption and fraud. DFID checked that potential delivery partners had the necessary systems to combat corruption and fraud. The WFP, CARE, Oxfam and Plan were DFID’s regular partners. DFID conducted a Due Diligence Assessment of the WFP in 2014 and also drew on central DFID assessments of International NGOs. Where fraud was identified and DFID had been informed, prompt actions were taken in line with DFID’s guidance. Money was recovered and distributed back to beneficiaries where possible. The DFID Fraud Unit supported this process. During the programme, two cases of fraud were reported and investigated. In one case stolen funds were recovered and redistributed to beneficiaries. In the second case it was not possible to recover funds as the programme beneficiaries from whom funds were stolen did not want to report the issue to the police. DFID therefore wrote off the stolen money.

Cash transfer programmes include risks of theft, fraud, coercion and bribery. A range of mitigation measures were used in this programme. For direct cash transfers, beneficiary cards were used, which held beneficiary details. Cash transfers were made in the presence of local administration officials, including security. There is a risk that the cash might be stolen or beneficiaries coerced to part with the money. This risk is difficult to manage by partners as it occurs after cash has been distributed. However, beneficiaries were encouraged to complain to the local administration if it does occur, and partners provided them with evidence of payment to make complaints easier to investigate. Mobile transfers are more secure as there are strict checks required to open a mobile bank account or to approve a sim card. The payment system is automated and only make payment to designated bank accounts or mobile numbers. Partners checked to ensure that beneficiaries had received payment.

e. Delivery risk due to political unrest: DFID spoke regularly to delivery staff in order to understand the potential impact of political unrest, to revise work plans, and to extend project timelines if necessary, to support delivery during such periods. Hartals (strikes) caused disruption at times, although with limited overall impact.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

In 2015, the programme was extended by £5 million through an addendum to the business case until March 2017. This provided bridge funding and ensured relief could continue to be provided while a new humanitarian programme was being designed. The new DFID humanitarian business case was approved by Ministers in July 2016. In late 2016, a time extension was sought for three months to ensure a smooth transition to the new programme. As noted previously, 12 of the 22 interventions in the programme required extensions.

Performance of partnerships

DFID worked with a range of International NGOs and UN partners to deliver the programme, establishing strong working relationships. Almost all of these partners worked with further downstream partners to deliver the programme. Their ability to manage these partners was evaluated as part of the proposal appraisal process. DFID support for the IOM was critical as it has helped bring together a range of actors with an interest in Rohingya refugee issues. The Joint UN Flood response in 2015 relating to floods in northwest Bangladesh was the first time that the United Nations Development Group’s (UNDG’s) Standard Administrative Agreement was used in Bangladesh. Three UN agencies (UNICEF, WFP and UNDP) came together and worked on the response jointly using this mechanism. This facilitated a coordinated response and the mechanism will be applied in new DFID programming.

Asset disposal and value obtained by DFID

Assets worth £1,000 or more were disposed of in line with DFID guidance and with the approval of DFID. Assets were mostly donated to the local implementing partners or used to deliver other humanitarian activities (for example laptops, cameras and office furniture were re-used in this way). The Mission Aviation Fellowship and the UNDP-managed support to the UNRC office held assets worth more than £1,000. DFID approved the use of these assets by these organisations for delivery of the new humanitarian programme.

G: CONDITIONALITY

Partnership principles assessment: Not applicable as this programme did not work directly with any Government of Bangladesh departments, only with NGOs and multilateral organisations.

H: MONITORING & EVALUATION

Evidence and evaluation

One of the project’s key aims was to develop the evidence base and provide better analysis for effective disaster management responses in Bangladesh. The project supported research under the WFP-led project on adaptive early recover to waterlogging. This research was used during project implementation and also to inform the new humanitarian programme. The Secondary Data Reviews and the Capacity Atlas funded under output two also helped strengthen the evidence base.

The Mission Aviation Fellowship conducted a value for money and environmental impact evaluation of its service. In 2015, The WFP conducted a Strategic Review of their work in Cox’s Bazaar. The IOM is planning an independent evaluation of their humanitarian response programme in Cox’s Bazaar, including work funded by DFID. This will be complete in July 2017. In response to an annual review recommendation, a whole-of-programme independent review was commissioned to generate lessons learned from the programme. These were used to inform the design of DFID’s new humanitarian programme. No further evaluations are planned for this programme.

Monitoring progress throughout the programme

DFID monitored the programme through desk based reviews of progress reports, meetings with partners, field visits and discussions with beneficiaries. Quarterly meetings were held with Mission Aviation Fellowship to discuss progress, while the WFP held quarterly Project Advisory Committee meetings to provide updates on their progress. For other short interventions and responses, progress meetings with partners were held during the interventions, and an end of project meeting was mandatory. DFID also attended lessons learning workshops, such as after providing support to the southeast flood response, Tropical Storm Mahasen response and others. Back to the office reports from field visits were drawn upon to inform this report. All 22 projects were visited at least once (or more depending on their duration) during implementation.

Partners such as the WFP and the NARRI consortium established complaint response and feedback mechanisms. For example, a dedicated mobile phone number was printed on beneficiary registration cards for this purpose. After this programme’s response to Tropical Storm Mahasen, evaluation work concluded that this method was more effective than one-off post-distribution monitoring exercises. Beneficiary feedback has been positive with both women and men being consulted during field visits. There have been no complaints about the programme; beneficiaries were aware of their entitlements, the selection criteria and of complaints mechanisms. They were aware that funding was from the UK, and there was good evidence from discussions with beneficiaries that individuals would continue community arrangements like project implementation committees. This provided evidence of commitment, ownership and sustainability of the projects

This review was undertaken in May over a two week period. The review was conducted by a two member team from DFID Bangladesh. The team undertook a field visit to northwest Bangladesh in January 2017 and to Cox’s Bazaar in February and April 2017.