Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	August 2016

Title: Increasing Access to Reproductive Health and Commodities in Ethiopia
Programme Code: 202980	Start Date: November 2011	End Date: June 2016

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score	A+	A+	A+	A	A
Risk Rating					Moderate

Financial Position

Original Programme Value	£18 million
Extensions/ amendments	The programme has been extended by £449,423.
Log-frame revisions (with dates)
Total programme spend	£18,449,423

Acronyms
AIDS	Acquired Immune Deficiency Syndrome
AFIDEP	African Institute for Development Policy
APHRC	African Population Health Research Center
BCIS	Behavioural Change Impact Survey
BCC	Behavioural Change Communication
CORHA	Consortium of Reproductive Health Agencies
CPR	Contraceptive Prevalence Rate
CYP	Couple Years Protection
DALY	Disability-Adjusted Life Year
DFID	Department For International Development
DHS	Demographic Health Survey
DRS	Developing Regional States
EKN	Embassy of the Kingdom of Netherlands
EOC	Emergency Oral Contraceptive
FHAPCO	Federal HIV/AIDS Prevention Control Office
FMHACA	Food, Medicine and Health Care Administration and Control Authority
FMOH	Federal Ministry of Health
FP	Family Planning
FSW	Female Sex Workers
GEA	Gender Equality Act
GOE	Government of Ethiopia
GPS	Global Positioning System
HEI	Higher Education Initiative
HIV	Human Immunodeficiency Virus
IEC	Information Education Communication
IUD	Intrauterine Device
LARC	Long Acting Reversible Contraception
MA	Medical Abortion
MDG	Millennium Development Goals
MVA	Manual Vacuum Aspiration
NGO	Non-Governmental Organisation
NTO	Non-Traditional Outlet
OC	Oral Contraceptive
ORS	Oral Rehydration Solution
PCR	Project Completion Review
PO	Purchase Order
RH	Reproductive Health
RIF	Reproductive Health Innovative Fund
RSM	Rural Social Marketing
SAP	Systems, Applications & Products
SRH	Sexual and Reproductive Health
TWG	Technical Working Group
UNFPA	United Nations Populations Fund
USAID	United States Agency for International Development
USG	United States Government
VFM	Value For Money

Follow up actions required following closure

Since 2011, the Increasing Access to Reproductive Health and Commodities in Ethiopia programme has been providing funding to DKT Ethiopia, an International Non-Governmental Organisation (INGO), to provide subsidised and socially marketed reproductive health (RH) commodities. It is estimated that the programme has achieved significant results in averting:
- 1.8 million unintended pregnancies
- More than 5000 maternal deaths
- More than 34,000 child deaths
- Between 35,000 and 100,000 HIV infections

Follow up actions from the project closure includes:
The lessons learned from the programme will be shared with internal and external partners. They will be used to feed into DFID’s new family planning programme which is currently under design.

Through DFID funding, DKT was able to acquire mobile team equipment, global positioning system (GPS) units and vehicles for programme implementation. As DKT will continue its development work, transferring the assets to DKT will ensure continuity in the investment DFID has made and more results are gained. These assets will be transferred to DKT following the proper guidance and procedures.
In regards to system-related closures, contracts and purchasing orders (PO) will be closed following outstanding payments. The last audit report for the programme will be submitted in March 2017.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202980/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202980/documents/

Outline of programme and what it has achieved

DFID’s support to DKT Ethiopia (DKT) has reduced the unmet need for family planning and incidence of HIV infection by encouraging the use of contraceptives and procuring the actual commodities.

Demand for contraceptives is built using television and radio adverts as well as billboards tailored to the language and culture of the community. They include advice on how to plan and space births and on using the right contraception for personal circumstances. Counselling and advice is also offered to first time users at local events with youth clubs organised to teach communities about HIV prevention.

In addition, DKT procures commodities, including condoms, oral and injectable contraceptives, intrauterine device (IUDs or coils) and implants. These are then sold at reduced rates in traditional outlets, such as pharmacies, clinics and hospitals, and non-traditional outlets, such as kiosks and small shops. A network of ‘young marketers’ also work with a range of youth and student groups to promote subsidised contraceptives. The breadth of this network ensures contraceptives are available in the most remote and rural parts of the country.

DFID has funded DKT to do this type of social marketing of contraceptives in Ethiopia for more than 15 years, most recently with £18 million over 5 years to implement the “Increasing Access to Reproductive Health (RH) commodities” programme. The programme is co-funded by the Embassy of the Kingdom of Netherlands (EKN), which has committed a further $19 million to DKT to support its new 5-year strategic plan from 2015 to 2020. In August 2015, DFID extended the programme by 12 months while future support to the sector was considered.

The programme has contributed to Ethiopia’s achievement of the Millennium Development Goals (MDGs) target of halting and reversing the HIV epidemic well ahead of time by reducing new HIV infections by 90% and mortality by more than 50% among adults in the last decade. Furthermore, the programme has contributed to Ethiopia’s health MDG targets 4 and 5 of reducing child and maternal mortality by improving the contraceptive prevalence rate (CPR) and reducing fertility.

DKT Ethiopia is the largest importer, distributor, and promoter of family planning, reproductive health, and HIV prevention products for private pharmaceutical, clinical and non-traditional outlets across the country. DKT Ethiopia has been promoting family planning (FP) and HIV and AIDS prevention through social marketing since 1990. It is the only organisation in Ethiopia engaged in the social marketing of a wide range of reproductive health commodities that include male and female condoms, short and long term contraceptives, lubricants and safe abortion services. Furthermore, DKT distributes other health products, such as Oral Rehydration Solution (ORS) and ‘ORS with zinc’, for the management of infant and child diarrhoea.

Results achieved over life of programme:

Every year, on average, the programme has protected 2.3 million at-risk women and their partners from unwanted pregnancy and sexually transmittable infections. As a result, it is estimated to have saved the lives of 5,000 women. DKT has an existing distribution network and supply chain system that involves 13,000+ pharmaceutical and clinical outlets with direct product distribution. DKT also services tens of thousands of non-traditional outlets (NTOs) such as small shops with condom sales indirectly through resellers, including Young Marketers clubs.
The programme has performed strongly in its core mandate by improving access to, and creating demand for, 16 different types of contraceptives and reproductive health (RH) commodities. Over the life of the programme, DKT distributed 11,644,120 million couple years of protection – or CYP – which is a measure that estimates the protection from pregnancy provided by contraceptive methods during a one-year period. This was 113% of the project target. In the past five years, the programme has delivered about 30% of all Ethiopia’s CYPs. DKT’s average annual CYP from 2011 – 2015 was 2.34 million, a considerable increase over DKT’s per-year average in the previous programme (2008 – 2011), during which DKT averaged 1.71 million CYP per year. Injectable contraceptives, condoms, and IUDs each contributed approximately one fourth of CYP throughout the programme period. Commodities procured and distributed with UK and EKN (joint) funding included:

- 310 million male and 110,000 female condoms
- 19 million oral contraceptives
- 11 million injectable contraceptives
- 10 million emergency contraceptives
- 1.6 million misoprostol to prevent postpartum haemorrhage

While the full impact of the programme can only be determined after the next Demographic Health Survey, expected to be completed by 2017[1], it is estimated that these efforts have averted:
[1] The DHS was expected to be conducted by 2015 , it is delayed and results will be shared in early 2017
- 1.8 million unintended pregnancies
- More than 5000 maternal deaths
- More than 34,000 child death
- Between 35,000 and 100,000 HIV infections

As a complementary approach to the supply of RH commodities, the programme has reached different populations through a variety of behaviour change communication (BCC) approaches to increase demand for sexual and reproductive health (SRH) commodities. The cumulative accomplishments over the programme period was marked by increased, nationwide product sales as well as the significant expansion of targeted behaviour change activities for rural women, university students, community members, and female sex workers (FSW).

DKT’s condom sales declined year-to-year over the programme period, likely due to the increased availability of condoms from the United States Agency for International Development (USAID). Many of these condoms leaked into the private sector and disrupted established social marketing channels.

In the final years of the programme, DKT began scaling-down many project activities in order to focus on urban social marketing, which it considers to be the key to long-term sustainability and financial self-sufficiency.

Context Shift: It is important to note the context of this programme has changed over the past 10 years. There are two major shifts - a shift of focus from HIV prevention into a comprehensive reproductive health programme that prioritises family planning; and a growing policy shift from the use of short-acting to long-acting contraceptives. Led by a strong political commitment and support from development partners, the contraceptive use has been rising fast in both urban and rural Ethiopia, relying mainly on injectables, which are now used by three quarters of all women using a modern method. The Government of Ethiopia (GoE) is committed to further increase the contraceptive prevalence rate (CPR) from 42% in 2014 to 55% in 2020, and plans a big shift in the method mix towards implants and, to a lesser extent, sterilisation.

Initially the programme was established to respond to the HIV epidemic by making condoms available at scale. As the country succeeded in controlling HIV infections and the need for family planning / maternal health services grew, the programme added family planning and safe abortion care commodities into its portfolio. Further, the programme served as a stop-gap partner to the GoE by providing logistics and procurement functions. The programme then evolved by bringing a new focus of serving unreached and disadvantage populations through a tailored package of services. However, during the extension period of the programme, from June 2015 – June 2016, DKT was forced to scale back and focus on procurement and distribution of SRH commodities.

This context shift is also reflected in the difference between the original Business Case Outcome and the Outcome reflected in the programme results framework.

In the past, DKT played a significant role procuring and distributing commodities for the GoE, though DKT’s role in this regard has decreased in recent years as the government’s procurement has improved. The Federal Ministry of Health (FMOH) now has the systems to procure and distribute commodities at scale. In the context of a stronger public health system delivering an increasingly complex array of services, a key question is now emerging of the relative contributions to health that should be made by the public, subsidised private, and fully private sectors in Ethiopia.

Recommendations:
As DFID is currently designing a new comprehensive family planning programme, it will assess whether it should continue to support socially marketed condoms and reproductive health commodities, given DKT provides 40-60% of all condoms in Ethiopia. The following are recommendations drawn from the programme’s life.

1. Despite the fact that HIV infections and AIDS-related deaths have declined sharply in the past decade, HIV is still considered as a public health challenge in Ethiopia. Much of this success is attributed to the multi-sectoral response supported by GoE and donors. There is concern that this success is shifting donor priorities and that the gains made could be reversed if continued support is not in place. Although not currently a DFID priority, DFID should strategically assess whether it should continue support for condoms social marketing as the programme provides 40-60% of all condoms in Ethiopia every year.

2. Given the UK’s and Ethiopia’s commitments to FP2020, DFID will make an appropriate contribution to the continuing rise in Contraception Prevalence Rate (CPR). It is not convinced that continued funding of social marketing is the only - or the best - way to do this. The recent scoping study on the future direction of DFID’s funding of reproductive health in the country is very much framed by this changing context and DFID priorities. The recommendations of the scoping study should be taken forward in the design of a new programme while consideration should be made for an interim programme to support DKT’s transition to a fully self-sustained business. EKN is committed to continue funding DKT over the next few years and is keen for DFID support, preferably through a silent partnership arrangement.

3. In the past, the programme gave significant attention to the health behaviours of rural women, university students, and female sex workers through the project’s signature initiatives: rural social marketing (RSM), higher education initiative (HEI), and Wise-Up, respectively. While DKT continues to target these groups and sustain these initiatives, it is doing so at reduced levels in light of funding limitations. In light of DFID’s commitment to gender equality under the Gender Equality Act (GEA) and Strategic Vision for Women and Girls, any new DFID programme should consider a focus on targeting women and girls in hard to reach areas.
4. DKT has used tailored TV, radio and billboard promotions to create demand for reproductive health commodities - targeting adolescents, rural women and women in their post-partum period. The social marketing strategy uses the culture context and the language of the community. In addition to the promotion activities, DKT uses young marketers to increase demand for condoms and contraceptives through peer counselling, entertainment and using community gatherings and festivals. The rural social marketing (RSM), on the other hand, targets rural women during market days. The RSM programme includes provision of advice on how to plan and space births and on using the right contraception for personal circumstances. The lessons from social marketing as demand creation needs to be taken by the upcoming DFID FP business case.
5. With the GoE’s ambitious targets of increasing access to FP for 9.5 million users by 2020, it is imperative to have a better understanding of the current barriers for users. While barriers of access, quality, and cost are generally well-researched, socio-cultural and religious barriers for women and girls utilisation of FP have been less researched. In addition to tapping into the lessons learnt from the DFID-supported Reproductive Innovation Fund, DFID should consider commissioning research to better understand what can be done to address the socio-cultural barriers to family planning and reflect recommendations in the new programme.
6. The Health Sector Transformational Plan (HSTP) aspires for more than 90% of the population to have access to modern family planning methods through community facilities, social marketing and outreach modalities. Although there are grass-root level organisations that work on family planning, there is lack of institutions in Ethiopia which would carry knowledge and experience about FP forward for the next 15-20 years. There are, however, several which perform this function in Kenya, such as African Population Health Research Center (APHRC), Population Council, and African Institute for Development Policy (AFIDEP) etc. DFID could consider supporting the development of such institutions.
7. Over the programme period as well as the programme life, the programmes provided good value for money (VfM), as revealed by the relatively lower commodity procurement unit costs, reasonable cost per couple’s year protection (CYP) and lower cost per disability-adjusted life year (DALY) measures. DKT’s unit cost of commodities was lower than other comparator organisations (USAID and UNFPA) and the cost per CYP has been declining year on year. The reasons behind this – and the risk of alternative sources of contraceptives disrupting supply chains – must be fully understood to ensure future interventions offer similar (and sustainable) vfm.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

This Project Completion Review (PCR) of Increasing Access to Reproductive Health Commodities programme in Ethiopia programme has met its output targets for the year 2015/16 (Score: A). This PCR has also assessed the programme against its outcome targets and concluded the programme has cumulatively met its objectives and targets.

Since June 2015, the programme was on a 12-month extension and was operating at a reduced level of funding; from £3 million per year to £950,000. All outcome results for this programme were assessed and recorded in October 2015. The outcomes were assessed based on four surveys DKT had conducted (baseline and end line). Which were done in 2012/13 (baseline) & 2015 (end line) and were captured in the last annual review. As a result, there was no change to the outcome targets specifically for the extension period that covered June 2015 to June 2016. Similarly, there were very few outputs assessed during the extension period.

Based on the October 2015 review, the programme partially met its outcome targets over the life of the programme. Cumulatively, at the outcome level, the programme has:
- improved consistent use of condoms by FSW from 86% to 94% (target 90%);
- reduced unprotected sex among university students from 78% to 64% (target of 70%); with female consistent condom use being at 34.9% and that of males being 65.1%, and
- increased the use of modern contraceptives among rural women of reproductive age from 32.2% to 44% (no target specified).
- the programme hasn’t fully achieved the goal to improve FSW condom use with non-paying partners (36% against a target of 60%).

Over the course of the programme, several large-scale initiatives were in place, driving grassroots demand for SRH products and desired behaviours.
- In addition to mass mobilisation, the project provided one-to-one counselling to 99,152 rural women on contraception and referred women to health centres/clinics to receive modern contraceptives of their choice. Due to a shortage of funding, the RSM initiative, which started in 835 market towns targeting rural women in hard to reach areas, was scaled-down to 200 towns. It still managed to distribute products worth 92,408 CYP.
- The Wise-Up initiative for condom promotion and HIV-prevention for FSWs targeted 12,525 FSWs for consistent condom use with their paying clients and non-paying partners, through outreach and referral services, coffee ceremonies, drop-in centres and BCC materials. During the reviewed extension period, Wise-Up distributed 333,005 condoms for FSWs and a total of 4,616,933 condoms over the life of the programme.
The Young Marketers (YM) initiative continued to serve as a robust mechanism for engaging youth in behavioural change, peer counselling and selling condoms to non-traditional outlets. Since the start of the programme, the initiative’s 200 active clubs and 519 sales people sold 169,279,400 condoms over the programme period; accounting for over 30% of DKT’s overall condom sales.

Output Score and Description

For this review period (October 2015- June 2016), the programme has been operating at a reduced level of funding to prevent a crisis in commodity supply. DKT is the leading supplier in condoms and reproductive health commodities after the GoE and a major provider of intrauterine devices for the government. A drastic withdrawal from the programme would have created a crisis in commodity supply. For that reason, DFID extended the programme by one year at a reduced level of funding. This reduced level of funding necessitated a focus on highest impact/lowest cost activities through CYP and revenue positive urban social marketing. A supplementary log-frame was developed to capture achievements in the extension period. Major output indicators that require expensive surveys, and are not directly related to the minimal core activities funded this year, were excluded from the supplementary log-frame.

Output 1: Improved supply of Reproductive Health Products in rural and urban Ethiopia

Only 2 indicators were assessed in this review and they both focused on CYPs (the volume of contraceptives). Several indicators were excluded reflecting the % of traditional and non-traditional outlets in rural and urban areas stocking DKT products. The programme exceeded its CYP target by 14% (2,281,454 compared to a target of 2,000,000). A new indicator was added to reflect the number of CYPs generated by Long Acting Reversible Contraception (LARCs). The project has also made impressive progress in the shift from short to long-term contraceptives, exceeding the target (32% compared with a target of 20%).

Output 2: Increased demand for these reproductive health commodities among target groups

The programme’s Output 2 for 2012-2015 was “increasing demand for reproductive health (RH) commodities.” The indicators were based on results of projects targeting rural women, female sex workers and students; RSM, Wise-UP and HEI, respectively. During the project life, we recorded impressive progress towards improving attitudes and demand for contraceptives among rural women as evidenced in the final Behavioural Change Impact Survey (BCIS) that was conducted and captured in the last annual review. The reduction in DFID funding necessitated scaling-back these initiatives. For the output review period October 2015- June 2016, DFID revised the outputs and added a new indicator, “Complete scoping, and start early phases of procurement depending on the Bilateral Aid Review (BAR) 2016-20 outcomes.” This indicator was achieved as the scoping study was conducted in December 2015. There was a delay following the BAR process (a review of DFID funding), which delayed the full roll out of procurement processes.

Output 3: Improved environment and capacity for supply and promotion of Reproductive Health Products and Services

Two out of three indicators in Output 3 were assessed in this PCR. Both these indicators were fully achieved. The programme supported “improved policies supporting private sector distribution of RH products” and “research methodology and results were shared with RH community.” (See Output 3 for details).

Overall for this review period (2015/16), this programme has met expectations in all three outputs to score an A.

The programme has continued to provide very good value for money (VFM). In the year under review, the programme achieved cost per CYP of $3.24, which is considerably lower than the previous year ($4.36/CYP) and half of its cost per CYP from 2011-14 ($6.48). The exclusive investment on CYP has helped to reduce the total cost per CYP this year. To date, the programme’s average cost per CYP was $4.88, which is roughly 25% lower than the international average of $6.35 and less than one-third the United Nations Population Fund (UNFPA) estimated cost per CYP for Africa ($10.65). Furthermore, the programme response to downsizing amid diminished funding resulted in a leaner and more efficient structure enabling the organisation to deliver health impacts in a far more cost-effective way.

Lessons and how these have been shared

1. DKT is operating an effective, complex national social marketing operation across Ethiopia that is delivering tangible reproductive health services to the population in a cost efficient manner. However, there is a tension between equity and efficiency in the delivery of the social marketing programme. As long as the objectives and payment incentives for social marketing companies remain on CYPs, if/when budgets get tight, it is logical for these companies to reduce costly/low CYP return efforts and focus on larger, easier to reach, higher CYP yield population groups. This can reduce the accessibility of the programme to the poorer/harder to reach.

However, as the objective of donor agencies is to provide services to the poorest, focusing only on CYP returns can conflict with that objective. Social marketing, if utilised well, is one strategy where family planning services could be provided to the poorest and hardest to reach.

2. It is clear that the Ethiopian public health system has strengthened over the past 10 years and is now efficiently and effectively providing some of the products/services also being provided by the social marketing programme. However, there is a need to constantly calibrate social marketing programmes with the operating environment. The programme needs to adapt to the shift in the market, mainly driven by increased, free distribution of similar commodities by the GoE and USAID programmes intended for the public services but that find their way into the private sector. Donor agencies along with the GoE should work together on commodity security to monitor the flow of commodities within the public and private sectors.

3. Oral Contraceptives (OC) are preferred by new users, youth and rural women who have limited access to a broad choice. Therefore OC are considered as a point of entry into family planning. There was a 30% increment in OC sales from 2014/15 to 2015/16. This is important to note the Demographic Health Survey (DHS, 2011) data on the 70% discontinuation rate for OC by users.
4. The sales of all products, including contraceptives, continued to be low in Developing Regional States (DRS). Most forms of contraceptives decreased from this year to last year mainly because of improvements in the free supply of these products through the public health system, with some growth in sales of emergency contraception and safe birthing products. This raises a more fundamental question about what strategies are likely to work in relation to family planning in these areas, and if social marketing is the most appropriate approach.
5. In previous years, the programme gave significant attention to the health behaviours of rural women, university students, and female sex workers through DKT’s signature projects: RSM, HEI, and Wise-Up, respectively. While DKT continues to target these groups and sustain these projects, it did so with reduced DFID funding during the extension period. The decision to reduce the DFID funding arose due to the commercial principles/rules that had to be followed in order for the extension to happen. This decision had a significant effect on performance in 2015/16 as DKT focused on highest impact/lowest cost activities.
During field visits, local RSM project staff expressed serious concerns about the downsizing; especially on the reduced ability to target rural women in hard to reach areas as their staff had been cut from 15 teams to 3 teams and could now only visit rural markets every other month in the central region area. “Cuts to RSM, HEI, and Wise-Up have been painful, but necessary, and projects are now refined to their highest impact/lowest cost activities,” said the Country Director. While initial DFID funding significantly contributed to the success of these initiatives, the investments and gains made are at risk of being eroded due to lack of ongoing funds. The new business case by DFID should recommend putting more resources into these initiatives in the future.

Dissemination: Over the life of the programme, over 15 surveys and research studies have been conducted and disseminated to measure success of the demand creation and distribution activities. This has included behavioural change impact surveys (BCIS) on various target groups including FSWs and students, pre-testing of communication materials and market assessments for new products. DKT has used the research and surveys internally to improve programme learning and product marketing. Furthermore, the research has been strategically disseminated through the various FMoH taskforces and technical working groups related to family planning, local and international family planning conferences, contraceptive forecasting, abortion care, and HIV prevention where DKT is a key stakeholder. Furthermore, DKT has presented and shared the programme’s research at various regional and international conferences on family planning and reproductive health. While commending DKT’s overall role in the reduction of HIV in the country, the Deputy Director of Federal HIV/AIDS Prevention Control Office (FHAPCO) referred to DKT as “the key player in the Condom Technical Working Group (TWG)…” and appreciated the technical expertise, knowledge and research shared by DKT in the development of the national condom strategy.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved Supply of Reproductive Health Products in Rural and Urban Ethiopia
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Couple years protection provided by reproductive / health products sold by DKT[2]	11,362,666	11,644,120
1.1.1 % of CYPs generated from Long Acting Reversible Contraception (LARCs)	20%	32%
[2] Data covers the period of July -June for each year.

Key Points

Score: A+ This output has exceeded its targets. For the extension period, DFID decided to finance this component to avoid any commodity pipeline rupture. The log frame for the extension period captures only 2 indicators under Output 1 (1.1 and 1.1.1).

This core output measures the quantity of commodities distributed, the coverage and reach of products in the country. Data is gathered based on project documents, DKT sales figures and Market Penetration Surveys.

DKT remains the second largest distributor of family planning and reproductive health products in Ethiopia after the GoE and the largest provider of these products to the private sector. It regularly accounts for approximately one-third of CYP in the country. DKT delivers a full basket of RH commodities to nearly 11,000+ pharmaceutical and clinical outlets on a routine basis.

DKT’s re-seller partners, including youth and anti-AIDS clubs in the young marketer’s initiative and large-scale re-stockists, reach tens of thousands of non-traditional outlets, including supermarkets, hotels, and kiosks, with condoms.

Cumulatively, the programme has achieved 102.5% of the overall programme target for CYPs (11,644,120 compared to a target of 11,362,666). During the extension period, the programme exceeded its target by 10% (2,281,454 compared to a target of 2,100,000). This was a 3.5% increase from last year when the organisation distributed 2,025,981 CYP.

In the review period, DKT introduced a new product, fasile-one Emergency Oral Contraceptive (EOC) to broaden the options for emergency contraceptives. Fasile-one has the same formulation as DKT’s existing EOC (Postpill) but is packaged as a single tablet, which consumers may find preferable. A total of 53,066 packets of fasile-one were distributed during the extension period.

In 2015/16, the programme achieved a revenue return of 28% - which was the highest ever for the programme. This result was based on a decision to review, and slightly increase the prices charged for certain products. In terms of year-over-year sales, DKT experienced considerable growth in EC (+40%) and injectable (+32%) as well as DKT’s abortion-related products (Manual Vacuum Aspiration (MVA) Kits, +237%; Medical Abortion (MA), +41%).

Sales Performance by Year and Product Category July 2011 – June 2016
Product Category	July 2011 – June 2012	July 2012 – June 2013	July 2013 – June 2014	June 2014 – July 2015	July 2015 – June 2016
Male Condoms	70,394,912	66,166,470	66,718,457	53,299,572	54,132,320
Female Condoms	-	4,199	31,619	28,769	46,833
Oral Contraceptives	3,449,386	3,458,752	4,130,354	3,471,354	4,542,666
Emergency Contraceptives	1,299,844	2,568,288	1,769,496	2,483,172	2,590,322
Injectable Contraceptives	106,717	1,631,171	2,722,430	3,600,407	3,636,559
IUDs *	95,076	142,200	130,980	64,400	107,208
Implants	6,600	152,730	122,455	9,267	37,345
MVA Kits	13,556	6,438	3,162	10,667	4,845
Extra Cannula for MVA	127,692	14,028	4,987	19,987	9,723
Medical Abortion Drug	342,596	178,310	232,515	327,799	314,584
Misoprostol (including clean / birth kit)	12,709	295,092	515,052	708,796	158,389
Smooth Move Lubricant Gel	-	8,496	128,910	48,960	114,546
Lemlem ORS	3,224,043	50,970	2,626,032	2,501,156	2,464,080
* Excludes supplies to the FMoH through an anonymous donor fund
DKT's CYP total is derived using USAID's CYP conversion factors where 1 CYP is equal to: 120 male and female condoms, 15 and 20 cycles of OCP and EC respectively, 4 injectable contraceptives, 0.2174 IUCDs, and 0.3125 implant contraceptives

Summary of responses to issues raised in previous annual reviews (where relevant)

Issues raised during previous annual reviews	Progress
In the context of the changing nature of the Ethiopian HIV and family planning programmes, epidemiology and the pattern of product sales achieved by DKT over the life of the current programme, DFID should review its approach for future programming support of social marketing. This strategy should be informed by the GoE and DFID strategic objectives for SRH services and the specific strategic value add of social marketing for individual products for specific populations.	This recommendation was the basis of the independent scoping study, which considered feasible options for a further five years funding of reproductive health and assessed the state of current provision of reproductive health commodities in Ethiopia and scoped out feasible options that can lead to a responsible exit from social marketing of sexual and reproductive health commodities in Ethiopia. All five options provided for future programming have taken this changing context into consideration.
Future programming needs to consider the relevance of non-traditional outlets as a main route of condoms distribution competing against free condoms.	This is likely to be a key consideration in the design of a new programme- non-traditional outlets being kiosks, market places and hot spots rather than pharmacies and clinics

Recommendations for future programmes
With the GoE’s ambitious targets of increasing access to FP for 9.5 million users by 2020, it is imperative to have a rights-based approach and better understanding of the current barriers for users. DFID’s future support shall provide alternative sources and choices of family planning to users on a rights-based approach. DFID’s 20 years of investment on DKT’s infrastructure and the 11,000 networks should be considered as future resources for its future FP programmes.
The risk level for this output has been changed from low to medium (or minor to moderate) due to a risk of sustainability. DFID needs to monitor how the contraceptive pipeline is managed until the new FP programme is started. This programme being the largest supplier of condoms, DFID might need to consider a stop-gap measure if any stock-out of condoms is anticipated in the next 12 months.
Output Title	Increased demand for these reproductive health commodities among target groups
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.2 BCC in Market Town Project / Number counselled for FP in Market Towns (individual counselling)	22,000	16,595
2.3 Higher Education Institutions BCC / a. Number of events with majority male target group heled in DKT project HEI / b. Number of sessions with female target group in DKT project HEIs	120 / 120	85 / 125
2.4 New process indicator for the development of a follow on programme	Complete scoping, and start early phases of procurement depending on the BAR 2016-20 outcomes	Achieved, scoping work completed and early phase of procurement started by development of business case and consultation of FP partners

The reduction in DFID funding necessitated a scaling-back of these projects and only two out of the three traditional indicators were planned and measured for this Output. Progress against indicators was below milestones for most of this Output, which can be explained by the reduced funding. DKT cut its staff and restructured its regional offices to accommodate the budget reduction as well as to effectively and efficiently implement programmes. The reduction in funding has ultimately limited their capacity to offer services to certain target groups such as rural women and men and higher education students.

Given it was the last year of the programme, DFID revised the Output and added a new indicator, “Complete scoping, and start early phases of procurement depending on the BAR 2016-20 outcomes.” This indicator was achieved as the scoping study was conducted in December 2015, but the procurement process for a new programme is not yet underway. This is because the result of the BAR process has led to an increased investment in family planning, requiring a new programme to be designed.

Key Points

Score: B This output was partially met

- The Scoping Study assessed the state of current provision of reproductive health commodities in Ethiopia and considered feasible options that can lead to a responsible exit from social marketing of SRH commodities in Ethiopia.
- The result of our rural social marketing work has been mixed; the marketing approaches were not directly linked with health extension workers who control health care provision in rural Ethiopia. The rural social marketing programme was not able to fully avail long-term contraceptives that require highly skilled clinician’s interventions.
- DFID E’s overall aim is to ‘contribute to a significant increase in CPR’ while having ‘no negative impact on HIV’, and to achieve these aims in a cost-effective way, ‘having regard to other DFID strategies.’ This can be achieved by working with the largest donors of HIV prevention and FMOH in Ethiopia. United States Government (USG) is championing HIV prevention in universities and among sex workers, which provides space for DFID to focus on family planning services.
Technical options recommended from Scoping Study:

1. Continue to fund DKT, using the leverage of further funding to push DKT to correct the problems identified in the PCR and by the scoping mission. Make clear from the outset that this would be the final funding for a responsible exit from social marketing.
2. Shift social marketing to the government, as has been done with the Reproductive Health Innovation Fund (RIF), an innovative way of reducing barriers and increasing demand for reproductive health through government system. This will make DKT better integrated with government programmes, and build GoE capacity for tendering and managing contracts. As with option 1, above, DFID can make it clear from the outset that the funding will not be renewed, though it will almost certainly come under great pressure as the project comes to an end.
3. Focus on complete reproductive health services this recommendation broadens the scope of DFID’s future engagement from family planning to broader care that includes sexual health, safe abortion and women’s health.
4. Focus on adolescents, DFID can extend this to interventions aimed at changing the attitudes and behaviour of boys and young men, many of whom want to resist the gender norms of masculinity to which they are subjected. Changing these would improve the situation not just of boys but also of girls.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issues raised during previous annual reviews	Progress
DFID should assess the most appropriate and effective strategies and programme modalities to increase the accessibility and uptake of sexual and reproductive health services in remote/poor/underserved parts of Ethiopia. This would include a critical assessment of the role, if any, of social marketing in this strategy.	Through DFID support, DKT has conducted several surveys and research pieces, which measure success of the demand creation and distribution activities, and also assess behavioural change among various target groups in remote, poor and underserved parts of Ethiopia. This research includes: / The Behavioural Change Impact Survey of Female Sex Workers in Ethiopia, July 2015 / The Behavioural Change Impact Survey of Higher Educational Institutions Project, June 2015 / Survey of the knowledge, attitudes, and practices of workers from the Great Ethiopian Renaissance Dam Project and sex workers in nearby Bamza Town with regards to HIV/AIDS and condom use. / While not comprehensive, these surveys provide useful insights to increase the accessibility and uptake of SRH services among the specific target populations.

Recommendations for future programmes

Social marketing has a well-documented impact in targeted promotion of family planning and freeing-up resources for the poor. The new family planning programme should determine the size and role of social marketing in increasing demand to benefit 1,000,000 new users of family planning.
 Possible interim programme

While DFID funding to DKT has ended in June 2016, a new programme will not be in place until April 2017 at the very earliest. Given the success of the programme over the previous funding cycles, DFID should consider funding an interim programme that would enable DKT to continue some of its star initiatives targeting women, girls and youth in rural and geographically hard-to-reach areas. Furthermore, donor funding, albeit reduced, would support DKT’s transition to a fully self-sustained business. EKN is committed to continue funding DKT over the next few years and is keen for DFID support, preferably through a silent partnership arrangement.

Output Title	Improved environment and capacity for the supply and promotion of RH products and services
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	N

Score: A this output has met its targets.

Description: The provision of SRH services in Ethiopia exist in a complex institutional environment involving government and non-state actors. An important aim of this programme is for DKT to interact and, where possible, influence this environment to facilitate improved access to RH products and services for the people of Ethiopia.

Progress against targets: Two out of three indicators in output 3 have been assessed in this PCR.

Indicator(s)	Milestones	Progress
3.2 Improved policies supporting private sector distribution of RH products	Improved	Yes
3.3 Research methodology and results shared with RH community	Quality research conducted and disseminated	Yes

Key Points

Policy Advocacy: DKT continued to engage productively within Ethiopia’s Reproductive, Maternal and Neonatal Health policy environment during the extension period. DKT disseminated the different studies and surveys conducted through the various FMoH taskforces and technical working groups to bring about policy dialogue and shape strategies. DKT along with other non-state actors was actively involved in supporting FMoH to develop the National Contraceptive Forecast, 2015 – 17. Furthermore, it was selected as a member of the core team to develop a FP message guide and standardise FP messaging in Ethiopia. DKT works closely with the FHAPCO, the government organisation mandated to coordinate and lead the multi-sectoral HIV/AIDS response in the country. DKT jointly with the FHAPCO provided joint supportive supervision and technical support to the Consortium of Reproductive Health Agencies (CORHA). In addition, DKT was actively engaged in the design of the National Condom Strategy led by FHAPCO. The Deputy Director of the FHAPCO, Ato Alemu credited DKT with “playing a very crucial role in combatting HIV/AIDS in the country through the introduction of social marketing of condoms.” He also asserted that DKT covers 70% of condom distribution of the private sector. DKT continues to actively participate and influence a wide variety of FMoH technical working groups related to family planning, contraceptive forecasting, abortion care, and HIV prevention.

DKT continued routine activities with the Food, Medicine and Health Care Administration and Control Authority (FMHACA) during the period, including completing 11 purchase orders, 5 applications for product variation, and first-time registration for an alternative condom supplier. DKT also completed registration of new commodities in Ethiopia - this includes the registration of the ENOVA IUD, which will serve as a backup and/or alternative in DKT’s IUD product line, and supervised destruction of unfit products in different parts of the country.

Research: During the extension period, DKT also researched a range of areas. These included:
- Pre-testing communication materials including the Orange-flavoured LemLem Plus Packaging (to compete with Electra, an orange-flavoured competitor ORS that is favoured by many consumers) and Hiwot Trust Billboard designs, both showcasing the new rectangular Hiwot Trust packaging.
- Rapid market assessment of the implant Implanon
- Assessed the feasibility of a hotline for Partner Clinics, health providers and consumers who might be interested in learning about DKT’s products.
- Survey of the knowledge, attitudes, and practices of 367 workers from the Great Ethiopian Renaissance Dam Project and 98 sex workers in nearby Bamza Town with regards to HIV/AIDS and condom use.
- The Behavioural Change Impact Survey of Female Sex Workers in Ethiopia, July 2015 End line Survey
- The Behavioural Change Impact Survey of Higher Educational Institutions Project, June 2015

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations for future programmes

The upcoming FP programme could consider the production of more studies and evidence to reduce contraceptive inequality and reduce unmet needs in Ethiopia. The programme should also engage in policy dialogues that can ensure equitable and right based scale up of contraceptives.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The cost drivers for the programme are expenditures in commodities; advertising, promotional information, education and communication (IEC)/public relation; and training and advocacy. DFID’s funding was exclusively used to procure commodities.

Looking at the spending by expenditure category over the life of the programme, commodity procurement account for - on average - 51% of the total expenditure, followed by advertising, promotional information, education and communication (IEC)/public relation (30%) and training, advocacy and research (8%).

During the current review period, DKT received a sum of $8,596,090 (£6,415,660) from donors, of which DFID contributed $1,345,510.00 (£950,000); EKN contributed about $5,664,307 (£4,227,555.53), and an anonymous donor contributed $1,586,273 (£1,183,910). DKT also generated an additional $4,132,441 (£3,084,230) from sales revenue. With a total expenditure of $11,015,529.90 (£8,221,400), for this review period, 100% of DFID’s contribution had been used for procurement of commodities[3]. The table below summarises the different contribution during the extension period.
[3] June 30, 2016 conversion rate of $1.00 at £0.74635 is used

Donor	June 2015 – June 2016 Contribution
DFID	£950,000.00
EKN	£4,227,555.53
Anonymous donor	£1,183,910.00
DKT Sales revenue	£3,084,230.00
Total	£8,221,400.00

June 2015 to June 2016 Donor contribution and DKT sales revenue

In the life of the programme, DKT has received a total of £52,124,230 from donors, of which DFID has contributed £18,449,423, and EKN contributed £20,459,902. DKT has also generated £13,457,463. The table below summarises the total donor contribution as well as the sales revenue DKT has generated.

Income collected from November 2011- June 2016
Description	Years and amount in GBP
	2011	2012	2013	2014	2015	2016	Total
DFID	7,495,372	1,197,801	3,780,950	3,571,837	4,102,372	615,624	20,763,957
EKN	2,798,794	4,925,888	3,074,649	4,114,029	3,307,502	2,239,041	20,459,902
Other	460,209	619,124.	3,193,916	3,757,151	2,201,391	668,577	10,900,371
DKT Sales revenue	432,591	2,480,804	2,523,744	2,525,954	3,392,300	2,102,069	13,457,464
Total Income during the period	11,186,967	9,223,618	12,573,259	13,968,972	13,003,566	5,625,312	65,581,694

November 2011 to June 2016 donor contribution and DKT sales revenue

VfM performance compared to the original VfM proposition in the business case

Commodity Procurement: DKT versus USAID and UNFPA

When compared with much larger organisations like USAID and UNFPA, DKT’s prices are competitive: unit costs of different RH commodities procured by DKT in 2015/16 was 6 – 14% lower than that of USAID and UNFPA when DKT’s entire product bundle is considered. This is despite the fact that, unlike the other organisations, DKT imports most products in branded and packaged in gross and individual containers, significantly increasing cost. Worth noting the fact in 2014/15 DKT enjoyed a favourable advantage in the costs of 11 items of the 16 reproductive health commodities procured.

Fig. The 2015/16 Unit Cost in USD per selected contraceptive procured by DKT, USAID and UNFPA

Cost Per CYP
The programme continues to achieve a very competitive cost per CYP. In the extension period, the programme achieved cost per CYP of $3.24, which is considerably lower than the previous year ($4.36/CYP) and half of its cost per CYP from 2011-14 ($6.48), evidence of DKT’s concerted drive towards CYP generation and cost-efficiency. Furthermore, it is roughly half of the global average of $6.35 and less than one-third UNFPA’s estimated cost per CYP for Africa ($10.65). The chart below summarizes the project’s annual trend in Cost per CYP.

Fig. Cost per CYP

Efficiency
The programme had to downsize and restructure to reflect the reduced funding for the extension period. DKT went from 350 staff to 260 staff and from 11 regional offices to 8 semi-autonomous areas, forming a leaner and more efficient structure, enabling the organisation to deliver health impacts in a far more cost-effective way. Furthermore, the organisation centralised finance, monitoring and evaluation, certain elements of marketing, administration, human resource and payroll and is in the process of introducing a new initiative to automate sales recordkeeping - E-Sales, which have until now been on a paper-based system. Although the new system will not be operational until January 2017, the process has begun and is expected to enable DKT to manage its sales and distribution operation with unprecedented efficiency.

Cost Per Health Impact

Over the extension period, contraceptives and other RH commodities that DKT distributed have: a) prevented an estimated 472,000 unintended pregnancies and b) averted an estimated 7,000 HIV transmissions. These outcomes in turn have averted an estimated 860,000 disability adjusted life years (DALYs) – of years of life lost to ill health - during the period at a cost of $23.33 (£17.94) per unintended pregnancy and $12.8 (£9.84) per DALY averted. These rates are lower than in the previous reporting periods and considerably below global estimates of $33.00 (£25.38) and $61.00 (£46.91) per unintended pregnancy and DALY averted, respectively[4]. The cost per DALY averted of $12.8 (£9.84) is way below the Gross Domestic Product per capita of Ethiopia, which the World Health Organisation uses as a measure of an overall cost effectiveness threshold for assessment of programmes. This suggests that the DKT RH commodities programme has been delivering very good VfM.
[4] Ibid.

Assessment of whether the programme represented value for money

Over the programme period, the programmes theory of change remained valid and the DKT Social Marketing programme was highly relevant to Ethiopia and the UK’s overall health agenda of reducing maternal and child death in Ethiopia. The programme has continued to provide very good value for money (VfM) as revealed by the relatively lower commodity procurement unit costs, reasonable cost per CYP and lower cost per DALY measures. As highlighted above, DKT’s unit cost of commodities was lower than other comparator organisations (USAID and UNFPA) and the cost per CYP has been declining year on year. The programme was highly cost-effective as revealed by the lower cost per DALY and the programme response to downsizing amid diminished funding resulted in a leaner and more efficient structure enabling the organisation to deliver health impacts in a far more cost-effective way.

Quality of financial management during programme

This is a milestone-based payment contract arrangement. DFID has received an unqualified audit report for the review period. DKT’s quarterly reports provide an accurate picture of financial data for the period under review, including comprehensive expenditure summaries, and a cash flow analysis with opening and closing cash balances. The last external audit report covered the 2015 fiscal year and was completed by March 2016.

Year	Budget	Disbursement	Variance
2011	£6,500,000	£6,500,000	Nil
2012	£2,800,000	£2,800,000	Nil
2013	£3,000,000	£3,000,000	Nil
2014	£2,000,000	£2,000,000	Nil
2015	£3,984,423	£3,984,423	Nil
2016	£665,000.00	£665,000.00	Nil

Date of last narrative financial report	30 August 2016
Date of last audited annual statement	08 March 2016

E: RISK (½ page)

Quality of risk management over the life of the programme

Overview of programme risk: While the programme risk started out as low, it is now medium/ moderate to high/ major due to DKT’s concerns over sustained donor funding. DFID has no immediate plans to fund DKT and potential future funding will be dependent on the design and focus of the new programme. While DKT could potentially be a partner in a new programme, the immediate risk is reduced funding for many activities that DFID funding had been sustaining in the past. Specifically, these were activities focusing on rural women and youth in hard to reach areas of the country. Due to the high cost/low impact nature of these activities, DKT is redirecting its funding to more cost-effective components focusing in urban areas.

Sustainability has remained the main programmatic risk and it is reassuring to note that DKT has managed this risk by transitioning from being a donor dependent NGO to a partially self-sustaining business. The transition to a fully self-sustained business is expected to be realised within 10 years, provided Ethiopia’s progression towards middle income country status continues on its current trajectory.

F: COMMERCIAL CONSIDERATIONS (½ page).

Delivery against planned timeframe
DKT delivered what they had planned; they have exceeded the CYP target set for their extension period. DFID needs to determine if and how it shall continue social marketing of SRH commodities. A Scoping Study that was conducted in 2015 had outlined how DFID’s engagement can include social marketing. Furthermore, DFID is in the process of designing a new programme on family planning, in which DKT may have a role if it chooses to bid. Other options include an interim programme with EKN through a partnership arrangement.

In the years to come, DKT plans to transition from being a donor dependent entity to a self-supporting organisation. This is prompted by the following considerations:
1. Plans by the Government of Ethiopia to achieve the status of a middle income country by 2025;
2. Growing urban population with increased purchasing power will facilitate the growth of private medical and RH suppliers.
3. The public sector’s increasing reliance on its own procurement system that has reduced its dependency on DKT’s commodities and services;
4. DFID’s and other donors’ funding capacity for such programmes may not stay the same during and beyond the next 5 years

The screen shoot below shows the fund flow for the programme.

The deadline for the PCR on DFID’s system is September 30, 2016. All required procedures on closing a programme have been followed.

Performance of partnership (s)

DFID and EKN have been in an effective partnership with DKT over the life of the programme. Programme management remains strong with quarterly and annual reports received on time; regular meetings held; and internal/audit reports provided on schedule. DFID spot checks have also revealed the monitoring and evaluation (M&E) systems are strong and accurate. Government stakeholders have also commended DKT’s partnership, especially in terms of its integral role in the reduction of HIV in the country. DKT has also been recognised as an integral technical partner in key government technical committees and working groups on family planning and reproductive health.

Asset management, disposal and value obtained by DFID

DKT has an up to date asset registry which is audited annually by external auditors. During the implementation phase, DKT had procured mobile team equipment, GPS (Global Positioning System) units and vehicles for programme implementation. DKT had used its revenue generated, DFID’s and EKN’s funds to procure the assets. DFID’s funding enabled DKT to procure five vehicles (three for rural and two for urban programmes), mobile team equipment and GPS units. The values of the commodities during procurement and the current market value is shown below

Description	Total Cost (Br)	Total Cost (GBP)	Current value (GBP)
Mobile Team Equipment	419,296	14,692	1,125.56
GPS Units/13	49,511	1,735	162.07
Vehicles /3 Rural & 2 Urban	4,286,630	150,199	59,411.82
Total		166,625	60,699.45

DKT will continue its development work as it has secured funding from EKN until December 2019. Allowing DKT to use the assets procured with DFID funding will ensure continuity in the investment made and more results are achieved. For that reason, it was approved for the assets to be transferred to DKT with obligations stated under the Smart rule.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Given that this programme does not include direct funding to the Government of Ethiopia DFID’s conditionality policy and partnership principles are not relevant.

H: MONITORING & EVALUATION (½ page)

Monitoring progress throughout the programme

DKT’s M&E activities during the extension period include:
Joint supportive supervision to outlets and project sites to ensure the smooth implementation of all programme activities. The DKT M&E team undertakes supportive supervisions to all the regions on a monthly basis. These supervision visits focus on assessing: the coverage and penetration of products; customer satisfaction and quality of services. The visits have proven to be very effective tools to assist DKT deliverables and support regional offices to increase coverage, quality and penetration of DKT commodities.
- Feedback and technical assistance to Area and Head Office staff on overall programme implementation, data collection, and reporting.
- Periodic analysis of sales and revenue for frequency of sales contacts, outlet penetration and coverage, and volume of product sold versus target and by category.
- Summary and detail sales reports for Area Offices for staff appraisal and monitoring and developing action plans.
- Periodic analysis of sales and BCC activities for: frequency of sales contacts, outlet penetration and coverage, volume of product sold versus target and by category.
- Area Office’s strategic use of performance monitoring data for planning, monitoring and programme review.
- Compilation and analysis of large data sets from DKT's MIS and external sources to propose and form new Area Offices and Sales Territories, which started as a pilot in July 2015 and will be fully operational in 2016.
- Regional and National Review Meetings and presentation of regional performance based on monitoring indicators.
- DKT’s 2015 Annual Report and 2016 first quarter report that were submitted to GoE counterparts.
- Although a formal evaluation was not conducted for the programme, throughout its life, eight key baseline and endline surveys were conducted in addition to several studies. These surveys and studies were used to monitor the progress made in the programme and have been shared with the wider RH community. DKT disseminated these different studies and surveys conducted through the various FMoH taskforces and technical working groups to bring about policy dialogue and shape strategies. DKT along with other non-state actors was actively involved in supporting FMoH to develop the National Contraceptive Forecast, 2015 – 17. Furthermore, it was selected as a member of the core team to develop a FP message guide and standardise FP messaging in Ethiopia.
Some of the key surveys and other research pieces conducted through the life of the programme that have been conducted to measure success of the demand creation and distribution activities include:
  - The Behavioural Change Impact Survey of Female Sex Workers in Ethiopia, (baseline and endline July 2015)
  - The Behavioural Change Impact Survey of Higher Educational Institutions Project, (baseline 2012 2012 and endline June 2015)
  - The Behavioural Change Impact Survey of Rural married women and men in Ethiopia (baseline 2012 and endline June 2015)
  - Measuring Access and Performance survey of market towns and big urban areas (rounds 2 and 3);
  - Measuring Access and Performance survey of condom coverage and penetration in non-traditional outlets in urban areas (rounds 3 and 4);
  - Survey of the knowledge, attitudes, and practices of workers from the Great Ethiopian Renaissance Dam Project and sex workers in nearby Bamza Town with regards to HIV/AIDS and condom use.
Spot check: The DFID programme team conducted a spot check of DKT’s M&E System in June 2016. The team was impressed by the systems application DKT uses (Systems, Applications & Products). This spot check was to validate the quality, accuracy and completeness of DKT’s routine reports. In conducting the spot check, the team verified that the reports sent by DKT for the period were accurate. The review covered what was reported by DKT between January and April, 2016. The team conducted spot checks on the raw and complied data that the report was generated from. This included interviews with the DKT team, physical viewing and verifying the raw data in the M&E department. Currently, DKT uses both manual and electronic (excel and SAP) means to track stock, sales, distribution and finance of commodities in an integrated manner to generate donor-specific reports. The system is tamper proof, with layers of approval and division of roles. The team found a reliable system and a very high level of accuracy in DKT’s reports. The team was able to inspect a daily logged list of distribution of DFID-funded commodities for the review period. The team found no errors and zero discrepancy between what was reported to DFID and what is captured and processed in the DKT system. The manual process (including tax compliance forms) enables them to provide receipts and appropriate documents to customers as sales and stocks are logged on an excel sheet by DKT regional offices for the M&E team to verify. The screen shoot below is from a SAP system, by which DKT logs daily distribution of commodities by outlet.

E-sales are DKT’s initiative to automate sales record keeping. DKT relies on a paper-based system to record transactions and provide receipts to customers, which DKT is in the process of making digital. The new system will eliminate duplicate record keeping and reduce data entry error while speeding analysis and monitoring. It will enable DKT’s Head Office to stream real-time price and product updates to the entire sales force, which will also have ready access to customer sales history. It will also allow DKT to track and monitor individual salesperson performance on a daily, weekly, and monthly basis. This, in turn, will allow DKT to manage its sales and distribution operation with unprecedented efficiency. The net results are expected to decrease costs, increase sales, increase revenue, and a more efficient utilisation of resources. DKT is in the process of importing selected devices and accessories and expects national deployment to begin in June of 2016. Final field trials and beta testing will then follow in selected regions. The e-sales system is expected to be fully operational by January 2017. Every DKT sales person will then be trained and in possession of a device and printer, and all sales transactions will be captured and processed via the sales automation system.

The PCR Process: The core team for this PCR review included: Rabya Nizam, Social Development Advisor, DFID London (10% support); Kassa Mohammad, Health Adviser, Atsednesh Getachew, Programme Officer, Berhanu Lakew, Economist, and Jyoti Tewari, Senior Human Development Advisor in DFID Ethiopia. The review team carried out interviews with all key stakeholders including DKT national, regional and local staff, FHAPCO, EKN, DFID Ethiopia Human Development Team members youth club members (Young Marketers) in Bishoftu, shop and pharmacy owners in Addis Ababa and Bishoftu towns. Field visits included a visit to the Gonde market town (139 km from Addis Ababa), traditional and non-traditional outlets in Addis Ababa and Bishoftu towns and partner clinics in Addis Ababa. A number of key documents were also consulted as part of this review including: the BC, Log frame; previous annual reviews; and, DKT’s quarter and annual progress reports and scoping study of the future direction of DFID’s social marketing support in Ethiopia.
Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process