Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Policy Development Facility Programme – phase II.
Programme Value: 18,500,000		Review Date: September 2017
Programme Code: 203922	Start Date: 01/04/ 2015	End Date: 31/03/2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017/18
Programme Score	A / (Pre-Contracting)	A / (Inception Phase)	A / (First full year of implementation	A / (2nd Year of implementation)
Risk Rating	Moderate	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review

PDF II is a flexible, rapid response facility for funding policy studies, policy consultations and organisational support, primarily through contracts for technical assistance to key federal government ministries, departments, and agencies (MDAs). Organisational support includes but is not limited to, long-term placement of consultants in MDAs.

The UK’s Policy Development Facility (PDF II) has continued to mobilise technical assistance to support President Buhari’s economic policy agenda which has centred on restoring growth, investing in people and developing a competitive economy. It has been another year of ‘responsiveness’ by the programme. Having laid the foundation of support and policy influence in the first year, in the year under review, PDF II has leveraged this base of support and influence for better policy outcomes for Nigeria. The programme has also expanded into new policy areas within the year for example; into infrastructure, keeping up momentum and ensuring previous gains are not lost with any DFID programming gaps. This will be even more critical as Nigeria heads into the pre-election year (2018).

PDF has been responsive to opportunities with Nigeria’s Federal government, but importantly, is also helping to facilitate consultation on policy and national planning that could have significant impact on economic growth and the livelihoods of the poor following the recession which began in 2016. With Nigeria’s economy going into recession in the second quarter of 2016, helping to produce credible evidence and consultation processes has helped to influence some of the more damaging economic policies. Responsiveness of technical assistance to beneficiaries is critical to help shape policy direction and improve the likelihood of good policy implementation.

The UK’s programmatic response to Trade Policy in Nigeria has now been established within PDF. This approach focuses on the ‘building blocks’ for trade policy, aiming to increase the voices of erstwhile under-represented groups in trade policy discussions and widen the trade policy debate away from narrow vested-interests. Partly this is about making policy discussions more evidence based and inclusive. Also, this recognises and tries to address the underlying political incentives that have constrained Nigeria to restrictive trade practices in the past and undermined the use of trade to drive Nigeria’s long-term economic competitiveness. In addition, PDF has stepped in to support the newly established Nigeria Office for Trade Negotiation which shows promising signs of significant change in Nigeria’s engagement on trade policy.

Despite the programme’s political economy analysis (PEA) in 2016 indicating some challenges in policy alignment and a lack of appetite for big reforms, PDF II has been able to idenfity some promising opportunities for reform leveraging on relationships developed with key partners such as the Nigeria Economic Summit Group (NESG) and other beneficiaries including the Office of the Vice President (who has responsibility for the economy and was acting president for a substantial part of the current year). In addition, the programme is working with other DFID programmes (e.g. Partnership to Engage, Reform and Learn; PERL) to support the efficacy and independence of the Office of the Auditor General of the Federation. These partnerships are beginning to show some positive and potentially significant impact.

Agreeing to cap consultant rates/ embedded advisers with a more unified payment system across embedded advisers has provided value for money when carried out in conjunction with other DFID programmes. In addition, bringing in sector specific programme experts to help shape the terms of reference for embedded advisers in their area has provided strong support and technical networks that the embedded adviser can later draw on.

Action on recommendations from 2016 Annual review of PDF
Please see table 1 below for progress against recommendation from the last Annual review.

TABLE 1: Progress on Recommendations from 2016 Annual Review.
Economic Policy Dialogue / Strengthen mechanisms for regular economic policy dialogue with State House and Nigeria’s Economic Management Team. - Achieved – In addition to the Economic Advisory Council which directly supports the Vice President, PDF expanded its support through a newly constituted Economic Advisory Board which supports the Special Adviser to the President on Economic Matters. The Board consists of eminent Nigerian economists, and is beginning to feed into the Nation’s economic policy. For example, on the recommendation of the Board, the Federal Government of Nigeria (FGN) recently set up a Nigeria Office for Trade Negotiations (NOTN). A body bringing experts from across all the relevant ministries, and led by a highly experienced, progressive World Trade Organization (WTO) Trade expert. This move marks an important first step by Nigeria towards a more open and progressive Trade stance / Quickly step-up engagement with DFID embedded adviser network on the substance of economic policy issues. - Achieved – PDF II held economic back stopping sessions (November 2016 & June 2017) with its network of embedded advisers and drew on research done and presented by the Overseas Development Institute (ODI) consultants and the NESG in the June session. This provided strong evidence in a very practical way that EAs could in turn use in their work.
Supporting Champions of Change / Sense-check the balance of its support through the next round of political economy analysis. - Achieved – Through the one-year-on Political Economy Analysis of the cabinet, PDF was able to validate the balance of its support across the priorities of the Nigerian Government. The PEA also highlighted potential areas for additional support due to shifts in the balance of responsibilities within the cabinet (e.g. Honourable Minister of State (HMS), Budget and National Planning’s increased portfolio), and informed PDF II’s response to the HMS’ request for support. / Collaborate with DFID advisers and other DFID programmes to improve the efficiency and effectiveness of the UK’s package of technical support to the office of the Vice President. -Achieved – PDF II plays an active role in supporting DFID’s programming decisions and management of support to the Office of the Vice President. PDF regularly provides information which supports DFID meetings with the OVP, and ensures maximum efficiency in the use of resources. PDF also works with other DFID programmes to deliver the required package of support to beneficiaries. For example, following the Franchising study, PDF engaged with ENABLE to take forward recommendations on the Franchise Bill that was before the national legislature. PDF is also working with DFID’s (Partnership to Engage, Reform and Learn) PERL programme to deliver support to the Office of the Auditor General of the Federation (OAuGF) on its bill currently before the Senate.

Supporting Institutions / PDF should explore ways to strengthen the Efficiency Unit within the Ministry of Finance. - On-going – PDF has continued to support the Efficiency unit with 2 technical assistants. A replacement is under discussion. When looking for a suitable TA to the head of the unit proved challenging, PDF supported the head of unit through a rigorous process to find a TA with appropriate experience and skill to support the unit effectively. / Consider anchoring an embedded adviser within the Office of the Auditor General to coordinate UK support such as National Audit Office (NAO) missions and other PDF support. - Achieved – In January 2017, PDF II began to support the OAuGF with a TA and a Programme Manager to drive the Office’s reform programme. This has worked well and has supported various missions and training delivered by the UK’s NAO. An audit guide was finalised and published and is being rolled out across the organisation. Furthermore, the agency’s Strategic Development Plan (2017 – 2022) was launched on the 21st of September 2017 by President Muhammadu Buhari, ably represented by the honourable Minister for Finance. In addition, the Code of Ethics & Conduct as well as the Quality Control & Assurance Manuals have also been finalised and has been launched.
Building Blocks for Trade Policy / Set a target for increasing Nigeria’s non-oil exports into regional and non-regional markets and work with partners such as Nigeria’s Export Promotion Council, Ministry of Industry, Trade and Investment and Ministry of Foreign Affairs as well as potential exporters to help make this achievable. - Achieved – Recognising that increasing Nigeria’s non-oil exports is a long term aspiration which given the country’s history and stance on Trade issues goes well beyond the scope of PDF, PDF II’s trade policy work stream set an ambitious target of increasing Nigeria’s non-oil exports to an average of 20% of total export by the year 2030 . A work stream strategy was then developed to contribute building block towards achieving this ambitious goal. / Develop a vision, strategy and work plan for building consumer voices in Nigeria that covers the remaining period of the PDF programme and commence a range of interventions. - Achieved – During the inception phase, a strategy was developed with strengthening consumer voices in line with initial thinking and research (Kingsmill & Ugbajah, 2015). Upon testing with DFID’s Chief economist during his visit in February 2017, a fundamental change in the primary target group from Consumer groups to Exporter groups was advised. The team went back to work, and after consultation with the new target group, a revised strategy was submitted and signed off by DFID in April 2017. Since April, the work stream has built relationships with partners such as the NESG, Nigerian Exports Promotion Council (NEPC), and Enabling Business Environment Secretariat (EBES). Two studies (one on exporter experience and the other on export value chains of selected commodities) are near completion as of the time of submission of this report (draft research report on Exporter experience has been submitted for stakeholder review). Stakeholders were well engaged in the design and execution of the studies, which are expected to feed into policy within their various MDAs/organisations. / Strengthen the collaboration between PDF and the Nigeria Economic Summit Group (NESG), Lagos Chamber of Commerce, and develop a new relationship with the British Nigeria Chamber of Commerce in Lagos. - Achieved – An exporter Dialogue was also held in August 2017 to begin the process of galvanising exporter voices to influence national Trade Policy discourse. The event gave opportunity for exporters and Partners (organised private sector and government including the Nigerian-British Chamber of Commerce (NBCC), NESG, NEPC, EBES etc.) to dialogue. Underpinned by the Trade policy team’s deepening relationship with the NESG Trade Policy Commission, this event helped to prepare exporters and enable their participation in forthcoming events such as the NESG’s high level exporter dialogue which is scheduled for Q4 2017. / Build the knowledge developed from the Chatham House study into the new work stream on trade policy influencing. - Achieved – Building on the knowledge developed from the Chatham house study, the PDF II Trade work stream is now engaged with the honorable minister for state (HMS), Federal Ministry of Industry Trade and Investment (FMITI) on supporting an initiative to help small business formalise, and to encourage changes in government guidelines that will enable small businesses to participate in government procurement bidding.
Disseminating Information / Grow the active user-base of PDF research and evidence products. - Achieved – PDF’s Website is fully functional. Steps were also taken to engage with users through the website e.g. PDF II EAs are sent links to new products uploaded on the website and regular reminders on what’s new on the website. This has helped to grow the number of users. / PDF Website Analytics / September 2016 September* 2017 / N/A 13,201 / Twitter Analytics (No. of Followers) / September 2016 September 2017 / 138 372 / *Average number of hits from February to September 2017. / In addition, PDF II held an event in Lagos in May 2017 to disseminate the findings of the Study on Franchising. This event convened stakeholders from the legislative and executive arms of government, private sector, financial sector, potential and existing franchisees and franchisors, etc. Hon. Sylvester Ogbaga, Chairman, House Committee on Commerce who was present committed to supporting the franchise bill and encouraged the public to participate in the public hearing during the legislative process, to ensure that stakeholder views are fed into the bill currently under consideration of the National Assembly (NASS).
Gender and inclusion / Strengthen gender and inclusion appraisals within newly developed interventions. - Achieved – PDF Sought guidance on gender appraisals in Macroeconomics from DFID’s Economic Advisor on Female Economic Empowerment. After review of PDF’s approach to addressing Gender issues, the adviser validated the approach and suggested small changes to the questions on Gender in PDF’s templates. The changes were incorporated, and PDF II as agreed, continues to opportunistically seek to incorporate gender markers in commissioned studies. In line with this, studies commissioned by PDF II that required primary data collection, actively incorporate gender markers e.g. 3 studies by the International Food Policy Research Institute (IFPRI) for the Federal Ministry of Agriculture and Rural Development (FMARD), Study on improving livelihoods of fishing communities, etc.

Summary of recommendations for the next year

Policy Recommendations:
1. Carry out the political economy analysis (PEA) of the current cabinet to influence/shape future programme direction.
2. Consider strategic and focused areas of support towards the coordination of the Economic Recovery Growth Plan (ERGP) implementation. This should be put into action in advance of potential campaign distractions linked to Nigeria’s 2019 elections.
3. Proactively identify opportunities to keep momentum going on potential reforms / policies e.g. the franchising bill and the audit bill.
4. Strengthened MDA coordination on thematic issues:
  1. More proactive linking up of MDAs (such as the NEPC, PEBEC, EBES and NIPC) in the use of research products to support the policy formulation process.
  2. Support cohesion of the OAuGF and the Public Accounts Committees towards final passage of the audit bill and improved ways of working.

Programme Management Recommendations:
1. Prioritise package of support based on the outcome of the PEA towards MDAs with the most potential of achieving high value successes.
2. Strengthen Monitoring and Evaluation around conducted studies/research for anticipated impact including progress monitoring around MDA service delivery.
3. Strengthen risk management within the programme with actions taken towards risk mitigation documented and reported to DFID on a quarterly basis.
4. Recruit additional resources to manage the increased stretch and workload of the programme
5. Revise the log frame to better shape the programme to capture “projects” more strategically and more realistically.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5178112.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203922/documents

Outline of the programme.

The Policy Development Facility Phase II (PDF II) is the successor to DFID Nigeria’s Policy Development Facility (PDF) programme, which succeeded the Policy and Knowledge Programme (PAK). PDF II started April 1, 2015, and is set to end 31 March 2020 and is comparable in most respects to PDF but has a more robust approach to knowledge management designed during the Inception Phase.

PDF II’s objective is to provide targeted assistance over a 5 year period to help Nigeria’s ‘champions of change’ to implement economic and social policies that lead to poverty reduction, enabling HMG support reform through:
- Backing key economic and public sector reformers in Nigeria with technical support
- Conducting research and studies that can be used to influence and shape Nigeria’s economic reform agenda.
- Initiating explorative studies for potential complimentary DFID programming.

The Impact of PDF phase 2 is that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform.

The impact and outcome of this programme (PDF II) are fully aligned with DFID Nigeria’s business plan. It will help leverage better use of Nigeria’s resources for its national development, unleashing its growth potential. Its approach reflects a principle in the operational plan that better governance and growth are inter-dependent. Much of the support will be aimed at addressing constraints to growth but it will also make a small contribution to the number of poor people whose incomes increase by between 15 and 50% (an operational plan result target). 6,300 incomes have already been increased by PDF 1; and PDF 2 may have helped more jobs to be created through its influence on government schemes such as the Npower project currently run through the Office of the Vice President.

Context:

Despite delays by Nigeria’s Government to initially appoint a Cabinet (there was a six month delay) which meant a slow start to Nigeria’s policy agenda, PDF II has proactively sought opportunities and responded to the needs of the current administration. Since the inception of the programme, PDF II has taken on 165 projects; 104 projects under output 1 and 61 projects under output 2; a significant increase from the executed total of 105 projects under PDF 1 over the 5 year period of its operations from 2010 – 2015.

Nigeria, with the largest economy and population on the continent and a delicate security situation with a history of internal conflict, matters greatly to West Africa, Africa as a whole, and the UK. In addition, the country has a large diaspora with strong links to Britain.

After over 50 years of independence, and 50 years since oil revenues came on stream, and more than a decade of high economic growth, a third of Nigerians still live in extreme poverty, while a small elite is extremely wealthy. “The system [in Nigeria] is deeply rooted in vested interests, a history of intrinsic tension between traditional values and electoral government, systemic violence and conflict often fuelled by ethnic rivalry”[1]. This review and those of its predecessor programme finds that these fundamental features of Nigeria, identified in a DFID paper of 2005, remain valid, and help explain persisting mismanagement of public resources, weak accountability, and a personalised public policy process which in general gives little weight to evidence of what would most effectively achieve wider national objectives. These contribute to weak institutions and government agencies, pervasive corruption, and to poor governance and policy outcomes.
[1] C Heymans, C Pycroft, DFID 2005.

For 18 years, Nigeria has been embedding democratic politics after decades in which military government predominated, with a harmful effect on public ethics and the quality of governance. Up until 2014, economic growth had accelerated (though the benefits were poorly distributed); and some (but by no means all) social indicators had improved (though far below potential)[2].The 2015 elections created increased reform momentum. With the incumbent political party losing the election and allowing a peaceful transition to the opposition, there was hope that this democratic landmark for Nigeria may increase public accountability and help shift policy making to be more reflective of a broader constituency rather than just the will of small dominant elite. To some extent, this has been seen over the last year with President Buhari’s anticorruption agenda. For many Nigerians however, given their expectations, this has not changed fast enough.
[2] http://unstats.un.org/unsd/mdg/Data.aspx

Global economic developments have created tailwinds to President Buhari’s economic development agenda. With the global fall in oil prices since 2014, Nigeria has faced substantial economic challenges due to its overdependence on oil exports. In 2016 the economic situation went from bad to worse with oil prices falling below $40 per barrel from January through to March. Since then, prices have risen to about $50 per barrel as at August 2017. This compared with oil prices that were in excess of $100 per barrel for much of the period from 2012 to 2014, combined with oil production disruptions in the Niger Delta. Nigeria has struggled to keep its economy on track, sliding into recession in the second quarter of 2016. The IMF have forecasted that the Nigerian economy will grow at 0.8 percent in 2017, but warned that threats to recovery remained elevated, and that the economy will not grow enough to reduce unemployment and poverty.

1. The government responded in the first quarter of 2017 with the Economic Recovery and Growth Plan (ERGP) to drive its diversification strategy. Implementing an appropriate and coherent set of policies that will deliver on the goals set out in the ERGP remains critical. However, months after its launch, signs of implementation have been much slower.
2. The Central Bank continues to intervene in the foreign exchange market to support the Naira fuelled by higher crude oil prices and production levels. In addition, restrictions to foreign exchange remain; in particular are the restrictions on foreign exchange on 41 imported class of goods. There are still various tiers to accessing foreign exchange which create hurdles for businesses and rent seeking opportunities for others. A positive development however is the new Investor and Exporter Foreign Exchange window which has helped ease the demand on foreign exchange. Nevertheless, should supply disruptions reoccur, foreign exchange access may be back to levels observed in 2016 which had a detrimental impact on the economy.

Given the importance of Nigeria to achieving the SDGs, and the broadly positive governance agenda of the administration, there is a strong case for DFID continuing to be engaged in influencing Nigeria’s policy process for better development outcomes. Progress is possible, and the potential gains in security, and development are large. However, realism is necessary on the risks and uncertainties involved. There remains an unsettled economic approach which the UK could help positively influence and DFID technical support through PDF could play an important role in doing so. Despite the democratic progress and positive demonstration of accountability in the 2015 election, vested interests continue positioning themselves to attempt to influence government’s public policy agenda. In some cases even the best efforts of PDF will not be able to overcome this influence.

The government’s response on policy development has been varied. Amidst the challenges, PDF II has actively sought and seized opportunities within government’s priorities, which are beginning to show positive outcomes. For example with PDF’s support to the Efficiency Unit, the government has set up an on-line price register where government agencies can compare costs across multiple suppliers to control recurrent expenditure. In addition, PDF’s support to the Office of the Auditor General of the Federation (OAuGF) as part of support to the current government’s anticorruption drive has enabled the Auditor General’s office conduct more periodic audits of government agencies. Work has also begun to support Nigeria’s recently created National Office for Trade Negotiations in conjunction with the Overseas Development Institute.

Programmatically, the major part of this year was spent seeking opportunities that could potentially yield the high value successes as experienced in PDF 1; the adoption of the Nigeria Infrastructure Advisory Facility phase 2 (NIAF2) programme technical assistance to ensure that key reforms in the power sector were continued, and ensuing that past gains are maintained towards more efficient outcomes. Through the programme reviews, there is evidence that the support provided by the programme remains crucial in the policy space and continues to be valued by beneficiaries.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The Outcome that PDF II seeks is that Nigeria’s ‘champions of change’ use increased capacity and evidence to enable them to pursue vital economic and social reform. Logframe indicators for this outcome are:

Outcome Indicators:
1. Indicator 1: 7 instances when beneficiaries can demonstrate that PDF II support directly influenced any of the 5 stages of policy formulation[3].
  [3] Policy Formulation is covered by the following 5 areas: a. framing debates and getting issues on to the political agenda b. encouraging commitments from the public sector and other policy stakeholders c. securing procedural change at domestic or international level d. affecting policy content e. influencing behaviour change in policy execution/regulatory enforcement
2. Indicator 2: A rating of a sample of instances when PDF II support contributed to implementation of vital social and economic reforms.

  1. Indicator 1: 7 Case Studies:

PDF II conducted case studies aimed at understanding the extent to which relevant and high quality PDF II organisational support (Output 1) and policy research, explorative studies and consultation products (Output 2) delivered to beneficiaries stimulate Nigeria’s ‘champions of change’ to pursue vital economic and social reform. The findings are presented in summary below, and inform the overall rating of instances (as required by outcome indicator 2 in (ii above) where PDF II support contributed to implementation of vital social and economic reforms. The cases below show how the programme’s support has influenced the policy process in a way that could plausibly feed-through to poverty reduction (the programme’s overall intended impact).

    1. Support to Nigeria Sovereign Investment Authority (NSIA): Following the establishment of the NSIA in 2011 and the inauguration of its Board in October 2012, with PDF’s support, DFID has continued to provide support under PDF II for a communications adviser. This is in response to the negative press the NSIA suffered as a result of opposition from politicians who claimed that the NSIA’s set up was a political arrangement of the Goodluck Jonathan government with no legal backing. In August 2015 shortly after the President Muhammadu Buhari led APC government took office on a mantra of fighting corruption, NSIA was accused of not being able to account for $700m out of its $1.5bn seed capital, thereby smearing the credibility of the NSIA as an institution. NSIA responded in a constructive and strategic manner by publicizing the NSIA business plan as well as directly engaging media houses and key stakeholders. With PDF II Embedded Adviser’s (EA) support, about 35 stakeholders were identified and profiled, from the Presidency to the legislature. In addition, at the peak of this challenge, PDF II supported the EA by organising sensitization meetings with sister DFID programme State Partnership for Accountability, Responsiveness and Capability (SPARC) which was well acquainted with the Nigeria Governors’ Forum. As a result of these engagements which provided better understanding, famous opponents became the NSIA’s biggest advocates, and the President approved an additional capital contribution of $250 million.

    1. Support to Job Creation Unit (JCU), Office of the Vice President (OVP): Due to high unemployment rates across the country, at the start of the Buhari administration, job creation was quickly prioritised. Following a request from the OVP, PDF II has supported the JCU with an embedded Adviser since November 2015. In response to additional request from the JCU, PDF II also supported development of a Strategic Framework and Implementation Plan for Job Creation and Youth Employment in Nigeria which currently underpins all the work of the JCU and other MDAs on job creation. Now in the implementation phase, the key broad job creation strands: Aso Villa Demo Day, Npower, Innovation Hubs and Skills acquisition are starting to address unemployment.
A pivotal programme - The Npower Programme - speaks directly to the administration’s commitment to job creation with a clear promise from government to create 500,000 jobs for youth between the ages of 18 and 35. It is a two year programme that aims to provide a consistent series of empowerment/skills competency programmes for graduates and non-graduates. The Npower portal www.npower.ng was launched June 12, 2016 and was closed after 10 weeks with about 1 million applications out of which 350,000 were valid graduate applicants. The Npower graduate programme is broadly divided into three categories namely NAgric, NTeach and NHealth within which the graduates selected from all the 36 states across of the Federation were trained and deployed in November 2016 to various Primary Places of Assignment (PPA). Through the 2016 round, 200,000 public and private sector positions were filled, where the government provided stipends to enable participants transition into the private sector at the end of the programme. Some beneficiaries having become entrepreneurs themselves have opted-out of the scheme early to pursue the businesses they have set up with stipends received from the Npower programme hence creating more jobs (see Annex 2 for some testimonials collected from the #MuchMore campaign of the Npower programme). The end goal is to Learn, Work and Entrepreneurship to enable the beneficiaries live a sustainable life after the end of the programme. Unlike with the YouWin business plan competition under PDF 1, where there was significant independent monitoring and evaluation funded by DFID, we do not have the same structures in place to monitor the programme’s long-term impact. Npower gave birth to the #MuchMore which is being used to illustrate and tell success story from the various Npower beneficiaries. The non-graduate tranche of Npower is expected to kick-off before the end of 2017. PDF II also provided additional support to the second strand; development of Innovation Hubs. The third strand; Skills Acquisition is yet to commence.

    1. Support to the Efficiency Unit: The programme’s support to the Efficiency Unit within the Federal Ministry of Finance included funding the Head of Unit since June 2016. The efficiency unit is taking the lead on cost cutting and generating savings from various activities of government. Cost cutting is being achieved from a review of work processes and practices as well as streamlining of the subsisting procurement process. As a large consumer, by being more efficient in procurement, government should deliver significant savings. The funds released from the cost cutting measures and savings generated would then be available to finance capital projects. Soon after set up, a number of quick wins were achieved. Five top items identified were: travel, welfare, training, maintenance and stationaries/computer consumables. The overarching strategy used was to stick to administrative processes, which did not require going through the National Assembly. For this, the Head of Civil Service and Secretary to the Federal Government of Nigeria (SGF) were engaged, and with evidence provided by the Efficiency Unit, recommendations (circulars to the civil service on the five items mentioned above amending subsisting practices), were quickly issued. Subsequently, circulars on travel, honorarium/sitting allowance, meals and refreshments have been issued.

A key challenge encountered has been resistance to change from some civil servants. Despite the high level of support from the Minister of Finance and Head of Service, and other key drivers of the change process has been slower than hoped. Budgetary constraints also proved challenging as finding competent staff for the unit and providing basic office resources require funds. To assist with the staff constraints, DFID through PDF II also provided a Technical Assistant to support the Head of the Efficiency Unit. Early indication show that significant savings have been made, but actual figures are still expected from the Office of the Accountant General for the Federation. The government now plans to make the Efficiency Unit a department within government to institutionalise the ongoing reforms. The mandate of the unit has grown much more than initially envisaged, partly due to the savings achieved and the strong political will to make the efficiency unit into an MDA. In July 2017, the head of the unit was appointed as the new Director-General to the Debt Management Office (DMO) and has since vacated this position. The ministry of finance is seeking a replacement for this role, along considering the unit becoming part of the budget office.

    1. Support to Ministry of Agriculture: In response to a request by the Honourable Minister for Agriculture and in recognition of the need to diversify the Nigerian economy, PDF II provided support for an Embedded Adviser from January 2016 till date. The first year of the support focused on developing the Agriculture Promotion Policy (APP) also known as the Green Alternative (GA). The design, development and adoption of the Green Alternatives at the Federal Executive Council meeting are a major achievement of this project. Since its launch during second quarter 2016, continuous advocacy for its use as a standard in translating agricultural policy in Nigeria to strategic imperatives and actionable items has been sustained. The second year’s support is focusing on partnering with global, regional and local partners who will provide various streams of support to speed up development in the sector. Translating the GA into operations requires technical competence in project management, stakeholder engagement and institutional/policy alignment which are what the PDF II support is providing.

    1. The Central Bank of Nigeria (CBN) Forex Policy Dialogue: Insufficient foreign exchange (FOREX) access, supply and trade had compounded Nigeria’s economic difficulties, triggered by the decline in crude oil prices in 2014. With declining gross domestic product (GDP), rising inflation, declining reserves and scarcity of imported inputs in key sectors, the FOREX problems highlighted deeper issues in Nigeria’s ability to respond to external shocks. The CBN had struggled to sustain confidence in the FOREX market, with inconsistent policies. In June 2016, Central Bank of Nigeria (CBN) announced that it would be abandoning the official Naira-US Dollar peg (of $1/N199) for a market-determined exchange rate and inspire confidence in the economy; the parallel market had valued the naira at between N305 – N380. In order to sustain dialogue between economic managers, private sector, development partners and other stakeholders, and achieve some consensus on key issues, the British High Commission and PDF II, in partnership with the Nigerian Economic Summit Group (NESG) held a dialogue in November 2016 to examine the impact of the CBN’s foreign exchange policy on small and medium size businesses and citizens, with the view to proposing constructive next steps.

Prior to the event, in response to a request from the Office of the Vice President (OVP), PDF II commissioned a study on ‘Poverty and Social Impact Assessment (PSIA) of the Flexible Exchange Rate’. The study was to provide evidence on the impacts of a more flexible naira exchange rate on various segments of society and particularly the poor, which could inform government response to the economic challenges. The study found that, the transition from oil revenue windfalls to shortfalls in Nigeria meant an inevitable end to general subsidy programmes that successive governments had pursued for decades. While all income groups will suffer welfare losses from subsidy withdrawals, with the middle class suffering the most in nominal terms, the poor are likely to suffer larger relative welfare losses. With inflation on a number of primary food produce, the study indicated that second order effects on the poor would dampen the initial impact of the welfare losses. This study therefore presented new empirical evidence on the sizes of the distributional effects of downward adjustment in the exchange rate of the Naira for the different income groups in the country, across rural and urban areas, and across the six geopolitical zones. The findings of this study fed into the CBN FOREX Policy Dialogue, enriched the discussions and also informed the design of social safety interventions by the VPs office.

    1. Anti-Corruption Drive: Support to the office of the Auditor General for the Federation (OAuGF) - In October 2015, the DFID began a two-pronged approach to support the OAuGF through PDF. The first was targeted technical assistance in the form of embedded support, and the second, through periodic technical missions from the UK National Audit Office (NAO). Five mission visits have been carried out by NAO out of six agreed visits for the first two-year period. During the Prime Minister’s Anti-Corruption Summit on 12 May 2016, David Cameron pledged his support to the Buhari Administration in its fight against corruption. Consequently, DFID stepped up its support to the OAuGF. At the start of 2017, DFID increased the level of support by engaging two new advisers; a project manager and a part time technical adviser. This support has already started yielding some positive results, helping the OAuGF improve its operations. – Please refer to details of progress in section c of the annual review.

    1. The Micro Small and Medium Enterprise (MSME) Development – Unlocking the Potential of Franchising in Nigeria: PDF II in collaboration with FEPAR[4] organised a Youth Employment Summit in December 2015. The objective of the summit was to ‘Learn lessons from job creation initiatives within Nigeria and from other countries, and consider implications for the new government’s initiatives.’ The main audience of the summit were the incoming government who were informed of the past government initiatives on job creation – successful and the not so successful ones so that past mistakes were not replicated. The findings of a YouWiN![5] Evaluation conducted by the World Bank was also disseminated at the summit. The summit also fed into the Job Creation initiative – development of a Strategic Framework for Job Creation and Youth Employment, which was on-going at the time by the Office of Vice President (OVP). A highlight of the event was a ‘Market Place of Ideas’ set up for SMEs to show case job creation ideas that could be ‘bought’ and replicated. This innovative approach by PDF II led to the Osun State Government ‘buying’ the idea of a tomato franchise business. Following the event, the Government of Osun requested that PDF II link them with the tomato franchise as they wanted to replicate the idea. PDF brokered the relationship.
      [4] Federal Public Administration Reform Programme funded by UK Aid and closed 1st quarter 2016
      [5] YouWiN! Was business plan competition which was supported by UK Aid along with the Ministry of Finance. Findings from the evaluation revealed that of all FGN job creation initiatives, it was the most successful.

In addition, PDF II supported a study that looked at ‘Tackling Access to Finance: The Potentials of Franchising in Nigeria’. The study aimed at understanding the potential of Franchising in Nigeria and the roles for various actors. Following the completion of the study, in partnership with Franchise Business Development Services (FBDS), a dissemination event was held, which convened stakeholders from the legislative and executive arms of government, private sector, financial sector, potential and existing franchisees and franchisors, etc. Hon. Sylvester Ogbaga, Chairman, House Committee on Commerce who was present committed to supporting the franchise bill. Private sector players (Bank) also committed to developing ‘Franchise friendly” products to support franchise development in Nigeria.

  1. Indicator 2: A rating of the sample of instances:
The overall outcome score takes into consideration a qualitative judgement, similar to PDF I PCR, that despite the concentration of the programme’s partnerships to Federal Government Ministries, Departments and Agencies, the quality of the overall results achieved by the programme remain substantial and justifies continued support, exceeding reasonable expectations of the type of outcomes that a flexible programme of technical assistance and support of this size should deliver.

Overall Outcome score and description

The programme’s impact statement is that the Nigerian Government implements policies that lead to poverty reduction. A recent assessment of the “pro-poorness” of the government’s policies indicate that while the economic policies have not always had a direct link to poverty reduction, the programme continues to support Nigeria in a direction of better management of public resources and policies that should help create a better environment for growth and investment.

The impact level indicator for 2017 in the logframe is:
Qualitative rating of the extent to which government policies in selected priority areas under implementation are conducive to pro-poor outcomes.

  1. A baseline assessment was carried out in 2015 at the start of the administration (and PDF II) which provided a rating for the policy areas that were determined as priority for the new administration. These priorities were assessed and rated based on pro-pooredness and likelihood of successful impact at implementation. Though scores varied between policy areas, on average, the extent to which government policy priorities were expected to deliver pro-poor outcomes was rated 3.225 out of a possible maximum of 5.

The mid-term assessment (half way through programme implementation) was carried out in September 2017 (see Annex 1), and found that with some exceptions, the administration’s overall formulation and delivery of policy on pro-poor growth areas has been less than predicted and hoped for. The most important factor responsible for this observation is that there has been the lack of clear formulation, implementation and coordination of policy on a cross-governmental basis and even within the Executive. Hence on average, the September 2017 is rated 3.019.

PDF II has projects in most government priority areas except where the priority may not fit well within the PDF remit e.g. military and counter-insurgency campaign against Boko Haram, or areas where other DFID programmes may already be working e.g. school feeding programme at the state level. PDF II projects provide outputs to beneficiaries which given the relevant logframe assumption (mainly that, “FGN MDA leadership and civil servants willing and able to feed PDF II products effectively into policy processes”), should translate into outcomes which in turn deliver impact if the logframe outcome-to-impact assumptions hold. The evidence provided shows that PDF products are being used by beneficiaries to influence policy and reform, and are beginning to have impact. Given that 2018 is a pre-election year in which it is expected that members of the executive will become distracted with politicking, the assessment recommended that PDF II should focus on winnable areas, and locking-in wins from Q2-2018 onwards. Also, in areas where only ground work would have been completed, PDF II should concentrate on strategies that will safeguard its work and relationships with partners and advocates.

Based on feedback from beneficiaries, there is little doubt that the support provided by PDF to beneficiaries is appreciated and provides them with capability to deliver impact during their four years in office. The UK Government’s ability to be responsive and provide this type of support helps the UK to stand-out as a donor partner of choice and provides important political capital to the UK’s work in Nigeria. Yet, the recession the Nigerian economy just came out of, challenged with government policy formulation and coordination demonstrate the limits of providing technical assistance to influence policy outcomes. Critically, the work that PDF has done in building an evidence base for policy making has been complemented by UK Government influencing through DFID Advisers along with support from the British High Commission. PDF should continue to operate in ways which leverages the full-suite of UK government influencing to ensure it has the most possible effect. This follows the theory of change set-out in the PDF II business case (see below), which this review assesses to still be valid.

PDF II has established and shaped itself with the appropriate competencies and approach to be on the right trajectory to achieve its intended outcome. Being flexible and responsive to the needs of beneficiaries has however come at a price. While the predecessor programme executed 105 projects during its 5 years, at the 2 year mark, PDF II had 106 projects (not including 33 additional projects working in the infrastructure space, which it took on to ensure continuity of DFID’s support to the Nigerian government when the sector programme (NIAF2) closed). Even without counting the NIAF projects, it is clear that there has been a significant increase in the volume of work, and this has meant that the small team of 4, though able to punch above its weight, has been stretched and may need additional capacity.

It is worth noting that the challenges involved with the transfer of the 33 infrastructure projects at one go meant the programme resources were stretched beyond expected; the PDF II team provided support to ensure the process was managed towards the best possible outcome for all individuals concerned. Despite various challenges including unmet expectations of EAs, changes to contracts and fee rates etc., PDF II was able to provide necessary support through the transition, dealing with sometimes difficult transition issues with sensitivity. PDF also quickly recognised the need for an Infrastructure expert to support the projects and with DFID’s agreement recruited a Senior Infrastructure Adviser to provide much needed technical support, monitoring and leadership of the infrastructure projects. PDF II’s portfolio of infrastructure projects is now well structured and positioned to help EAs to deliver on the power sector reforms.

This review therefore assesses PDF II as having achieved an ‘A’ outcome – outputs met expectations.

Key lessons
1. Responsiveness of technical assistance to beneficiaries is critical to help shape policy direction and improve the likelihood of good policy implementation.
2. Consistency in the implementation of fee-rate caps on technical support can be effective when carried out in conjunction with other DFID programmes.

Key actions
1. Take action on recommendations set-out on page 4 of this review.
2. Focus should be placed on policy areas that appear to have the most traction and that have potential to yield gains before the 2019 election campaigns commence.
3. A review of the team resourcing needed in light of current and future number of projects being handled.

Has the logframe been updated since the last review?

No, the logframe was last revised as part of the inception period discussions. This was to reflect annual milestone targets commencing a year from inception and also to include a third indicator to the two outputs. Indicators were also adjusted at impact and outcome level to better represent measurable progress of the programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Relevant and high quality PDF II organisational support delivered to beneficiaries
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones**	Progress
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	None (as per Log frame targets for 2017)	No milestones for 2017. As of the time of this review, PDF II had made excellent progress with 42[6] projects assessed satisfactory at implementation/Completion stage (more than half way towards achieving the next milestone of 53 in 2018)
Beneficiary, user perceptions of relevance and quality of PDF II funded organisational support	Log Frame threshold for relevant years: / Relevance…………………90% / Quality……………………..80%	No milestones for 2017. Beneficiary feedback has been very positive with projects scoring on average 93% on relevance and 87% on quality, well above the log frame thresholds.
Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs……. None as per Log frame targets for 2017	So far as at September 2017, collated number of instances add up to 45, across 14 MDAs; hence on track to exceed the log frame target of 10 by 2018. / See annex 3 for evidence table recording instances where programme supported data and analysis influenced any of the 5 stages of policy formulation.
[6] Note: In the year under review, 2 projects under this output (022 MITI TO & 031 MoF DA) were assesses as unsatisfactory during implementation. Though both technically met the beneficiaries’ approval, they did not meet objectives/standards desired by PDF, and so have not been included in Indicator 1.1.

**There are no output level milestones in the log frame for 2017 although the milestones are in place for 2018. Milestones are however available for 2017 at the Impact and Outcome levels.

Key Points

At the time of this review, under Output 1, PDF II has 6 projects in pipeline, 62 ongoing projects (8 are in the process of an extension), 29 completed/closed projects (of which 10 projects inherited from PDF were completed and archived during the Inception Phase of PDF II), and 7 dropped projects. 57 of these are new projects which commenced within the last year (including 33 EAs and 3 EAs that were transferred from other DFID closing programmes i.e. NIAF 2 and GEMS 3 respectively). Most of the transferred projects are now being successfully implemented.

DFID and PDF have maintained commitment and have moved quickly to shape its offer of support to those identified as potential ‘Champions of Change’ within President Buhari’s cabinet (appointed in November 2015). A one-year-on political economy analysis of the cabinet (PEA) was carried out in October 2016 and focused on individuals within the cabinet, balance of influence and potential policy opportunities. The findings of the PEA fed into internal DFID efforts to identify areas of promise on the development agenda, and priorities for PDF II. Another PEA will be carried out in October 2017 to help shape the future support, especially as Nigeria moves into the pre – election year of 2018.

Technical Assistance has been provided to the following Federal Ministries, Departments and Agencies (MDAs) as set-out in table 2 below.

Table 2: Overview of areas of technical assistance:
Federal Ministry, Department & Agency	Areas of Technical Assistance
State House ( office of the Vice President [OVP] & Chief of Staff [CoS])	Economic Advisory Council
	Job Creation & Youth Employment
	Policy and Delivery Unit
	Internally Displaced Persons (IDPs)
	Economic Advisory Board
	Communication, Digital & New Media
	Advisory Power Team Cross-sectional Support
	Nigeria Asset Decision Support System (NADSS)
	Rural Electrification Agency & Power Sector Recovery Plan
	Energising Education & Regulation Programme Implementation Support
	Industry Trade & Investment
Ministry of Industry, Trade and Investment (MITI)	Special Advisers on Investment & Strategic Communications
Ministry of Foreign Affairs (MFA)	Senior Adviser on trade & investment issues
	Technical Assistance on Economic Diplomacy Initiative
Ministry of Finance (MoF)	Chief of Staff, Support to Efficiency Unit, Economic Reforms
	Technical Assistance on Improving Tax Compliance in Nigeria
	Special Assistant on Key MSMEs financing Initiatives
Ministry of Planning and Budget (MBP)	Monitoring and Evaluation, Media adviser, Policy and Planning.
	Humanitarian Coordination Group
Ministry of Health (MoH)	Universal Health Coverage Agenda: One PHC Per Ward and Rapid Results Initiative
Ministry of Environment (MoE)	Special Adviser
	Communications Support
	Climate Finance Advisor
Ministry of Agriculture and Rural Development (FMARD)	Project Management
	Senior Technical Advisor on Investment Promotion & Agribusiness
Ministry of Solid Minerals (MSM)	Delivery Unit /Technical Adviser
Nigeria Extractive Industries Transparency Initiative (NEITI)	Policy, Planning & Strategy
Nigeria Sovereign Investment Authority (NSIA)	Investment Advisor & Communications
	Technical Assistance & Investment Decision support for the Nigeria Infrastructure fund
Office of the Auditor General for the Federation (OAuGF)	National Audit Office Partnership
	Technical Advisor & Project Management of the OAuGF Reform Initiatives
Central Bank of Nigeria (CBN)	Technical Support on Energy (Power) matters
Federal Ministry of Power, Works, and Housing (MoPWH)	Chief of Staff & Project Management Unit Support
	Policy, Roads, Urban Development & Housing, Energising Education, & Emergency Generation
	Communications

Over 60 plus projects under output 1 are characterised mainly by the embedding of advisers within key MDAs, supporting champions of change. This review continues to support the evidence that this approach remains key to influencing policy that could plausibly lead to poverty reduction. The case studies highlighted in section B of the review are a sample of the influence and impact. The following below, also expand on the impact the use of embedded advisers have had in the policy space within some key MDAs which the programme envisages could potentially yield high value successes in the medium to long term.

Support to the Office of the Auditor General for the Federation (OAuGF): At the start of 2017, DFID increased the level of support by engaging two new Advisers, a Project Manager and a part time Technical Adviser. This support has already started yielding some positive results:

  1. Engagement with the Public Accounts Committees (PACs) of the National Assembly - A poor relationship with PAC resulted in a significant lessening of the profile of the OAuGF, and audit reports from 2010 onwards were not considered by the Committees. Following a DFID funded retreat between the OAuGF and the PACs in 2015, areas for improvement in the working arrangements and relationship were identified and an agreement was reached between all sides to work better. With more recent DFID support through the appointment of a new Technical Advisor (TA) in 2017, and a follow-on retreat with the PACs (July 2017), the OAuGF now has a PAC engagement Strategy and better relations with the PACs. In addition, the PAC of the House of Representatives has begun working to reduce the backlog of audit reports, starting with a consideration of the 2010 report in February 2017. During the 2017 retreat, it was identified that addressing the capacity needs and engagement challenges of the OAuGF though essential may not be sufficient to optimise the impact of the suite of OAuGF reforms supported by PDF II. The organisation’s independence is critical. The audit bill before the NASS therefore needs to be pushed and influencing through available DFID and other donor channels would be required. This has led to plans of a high level dinner hosted by the British High Commissioner to provide such an opportunity with the leadership of both chambers of the NASS present to deliberate on the issues.

  1. In addition to supporting the independence of the OAUGF, embedded advisors developed, published and operationalised an Audit Guide, a Quality Control & Assurance Manual, a five-year Strategic Development Plan and engaged other anti-corruption institutions such as the Economic and Financial Crimes Commission. All of this capacity building outreach and collaboration is being done through DFID support and mainly by the DFID funded EAs. Given Nigeria’s current economic challenges and budget constraints of the institution, it is highly unlikely that these results would have been achieved as quickly as they have been without DFID support.

Support to the office of the vice president (OVP) and Ministry of Power, Works and Housing (MoPWH) on Infrastructure projects have helped to bridge the gap that would have existed following the closure of the NIAF 2 project since March 2017. This was to ensure that past gains are maximised and kept active towards future achievements. PDF II is currently providing support to the Transmission Company of Nigeria (TCN) – responsible for transmitting power across the nation- and also the Power Sector Recovery Programme (PSRP). The construction of a significant number of substations and transmission lines at the Transmission Company of Nigeria (TCN) have been hindered by lack of funding; slow administrative processes, project management complications and many other issues. To accelerate the transmission wheeling and power transformation capacity of TCN, the Federal Ministry of Power, Works and Housing (FMPWH) and the Management of TCN sought the assistance from DFID to procure a Programme Support Team (PST) to support the delivery and completion of the priority projects. The PST was initially supported by the Nigeria Infrastructure Advisory Facility Phase II (NIAF II) and is now supported by the PDF II programme.

The Programme Support Team is pursuing the following key objectives:
      - Support TCN to complete or advance the construction of the 22 priority projects within scope, schedule and budget;
      - Support TCN to resolve project bottlenecks, risks and issues (including wayleaves, port clearing, delays in invoice processing/payments);
      - Deliver sustained enhancements to TCN processes, procedures, systems, and project management practices; and
      - Introduce and support the implementation of best practice reporting standards.

The PST continues to support TCN in advancing the priority projects. As of September 2017:
- 10 projects have reached a project completion of 90% or above;
- 7 projects have reached a project completion of between 70% - 90%; while
- 5 projects have a percentage completion below 70%.

On the Power Sector Recovery Programme, Power plays a critical role in the socio-economic development of Nigeria. To that end, the Federal Government Economic Recovery and Growth Plan 2017 – 2020 (“ERGP”), has prioritised the expansion of power sector infrastructure to diversify Nigeria’s economy. Given the current crisis in the electricity market, the Federal Government of Nigeria has initiated a comprehensive electricity market intervention – the PSRP. With support from the World Bank and DFID (through PDF II), the PSRP is a series of policy actions, operational, governance and financial interventions to be implemented by Federal Government over the next five years. Its objective is to restore the financial viability of power sector, improve transparency and service delivery, and reset the Nigerian Electricity Supply Industry (NESI) for future growth. PDF II supports the advisory power team, communication advisor and senior strategy advisors who play an integral role in the implementation process, especially in the areas of communication strategy, monitoring and evaluation, strategy and conflict resolution.

Support to the office of the vice president has been multi-faceted and includes supporting the Presidential Economic Advisory Council which functions as the central economic advisory hub embedded in the office of the Vice President, supporting the Vice President in his role coordinating on economic matters. With the current challenges facing the Nigerian economy due to the fall in oil prices, the Economic Advisory Council coordinates across government to ensure that the economic responses are in alignment and well designed and implemented for maximum impact in addressing the challenges. They will also act as the coordinator of the affairs of the Vice President in the execution of his oversight of the National Economic Council (NEC) which will entail liaisons with the National Planning Commission, Central Bank of Nigeria, Ministry of Finance, Debt Management Office, Federal Inland Revenue Service, etc. Through this support, the advisory council has gone a long way to improve communication across departments. The administration has launched the Economic Recovery Growth Plan (ERGP). There is still work to be done in terms of implementation.

Support to the Ministry of Finance (MoF) has also yielded some good outcomes over the last year and has included the work done by the efficiency unit (see section B paragraph 17.1.3 for details of achievements). Other support was on economic reforms, project management and MSME financing initiatives. Programme management support was also provided towards the design and implementation of an efficient scheme that improves tax compliance in Nigeria. To achieve this the EA helped to set up and manage sub-committees working on Voluntary Asset and Income Declaration Scheme (VAIDS), design and management of the VAIDS website and project management of implementation of the scheme including operations of the asset tracing team.

Some technical Assistance is also focused on Enabling the Development Bank of Nigeria (DBN) and its Participating Financial Institutions (PFIs) use best practice for providing loans to MSMEs; Disbursement of family homes fund to beneficiaries to enable the delivery of affordable homes; and Piloting a road trust fund. The project aims to the deliver the following:
Fully functional DBN evidenced by number of MSMEs securing loans
- Number of companies securing funding to deliver affordable homes
- a completed pilot of the road trust fund
- Number of affordable homes to be delivered by projects commissioned under the scheme.

Summary of responses to issues raised in previous annual reviews (where relevant)

[Please refer to table 1 for progress on recommendation from the last annual review.]

Recommendations

- Carry out the political economy analysis (PEA) of the current cabinet to influence/shape future support of the programme.
- Prioritise package of support based on the outcome of the PEA towards MDAs with the most potential outlook of achieving high value successes.
- Play a more active role in supporting coordination economic policy development across MDAs/institutions where collaboration would yield stronger impact. For example there are synergies between various agencies such as the Ministry of Trade Industry and Investment, the Nigerian Export Promotion Council, Ease of Business Executive Secretariat, etc.
- The Economic Recovery Growth Plan (ERGP) needs strengthened coordination for traction and implementation as progress has been remarkably slow and its coordination questioned. The programme should explore ways of ensuring better coordination across MDAs towards yielding the gains of the plan.
- Keep the momentum going to track and push through more proactively potential reforms / policies e.g. the franchising bill and the audit bill.

Output Title	Relevant and high quality PDF II policy research, explorative studies and consultation products delivered to beneficiaries
Output number per LF		2.	Output Score	A
Risk:		Low	Impact weighting (%):	40%
Risk revised since last AR?		No.	Impact weighting % revised since last AR?	No

*Note: in the year under review no projects under Output 2 were assessed as unsatisfactory.
Indicator(s)	Milestones (None for 2017)	Comment
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	No 2017 milestone as per log frame.	No milestones for 2017. As of the time of this review, PDF II had made excellent progress with 35 projects assessed as satisfactory at implementation/Completion stage (close to achieving the next milestone of 36 in 2018)
Beneficiary, user perceptions of relevance and quality of PDF II-supported policy studies and events	Log frame thresholds for relevant years: / Relevance………………… 90% / Quality………………..…… 80%	No milestones for 2017. Beneficiary feedback has been very positive with projects scoring on average 94% on Relevance and 85% on quality, well above the log frame thresholds.
Number of instances*** where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs….. (None as per 2017 Logframe targets.)	So far as at September 2017, collated number of instances add up to 4, hence on track to meet the log frame target of 7 by 2018. See annex 3 for evidence table recording instances where programme supported data and analysis influenced any of the 5 stages of policy formulation.

Key Points

Since the inception of the programme, PDF II has taken on a total of 61 projects under output 2. Of these projects, 12 are in pipeline, 8 ongoing, and 41 completed (this includes 1 project inherited from PDF which was completed and disseminated). Over the last year, PDF II has taken on 34 new projects under output 2; 1 of which was transferred from NIAF.

Following recommendations from the programme completion review (PCR) of PDF 1 a website has been created which serves as a learning platform. PDF II now makes greater use of social media to highlight policy implications of PDF II’s work. Building on lessons from using this approach during the policy dialogues and events organised by PDF II, PDF II is building a stronger base of followers and users of PDF’s content.

Over the year, the PDF II programme has supported champions of change with insightful policy research, explorative studies and consultation products. Some of these and their corresponding impact include:

Unlocking the Potential of Franchising in Nigeria.
PDF II supported a study that looked at ‘Tackling Access to Finance: The Potentials of Franchising in Nigeria’. The study aimed to understanding the potential of Franchising in Nigeria and the roles for various actors. Following the completion of the study, in partnership with Franchise Business Development Services (FBDS), a dissemination event was held, which brought together the range of stakeholders including members of the National Assembly (NASS), existing and potential franchisors and franchisees, government and other private sector players. The event explored opportunities and challenges, and the potential role of the various stakeholders in developing franchising as a viable business model in Nigeria. From the discussions at the event, it was obvious that for decades, the legislative and regulatory framework guiding the Franchise Industry in Nigeria has been largely unclear and in some cases non-existent. The need to strengthen the Nigerian Franchise Association (NIFA) to advocate for players in the Franchise industry was also discussed. And on the part of the Nigerian government, ensuring that the environment is business friendly is essential to spur investments into the Franchise industry. Overall, it was a successful event with the right stakeholders in the room, which contributed to the vibrancy of the discussions. FBDS has carried on with work in this space with a follow on match making event, which held in August 2017. PDF II has also continued to link interested potential franchisors to FBDS for guidance.

Diaspora Study
Diaspora remittances are a significant part of foreign exchange inflow to Nigeria, but not much seems to be known about how these remittances are used. And while recent discussions with diaspora groups in the UK have highlighted various challenges that may impede diaspora investment, there may be potential which DFID wishes to explore in order to determine if indeed there is scope to leverage remittances more towards investments. A number of opportunities have been flagged through PDF II funded projects, which are also aimed at pushing linkages with the diaspora with the aim of generating investments. Upon initial engagement with relevant government stakeholders, it became clear that this study was timely and needed. The Nigerian Investment Promotion Commission (NIPC) is currently developing an intervention aimed at generating domestic and foreign funds that may be invested in development projects in key areas (e.g. infrastructure). Hence beyond DFIDN’s programming needs, the study will feed into various interventions (NIPC, Ministry of Foreign Affairs etc.) of the Government of Nigeria that could potentially generate much needed resources for development.

Bearing this in mind, the study was designed to explore the purpose of current diaspora remittances, ability to make investment remittances and/or to switch between consumption and investments remittances (wholly or in part), willingness to invest in Nigeria, key challenges with investing in Nigeria and potential solutions. Early findings show that 57% of respondents remit funds to Nigeria and 30% of remittances go to investment-related uses. Furthermore, first generation UK-based male respondents are also more likely to invest in Nigeria. Real estate and agriculture were potential categories for investment. This information is relevant for DFID upcoming LINKS programme which aims to attract and facilitate investment (which could in this instance be remittances).

Trade Policy Support: The political economy of trade policy remains challenging with certain groups dominating the policy discourse and many other local voices unrepresented. Rather than traditional institutional support, the balance of PDF II’s efforts is focused on the building blocks of long-term trade policy by strengthening alternative (or under-represented) voices that can feed into the policy processes. PDF II explored how it might strengthen the role of relatively weak exporter groups to feed into policy formulation as well as consider how it could work to reflect a broader group of manufacturers and businesses into policy discussions (including Small and Medium Enterprises (SMEs) and the informal sector). The work stream commenced on the 1st of November 2016 with two embedded advisers and one project support consultant. Based on findings from a baseline assessment and engagement with various stakeholders, PDF II developed a strategy that would by 2020 strengthen exporter groups so that gains in their participation and influence in the policy space would be sustainable beyond the close of PDF II in 2020.

  1. The PDF II Trade Work Stream commissioned a study to map experiences of exporters of non-oil commodities in Nigeria. The aim of the study was to analyse and document the exporters’ experience on sequence, processes and costs for exporting products from Nigeria and thus, to bridge the knowledge gap in exporting by clearly drawing up a sequential procedural map with costs and approximate durations for processing. This will contribute towards improving the business environment for exporters by providing transparent published information, which can form the basis for any potential advocacy around process improvement. It will also provide guidance, which will cut down time spent sourcing for information and costs associated with illegal charges. Early findings indicate that more work needs to be done around transparency of costs of services provided by key public agencies in the chain of exports such as registration costs. In addition, for most of the processes there was a lack of clarity on sequence of agencies to visit and duration of time required to process. It was also found that there is no clear recourse for export operators to register their grievances.
  2. The second study which is also near conclusion targeted key UK, ECOWAS, and EU market value chain for shea butter, cashew nuts and sesame seed. The third study which is on-going is a deep dive into the ‘Made in Aba’ manufacturing cluster to highlight inputs, outputs and cross border export destination of goods to indicate areas for potential private sector or government intervention. Finally, in response to a request from the newly established Nigeria Office for Trade Negotiations, PDF has provided materials for set up of the Office’s library, and is currently supporting a trade policy formulation training initiative for the unit’s staff in collaboration with the Overseas Development Institute (ODI) and the UK Department for Trade and Investment (DTI). Thus, PDF II has taken pro-active steps and seized every opportunity aimed at achieving change in Nigeria’s Trade policy space.

The work stream has developed good relationships with the Presidential Enabling Business Environment Council’s (PEBEC) Enabling Business Environment Secretariat (EBES). In addition, the team has in collaboration with key stakeholders within and outside government and identified a few key reform areas to increase non-oil exports. NEPC and EBES have shown strong interest in some of the outcomes of the trade work stream, specifically, the report on Exporter Experiences. In addition to the Exporter experience study, a dialogue was held on 31 August 2017 (which provided a platform for interaction between exporters to learn and share their experiences) laid the foundation for galvanizing exporters into an effective community for advocacy and influencing trade policy. Furthermore the dialogue provided a mechanism for exporters to interact directly with EBES; the reform agency driving cross border and ease of doing business reforms in Nigeria.

Summary of responses to issues raised in previous annual reviews (where relevant)

[Please refer to table 1 for progress on recommendations from the last annual review.]

Recommendations

      1. More proactive linking up of MDAs in the use of research products to support the policy formulation process.
      2. Keep the momentum going to track and push through potential reforms and or policies e.g. the franchising bill.
      3. More proactive and strategic support of relevant bills in the national legislature which will support transparency (the Audit Bill) and ease of doing business (Franchise Bill) in Nigeria.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for PDF is the technical expertise it deploys through its two outputs. Building on the recommendations in the 2014 ITAD review of Value for Money (VfM) in Nigeria’s Economic Growth Portfolio, PDF II set-up an approach to monitoring value for money during its inception period which covers the following:

1. Recording cost data and, where meaningful, calculating moving six monthly averages of unit costs (e.g. fee rates and knowledge products/deliverables) and ratios of programmable to overhead costs (Economy);
2. Relating these to the changing values of the Outputs’ indicators (Efficiencies); and
3. Learning about how and to what extent the services and products made available through the programme’s outputs are being used, or rejected, by the Champions of Change and others, including DFID, and supporting changes that promote inclusive growth and other pro-poor policy impacts (Effectiveness and Equity).

The key questions regarding VfM (including the four Es) is also tracked through individual project terms of reference and reports and assessed against the Programme’s output and, later on, the outcome’s indicators[7].
[7] The requirements for comparing their values would be with the previous six monthly report and among those at output level for the current reporting period

Project budgets are individually designed with the objective of achieving best value for money for agreed activities required to achieve the outputs and outcomes of the terms of reference (ToR). In particular, for Output 2 projects, activities are scrutinised to ensure that they are planned in a way that delivers best VfM. To further ensure VfM, PDF II has put in place a structured procedure for negotiating fees with consultants and has standard unit costs for certain expenditures.

Per the Business case under PDF II below is a summary of the:
-	Average monthly fees of embedded advisers, Output 1
-	Average daily fees of expertise brought in primarily for Output 2 (policy studies and research)

Description	Monthly Fee Rate (£) / (long term consultancy)			Daily Fee Rate (£) / (short term consultancy)
Period	2016	2017	Variance	2016	2017	Variance
Minimum	2,759	1,379	1,380	34	60	26
Mean	5,360	5,509	149	428	400	(28)
Maximum	6,250	6,250	NA	870	985	115

Although there is an increase in average monthly fee rates from the last Annual Review, a strict cap of £75,000 per annum remains in place on fees for embedded advisers to control costs of this expenditure. Average daily fee rates however fell in the one year period. The PDF II approach continued to be implemented for all embedded advisers recruited during the period under-review. This had a significant impact on the transition of Embedded Advisers from the NIAF 2 and GEMS 3 programmes. The PDF II approach to negotiations and the cap continues to be applied with good results on value for money.

Highlights of VFM under PDF II:
Despite the challenges faced when negotiating with the EAs, as at the time of this review, PDF II had successfully transferred 33 EAs from NIAF and 2 EAs from GEMS 3. There are currently 32 ongoing transferred projects (NIAF (30), GEMS 3 (2)), 1 EA transitioned for 1 month and contract now closed, 1 EA transitioned into the PDF II Management Team as the Senior Infrastructure Adviser, and 2 EAs contracts are still in pipeline. On average, PDF II fee rates are lower than the fees EAs were paid under NIAF 2 and represents a monthly savings to DFID of about £20,000, a significant VfM achievement.

The Programme has shown other good examples of where it has been able to bring down costs; one example was the negotiation process for support to a presidential initiative the ‘Accelerating implementation of business enabling environment reforms in Nigeria’, where costs were negotiated down by 74%.

Despite the challenge with engaging very senior consultants to support the Office of the Vice President through the Economic Advisory Board (EAB) - one of which is a former CBN Governor), following several brainstorming sessions with DFID on the best approach to engage the consultants, PDF II emphasised on the national service element to which 3 of the members responded positively and are performing the role pro-bono.

VfM performance compared to the original VfM proposition in the business case

There has been strong progress on the efficiency and effectiveness of interventions while continuing to keep costs low. As illustrated from the Case Studies above, technical support provided through PDF II projects are being used by beneficiaries to pursue vital economic and social reform.

DFID and the PDF II programme have also recently introduced a budgetary and head count cap to the embedded advisers in key MDAs and are working to make this standard across board, where additional requests are reviewed in the light of total package of support. This has helped to manage the increasing number of requests received.

Assessment of whether the programme continues to represent value for money

The overall Value for Money of the programme will depend on the ability of PDF to help shape, influence and support Nigeria to achieve two or three substantial policy wins over the life of the programme. For example the backing of the Efficiency Unit within the Ministry of Finance could plausibly lead to large impact across the Nigerian Government in driving savings in the recurrent budget. The Innovation Hubs driven by the Office of the Vice President is a viable opportunity to create jobs and raise incomes within different regions of the country.

With the next year being a pre-election year, ensuring delivery of value for money would include a consolidation of support to the OAuGF towards independence, improving cohesion with the Public Accounts Committees, locking in innovations in the Efficiency Unit and supporting the creation of an outward looking National Office for Trade Negotiations.

Quality of financial management

Financial Management from PDF has overall been improving, and whilst a significant proportion of its expenditure is fixed through-out the year, it has done well to adjust the more flexible elements of its expenditure profile to fit with DFID requirements. The main challenge to financial management has stemmed from the challenging economic environment in which Nigeria has been operating since 2014. In particular, since the exchange rate regime was moved from a fixed official rate to a ‘managed floating exchange rate’ system, forecasting and the ability to achieve forecasts have come under pressure. PDF II has responded by developing a responsive tool for monitoring cost sensitivities, and impact of the new floating exchange rates on forecast.

Another key challenge is receipt of timely invoices from PDF II contractors. In response to this challenge, along with the existing procedure of agreeing an invoicing schedule with contractors; briefing contractors on expectations for invoicing; sending monthly invoice reminders to contractors; PDF II has also included an invoice forfeit clause on all contracts. As this procedure was recently implemented, it is yet to be seen how effective it will be. PDF II is mindful that there is a constant need to balance financial expectations alongside the political sensitivity of managing relationships with contractors who work closely with PDF II Beneficiaries.

Overall, DFID is working with the programme towards strengthening the financial management and addressing the challenges with variances between monthly forecasts and actual spend averaging about 4% over the past year (October 16 – September 17).

Of the £13.2m funds set aside for PDF II projects, DFID has committed £8.9m (including £1.2 that has been set aside for the PDF II Trade Work stream which is currently ongoing). This leaves a balance £4.3m for new projects over the remaining 2.5 years of the programme. Considering the average monthly cost of a PDF II EA is £5,509, if DFID through PDF II continues to fund an average of 31 EAs per year (i.e. assuming NIAF projects transfer to a successor programme in March 2018), EA funding alone is likely to quickly exhaust the balance of £4.3m before the scheduled closure of the programme in 2020. Following this annual review, the project budget will also be reviewed.

An independent programme audit has also just been concluded which was unqualified and did not flag any issues of concern. This provides assurance of the robustness of the financial controls. DAI’s last annual audited statements (AAS) for the period ended December 2016 also did not flag any issues of concern. The next company annual audited statement is expected early 2018. The next statement will be for the period ending December 2017.

Date of last narrative financial report	October 2017
Date of last audited annual statement	18249908 – Period ended December 2016.

E: RISK (½ page)

Overall risk rating: The overall risk remains at Moderate for PDF II which continues to reflect the substantial uncertainty about the political environment for reforms that PDF 2 was entering post elections and indeed still face with changing priorities resulting in a slower the pace of reforms than hoped.
The programme could benefit from improving on risk monitoring across the portfolio, regularly collating and managing programme risks in line with DFID’s guidance.

Overview of programme risk
The section below highlights the main risks areas from the PDF II risk register and maps these against DFID Nigeria’s risk appetite.

External Context: The operating context remains broadly positive, though initial promising opportunities for significant economic reform from the new government in the oil and gas sector and government's continued commitment to the power market development have somewhat stalled. The overall administration formation and delivery of policy on pro poor growth areas have been less than predicted and hoped for, including a lack of clear implementation and coordination of policy across government.
Gross risk: Major risk
Mitigation: Strengthen voices (such as private sector) feeding into policy debates and link up with UK Government influencing. Identify areas - such as Office of the Auditor General and the Ministry of Finance Efficiency Unit where political will may exist for quiet reform throughout the programme life span.
Net risk: Major risk

Delivery:
        1. Backing individuals/ institutions that are unable or unwilling to pursue policy and implementation reform
Gross risk: Moderate risk
Mitigation: The service provider has been contracted in a flexible responsive way which minimises delivery risk due to its ability to be adaptive to the reform environment PDF II coordinating support with other DFID programmes and where possible, putting together a cohesive long term package of support to build the capabilities of the agencies.
Net risk: Minor risk

  1. Increase in overall number of projects than anticipated, including transfer of Infrastructure embedded advisers to the programme which is new territory for programme will be additional stretch to the small team and management of the portfolio could be ineffective.
Gross risk: Severe risk
Mitigation: Recruitment of an infrastructure lead with high levels of competence for managing the set of projects, including also approved hiring of support contracts & admin staff and two new advisers within the PDF team to lead on trade policy providing more operational capacity to the programme. Additional resourcing to the programme team to manage stretch is also being considered.
Net risk: Minor risk

Operational: Small in country PDF2 team (mostly focused on programme administration and management) and it relies heavily on DFID adviser strategic direction disproportionately compared to other programmes
Gross risk: Minor risk
Mitigation: DFID has recently strengthened its capacity to provide strategic oversight by hiring a new Country Economist to support the Economic Growth Team Leader, including a separate SRO and programme officer.
Net risk: Minor risk

Fiduciary: Risk that funds are misused or misappropriated
Gross risk: Minor risk
Mitigation: No DFID funds put through Nigerian Government systems and currently no grants are provided from the programme. DFID N will also commission independent audits to ensure proper procedures are in place to properly monitor the use of other expenditures from the programme. if the programmes does start providing grants in the future it will need to have appropriate procedures in place at this risk rating will be re-evaluated. There is an associated reputational risk due to use of embedded advisers that in some cases may have a degree of influence over the use of Nigerian Government funds.
Net risk: Minor risk

Reputational:
  1. Risk of comments being attributed to DFID which may harm the UK's Government relationship with Nigerian counterparts. There is also a risk on the public position or actions taken by DFID funded embedded advisers having negative impact on DFID.
Gross risk: Moderate risk
Mitigation: Service provider has put in place rigorous approach to making reports public and staff avoid providing comments to the media. There is also reputational risk from the use of embedded advisers who are not directly managed by the programme. This risk is mitigated to an extent by regular performance reviews with the beneficiaries, and taking prompt action if problems are identified.
Net risk: Minor risk

  1. Risk of embedded advisers moving to PDF 2 terms and conditions from other programmes not satisfied and escalating into lawsuits against DFID.
Gross risk: Moderate risk
Mitigation: Timely and documented discussions on Terms &Conditions to ensure understanding/agreement in advance of engagement of consultants. Generally need a more proactive contract management.
Net risk: Minor risk

Safeguard: New risk area to be considered as programme is evolving; Interventions like the N-power programme creating jobs should be monitored against risks towards child labour as well as mature job seekers.
The infrastructure component with risks linked to possible abuse of local populations on construction sites, including any social and environmental risks linked to land acquisition / clearance.
Gross risk: Moderate risk
Mitigation: Ensure this is kept in view and active in the project management of ongoing projects and reflected in consultant ToRs so that risks are prevented from materialising, including with regular monitoring and reporting.
Oversight functions to also include focusing on issues related to contractor behaviour towards local communities and due process in land acquisition covered extensively in contractual documents to different contractors. Additional mitigation measures could include active management with the beneficiaries for example the development of a communication and engagement strategy in advance as well including obtaining written commitment by all stakeholders to manage these risks.
Net risk: Minor risk

Outstanding actions from risk assessment

Delivery: Major outstanding actions from the above include the recruitment and on boarding of additional resources to manage the increased stretch and workload of the programme.
Reputational: More proactive contract management by the programme to ensure terms and conditions are agreed to ahead of engaging consultants.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Contracting commenced in April 2015, after an open tender process, and the inception period was successfully completed by the programme within six months. Two years into full implementation and the programme remains on track.

Performance of partnership(s)
PDF II service provider has performed well and been responsive to DFID and beneficiaries during this period.

Asset monitoring and control
Appropriate systems and processes have been put together for asset monitoring and control and are updated regularly and shared with DFID. The 2017 independent audit of the programme has also confirmed proper management of assets in line with DFID’s assets guidance.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The programme does not use the Partnership Principles as formal conditionality in programming as no UK aid money goes directly to the Government of Nigeria. But we will use the relevant Partnership Principles at two levels to guide our decisions; first as criteria in the selecting the partner institutions and ‘champions of change’ that PDF provides technical assistance to and with the choices of modes/depth of engagement (and as part of the decision on when to exit support from these institutions), and secondly as ‘live’ principles for active monitoring during annual reviews. In particular, institutions committed to pursuing pro-poor economic and social policy, strengthening transparency and minimizing corruption, and enabling domestic accountability may be considered when determining the level of technical assistance that the programme provides. Greater resources will be directed to those institutions that demonstrate greater commitment to the partnership principles and this will be used alongside political economy analysis of where pro-poor economic transformation is likely to come from.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

This review provides evidence that the programme continues to be valued by the beneficiaries and is useful in supporting champions of change. There are however instances where further effort could be deployed into turning opportunities into successes. This review also suggests additional capacity in Monitoring and Evaluation in tracking progress across projects to ensure that potential high value successes are followed through. For example, monitoring and tracking of the progress with the franchising bill will provide a more structured approach towards supporting the final passage by the upper house given its potential. The Nigerian Franchise Association (NIFA) could play a more strategic role in liaising with the Nigerian Government and other stakeholders to take forward franchising in Nigeria. The benefits will also impact on the new programme LINKS when its starts.

There is no formal evaluation planned for PDF II. A review of key case studies from the programme is presented in this annual review which will provide an important opportunity for lesson learning and path-correction.

Monitoring progress throughout the review period

A logical frame work has been agreed with DFID and is in place to guide PDF II’s outputs and activities. Monitoring and Project Management tools and processes have been put in place and continue to be tested and improved upon. Through a light touch monthly project monitoring approach and more formal interim reporting, PDF II collects knowledge on opportunities, threats, and lessons learned which are regularly fed back to DFID for better coordination and planning of DFID interventions.

The logical framework may benefit from a review on how projects are being defined including a review of the relevant milestones. Projects should be contributing to specific outcomes rather than individual packages of support. The logframe should be reviewed in light of the pro-poor evaluation of the FGN policies and the planned political economy analysis of the cabinet.

PDF II Abuja office team developed templates and procedures for project administration and monitoring that incorporated new features for monitoring VfM, environmental/climate impacts, gender impacts, progress of projects towards achieving outputs and outcomes.

Beneficiary Feedback

Relationships with Beneficiaries have continued to develop. PDF II has sought beneficiary feedback through a project scoring matrix which shows that beneficiaries are satisfied with projects, and PDF II’s management of projects, and on average (i.e. across Output 1 and Output 2) PDF II’s projects scored 94% on relevance and 85% on quality, well above the log frame requirement of 90% and 80% respectively.

Review Process

This review was carried out by the DFID Senior Responsible Owner (SRO) for PDF II, and the DFID Nigeria Country Economist and the DFID Project Officer, the PDF project team, and selected beneficiaries.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process