Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Strengthening Emergency Preparedness and Response in Kenya (EPRP)
Programme Value: £1,750,000		Review Date: October 2017
Programme Code: 203768	Start Date: 1/12/2014	End Date: 31/05/2018

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review

Good progress has been made during this reporting period. a majority of results have either been achieved or exceeded with a few that are off track. The three programme outputs are (1) increasing capacity to prepare for disasters related to climate shocks (droughts, floods, landslides), conflicts, terror attacks, election related skirmishes, urban disasters (fires and building collapses) and disease outbreaks (cholera, malaria, chikungunya); (2) increasing response efficiency and accountability and (3) sharing learning. The outputs are on track to meet the programme’s outcome which is: ‘increased capacity of the Kenya Red Cross Society (KRCS) to prepare and respond to the needs of people affected by these disasters.

The programme is demonstrating positive impact. A February 2017 independent evaluation of KRCS noted that “KRCS has developed greater ownership of the programme as it has evolved, with the programme now perceived as led by KRCS”. This is important given that KRCS is an auxiliary to the Government of Kenya (GoK) in disaster management. The evaluation further highlighted that; KRCS has made positive strides in its disaster preparedness and response work; however, there are areas where practice could be strengthened to better meet the needs of those affected by disasters. These include better utilisation and dissemination of agreed policies and embedding the culture of continually assessing its responses.

KRCS made substantial progress under its Cash Transfer Programming (CTP) reaching 16,486 households (c. 82,430 individuals) from 3,982 (c. 19,910 individuals) reached during the last reporting period. The CTP witnessed a significant shift in KRCS’s organisational awareness that has now translated into practice. Acceptable controls and procedures for managing the CTP are in place. KRCS has embedded a strategic pillar dedicated to Value for Money (VfM) in its 2016 – 2020 Strategic Plan. These measures will not only ensure efficiency in responding thus saving time, lives and money but will also ensure that resources have a greater reach, thus maximising impact.

The collaboration between KRCS, GoK, county governments and other humanitarian partners under the Kenya Interagency Rapid Assessment (KIRA) mechanism has the potential to further enhance responses to disasters in a more coordinated way that is also an effective accountability mechanism. DFID supported KRCS to engage and lobby parliamentarians towards finalisation of the 2016 Disaster Management Bill. This Bill is expected to further complement the programme’s objectives. The Bill will be tabled for approval in the new Parliament once it settles in. KRCS has so far leveraged £950K funding from other donors and Corporates to support and enhance response to disasters.

Other highlights during this period include; KRCS’s drought response that has so far reached over 750,000 people and election preparedness through pre-positioning of non-food items (NFIs).

In the remaining seven months of the programme, emphasis should be placed on sharing lessons within KRCS and externally with national and county governments; and other partners in the humanitarian disaster management space. Contingency plans and Standard Operating Procedures (SOPs) need to be known more widely across KRCS and its volunteer base for increased understanding and effective application in emergency responses. To mitigate against challenges in registering beneficiaries and double counting under the CTP, KRCS should explore linking up with GoK’s Social Protection Single Registry. Where feasible, KRCS should tap into delivery mechanisms that are running efficiently rather than creating parallel systems.

Priority actions
Priority actions over the next seven months are:-

KRCS has made great progress in putting together excellent policies, guidelines and Standard Operating Procedures (SOPs). These policies have set the bar high in terms of response. However, going forward, behaviour change from its Senior Management Team (SMT) staff and volunteers is required;

KRCS has made commendable efforts in developing SOPs and other useful reference materials. However, there is need to have these easily accessible to staff and volunteers. A recent online sample survey of 156 people indicated that 78% of respondents did not have final versions of contingency plans, thus impeding their response capabilities. KRCS needs to explore ways of creating a central registry that allows staff and volunteers to access final documents on an on-going basis. In addition KRCS should consider an internal interactive digital platform that allows staff and volunteers to share lessons and challenges;

There is need for KRCS to enhance its monitoring and evaluation (M&E) approaches to reflect its operations on the ground and within the expectations and standards of the programme. Learning is an essential element of this programme, hence key to have monitoring systems that are adaptable to capture the varying complexities of the emergency at hand to best meet people’s needs. A robust M&E system will also ensure that double counting is minimised to the extent possible;

KRCS should continue to lobby for the passing of the 2016 Kenya Disaster Management Policy in the new Parliament and where possible call upon other key players to help influence its passage;

There is need for better coordination and alignment in emergency responses. The coordination of KIRA activities both at the national and county levels has not progressed well despite the roles of various actors having been set out in the signed MOU. GoK needs to take lead in ensuring that all signed up partners play their rightful role;

There is need for KRCS to operationalise the online stock management system beyond a couple of branches and further strengthen its financial management systems across its branch network. This will go a long way in providing the safeguards required to enable KRCS attract more funding from others;

There is need for KRCS to develop a sustainable exit strategy that provides a framework of how it will engage and influence key stakeholders, donors and the private sector in order to consolidate gains made under this programme and further enhance future results.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203768/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203768/documents

Kenya faces a range of disaster risks including climate-related risks (drought, floods and landslides), conflict, terror attacks, periodic urban disasters (fires and building collapses) and disease outbreaks (cholera, malaria, chikungunya). While GoK is responsible for disaster response, KRCS has time and again been at the forefront of responding to disasters across the country. GoK formally recognises KRCS as the official first responder in sudden onset disasters. This programme was designed to strengthen KRCS systems and processes around preparedness and response to disasters. The programme is co-funded with the the British Red Cross, European Civil Protection and Humanitarian Aid Operations (ECHO), the Finnish Red Cross and the Danish Red Cross.

The approved programme budget as per the original Business Case was £1m over three and a half years (December 2014 – May 2018). However, to date, DFID has committed £1.75m. The additional £750,000 has been provided through activation of an internal risk facility (IRF) to facilitate preparedness and response to the 2015 el nino rains and cholera outbreak and the 2017 election preparedness.

During the year in review, the programme supported the following:-

Disaster Management Strengthening: KRCS met the immediate needs of 1.5 million people affected by disasters. The disasters were related to conflict, drought, cholera, flooding and election-related skirmishes. An additional 750,000 benefitted indirectly from KRCS interventions, for example through health education messages and psychosocial support. Thus over 2.2 million people were reached in total, representing a reach of 56%. During this period 3.9 million people in Kenya were affected by disasters. It is encouraging to note that in a recent online survey of 156 KRCS staff and volunteers, 81% of them reported an increased capacity to prepare for disasters.

Through DFID funding, KRCS played a critical role in the finalisation of Kenya’s Disaster Management Bill that is expected to be presented in Parliament in the coming months. The Bill provides for the establishment of a Disaster Risk Management Authority that will liaise with national and county governments on disaster preparedness, mitigation, response and recovery measures. Meanwhile it continues to collaborate with county governments in building and strengthening their disaster management response mechanisms.

Drought response: KRCS reached 16,486 vulnerable households (c. 82,430 individuals) in Mandera, Wajir, Garissa, Isiolo, Samburu, Turkana, Kwale, West Pokot and Kilifi counties through cash transfers. Given that DFID contributed about 62% of this; cash transfers to 51,107 individuals can therefore be attributed to DFID support. The one-off cash payments varied from between £22 to £44 per household and were guided by levels of need and context. This enabled the households to better cope with the ravaging effects of drought. There were challenges in targeting beneficiaries as well as in coordinating cash responses with other actors but KRCS is actively engaged in addressing these issues.

Contingency Programming: In conjunction with GoK, KRCS played a key role in the development and dissemination of the 2017 Kenya Elections Contingency Plan. This plan was heavily relied on by national and county governments as well key stakeholders in preparing and mapping out effective response mechanisms based on need. These comprised; first aid, emergency medical services, temporary shelter support, public health services, WASH services and tracing and restoration of family links.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome indicator 1	Baseline	Target	Achieved	Indicator score
Percentage of KRCS staff (disaggregated by gender) reporting improved capacity to prepare for disasters	Total: 0%	60%	65%	A

Outcome indicator 2	Baseline	Target	Achieved	Indicator score
Percentage of population affected by disasters (reported to Emergency Operations Centre (EOC) reached by KRCS response	Total: TBD	45%	56%	A+

Overall EPRP is making strong progress in the achievement of its outcome ‘increased capacity of KRCS to prepare for and respond to the needs of people affected by disasters’. This is the programme’s last annual review and there are clear indications that it will meet its outcome target at completion. There is a demonstrated and sustained momentum amongst KRCS staff and volunteers towards improved skills in disaster preparedness and response. KRCS has also reached more people affected by disasters than earlier envisaged.

The following quote from a KRCS staff summarises the leaps that have taken place ’Initially, I would struggle with a number of issues concerning proper management of KRCS response teams. Whenever I was called upon to respond during disasters, I would first call the Regional Manager to verify certain procedures that had never been made clear. For instance, the Regional Manager was the custodian of key data collection tools and would share them when there was need to do so especially when the team needed to respond. I am now much aware of the 24 hour assessment tool, the 72 hour tool, KIRA tool, situation reporting tool as well as the household data collection tool’

Overall output score and description

Outcome indicator 1: Percentage of KRCS staff (disaggregated by gender) reporting improved capacity to prepare for disasters. This indicator captures percentage of KRCS staff (disaggregated by gender) reporting improved capacity to prepare for disasters. In the annual independent online survey to assess the capacity of KRCS staff 82 (53 male and 29 female) out of 126 reported having improved capacity, thus indicator met expectation.

Outcome indicator 2: Percentage of population affected by disasters reached by KRCS response. This indicator captures percentage of people affected by disasters who are reached by KRCS. Through various interventions KRCS reached 2.2 million people against an affected population of 3.9 million. This represented a reach of 56%, thus moderately exceeded expectation. This is an improvement of 17% as compared to those reached during the last reporting period. However, there is need to revise this indicator to capture proportion of those in need of life-saving assistance who receive it as not all people affected by disasters necessarily require assistance.

Key lessons
Cash transfer programing (CTP): KRCS has made commendable progress in the use of cash as a response mechanism. Its recent approach of involving the community in the selection of beneficiaries and communications around this has proven effective for improved targeting. However, KRCS needs to focus on other areas related to CTP. These include, but not limited to, building robust systems that can respond at scale and enhancing their staff capacity on CTP across all levels of the organisation;

Organisational change management (OCM): KRCS has undergone a positive organisational change for example use of CTP in emergency response. This has further enhanced the outcomes under this programme. It is important that these changes are further institutionalised within the organisation with mainstreaming continually embedded within the organisation. It is vital that these changes are supported and maintained across KRCS’s Senior Management Team (SMT);

Monitoring and evaluation (M&E): This is an important management tool that determines effectiveness of the response. Due to the nature of its multi-sectoral responses, there is need for KRCS to improve its systems and have the correct tools in place to better monitor progress. This will ensure that the right people are reached with the right kind of interventions at the right time. Having the right evaluation capacity within the organisation is key;

Collaboration and alignment: The increased collaboration with national and county governments as well as with other key players is realising good outcomes. However, there is need for further improvement under the KIRA framework in order to realise optimal responses;

Capacity to deliver: There is increased confidence by both staff and volunteers in terms of improved skills in disaster preparedness and response. However, there is need to go beyond assessing the knowledge and understanding and ensure that capacity is in place to do so.

Key actions
Given the timeframe of the programme, KRCS needs to focus on roll out and application of existing SoPs rather than developing new ones. For those that are under development, focus should be on reviewing and finalising them;

KRCS needs to build additional internal technical capacity on CTP that can support CTP responses. This will free up HQ focal points to focus on more strategic work rather than being absorbed in implementation work;

There is need for KRCS to undertake a VfM analysis to get a better sense of how efficient CTP is as compared to in-kind support. It also needs to conduct a comparative analysis to better understand personnel cost savings achieved through use of local staff and its volunteer base;

To assess the programme’s efficiency KRCS needs to undertake a cost per beneficiary analysis and how it compares with other emergency interventions operating in similar regions.

Has the logframe been updated since the last review? No. The logframe was not updated during this review period.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased KRCS capacity to prepare for disasters
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
1.1 KRCS contingency plan developed and reviewed every 6 months	4	2	B
1.2 Number of risk-hazard bulletins shared internally and externally	10	10	A
1.3 KRCS has systems and procedures to manage the funds raised from the public in order to respond to disasters.	1	1	A
1.4 Number of KRCS staff/volunteers (disaggregated by gender) trained and available to lead operations	110	114 (89 men & 25 women)	A

Key Points
This output primarily addresses preparedness at the operational level so as to improve the quality of response. As indicated above, good progress has been made across all the indicators. These deliverables are important to effectively support emergency preparedness, rather than just the response, thus offering better value for money in meeting ongoing and anticipated needs. This output is assessed to have met expectation and therefore scored an ‘A’.

1.1 Contingency Plans: In line with best practise, the plans were continuously monitored and underwent testing with field staff to ensure that lessons learnt were entrenched within them. During this review period, the multi-hazard contingency plan was developed and reviewed twice by KRCS. The development of an elections preparedness plan took place during the review period.

1.2 Number of risk-hazard bulletins shared internally and externally: The target of 10 bulletins was achieved. The bulletins were widely shared across KRCS and its volunteers. Following feedback, the bulletins were adjusted to link response interventions to the multi-hazard contingency plan.

1.3: KRCS has systems and procedures to manage the funds raised from the public in order to respond to disasters: The Disaster Fund guidelines were developed, reviewed and approved. The fund provides for quick response to small and medium disasters at the local level. It is expected that these will come into use once the application and fund management documents are made available. Once operational these will be reviewed annually.

1.4: Number of KRCS staff/volunteers (disaggregated by gender) trained and available to lead operations: Of the 114 trained by KRCS to lead operations, 28% were women. In place are clear roles and responsibilities for response leaders at the national, regional and branch level. Mentorship sessions have begun in a number of county branches aimed at preparing other responders to take up leadership roles in emergencies. This is an improvement of 22% as compared to the last reporting period.

The trainings (knowledge and skills) provided by KRCS to its volunteers referred to as the Red Cross Action Teams (RCATs), have helped to professionalise responders from a collection of individuals into teams. However, there have been challenges providing them with the necessary equipment (protective gear) and resources required for an effective response.

Summary of responses to issues raised in previous annual reviews (where relevant)
The process of developing or revising contingency plans should include the regional and county KRCS offices branches and where this is not possible, proactive efforts should be made to sensitise the branches on the existence and contents of the contingency plan.
There has been a sustained effort to involve other branches of KRCS in the development of contingency plans. The election preparedness plan was developed following wide consultation across KRCS HQ and at branch level. Indeed a section of respondents from the online survey said their plans were adapted to county contexts.
Recommendations
It is important that the RCAT’s majority of who are the first responders are continually motivated. KRCS need to consider undertaking a review of the trainings offered to RCAT’s to ensure that they are appropriate and ‘fit for purpose’. KRCS need to ensure that all RCAT’s are provided with the requisite equipment (protective clothing) and resources (funds) needed for an effective response.

Output Title	Increased KRCS response efficiency (time, money) and accountability
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
2.1 KRCS has approved disaster response SOPs that it applies in emergencies.	SOPs developed.	5	A
2.2 Percentage of post-assessment responses which target the needs of 600 or more people where a formal feedback/complaint mechanism is set-up and implemented.	40%	33%	B
2.3 Percentage of post assessments responses which target 600 or more people where aspects of value for money is analysed.	50%	22%	C

Key Points
This output puts emphasis on the management of an efficient response, from pre-disaster to post-disaster. This is done internally through the use of SOPs to guide the response and externally through feedback from beneficiaries. Continuous learning and value for money is embedded throughout these stages.

Whilst good progress has been attained under indicator 2.1, progress against the other two indicators has not been as good. The complaints and feedback guidelines were approved and shared, but assessments are lagging behind. In this regard this output is assessed to have scored a ‘B’ outputs moderately did not meet expectation.
Indicator 2.1 KRCS has approved disaster response SOPs that it applies in emergencies: There has been an improved clarity on roles and responsibilities that has been achieved through continuous dissemination sessions. However, there is need for better dissemination of the SOPs as they are not widely known across KRCS staff beyond HQs and its volunteers.
Indicator 2.2 Percentage of post-assessment responses which target the needs of 600 or more people where a formal feedback/complaint mechanism is set-up and implemented: 33% of KRCS guidelines for handling community complaints and feedback have been developed approved and shared. These are being implemented in the ongoing drought interventions. However, KRCS need to ensure that standardisation is taking place.

Indicator 2.3 Percentage of post assessments responses which target 600 or more people where aspects of value for money is analysed: KRCS developed a VfM matrix tool that was tested in 5 out of the 18 responses. Those tested related to responses under floods, el nino, cholera, chikungunya, drought and conflict. This represents a low uptake due to the fact that field teams did not have adequate time to engage with the tool and those who did found it difficult to understand due to its complexity.

Summary of responses to issues raised in previous annual reviews (where relevant)
There is need to revisit how the success of the VfM tool will be captured in the review of the programme.

The VfM tool has been invigorated to capture both qualitative and quantitative measures with the aim of learning to improve the effectiveness and efficiency of future responses.

Recommendations
There is need for KRCS to develop some ‘top tips’ on what makes a good assessment under different situations and share with its staff and volunteers. Further, the VfM tool analysis should link to other reviews and be used to form recommendations for KRCS to take forward. This would ensure that KRCS is learning holistically;

To increase usage of the VfM template, KRCS needs to consider making it more user friendly whilst drawing on best practice. It should build a pool of VfM ‘champions’ that could be drawn upon for support;

There is need for KRCS to standardise data collection for disaster responses, particularly for those targeting over 600 people.

Output Title	Increased sharing of learning from KRCS preparedness and response operations
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
3.1 Number of articles based on KRCS DM learning published in internal and external media	4	12	A++
3.2 Percentage of post-assessment-responses which target the needs of 600 or more people that are reviewed with reference to relevant DAC criteria	75%	44%	B
3.3 Number of fora (external) where KRCS DM lessons learned (positive and/or negative) are presented.	4	6	A+

Key Points
This output puts emphasis on learning and sharing in order to develop sound working practices that increase effectiveness. KRCS has exceeded the targets under indicators 3.1 and 3.3. However, indicator 3.2 has fallen below expectation by 31% for reasons beyond KRCS’s reach. This output is assessed to have moderately exceeded expectation and therefore scored an ‘A+’.
Indicator 3.1 Number of articles based on KRCS DM learning published in internal and external media: 4 external and 8 internal articles were published. Examples include; Lessons Learnt from CTP and Use of Technology to Engage with Communities affected under El Nino both of which were published in the International Federation of Red Cross and Red Crescent Societies (IFRC) website. KRCS Cash and Voucher Programming Process was published in the The Cash Learning Partnership (CaLP) website. The target of 4 was set against previous performance. In the first year (2015) no articles were published. In 2016, 4 articles were published against a target of 3. This performance was the basis of the target for 2017. The overachievement under this indicator (12 against a target of 4) demonstrates the great progress made in institutionalising learning and dissemination of lessons and experiences within the programme and KRCS in general.

Indicator 3.2 Percentage of post-assessment-responses which target the needs of 600 or more people that are reviewed with reference to relevant DAC criteria: During this review period KRCS responded to several disasters in which more than 600 people were affected. These included cholera, drought and floods. 8 out of the expected 18 were reviewed with reference to the Development Assistance Committee (DAC). The DAC evaluation criteria is an assessment that is used to determine the relevance of the response. Though KRCS has made some strides here they experienced challenges meeting the target due to the high cost, time and capacity required to evaluate using the DAC criteria. KRCS could consider sampling assessments under the DAC whilst considering the increased use of After Action Reviews (AAR) for the others.

Indicator 3.3 Number of fora (external) where KRCS DM lessons learned (positive and/or negative) are presented. Over the programme period six lessons were presented. These were; (1) Evaluating[1] in Conflict and Fragile States; a case of KRCS, presented at the 8th African Evaluation Association International Conference, Kampala, Uganda in March 2017, (2) Institutionalization of CTP presented at the CaLP East Africa Learning Event, Nairobi in December 2015, (3) El Nino Preparedness: Case Study on Seed Distribution in Kitui: Preliminary Findings, presented to the Kitui County Government in June 2015, (4) Gaps underpinning Disaster Management Programming, Progress and Challenges to Date presented at the Kenya informal donor group meeting in June 2015 and (6) From Preparedness to Rapid Emergency Cash Transfer Programming: Lessons Learnt by KRCS in the Huruma & Mukuru Floods Response, presented to CaLP level 2 training participants in Harare, Zimbabwe in July 2016. This indicator had positive impact on how KRCS improved on its responses; for example under the drought response, there was streamlined registration in subsequent responses following lessons learnt in Ganze, thus ensuring that the right people benefited.
[1] The paper explored the experiences by KRCS response teams during the twin epidemic (cholera & Chikungunya outbreak) in Mandera County.

Summary of responses to issues raised in previous annual reviews (where relevant)
Progress on DAC evaluations is slow and there is need to not only consider how to improve this, but also to ensure that lessons learnt are fed into subsequent planning and responses.

DAC evaluations are costly (c. £15,000 each) and take time. Because of this, KRCS have instituted AARs which are faster to conduct and don’t cost much beyond staff time. The AARs guidelines include some DAC criteria but are not as detailed.

Recommendations
There is need for KRCS to streamline and strengthen its data collection and learning across its different offices, staffing levels and its volunteer base in order to continuously improve on its practices. For example sharing learning on good practice between RCAT’s, sharing lessons from simulation exercises and harmonising data held in the EoC database with that held by the disaster management operations team.

Using the DAC evaluation standard would be ideal. However, KRCS is experiencing difficulties with this due to the challenges raised above. KRCS should consider sampling a few that provide the essential quality assurance required rather than evaluate all. Additionally, KRCS should be encouraged to further strengthen the AAR practice.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers during this reporting period were, costs related to drought response (29%), personnel costs (22%) training and simulation (16%).

Drought response: KRCS responded to drought in Mandera, Wajir, Garissa, Isiolo, Samburu, Turkana, Kwale, West Pokot and Kilifi counties. In total KRCS reached over 750,000 people. It is noted that these areas are amongst the hardest to reach in Kenya, thus the cost of delivery, monitoring and identification of beneficiaries is expected to be higher. To manage these costs the programme applied a mixed approach in the delivery of the cash to mitigate against high delivery costs. Thus a variation of delivery channels (Mpesa or bank transfers) based on context was applied.

Personnel costs (salaries): KRCS has managed these costs by leveraging on local knowledge, hiring national staff and relying on thousands of volunteers to support programme delivery.

Training and simulation: This has consistently remained one of the biggest cost drivers on the programme. This programme is about building the capacity of the KRCS staff and volunteers to respond optimally to emergencies. A timely response will reduce the risk of prolonged suffering for those in need. KRCS has a wide geographical reach with a presence in each of the 47 counties in Kenya providing multi-sectoral responses. It has a volunteer base of over 100,000 people. Thus a high investment is required here. To manage these costs KRCS used planned regional coordination meetings to disseminate SOPs, thus saving on time and cost and use of KRCS facilities for training.

Within the year, gains that have been made include:-

Economy:	Savings were realised through effective procurement practices. For example, under the CTP, KRCS negotiated transfer fees downwards to £0.1 from £.0.2 thus realising absolute savings of £1.5 K.

Efficiency:	KRCS used bulk SMS messaging to communicate with people facing imminent disaster by advising them to relocate to safer grounds thus saving lives and costs. In Mathare a total of 576 families affected by fire received these, thus supporting an effective response mechanism. Joined up KIRA trainings further reduced duplication of effort by partners.

Cost
Effectiveness:	Additional funding amounting to £950K was leveraged from donors and Corporates to support disaster response. Through KRCS’s advocacy and influencing, GoK and its agencies are beginning to take their rightful role in leading coordination and disaster management responses thus ensuring sustainability at programme’s exit.

Equity:	CTP targeting focused on gender aspects. More women were included on the programme through their selection as cash recipients thus ensured gender sensitive programming. To ensure that the preparedness and responses made even greater impact efforts were made to take into account differing impact of the same on women, girls, boys and men, the elderly, disabled and marginalized. For example the drought response targeting criteria considered vulnerability.

Assessment of whether the programme continues to represent value for money
Overall the programme continues to represent good value for money based on adequate and satisfactory VfM metrics and practices; some indication of cost savings; and a valid and consistent theory of change.

Quality of financial management
Overall, financial management during the annual review period was satisfactory. BRCS demonstrated good oversight of spending by KRCS. Quarterly expenditure reports were provided to DFID that formed the basis of release of funds. The reports clearly specified expenditure incurred by the multiple donor partners under the various budget lines. Programme spend to date is on track and stands at 81% (£1,426,000).

The programmme’s independent annual audited statement for the period 1 January to 31 December 2016 was unqualified. Thus giving assurance that DFID funds were utilised well.

In July 2017, the programme received an additional pre-approved £1.5 million IRF to facilitate timely emergency preparedness and response. £300K of these funds were used for election preparedness. Following the increase in budget, DFID conducted a refreshed due diligence assessment that re-confirmed that KRCS has adequate systems in place. Its overall risk rating was ‘moderate’. There were no outstanding audit actions from the previous assessment.

The overall fiduciary risk rating is ‘moderate’.

Date of last narrative financial report	June 2017
Date of last audited annual statement	April 2017

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

Overall risk rating: Moderate
Output 1: Moderate
Output 2: Moderate
Output 3: Moderate

Overview of programme risk
The overall risk rating on the programme is ‘moderate’. The main risks are:-

Risk of cash not reaching intended beneficiaries: This risk was flagged during the last review period. During this review period KRCS built robust systems to alleviate this risk.

Capacity to implement CTP: There are capacity gaps within KRCS in terms of applying CTP. Knowledge on this is limited to HQ staff and some members of SMT have not bought into it. KRCS needs to build capacity across the organisation and get SMT buy in on the CTP concept. This will ensure that positive progress made so far is not eroded.

Election related violence: Kenya experienced a relatively peaceful August General Election. However, the Supreme Court’s nullification of the Presidential election and the withdrawal of the main opposition coalition in the Presidential repeat election has created political uncertainty. There are heightened tensions across the country and if not managed well may lead to mass displacement and injury. DFID has supported KRCS to pre-position response resources. In the event that demand exceeds this, DFID is prepared to step up its support depending on need and availability of resources.

Poor alignment and coordination: The KIRA framework allows for a more coordinated emergency response. However, there is need for stepped up collaboration amongst national and county governments; and with key humanitarian stakeholders. Currently, partnerships have been established within the KIRA MOU, but this has not fully been translated into practise. GoK needs to firmly take lead and drive the KIRA framework forward to ensure that it is functional.

Outstanding actions from risk assessment: None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The results specified in the logframe are on track to be delivered by the end of the programme.

Performance of partnership (s)
BRCS is responsible for the management of KRCS whilst KRCS is responsible for the implementation and results management on the programme. Working relationships are good between BRCS, KRCS and DFID. KRCS has expressed appreciation of the technical expertise provided by BRCS. A culture of openness in discussing risks and challenges has been embedded within the programme. All parties have demonstrated a good response record in all matters. Collaboration in country is with ECHO. The other donors do not have presence in country.

Overall, implementation has been timely and of high quality, notwithstanding a slowdown in some activities experienced due to staff movements and staff turnover. Procurement delays were also experienced. KRCS managed this by realigning key staff during transition periods and provision of uniform procurement guidance for similar commodities.

Asset monitoring and control
BRCS and KRCS do not have any DFID assets under this programme.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
EPRP does not use government financial systems for delivering DFID’s results. DFID Kenya has judged that the partnership principles do not apply in the detailed management and monitoring of this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme’s logframe has been used to review the results. The results have been triangulated using field visits, quarterly reports and the independent mid-term evaluation on the programme. Though DFID staff did not undertake field visits specifically for this annual review, they have done through the course of the year to (i) validate the data provided by KRCS and ii) gather feedback from beneficiaries. The DFID programme team have had and continue to have regular meetings with KRCS to discuss progress and risks and continue to collaborate with ECHO.

Monitoring progress throughout the review period
This annual review was desk based and undertaken by DFID Kenya’s Humanitarian Adviser Team Leader and the Senior Humanitarian Programme Officer. The DFID programme management team made the judgement to conduct a desk-based review in this instance, given the intensive field visits undertaken in the lead up to the last annual review and field visits undertaken so far during this year. Further an independent evaluation on the programme took place with a positive outcome. Field visits will be undertaken during Project Completion Review (PCR) in early 2018.