Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA) – Phase 1 & 2
Programme Value: £50m		Review Date: October 2017
Programme Code: 200706	Start Date: 01/10/2010	End Date: 31/12/2018

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	A	A	A	A+	A+	A+
Risk Rating	Low	Low	Medium	Low	Minor	Moderate

Summary of progress and lessons learnt since last review

The project has supported the delivery of 120 million treatments by the end of August 2017, with all 10 countries having undertaken a minimum of 2 rounds of mass drug administrations (MDA) as per WHO Guidelines. This programme is managed by the Schistosomiasis Control Initiative (SCI) based at Imperial College. All Phase I countries have reached national coverage with the exception of Liberia which recommenced treatment at scale in June 2016 after the suspension of all routine health services during the Ebola epidemic. Of the Phase II countries, Ethiopia has also reached national scale and MDA continues to expand geographically in DRC.
The DFID Payment by Results (PBR) target, measurable at the end of June each year, was set for 2017 at 114.8 million treatments. Despite severe delays in drug delivery by contracted manufacturers and resulting treatment postponement as a consequence in Malawi, the PBR target has been met.
The WHO target of reaching at least 75% coverage of school-aged children (SAC) is being met in 4 countries whilst the other countries are exceeding 70% coverage. This target has been confirmed through an increase in coverage evaluation surveys, all 10 countries have had at least one survey conducted. Health impact in terms of reductions in mean intensity and heavy intensity of infection have been observed across the ICOSA countries though in some countries this has not met the impact target. Where infections levels are low, following multiple rounds of treatment, current sampling strategies are being revised by SCI to ensure robust impact monitoring. Financial forecasting remains challenging.
Lessons learnt include:
-slow start up in a number of countries which are now delivering well,
-the importance of reaching out of school children
-the importance of working closely with all partners including WHO
-importance of building sustainability
-Importance of working closely with the water and sanitation sector
Response to Recommendations from 2016 Annual Review
Following the 2016 DFID annual review, a number of recommendations for project improvements were made. A summary of the responses to each recommendation are included in Table 1 and are further elaborated within the text of this report.During FY7, an audit of SCI was also conducted by KPMG and SCI continues to address all recommendations to ensure operational efficiency, transparency and continued project success. Arrangements are being put in place to to receive a copy of the audit report.
Table 1: Recommendations from Annual Review 2016
Category	Recommendation	Response
Governance	It is recommended that SCI finalise a governance structure that ensures the appropriate level of support and oversight within Imperial to continue the improvements it has made in financial management, audit and the development and documentation of risk mitigation strategies.	SCI has reviewed its governance structure and put in place 3 advisory committees that report to the Advisory Board. The committees comprise of international experts and senior members of Imperial College to focus on providing advice and developing mitigation strategies on operational, scientific and technical and fundraising and advocacy issues. There has been an excellent level of engagement from the members of all committees which has provided significant value to SCI.
Value for Money	It is recommended that SCI work with World Health Organisation NTD Department on value for money, domestic investment and the VfM partnership group continue to be a priority.	SCI have continued to collaborate with WHO and NTD partners through the Investment for Impact working group of the WHO which met in April 2017 in Geneva.
Forecasting and Risk Management	It is recommended that the monthly meetings with DFID around financial forecasting continue especially around mitigating risk at the end of the financial year and ensuring that the communication around budgets between SCI, Crown Agents and DFID is smooth and transparent.	SCI has further engaged with Imperial College Risk Management processes and will aim to further improve its risk assessment and development of mitigation strategies at the country, project and organisation level. SCI will continue to convene monthly meetings and work to further facilitate communication between ICOSA partners. SCI profiled the countries to prioritise the top five with the highest risk scoring based on the criteria of; scale of the program and the number of treatments, the annual budget, the level of corruption perception as per the transparency international index and the level of security. The top 5 countries will be visited by the finance team for review purposes.
Country Level Assessment	It is recommended that SCI with Imperial College’s Support carry out country level audits so they can work to build financial capacity at a country level. The recruitment of a financial director has made this possible.	SCI has developed a financial management assessment tool that has been reviewed by SCI and Imperial financial teams. This is being piloted in the ICOSA-supported countries of Malawi, Ethiopia and Liberia. The same tool was tested by KPMG in Niger in Sept 2017 during an audit visit and we are waiting for recommendations from KPMG.
Visibility	It is recommended that SCI work with DFID on a communication plan to ensure good visibility of DFID within country and in the UK	SCI has recruited an experienced communications manager with extensive experience in the health care sector to assist SCI to improve the visibility of ICOSA and other projects. SCI led the development of communications materials outlining the successes of DFIDs NTD investments that were distributed at the NTD summit. In addition SCI is contributing case studies to be included in the Uniting to Combat NTDs 5th Scorecard report which will have a large readership. SCI is further developing its internal communications strategy in line with a wider strategic review.
Collaboration	It is recommended that SCI continue to take lead in collaborating with partners (such as USAID & RTI) to help coordinating Praziquantel donation programme with WHO.	SCI continues to work closely with WHO (as part of the Working Group for Access to Quality Medications) and liaises regularly with USAID and Merck to ensure coordination of the supply of PZQ. As a result of these discussions, WHO has committed to providing the PZQ required for all SAC in ICOSA-supported countries with DFID purchasing PZQ for the adult populations and to fill intermediate gaps in the supply chain as countries transition to receiving donated medications.
Lessons Learned	It is recommended that work continues to be developed on sharing lessons learned from the programme so far, to inform ongoing progress and to communicate to other programmes where these are transferrable	SCI has used the platform of the NTD NGO Network (NNN) conference to disseminate lessons learned. In addition to SCIs Executive Director chairing the meeting of around 300 delegates, SCI led workshops on sustainable programmes, gender equity and integration with the WASH sector. SCI will also aim to convene another DFID partners knowledge sharing seminar in the next financial year.
Output 1	No further outputs or activities should be recorded for output 1. The scoring may then need to change across all other projects for 2017 annual review, otherwise next year’s review will score an output that has not delivered outputs. This will be reflected in an updated logframe and scoring	SCI has up-dated the log frame in accordance with this recommendation.

Summary of recommendations for the next year

There is an urgent need for stronger financial management and forecasting. This should be clearly tracked on a month-by-month basis and included as part of regular financial reporting to DFID

SCI to provide a visibility statement of how and when they will acknowledge funding from DFID and where they will use the UK aid logo – this should be in line with the latest DFID guidance on branding available on DFID website. The reference to visibility should be made in progress reports and annual reviews
 Consider why despite reaching high coverage levels the intensity of infection in some countries has not fallen as much as anticipated.

SCI should continue to work with partners to ensure adequate quality drugs to treat school aged children and vulnerable adults.

There remain many outstanding policy questions on schistosomiasis and SCI have much evidence to contribute to resolving these issues. SCI should actively engage with WHO and other partners to improve the situation.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4127168.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4708186.xlsx

In October 2010, DFID provided £25 million to deliver treatments for schistosomiasis (SCH) and intestinal helminths (STH) in 8 countries in sub-Saharan Africa (Phase I). Of the £25 million, £14.5 million was allocated to Crown Agents largely for the procurement of praziquantel (PZQ), with £10.5 million provided to the Schistosomiasis Control Initiative (SCI) to provide technical support to the national control programmes within the countries for the delivery of treatment through preventative chemotherapy (PCT). In June 2014, DFID increased the ICOSA project by an additional £25 million (Phase II) to expand the scope of the project within the currently supported countries and to include 2 further countries in the portfolio. Of the £25 million, SCI received an award of £16.6 million with the remaining allocated to Crown Agents for any necessary procurement. The project additionally leverages the increased donation of PZQ by Merck, available to countries by application through the World Health Organization (WHO).
The implementation of this programme involves close cooperation with country governments, particularly Ministries of Health and Education. In all countries, the Ministry of Health works with the WHO to develop a national strategic plan for NTDs which outlines their context-specific strategic approach to controlling and eliminating NTDs, through integration where feasible. The plan typically lasts for 5 years and provides an indicative budget to support the implementation of all activities. Any partners wishing to support NTD activities are encouraged to align their support within this framework to ensure strong Government commitment and country ownership. The ICOSA project participates in annual stakeholder meetings in each country to ensure this alignment and provide financing to support endemic country Governments to meet their objectives. Such partnership working additionally allows countries to efficiently use the external resources made available to them.
Although this has significant advantages to the country for the optimisation of their national NTD programme, there can be challenges in terms of timelines such as budgeting to the different fiscal years of donors and reporting against these different cycles. The project mitigates this where feasible by, for example, aligning to the recipient Government fiscal year such as in Ethiopia. Of the 10 countries that benefit from the programme, eight are priority countries for DFID.

Recipient countries are Cote d’Ivoire, Democratic Republic of Congo (DRC; Phase II), Ethiopia (Phase II), Liberia, Malawi, Mozambique, Niger, Tanzania (including Zanzibar), Zambia and Uganda. The Ministry of Health programme in Mozambique receives direct management support through the Centre for NTDs, Liverpool School of Tropical Medicine under a sub-contract with Imperial College, although SCI and LSTM are aligned in interventions in DRC, Liberia, Tanzania and Zambia. Additional funding for country programmes continues to be successfully leveraged with grants from END Fund and the Childrens Investment Fund Foundation (CIFF); in addition to donations to SCI as a result of the ongoing recommendation of GiveWell, which considers SCI as one of the top two charities to invest in globally.
ICOSA commenced in October 2010 and has now been extended with Phase II until December 2018. The project is currently in Financial Year 8 (FY8; 1st April 2017 – 31st March 2018) after 83 months of operation by August 2017. There are two types of schistosomiasis– schistosomiasis mansoni and schistosomiasis haematobium.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The impact of the project will be to contribute to the achievement of the human-development-related Millennium Development Goals (MDGs) and the Sustainable Development Goals (SDGs) through the control and treatment of schistosomiasis (SCH) and soil-transmitted helminths (STH). There are two indicators at impact level.

Impact Indicator 1: Mean Intensity of Infection

Impact indicator 1 relates to the health impact of the project by measuring the reduction of intensity of infection over time. Intensity of SCH infection is an accepted proxy for disease morbidity[1]; therefore regular collection of this data gives a direct measurement of the effects of treatment on the occurrence of infection and an indirect measurement of the effectiveness of treatment in improving health status[2]. Intensity is measured as the number of eggs per gram of faeces (epg) for Schistosoma mansoni and as the number of eggs per 10 ml of urine (eggs/10ml) for S. haematobium.
[1] Van der Werf et al (2003) Quantification of clinical morbidity associated with schistosome infection in sub-Saharan Africa. Acta Tropica 86:125-139
[2] Helminth Control in School-Aged Children, 2nd Edition, World Health Organization ISBN9789241548267.
Intensity data are collected through cross-sectional parasitological surveys from a sample of school aged children (SAC) in sentinel schools. The same age and gender groups are successively followed-up pre- (at baseline) and post treatment.
IMPACT Indicator	Milestone	Baseline data	Achieved
	by end 2017		by July 2017
1. Mean intensity of infection in treated areas	Baseline conducted in all Phase I countries ready to commence PC / Post 1 round of PC / S. mansoni (Sm): / 50% reduction from baseline / S. haematobium (Sh): / 65% reduction from baseline (rfb) / Post 2 rounds of PC: / Sm: 55% rfb / Sh: 68% rfb / Post 3 rounds of PC: / Sm: 60% rfb / Sh: 70% rfb / Post 4 rounds of PC: / Sm: 65% rfb / Sh: 75% rfb	Cote d’Ivoire / (2013 Phase 1)	Post 1 round of PC (2015):
		Sm = 33.94 epg	Sm = 27.86 epg (39.4% rfb)
		Sh = 5.96 e/10ml	Sh = 4.66 e/10ml (22.1% rfb)

		(2015 Phase 2)
		Sm = 6.78 epg
		Sh = 5.91 e/10ml
		DRC (2015):	Post 1 round of PC (2015):
		Sm = 58.6 epg	cleaned and under analysis
		Sh = 5.1 e/10ml
		Ethiopia (2015):	Post 1 round of PC (2016):
		Sm = 8.97 epg / (10.36 epg for FY1 schools) Sh = 0.024 eggs/10ml / (0.068 eggs/10ml for FY1 schools)	For 146 out of 175 schools: Sm = 5.54 epg (46.5% rfb) Sh = 0.007 eggs/10ml (89.7% rfb)
		Liberia (2012):	Post 1 round of PC (2014):
		Sm = 16.32 epg	Sm = 16.78 epg (-2.8% rfb)
		Sh = 42.36 eggs/10ml	Sh = 6.97e/10ml (83.6% rfb)
		Malawi (2012):	Post 1 round of PC (2014):
		Sm = 1.89 epg	Sm = 0.06 epg (96.8% rfb)
		Sh = 4.30 eggs/10ml	Sh = 1.73 e/10ml (59.8% rfb)
			Post 2 rounds PC (2015):
			Sm = 0.72 epg (61.8% rfb)
			Sh = 1.07 e/10ml (75.0% rfb)
			Post 3 rounds PC (2016):
			Sm = 0.82 epg (55.8% rfb)
			Sh = 1.41 e/10ml (67.3% rfb)
			Post 4 rounds PC (2017): / cleaned and under analysis
		Mozambique (2013/4)
		Sm = 0.53 epg	Reassessment surveys
		Sh = 28.59 eggs/10ml	Scheduled for FY8
		Tanzania (2013)*:
		Sm = 29.47 epg
		Sh = 1.85 eggs/10ml
		new baseline (2016)**	Post 1 round of PC (2017):
		Sm = 2.31 epg	Sm = 5.36 epg (-132% rbf)
		Sh = 2.33 eggs/10ml	Sh = 0.01 eggs/10ml (99% rfb)
		Zambia (2013):
		Sm = 2.36 epg	Post 2 rounds of PC
		Sh = 9.20 eggs/10ml	Scheduled for FY8

* No further data collected from original 2013 baseline as, in 2014 there was no treatment and no surveys; in 2015 there was treatment but no surveys due to late arrival of funds.
** New baseline in regions not treated for 8 years

Key Points
Baseline data collection in sentinel schools, to measure impact, has been completed in all ICOSA-supported countries. Based on post-treatment follow-up surveys, impact of preventive chemotherapy (PC) is being achieved through the reduction of intensity of infection. Milestones have been met in Ethiopia, Liberia, Tanzania and Malawi for S. haematobium. A reduction in intensity of infection was also observed in Cote d’Ivoire, and was statistically significant, but did not meet the target. The results are being analysed for DRC. There are no data for Mozambique and Zambia.

Milestones have been met in Malawi and Ethiopia for S. mansoni. A reduction in intensity of infection was also observed milestone in Cote d’Ivoire, and was statistically significant, but did not meet the target. In Liberia and Tanzania there was an increase in mean intensity of infection, however, as the number of individuals infected with S. mansoni and level of intensity are so low, small absolute increases in intensity result in large relative increases. We will continue to monitor in these countries. The results are being analysed for DRC. There are no data for Mozambique and Zambia.
Specific updates for 2017 are:
  - Côte d’Ivoire, by the end of FY8 Côte d’Ivoire will have completed post-2 round of PC data collection in all phases. From the post 1 round (phase 1) results we saw statistically significant reductions in S. mansoni infection from baseline by 39.4%. The mean intensity of S. haematobium infections also reduced by 22.1% from baseline.
  - DRC, post-1 round PC survey data cleaning and analysis and a second round of baseline data, following expansion of the programme, are underway. Post-2 rounds surveys are scheduled for late FY8.
  - Ethiopia, has 175 sentinel sites in total. Due to the size of the programme impact surveys are conducted in phases. At this time results are available for 146 schools and after one round of treatment the average intensity of S. mansoni infection reduced by 46.5% from baseline. S. haematobium is less prevalent across the country than S. mansoni. Average intensity of infection for S. haematobium reduced by 89.7% from 0.068 eggs/10ml at baseline to 0.007 eggs/10ml following one round of treatment.
  - Liberia, following the Ebola induced hiatus and decision by the MoH and SCI to leave at least one year before human sampling was conducted, post-2 rounds of treatment data collection will take place in late FY8.
  - Malawi, is continuing to be in the target range for reductions in intensity from baseline post-3 rounds of PC and post-4 rounds of PC are currently being cleaned and analysed.
  - Tanzania, selected 40 new sentinel sites with baseline data collection occurring in 2016, in an area that had not had treatment since 2008. After one round of (current) treatment the mean intensity of S. mansoni increased by 132% from baseline, going from 2.31 epg to 5.36 epg. The overall intensity of infection was low at baseline thus even small absolute increases result in large a relative increase. S. haematobium reduced by 99% from baseline going from 2.33 eggs/10ml at baseline to 0.01 eggs/10ml at FY1.
  - In Mozambique and Zambia, following the establishment of the baseline sentinel schools, further data collections (Mozambique) have not followed protocol or have not happened at all (Mozambique and Zambia). In Mozambique, SCI is working with partners LSTM and MoH to establish impact over time through reassessment surveys. The first phase of these scheduled for October 2017 has been postponed due to CA not delivering the necessary equipment in time. Follow-up in Zambia has not been possible due to lack of in country commitment to the programme and subsequent effects on contracts and treatments. DFID will consider with SCI how to take forward data collection in Mozambique and Zambia.
- Timely uptake of survey results for more efficient and effective planning and implementation by six of national MoH programmes have been supported by the continued uptake of SCI’s MER tools and pre and post-survey processes. The tools – Dashboards and Recommendations Reports – allow for rapid interpretation of the survey results and knowledge in to practice by the MoH, supported by SCI. For example, impact survey results in Malawi have indicated the need to reassess prevalence of schistosomiasis in regions of the country which will lead to reduced and more targeted treatments under the national programme.

Impact Indicator 2: Validated Treatment Coverage
The project is making an impact by reducing prevalence and intensity of infection and preventing progression of morbidity in infected individuals who are treated. Impact of the project is, therefore, also determined by the number of individuals receiving the tablets for schistosomiasis (SCH) and soil transmitted helminths (STH) out of the eligible population, i.e. the treatment coverage. In line with WHO Guidelines, the target coverage for deworming programmes is 75% in SAC for both PZQ and ALB (WHO, 2011). If high drug coverage is not attained, untreated individuals could potentially act as reservoirs of transmission, hindering control and elimination efforts. Each country collects and submits reported drug coverage, calculated using the number of doses distributed during a round of PC recorded in treatment registers for the numerator, and population figures (often obtained from census population figures) as the denominator. This routine reported coverage can be unreliable due to the overestimation and at times underestimation, of the numbers of individuals treated and also because of out of date and inconsistent projections of eligible populations. In addition, these reported numbers do not include gender disaggregated data to understand if equity is being achieved in the programmes.
The ICOSA programme oversees independent post-treatment coverage surveys to give a more precise estimate on the number of SAC and adults receiving treatment. These household-based multi-stage cluster surveys, ensure that the coverage data reflect the treatment at the school and community-level and allow for the results to be disaggregated by age (SAC or adults) and gender.

IMPACT Indicator	Milestone	Achieved
	by end 2017	By Aug 2017
2. Validated treatment coverage in school-aged children (5-14 years) (disaggregated by gender) by country	Post 1 round of PC: / at least 70% / Post 2 rounds of PC: / at least 70% / Post 3 rounds of PC: / at least 75% / Post ≥3 rounds of PC: / at least 75%	Cote d’Ivoire:
		Post 1 round PC (2014): 80.6% female; 79.0% male
		Post 1 to 3 rounds PC7 (2016): 73.3% female, 69.2% male
		Liberia
		Post 1 round (2017): 71.8% female, 74.1% male
		Ethiopia:
		Post 1 round PC (2015): 84.0% female; 84.7% male
		Post 2 round PC (2016): 44.5% female, 46.6% male
		Post 3 rounds PC (2017): 82.9% female, 82.8% male
		Malawi:
		Post 1 round PC (2012): 75.9% female; 79.9% male
		Post 2 rounds PC (2014): 78.3% female; 78.7% male
		Post 4 rounds PC (2016): 86.3% female, 82.7% male
		Mozambique:
		Post 3 rounds PC (2015): 83.0% female; 81.0% male / Post 4 rounds PC (2016): 89.0% female; 66.0% male
		Niger
		Post >10 round PC (2017): 78.5% female, 70.5% male
		Uganda:
		Post 1 round PC (2014): 35.7% female; 36.2% male
		Post >10 rounds PC (2016): 83.2% female; 85.5% male
		Zambia:
		Post 1 round PC (2015): 91.8% female; 91.2% male
		Zanzibar:
		Post 1 round PC (2012): 75.0%*
		Post 2 rounds PC (2013): 85.1%*
		Post 3 rounds PC (2013): 87.3%*
		Post 5 rounds PC (2014): 72.0%*
		Post 6 rounds PC (2015): 80.8% female, 77.9% male
		Post 8 rounds PC (2016): 86.0%*

*Government of Zanzibar’s own post-MDA coverage survey which does not disaggregate by gender. N.B. Zanzibar conduct biannual treatment for schistosomiasis according to their national strategic plan for elimination. In 2015 ICOSA supported an independent coverage validation survey.

Key Points
- The results from the validated coverage surveys undertaken in 2016 and 2017 indicate that in 4 out of the 11 ICOSA countries the WHO target for SAC treatment coverage (75%) was exceeded. In 6 out of the 11 countries the ICOSA targets (70% to 75%) have been met.
- ICOSA programme results continue to critically highlight that gender is not a barrier for equitable treatment access through the school-based MDA platform. Multi-stage cluster sampling household surveys conducted by SCI ensure that any gender inequity in school enrolment does not bias the results.
- The new WHO Coverage Survey Guidelines, have been used in Ethiopia and Uganda. The surveys have been a success and there have been valuable learning in the new methodology for future surveys. In addition, feedback will also go back to WHO to strengthen their training tools.
- Niger and Liberia conducted their first post-MDA coverage surveys in 2016. In DRC coverage surveys are currently not possible due to political instability.
- The coverage surveys also enable programmes to pinpoint where routine treatment data are inaccurate. This has triggered the use of the new WHO Data Quality Assessment (DQA) tool which allows the MoH to evaluate their treatment reporting systems, highlight weaknesses and strengths and create actionable soultions. DQA surveys have taken place in Malawi, Ethiopia and Uganda and are scheduled to take place in Cote d’Ivoire, Liberia and Zanzibar in this financial year.

The outcome of the project will be to contribute to the WHO global strategic plan for SCH (2012-2020) by providing a total of 203.5 million treatments by end 2018.
By end August 2017, the project has delivered a total of 119.999 million treatments, in excess of the 114.8 million log frame target.
OUTCOME Indicator	Milestone by end 2017	Achieved / by end Aug 2017
Number of treatments delivered, in millions (cumulative)	114.8 million	119.999 million

Routine MDAs are taking place in all ICOSA-supported countries. In June 2016, Liberia restarted treatment following suspension of routine health services due to the Ebola outbreak such that all programmes delivered treatment during FY16-17. Programmes in all countries operate within the governance of the respective Ministry of Health as either vertical SCH/STH programmes, or as part of an integrated NTD programme.
Overall output score and description A

The programme is making good progress. It has met all the treatment milestones and SCI are confident that they will meet the end of project target, it will however require concerted effort as a large number of treatments still need to be delivered.

The project data is contributing to new knowledge and thinking on schistosomaisis and this needs to continue and where possible be enhanced.

Key lessons

The importance of having robust indicators of impact and not just measuring treatments given.

The importance of carrying out validation surveys and not only relying on reported coverage data.

Key actions

Final forecasting needs to improve substantially.

Given that the coverage surveys are reporting high coverage SCI should explore why the intensity of infection in some countries is not reducing as much as expected.

Ensure continuing effort to meet the treatment target.

Has the logframe been updated since the last review? Yes

The output milestones on percentage of population with heavy infections were changed in August 2016. The milestones are now in line with WHO guidelines, and report on the percentage of sentinel schools falling below the 5% threshold.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Priority areas identified through mapping of infected populations (Group 1&2 countries)
Output number per LF		1	Output Score	Unscored
Risk:		Minor	Impact weighting (%):	0
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y (output complete)

Indicator(s)	Milestones	Progress
1.1 Number of country specific mapping protocols available	8 available (including Phase II countries)	8 available (Phase II country protocols not developed through ICOSA) - ACHIEVED IN MARCH 2015
1.2 Target areas mapped for disease by country	100% all countries	100% all countries - ACHIEVED IN MARCH 2015

Key Points

Following the 2016 Annual Review, Output 1 was considered complete with no further activities to be recorded going forward therefore the report focuses on progress on the remaining Outputs 2-5.

Output Title	Drugs procured and delivered
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	75
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 No of tablets delivered to countries	387 million (including Phase I and II)	408.2 million / of which: / 212.5 million Crown Agents procured / 139.3 million donated by WHO / 56.8 million donated by other sources
2.2 No of countries implementing MDA according to their National Strategic Plans	8 countries	10 countries
2.3 DFID will monitor, and contribute to the effective management of the market for PZQ	Develop scope of work for report	Completed in 2016

Over 408 million tablets of PZQ had been delivered to countries of which over 212 million have been supplied directly by the project. A further 18.25 million tablets are currently on order through Crown Agents for FY17-18 with final orders to be completed on the basis of WHO donation allocations agreed in October 2017. The delivery of drugs across each of the countries by source is indicated in Table 2.

Key Points

- Supply of quality-assured PZQ continues to be essential. Following CIPLA’s success at becoming the first PZQ supplier to become prequalified by WHO, MacLeods also reached PQ status during 2017. In addition, 3 further manufacturers have received favourable ratings from the WHO Expert Review Group allowing Crown Agents to include them in framework agreements as potential suppliers. During FY16-17, a new supplier SKant was awarded and met all conditions on a contract for PZQ supply to Malawi.
- During FY16-17, PZQ delivery delays had significant programmatic impacts despite mitigation actions involving Crown Agents, SCI and DFID. 2 country programmes were therefore required to postpone their MDA campaigns (Malawi and Liberia) to ensure the treatment activities aligned with drug availability. As noted above, the supplier base has now been widened and this should help to prevent such delays.
- The project is successfully leveraging the WHO donation of PZQ with an increased quantity of donated medication being provided to project countries during FY16-17, including to countries which had sole-source supplies from the procurement channels of DFID and USAID.
- USAID no longer supplies PZQ for endemic countries within their portfolio. In addition, their financial support will only be provided for the delivery of WHO donated PZQ to SAC via a school-based platform. This has implications for countries who treat adult populations within their treatment programmes which will require both a source of funds and a source of procured medication.

Recommendations

Continue to engage with all partners to ensure adequate supplies of quality PZQ are available to countries.

Support countries to ensure that the PZQ ordered reflects the quantity likely to be distributed.

SCI to consider implications of changes to USAID approaches noted above and to recommend whether these can be addressed through the programme.

Output Title	National programmes using monitoring and evaluation results to refine strategies
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

OUTPUT 3	Milestone		Achieved by Aug-17
Indicators	by end 2017
3.1 Percentage of targeted districts submitting reports 90 days after MDA (Phase II Indicator)	80%				2014	2015		2016	2017
			Cote d'Ivoire		100%	0%		100%	100%
			DRC		30%	-		90%	57%
			Ethiopia		-	83.5%		Pending*	75%
			Liberia		100%	-		Pending*	100%
			Malawi		50%	100%		Pending*	100%
			Mozambique		100%	100%		100%	100%
			Niger		16%	43%		83%	73%
			Tanzania		70%	-		100%	100%
			Uganda		80%	90%		N/A	100%
			Zambia		tbc	100%		N/A	100%
			Zanzibar		100%	100%		100%	100%
3.2 Validated coverage of children not at school by gender	Post 1 round of PC: at least 70% Post 2 rounds of PC: at least 70% Post 3 rounds of PC: at least 75% Post ≥3 rounds of PC: at least 75%		Cote d’Ivoire:
			Post 1 to 3 rounds PC14 (2016) Females 43.1%, Males 37.4%
			Liberia
			Post 1 round PC (2017) Females 52.8%, Males 62.4%
			Ethiopia:
			Post 1 round PC (2015) Females 55.2%; Males 48.3%
			Post 2 rounds PC (2016) Females 21.7% ; Males 16.8%
			Post 3 rounds PC (2017) Females 28.7%, Males 33.1%
			Malawi:
			Post 1 round PC (2012): Females 14.8%; Males 15.5%
			Post 2 rounds PC (2014): Females 42.1%, Males 44.3%
			Post 3 rounds PC (2016): Females 31.1% , Males 25.6%
			Mozambique:
			Post 3 rounds PC (2015) 67%
			Post 4 rounds of PC (2016) 64%

			Niger
			Post 1 round PC (2017) Females 57.9%, Males 44.0%
			Uganda:
			Post 1 round PCT (2014): Females 5.5%, Males 1.0%
			Post 2 round PCT (2016): Females 72.5%, Males 69.6%
			Zambia:
			Post 1 round PCT (2015): Females 68.4%, Males 64.3%
			Zanzibar:
			Post 1 round PCT (2015): Female 66.7%, Male 67.0%
OUTPUT 3		Milestone					Achieved by
Indicators		by end 2017		Baseline			Aug-17
3.3 Percentage of population with heavy infections / (Group 1 & 2 countries)		Baseline: / Conducted in all countries / Post 1 round of PC: / 50% of sentinel schools <5% heavy intensity of infection / Post 2 rounds of PC: / 60% of sentinel schools <5% heavy intensity of infection / Post 3 rounds of PC: / 70% of sentinel schools <5% heavy intensity of infection / Post 4 rounds of PC: / 80% of sentinel schools <5% heavy intensity of infection / Post 5 rounds of PC: / 90% of sentinel schools <5% heavy intensity of infection		Cote d'Ivoire / Baseline (2013 & 2016) / Sm = 57%, Sh = 73%			Post 1 round of PC (2016) / Sh = 65%3
				DRC / Baseline (2014) / Sm = 55%, Sh = 45%			Post 1 round of PC (2015) / data awaiting in-country analysis
				Ethiopia / Baseline (2015) / Sm = 95%, Sh = 99% (Sm = 97%, Sh = 100% for FY1 schools)			Post 1 round of PC (2016) / Sm = 98%, Sh = 100%
				Liberia / Baseline (2012) / Sm = 82%, Sh = 32%			Post 1 round of PC (2014) / Sm = 58% Sh = 45%
				Malawi / Baseline (2012) / Sm = 56%, Sh = 18%			Post 1 round of PC (2014) / Sm = 88% Sh = 59% / Post 2 rounds of PC (2015) / Sm = 100% Sh = 73% / Post 3 rounds of PC (2016) / Sm = 88% Sh = 73% / Post 4 rounds PC (2017) / data cleaned and under analysis
				Mozambique / Baseline (2013/14) / Sm = 100%, Sh = 85%			Reassessment surveys / Scheduled for FY8
				Tanzania / Baseline (2012) / Sm = 96%, Sh = 81% / new baseline (2016)** Sm = 92.5%, Sh = 97.5%
				Zambia / Baseline (2013) / Sh = 91%, Sm = 69%			Post 2 rounds of PC / Scheduled for FY8

The WHO considers M&E as an integral component of any control programme. Suggested indicators for SCH and STH control programmes in SAC are grouped into 3 main categories; process, performance and impact. The process indicator for ICOSA measures the timely reporting of treatment numbers back to the central level after a treatment round. Performance indicators assess the success of the programme in reaching the target population, i.e. coverage. Within this output, ICOSA evaluates equitable access to treatment by gender and also by those children who do not attend school. Impact is measured according to improvement in health by the proxy indicator of reduction in heavy infections.

Key points
The percentage of implementation units reporting within a 90 day time-frame has continued to increase, for the majority of countries in 2016/7 and are exceeding ICOSA targets
The coverage surveys have continued to be pivotal in highlighting that we have high coverage and gender equity in those SAC attending school and that reaching non-attending SAC can be more of a challenge through existing platforms. All ICOSA programmes, excluding Tanzania and Zambia, have progressed from being solely school-based to having additional community outreach (community-based or door-to-door platforms) to increase programme reach in the non-attending SAC and high-risk adults. Tanzania and Zambia have made the decision to continue to use the school-based platform until they have sufficient resources to expand to the community. The programme is supporting Malawi and Uganda to try innovative strategies to increase coverage.

Recommendations
Continue to support countries to improve reporting
Ensure innovative strategies to improve coverage target the most vulnerable. Share lessons on findings.

Output Title	Elimination of SCH as a public health problem
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress: Achieved by July 2017
4.1 Transmission hotspots (areas with persistent transmission) treated with adjusted preventive chemotherapy (PC)	100% hotspots treated by adjusted PC	Niger: 100% hotspots treated by adjusted PC
		Zanzibar: 100% hotspots treated by adjusted PC
		Uganda: 100% hotspots treated by adjusted PC
4.2 Percentage of heavily infected individuals in areas with ≥6 rounds of PC	Post 1 round of PC: / 60% of sentinel sites <1% heavy intensity of infection / Post 2 rounds of PC: / 70% of sentinel sites <1% heavy intensity of infection / Post 3 rounds of PC: / 80% of sentinel sites <1% heavy intensity of infection	Niger / Baseline (2011) / Sh =57%, Sm = n/a	Post 1 round of PC (2012) / Sh= 73% / Post 2 rounds of PC (2013) / Sh= 63% / Post 3 rounds of PC (2014) / Sh= 71% / Post 4 rounds of PC (2015) / Sh=50% Sm=81%
		Uganda / Baseline (2013) / Sh = n/a, Sm = 99%	Post 1 round of PC (2015) / Sm= 100% / Post 2 rounds of PC (2017) / Survey in Oct-17
		Zanzibar / Baseline (2012) / Sh =tbc, Sm = n/a	Post 2 round of PC (2013) / Sh = 100% / Post 4 rounds of PC (2014) / Sh = 100% / Post 6 rounds of PC (2015) / Sh = 100% / Post 8 rounds of PC (2016) / Sh = 100%

Following the recognition of the long-term health impact of disease elimination outlined in the World Health Assembly Resolution 66.12 in May 2013, ICOSA is supporting the development of elimination strategies in Zanzibar, Uganda and Niger which have been undertaking MDA for over a decade.

Key points:
- As with output 3.3 this indicator has been adapted to be more in line with recent WHO guidelines and will now measure the percentage of sentinel sites with <1% heavy infection.
- Both Uganda and Zanzibar have achieved WHO targets for the reduction in heavy intensity of infection. Further reassessment surveys will be conducted to understand the current distribution of infection which will support our understanding of where hot spots, or areas of persistent high infection remain, and where resources need to be focused.
- SCI continues to partner with both the SCORE operational research project (University of Georgia) and the University of Glasgow to understand better what is happening in these areas and individuals with persistent high infection and what the possible programmatic solutions might be.
- In Niger, a reassessment survey in FY9 to determine the overall impact of the ICOSA programme and identify remaining foci of persistent infection.

Output Title	Value for Money Achieved
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	5
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Number of countries with financial cost per treatment determined	Costs determined in 8 countries	Costs determined in 9 countries
5.2 Direct financial cost per treatment within benchmark range[3]	6 countries achieving cost per treatment within benchmark range	Financial Year 7 / Cote d’Ivoire: £0.24 / DRC: £0.09 / Ethiopia: £0.18 / Liberia: £0.75 / Malawi: £0.10 / Niger: £0.11 / Tanzania: £0.22 / Uganda: £0.22 / Zanzibar: £0.21
[3] Fitzpatrick C et al. Benchmarking the cost per person of mass treatment for selected neglected tropical diseases: an approach based on literature review and meta-regression with web-based software application. Publication under peer review. https://healthy.shinyapps.io/benchmark/

Key points
- The ICOSA programme has demonstrated Value for Money (VfM) in FY7 for the 9 countries for which 6 have a full set of verified expenditure data from in-country and 3 have a combination of cashbook data and transfer records. Due to timings of treatments and completed cashbooks, cost per treatment is reported retrospectively i.e. for FY7 and not FY8.
- The financial processes and cashbook, which were designed to record all financial transactions at country level, continue to be implemented in all ICOSA countries directly managed by SCI in FY7 (not Zambia and Mozambique). The collection of complete financial information from several countries has improved dramatically, following the implementation of in-country training programmes and increased central SCI monitoring of financial reporting. Central SCI monitoring continues on a monthly basis to strengthen existing systems and ensure timely reporting of expenditure from in-country teams.
- The project has extended VfM analyses to include the majority of funding sources from SCI which contribute to the MoH treatments delivered, however, barriers to expenditure data sharing between partners and hence VfM analysis still exist and are part of ongoing collaborations and the DFID-partner VfM Working Group. As a result, SCI cannot present entirely accurate VfM results for countries with integrated programmes, such as Ethiopia and DRC, where expenditure funded by SCI doesn’t fully reflect the in-country activities that have involved different funding partners.
- A dashboard template of financial cost per treatment and other VfM metrics to aid MoH team and SCI programme manager in improving economic efficiency and cost-effectiveness has been developed. Over the next two months dashboards with the latest FY7 VfM analysis results along with recommendations reports will be produced for each ICOSA country.
- SCI are working with in-country teams to obtain better process data across ICOSA countries as currently only estimates are being reported and a standardised method for measuring number of people trained does not yet exist.
- Output indicator 5.2 has been adapted from milestones expecting to see costs per treatment decline over time as the ICOSA programme progressed. Reductions in cost per treatment may not be realised due to factors outside of the programme’s control (e.g. currency fluctuations, price of inputs like fuel increase, etc.) or due to strategic changes to the programme (e.g. changing target populations or delivery methods).
- As an alternative approach cost per treatment will be monitored against benchmark ranges published in a multi-country literature review of costs of MDAs for PC-NTDs.[4] These benchmarks are customisable using setting parameters that reflect country programme attributes. This feature makes the benchmark ranges a better indicator of a programme’s cost-effectiveness than historical comparisons.
  [4] Fitzpatrick C et al. Benchmarking the cost per person of mass treatment for selected neglected tropical diseases: an approach based on literature review and meta-regression with web-based software application. Publication under peer review. https://healthy.shinyapps.io/benchmark/
- Cost per treatments have shown variation over time. Variation has been due to:
    - treatment numbers and subsequent economies of scale i.e. where more individuals are treated the cost per person decreases;
    - changes in cost drivers, especially the inputs of per diems and fuel and the activities of training and activities of training and drug distribution. All of these cost drivers correspond directly to the population and geographic scale of the programme.
    - external influences (see key point above).

FY7 cost per treatment overview

* Countries presented in more detail in following section

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
As reported in previous reports, and consistent with published literature, financial resources in country are largely spent on per diems for government staff at the central, implementation unit (i.e. district), at the front-line health facility level and also to those that distribute the drugs, the teachers and CDDs. Per diems are generally aligned with government rates, but a short supply of skilled labour or higher rates paid by other agencies drives up costs particularly in remote areas. The next major input requiring financial resources varies by country and whether MDA is occurring that year, however fuel and travel are significant key costs. A widely spaced geographical area or difficult terrain increases the number of days of fieldwork, driving up costs. In line with other major NTD projects that deliver MDA, the key cost drivers for MDA are the campaign approach followed, the efficiency of the drug supply chain, and the frequency of impact surveys and surveillance. Security and location will be key cost drivers across all aspects of the programme (see also output 5).

SCI continues to play a leading role in the VFM Working Group with members from DFID partner organisations – Sightsavers and the Filarial Programmes Support Unit at Liverpool School of Tropical Medicine. The group has committed to developing a shared methodology for VFM analyses as well as exploring commonalities for assessing the wider impact of their programmes on equity. Successful outputs from the working group will make VFM metrics between organisations more comparable and transparent and will highlight the impact of the DFID investments on equity in the communities it serves.

Since the last annual report, there have been areas of progress for measuring VfM for the ICOSA programmes:
1. Further development of the VfM section of the financial cashbooks to ensure consistency and standardisation in expenditure data reporting across the ICOSA countries.
2. The standardisation of country level VfM analysis has enabled SCI to develop a tracker to monitor expenditure by activity type against treatment delivery dates.
3. The development of a protocol for collecting and reporting economic costs of ICOSA programmes, as current SCI VfM analysis reports financial costs only and economic costs are not systematically collected by SCI. These include opportunity costs of donated items (e.g. vehicles, ‘free’ use of building space, drugs), time allocated by MoH staff and time volunteered by community drug distributors (CDDs).

VfM performance compared to the original VfM proposition in the business case
Value for Money continues to be closely monitored. There are logframe indicators (output 5) focussed on VFM and the programme has implemented a standardised approach to VFM monitoring across all country programmes. The cost per DALY averted is calculated to be lower than the original propostion in the business case (see below). The project continues to compare well with the VFM proposition in the business case.

The interventions that are being supported are in line with the WHO strategy for schistosomiasis control - preventing morbidity in later life through regular treatment with praziquantel, which is currently the only recommended drug. Mass treatment is targeted at high risk groups. The high risk group targeted and the frequency of treatment depends on the prevalence of infection. This strategy is based on evidence from field trials and is continually being refined by operational research that informs national policy and planning.

Good evidence exists to support the cost effectiveness of individual components and the programme is expanding this evidence base. It is too early to detail quantitative assessment but ongoing work and the development of a standardised approach to VfM will enable a fuller analysis at a later date.

Assessment of whether the programme continues to represent value for money
Overall, the programme continues to be good value for money.

The programme is collecting the following VFM metrics:

VFM Criteria	VFM Metric
Equity	Non-attending children being reached
	Girls (and women) being reached
Effectiveness (Cost-effectiveness)	Cost per treatment delivered
	Cost per DALY averted
Efficiency	Cost per person trained
	Treatments delivered per drug distributor
	Workplan and budget implemented on time
Economy	Cost of inputs by country
	Costs of activity by country
	Costs of procurement

Equity
There are many dimensions to disadvantage and the ICOSA programme focuses on gender and school attendance status as potential sources of inequity.

Gender: SCI collects disaggregated data as part of its impact (epidemiological) and performance (coverage) surveys. The data shows that the programme has an equitable impact on health of female and male school-aged children (SAC).

Gender disaggregated data is being used with other DFID and USAID partners to increase evidence for gender equity across NTD mass treatment programmes. SCI, with WHO, is leading efforts with NTD partners to develop and pilot the WHO gender, equity and human rights approach tool for NTDs, support entry of gender disaggregated data into the WHO Integrated NTD Database and has presented on the ‘The Role and Impact of Women in Community based NTD Programmes’ at the All-Party Parliamentary Group for Malaria and NTDs in Westminster.

SCI is supporting MoH partners to adapt programmes and ensure treatment coverage in non-attending SAC is increased. Intra-country variations have been observed through the coverage surveys and closer monitoring through more in-depth surveys and evaluating additional outreach interventions is ongoing.

In order to investigate whether there is equitable distribution, the programme has piloted the Equity Tool (http://www.equitytool.org/) to measure the relative wealth of beneficiaries. Preliminary analysis from adding the Equity Tool to coverage surveys in Ethiopia, Liberia, Malawi and Uganda demonstrates that the reach of treatment programmes is equitable in terms of wealth quintiles

Effectiveness
The ICOSA programme reports back on effectiveness measures in the logframe. The indicators of effectiveness are covered in section B of the Annual Review:
- Health impact
- Validated treatment coverage
- Cost per treatment

In addition to the Log-Frame effectiveness measures, ICOSA is also calculating the cost per DALY averted. The table below shows DALYs averted estimates, in comparison to the Business Case and estimates for cost per DALY for all countries where there is a value for cost per person treated.

Country	Total ICOSA / DALYs averted (millions)	Business Case DALYs averted / (millions)	ICOSA cost per / DALY averted (£)
CDI	0.04	0.07	22.40
DRC	0.02	0.01	43.21
Ethiopia	0.04	0.03	no cost data
Liberia	0.01	0.05	37.58
Malawi	0.10	0.13	25.56
Mozambique	0.15	0.17	4.85
Niger	0.01	0.01	78.33
Tanzania	0.04	0.07	29.61
Uganda	0.01	0.02	87.17
Zambia	0.01	0.01	56.25
Zanzibar	0.02	0.05	27.90
TOTAL	0.43	0.62	£41.29

The DALYS averted by the programmes is estimated to be 0.43 million, above what was projected in the Business Case. This can be explained by the increased treatment numbers. The financial cost per DALY averted is currently higher than that of the Business Case, £41.29 compared to £35. This increase is being driven by the higher cost per treatments in Uganda, Niger and Tanzania and because we currently have no cost data for Ethiopia. Nevertheless when compared to the WHO definition of cost-effective programme, the cost per DALY averted falls well below the Gross Domestic Product per capita in each of these ICOSA countries.

### Efficiency
SCI is achieving efficiency through good project management, planning and implementation. Key measures include the cost per person trained and treatments delivered per distributor.

Cost per person trained: The data on the number and cost per persons trained by country allows ICOSA to compare between annual workplans and budgets with what has actually been delivered.

Treatments delivered per drug distributor: It is projected that as a country increases its experience in implementing PC programmes it will gain efficiency by increased productivity, for instance, increasing the numbers of treatments delivered by the numbers of drug distributors used per district. Preliminary results from Cote d’Ivoire and Malawi indicate that on average there are 110 and 547 treatments per distributor, respectively. This compares to 110 and 219 treatments delivered per distributor last year. However, these are only estimates and should be treated with caution.

	Last year	This year
Cote d'Ivoire	175	110
Malawi	219	547

Economy
Please refer to output 5 above.

Quality of financial management

The 2016 Annual Review recognised the significant improvements SCI has made in its financial management processes but also highlighted areas where further work was required. During this reporting period SCI has worked with other functions within Imperial College including the Joint Research Office (JRO) and the finance unit of the Department of Infectious Disease Epidemiology and School of Public Health to continue to improve accountability, mitigate risks and improve contracting and transfers to partners in countries. For example, there have been significant improvements to the contracting process with country partners including the development of updated templates and timeliness in signature. Payments to partners are now processed along improved timelines with appropriate prioritisation by Imperial College. This has been supported by the DFID SRO, with guidance from DFID allowing SCI to prioritise and develop effective strategies and monthly DFID/SCI financial meetings allowing timely resolution of challenges.

Following an audit scoping exercise during 2016, KPMG conducted an external audit of SCI in May 2017 and the final report was issued on 12 July 2017. The audit covered the following areas:
- Control Environment Assessment
- Terms and Conditions for the Grants contracts
- Substantive procedures

KPMG verified SCI budget verses actual for the period 1 April 2016 to 31 March 2017. KPMG tested 77% of all costs and no costs were disallowed or found ineligible.
There was one high priority finding around improving the financial monitoring on the partners in the countries from the finance team. SCI has developed a series of monitoring tools for use in partner countries and this finding will further strengthen support for the use of these tools. It will also increase the justification for SCI financial team members to travel to partner countries and work with Program Advisors to ensure robust financial monitoring and evaluation systems are in place to increase transparency and accountability. SCI has also developed a strong relationship with KPMG and will be able to seek their further advice where needed. We are confident to report that the recommendations have been actioned.

Financial Reporting and Monitoring: SCI continues to improve its reporting and monitoring capabilities by continual review and improvement of tools and processes. During the last project year, a new process to respond to perceived risks and issues within country programmes has been implemented allowing weekly monitoring of any financial and operational issues arising. The cash-book (the template used to collect monthly financial reports and detailed expenditure from each country programme) has been updated and rolled out to all countries alongside a training package on its use and the supporting documentation required.

Budgeting and Forecasting: An annual organisation master budget is now developed including ICOSA funds to capture central and country costs and allocate staff costs alongside other funding sources to each country. This allows accurate tracking, forecasting and allocation across different donors. The budget is monitored by preparing a Budget vs Actual report. For forecasting against this budget, SCI has been working closely with DFID and Imperial College Joint Research Office (JRO) to improve financial forecasting and SCI has agreed to monthly re-forecasting and variance reporting to DFID. DFID have advised SCI on a different timeframe that satisfies Imperial College and DFID. However until now the annual available budget for 17/18 is not confirmed and there is a discrepancy between Imperial College Records and DFID records and the same with available budget for CA.

SCI has prepared a 3 Years budget and identified an ideal budget scenario and funding gap analysis to continue to support all country programmes and continues to fundraise against these targets.

Contracts: With support from the contracting team of the JRO, contracts are being issued in an expedited manner and with clearly defined payment schedules to in-country partners, assisting accurate forecasting. During 2017, all contracts were signed on time with the exception of DRC and Ethiopia, for reasons beyond SCI control. Both countries operate integrated programmes resulting in increased budgeting complexity as all partners provide funds to a consolidated budget. Budgets can only be finalised when all partner inputs are known.
Invoicing: SCI provides a detailed invoice in-line with DFID recommendations and requirements.

Date of last narrative financial report	N/A
Date of last audited annual statement	2015/16 at http://www.imperial.ac.uk/media/imperial-college/administration-and-support-services/finance/public/Imperial_ReportAndAccounts2015-16_WEB_Singles.pdf

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

Moderate

Overview of programme risk

Risks	Probability / (3 high, 1 low)	Impact / (3 high, 1 low)	Mitigation strategy
PZQ shortage as a result of shortfalls in donations or procurement.	2 / (change from business case: 0)	3 / (change from business case: 0)	ICOSA is represented on the subcommittee of the WHO Working Group on Access to Quality Assured Donated Medications. The subcommittee meets annually to coordinate the supply of drugs for NTD programmes. WHO, USAID, Crown Agents, SCI, World Vision and DFID work closely to ensure no duplication in the supply of PZQ to countries. / The current major challenge to the project is coordinating the transition from Donor-procured to donated PZQ within specific ICOSA countries as ICOSA-procured PZQ continues to scale down and USAID-procured PZQ stops. The WHO JRSM process runs to deadlines for countries to submit applications in April and August each year for the Merck-donated PZQ. As yet, the requests from countries have not yet exceeded the 250 million allocation from Merck, allowing for scope for previously procured PZQ to be made available through the donation route enabling ICOSA to supplement for adult populations and shortfalls during the transition process. However, the information held between country programmes and the WHO via AFRO is not always consistent, making it challenging to predict the true requirement at country level. To mitigate this, ICOSA continues to discuss directly with Merck on a monthly basis and regularly provides updated information to WHO.
	Major

PZQ price rise	1 / (change from business case: / -1)	2 / (change from business case: / 0)	Crown Agents continue to purchase PZQ against a competitive tendering process. Currency fluctuations have negatively impacted the rate of £GBP to $USD at which PZQ is supplied. However, the price per tablet in $USD has remained stable. Although there is an increased risk that the funding available for PZQ procurement will impact unfavourably in the number of PZQ tablets which can be purchased, the commitment by WHO to meet the PZQ need of all SAC through the donation channel has relieved the pressure on ICOSA to procure high numbers of tablets.
	Minor

Difficulty in scaling up on part of contractor	1 / (change from business case: 0)	1 / (change from business case: / -1)	Finding appropriate staff to manage scale up at SCI was not considered a major risk, and indeed the project staffing is continually appraised and strengthened where necessary. This aspect of ICOSA performance is closely monitored.
	Minor

Resistance to PZQ and side effects	1 / (change from business case: 0)	1 / (change from business case: 0)	Resistance to PZQ has not yet been encountered and there is good evidence that the risk of resistance developing is low. / Very few side effects have been recorded (and these are transient). Appropriate information on side-effects and longevity will be provided at the time of PC campaigns, and taking food prior to treatment will be encouraged. The programme will monitor side-effects and investigate cases experienced through appropriate MoH channels in each country. / The project will also ensure adequate training for drug distributors to distinguish children who are ill at the time of treatment to exclude them from taking medication.
	Minor

Outstanding actions from risk assessment

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Despite a slow start in some countries the programme is on track to meet the targets. However a large number of treatments still need to be delivered to meet this target.

Performance of partnership (s)

SCI works well with partner countries. They are also working closely with other partners working on DFID NTD programmes. Though SCI do contribute to wider policy discussions on schistosomiasis this should be enhanced as this programme has much to offer wider policy and impact debate.

Asset monitoring and control

A standardised asset register allows ICOSA to track assets. All procurement items (excluding single use consumables) procured through Crown Agents or within country are included in the register and regularly updated by the ICOSA finance team. In addition to providing knowledge of specific assets available for use in country this register will also assist with planning for replacement items in the future.

G: CONDITIONALITY (½ page)

There is no specific conditionality attached to the business case.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The theory of change and assumptions in the business case are still valid. As SCI collates the data from each process and survey, it is beginning to develop a multi-disciplinary view on the success factors and challenges for schistosomiasis control and elimination. Over the next year SCI shall continue to programme evidence to further inform the in-country implementation in a real-time basis, and also to share the multi-country evidence at a global level. Collaborations led by WHO, have begun to analyse the impact of treatment on schistosomiasis over last 10 years. SCI will be critical to supporting their partner countries and WHO to ensure access to data and statistical rigour in the analysis and outcomes. Due to the quality and quantity of the ICOSA data, it will form a significant part of the database to be used and the exercise will allow an external evaluation of the impact of DFIDs investments in schistosomiasis control.

Determining where schistosomiasis infection is within a country has been through prevalence mapping surveys supported by SCI. National plans are then based on this data. A recent publication by SCI in PLoSNTD using ICOSA supported data from Cote, d’Ivoire, Liberia and Malawi determined ‘Optimising cluster survey design for planning schistosomiasis preventive chemotherapy’ and has led to interest from other DFID partners and WHO regions i.e. PAHO and EMRO, to consult on mapping strategies for schistosomiasis endemic countries.

Monitoring progress throughout the review period

This review was done as a desk exercise by DFID staff members.

There has been some progress on financial management through closer monitoring of activities. This has been achieved with the development of several tools and processes such as:
- Monthly meetings being held between the finance team and programme managers with DFID to review the expenditures of each country and;
- Regular follow-up with the endemic country accountants on the quality of the supporting documentation, timely recording and accuracy of figures.
- Development of grants management tools to improve management processes.

These tools have allowed SCI to improve its grants management and financial monitoring. For example, by preparing quarterly budget versus actual allows SCI to take timely corrective measures. The increased frequency of supportive interactions with countries has resulted in improved budgeting and timely finalisation of contract.