Annual Review – Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Animal Health and Veterinary Science Specialist Advice
Programme Value: £103,540		Review Date: 4 January 2018
Programme Code: 300361	Start Date: 4 January 2017	End Date: 30 September 2019

Summary of Programme Performance

Year	2017
Programme Score	A
Risk Rating	Minor

Summary of progress and lessons learnt since last review

The rapidly growing demand for livestock products (milk and meat) in developing and emerging economies is driving large-scale expansion and change in livestock production systems. This rapid expansion exposes livestock and those who work with livestock or consume meat or dairy products to outbreaks of disease. Zoonotic diseases (diseases which can be transmitted from animals to humans), such as tuberculosis, are estimated to cost more than £15 billion in direct and indirect costs annually.

Nearly 900 million people rely on livestock for their livelihoods, and livestock fulfil important economic, social and cultural roles. Livestock not only provide food, but they are often themselves a highly valuable and productive asset for poor people in developing countries. The loss of animals through disease devastates the lives of individuals, families and communities around the world.

DFID’s Agriculture Research team supports a number of animal health research programmes which aim to reduce the impact of zoonotic disease on poor communities in developing countries, while also helping to identify and halt the spread of pandemics across the globe.

Owing to the relatively limited and fluctuating requirement for deep specialist expertise in these areas, DFID does not currently retain an in-house veterinary and animal health specialist. DFID’s Livelihoods cadre does not attract applicants with specialist expertise in these areas, most likely because – given the limited number of animal health programmes – there is limited demand for specialist inputs and no career path within DFID for specialists in this field.

The development of animal therapeutics, diagnostics and vaccines is a highly complex and rapidly evolving area of science: maintaining in-house capacity to deliver specialist technical inputs in these areas would require the development of deep technical skills which would not be deployable across the rest of the organisation.

This programme addresses the need within DFID for short-term, infrequent access to specialist expertise in animal health and veterinary science. The objective of the programme is to ensure that we are able to maintain strong technical oversight of a complex and technically sophisticated portfolio of investments, at relatively low cost to DFID. Under this programme, DFID has established a call-down contractual arrangement with Livestock Incorporated Ltd., allowing DFID to access high quality technical advice, in a timely manner, to support robust project and risk management of programmes with an animal health or livestock component. By ensuring DFID has a clear understanding of the technical challenges facing its portfolio of animal health research programmes, this project enables DFID to manage and mitigate delivery and operational risks, and to challenge implementing partners on timelines and delivery, ensuring we deliver value for money.

The technical inputs provided during the reporting period have been of a consistently high quality, strongly grounded in development realities. By drawing on these inputs, DFID has been able to work more effectively with key partners including the Bill & Melinda Gates Foundation (BMGF) in the area of animal health research, and has been better equipped to quickly identify and robustly manage risks on animal health and livestock research programmes. The project has successfully supported DFID’s Senior Responsible Owners (SROs) and programme managers in their management and direction of the animal health research portfolio, providing a specialist perspective on the challenges and risks facing these programmes.

This programme also strengthens DFID’s capacity to deliver on both the UK’s development commitments and the UK Government’s Animal and Plant Health Strategy, which sets out a compelling case for the UK’s role in developing integrated approaches to tackling global animal health challenges.

Summary of recommendations for the next year

Recommendation #1: DFID should retain the best practice contract management approach trialled during the reporting period. This provides for a transparent audit trail and efficient and effective management of the call-down contract. Moving into the next reporting period, to support effective management of the project budget, this mechanism will also be used to prioritise requests for specialist inputs where needed (for example, if there are times when demand for specialist support is particularly high), ensuring the highest priority inputs are commissioned.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/14392391.odt
DevTracker Link to Log frame:	Not applicable – the programme is governed by a contract/service level agreement rather than a logframe.

Outline of the programme

This programme enables DFID’s Agriculture Research Team to access specialist animal health and veterinary science expertise – on a short-term and infrequent basis – to support the delivery of a portfolio of agriculture research projects with an animal health or livestock component.

The 20 month call-down contractual arrangement established under this programme provides for a maximum of two days per week of specialist technical animal health inputs to DFID advisers, Senior Responsible Owners (SROs), programme managers and senior managers. This resource enables DFID to target its investments in animal health and livestock research more effectively, and to identify and manage key technical risks robustly.

The programme contributes to an overall intended impact of developing and deploying new technologies (vaccines, diagnostics and medicines) to address livestock disease quickly and effectively. It does this by providing DFID SROs and programme managers with the technical inputs needed to manage risks and challenge implementing partners on delivery approaches and timelines.

The key outcome of this programme is more effective DFID-funded animal health research and programme delivery.

The principal output of this programme is high quality animal health and veterinary science technical support, enabling DFID to make robust and well-informed decisions relating to the programme and risk management of DFID’s animal health research programmes.

The key activities conducted during the reporting period are reported on elsewhere in this Annual Review.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The technical inputs provided during the reporting period have been of a consistently high quality, strongly grounded in veterinary science and in the delivery of animal health programmes in developing countries. By drawing on these inputs, DFID is able to work more effectively with key partners including the Bill & Melinda Gates Foundation (BMGF) in the area of animal health research, and has been better equipped to quickly identify and robustly manage risks on animal health and livestock research programmes. The project supports DFID’s Senior Responsible Owners (SROs) and programme managers, providing a specialist perspective on the challenges and risks facing these programmes, which enables DFID to manage its portfolio of animal health research programmes more effectively and efficiently.

This programme also continues to strengthen DFID’s capacity to deliver on both the UK’s development commitments and the UK Government’s Animal and Plant Health Strategy, which sets out a compelling case for the UK’s role in developing integrated approaches to tackling global animal health challenges.

Key technical inputs provided during the reporting period are detailed in the output scoring section below.

Overall output score and description

The programme has scored an A overall. High quality animal health and veterinary science technical inputs were provided in a timely manner throughout the reporting period, enabling DFID to make robust and well-informed decisions relating to the project and risk management of DFID’s animal health research portfolio.

Key lessons

Given the nature of this programme, key lessons learned are most likely to relate to the contract management and oversight of call-down technical support arrangements.

Early in the reporting period, the SRO and Deputy Programme Manager (DPM) consulted DFID’s Procurement & Commercial Department (PCD) on best practice management of these arrangements. The management team subsequently trialled and implemented a contract oversight process involving 3 month rolling workplans and the issuing of reference numbers to the call-down specialist and to commissioning SROs within the Agriculture Research team. This mechanism has worked very effectively and has provided for a highly transparent audit trail of technical support commissioned and received. Moving into the next reporting period, to support effective management of the project budget, this mechanism will also be used to prioritise requests for specialist inputs where needed (for example, if there are times when demand for specialist support is particularly high), ensuring the highest priority inputs are commissioned.

Has the logframe been updated since the last review?

Not applicable – this programme is governed by a contract/service level agreement rather than a logframe.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	To provide specialist inputs and advice on aspects of a range of animal health research programmes.
Output number	N/A	Output Score	A
Risk	Minor	Impact weighting (%)	N/A
Risk revised since last AR?	N/A (this is the first Annual Review)	Impact weighting % revised since last AR?	N/A

Key Points

Livestock Incorporated Ltd. has delivered strongly against the contractual Terms of Reference, providing high quality and timely technical inputs in response to requests for support from DFID advisers and Senior Responsible Owners.

The organisation has established strong and effective working relationships with DFID technical and programme staff, and key external partners for DFID in the animal health research space, including the Bill & Melinda Gates Foundation (BMGF).

Over the reporting period, the technical inputs provided have enhanced the capacity of DFID’s Agriculture Research team to successfully implement DFID’s animal health research programme portfolio.

The table below provides a breakdown of key inputs commissioned over the reporting period, and the impact of these inputs for DFID programme and risk management. In line with the Terms of Reference for the call-down contractual arrangement, the inputs listed reflect areas where DFID requires specialist, technical support in the area of veterinary science and animal health. Responsibility for the management and overall direction of all animal health research projects funded by DFID remains the remit of the DFID SRO, adviser and programme manager.

Inputs commissioned	Impact on DFID programme and risk management
Participation in planning workshop at the Centre for Tropical Livestock Genetics and Health (CTLGH), Edinburgh	Livestock Incorporated Ltd. attended this meeting to support the DFID SRO and programme manager with detailed technical advice and analysis. This support enabled DFID to understand and critique the implementation plans being presented by the CTLGH project team, from a technical and delivery perspective.
Participation in planning workshop in Nairobi, determining the research priorities and portfolio for CTLGH	This was a technical planning meeting, setting out and agreeing the detailed work plans and research targets for the CTLGH projects. Livestock Incorporated Ltd’s technical understanding of the research field and of the broader issues around livestock genetics and African agriculture enabled DFID to ensure that the plans were challenging, but deliverable – reducing overall risk exposure for DFID.
Delivery of evidence note on bovine tuberculosis to support internal DFID discussions	The epidemiology of tuberculosis is a complex technical area. Livestock Incorporated Ltd presented a concise and clear note synthesising the current evidence linking TB to the prevalence of zoonotic bovine TB, as a basis for DFID to consider whether to invest more.
Inputs to DFID/BMGF discussions on potential investments in bovine TB research	BMGF has a team of specialist livestock disease specialists. As noted elsewhere in this Annual Review, DFID does not currently have access to similar capacity in-house. The inputs of Livestock Incorporated Ltd enabled us to continue to work closely with BMGF in a complex technical area like zoonotic TB, ensuring that our decisions relating to the co-funding of projects with BMGF are firmly backed up by independent technical advice.
Inputs to management of DFID’s support to the Global Alliance for Livestock Veterinary Medicines (GALVmed)	GALVmed is a complex programme currently developing, testing and deploying up to 10 new products to address important livestock diseases. Each of these work streams involves a series of technical milestones and decision points linked to funding. With technical advice from Livestock Incorporated Ltd, DFID has been able to have a clear assessment – from a technical perspective – of the quality of GALVmed reporting, progress made, and the validity of programme management decision-making and technical progress.
Inputs to planning process for a new phase of DFID support to GALVmed	A proposal for a new phase of work has been developed by GALVmed, with support requested from DFID and BMGF. Livestock Incorporated Ltd’s technical analysis of the proposal highlighted a number of gaps and areas for revisions, linked to market development and access and to product development. This analysis was grounded in Livestock Incorporated Ltd’s specialist knowledge of livestock veterinary provision in Africa. It enabled DFID to target comments on possible weaknesses in the proposal, driving a revised proposal which will deliver DFID objectives.
Inputs to GALVmed’s work on developing diagnostics for Animal African Trypanosomosis (AAT)	AAT is a complex project which continues to make slow progress. To support DFID’s programme and risk management of the project, Livestock Incorporated Ltd has been participating in technical working groups assessing product progress, usually by phone. Livestock Incorporated Ltd then provides a quick and accurate readout of progress to DFID, enabling DFID to identify and respond to technical risks.
Inputs to planning discussions between DFID and other donors on potential new work on anti-microbial resistance (AMR)	Livestock Incorporated Ltd conducted a quick assessment of AMR and livestock for DFID – a complex, but important and growing area of research. Livestock Incorporated Ltd joined a discussion with the UK Department of Health, the International Livestock Research Institute (ILRI) and DFID, bringing a strong technical perspective into a discussion with these parties, focusing on technical questions and advising and supporting the development of a DFID position on AMR.
Review of the International Livestock Research Institute (ILRI)’s 10 year strategy	Drawing on wide-ranging experience and expertise, Livestock Incorporated Ltd was able to provide useful guidance and direction to ILRI, linking it to the CTLGH work.
AgResults programme – inputs to judging panel for brucellosis competition	Livestock Incorporated Ltd provided high quality advice on brucellosis competition rules, based on expert knowledge of the field.
AgResults programme – inputs to preparation for Steering Committee	Livestock Incorporated Ltd provided timely inputs on options for new livestock pilots, drawing on the new AgResults knowledge note drawn up by the Evaluator (Abt Associate) as a World Bank and Steering Committee output. The use of the framework was appreciated by the Steering Committee. This enabled the Committee to look beyond the two BMGF proposals on the table as well as to reflect on selection criteria.
Inputs to Annual Review 2017 process for the DFID-BMGF strategic partnership for the development and scaling of next generation agricultural technologies	Livestock Incorporated Ltd provided timely inputs and comments on the livestock portfolio, providing technical inputs in assessing progress of specific livestock projects. This enabled the DFID programme management team to assess robustly the quality of the portfolio as a whole, whether it is on track, and identify any specific risks emerging.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable – this is the first Annual Review of the programme.

Recommendations

Recommendation #1: DFID should retain the best practice contract management approach trialled during the reporting period. This provides for a transparent audit trail and efficient and effective management of the call-down contract. Moving into the next reporting period, to support effective management of the project budget, this mechanism will also be used to prioritise requests for specialist inputs where needed (for example, if there are times when demand for specialist support is particularly high), ensuring the highest priority inputs are commissioned.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost driver for this project is the level of demand for call-down services from Livestock Incorporated Ltd. Of the maximum £103,540 contract limit, £43,783 has been spent to date. This represents approximately 42% of the contract value, over a time period of just under 1 year (approximately 50% of the contract duration).

The contract arrangement is on a call-down basis, meaning DFID will only disburse funding to pay for commissioned inputs over the life of the contract. At the current spending rate, it is anticipated that spending on this project will be under budget. There is no obligation for DFID to spend the full contract value.

VfM performance compared to the original VfM proposition in the business case

The business case for this project set out the following measures for ensuring value for money. A brief update on progress over the reporting period is included below:

1. DFID will pay for advice on a call-down basis: as noted above, the spend rate over the reporting period indicates that total spend will be slightly under budget when the call-down contract ends in September 2018.
2. The DFID SRO will monitor the quality of support provided by Livestock Incorporated Ltd: as part of this Annual Review process, the SRO sought feedback from the advisers and SROs in the Agriculture Research team who have made use of support from Livestock Incorporated Ltd during the reporting period. This feedback is reported under the output scoring section of this Annual Review, and illustrates the high quality and valuable support provided by this project over the reporting period.
3. Invoices will be checked by DFID on receipt to ensure rigorous financial management: As noted in Section B, early in the reporting period, the SRO and DPM consulted DFID’s Procurement & Commercial Department on best practice management of call-down contractual arrangements. The management team subsequently trialled and implemented a contract oversight process involving 3 month rolling workplans and the issuing of reference numbers to the call-down specialist and to commissioning SROs within the Agriculture Research team. This mechanism has worked very effectively and has provided for a highly transparent audit trail of technical support commissioned and received. In addition, this new approach has greatly streamlined the invoicing and payment process. Invoices are received by the SRO and DPM, who then cross-check the reference numbers and details of the listed items against the workplan which is kept up to date by the DPM.

Assessment of whether the programme continues to represent value for money

The table below assesses the project against the ‘4 E’ framework, and presents an overall conclusion on the value for money of the programme during the reporting period:

4 Es	Summary of performance
Economy	The project has been strongly economical for DFID over the reporting period. Livestock Incorporated Ltd’s familiarity with DFID’s programme portfolio and administrative procedures meant that the start-up phase of the contract proceeded smoothly, with the supplier able to provide timely and high quality inputs from the outset (rather than requiring a familiarisation phase to understand DFID’s procedures and technical priorities). / The day rate agreed with Livestock Incorporated Ltd prior to contract award stage was assessed as competitive by Research and Evidence Division’s Delegated Procurement Officers. The agreed day rate reflects a 20% discount on the organisation’s typical short-term consultancy rate for specialist advice.
Efficiency	The project performs well on efficiency measures, and improvements have been made over the reporting period to further strengthen this area – i.e. the invoicing process has become much more streamlined, owing to the introduction of reference numbers linked to a rolling workplan managed by the SRO and DPM.
Effectiveness	‘Effectiveness’ in the DFID value for money framework relates to how well programme outputs achieve their desired outcomes. The programme business case outlined the intended outcome of the programme as ‘more effective DFID-funded animal health research and programme delivery’. As outlined in the output scoring section of this Annual Review, the call-down arrangement has allowed DFID to draw on high quality technical inputs over the reporting period in support of key animal health research programmes. This support has strengthened DFID’s capacity to identify technical risks in these programmes and steer programme partners to take robust action to mitigate and manage these risks.
Equity	Owing to the nature of this project (a call-down contract supporting broader technical work within DFID), the DFID review team concludes that equity indicators are not relevant in this case.
Overall	The DFID review team concludes that this programme represented good value for money over the reporting period.

Quality of financial management

Livestock Incorporated Ltd invoices DFID on a monthly basis. Time sheets are provided with invoices, which are then cross-checked against the DFID management team’s workplan records.

Date of last narrative financial report	6 November 2017
Date of last audited annual statement	Not required under call-down contract terms and conditions.

E: RISK (½ page)

Overall risk rating: Minor

Overview of programme risk

Risk category	Gross risk description	Mitigation	Residual risk rating	Likely trajectory over the coming reporting period
Context	Owing to the relatively limited and fluctuating requirement for deep specialist expertise in these areas, DFID does not currently retain an in-house veterinary and animal health specialist. As explained elsewhere in this Annual Review, there is limited demand for specialist inputs and no career path within DFID for specialists in this field. Without access to specialist technical inputs in the areas of animal health and veterinary science, however, DFID’s capacity to manage its animal health research portfolio would be constrained.	This project addresses the need within DFID for short-term, infrequent access to specialist expertise in animal health and veterinary science. The call-down arrangement allows DFID to access high quality technical advice, in a timely manner, to support robust project and risk management of programmes with an animal health or livestock component.	Minor
Delivery	There is a risk inherent in contracting call-down specialist support that the technical inputs provided may not be of a consistently high quality.	Livestock Incorporated Ltd provides services to a range of development partners including DFID. The supplier has extensive animal health and development expertise, directly relevant to the objectives of DFID’s Agriculture Research team. Quality of inputs provided has been assessed as part of this Annual Review process, and the DFID review team has found these to be of a consistently high quality, firmly grounded in development realities.	Minor
Operational	Operational risk overlaps with context risk for this project. As noted above, DFID’s capacity to manage its animal health research portfolio would be constrained if the DFID programme team were unable to access specialist expertise in animal health and veterinary science when required.	Drawing on specialist animal health expertise when required has enhanced DFID’s capacity and capability over the reporting period. This reduces operational risks to the DFID Agriculture Research team’s overall portfolio.	Minor
Safeguarding	Given the nature of this project, safeguarding risks are not considered to be pertinent.	Not applicable.	Minor
Fiduciary	There is an inherent risk in all commissioning activity that funds are not used for the intended purposes.	Livestock Incorporated Ltd’s invoices over the reporting period have been 100% accurate. The SRO and DPM have checked each invoice against DFID’s own workplan records and have verified hours claimed with the SROs who commissioned each input.	Minor
Reputational	There is a potential reputational risk inherent in contracting specialist expertise from an external partner.	DFID’s Agriculture Research team, with the support of Research and Evidence Division’s delegated procurement officers, negotiated a competitive rate with Livestock Incorporated Ltd. Given that DFID does not currently require a full time animal health and veterinary science specialist, this project represents good value for money for DFID in the current context.	Minor

Outstanding actions from risk assessment

Not applicable.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

All technical inputs commissioned during the reporting period were delivered on time.

Performance of partnership (s)

Livestock Incorporated Ltd has established strong and effective working relationships with DFID technical and programme staff, and key external partners for DFID in animal health research, including the Bill & Melinda Gates Foundation (BMGF).

Asset monitoring and control

Not applicable – the supplier has not purchased any assets with DFID funding.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable – no direct funding to partner governments is provided under this project.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Not applicable to this project, which provides call-down technical services to DFID programme management staff.

Monitoring progress throughout the review period

Throughout the reporting period, the DFID SRO and DPM have managed a rolling workplan within the Agriculture Research team, which sets out required inputs from Livestock Incorporated Ltd. SROs and advisers within the Agriculture Research team are commissioned to update this on a monthly basis. An up to date workplan is then shared with Livestock Incorporated Ltd.

As part of this Annual Review, the SRO sought feedback from SROs and advisers who have made use of call-down support over the year. This feedback is reported in the output scoring section.

Approach to the Annual Review

This Annual Review was conducted by the DFID SRO and DPM, drawing on feedback from other SROs and advisers within the Agriculture Research team who have utilised call-down support from Livestock Incorporated Ltd over the reporting period. The SRO and DPM also reviewed the original programme Business Case, the rolling workplan, and all invoices received.