## Logframe
PROJECT NAME | Joint Programme for El Nino Drought Response in Lesotho 2016/17
IMPACT | Impact Indicator 1 |  | Baseline (May 2016) | Target Aug 2017 | Assumptions
Enhanced livelihood security of drought-affected households in supported 9 districts in Lesotho (detailed below) by 31.08.2017 | Coping Strategy Index | Planned | Emergency 2% Crisis 11% Stress 42% | emergency 0% survival deficit <11% stress <42% | Households reduce sale of assets
|  | Achieved |  | (tbc)
Source
LVAC round 1, round 2, round 3 WFP post distribution monitoring
Butha-Buthe | UNFPA, UNICEF (WASH), WFP, FAO
Mohale's Hoek | UNFPA, WFP
Maseru | UNFPA, WFP
Mafeteng | UNFPA, UNICEF (WASH), WFP
Quthing | UNICEF (WASH), WFP, UNICEF (Social Protection)
Thaba-Tseka | UNICEF (WASH), UNICEF (Social Protection)
Mokhotlong | UNICEF (Social Protection)
Leribe | FAO
Berea | FAO, UNICEF (WASH), WFP
OUTCOME 1a - WFP | Outcome Indicator 1.1 |  | Baseline (May 2016) | Target Aug 2017 | Assumptions
Adequate food consumption reached or maintained over assistance period for targeted households. | Poor food consumption score | Planned | Quthing 17% | Quthing 3% | - A large proportion of the cash transfer will be spent on food. - Cooperation from community members, District Disaster Management Teams for efficient monitoring. - Continuous food availability in the targeted areas. - Other donor funding will be sufficient to address acute food needs of vulnerable populations outside of project areas. - Exploitative behaviour by traders does not lead to unjustified significant and sustained price increases. - Heavy rains occur.
|  |  | Maseru 15% | Maseru 3%
|  |  | Butha-Buthe 18% | Butha-Buthe 4%
|  | Achieved |  | Quthing 10% Maseru 7% Butha-Buthe 7%
Source
Baseline survey, LVAC Report, Post Distribution Monitoring Report & Evaluation Report
| Outcome Indicator 1.2 |  | Baseline | Target Aug 2017
| Cost of food gap versus value of cash transfer | Planned | 100% | 100%
|  | Achieved |  | 100%
Source
Post Distribution Monitoring Report & Evaluation Report
| Outcome Indicator 1.3 |  | Baseline | Target Aug 2017
| Dietary diversity score | Planned | Quthing 4.1 | Quthing >4.1
|  |  | Maseru 4.3 | Maseru >4.3
|  |  | Butha-Buthe 4.4 | Buthat-Buthe >4.4
|  | Achieved |  | Quthing >5.9 Maseru >5.0 Butha-Buthe >5.6
Source
LVAC Reports, Post Distribution Monitoring Report & Evaluation Report
| Outcome Indicator 1.4 |  | Baseline | Target Aug 2017
| % of households that use more than 50% of cash transfers for food. | Planned | 69% | 80%
|  | Achieved |  | 88%
Source
Post Distribution Monitoring Report & Evaluation Report
OUTPUT 1a - WFP | Output Indicator 1.1 |  | Baseline | Target Aug 2017 | Assumptions
5,000 targeted HHs received timely cash transfer and feedbacks have been acted upon | No. of households/people reached with cash transfer | Planned | 5,000 HH in Quthing | 28,000 people receive emergency cash assistance | - Cellular coverage is maintained during the project period/sufficient agents deployed for cash distribution. - Feedback received (including complaints) to follow up upon.
|  | Achieved |  | 42,250 people received emergency cash assistance
Source
Quarterly PDM report (HH size: 5)
IMPACT WEIGHTING (%)
OUTCOME 1b - UNICEF SP | Outcome Indicator 1.1 |  | Baseline (May 2016) | Target Aug 2017 | Assumptions
3,681 households in 3 affected community councils receive cash transfers reaching a minimum of 11,043 vulnerable children. | Number of households receiving emergency cash transfer top ups in three community councils | Planned | 0 | 3,681 HH | - The Ministry of Social Development (MoSD) processes the disbursement of the funds. - The number of families enrolled and eligible for assistance remains the same (Child Grant pProgramme's beneficiaries may graduate due to children turning 18).
|  | Achieved |  | 3,681 HH (18,405 people, including 11,043 vulnerable children)
Payrolls of MoSD
| Outcome Indicator 1.2 |  | Baseline | Target Aug 2017
| Number of community leaders and beneficiary households reached with emergency transfer message | Planned | 0% | 70 leaders and 3,500 HH
|  | Achieved |  | 70 community leaders (47% female) and 3,681 HH reached with emergency transfer messages
Source
Post Distribution Monitoring Report & Evaluation Report
| Outcome Indicator 1.3 |  | Baseline | Target Aug 2017
| Number of sensitization sessions on child protection in emergencies conducted during payment days | Planned | 0 | 12 sessions
|  | Achieved |  | 22 sensitization sessions and 3,681 HH on child protection in emergencies conducted during payment days
Source
Post Distribution Monitoring Report & Evaluation Report
| Outcome Indicator 1.4 |  | Baseline | Target Aug 2017
| Number of field monitoring and spot checks visits | Planned | 0 | 9 visits
|  | Achieved |  | 14 visits
Source
Post Distribution Monitoring Report & Evaluation Report
OUTPUT 1b - UNICEF SP | Output Indicator 1b.1 |  | Baseline | Target Aug 2017 | Assumptions
| Number of TWG meetings organized by MOSD with other stakeholders | Planned | 1 per month | 1 per 2 weeks | n/a
|  | Achieved |  | 2 TWG meeetings held
Source
TWG reports
| Output Indicator 1b.2 |  | Baseline | Target Aug 2017
| Number of reports shared with partners | Planned | 0 | End of Project Report
|  | Achieved |  | Report shared with MoSD
Source
n/a
IMPACT WEIGHTING (%)
OUTCOME 2 - FAO | Outcome Indicator 2 |  | Baseline | Target Aug 2017 | Assumptions
Nutritional status of targeted food insecure HH improved | Number of HHs reporting increase in vegetable consumption and diversity of consumption from their own production (FAO) - Percentage of HHs reporting an increase of vegetable food groups in their diet (FAO) | Planned | 0 | 12950 | - Asset disposal or acquisition is not significantly affected by the national economic situation during the project period. - At leat 60% of the total target group (11,100 HHs) present characteristics of improved resilience to natural shocks and disasters. - The yield per ha is based on very conservative estimates as generally subsistence farmers in Lesotho do not produce high yields per ha. The target yield of 270kg would be enough to cover at least 4 months of food requirements for a family of 5 people. With distribution of improved seeds and inputs, yiled may get higher but that will be clarified in the reports. - The project foresees an increase in the number of months that the target HHs will be food secure. - At least 20% (3,700HHs) out of the total target HHs for SP and livelihhod package report an increase in income attributable to inputs from the project. - At least 70% of the target HHs adopt climate smart agricultural techniques.
|  | Achieved |  | 12205
Source
Baseline and Post Harvest reports (FAO)
OUTPUT 2.1 - FAO | Output Indicator 2.1 |  | Baseline | Target Aug 2017
Community or livelihood assets built, restored or maintained by targeted households and communities | Percentage increase in crop production reported by beneficiary HHs (FAO) | Planned | 3500 | 180%
|  | Achieved |  | 233%
Source
Baseline and Post Harvest reports (FAO)
IMPACT WEIGHTING (%)
OUTCOME 3 - UNICEF WASH | Outcome Indicator 3 |  | Baseline | Target Aug 2017 | Assumptions
46,000 targeted beneficiaries of the total Basotho rural population (1,400,000) who are able to meet the minimum needs of potable water (up to 30 litres per person per day) by end of August 2017 | Percentage of (rural) HHs in targeted communities have access to more than 30 litres of potable water per day/per person using bores, springs, public tap, standpipe, etc. | Planned | 52.1% (729,600) | 53.9% (754,600) | - Partners have sufficient capacity to ensure application of technical quality standards and procedures in programme implementation. - Initiation, implementation, and reporting agreed activities and deliverables not delayed - Water infrastructure rehabilitation works not affected by the rainy season / La Nina. - There is not another drought year. - Political and security instability do not affect interventions. - High inflation does not cause a significant drop in value of Maluti vs the Rand/ USD or a significant increase in cost of supplies and contractors.
|  | Achieved |  | 54.9% (768,948)
Source
LVAC Report 07-2016, WASH Monitoring tool, 2017 monthly reports and partners reports indicates 39,348 beneficiaries reached by interventions.
OUTCOME 3.1 | Outcome Indicator 3.1 |  | Baseline | Target Aug 2017
46,000 targeted beneficiaries of the total Lesothan Rural population (1,400,000) - who will no longer access un-protected water sources | Percentage/# of HHs in targeted communities using unimproved water source | Planned | 39.6% (554,000) | 37.8% (529,000)
|  | Achieved |  | 36.7% (514,652)
Source
LVAC Report 07-2016, WASH monitoring tool, 2017 monthly reports and partners reports that indicates 39,348 beneficiaries reached by interventions.
OUTPUT 3 - UNICEF WASH | Output Indicator 3.1 |  | Baseline | Target Aug 2017 | Assumptions
Community or livelihhod assess built, restored or maintained by targeted households and communities. | Number of new water points established (Public taps, Hand Pumps, Boreholes) | Planned | 0 | 20 | n/a
|  | Achieved |  | 31
Source
Baseline survey conducted at the beginning of the programme. Monthy project verification visits, WASH monitoring tool, monthly reports and partners reports, signed contract awards, job completion certificates.
| Outcome Indicator 3.2 |  | Baseline | Target Aug 2017
| Number of new established spring boxes to protect un protected viable natural springs | Planned | 0 | 24
|  | Achieved |  | 14
Source
Baseline survey conducted at start of the programme. Project verification visits, WASH monitoring tool, monthly reports and partners reports, signed contract awards, job completion certificates.
IMPACT WEIGHTING (%)
OUTCOME 4 - FAO | Outcome Indicator 4.1 |  | Baseline | Target Aug 2017 | Assumptions
3,500 targeted households are more resilient. | Percantage of beneficiary HHs reporting an increase in area planted with crops | Planned | 0 | 60% | - At least all target HHs receive agricultural inputs as planned. - At least 70% of the target HHs receive training on CSA techniques.
|  | Achieved |  | 70%
Source
Baseline and Post Harvest reports (FAO)
| Outcome Indicator 4.2 |  | Baseline | Target Aug 2017
| Yield per hectare / number of months of HH food security produced | Planned | 150 kg | 270 kg
|  | Achieved |  | 350 kg
Source
Baseline and Post Harvest reports (FAO)
| Outcome Indicator 4.3 |  | Baseline | Target Aug 2017
| Increase of consumption of staple food from owm production in number of months per HH | Planned | 2 months | 4 months
|  | Achieved |  | 5 months
Source
Baseline and Post Harvest reports (FAO)
| Outcome Indicator 4.4 |  | Baseline | Target Aug 2017
| Percentage of HHs reporting an increase in amounts of agriculture produce being sold/intended for selling for income generation | Planned | 0% | 20%
|  | Achieved |  | 30%
Source
Baseline and Post Harvest reports (FAO)
| Outcome Indicator 4.5 |  | Baseline | Target Aug 2017
| Percentage of beneficiary HHs adopting CSA technologies for household production (FAO) | Planned | 29% | 40%
|  | Achieved |  | 33%
Source
Baseline and Post Harvest reports (FAO)
OUTPUT 4 - FAO | Output Indicator 4.1 |  | Baseline | Target Aug 2017 | Assumptions
Households receive seed packs, climate smart agriculture kits and training on climate smart farming initiatives | Percentage Households that received FAO seed packs | Planned | 0% | 2450
|  | Achieved |  | 5424
Source
Baseline and Post Harvest reports (FAO)
| Output Indicator 4.2 |  | Baseline | Target Aug 2017
| Percentage of beneficiary HHs trained on Climate Smart Agriculture | Planned | 0 | 100%
|  | Achieved |  | 87%
Source
Baseline and Post Harvest reports (FAO)
IMPACT WEIGHTING (%)
OUTCOME 5 - UNICEF WASH/UNFPA | Outcome Indicator 5.1 |  | Baseline | Target Aug 2017 | Assumptions
Reduce vulnerability for women and adolescent girls to El Nino-linked GBV | Percentage of HH with water more than 30 minutes away (round trip) | Planned | 36.6% (pre-emergency 2014) | 36.6% | - By establishing more water points and spring boxes that are closer to targetted beneficiries this will decrease the time taken and distance to collect water. In turn this will decrease risk to women collecting water. - The project targets 2 health workers per health centre in the 4 targeted districts. - The targeted districts have overall 60 health centres/districts hospitals and other health providers that are targeted by the programme. - The project knowledge process is through ToTs, trainings, dialogues, sensitization and use of IEC material (English and translated in Sesotho). - The national level working committee will serve maseru District. - Natonal level referral serving Maseru District and the 3 district specific referral mechanisms for Mafeteng, Mohales' Hoek and Butha-Buthe. Baseline data for Indicator 5.2 will be established by implementing partners to determine distance to water source which will affect the time taken to collect water. - The reporting structures and community reporting mechanisms are build through the programme and will enhance the reporting of cases. - Availability of 1 community protection network per district of operation.
|  | Achieved |  | 33.7% (473,052)
Source
LVAC Report 07-2016, WASH Monitoring tool, 2017 monthly reports and partners reports indicates 39,348 beneficiaries reached by intervention.
| Outcome Indicator 5.2 |  | Baseline | Target Aug 2017
| Number of women and girls with knowledge and skills about prevention and protection against GBV | Planned | 0 | 5000
|  | Achieved |  | 10326
Source
Activity reports, attendance lists, photos and story gallery.
| Outcome Indicator 5.3 |  | Baseline | Target Aug 2017
| Number of reported cases of GBV in communities and district level | Planned | 0 | 0
|  | Achieved |  | 0
Source
n/a
| Outcome Indicator 5.4 |  | Baseline | Target Aug 2017
| National GBV coordination structures established and functional | Planned | 0 | 1
|  | Achieved |  | 1
Source
Meeting minutes
| Outcome Indicator 5.5 |  | Baseline | Target Aug 2017
| Number of health service providers trained in clinical management of GBV | Planned | 0 | 120
|  | Achieved |  | 148
Source
ToT training reports
OUTPUT 5 - UNICEF WASH/UNFPA | Output Indicator 5.1 |  | Baseline | Target Aug 2017 | Assumptions
Water sources are established closer to HH. | See Output Indicator 3.1 and 3.2 | Planned | 41% (574,000) | 42% (588,142) | n/a
|  | Achieved |  | 43.8% (613,348)
Source
GBV Survey, GBV Survey, Project verification visits,WASH monitoring tool, monthly reports and partners reports indicates 39,348 beneficiaries served.
| Output Indicator 5.2 |  | Baseline | Target Aug 2017
| Referral mechanisms against GBV are established in targeted districts and communities | Planned | 0 | 1
|  | Achieved |  | 1
Source
GBV referral pathway, Maseru
| Output Indicator 5.3 |  | Baseline | Target Aug 2017
| Number of GBV workshops for prevention and response conducted at national and district levels | Planned | 0 | 10
|  | Achieved |  | 21
Source
Activity reports, attendance lists, photos and story gallery.
IMPACT WEIGHTING (%)
OUTCOME 6 - UNDP/RCO | Outcome Indicator 6.1 |  | Baseline | Target Aug 2017 | Assumptions
Improved coordination of the joint humanitarian response | Effective delivery of the Joint Program | Planned | n/a | Yes | - DMA continues the drought response coordination. - Humanitarian partners provide provide information metarial to the RCO - Continous participation of UN Agencies (resident and non-resident) and NGOs in the drought response activities.
|  | Achieved |  | Yes
Source
Minutes, TORs, Action Plans, (see output indicators 6.1 - 6.4)
| Outcome Indicator 6.2 |  | Baseline | Target Aug 2017
| Effective humanitarian response coordination | Planned | n/a | Yes
|  | Achieved |  | Yes
Source
Minutes, TORs, Action Plans (see output indicators 6.1 - 6.4)
OUTPUT 6 - UNDP/RCO | Output Indicator 6.1 |  | Baseline | Target Aug 2017 | Assumptions
Establishment of documents that improve coordination | Establishment of Terms of Reference | Planned | n/a | Yes | n/a
|  | Achieved |  | Yes
Source
Terms of Reference adopted.
| Output Indicator 6.2 |  | Baseline | Target Aug 2017
| Establishment of Technical Working Group | Planned | n/a | Yes
|  | Achieved |  | Yes
Source
Terms of Reference adopted for Technical Working Groups, meeting minutes.
| Output Indicator 6.3 |  | Baseline | Target Aug 2017
| Establishment of Action Plan | Planned | n/a | Yes
|  | Achieved |  | Yes
Source
Action Plans adopted
| Output Indicator 6.4 |  | Baseline | Target Aug 2017
| Minutes Taken | Planned | n/a | Yes
|  | Achieved |  | Yes
Source
Meeting minutes
Note: targets for outcome indicators may need to be adjusted once baseline data has been collected
Last update: 28 September 2017

## Diagram (hidden)
Emergency food security in Taiz and Lahj governorates of Yemen
OUTPUT | OUTCOME | IMPACT
Most vulnerable households in targetted districts in Taiz and Lahj have cash or vouchers to meet basic food needs | #REF! | #REF!

## Simplified logframe (hidden)
Emergency food security in Taiz and Lahj governorates of Yemen
Results Chain |  |  | Indicators | Source
Impact | #REF! |  | #REF! | #REF!
#REF!
| #REF! |  | #REF! | #REF!
Outcome |  |  | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Outputs | #REF! | #REF! | #REF! | #REF!
#REF!
|  |  | #REF! | #REF!
#REF!
| #REF! | #REF! | # of households enrolled in cash transfer programme | #REF!
#REF!
#REF!
|  |  | #REF! | #REF!
#REF!
| #REF! | #REF! | #REF! | #REF!
#REF!
| #REF! |  | #REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!