Annual Review - Summary Sheet
Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium (RPC)
Programme Value: £7,977,172		Review Date: 6th October 2017
Programme Code: 201446	Start Date: May 2011	End Date: 30th April 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	A	A+	A+	A+	A+	A
Risk Rating	High	High	High	High	Moderate	Moderate

Summary of progress and lessons learnt since last review
PRIME continues to be a well-managed and effective RPC, doing research on implementing and scaling up care for priority mental health disorders. It has robust systems and processes in place to maintain appropriate oversight at RPC and country level, and allow for open communication and engagement between staff and stakeholders. Key achievements during the reporting period include: at least one substantial influence on policy and practice in each PRIME country (see section B for details); the use of PRIME evidence in at least 83 districts in PRIME countries (Ethiopia:15, India:51, Nepal:8, South Africa:5, Uganda:3); publication of 9 peer reviewed journal articles (100% with a southern based female lead or co-author), £14.2m of funds leveraged for scale-up of PRIME activities; and a cumulative total of a 117 formal requests for PRIME support, collaboration and/or sharing of PRIME tools from a range of public and private organisations, including 9 LMIC governments - at least 5 programmes in non-PRIME countries are now using PRIME evidence or tools.

PRIME is involved in many influential fora and policy initiatives and the programme has contributed to the increased profile of mental health on the international agenda. PRIME delivered 23 conference presentations during the reporting period and was featured at the WHO/World Bank meeting (in Washington DC) ‘Out of the shadows: making mental health a global development priority’. In addition, four senior members of the PRIME team are editing the Global Mental Health Lancet Commission, which will be published in early 2018 and will include substantial content from PRIME. PRIME is partnering with WHO to provide case studies and tools to be used in the mhGAP 2.0 Operations Manual. The WHO mhGAP is a primary care clinical guideline for the detection and management of common mental health problems in primary care, and is currently being implemented in over 100 countries. The Operations Manual, due to be launched in October 2017 will provide a district level planning tool for implementing and scaling up mhGAP, and will draw substantially on PRIME tools and experiences.

PRIME has addressed all recommendations from previous reviews. Key challenges during the year included: exchange rate fluctuations; the cancellation of the licence of PRIME`s lead India partner (Public Health Foundation India) by the government due to new regulations for foreign funding; the declared state of emergency in Ethiopia in 2016; and the political transition to federalisation in Nepal. The team have managed these challenges well, keeping DFID appropriately informed. As PRIME enters its 7th year, the team should assess the impact of the delays caused by these external challenges and ensure that the objectives of the extension phase remain realistic.

Summary of recommendations for the next year

The following changes to the logframe are recommended and should be made by December 2017:
- incorporate the new DFID results framework indicators into the logframe
- Ensure extension phase activities are reflected in the logframe and targets are set for 2018 & 19 are clearly defined.
- Update logframe assumptions, many still refer to the inception phase
- Increase output indicator targets for 2.2. and 3.3 (as detailed under output recommendations)
- Closely monitor the impact of delays in research activities on achieving extension phase objectives

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3682501.odt

The need for mental health services is high. It is estimated that 10.4 % of the global burden of disease is due to mental, neurological and substance use disorders with a significant proportion in low and middle income countries. This equated to 258 million disability adjusted life years (DALYs) in 2010. Despite this burden, is it estimated that almost four out of five persons with severe mental disorders in LMICs did not receive any treatment in the previous year[1][2].
In order to address this, there have been numerous calls for the implementation and scale up of evidence based treatment in low and middle income countries but there remains little evidence on how to practically develop and implement this within the significant financial, human resource and system constraints.
[1] Kohn R, Saxena S, Levav I, Saraceno B. The treatment gap in mental health car. Bull World Health Organ 2004; 82 (11): 858-66.
[2] WHO. Mentlah health gap action programme (mhGAP): Scaling up care for mental, neurological and substance use disorders. Geneva. World Health Organization; 2008

The Programme for Improving Mental Health Care (PRIME) is an eight-year DFID-funded Research Programme Consortium (RPC) working in 5 countries; India, Uganda, Ethiopia, Nepal and South Africa. The programme aims to generate high quality research evidence on the implementation and scaling up of treatment programmes for priority mental disorders (depression, alcohol use and psychosis, with the addition of epilepsy in Nepal, Uganda and Ethiopia) in primary and maternal healthcare contexts in low resource settings. It seeks to achieve this through the following overlapping phases and activities:
- Inception (2011-12) - develop district specific integrated mental healthcare plans (MHCPs) comprising packages of mental healthcare for delivery in primary and maternal healthcare.
- Implementation (2012-13) - implement the MHCPs in partnership with Ministries of Health in PRIME countries (Uganda, Ethiopia, South Africa, India and Nepal), and evaluate the feasibility, acceptability and impact of these plans in primary healthcare and maternal healthcare.
- Scaling Up (2015-17) - evaluate the scaling up of these packages of care at district or sub-district levels.
- Extension (2017-19) – use data and evidence gathered during the implementation and scale up phase to refine the PRIME MHCPs, publish findings and ensure PRIME research is understood, effectively shared, and used to inform policy and practice

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment: A – outcome met expectations

PRIME has had a significant influence on policy or practice including:
Scaling up mental health services in Madhya Pradesh, using the PRIME India model, The PRIME District Mental healthcare plan has been used to inform the current revision of the 2012 Ethiopian Mental Health Strategy, PRIME Nepal, working with the Nepalese Government, used programme evidence to integrate mental health services into primary care in five of the districts most severely affected by the 2015 earthquake. The PRIME model developed at the District level has informed the content of the South African Department of Health Mental Health Policy Framework and Strategic Plan (2013-2020) for which the PRIME CEO sits on the technical advisory committee. In Uganda, 3 of the members of PRIME team have been part of the working committee involved in drafting the national mental health strategic plan, which is informing planning, practice and service delivery in a number of districts.

The PRIME model and tools are being used by a range of external organisations and governments of non-PRIME countries. By March 2017, a total of 117 formal requests (9 from Low and Middle Income Country (LMIC) governments) had been received through PRIME`s expression of interest platform for collaboration or sharing of PRIME tools. This demonstrates the success of research uptake and engagement platforms, and the credibility of PRIME work internationally.

Data are not yet available to measure the absolute percentage increase of men and women suffering from priority mental health disorders who receive evidenced based treatment in study districts. However, as reflected in figure 1, there was a substantial increase in monthly mental health visits to PRIME facilities.

Country	Number of visits in PRIME facilities during the implementation period	Average number of monthly mental health visits at baseline	Average number of monthly mental health visits at end of the Implementation Phase
Ethiopia*	>4103	0	414
India	3794	0	141
Nepal	4533	17	168
South Africa (Referrals)	572	8	21
Uganda	6435	134	202
Total	19281	32	189

Figure 1. Increase in mental health visits to PRIME facilities during the implementation period

Overall output score and description – A - outcomes met expectation

PRIME has met expectations. Delays in research project implementation has meant the programme just missed being moderately ahead of expectations. PRIME continues to produce and disseminate high quality research outputs, whilst effectively advocating to increase the profile of mental health on international and national agendas and building the skills, knowledge and resources to enable locally-led mental health research beyond the end of the programme.

Challenges to scale up continue to be available government resources and fragmentation and parallel services for mental health. Scale up is critically dependent on government judgments of priorities across many programmes, of which mental health is but one. PRIME is aware of these challenges, their model and engagement activities have been designed to support the alignment of these services into one package of basic mental health care and demonstrate the benefits of investing in mental health services.

Key lessons
PRIME have highlighted the following lessons in relation to both the function of the RPC as well as the implementation and scale up of RPC services:
- Strong, long standing and trusting partnership with Ministry of Health partners is essential to ensure RPC partners are aware of the evidence gaps and policy opportunities to maximise the influence of their research. To incorporate this learning, PRIME provides updates and is in regular communication with key stakeholders; PRIME staff sit on a range of national technical working groups (the majority of this engagement did not exist before PRIME) and PRIME has established Consortium Advisory Boards (CABs) in four PRIME countries.
- Training alone is not sufficient to lead to changes in primary care providers to detect and manage common mental health problems, and health system strengthening activities are essential to bring about sustainable change. To respond to this, PRIME have incorporated a wide range of health system strengthening activities into their work, e.g. establishing clear referral pathways, carrying out change management workshops to re-orient primary care providers, providing resources for the hiring of counsellors and strengthening medication supply.
- Uptake of mental health services in primary care facilities is unlikely to increase without interventions to improve community awareness and detection. PRIME have carried out a range of activities to achieve this, including: community radio station programmes to create awareness about mental health in Uganda; a community informant detection tool in Nepal, used by community health workers to identify people with mental health problems and facilitate access to care; conducting home visits to identify people living with severe mental illnesses, using case ascertainment methods in Ethiopia. PRIME should compare service utilisation across countries and through this reflect on the effectiveness of the different tools/approaches used

Key actions

- There have been some delays to data collection. PRIME must continue to focus on completion of collection, cleaning and analysis of this data to ensure that these delays do not impact on the quality of research outputs.
- PRIME should review extension phase activities to ensure they remain achievable. DFID should be informed of any potential impacts these setbacks may have on the delivery of extension phase objectives.
- DFID should work with PRIME partners to revise the logframe to include 2018 and 19 extension phase milestones and core results framework indicators.
- PRIME have found it challenging to report against their outcome indicator (1.3) ‘the absolute % increase of men and women suffering from priority mental health disorders who receive evidenced based treatment in study administrative health units (AHUs)’, as there were no mental health visits at baseline (and very few in other countries).

Has the logframe been updated since the last review?

- Three output indicator targets (2.2, 3.3 and 3.4.) were increased, as per the recommendations made during the previous annual review.
- During the current reporting period the programme was awarded a 2 year cost extension of £2m. The logframe was extended to monitor progress over this additional period.

## C: DETAILED OUTPUT SCORING

Output Title	Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Proportion of the following key RPC / deliverables completed in consultation with all consortium partners: / - Contracts between partners / - PRIME country personnel / recruited / - M&E framework including / logical framework refined / - Detailed financial management / plan for Phases 2 and 3 / - Capacity Building Plan agreed / - Research uptake Plan agreed	Key programme documents reviewed and revised as / needed during project to improve / progress towards achieving outputs, purpose and goal of RPC.	Target exceeded: documents and processes have been reviewed and revised as needed. Includes better alignment between PRIME`s publication and EoI policy and DFID`s open access policy, and improved processes for meeting structures and lines of accountability.
1.2. Number of meetings held during / inception phase of key governance / groups ( PRIME management group (PMG), consortium advisory group (CAG) Consortium Management Group (CMG))	All groups meet as planned during the life of the consortium (4 meetings annually of the PMG, 2 annual meetings of CAG and monthly CMG meetings)	Target met: all meeting conducted as per the milestone target.
1.3. Draft mental health care plans for priority disorders in primary care and maternal care available.	No target for current reporting period

Key Points

Output moderately exceeded expectations. PRIME is a well-managed and effective consortium and has strong processes and structures for effective oversight, open communication and high levels of participation across the consortium. The RPC hosts: an annual face-to-face meeting, quarterly teleconferences, which include all PRIME partners, and monthly teleconferences between the core PRIME Management Group (PMG). At the country level, teams meet at least every 2 weeks and MoH partners receive regular updates on progress. The community advisory boards (CABs) continue to be an important forum for engaging government officials in the project, and have been successful in 3 out of 4 PRIME countries where they have been established. Scheduling CAB meetings and engaging staff in Nepal has been challenging due to high turnover of senior district officials. Alternative approaches should be taken if this does not improve.

PRIME has made revisions to their Publication policy and Expression of Interest form to ensure that they comply with DFID`s Open Access policy and external researchers can request access to PRIME data. PRIME are also determining whether data can be made publicly available, either in a public repository or on request.

Summary of responses to issues raised in previous annual reviews (where relevant) – N/A

Recommendations
- PRIME to complete the revised research uptake strategy so it can be implemented (December 2017)
- Assumptions must be updated as many currently refer to the inception phase

Output Title	A coherent body of high quality, peer reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders.
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Research project is implemented in Countries	Evaluation of scale up completed in / additional districts in 3 PRIME / countries by 2017	Target not met: Evaluation of scale up completed in South Africa. Completion in Ethiopia, India and Nepal expected by end of year 7.
2.2 of high quality policy relevant / primary research papers by RPC / partners published in peer reviewed / publications.# of conference / presentations by RPC partners.	65 papers published, 55 conference / presentations by mid 2017	Target moderately exceeded: 66 papers published and 59 conference presentations delivered
2.3 No of partner institutions who / collaborate and publish with each / other.	The number of partner institutions / who have collaborated on a non- / PRIME output >5 by mid 2017	Target exceeded: all 9 PRIME partners have collaborated with a non-PRIME partner

Key Points

This output seeks to measure progress of research activities and the production of high quality research. Progress this year met expectations. The programme is building a strong coherent body of mental health literature that is relevant to policy and practice. PRIME research has been published in high impact journals, including The Lancet and PloS Medicine, and four senior members of the PRIME team are currently editing the Global Mental Health Lancet Commission, which will be published in early 2018.
During the reporting period, articles have been published in journals including: PloS One, Global Mental Health and BMC (Pregnancy and Childbirth, Health services research, psychiatry, family practice). Impact factors for these articles range from 1.7-2.8. The most recent publications were from Ethiopia, on: the recognition of depression by primary care clinicians[3]; job related wellbeing (stress and burnout) among healthcare workers[4]; and Antenatal depressive symptoms and maternal health care utilisation[5].
Partnerships and building southern and female research leadership remain strength of the consortium, all publications published during the reporting period had a lead or co-author that lives in a LMIC, and almost half of publications (30/62) were led by women. All PRIME partners have now published jointly at least once and they have collaborated on the publication of 37 other research outputs, facilitating longer term south-south collaborations beyond the PRIME programme.
[3] Fekadu A, Medhin G, Selamu M, Giorgis TW, Lund C, Alem A....Hanlon C, (2017). Recognition of depression by primary care clinicians in rural Ethiopia. BMC family practice, 18 (1), pp. 56
[4] Selamu M, Thornicroft G, Fekadu A, Hanlon C, (2017). Conceptualisation of job-related wellbeing, stress and burnout among healthcare workers in rural Ethiopia: a qualitative study. BMC health services research, 17 (1), pp. 412
[5] Jordans M, Rathod S, Fekadu A, Medhin G, Kigozi F, Kohrt B....Lund C, (2017). Suicidal ideation and behaviour among community and health care seeking populations in five low- and middle-income countries: a cross-sectional study. Epidemiology and psychiatric sciences, pp. 1-10

The target of completing the evaluation of scale up of the PRIME model in additional districts in 3 PRIME countries was not met. Evaluation of scale up activities was only completed in South Africa. Reasons for delays in the other 3 PRIME countries where scale up has taken place included: the state of emergency declared in Ethiopia, which halted research activities; lack of availability of health workers for training in India, due to their deployment to provide support at two major festivals; and the decision to extend the timeframe for scale up in PRIME Nepal in order to collect data on programme sustainability. PRIME expects endline data collection to be completed in these three countries by the end of the grant year.

The cohort studies were not completed by September 2016, as initially anticipated, due to external contextual challenges. All cohort studies are now complete and data cleaning is underway.

Summary of responses to issues raised in previous annual reviews (where relevant)

The PRIME research publication target (indicator 2.2) was extended from 40 to 65 as recommended in the 2016 annual review.

Recommendations
- The output indicator 2.2. target of 75 research publications by the end of the programme (2019) should be moved to year 7 and replaced with a new target of 85.
- Over the next 6-12 months PRIME must ensure researchers are supported to ensure that data analysis can be completed and publications disseminated by the end of the extension phase.

Output Title	Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle income countries.
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 # of PRIME products disseminated to policy makers and donors across relevant sectors via multiple channels (conferences, high level briefings, workshops etc.) at the following levels: Local, National, International	At least 50 PRIME products disseminated to policy makers and donors. / At least 2 PRIME research / results adopted into policy in the study countries (end year 6)	Target exceeded: 80 PRIME products (policy briefs, website articles, research tools, newsletters, posters, brochures and infographics) disseminated to wide range of stakeholder groups. PRIME providing inputs to policy in Ethiopia, Nepal, Uganda and South Africa.
3.2 Participation of mental health / service users and community groups / in mental health care	MH service users taking an active role in service planning or delivery of mental health care in all the districts (end year 6)	Target met: Service users/carers of people with mental health illnesses Involved in service planning and delivery across all PRIME countries.
3.3. # of PRIME citations in the media	At least 160 media citations of PRIME or PRIME outputs	Target exceeded. 173 media citations in local and international media (49 during the reporting period).
3.4 # citations of PRIME outputs in research articles, other academic publications, curricula or training materials	1100 (in Google Scholar) and 650(in Scopus) citations of PRIME outputs	Target exceeded: outputs cited 1606 (google scholar) and 861 (Scopus) times.

Key Points
Output moderately exceeded expectations. PRIME activities to engage target stakeholders and disseminate research outputs and learning remain strong. The programme has cumulatively achieved 173 media citations over the past six years, 49 during the reporting period. In addition to the coverage in print media, the online and broadcasting footprint has grown over past two years. PRIME has made a large impact on the academic work in the field, with 1606 citations in Google scholar and 861 in Scopus. The PRIME website also received 4005 hits during the grant year (reaching a cumulative total of 17,066 by June 2017).

PRIME has used high level meetings to increase awareness of their work, including the “Out of the Shadows: Making Mental Health a Global Development Priority” event in Washington DC. The event aimed to move mental health from the margins to the mainstream of the global development agenda. PRIME presented at the Mental Health Innovation Network Innovation Fair and many PRIME partners took part in discussions. It has been challenging to ensure that service users are included in PRIME’s work in all countries. The success of PRIME`s engagement and dissemination work is clearly reflected through the large number of requests received through PRIME`s expression of interest platform, to use and apply the PRIME model and tools in other organisations and country contexts (see section B for details).

Summary of responses to issues raised in previous annual reviews (where relevant)
Indicator revisions (to increase targets for indicator 3.3 and 3.4 were revised and met.

Recommendations
Based on progress to date, the target for output indicator 3.3 for 2019 should be increased to 250.

Output Title	Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care.
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1. Number of externally funded policy-relevant research grants successfully applied for; and level of funding achieved.	4 externally funded research / grants successfully applied for. > / £10,000,000 in value (Year 6)	Target exceeded: PRIME partners have received 26 external funded research grants to the value of £26,402, 032 (~£14m within the reporting period)
4.2 Number of researchers who complete higher training and/or successfully apply for fellowships	2:5 (M:F) PRIME researchers / successfully graduate with PhD, / 130 registered or completed / masters, 5 successfully applied / for fellowships (Year 6)	Target met: 2 Female students submitted and graduated with PhD. 3 submitted (1 female, 2 male); 190 registered or completed masters; 5 successfully applied for fellowships.
4.3 Number of research publications and other research outputs by PRIME partner groups	Research publications by partner / groups increase by 20% since / end year 5 (Year 6)	Target exceeded: Average of 28% increase in research publications from 2015 to 2016.

Key Points
The output moderately exceeded expectations. This output aims to measure the progress towards increasing resources available and mental health research capacity in lower and middle-income countries.

PRIME maintains a strong track record of building institutional and individual capacity and empowering mental health professionals and researchers, particularly women, in LMICs to carry out mental health research. 5 of the 20 PhD students supported through PRIME have now submitted or completed their PhDs and 190 graduate students have registered or completed public or mental health masters. PRIME also supports junior and mid-level researchers to analyse and write up papers for publication. From 2015 to 2016 the average increase in publications across partner groups was 28% with a range of 7-80%. The groups which had the most established researchers prior to PRIME have tended to be those with the smallest percentage increase because their initial number of publications is much higher. These results show clearly the growth in institutional capacity over time in terms of writing and publishing papers.

At the institutional level, DFID funding has also enabled PRIME partners to leverage £26.4m in grants and fellowships since programme inception (£14.2m secured during the current reporting period) and PRIME senior staff provide teaching and supervision on formal graduate programmes, including: MPhil in Public Mental Health at the University of Cape Town; PhD in Mental Health Epidemiology, Addis Ababa University; MSc in Global Mental Health, London School of Hygiene and Tropical Medicine and King’s College London.

Summary of responses to issues raised in previous annual reviews (where relevant) – N/A

Recommendations
- Add 2018 milestones to the logframe for all indicators.
- PRIME should ensure PhD students are given protected time for data analysis and writing up of their PhDs to ensure they graduate are able to share the findings and recommendations of their work so it has maximum impact on target decision-makers.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Staff time is the main cost-driver for the programme. This is split between the core secretariat and the PRIME programme partners. Other significant costs include, travel/ subsistence and accommodation for dissemination (and other) events as the programme enters its final few years. There has been a reduction in costs related to data collection (including staff costs) as data collection for the scale up phase is less resource intensive.

VfM performance compared to the original VfM proposition in the business case
PRIME adopts principles of economy, efficiency, effectiveness and equity to guide all operations and its strategic visions. The business case outlined vfm measures based on the quality and volume of research outputs, the ability to leverage resources and the approach to economy and efficiency within the planned activities and day to day operations. As per these measurements, the programme continues to demonstrate vfm. Evidence of this includes:
- Ensuring the best value for money for planned activities: each partner has systems in place to ensure that quotes are obtained for equipment and activities and these are appropriately evaluated with regard to cost and quality.
- Maximising efficiency in activities: PRIME has procured a handheld data collection system which is used in India, Nepal, Uganda and South Africa. This helps to ensure accurate data collection and allows PRIME programme coordinators and data management team members to monitor data in real time. This means that data collection errors are spotted quickly and resolved ensuring the integrity of the data sets. The benefits of this system were reflected through the delays in data collection seen in Ethiopia, where these handheld data collection tools were not used.
- Utilising unspent funds to progress other activities that are consistent with the PRIME objectives, e.g. by funding 50% of a post-doctoral fellow to take forward PRIME work; includes modifying and adapting the PRIME ENACT tool to the South Africa context.
- Leveraging over £26m of resources using DFID funds (£7.9m), since programme inception (£14.2m during this grant period). PRIME South Africa has been particularly successful, obtaining three additional grants to further PRIME work. Similar examples of multiplier funding for PRIME objectives can be seen in all PRIME country sites.
- Maximising female and southern research leadership both in terms of recipients of training, graduate studies supported and articles published.

Assessment of whether the programme continues to represent value for money
As demonstrated in the above examples, PRIME continues to represent good vfm across all areas of the programme, including research, capacity strengthening, research uptake and consortium management. In addition to making efficient use of funds and other resources, PRIME has continued to develop and extend the uptake of mental health plans, particular in India where the successes in Madhya Pradesh are being rolled out into other states. Approval of the 2 year extension phase for data analysis, research uptake and dissemination, and expansion of the PRIME model to other countries, will further increase the value of PRIME research by increasing the potential for its use in policy and practise.

Quality of financial management
PRIME has improved the accuracy of financial forecasting year-on-year and in 2016/17 there was approximately a 1% variance between budget and spend. Recently, the main PRIME partner in India lost its ability to accept foreign currency which made disbursing funds within the country challenging. Following a request from PRIME, DFID agreed to advance payments to a second (existing) Indian partner. This enabled work to continue albeit with minor delays while the terms of the advance were concluded. The advance payment process will be monitored closely during the remainder of the programme to ensure that funds are properly retired and maintained at an appropriate level. PRIME should continue to provide accurate forecasting and aim to submit quarterly invoices within 6 weeks of the end of the spend period.
Date of last narrative financial report	29/8/17
Date of last audited annual statement	24/6/17

E: RISK
Overall risk rating: Moderate

Overview of programme risk
The overall risk rating is moderate. although the nature of the intervention (involving mental health patients) presents a “major” reputational risk. Financial and operational systems are robust and PRIME has updated anti-virus software to maintain system security. The Primary risks relate to:
- Changes in senior staff – three changes within PRIME`s leadership team, (replacement of one research director, changes to institutional affiliation of PRIME`s CEO and the second research director) are low risk in terms of impact on programme activities. The new research director was already involved with PRIME in other capacities so this has been a relatively seamless process. PRIME should continue monitor these changes to ensure any negative impacts minimised.
- PRIME has been required to focus on core activities and seek greater efficiencies to ensure that the work plan remains deliverable, due to the weak GBP
- The state of emergency in Ethiopia and the change to a federal government in Nepal has resulted in some delivery risks. PRIME has managed these challenges effectively and, despite some initial delays, research activities are progressing well.
PRIME has successfully attracted multiplier funding to help achieve their larger objectives. There is a risk that incentives and focus shift to work on new activities, reducing the quality and/or quantity of research outputs. To mitigate against this, PRIME have put in place clear timelines for expected outputs to be delivered, and meet regularly with staff to ensure progress is closely monitored.

The fiduciary risk has not changed since inception of the programme. There is clear, regular reporting and oversight on finances at management and operational level. The PRIME country fraud and anti-corruption policy has been in place for three years. To date there have been no cases of fraud or misappropriation.

Outstanding actions from risk assessment
PRIME recently revised its relationship with Indian partners following the foreign currency restrictions placed on Public Health Foundation India (PHFI) by the Indian authorities. This has involved revising partnership agreements and working with DFID to establish a process for advance funding of Sangath who are now the primary partner within India. PRIME will continue to monitor the political situation in PRIME countries in order to minimise the impact of any external risks.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
Completion of the workplan is mainly on track to deliver within the proposed timescales, although some data collection activities are continuing into the extension phase, to overcome slippage and to collect data on the sustainability of the programme. The delays in Ethiopia, due to the State of Emergency in 2016, are now being addressed and the Ethiopian team is on track to complete the work by October 2017. PRIME has an ambitious set of objectives for the remainder of the programme and should continue to keep DFID advised of any delivery concerns.

Performance of partnership(s)
Over the past 6 years PRIME has built a significant amount of trust and good working relationships with its programme partners. At the beginning of each year, all partners agree activities for the year ahead (by quarter). These are reviewed regularly to ensure that they remain relevant and delivery is kept on track. Late submission of financial reports (and other management information) from partners can occasionally create challenges for the PRIME core management team, however these issues have not interfered with the partnership overall.

Asset monitoring and control
The PRIME core team maintain a central register which is built up from annual asset returns from partners. UCT conducted early financial management audits in years 2 and 3 which reviewed partner systems, including asset management. Where there were questions over controls, spot checks were carried out to ensure that systems were robust. PRIME report that there have been no concerns about the financial management of any of the partners raised with the PRIME management team since the audit and spot checks were completed.
G: CONDITIONALITY

Update on partnership principles (if relevant)
Not applicable. DFID provides funding to the RPC through the lead institution and no funding flows directly through any Governments.

H: MONITORING & EVALUATION

Evidence and evaluation
The PRIME theory of change assumed that achieving outputs would enable PRIME`s world class research on implementation and scaling up of treatment programmes for mental disorders to be adopted by policy makers & practitioners for the benefit of the poor including mothers. This in turn would contribute to the impact of widespread implementation of mental health programmes that improve the health and socio-economic status of individuals, particularly women and those living in poverty.

Based on evidence collected during this annual review, the majority of assumptions underpinning the theory of change remain relevant and appear to hold true. PRIME should continue to monitor and update based on the current work plan, as a few assumptions still refer to the inception phase. There is a high risk that the following assumptions do not hold true during the next grant period and in part have already impacted on programme progress; PRIME should monitor these assumptions closely and take action where possible to prevent their impact on the programme:
- Stakeholders/beneficiaries available and interested in participating in meetings - as discussed previously under output 3, service user involvement in delivery and programme design has not met expectations.
- The countries and their health systems remain stable enable to implement and evaluate the programme – this did not hold true in Ethiopia for part of the reporting year due to the state of emergency.
- Political buy-in is obtained despite competing priorities – high risk that this does not hold true in Nepal due to the change to a federal government
- Any turnover in health staff is well-managed and does not impact on the programme implementation or quality – high turnover in health staff in Nepal has reduced their attendance at CAB meetings
- Individual capacity, and capacity to supervise PhD students, is retained within institutions - there is no evidence that this is being monitored by PRIME

In addition to regular monitoring and reporting on the logframe and theory of change, PRIME provides: quarterly narrative reports, quarterly financial reports, monthly meetings between core PRIME staff (including representatives from all PRIME partners), monthly implementation logs and weekly data management updates. New procedures put in place this year include: reporting against the results framework indicators through the online platform ResearchFish and regular bilateral quarterly meetings where PRIME provides updates on research activities, risks and financial activities. In the last 6 months PRIME have conducted a formal research uptake evaluation. The programme will use the results to revise the PRIME research uptake strategy to maximise its impact on research influence during the extension phase.

In summer 2015, an independent midterm review was conducted. PRIME has successfully responded and addressed all six of the review team`s recommendations.

Monitoring progress throughout the review period
This review was carried out by members of the Health Team in DFID’s Research. During the reporting period members of the DFID team have: attended the biannual Consortium Advisory Group; had two face to face meetings and frequent telephone and email engagement with the Senior Management Team; and instigated quarterly catch-up calls with the DFID and PRIME teams, on progress, challenges and highlights, risks and any financial management. The review team also used supporting materials including annual and other reports from PRIME, the PRIME website, data from the online platform ResearchFish, key articles published by PRIME and regular e-mail update.