Project Completion Review - Top Sheet

Review Date:	August 2017

Title: Accelerating the Rise in Contraceptive Prevalence in Uganda (ARC)
Programme Code: 202420	Start Date: 16/09/11	End Date: 30/07/2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	A	A	A	B	A	A
Risk Rating	Minor	Minor	Minor	Moderate	Moderate	Moderate

Financial Position
Original Programme Value	£35,000,000
Extensions/ amendments	Extensions: The programme was extended from 31 December 2015 to 30 September 2016 and again to 31 July 2017 at no extra cost. These extensions were required because the project delivered at a slower pace than originally planned, mainly due to the programme being temporarily suspended between June 2014 and April 2015. / Amendments: The Delegated Cooperative Agreement (DCA)[1] between DFID and USAID for managing the ARC programme was amended twice: 10 December 2013 and 2 September 2015. These changes were made to (i) re-programme activities to ensure delivery of expected results (ii) to change the implementing partner.
Log-frame revisions	The logframe was revised on an annual basis.
Total programme spend	£ 30,635,813
[1] DFID signed an agreement with USAID, in which USAID was tasked to manage both the funds and contracts with implementing partners under the ARC programme on behalf of DFID.

Follow up actions required following closure
1. The DFID Uganda team should ensure that the lessons learned are shared across the DFID network and are used to inform the implementation of DFID’s new programmes including those that address specific family planning challenges (e.g. RISE - Reducing high fertility rates and Improving SExual reproductive health outcomes in Uganda) as well as broader human and economic development programming.
2. DFID Uganda, together with other stakeholders, should work with the Ministry of Health (MoH) to finalise the development of the Social Behaviour Change Comminucation (SBCC) strategy, that clearly outlines key family planning messages and the role of central and district stakeholders in behaviour change communication.
3. DFID Uganda should use its new RISE programme to strengthen systems for better family planning service delivery, through building the capacity of health workers in quality service delivery and supply chain management. In addition, DFID Uganda should, together with the Family Planning 2020 (FP2020) focal points, intensify advocacy for increased domestic financing for family planning, and prioritising of the young people and those in hard to reach locations in order to accelerate the achievement of Uganda’s commitments at the July 2017 summit in London.
4. Marie Stopes International Uganda (MSIU), under the follow-on Preventing Maternal Deaths[2] (PMD) programme, should intensify the mentorship process for the 100 public health workers who did not meet the recommended quality score under the ARC programme, to ensure they meet the expected standards.
  [2] Following the closure of ARC, central funding was secured for a period of one year, from DFID under the multicountry family planning programme –Preventing Maternal Deaths to ensure continued service delivery as we set up the new bilateral family planning programme-RISE.
5. DFID, through the RISE programme, should work with the Government of Uganda (GoU) to develop a cost effective and coordinated capacity building strategy for health workers who provide family planning services in the public and private sector. This should include strengthening ownership and participation in family planning outreaches.
6. USAID should submit to DFID a final narrative and financial report to establish if there are any unspent funds to be returned to DFID’s central contingency fund.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3719238.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5191622.xls

Outline of programme and what it has achieved

Context: Addressing Uganda’s population challenge will require sustained delivery of proven interventions at scale. During the July 2017 family planning summit in London, Uganda presented its expanded family planning commitments that aim to curb the growing population challenge (Annex A).

Uganda’s fertility and population growth rates are among the highest in the world. In 2016, as evidenced by the Uganda Demographic and Health Survey (UDHS), there was a 28% unmet need for family planning, and a 35% contraceptive prevalence rate. This is an improvement on the situation in 2011 where 34.3%[3] of women had an unmet need for family planning (nearly 40% of which was for long term and permanent methods). Only 31.9% of women were using modern contraception in 2011; this was an increase from 24% in 2006. The abortion rate for Uganda is slightly higher than the estimated rate for the East African region. Over half of all pregnancies in Uganda are unintended, 38% of which end in abortion, contributing to 8% of maternal deaths[4]. The burden of unwanted pregnancy and its consequences in Uganda disproportionately falls on poor women and adolescents.
[3] Uganda FP2020 CIP – Family planning 2015-2020 page2
[4] Guttmacher institute 2017

ARC Programme Overview: DFID Uganda committed to provide £35,000,000 for the implementation of the ARC programme between 2011 and 2017. The ARC programme aimed to save the lives of women during pregnancy and childbirth, through partnerships between state and non-state actors. The programme focused on improving the range of available choices, particularly long-term and permanent contraceptive methods and ensuring that the poorest groups benefited most from the programme through rural outreach.

Funded jointly by USAID and DFID, during the period, the programme contributed to over 70% of the family planning funds for Uganda. This funding aimed to increase the coverage of high quality long term and permanent family planning methods, including through proven delivery channels such as outreach and social franchising with vouchers. DFID-attributable outputs, as stated at the start of the programme, included better information about family planning choices, fewer barriers to accessing family planning services, a better supply of quality family planning services and better choices of family planning methods.

Between 2011 and 2014, the programme was implemented by Marie Stopes Uganda (MSU). Marie Stopes International Uganda (MSIU) was the implementing partner from April 2015.

The ARC programme contributed to the equitable increase in the method mix for family planning. For example implementation by the Uganda Health Marketing Group (UHMG) led to an increase from three to five Long Acting Reversible Contraceptive (LARC) products offered through social marketing. Similarly, evaluation of the SBCC component implemented by Communication for Healthy Communities (CHC) showed an increase in awareness of modern contraception from 78% to 88% in the communities evaluated in East-Central Uganda. Quarterly monitoring of the programme showed an increase in access to quality family planning services with 19% of young people (15-19 years) and 32% of 20-24 year olds accessing LARCs of their choice. Such improvements could be attributed to increased awareness of the need to delay pregnancy and the available contraceptive options, through interpersonal communication, media exposure, reduced physical barriers to access and the improved supply of family planning commodities realised through procurement.

The ARC programme also contributed to an improved health system through enhancing health worker capacity to provide quality services, and manage the family planning commodity stocks to ensure adequate supply. The procurement of family planning commodities under the ARC programme benefitted from donor subsidised global rates, with a 55% price reduction on implants (from $18 for Jadelle and $16.5 for implanon to $8.5 per unit) leading to savings of £3,096,630. These savings were used to procure more implants for the programme, reaching more women and girls with their method of choice.

A value for money assessment of ARC (Annex B) estimated the Social Return on Investment (SROI) to be $21.40, implying that each dollar spent on the project generated a social benefit of $21.40, the larger part of this benefit accruing to women and young girls.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment
The ten-month pause in programme implementation and slow uptake of services when the project re-started in 2015 was associated with slower progress than planned against the original milestones. Good progress has since been made in 2016 and 2017 in order to deliver the milestones.

The table below highlights progress in delivering on the three programme outcomes:

Outcome indicator		Baseline	2012	2013	2014	2015	2016	2017
1. Contraceptive prevalence rate (modern methods: women of reproductive age)	Milestone	25.6%[5]	28.1%	30.6%	33.1%	34.6%	35.6%	35.6%
	Achieved		30.2%	30.6%	-	31.8%	32.2%	35%
2. Couple Years of Protection (CYP) delivered through ARC	Milestone	0	666,666	1,323,988	-	174,195	850,374	317,74210
	Achieved		953,268	1,029,417	-	79,486	403,031	609,398[6]
3. Cost per CYP- per delivery channel	Milestone	Outreach	-	-	-	£5	£2.50	£8.5
	Achieved		-	-	-	£8.57	£10.97	£7
	Milestone	Social Franchise	-	-	-	£7	£3.00	£6.5
	Achieved		-	-	-	£24.91	£7	£6
[5] Sources for outcome indicator 1: baseline (UDHS 2011); 2015 (PMA 2015); 2016 (PMA 2016) 2017 (UDHS 2017) - Although the baseline and final CPR was estimated from the UDHS reports, CPR rates in between were estimated from another independent survey the PMA as the UDHS is conducted once in five years.
[6] The earlier half of ARC implementation was characterised by falsification of results, while measures were instituted to mitigate this risk in the latter half of the programme, albeit with high unattainable targets that called for a downward revision during the annual review.

Modern Contraceptive Prevalence
The ARC programme aimed to contribute to an increase in the use of modern contraception in Uganda. This outcome was tracked through the Contraceptive Prevalence Rate[7] for modern methods (mCPR) and this section outlines the performance of the ARC programme in that regard.
[7] The percent of women of reproductive age who are using (or whose partner is using) a contraceptive method at a particular point in time, reported for women married or in sexual union. The measure includes all contraceptive methods (modern and traditional), but it may include modern methods only. The indicator is calculated as follows: (# of women 15-49 using a contraceptive method / total # of women 15-49) x 100

The mCPR in Uganda has shown an upward trend from 25.6% in 20116 to 35% in 20169. With a 9-percentage point increase in mCPR over six years, the average annual increment is estimated at 1.5%, suggesting potential to lower fertility rates in Uganda; the success is attributed to demand creation and increased choice of available methods.

Uganda set a target to reach a 50% Contraceptive Prevalence Rate (CPR) by 2020. It lags behind its regional couterparts, including Kenya and Rwanda, who have attained a CPR above 50%[8]. In the East African region the average CPR is projected to grow from 40% in 2015 to 50% in 2030. Uganda needs to make significant progress with its results and approach in order to compare more favourably within the region.
[8] UN 2015: Trends in Contraceptive use worldwide

Couple Years of Protection Performance
The ARC programme targeted to attain 3,332,965 Couple Years of Protection[9] (CYP). There was mixed progress against this indicator over the years, and by its end, the programme had achieved 92% of the original target. The focus on equity led the programme to maintain a mix of delivery options even though some did not deliver many CYPs. As anticipated, intrauterine devices (IUDs) and implants were the biggest contributers of CYPs, denoting a shift in the uptake of Long Acting and reversible contraceptives (LARCs).
[9] Couple years of Protection - estimated protection provided by family planning services during a 1-year period, based on the volume of all contraceptives sold/distributed free of charge to clients during that period. https://www.measureevaluation.org/prh/rh_indicators/specific/fp/cyp

Cost per CYP
The cost per CYP was not tracked in phase 1 of the implementation of ARC. The indicator was introduced in 2015 to inform the monitoring of value for money. The cost per CYP varied significantly throughout the programme. In 2015, the high cost of delivering the social franchise component was driven by the initial costs associated with accrediting new health facilities as well as setting up new data and voucher management systems. The cost reduced as the programme took shape.

The high costs associated with the dedicated provider model[10] was a key driver of the cost of delivering outreaches. The model focused mainly on training and was thus not generating many CYPs. It was however deemed appropriate to maintain it, as in the long term it aimed to strengthen the health system to provide routine family planning services during and beyond the life of the ARC programme. By the end of the programme, the cost per CYP was in line with the benchmarks in the business case.
[10] The project placed up to 75 health workers (Dedicated Providers of family planning) at public health facilities across 43 districts, in the East-Central, Eastern, West Nile and Northern regions. These health workers were tasked to: to provide family planning services; on-the-job training

Output Score and Description: A Based on the progress during the duration of the programme, the programme met expectations.

Achievements
The ARC programme made a substantial contribution to Uganda’s progress to increase the use of modern contraception and hence the CPR. This is attributed to the harmonised implementation of a mix of interventions including social behaviour change communication (SBCC), expansion of available options through promoting long acting methods, improving the knowledge and skills of health workers to deliver quality family planning services and adaptability of the programme to target hard to reach populations (e.g. the urban poor living in slums, young people and those living on islands and mountainous areas). The approaches collectively aimed to address various barriers to contraceptive use.

The programme implemented a range of SBCC activities including mass media, community media and interpersonal communication. Data from the ARC quarterly monitoring reports shows that 75% of the people turning up at the outreach sites took up a contraceptive method after listening to the family planning messages. The endline evaluation of the SBCC campaigns showed that awareness of modern contraception increased from 78% to 88% in the east-central region of Uganda, with 34% and 43% increases in those seeking advice and those seeking to take up contraception respectively.

The expansion of family planning options through promoting long acting methods realised a shift in the trend from the use of short term to long term and permanent methods across age groups. Compared to other methods, implants and IUDs generated the highest number of CYPs, and this has guided advocacy efforts with government to increase the range of contraceptive options.

Challenges
The major challenge was the negative media surrounding the delivery of family planning to young people and the ensuing lack of access to information among this age group. The former was exacerbated by the delay in finalising the adolescent health policy and national sexuality education frameworks which were expected to guide this process. In addition, the interruption to programme implementation generated concern among communities which meant they were reluctant to re-engage with the project when it re-started. As noted above, the programme was granted two “no-cost” extensions to enable the achievement of the intended results.

Key lessons from implementation of the programme include:
1. Interpersonal communication (IPC) is a stronger tool compared to mass media communication for influencing changes in behaviour regarding use of family planning. This is because the biggest barriers to use of family planning are largely related to strong social and cultural norms. IPC activities designed for young people and delivered by their peers will be critical for increasing uptake among this group.
2. Boys, men and parents are key influencers on family planning decisions for girls and women. Interventions that target these groups will be critical for increasing uptake and continued use of family planning.
3. To avoid coercion, family planning programmes must institutionalise controls to ensure service teams maximise their time in the field, as opposed to pushing for results. Providing job aids[11], conducting regular monitoring field visits and quality checks will safeguard the users.
  [11] Job aids include policy guidelines and service standards, counselling guides, standard operating procedures, etc.
4. While the outreaches increase access to family planning by the largely rural and poor community, they may be adapted to include urban outreaches to increase access for the urban poor. Social franchising on the other hand is better for those in semi-urban/urban localities who cannot afford to pay the full amount for the services. This ensures that the free services are reserved for the most vulnerable. The design of family planning programmes must thus consider a total market approach[12] and purposively target young people, the urban poor and those in hard to reach locations to maximise yield.
  [12] Total Market Approach (TMA) - A total market approach can be applied to develop strategies that increase access to priority health products in a sustainable manner. The approach develops the market for health products by better targeting free or subsidized products, reducing inefficiencies and overlaps, and creating room for the private sector to increase its provision of health commodities.
5. To ensure sustainability and hence value for money, family planning programmes should, in addition to service delivery and skills building, seek to generate evidence that will inform more strategic approaches to the population challenge and advocacy for incremental government allocations via the budget process. This includes how investments across government can contribute to the desired family planning outcomes

Lessons from the implementation of the ARC programme have been shared through national level fora including the national family planning conferences; family planning technical working groups (FP-TWG) meeetings and international meetings at which MSI/MSU made presentations. Learning from the ARC programme has influenced the task sharing policy which allows lower level health workers to take up the provision of LARCs, thus freeing up doctors’ time to attend to more complex tasks.
## C: DETAILED OUTPUT SCORING

Output Title	Women and men have better information to make healthy reproductive choices
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Status
Output Indicator 1.1: / Number of people reached with FP messages through IPC and community mobilisation activities	2013:70% of popl’n	65% of popl’n	Met expectation / A
	2014: 700,000	553,430
	2015: 25,706	25,911
	2016: 125,722	230,395
	2017: 115,198	115,312
Output Indicator 1.2: / Number of IPC touch points through Communication for Helth Communities (CHC)	2011-12: Not set	-	Outputs moderately exceeded expectation / A+
	2015: 2,840	5,000
	2016: 51,750	65,160
Output Indicator 1.3: / Number of Family Planning radio mentions through CHC	2011-14: Not set	-	Met expectation / A
	2015: 1,350	1,350
	2016: 70,000	73,440

Successful family planning programmes need a strong emphasis on appropriate messages for targeted groups. This includes the use of interpersonal communication, community and mass media to bridge the gap between knowledge and behaviour change, and ensure that women and men have better information to make healthy reproductive choices. This output was tracked through three indicators and this section outlines the performance of the ARC programme in that regard.

Key Points
Despite slow performance at the start, the project achieved the set target for the number of people reached with family planning messages (41% of those reached were young people, 15-24 years).

The SBCC component implemented by CHC started with operational research that informed the kind of messages and delivery channels that would appeal to the target population. Success in delivering this output is attributed to the use of evidence based messaging for the different communities, age groups and genders. Using the 94% radio listenership in Uganda, radio remained a key tool to reach large numbers with family planning messaging. However, deeply rooted norms,cultures, myths and misconceptions meant that this was not necessarily the best way to communicate on the fear of side effects (a key determinant of whether the person continues family planning or not), hence the move to enhance interpersonal communication.

Despite the achievement of this output, challenges remain in demand for family planning among young people, owing to myths,misconceptions, negative community attitudes and limited channels that are effective in reaching different age groups or genders.

Summary of responses to issues raised in previous annual reviews

A continued focus on behaviour change interventions including communication is necessary for increasing demand.
Structured community dialogues were incorporated into the IPC awareness raising activities. The dialogues focussed on the various family planning methods, side effects, myths and misconceptions. Some dialogues were youth focused and involved the use of youth peer educators for mobilization and the screening of film shows. Other Social Behaviour Change Communication (SBCC) interventions included radio talk shows.

Continued discussions with MoH on the wider systemic challenges that influence uptake of family planning such as human resource and commodities security is critical.
DFID along with other stakeholders such as USAID, through national fora such as the FP2020[13] task force, and the maternal and adolescent health technical working group, routinely engaged the Ministry of Health on key system barriers to the uptake of family planning. Through the Reproductive, Maternal, Newborn and Child Health (RMNCH) commodity security working group, DFID contributed (though ARC) to the national quantification of RMNCH supplies, and supported the national efforts to transition from Implanon classic to Implanon NXT[14], through training health workers at the ARC outreach sites, and MSIU leading the redistribution of the old Implanon classic stocks to prevent expiry.
[13] Family Planning 2020 (FP2020) is a global partnership that supports the rights of women and girls to decide, freely, and for themselves, whether, when, and how many children they want to have.
[14] Implanon classic and NXT are a one-rod implants containing the hormone etonogestrel (ETG) that provides contraceptive protection for up to three years. The production of Implanon classic has been phased out and it is being replaced with Implanon NXT. Implanon NXT is a subdermal contraceptive implant identical in composition to Implanon classic. Both contain ETG, are prequalified by the World Health Organization (WHO), and are more than 99% effective at preventing pregnancy. As opposed to Implanon classic, Implanon NXT uses an improved insertion device, thus the need to train health workers in its insertion..

Review key interventions that target boys, men and parents as key influencers on FP decisions for Adolescent Girls and Young Women (AGYW) that could be implemented in the remaining period of the programme.
A male engagement strategy, “the three wise men” was developed and used by the IPC coordinators as a guide to engage men as influencers and promoters of family planning in the community. A pool of boys and girls were trained as peer educators to spearhead demand creation and awareness activities among their peers.

Future DFID programming on family planning should explore options to provide integrated services for the AGYW including on nutrition and linkages to other empowerment programmes to provide incentives to delay pregnancies.
DFID’s new programme on family planning (RISE) will integrate with other DFID programmes including on nutrition in Karamoja, malaria and education to improve the wellbeing of young women and increase awareness to delay future pregnancies.

Recommendations for future programmes

1. Through the UNFPA implemented component of the RISE programme on addressing the broader population challenge in Uganda, DFID will work closely with both the health and education sectors to accelerate the finalisation and dissemination of the national sexuality education framework, the adolescent health policy as well as the policy guidelines and service standards for sexual reproductive health, to increase access to age appropriate information and services for young people.
2. Through the RISE programme DFID Uganda should intensify family planning dedicated SBCC to address the deeply rooted norms and cultures, myths and misconceptions and negative community attitudes that form a barrier to accessing family planning messages. The SBCC will particularly target the negative perceptions on the use of contraception by the young people.
3. DFID should build on the work under the Girls Education Challenge and other centrally funded programmes for young people to drive innovative interventions to promote sexual reproductive (SRH) messages in secondary schools and tertiary institutions, as well as in the community to increase awareness among young people in and out of school.
4. MSIU under the follow-on centrally funded family planning programme Preventing Maternal Death, should debrand all programme assets and rebrand them with UKaid logos; similarly, all vehicles should be deregistered from USAID to DFID ownership.

Output Title	Women and men face fewer barriers to accessing Family Planning services
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones[15]	Progress	Status
Output Indicator 2.1: / Number of LAPM vouchers redeemed through accredited service delivery points (attributable to DFID)	2012: 21,000	8,463	Outputs moderately did not meet expectation / B
	2013: 59,000	56,773
	2014: 79,000	92,547
	2015: 13,531	3,312
	2016: 71,039	32,224
	2017: 16,112	44,042
	TOTAL: 259,682	TOTAL: 237,361
Output Indicator 2.2: / Number of Long Acting and Permanent Methods (LAPM) provided by outreach at public health sector facilities (attributable to DFID)	2012: 62,000	94,641	Outputs moderately did not meet expectation / B
	2013: 72,000	116,805
	2014: 83,600	Results flawed
	2015: 27,930	14,932
	2016: 131,819	53,539
	2017: 26,770	64,268
	TOTAL: 404,119	TOTAL: 344,185
Output Indicator 2.3: / Percentage of HCWs that score above 85% on the QTA score after the training and mentoring process	2015: 70%	Not done-new programme	Outputs moderately did not meet expectation- B
	2016: 75%	Not done
	2017: 40%	43%
[15] 2015 and 2016 were characterized by very ambitious and unachievable targets hence the recommendation at the 2016 annual review to have a downward review of the 2017 targets.

Barriers to accessing family planning services exist on the demand and supply sides of the health system. This section outlines DFID’s contribution to increasing access to long acting and permanent methods of family planning through the ARC programme

Key Points
The ARC programme sought to deliver family planning services through a mix of interventions to achieve a total market approach. Performance was slower than expected, particularly when the programme re-started in 2015. Client confidence was gradually regained through intensifying SBCC messaging, maintaining high quality services and reassuring the community by satisfied users. In addition, systems to improve voucher redemption rates were institutionalised.

Training and capacity building are related to Health Care Worker (HCW) capacity to provide quality services and drive demand. Over the life of the programme, in areas where there had been training, it was noted that more people came for services as HCWs were more equipped to provide necessary information for informed choice, provide quality services and manage adverse effects. However, lack of incentives for HCWs to enrol and complete the mentoring programme prohibited the attainment of higher performance under this output.

Despite the progress made to increase access to quality family planning services, challenges remain with reaching the hardest to reach populations with quality services, owing to the high cost of delivery and the lack of incentive by the qualified health workers to stay in such areas. This calls for renewed efforts by government to increase the deployment and retention of critical HCW cadres in hard to reach areas.

Summary of responses to issues raised in previous annual reviews

MSIU to continue supportive supervision and mentoring of CBDs to improve on reporting.
A two day training was conducted for community based distribution staff, with the aim to enhance their skills in family planning counselling, mobilization, marketing of services and reporting. In addition, guidelines and tools were developed to track performance on a weekly basis. Performance reports were used to inform support supervision.

MSIU to continue working closely with the Blue Star proprietors to understand the reasons for the high staff turnovers and identify what MSIU can do to support staff retention in these facilities.
Staff attrition among the social franchises was attributed to poor working facilities, lack of sufficient motivation and poor remuneration. Results-based financing and increased training opportunities were suggested as potential solutions to the high attrition. To respond to the challenge, human resource and business management training was conducted for proprietors of the BlueStar clinics. Facility based training was also piloted in one region to reduce on the time the health workers spend out of the facility. The number of social franchises with a trained health worker at any time improved from 72% to 92%.

Recommendations for future programmes

1. DFID Uganda, through the FP2020 focal points, should work with the GoU to strengthen partner capacity and coordination to provide family planning services to high burden and hard to reach populations including refugees, the urban poor and those residing on islands and mountainous areas.
2. DFID Uganda should, in the future, ensure adequate communication of service interruptions in order to minimise negative perceptions that decrease the uptake of family planning.
3. DFID Uganda, through the RISE programme, should work with the Ministry of Health and local governments to develop cost effective, coordinated and incentivised strategies for health worker capacity building, to ensure dedication and regular attendance by the HCWs as well as learning.
Output Title	A better choice of family planning methods is available and being used
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones[16]	Progress	Status
Output Indicator 3.1: Number of implants and IUDS provided by MSIU programmes (attributable to DFID)	2012: 70,000	76,023	Met expectation / A
	2013: 135,000	147,125
	2014: 174,000	163,113
	2015: 34,674	16,926
	2016: 170,160	104,770
	2017: 52,385	119,333
	TOTAL: 636,219	TOTAL: 627,290
Output indicator 3.2: / Number of tubal ligations/vasectomies performed	2012: 26,400	27,081	Outputs moderately did not meet expectation / B
	2013: 31,100	26,138
	2014: 34,620	Results flawed
	2015: 6,787	1,319
	2016: 32,698	5,278
	2017: 2,639	4,336
	TOTAL: 134,244	TOTAL: 64,152
[16] 2015 and 2016 were characterized by very ambitious and unachievable targets hence the recommendation at the 2016 annual review to have a downward review of the 2017 targets.

The reproductive health policy guidelines and service standards for Uganda require that women have access to a family planning method of their choice. The ARC programme sought to increase the choice of contraceptive method through providing long acting reversible and permanent methods. This section highlights ARC’s contribution to the better choice of family planning methods.

Key Points
As with other outputs, progress was slower than expected but performance picked up in 2016 following improved social and behaviour change interventions. The ARC programme created a shift from the short acting methods (injectables and pills) to the use of Long Acting Reversible Contraceptives (LARCs), and this evidence has been used to advocate for expansion of the range of government procured commodities to include LARCs. Among young people, however, short term methods remained the preferred choice.

Throughout the programme, the delivery of services was characterised by challenges in collection and utilisation of data to inform market segmentation and estimate the contraceptive needs of the population.Through the implementation of the ARC programme, we observed that choice of method was driven by testimonies from satisfied users, the absence of side effects and whether the woman wished to stop or delay child birth.

Summary of responses to issues raised in previous annual reviews

DFID and USAID to broker discussions between MSIU and MoH to clarify the role of Dedicated Providers and agree how best to achieve the objectives of the model.
The Ministry of Health (MOH) supported of the mentorship process by the Dedicated Providers, and played an active role in the review of assessment tools and pilot assessment of HCWs who completed their mentorship programme. MOH also adopted the MSIU competency assessment checklists for the draft mentorship manual for RMNCAH services (the first attempt at an integrated manual for mentorship of public health workers). Further work is required to improve understanding and ownership at the regional and district levels.

DFID and USAID should raise the issue of lack of prioritization and ownership of FP at the district in the family planning technical working group as well as the FP2020 task force to work out ways of strengthening district planning and prioritization of FP services.
The Family Planning Costed Implementation Plan (FP-CIP) was agreed as a tool that will improve planning and prioritisation of family planning. Progress has been made with the development of a performance monitoring tool for the FP-CIP at the national level with a web based database for capturing inputs by all stakeholders. The FP-CIP has been rolled out in some districts and the ministry of health is engaging family partners to support the roll out in other districts.

MSIU to put more focus on training the public facility health workers in youth friendly health services and negotiate for more private spaces for counselling the AGYW.
Service providers across the various delivery channels have been trained to speak to the contraceptive needs of young people. The training included building their competence to provide counselling as well as to safeguard the rights of adolescents/young people with a focus on privacy, confidentiality, informed consent, safety, and correct information. The Dedicated Providers model this approach as they mentor public health workers.

Recommendations for future programmes

1. DFID through the FP2020 task force should continue advocacy with government towards the inclusion of LARCs on to the list of commodities procured by government through the National Medical Stores (NMS), so as to improve the range of options and choice of family planning method.
2. In addition to imparting skills for quality service delivery, future health worker capacity building programmes to include data management and utilisation for quantification and forecasting to improve commodity stocks.
3. The Ministry of health should invest in stakeholder relationships including with civil society, development partners and the private sector to drive value for money through harmonisation of programming and proper market segmentation towards achieving a total market approach to family planning service delivery.
D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance[17]
[17] Exchange rates for this report are based on MSIU June 2017 rates. $1.29 to £1. UGX 4,628.89 to £1.

Financial Performance
DFID commited to spend £35m for implementation of the ARC programme. The programme had by its end utilised £30.6m. The unspent funds were due to a pause in programme implementation between 2014 and 2015. Financial performance was mixed over the project with no disbursements during project suspension and then slow start-up of phase 2 in 2015. A no-cost extension for a period of 10 months, ending 31 July 2017 was put in place to enable the project to make progress and deliver intended results. As of July 31, all of the funds disbursed to MSIU had been either obligated or expended.

Key Cost drivers
The key cost drivers for the first part of ARC implementation by MSU and UHMG were operational costs, while labour (salaries, fringe benefits and allowances), travel and other direct costs dominated the latter half of ARC implementation by MSIU. The cost of improving quality standards among the social franchises and the roll out of Implanon NXT escalated the training costs. Annex C and D present a detailed analysis of the cost drivers.

VfM performance compared to the original VfM proposition in the business case
The key value for money indicator in the business case was the cost per CYP. Although the programme achieved less CYPs than originally targeted, the cost of delivering the CYPs was also less. By the end of the programme, the cost per CYP was £7, reflecting a 36% reduction from £11 originally proposed in the business case.

The procurement of family planning commodities under the ARC programme benefitted from donor subsidised global rates, with a 55% price reduction on implants, from $18 for Jadelle and $16.5 for implanon to $8.5 per unit, leading to savings of £3,096,630. The savings were used to procure more implants for the programme, therefore reaching more women and girls with their method of choice. Annex E summarises the VFM performance in comparison to benchmarks in the business case.

Assessment of whether the programme represented value for money
The delivery through a Delegated Cooperative Agreement (DCA) with USAID and the procurement of commodities through the International Procurement Agency (IPA), were key cost savers for the programme. The DCA improved efficiency due to coherence and harmonisation by the two largest family planning donors in country. It also led to the realisation of savings on both the upfront costs of setting up a new programme as well as management costs, while drawing on USAID’s financial and programme management systems to enhance accountability. The inputs to the programme were a good demonstration of value for money as evidenced by the drop in cost of delivering each CYP to below the business case benchmark. Furthermore, learning from programme evaluation led to the introduction and strengthening of information systems (CLIC and MarieTXT[18]) to further mitigate fiduciary risks.
[18] The Client Information Centre (CLIC) is a computer based information management system which was used to capture real time data during sessions with the client. It has in-built controls to mitigate against mismanagement of data. Likewise, the MarieTXT ensured proper management of the voucher system.

In terms of effectiveness, the programme contributed to improved access and uptake of family planning including among vulnerable groups like young people and hard to reach areas. Data from the UDHS shows that there was a significant increase in the mCPR, with a shift from short term to the use of LARC and LAPM, which generate more CYPs. A recent value for money assessment estimated the Social Return on Investment (SROI) to be $21.40, implying that each dollar spent on the project generated a social benefit of $21.40, the larger part of this benefit accruing to women and young girls. The key long term benefits for women were improvements in family planning choices, improved family relations, better health status of the mother, and improved family economic welfare.

A focus on family planning is a priority for DFID Uganda. The ARC programme has been useful in generating evidence for DFID to engage and influence family planning policy and delivery, and also to inform the design of DFID Uganda’s new family planning programme. As highlighted in this report, the shift from using short to long term methods observed under the ARC programme, has informed the advocacy efforts for government to include LARCs on the list of government procured family planning commodities. Learning from ARC informed the decision to combine SBCC, systems strengthening and a range of service delivery oprions under the RISE programme.

Quality of financial management during programme
All funding for this programme was disbursed to USAID who provided quarterly narrative and financial reports. USAID demonstrated good financial management, open communication and follow up with implementing partners.

Date of last narrative financial report	31st March 2017
Date of last audited annual statement	n/a. USAID does not provide audited statements. Audits are conducted for the whole USAID portfolio and are not specific to Uganda. Only financial reports are shared. In the event that the audit picks up an issue relevant to the DFID programme, this would be shared.

E: RISK

Quality of risk management over the life of the programme
Review of the risks and risk mitigation strategies was completed during quarterly review meetings with USAID/MSIU and the other partners. DFID also reviewed programme risks on a monthly basis during meetings between the Senior Responsible Owner and programme manager, updating the risk register accordingly.

Overall risk rating: Moderate

Overview of programme risk
The risk rating of the programme was driven mainly by the likelihood of misuse of funds (misappropriation of funds, over reporting of results or fraudulent reimbursements on the voucher system). With the institutionalisation of mitigation measures, the residual fiduciary risk was rated moderate. Other risks included reputational risk linked to the UK being associated with funding abortion as a method of family planning, failure of partners to implement and manage the programme, safeguards/biohazard risks associated with coercion, poor quality services, and the provision of services to young people. The residual risk for these was minor.

Fiduiciary risk
The fiduiciary risk was rated low during the design phase of the programme, with USAID responsible for ensuring rigorous financial accounting processes for the partners. The evaluation of the ARC programme voucher management scheme by DFID’s internal audit department provided reassurance that the programme had adequate controls in place to mitigate against the risk of fraudulent reimbursements on the voucher system, but the assessment of other programme aspects raised the fiduiciary risk profile to moderate and recommended increased oversight by DFID. DFID worked with USAID to institutionalise measures to strengthen compliance and data quality assurance through the installation of a computer based information management system (CLIC) with in-built controls to mitigate against misrepresentation of data. Direct mobile money payments to the beneficiaries were also introduced to mitigate the risk of financial loss. In addition, regular spot checks and quarterly assessment of risk ensured that risk was mitigated throughout the remaining part of the programme. The residual fiduiciary risk rating was maintained as moderate.
Social safeguards
The risk of inappropriate information, coercion and the provision of family planning to young girls was mitigated by training health workers to work with young people, providing standard operating procedures and counselling guidelines and ensuring that all family planning users signed the consent forms. Spot checks, support supervision visits and analysis of risk during quarterly meetings ensured that safeguards were being implemented. The residual safeguards risk rating was maintained as minor.

Delivery risk
Following the resumption of the programme after suspension there was sub-optimal uptake of services largely driven by fears that the programme would end again. To tackle this, MSIU embarked on the district family planning days campaign to accelerate the reach of clients with family planning information and services as a way of improving programme performance. There was however no observed acceleration of performance, hence the deduction that family planning days are not an ideal intervention to increase productivity. Initially rated as minor, the residual delivery risk increased to moderate from the mid-term to the end of ARC implementation.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Delivery was slower than expected, primarily due to the temporary suspension of the project and the change in service providers mid-way through the project. Following resumption of the programme in March 2015, progress was also slower than expected. Rather than delivering the planned outputs within 18 months, a no cost extension was put in place to enable delivery by July 2017.

Performance of partnership(s)
The DFID/USAID partnership produced efficiency gains in cultivating a close relationship with the MOH, for increasing access to family planning in Uganda. The partnership improved efficiency due to coherence and harmonisation by the two largest family planning donors in country. Furthermore, both DFID and USAID provided technical guidance and oversight instrumental in the definition of Uganda’s milestones towards achievement of the FP2020 targets.

The ARC programme brought on board several other partners (including MSIU, FHI 360 and UHMG) each having a comparative advantage and experience delivering a different component of the programme. Such a partnership promoted a total market approach to the delivery of family planning, while ensuring equity. Similarly, the interventions by the various partners ensured a balance of inputs as suggested in the theory of change.

Asset disposal and value obtained by DFID
Assets under the ARC programme were managed in accordance with the USAID asset management policy, in consultation with DFID. MSIU maintained an inventory of all the assets procured for the programme and spot checks were jointly conducted by DFID and USAID to ensure value for money. As part of the close out plan[19] MSIU submitted a disposal plan which was discussed and partners resolved to:
[19] Within three months of project closure, USAID partners are required to submit for discussion and approval a plan of activities for programme closure. This should include a plan of how the assets will be managed.

1. Transfer 28 vehicles to DFID to support the follow-on DFID funded family planning programme-Preventing Maternal Deaths (PMD)
2. USAID to retain four vehicles to support another reproductive health programme
3. Transfer all other programme assets in good working condition to MSIU to support activities under the PMD programme.
4. Dispose of any programme assets that are no longer in a good working condition according to the MSIU disposal policy.

G: CONDITIONALITY

Partnership principles assessment
The latest assessment of the DFIDU Partnership Principles was carried out in August 2016 but they were not explicitly used for management and monitoring of this programme. There were no conditionalities because the bulk of this funding was not channelled through Government of Uganda systems.

Over the life of the programme, the government made a policy shift to prioritise funding for infrastructural development including long term investments in the oil and gas sector. Funding per capita on health remained below recommended levels, and lower than other countries in the region. The government maintains that whilst increased investment in infrastructure in the short term disadvantages funding for the social sectors, in the long term these investments are expected to boost GDP and therefore investments in health. The extent to which Uganda’s growth will be transformational but more importantly inclusive remains to be seen. With regards to respect for human rights, the government in 2014 enacted the Anti-homosexuality Act which may have contributed to reduced access to family planning and other health services for minority groups. The enactment of the Act resulted in several donors holding back funding including to the health sector given the violation of human rights. This Act was later repealed and funding restored.

H: MONITORING & EVALUATION

Evidence and evaluation

Throughout the implementation of the ARC programme, regular evaluations were conducted in consultation with all the partners. Following the Joint Managemnt Framework in 2015, oversight by DFID improved with requirements to input into terms of reference for evaluations. Evaluations of the project have included:

Evaluation	Key findings	Evaluation undertaken by
Effectiveness if SBCC	Increased awareness of modern contraception from 78% to 88% in East-Central Uganda.	CHC
Evaluation of the voucher scheme under the ARC programme	The ARC programme had adequate controls in place to mitigate against the risk of fraudulent reimbursements on the voucher system	DFID-Internal Audit Department
Value for money evaluation	The Social Return on Investment (SROI) for ARC was high, at $21.40; i.e. each dollar spent generated a social benefit of $21.40, the larger part of this benefit accruing to women and young girls.	DFID Uganda through Policy Analysis and Development Research Institute (PADRI) Uganda
Family Planning Days campaign evalution	Family planning days did not accelerate performance of the programme, and thus not an ideal intervention to increase productivity / They are resource intensive and potentially associated with quality of care compromises	MSIU
Evaluation of the dedicated service provider model	The model led to the integration of family planning into other maternal child health programmes and is a recommended model for HCW capacity building in the Health Sector.	MSIU

Monitoring progress throughout the programme
To strengthen DFID’s oversight of the programme, a Joint Management Framework (JMF) was agreed with USAID. As required by the JMF, field visits and spot checks were jointly conducted by DFID and USAID to assess programme implementation, and risk. Quarterly meetings were held between DFID, USAID and other partners, providing an opportunity to review performance, agree targets, share lessons, assess risk and explore opportunities for improved programme performance. Reports were shared with DFID as stipulated by the MoU to provide an update on progress. In addition, through regular meetings with the Ministry of health, updates were provided to the Maternal Child Health technical working group and the FP2020 donor focal points on progress to date and to ensure all activities conducted under the programme were in line with the family planning costed implementation plan. The project completion review was conducted by the a Senior Health Adviser and Programme Manager from DFID London, and involved the review of project documents and interviews with stakeholders.

Annex A: Expanded Family Planning Commitments in the July 2017 summit

No.	Thematic Area	Commitments
1	Innovative Financing	Ensuring that family planning is included in the National Health Insurance Bill.
		Use result basing financing through the Global Financing Facility (GFF), World Bank, GoU and other support to the RMNCAH Investment case to increase uptake of family planning services.
		Expansion of family planning voucher schemes
		Leverage private financing from large corporation’s and philanthropists to match locally generated district resources to finance FP services
2	Expanding Range of Contraceptives	Building capacity of health care worker’s to provide quality FP services including Long Acting and Reversible Contraceptives (LARC’s).
		Improving the quantification, procurement and distribution of commodities through both the National Medical Stores and the Alternative Distribution System
		Supporting a robust Social Behavior Change Communication Strategy to create more demand for services
3	Empowering Young People to Thrive	Finalise and operationalise the National Sexuality Education Framework and the National School health Policy to increase access to age appropriate sexuality education for in and out of school young people.
		Review, disseminate and operationalise the National Adolescent Health Policy to increase access and quality of sexual and reproductive health services for adolescents and young people.
		Continued engagement with influential leaders such as religious, cultural leaders and young people through youth council and networks.
		Integrate support for family planning programming into other sectors including Community development departments, government youth programmes like the Youth Livelihood Fund; National Youth council and the women entrepreneurship Fund.
4	Reaching the Hardest to Reach	Strengthen inter-ministerial and partner coordination to provide FP to high burden and hard to reach populations including (refugees, young girls, islands, mountains)
		Increase the deployment and retention of critical cadres (e.g. midwives) in hard to reach areas.

Annex B: Estimated SROI and contribution by stakeholder category

Stakeholder	Net Social Benefit (US$)	%age contribution
Women	252,306,587	99.10%
Youth	2,010,885	0.79%
CBD	67,307	0.03%
VHT	128,918	0.05%
Healthcare providers	89,971	0.04%
Total Net Social Benefit	254,603,668	100%
Total input cost	11,901,009
SROI	21.39

Source: Estimates based on Field data

Annex C: Key Cost Drivers of ARC implementation by UHMG and MSU

Uganda Health Marketing Group (UHMG) Cost Drivers
1	BCC activities	39%	Development of campaign materials
2	Training and workshops	27%	Training of LAPM providers of Good Life Clinics
3	Salaries	13%	Recruitment of staff to scale up services
Marie Stopes Uganda Cost Drivers
1	Operational costs	26%	Health worker training, voucher re-imbursements, IEC materials and branding
2	Staff	21%	Recruitment of staff to scale up services
3	Equipment	17%	Including vehicles and supplies

Annex D: Summary of expenditure by MSIU
Budget Category	Total Budget/ Obligations ($)	Apr-15 Sep-15 ($)	Oct-15 Sep-16 ($)	Oct-16 Jul-17 ($)	Total Spend Apr.15-Jul.17 ($)	%age Spend

Personnel	7,245,280	1,151,696	3,403,677	2,725,019	7,280,393	100%
Fringe	2,431,139	128,510	996,053	811,856	1,936,418	80%
Allowances	279,531	23,138	52,419	93,914	169,471	61%
Travel	2,947,411	315,095	1,580,565	1,754,476	3,650,136	124%
Furniture & Equipment	273,670	149,389	80,712	18,017	248,117	91%
Supplies	1,381,103	92,628	342,130	321,231	755,990	55%
Program Related Training	510,804	295,995	319,401	151,596	766,992	150%
Other Costs	3,781,203	501,823	1,783,554	1,746,446	4,031,823	107%
Total Direct Cost	18,850,141	2,658,274	8,558,511	7,622,555	18,839,341	100%
Indirect Cost	1,149,859	162,155	522,069	476,076	1,160,299
Total	20,000,000	2,820,429	9,080,580	8,098,631	19,999,640	100%

Analysis by cost categories
US$
Cost Category

Analysis by cost centres
US$
Cost Centre Name

Annex E: VfM performance compared to benchmarks in the business case

Measure	Indicator	Business case Standard	2015	2016	2017	% decrease;
Economy	Contraceptive input costs	$18/unit	$8.7/unit	$8.65/unit	-	52%
Efficiency	Cost per CYP	£11	$14.6	£9	£7	36%
	Delivery cost-Outreach	£ 5	£8.57	£11	£7
	Delivery cost-Social franchise	£ 8	£24.91	$5.43	£6	25%
	Cost/ unintended pregnancies averted	£42	£42	£25	£19	49%
	Cost/ maternal death averted	£18,391	£18,391	£11,300	£9,374	54%
	Cost/ unsafe abortion averted	£142	£142	£83	£65	54%
	Cost/ DALY averted	£20	£20	£12	£9	55%
Effectiveness	Contraceptive Prevalence Rate	26% / (UDHS 2011)	31.8% / (PMA)	-	35% / (UDHS)	9%