Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Health Transitions: Improving Reproductive Maternal and Child Health (RMCH) outcomes in Mozambique
Programme Value: £34.4 million		Review Date: November 2017
Programme Code: 205074	Start Date: Nov 2016	End Date: March 2020

Summary of Programme Performance
Year	2017
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review
The Reproductive and Maternal Health business case (BC) worth £34.3 million was approved in September 2016. The BC aimed to increase access to reproductive and maternal health in Mozambique to 20% of the population. This would be done through three main components:
- £23.4 million through the UN (WHO, UNICEF and UNFPA) for strengthening service delivery and improving the quality of primary health services delivered by the Ministry of Health (MoH).
- £7.5million for increasing demand and uptake for family planning with a particular focus on adolescents. The supplier will be procured through the Official Journal of the European Union (OJEU) tendering process. The supplier is to generate demand for family planning.
- £3.3million to improve coordination and coherence of all UK investments in the health sector and capture lessons from the programme. This included having a programme funded post to support coordination among the three UN agencies as well as the monitoring and coordination of non-bilateral UK investments.
Progress this year was slow across the two main components. The UN spent the first eight months defining the scope of the programme with the Government. This meant that the final work plan was approved by the MoH without any issues. However, securing this buy in delayed the start of implementation interventions.

The second component aims to address the unacceptably high birth rate among adolescents[1] through interventions to The programme team decided to split the component in two achieve this objective:
[1] Mozambique has the fourth largest birth rate among adolescents in the World according to the UN’s World Fertility Patterns 2015 (www.un.org/en/development/desa/.../pdf/fertility/world-fertility-patterns-2015.pdf)
1. £7.5m to raise awareness and change attitudes and pilot market based approaches to delivery. The OJEU process to contract a supplier was launched in April 2017, and is in its final stages with a submission to go to Ministers for approval of the contract.
2. £1.5 on innovation and coordination of family planning interventions. The programme team is in the final stages of exploring options that bring coherence to different interventions in the country thereby reducing existing fragmentation while being innovative.
This component has experienced delays due to the supplier review (for (i)) as well as the necessary scoping to ensure that our intervention is effective (for (ii)).

The third component was reduced during the Portfolio Quality Review (PQR) to £1.36million. The DFID office is not planning any external verification of progress to inform programming. Instead the team are exploring the use of beneficiary feedback to know how the programme is performing.

Summary of recommendations for the next year
The recommendations consist of outstanding actions as part of the BC implementation process and lessons learnt during this first year of the programme. These are listed below:

1. Set up a Governance Structure for the RMNCH Investment Case that oversees the different funding streams for RMNCH including DFID’s. Ideally this should be agreed within the next 3 months.
2. DFID to explore with the WHO how to strengthen disaster preparedness and response to disease outbreaks in the health sector.

1. Get buy in to the updated risk matrix from the MoH to monitor how the fiscal crisis is affecting the programme
2. Support the MoH to define WASH standards that should exist in different kinds of health facilities.
3. WASH and Health programme teams agree a work plan for joint technical meetings and collaboration to provide water and sanitation services in primary care facilities.
4. Programme team to set up the delegated cooperation arrangement with Sweden looking at programme compliance and gaps in programming that DFID can help address.
5. DFID to support UNFPA to convene partners working in family planning
6. DFID to ensure strong links between the Demand for Family Planning (OJEU) component and the innovation and coordination component through MoU agreements if possible, and if not by informal coordination mechanisms.
7. Programme team to define how coordination of the main UK investments to the sector will be undertaken. This will include a decision on whether to get a Funded Post
8. Develop provincial level risk matrices with each Provincial Health Directorate
9. Review the overall risk rating for the programme in light of the external environment and reduced MoH engagement with the programme.
10. DFID Health and Governance teams to agree an effective way to get beneficiary feedback to verify the performance of the programme.

A. Introductionand Context (1 page)
This has been the first year of the Health Transitions business case. The programme team focused on preparing for the different components of the business case to implement. The business case was designed to be flexible enough to respond to the rapidly changing context in the country. For this reason, it was approved only with a Theory of Change and the log frame populated only at the outcome level. The specific interventions the BC would support through the UN Joint Programme and Family Planning components still need to be defined. The final scope of the BC was defined in June 2017 with the UN submitting a proposal with a results framework to DFID in July 2017.

DevTracker Link to Business Case:	Due to the OJEU tender the business case was not published.
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5736765.xlsx

Wider context and how this has affected the programme
Mozambique has made significant improvements in child health and maternal health while HIV & AIDS, malaria and maternal health are lagging behind. The country achieved the millennium development goal target of under-five mortality (79/1,000 live births). Malaria, the biggest cause of deaths in the country has fallen to an incidence of 298/1,000 population. This is above the Sub-Saharan regional average of 234/1,000 population. HIV & AIDS is at 11% prevalence rate, more than double the regional average of 5%. Maternal mortality on the other hand has decreased from over 900/1,000 live births, one of the highest in the region to 489/1,000, below the regional average[2]. Health systems remain weak and there is risk that with the fiscal crisis (see below) they could grow weaker still.
[2] UNICEF 2017 Health Budget Brief

In 2017, the health sector received 7.8% of the State Budget. This is far below the Abuja target of 15% that WHO set out as necessary to provide a minimum package of essential health services. The sector also experienced a decline in the proportion of GDP allocated to health from 3% in 2016 to 2.8% in 2017. Despite this, internal resources to the sector have increased significantly from 48% of total health resources in 2008 to 73% in 2016 External resources halved from 52% to 27% over the same period[3].This is good given that donor support has become increasingly inconsistent and in the medium to long term unsustainable. However, these figures grossly underestimate the proportion of external off budget donor support that is not tracked by the Government. For example, the Gavi Vaccine Alliance disbursed $32.9million in in-kind contributions and programme budget only in 2017[4]. It has been difficult to track expenditures per thematic area due to the functional classification that the budget uses making it difficult to know if expenditures are being spent on the poorest.
[3] UNICEF 2017 Health Budget Brief
[4] http://www.gavi.org/country/all-countries-commitments-and-disbursements/ (Accessed 20th November 2017)

The debt scandal in April 2016 where it was revealed that the Government had contracted a $2billion debt, led the IMF to suspend its programme and DFID Ministers to suspend all financial aid in Mozambique. This coupled with the loss in commodity prices has led to 40% depreciation in the value of the local currency. As a result, the health sector has experienced a liquidity shortage with the Government unable to pay for medicines invoices worth an estimated $30million[5] and operational costs including fuel and utilities. In August 2017, anecdotal evidence suggested every province had accumulated debts on unpaid utilities and food for in-hospital patients. One of the results of inflation has been the attrition of experienced health workers to the private sector and NGOs which offer more competitive salaries. By August 2017, 325[6] health workers had left the sector, more than double the number that left the previous calendar year.
[5] July analysis from the Finance Technical Working Group in the Health Sector.
[6] Ministry of Health presentation – Perdas por Iniciativa Propia - Presented in Agosto 2017 to the human resources Task force

The suspension of financial aid has exacerbated the impact of inflation on the sector. Common Fund donors suspended their funding soon after the scandal emerged, resuming only in March 2017. Disbursements in 2017 have been only $27 million as some partners decided not to resume financial aid[7]. This is in sharp contrast to the 2008 disbursement of $90 million[8]. The Common Fund enabled the MoH to cover their funding gaps including contracting newly trained health workers for a year until they could be absorbed by the Government, paying for medicines and retaining specialists and managers in the National Health Service through the payment of incentives. Discussions between Common Fund partners and the Government to phase out this support due to its unsustainability have been ongoing for over three years with little progress. The Common Fund stopped the payment of incentives in March 2017. DFID are supporting this process by paying for a consultancy to assess how to retain and attract health workers (see page 12 below).
[7] Notes from the November Joint Coordinating Committee at the Ministry of Health. Canada and Netherlands have not signed the new Common Fund agreement and are exploring alternative funding mechanisms.
[8] UNICEF 2017 Health Budget Brief

As partners have found alternative funding mechanisms to support to the Government, there is increased risk of fragmentation and duplication in partner support to the sector. The weakening of the Common Fund which played a convening role of bringing partners together has increased fragmentation as partners have sought other instruments to support the sector most of the time outside Government systems. As a result, there has been an increase in duplication of interventions and technical support while some disease areas or geographical regions face significant gaps. Government engagement in policy dialogue has also reduced significantly as managers at the MoH have left. Heads of Agencies have been meeting in recent months to address this fragmentation by not focusing on instruments but other ways to increase collaboration and joint working (see page 7 below).

The sector also faced a cholera outbreak in the first months of the year. Between January and March 2017, 1,622 cases of cholera and three deaths were reported. Cholera is endemic in Mozambique, occurring every year. Yet the MoH struggled to address it with Nampula and Tete provinces reporting 75% of the cases (1216)[9]. Routine service delivery was disrupted as the Government struggled to contain the disease. In the first couple of weeks it was difficult to know the magnitude of the problem as information was not forthcoming from the Government. By May 2017, the outbreak had been contained. However, this week the programme team has been made aware of 420 cases of cholera and one death in Nampula province[10]. DFID will be exploring how to support the Government to respond to outbreaks as part of the system strengthening support (see page 7 below).
[9] https:reliefweb.int/sites/reliefweb.int/files/resources/cisa_bulletin_12week_12march2017.pdf(Accessed 21 November 2017)
[10] Discussion with WHO on 20th November 2017

The Global Financing Facility (GFF), a new instrument to Mozambique has the potential of strategically reducing this fragmentation. The GFF provides a platform for different stakeholders including the private sector, NGOs, other line Ministries and partners, to join efforts to improve RMNCH in Mozambique. The World Bank will be the Secretariat for the RMNCH Investment Case. They will also have a Trust Fund through which they will contribute $100m of grant funding through a results based approach from January 2018 for five years. Some partners will be joining the World Bank Trust Fund while others like the UN Joint Programme and the US Government will be supporting the Investment Case with their own instruments. The design of the Investment Case was inclusive with the active participation of different stakeholders. Partners including DFID are keen to build on this momentum by having a mechanism that has oversight of all the different funding streams and allows stakeholders to hold each other, and Government accountable for their investments in RMNCH. This is discussed further in output 1. Another benefit of such a structure would be that it would provide some oversight of the contribution that large vertical programmes such as the Gavi Vaccine Alliance and the Global Fund to combat AIDS, TB and Malaria (GFATM) make to RMNCH.

The business case has been directly affected by the external environment. The Director and Deputy Director at the Department of Public Health left in July and August 2017 respectively. They were directly involved in the GFF design process and more particularly in defining the scope of UK investments through the UN Joint Programme. These changes have meant that the level of engagement of the MoH with the UN Joint Programme has reduced in the last three months (see output 1 below). DFID have also had discussions with the UN about what proportion of programme funds should contribute to operational costs. This environment has meant that the programme needs to be responsive to arising needs while still delivering on our objectives.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
It is still too early to assess the outcome for the programme

Overall output score and description
The Output score was an A

This first year of the programme focused on getting the programme compliant with DFID Programme Management standards. Milestones to achieve this were set against all outputs except outputs 5 and 7.

Output	Description	Score
1	Enhanced availability and quality of trained midwifery workforce at national level by 2020	A
2	Improved facility readiness to provide essential and emergency obstetric and neonatal care (EMoNC), including safe abortion care and life saving commodities by 2020	A
3	Improve health infrastructure, focused on closing water and sanitation (WASH) gaps in primary health care (PHC) facilities with maternities by 2020	A
4	Platforms for community engagement focused on lowest performing districts strengthened by 2020 including through improved National health management information system (HMIS)	No milestone
5	Institutional reform agenda advanced for the sector for a better policy enabling environment by 2020	No milestone
6	Generating demand for family planning among adolescents	B
7	To improve the coordination and coherence of all UK investments in the health sector in Mozambique	No milestone

Key lessons
- The programme’s ability to flex by picking up operating costs and adjusting interventions to need as long as the main outcomes are still achieved, has meant that it is able to continue delivering in the current difficult operating environment.
- Agreeing the donor coordination architecture (in the absence of the Common Fund) has taken longer than would have been hoped. However, this dialogue is a worthwhile investment in order for the programme to achieve its outcomes
- Having funds for technical assistance has allowed the programme team to remain engaged and have influence in the sector while the rest of the programme is getting started.

Key actions
Review the log frame to ensure it captures the main interventions for each component in the new calendar year.

Has the log frame been updated since the last review?
Yes. The log frame was updated in September 2017 with milestones for the first year of the programme. This programme log frame is based on the results framework in the UN Joint Programme proposal that outlines the main outputs the UK will support and the activities that will help achieve this. Milestones were only set for 2017 due to the slow start of the main components. The programme team will therefore be reviewing the log frame after the New Year.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Enhanced availability and quality of trained midwifery workforce at national level by 2020
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
1.1 Number of maternal and child health (MCH) nurses available in health facilities	Agreement signed with UN to start implementation that includes (i) Governance Structure (ii) Results Framework (iii) Official endorsement of the project by the Ministry of Health	(i)Progress but not finalised. (ii)Included in proposal submitted to DFID in July 2017 (iii) Achieved in August 2017.

Key Points- Official endorsement of the Project by the MoH was achieved
A summary of the priority interventions that DFID will be supporting was presented at the MoH’s Technical Counsel where all the Departments officially endorsed it in August 2017. The process of defining the interventions included consultations with the main Departments at the MoH. This four week process led by the Department of Public Health, resulted in a three year costed workplan which was discussed with the UN and DFID in May 2017. The UN then used this workplan to draft their proposal to DFID. This process culminated in a presentation to the Heads of Department, the Permanent Secretary and the Minister of Health at the Technical Counsel where the programme was endorsed.

The BC had foreseen that emergency preparedness would be included in the UN Joint Programme. However, the MoH did not prioritise this intervention despite noting its importance in system strengthening and for the delivery of the programme at district level. The fiscal crisis and reduction in partner support through the Common Fund meant that there were many interventions without any funding. The Government’s slow response to the cholera outbreak earlier this year reinforced the need for support to be provided to disease outbreaks. DFID are therefore exploring with WHO how to support disease outbreaks and disaster preparedness with funding from the coordination component and the humanitarian programme.

The agreement with the three UN agencies was signed July 2017. The programme team focused on defining the scope of DFID support with the Ministry of Health (MoH) and subsequently getting the agreement with the three UN Agencies (WHO, UNICEF and UNFPA) signed. The definition of the scope was made easier by the Reproductive Maternal, Neonatal and Child Health (RMNCH) Investment Case for Mozambique which was being finalised. The Investment Case outlined the interventions needed priority districts in order to shift maternal mortality rate of 408 deaths per 100,000[11].The scope of DFID support was based on the UN’s comparative advantage, interventions that did not yet have any domestic or support and interventions that would be essential to achieve impact in RMNCH. For example, the project will use UNFPA’ s comparative advantage in procuring contraceptives to procure $5million worth of family planning commodities by March 2020[12]. This will cover 42% of the estimated gap in family planning from 2018-2020[13].
[11] UNICEF2017 Health Budget Brief
[12] UN Joint Programme Proposal
[13] Ibid

The proposal sets out how the UN agencies will implement the interventions selected for DFID support. It includes a summary of the management and coordination arrangements that will be used to implement the programme at the national and subnational levels and a results framework based on the six outputs in the programme’s theory of change.

The Programme’s Governance Structure – progress but not yet completed
Negotiations with the MoH for DFID’s investment to be focused in two provinces to enable the impact of our interventions to be assessed were unsuccessful. The MoH opted to select interventions in the Investment Case that would improve RMNCH outcomes but didn’t yet have any funding. This means that although the DFID programme may achieve its outputs, they will only be able to assess if this is translating into outcomes with oversight of the overall Investment Case. The programme team has therefore been advocating with the MoH, the World Bank and partners to have a Governance Structure that oversees the entire Investment Case. This would be led by a senior level official at the MoH with representation from the Departments at the MoH and partners supporting the Investment Case. One of the functions of the Investment Case would be for partners and the Government to hold each other accountable for results at the outcome level. There has been progress towards this as Heads of Agencies have met and agreed that the dialogue should not focus on the instruments but finding ways to increase collaboration and joint working.

However, the Investment Case doesn’t yet have an official governance structure. We expect the Governance Structure to be set up by the end of the first quarter when the sector will review performance of the previous year and when the World Bank Trust Fund will have been operational for three months.

Recommendations 1 and 2
- Set up a Governance Structure for the RMNCH Investment Case that oversees the different funding streams for RMNCH including DFID’s by March 2017.
- DFID to explore with the WHO how to strengthen disaster preparedness and response to disease outbreaks in the health sector.

Output Title	Improved facility readiness to provide essential and emergency obstetric and neonatal care (EMoNC), including safe abortion care and life saving commodities by 2020
Output number per LF		2	Output Score	B
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1Number of health facilities equipped with (i) ambulances and (ii) emergency obstetric and neonatal care (EmONC) Kits	Minimum condition for interventions to be successfully implemented agreed with Government and UN	Minimum conditions agreed with the UN and the MoH. They will be discussed on quarterly basis as risks to the delivery of the programme.

Key Points- progress towards milestone
The fiscal crisis in the health sector has meant that the MoH are struggling to fulfil some of their responsibilities. For example, at a visit to district hospital in the Northern Province of Cabo Delgado, the programme team saw several ambulances parked because there were no funds to buy fuel. There are also reports that recently trained health workers are not automatically being employed. To address this programme team set out minimum conditions that the Government would need to put in place, for specific interventions to be successful. These will vary according to the interventions set out in the annual workplan. DFID will have a discussion with the Government to know to what extent they are able to fulfil their obligations. Where Government are not able to, the programme team can either not invest in that particular intervention and use DFID funds elsewhere or choose to redirect funding from another intervention to support the Government. The ongoing discussions will enable the programme team to be aware of how the fiscal crisis is affecting service delivery and to ensure that our investments are being well used.

In September, the UN opted to set out these minimum conditions as risks to programme delivery to be used in our quarterly dialogue with the Government. These are now part of the programme risk matrix discussed below.

However, the programme team has struggled to get a meeting with the Government since August 2017. The change of both the National and Deputy National Directors of Public Health has meant that the new Director has had to get acquainted with the Programme.

Recommendation 3
Get buy in to the updated risk matrix from the MoH to monitor how the fiscal crisis is affecting the programme.

Output Title	Improve health infrastructure, focused on closing water and sanitation (WASH) gaps in primary health care (PHC) facilities with maternities by 2020
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of primary health facilities provided with adequate water and sanitation services in priority districts	Target health facilities for WASH construction/rehabilitation identified	50 health facilities to benefit from WASH construction/rehabilitation

Key Points

The UNICEF WASH team have been working with the MoH to identify what WASH needs different health facilities have. These have ranged from having running water in the laundry section of the district hospital, functional toilets in health centres or running water in maternity ward for inflection control. One of the challenges the UN team has found is that the needs vary widely because the MoH has not defined what WASH services should be expected from different kinds of health facilities (health units, health centres or district hospitals). The project estimated that 100 health facilities would benefit from DFID support. However, the needs analysis has demonstrated that several WASH services may be provided to one health facility. The number of health facilities that will benefit from the programme has therefore halved.

DFID and UNICEF’s WASH and Health programmes will be working together in Zambezia and Nampula provinces to implement this output.

Recommendation 4 and 5
- Support the MoH to define WASH standards that should exist in different kinds of health facilities.
- WASH and Health programme teams agree a work plan for joint technical meetings and collaboration to provide water and sanitation services in primary care facilities.

Output Title	Generating demand for family planning among adolescents
Output number per LF		6	Output Score	B
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Additional family planning users in target areas as a result of DFID interventions	OJEU tender for service provided completed and supplier selected OR plan B for family planning uptake approved	OJEU tender advanced but contract yet to be approved by Ministers
Young women and men with improved knowledge and more positive attitudes towards family planning	ToR for Youth and Adolescent Uptake Initiative finalised with a decision on the scope and focus of work	ToR finalised but scope changed in November 2017

Key Points- progress on the milestones
The OJEU tender was launched in April 2017, after the supplier review was complete. The process was slower than usual due to the addition of new processes such as getting Cabinet Office approval. Nevertheless, the contract will be submitted to Ministers this month for approval.

Between March and June 2017, the programme team initially explored launching a new Branded Multimedia Campaign (new Youth Brand and new Multimedia Platform) for nation-wide family planning messaging. This would be complimentary to the work being developed by the OJEU selected supplier. However, this idea was amended as there was deemed to be reputational risks associated with the approach. Instead DFID explored different options for reaching adolescents with family planning messaging. Following a discussion with the Head of Office and Team Leader in mid-November, we are likely to pursue a delegated cooperation agreement with Sweden on a Female Youth Programme implemented in two provinces in Mozambique. This programme would be implemented by UNFPA who could also assist to coherence to family planning partners in the country. However, further work still has to be done to scope this option, which will be undertaken in the coming months

Recommendations, 6, 7 and 8
- Programme team to set up the delegate cooperation arrangement with Sweden looking at programme compliance and gaps in programming that DFID can help address.
- DFID to support UNFPA to convene partners working in family planning
- DFID to ensure strong links between the Demand for Family Planning (OJEU) component and the innovation and coordination component through MoU agreements if possible, and if not by informal coordination mechanisms

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
N/A
VfM performance compared to the original VfM proposition in the business case
It is still too early to outline the VfM performance of the programme. However, different components are developing VfM indicators against which performance will be assessed in the future:

UN Joint Programme
The UN submitted a preliminary VfM section in the proposal. However, this focused on economy (price of inputs) and not sufficiently in assessing efficiency, effectiveness or equity. For example, provincial variations would enable the programme team to have a better idea of the differences in how inputs are converted to outputs throughout the country. We could also track the effect of inflation on service delivery throughout the lifetime of the programme. The Programme Team and DFID Commercial Advisor worked with the UN team in late October to improve the programme’s VfM. As a result, the UN submitted a new VfM proposal with a greater focus on efficiency and effectiveness. The programme team are aware that a large proportion of effectiveness will only be assessed if the Governance arrangement that has oversight of the Investment Case is set up.

Family Planning Demand Side
Once the contract is approved, the submission of a VfM framework by the supplier is one of the milestones of the inception phase of the contract.

Innovation and coordination
The additional component on innovation and coordination with a relatively small investment could generate lessons learned to have wider impact on the effectiveness of the other components. By including an element with UNFPA, we will have a voice at the table to pressure them to use their convening power to influence improved coordination in the family planning sector.

The programme team has also put the decision to get a programme funded post on hold. This has meant that a clear strategy for how to improve coordination of the main UK investments in the country has yet to be defined. Under the Joint UN Programme, a project coordinator has been contracted by UNICEF as the Convening Agent to help coordination between the three agencies. The programme team are exploring whether to support emergency preparedness and disease outbreaks at the MoH through WHO. This would be part of system strengthening as it would strengthen the sector’s ability to prepare for and respond to outbreaks.

Assessment of whether the programme continues to represent value for money
It is still too early in the programme to assess whether the programme represents VfM. As set out above, the design, including different implementing modalities and leads for different aspect, should demonstrate VfM in terms of ensuring the comparative advantage of each delivery partner. VFM metrics have yet to be agreed. However, this will be assessed in more detail at the next annual review.

Quality of financial management

Table 1: Comparison between the budget and expenditure for the programme in year 2017/18
Component	Budget / (£)	Spend / (£)	Balance / (£)	% of Spend to date

UN Joint Programme - Resource	5,550,000	3,005,749	2,544,251	54%
UN Joint Programme – Capital	1,150,000	1,000,000	150,000	87%
Family Planning Demand Side Support	500,000	0	0	0%
Programme Management and Coordination	110,000	33,415	76,585	30%
Total	7,310,000	4,039,164	2,770,836	55%

Despite a slow start, the programme is on track to achieve most of its spend by the end of the financial year. The first disbursement to the UN Joint Programme was in August 2017 and a second one for the outstanding balance is expected in December. Most expenditure in the programme this year will be on the procurement of commodities and equipment so that implementation can begin in January 2018.UNICEF submitted a work plan explaining that commodities and equipment take four to six months from when they are procured to when they arrive in country. This equipment and commodities will be needed for implementation by Government starting in January 2018. The capital spend has focused mainly on assessments for WASH and the first rehabilitations in health centres.

The family planning demand side component hasn’t spent because the contract is awaiting approval.

Programme management and coordination has focused on two consultancies:
1. A study on the retention and attraction of health workers to inform human resource retention and attraction strategy at the MoH. . The attraction and retention consultancy has enabled DFID to maintain our influence in the sector by getting involved in a strategic area.
2. Contracting a Senior Financial Management Consultant to support the MoH to respond to the findings of the GFATM ‘s Programmatic Audit undertaken in April 2017. The consultant will begin work on 20th November for a nine month period. This consultancy helps to address the Secretary of State’s concern that not enough was being done to respond to the GFATM audit findings.

Table 2: Changes to the programme as a result of the PQR process
Component	Original Budget	Revised Budget	Difference
UN Joint Programme Resource	18,500,000	18,500,000	-
UN Joint Programme Capital	5,000,000	5,000,000	-
Family Planning Demand side support	7,525,000	5,500,000	-
		1,500,000	500,000
Programme Management and Coordination	3,275,000	1,360,000	1,915,000
Total	34,300,000	32,885,000	2,415,000

There has been a total reduction of £2.4 million as a result of the PQR. The third component had a £1.9million reduction. These changes will affect when the programme decides to have independent verification or an evaluation of results. It will also need to be taken into consideration when deciding whether to have a Programme Funded Post.

Recommendation 9
Programme team to define how coordination of the main UK investments to the sector will be undertaken. This will include a decision on whether to get a Funded Post.

Date of last narrative financial report	Not yet applicable
Date of last audited annual statement	Not yet applicable

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk
Despite the medium overall risk rating the rating for the operating environment is high. The cholera outbreak and its effect on routine service delivery reduced Government engagement and fragmentation of donor support all contribute to make the operating environment high risk.
For the UN Joint Programme additional risks to programme delivery were added so the team can monitor the effects of the fiscal crisis on the sector. Four out of a total of 14 risks are now delivery risks, and three risks have been assessed as having a major residual risk. Risks to programme delivery include:
- Reduction of government and donor’s financing for contraceptives
- Low motivation, human and financial resources, and technical capacity to implement planned activities within MoH
- Inefficient utilisation of funds
To reduce these risks the UN will closely monitor implementation at subnational level.

Outstanding actions from risk assessment
- Agree the risk matrix including reassurances from the Government that they will be able to fulfil their obligations with the MoH. This will then be discussed at quarterly meetings between the MoH, DFID and UN Agencies.
- DFID to make donor coordination work over the next six months to reduce the risk of fragmentation in the sector.

Recommendations 10 and 11
- Develop provincial level risk matrices with each Provincial Health Directorate
- Review risk rating in light of the external environment and reduced MoH engagement with the programme.

 COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The 2017/18 budget of £9.5 million in the business case was reduced by 37% to £6million due to the eight months it took to agree the scope of the programme with the MoH. The consultations with different Departments at the MoH did secure buy in to the DFID programme but resulted in delays within the first year of the programme

The Family Planning Demand side component is behind schedule. An early market engagement was undertaken in October 2016. The OJEU launch date was pushed back due to the Supplier Review in December. The OJEU was only launched in April and is in its final stages. A submission to Ministers for the approval of the contract with the winning bidder is currently being reviewed to be submitted before the end of the month. Despite these delays, we expect the component to deliver results of 16,080 additional adolescents using family planning by 2020.

Performance of partnership (s)
DFID and the Government
The dialogue with the MoH has not been as effective over the last four months as it was at the beginning of the year. In the last three months, Both DFID and the UN have been unsuccessful at meeting with the National Director of Public Health to discuss the programme and its governance arrangement. Having a new National Director and Deputy Director has meant that we now need to get them to be familiar with the programme and its approach.

An informal meeting with the National Director or the Deputy National Director might be more effective.

DFID and the UN
The relationship with the UN Agencies has been good during the first year since the business case was approved. In response to DFID comments for example, UNICEF as the convening agent decided to contract a Programme Coordinator in October to support the agencies to work together. This has meant that deadlines for the submission of compliance reports such as the risk matrix, delivery chain mapping and VfM framework were met. The main technical staff member on UNFPA’s side left in mid-November. The agency has reacted quickly in contracting a replacement and has continued to engage in discussions with DFID using other staff members.

DFID and other bilateral donors
The head of office and programme team have been working to improve donor coordination in the sector. Heads of Agencies agreed in early November to have a troika system and to have more strategic and regular meetings with the Minister. The effectiveness of this new arrangement is to be tested.

DFID is also advocating for a Governance arrangement that has oversight of the RMNCH Investment Case.

UN and Delivery Partners
Each of the agencies submitted a delivery risk map outlining the main downstream partners they would be working with, the main risks to delivery of working with those partners, activities to mitigate these risks, how much each partner would receive and their geographical focus. Each partner had an average of four main downstream partners they would work with although UNICEF had more due to their larger geographical coverage.

Asset monitoring and control
This is not yet relevant as the programme has only just started.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The fiscal crisis has meant that less people are able to access quality health services. This has been due to the shortage of medicines and basic equipment in health centres, less people having funds to travel to health centres or the loss of qualified staff in health centres. DFID support for the Community Health Worker programme has reduced this by enabling the poor in rural communities to have a basic level of care. The programme team have also had discussions with the MoH at the technical and political level, to get them to map out their needs. This has not happened yet. Informal and ad-hoc requests from the MoH are making it difficult for partners to respond.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme was designed to be flexible in order to respond to arising needs in the sector. The fiscal crisis and changing needs at the MoH have proven that this was a good idea. The UN, DFID and MoH agreed that they would approve an annual work plan which would be revised at least every six months to reflect changing needs. The challenge will be to remain flexible while delivering on the programme objectives.

Monitoring progress throughout the review period
The programme had asset aside £1.5 million for independent monitoring in the business case. Although this has now been reduced to £900,000 as a result of the PQR, there is still to explore how to have regular beneficiary feedback, to verify if the UN Joint Programme in particular is being effective. An effective way to do this would be to align with the Governance Programme that is currently being designed focusing on increasing accountability of service delivery. The new BC will include beneficiary feedback in WASH and Health. Having said this, a mid term evaluation will still be useful to assess progress, learn lesson and find out if any significant changes to the programme will be necessary. This may happen the second half of 2018.

Recommendation 12
DFID Health and Governance teams to agree an effective way to get beneficiary feedback to verify the performance of the programme.