Annual Review - Summary Sheet
Title: Public Resource Management in Somalia (PREMIS)
Programme Value: £38m		Review Date: November 2017
Programme Code: 205065	Start Date: November 2015	End Date: March 2022

Summary of Programme Performance
Year	16/17	17/18	18/19	19/20
Programme Score	A	A
Risk Rating	Major	Major

Summary of progress and lessons learnt since last review
The programme has performed well in a complex and fluctuating environment. With new projects coming on stream, the programme is now operational across all levels of government in Somalia (and Somaliland): Federal Government of Somalia (FGS); Federal Member State (FMS); and district levels.
Overall, PREMIS six components are on-track. Two out of four new components are now up-and-running and delivering results. In particular, support to establishing basic building blocks of a system of public administration in the new FMS (Output 3) has rapidly picked-up pace over the last six months.
Procurement challenges (arising from the Suppliers’ Review and consequent procedural changes) and election postponements (in Somaliland) have delayed the two revenue projects: planned support to FGS on customs reform and Phase II of our support to tax reform in Somaliland. However, critical elements of this work have been supported through other components.
PREMIS was granted a two year no-cost extension to account for the deferred start-date for the two revenue projects, which was due to reasons beyond DFID Somalia’s control. The programme was also successful in crowding-in additional resources from other international partners to supplement UK investment.
Progress under each component is summarised below:
Components / Sub-programmes	Implementing Partner	Budget (UK funds)	Progress Update
Component 1 – Public Finance Management
Improve Federal Government of Somalia macroeconomic policies and statistics, and strengthen revenue generation	Private sector (TBC) and IMF-accredited experts	£5m	Procurement of service provider still ongoing. £5.4m additional co-funding secured from EU Delegation and USAID.
Strengthen Somaliland revenue generation	Private sector (ASI for finalisation of Phase I, Oxford Policy Management for Phase II)	£6m	Phase I of support to Somaliland tax reforms concluded and bidder for Phase II selected in September. New project to build on lessons to date (around need to establish a broad-based Tax Commission), and on Phase I success in reforming customs valuation and business processes; large taxpayers registration; and revenue forecasting.
Component 2 – Human Resource Management
Support FGS and Puntland capacity development	UNMPTF – UNDP	£4m	Continued provision of embedded advisory capacity at centre of government institutions; support to drafting of policies and legal/regulatory frameworks for Civil Service management; enabling the preparation of Somalia’s National Development Plan; and staffing of Office of Prime Minister’s Aid Coordination Unit.
Build political consensus on public service reform	World Bank (WB) - Externally Funded Output (EFO)	£1m	Additional staff time and expertise mobilised to step-up WB engagement and supervision of the Somalia Trust Fund economic governance portfolio.
Component 3 – Federalism and Decentralisation
Support public finance management and revenue collection in Federal Member States (FMS)	Private sector (Adam Smith International -ASI)	£10m	Systems and institutions for taxation, Public Finance Management (PFM) and Civil Service management set-up and maintained in the four new FMS through delivery of a comprehensive package of TA and training. £3.5m additional funding secured from the EU.
Improve local government policy and capacity	UNMPTF – Joint Programme for Local Governance (JPLG)	£12m	Enhanced local taxation and improved PFM leveraged in 16 districts/municipalities through Local Development Fund (LDF) and accompanying TA (Somaliland, Puntland). Groundwork for organising district council formation in South-Central initiated (Jubbaland and South West).

While the PREMIS theory of change and its underlying assumptions are still relevant, experience and evidence from its second year of implementation point to three high-level lessons:
- Despite a stagnant security situation and a highly fluid political context, it has been possible to drive substantive progress in some areas, through working closely with Implementing Partners (IPs) and applying a flexible and adaptable approach to programme management, informed by strong technical and political expertise.
- There is a need to actively mitigate the risk that the nascent Somali Public Sector becomes fiscally unsustainable. Experience to date suggests a need to align expectations by different stakeholders around the growth trajectory and composition of the Civil Service, and affordability of the government wage-bill (including the security sector).
- A number of work-streams have continued to be delivered by UN agencies, which retain important comparative advantages in Somalia. However, lessons and evidence emerging from PREMIS-funded interventions have pointed to continued weaknesses around strategy, reporting and value for money (VFM) aspects of their delivery. These had already been highlighted by reviews under the PREMIS precursor programme (Core State Functions) and are largely echoed across the DFID-Somalia portfolio. To date, programme-level efforts have been able to drive some progress in these areas. However, sustained senior engagement and communication about DFID expectations on delivery standards both in-country and at HQ level (as part of the Suppliers’ Review and UK UN Reform Agenda) will likely be needed to ensure a comprehensive response to these challenges in the future.

Summary of recommendations for the next year
The review identified two inter-related strategy/portfolio level recommendations:
First, the programme needs to support the development of a more realistic approach to public sector reform in the Somalia context, closely linked with revenue projections. DFID’s role should focus on encouraging greater coordination and collaboration between key stakeholders, with a view to facilitating a more comprehensive, affordable and properly sequenced strategy.
Second, decide on whether to continue funding UNDP capacity development interventions (by Q1 2018) and on a suitable delivery route for the remaining local governance allocation (by end 2017). In doing so, consider consolidating the projects portfolio by reducing or merging components, with a view to deepen impact in selected technical areas and streamline transaction costs (through a reduction in the number of IPs).
Many of the output level recommendations flow from these two high-level recommendations (see Annex 1 for a summary).
An additional recommendation is to consider pulling forward the date of the next AR to May-June 2018, so it aligns with yearly reporting cycles of IPs and reviews findings from the mobilisation phase of the upcoming revenue projects (including any changes in assumptions).

A. Introduction and Context
DevTracker Link to Business Case:	https://ec.vault.dfid.gov.uk/otcs/cs.exe/open/questid5417772
DevTracker Link to Logframe:	https://ec.vault.dfid.gov.uk/otcs/cs.exe/open/questid5206374

PREMIS is helping Somalis re-build a system of public administration, shattered after 25 years of conflict. It focuses on the foundations of a functioning state: government’s ability to manage the economy, raise and spend funds and deploy civil servants to fill critical positions. It is the first programme from the international community with a dedicated and substantial component of support to the establishment of core state functions in the newly established FMS of Jubbaland, Hirshabelle, South-West and Galmudug.
Building state capability by supporting nascent public administration institutions at the various tiers of government remains a key precursor to Somalia’s stability and economic recovery.
PREMIS plays an important role in delivering HMG Somalia Strategy, contributing to the DFID Somalia Business Plan Strategic Objective 1.1 “Supporting the establishment of a more stable and increasingly functional federal Somalia that is taking concrete steps towards increased democracy and accountability to its citizens and better management of the public purse and national resources”.
Somalia fundamentally remains a fragile state at constant risk of fragmentation, as a consequence of the failure to reach stable political settlements at the national, regional and local levels. The programme is working in a complex operating environment characterised by politics deeply divided along both clan and politico-religious lines, and by intense factional competition over the distribution of even small amounts of power and resources. This political dynamic is constantly working against efforts to establish a rules-based system of governance.
The programme is playing a key role in Somalia’s re-engagement with International Financial Institutions, by supporting the implementation of core policy reforms – with a focus on revenue enhancement - agreed in the context of an IMF Staff Monitored Programme (SMP).
The last 12 months saw a successful transition of power at the federal level with the election of President Farmajo, and the successful finalisation of the state formation process with the creation of the final member state of Hirshabelle (out of the merger of the Hiraan and Middle Shabelle regions).
Bedding in of the FGS administration and political instability in Puntland and the new FMS has posed significant operational challenges, due to the constant changing of programme official counterparts as a result of impeachments of State Presidents (in Hirshabelle and Galmudug) and frequent cabinet reshuffles.

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment
Outcome statement: To lay the foundations for a public resource management system in Somalia that will enable the provision of core state functions.
There was satisfactory progress against programme outcomes despite a range of unforeseeable procurement challenges materialising. Overall the milestones for 2017 outcome-level indicators are on-track. More detail is provided under the relevant output areas.
#	Indicator	Milestone	Update
1	Somaliland implements structural revenue reforms, leading to diversification of tax collection away from trade taxes	Legislation in place to allow diversification away from trade taxes	B Legislation is in place but stronger political will is required to ensure enforcement and gradual diversification of the revenue base
2	Federal member states become functioning and viable administrative entities, as evidenced by meeting World Bank 'readiness criteria' for recurrent cost financing	Jubbaland & South West State meet the readiness criteria	A+ Jubbaland, South West State and Galmudug State meet criteria
3	Total number of local governments that meet citizens' performance criteria (planning, budgeting, execution of priority services and projects)	16 (including at least 2 in South Central)	A (16 districts, but only one in South-Central covered to date by JPLG)

Overall output score and description
Out of four outputs, one scored an A, two a B, and one an A+. As a result, overall output score is A. The PREMIS logframe captures only a sample of results, drawing from component level results frameworks against which individual IPs report. Below is a summary of progress against selected outputs’ indicators over the reporting period.
Output/score	Milestone/score
1. Revenue legislation and administration reforms developed and enacted in FGS and Somaliland	A
2. Human resources policies, systems and procedures developed that enable more appropriate deployment of staff in the Civil Service	B
3. Federal member states have systems in place for managing and accounting for their expenditures	A+
4. District administrations are more responsive and capable	B

Key lessons
As per summary section
Key actions
As per summary section
Has the logframe been updated since the last review?
The Logframe has adjusted two milestones (for outputs indicators 1.1 and 1.3) to account for significant procurement delays.
## C: DETAILED OUTPUT SCORING
Output Title	Revenue legislation and administration reforms developed and enacted in FGS and Somaliland
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
A functioning revenue authority is in place in Somaliland that effectively manages revenue collection	Revenue forecasting tool used to inform Somaliland's 2018 budget preparation / Large tax payers registration process underway	A. Revenue forecasting model in place and applied in the budget preparation process. / 150 large taxpayers registered so far.
Customs administration in FGS is centrally controlled and providing increasing revenue returns	FGS has a feasible strategy in place to achieve improved customs policy and administration	B. Whilst diagnostic work and reform roadmaps now exist, they do not amount to a consolidated and sufficiently detailed revenue mobilisation strategy.
Enhanced statistical capacities for key fiscal data sets (forecasting of revenue and expenditure, balance of payment etc) in FGS	Qualitative assessment indicates positive role of IMF’s technical support to FGS’s efforts to meet SMP reform benchmarks	A. Feedback from government and donor stakeholders suggests the IMF has to date played a positive technical advisory role in (re)building the capacity of Somalia’s Ministry of Finance and Central Bank

Key Points
A three-year TA project in support of Somaliland Revenue Authority was tendered in June 2017. Two bids were received and evaluated in August and a preferred bidder selected. Political developments (postponed elections) and procurement delays have impacted on the project implementation schedule. The first phase of support to tax policy and administration in Somaliland ended in late 2016. The project delivered important reforms e.g. around customs valuation and business processes; large taxpayers registration; and revenue forecasting. Expectations around the establishment of a Somaliland Revenue Authority were set too high. Understanding the political economy of revenue reform, relations between the Government and potential large taxpayers, and the sticky nature of this reform were not strong enough. Lessons from Phase I reviews also suggest that proactive engagement of a wider set of stakeholders (e.g. politicians, businesses and clan elders) is needed to ensure that tax reforms are sustainably implemented.
The Federal-level customs reform project is still undergoing procurement (see commercial section for detail). Substantial additional financing from the USAID and EU has been secured for this project, bringing the total budget to £10.2m (or more than double the initial envelope). This delegated funding will enable more ambitious results to be targeted, and allow DFID to leverage greater influence in a key policy area.
There has been progress on the FGS side in developing policy and strategy documents that provide a pathway for increased revenue collection in Somalia. These include the revenue and customs components of the wider “PFM Reform Action Plan 2016-2020” and an “Action Plan for Modernization of Revenue Administration” developed by the MoF’s Revenue Directorate. These were in turn informed by diagnostic work carried out with World Bank support, including a road-map for moving towards a modern customs framework (underpinned by common ad-valorem customs duties); a review of customs operations in Mogadishu; and a tax gap analysis. The recently published flagship World Bank report “Somalia Economic Update” also has a specific focus on revenue mobilisation, including proposals for a number of short/medium term measures for addressing pressing gaps in tax policy and administration.
Whilst all these documents allow for a degree of strategic sequencing and prioritisation of inland revenue and customs reforms (including coordination of support by development partners), they still do not add-up to a coherent and sufficiently detailed implementation strategy that is fully owned by Government.
While a formal evaluation of the IMF Somalia Trust Fund (TF) for Capacity Development will be commissioned next year, feedback to date suggests that the IMF has played a positive technical/policy advisory role in Somalia through TF and Staff Monitored Programme (SMP) engagement.
Successful operationalisation of the TF in-country remains crucial in supporting progress against SMP benchmarks. Facilitation of in-country missions by IMF experts now constitutes a component within the FGS Revenue project currently being tendered. This will enable more “hands-on” follow-up to TF training activities (which take place in third countries) with Mogadishu-based mentoring or implementation support on agreed policies and legislation.
Therefore, DFID contribution to date has been limited to technical and policy engagement with IMF TF interlocutors (including through chairing the TF Steering Committee) and in the context of IMF SMP monitoring missions.
Summary of responses to issues raised in previous annual reviews (where relevant)
On track (as per Annex 2).
Recommendations
- Make full use of opportunities afforded by PREMIS engagement on revenue mobilisation at federal, state and district levels to facilitate consensus across relevant stakeholders (Government, IMF, WB, AfDB and donors) on key tax policy & administration priorities and on ways to ensure a more a coherent approach to developing tax policies, systems and institutions across tiers of government. These need to be linked with wider political negotiations around resource management and revenue sharing.
- Establish a Tax Commission in Somaliland to make the case for tax reform. This needs to include a wider range of stakeholders to establish a workable reform.
- Ensure that logframe milestones for this component are updated following the mobilisation phase for the two revenue projects, and that progress on tax reform in Somaliland is measured against quality/equity of taxation (in addition to a decreased reliance on trade taxes).

Output Title	Human resources policies, systems and procedures developed that enable more appropriate deployment of staff in the civil service
Output number per LF		2	Output Score	B
Risk:		Severe	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
A civil service establishment database that informs the payroll and enables other HR polices (including severance and pensions) is in place (FGS and Puntland)	Audit of civil service establishment conducted	B. The process has advanced in Puntland but was delayed at FGS level.
Civil service management and training policies are designed and adopted in FGS & Puntland	Revised legislation and regulations for civil service management and training approved by Cabinet/ Parliament	B. CS legal/regulatory frameworks have been prepared but not yet approved by the Federal and Puntland governments.

Key Points
Civil Service head-count audit and biometric registration exercises were successfully finalised in Puntland State, with preliminary results due to be issued soon. At FGS level the process has suffered significant delays, partly attributable to the change in government. Instituting a reliable CS staff database remains a crucial work-stream, as will enable the establishment of a robust baseline for planning the introduction of critical HR policies.
Although this work is primarily funded by the World Bank led Multi Partner Fund (MPF)[1] (under the Capacity Injection Programme – CIP), the PREMIS-funded work is providing additional support to the Bank in support of delivery by the three core programmes for strengthening economic governance in Somalia (namely PFM, Recurrent Cost and Reform Financing (RCRF) and CIP, collectively known as “the troika”). These collectively account for 70% of Trust Fund spending. The additional DFID investment in the Bank through PREMIS will ensure greater operational synergies and coherence in Trust Fund supported reforms.
[1] DFID is one of the largest contributors to the WB MPF via our Support to Economic Recovery in Somalia programme (SERS).
The WB funding under PREMIS is being used to mobilise additional WB expertise, and flexibly fund pieces of work that might unblock emerging problems, especially those that cut across the Troika programmes. It is expected that increased Bank’s engagement and supervision of these programmes, which are the largest and operationally most complex elements of the MPF, will contribute to accelerate progress on crucial, interlocking areas of state building in Somalia.
The Ministry of Labour and Social Affairs has finalised a draft Federal Civil Service Law and Code of Conduct, with support from UNDP. It is expected that subsequent passing by Parliament will catalyse renewed effort and attention around key outstanding policy work-streams that have to date suffered from weak government leadership and coordination.
These include the enforcement of establishment controls to ensure the number of civil servants does not grow beyond a sustainable size, and that new CS recruitment is properly planned and targeted (in alignment with strategic priorities). Other important work-streams concern the approval of policies and implementation frameworks for CS pay and grading, and for pensions and redundancy management. Some of these areas will benefit from additional WB support via PREMIS.
The UNDP delivered component (the Strengthening Institutional Performance project – SIP), which represent a continuation of previous commitments under the Core State Functions programme, has continued to present delivery challenges around strategic direction; quality/VfM; and M&E systems. Effective coordination between UNDP and the World Bank in this area remains an issue, as evidenced by failure to hold joint Steering Committee meetings for the Capacity Development programme.
A decision on whether to continue supporting public sector reform through UNDP will be made following an evaluation of the programme; an appraisal of the UNDP’s ProDoc for a new phase of support (expected by 2018 Q1); and an internal assessment of alternative options for effectively delivering PREMIS Civil Service Reform objectives (including shifting resources to other components of PREMIS).
Summary of responses to issues raised in previous annual reviews (where relevant)
Response is ongoing. Additional/complementary actions are recommendations below.
Recommendations
- Facilitate a more coherent approach to public sector capacity development, by maximising strategic focus, coordination and synergies between PREMIS supported projects, and opportunities afforded by co-chairing of relevant donor-government technical working groups. In particular, facilitate continued and strengthened coordination between the UNDP and WB programmes, as well as with DFID’s bilateral support to FMS (output 3) to ensure systems and institutions being currently developed are grounded on a shared vision about a realistic public sector model for Somalia.
- Use programme and policy engagement opportunities (including through continued close collaboration with SERS) to push for accelerate progress against crucial CS policy work-streams and help address CS affordability questions.
- Revise the WB-related indicator and/or milestones to clarify attribution to activities delivered using PREMIS funding.
- Decide on whether to support the next phase of the UNDP programme by end of Q1 2018.

Output Title	Federal member states have systems in place for managing and accounting for their expenditures
Output number per LF		3	Output Score	A+
Risk:		Severe	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Budget departments are in place in new Federal States with functioning FMIS	2	A+ 3 FMS (Jubbaland, Galmudug, South West)
Number of Federal States implementing projects using public procurement rules	1	A+ 2 FMS (Jubbaland and South West)

Key Points
The contract for the “PFM in FMS” project was awarded in November 2016, followed by a three-month Inception phase. £3.6m of co-funding from the EU Somalia Delegation was secured for this project, which has exceeded expectations in setting-up from scratch a basic administrative capability in a very low capacity environment.
Whilst the constant state of flux in programme counterparts has been a challenge, the project has succeeded in instituting basic systems for performing core PFM and CS management functions in Jubbaland, Galmudug and South West states. Work is currently underway to set-up budget and procurement departments in Hirshabelle, and to support the hiring and training of key staff. It is expected that the Hirshabelle IFMIS will go live in November. However, limited revenue mobilisation remains a serious constraint in all four FMS, meaning budgets are small (and mostly spent on the wage-bill) and limited procurement transactions are currently being undertaken.
Project TA and capacity building work to date has focused on:
- Preparing core statutory frameworks for taxation, PFM and CS management;
- Establishing basic macro-fiscal management, procurement and internal audit capacity (staffing and capacity development);
- Setting-up and maintaining integrated PFM IT systems linked to a single treasury account (allowing the formalisation of existing revenue streams, the preparation and execution of State budgets and preparation of financial statements); and
- Delivering a substantial package of trainings to newly recruited technical and executive cadres.
The project has also played a catalytic role in enabling FMS to access WB MPF financing for state building efforts. Salaries for 250 civil servants across three FMS are currently being reimbursed under the RCRF programme, through fiscal transfers from the FGS. This was made possible by the existence of a functioning PFM architecture (including payroll management and payment systems) and PREMIS additional efforts in supporting minimum fiduciary management practices, thus enabling recipient governments to demonstrate compliance with a set of WB’s 'readiness criteria' for recurrent cost financing (see outcome KPI)
The project’s visibility at the level of government and donor counterparts has been steadily increasing and the quality of the TA is demonstrated by adherence to PFM best practice (e.g. compliance with IMF’s Government Financial Statistics, and with International Public Sector Accounting Standards).
A flexible and adaptive approach was embedded in contract design to ensure timely response to the challenges of a fluid and unpredictable operating context, including through expanding the initial technical scope of activity to areas not initially foreseen in the project.
As would be expected for interventions seeking to strengthen economic governance in low accountability environments, the project has encountered significant political-economy challenges in its first year of implementation, and will likely continue to do so in the future.
To date, issues have emerged around e.g. options for outsourcing revenue collection and other government services; plans for granting concessions for foreign investment and port management; and political tensions with FGS that will increasingly come to the fore as FMS negotiate a framework for fiscal federalism and revenue sharing.
 Summary of responses to issues raised in previous annual reviews (where relevant)
On-track (as per Annex 2).
Recommendations
- Continue working closely with the Supplier in understanding and navigating political economy challenges as they arise, ensuring a timely escalation of issues at the appropriate levels.
- Explore concrete options for strengthening operational linkages and complementarities with the Somalia Stability Fund (SSF) and Security & Justice programmes to maximise the aggregate impact across DFID’s programme portfolio in FMS, and DFID’s policy influence on economic governance issues.
- Revise upwards the level of ambition for the selected milestones and/or consider amending the output indicators to better capture the breath of work supported through this component.

Output Title	District administration are more responsive and capable
Output number per LF		4	Output Score	B
Risk:		Severe	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Number of legitimate (recognised by State & Federal Government) district councils established in the South	4	B. 2 district councils have been formed to date in Adado (Galmudug State) and Hudur in South West (with complementary support from other stabilization programmes). Preparations for district council formation are currently being supported in Kismayo, Garbaharrey, Baidoa and Barawe.
Number of districts that have systems in place to increase revenue generation (either though property taxes or business licensing)	16	A. TA, training and system development support on local/municipal taxation delivered by UN-Habitat and UNDP to the 16 JPLG supported districts in Somaliland and Puntland.
Number of districts that implemented their local development fund (LDF) budgets as per their work-plan and are eligible for an increase in LDF funding.	2 more	N/A All 16 participating districts have been receiving a share of the LDF based on relative performance against a set of criteria: 20% of the LDF is shared equally; 30% according to an estimated population ratio and 50% based on performance (this indicator and accompanying milestones will be clarified going forward - reccomendation)

Key Points
Whilst there has been progress, concerns persist on the VfM delivered by JPLG as a whole (thus justifying a B for this output). Longstanding weaknesses and gaps with governance and coordination arrangements; and with overall strategic direction (including lack of clarity over the expansion and sustainability of the JPLG model) have only partially been addressed (see next section for detail). These were also highlighted in reviews under the PREMIS precursor programme (Core State Functions), which also funded JPLG.
The mixed uptake and commitment to implementing recommendations on these issues, coupled by the failure to meet previously agreed timelines for the development of the next phase of the programme, has led DFID to consider alternative options for delivering this support from 2018 (as had been communicated in December last year and as part of subsequent discussions).
Work for laying the ground for district council formation in south-central FMS has started. Local government laws were recently passed in Jubbaland and South West, paving the way for the election of District Councils in those FMS. Whilst work has begun on undertaking the required consultations and capacity development of government institutions responsible for decentralisation, progress has been slower than originally envisaged in the BC due to operational and funding constraints.
The LDF mechanism and accompanying TA to local districts/municipalities in Puntland (seven local governments), Somaliland (eight) and Galmudug (Adado district) has continued to leverage some local revenue generation and improved financial management and procurement practices in JPLG-supported districts.
These have included participatory annual planning and budgeting processes and the execution of priority services and small-scale infrastructure projects. For example, total local revenue in target districts and municipalities in Somalialnd has increased from $22.6m in 2016 to $33.2m in 2017 (Q3) i.e. a 41% increase (following a 59% increase registered the previous year). This progress is in large part attributable to JPLG-funded TA and public awareness raising work especially around property taxation and business licensing, in particular in the larger municipalities of Garowe and Bosasso (Puntland) and Hargeisa, Burao and Berbera (Somaliland).
Part of the PREMIS local governance has been used to fund an additional UNDP programme (the State Formation Programme) previously funded under the Conflict Security and Stability Fund (CSSF) and working on state building and capacity development in the new FMS. This was done after funding from CSSF was cut-short in-year, and in order to ensure that the programme remains well coordinated with DFID programmes in new FMS (PREMIS and SSF), thus maximising synergies between our local governance, stabilisation and state-building portfolio.
Summary of responses to issues raised in previous annual reviews (where relevant)
On-track (as per Annex 1).
Questions raised in reviews and assessments (e.g. Due Diligence Assessment and Mid Term Review) over the value and sustainability of the capacity building work (that accounts for most of the programme’s spending) and quality of programme management, have not to date been satisfactorily addressed.
Operational weaknesses have included inefficient planning and budgeting processes coordinated by UNDP (with limited consideration of evidence of past performance/VfM in informing allocations across participating agencies and output areas); insufficient financial reporting and transparency; weak M&E frameworks and high overheads. For instance, unrealistic budgets in 2016 have led to the transitioning of significant financial commitments into 2017 (thus eroding the financial space for new activities).
Early drafts of the new UN Project Document for the next phase of JPLG shared with donors suggest that many of the key questions repeatedly raised by donors have not been satisfactorily addressed. These included articulating a realistic roll-out strategy for new FMS and setting-out a leaner/more sustainable delivery model. Specific proposals included considering a reduced scope of activities and/or implementing agencies based on comparative advantage and more focused programme objectives; a clearer implementation strategy grounded on an evidence-based ToC; greater political awareness and conflict sensitivity; and instituting streamlined management arrangements.
Recommendations
- In close coordination with JPLG and in consultation with government and donor stakeholders, decide on the most appropriate delivery route for channelling the remaining Local Governance allocation based on the feasible options identified to date. Aim to make a final decision by December 2017 and have implementation arrangements in place by March 2018.
- Consider reducing the impact weighting of this output (to 25%) to better reflect the proportionate contribution of this component to the programme’s overall objectives.
- Clarify wording of output indicator 4.3 to better capture the impact of the LDF mechanism

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
VfM performance compared to the original VfM proposition in the business case
Effectiveness
For components that are currently operational, on the whole effectiveness has been good, as attested by good progress against logframe indicators at both output and outcome level.
Delay in procuring the two revenue projects (inc. the IMF in-country support on macroeconomic and fiscal management capacity) means it is premature to assess VfM for component 1. For the Somaliland Tax and the soon to be tendered FGS customs components, ultimately cost-effectiveness will be assessed by whether DFID funded reforms provide a foundation for increased revenues. Evidence from the Local Governance component (summarised under output 4) and from the first phase the Somaliland tax project suggests this has been the case in the more stable settings of Puntland and Somaliland. In Somaliland domestic tax revenue is projected to increase from $203m in 2016 to $259m in 2017) partly on account of DFID-funded efforts to reform tax policy and administrative procedures.
Similarly, Jubbaland has seen its tax revenue more than double from end-2016 up to Q3 2017 (from about $5m to $10.5m), largely on account of increased formalisation and recording on the Budget of trade taxes from Kismayo Port revenues. This progress can be attributed to PREMIS to the extent that the programme has supplied the technical advice and capability for enabling this revenue (and the expenditure it is funding) to be transparently captured in the budget. Given that less of £0,4m has been spent on TA/capacity building to Jubbaland over the last year (of which revenue was just one of many work-streams), the investment has clearly represented VFM for UK investment. It is expected that current work on tax systems and institutions will drive further domestic revenue mobilisation in Jubbaland and other beneficiary FMS in the coming years.
At FGS level early signs are also encouraging: the IMF estimates a 30% yearly nominal increase in tax revenue albeit from a very low base (from $87m in 2016 to $114 conservatively projected until December 2017). Although PREMIS and wider UK policy dialogue and influencing efforts (e.g. as part of engagement with IFIs on the SMP and of the London Somalia Conference) are likely to have contributed, it is premature to assign any direct attribution to the programme’s engagement with FGS on tax to date.
For the CS and wider public sector reform work, the VfM for UK investment has been less clear to date. Ultimately effectiveness (and cost-effectiveness) will be a function of whether the programme contributes in the long term to the development of a viable public sector model in Somalia, which is too early to tell. This will be as much the result of unquantifiable influencing and policy-dialogue (on issues such as functional assignments across tiers of government and wage-bill affordability) as to spending on inputs.
Efficiency
With regards to the CS component, macro-level efficiency (and long-term effectiveness) is being driven by: 1) policy and programme efforts around managing pressures for aspirational/fiscally unaffordable state structures and associated staff establishment (see output 2 narrative), and 2) groundwork on instituting merit-based recruitment practices at federal, FMS and district levels (which cross-country evidence suggests is the cornerstone of state bureaucratic capability)
Under the new “PFM in FMS” component, a degree of efficiency can be inferred from the fact that stretching project milestones were met against a relatively limited investment. This is affirmed by evidence of much lower cost of setting-up and maintaining PFM systems (about £0.45m per FMS), when benchmarked against similar WB projects at FGS level (and internationally). However, caution is required in drawing VfM conclusion as there is a need to account for context specificity of IFMIS development and the varying degree of IT sophistication and capability.
For UN-led components (SIP and JPLG), where DFID has less influence and control over M&E and financial reporting frameworks it has proven more challenging to perform a meaningful comparison of project inputs against activities and outputs and we have had to rely on external assessments. Preliminary evidence from a recent evaluation of the UNDP Capacity Development project suggests there is room to improve efficiency (the review highlights slow implementation coupled with high management costs driven by international staff and consultants). Earlier reviews of JPLG pointed to similar issues.
Economy
There has been some uptake of VfM recommendations by the LDF element of JPLGe.g. when evaluating procurement bids for LDF projects, ex-ante area-specific unit cost schedules are applied in bill of quantity reviews, ensuring that bids are reasonably costed.
For the private-sector delivered components economy (and wider VfM) was driven by the execution of rigorous processes for procurement, post tender clarification and budget negotiations. These include agreement on M&E/reporting expectations and on monitoring of selected VfM metrics (e.g. average costs of trainings per participant which have exhibited a one third reduction against budget estimates for the first six-months of the ASI-delivered component). Ex-ante embedding of VfM considerations and close engagement with suppliers after contract signature will be ensured for the upcoming tax projects.
For the PFM in FMS case, reductions in the fees budget, coupled by agreement on enhancing the technical scope and level of ambition of the project were also successfully negotiated. Additionally, efficiency savings from Inception were re-invested into implementation) and agreement on lower fee rates for Core Team members compared to initial commercial bid also drove improvements in economy. Economies of scale were also driven through shared operational platforms (including cost sharing on rent, security and administrative resources) for DFID-funded projects (PREMIS and SSF). A degree of sustainability was also ensured by the agreement to rebalance Team composition over the course of the project in favour of national TA (with a view to maximise skills transfer to Somali staff from international experts).
Assessment of whether the programme continues to represent value for money
As per the qualitative evidence discussed above, benefits from PREMIS, although largely of qualitative nature at this stage, continue on the whole to outweigh the costs and associated risks, thus offering value for money for UK investment.
Financial Performance
To date, cumulative spend against the programme’s total budget of £38m was £10.3m corresponding to about 27% of the original budget. Spend since the last AR was £6.4m or 17% of the budget, which although lower than the BC estimate of 27% execution rate for FY 2017/18, is still an acceptable rate in view of the delays experienced by the two revenue components. The breakdown of spend by components is as per the table below.

Tranches to UN agencies have been disbursed upon receipt of quarterly performance reports. Payment to the World Bank’s EFO will occur in two instalments (20:80 split) of which the first has been released. ASI is paid in arrears on a quarterly basis, following review of output delivery and financial performance against agreed budgets.
The programme exhibited an aggregate 90% disbursement rate against financial forecasts. Given the two-year no cost extension that was recently approved, the programme is on track to fully execute its budget by the new end-date of March 2022.
Key cost drivers and performance
Cost drivers vary across the six components, as illustrated below
Sub-programme / IP	Key cost drivers (% of total budget)
Somaliland Tax (Phase 1 extension)	Fees (77%); expenses (23%)
PFM in FMS (ASI)	Fees (43%); expenses (13%); training and capacity building costs (15%); IT systems (17%); grant component (11%)
JPLG	HR related costs (26%); grants and partnerships (19%); contracts and projects (18%); training and capacity building costs (17%); local office cost (6%)
UNDP – Strengthening Institutional Performance project	Local consultants (27%); contractual services (21%); international consultants (20%); rent (10%); IP staff 9%
World Bank EFO	Staff time and short term consultancy cost

Quality of financial management
All funds have been paid out in accordance with standard agreements/MoUs with multilateral agencies (UNDP and the World Bank), and as per contractual arrangements in the case of ASI.
Quarterly reports are received by three (ASI, UNDP, JPLG) of the four Implementing partners delivering the active components of PREMIS. For the WB agreement only annual reports are due.
Financial processes for ASI (despite some initial forecasting challenges) and the WB are assessed as robust and offering good fiduciary assurances whilst issues persist with timeliness, level of disaggregation and quality of financial reporting for UN executed projects.
At project level, the LDF is audited by Somaliland and Puntland Offices of Auditor General on a bi-annual basis. Latest available reports issued an unqualified opinion (also see risk section). Audits of financial statements were also conducted on UNCDF (the UN Agency effectively acting as the managing agent for the LDF); UNDP (JPLG project) and UNDP (SIP project) by UNDP Office of Audit and Investigation. An unqualified opinion was issued in all cases. A compliance audit of UNDP-Somalia was performed in 2017 to assess governance, risk management and control aspects. The Office was assessed as “partially satisfactory / some improvements needed”.
Audited project accounts by ASI are due at the end of year 1 of implementation (in April 2018).

Date of last narrative financial report	Q2 2017 (SIP); Q2 2017 (JPLG); Q3 2017 (ASI); UN-MPTF (2016)
Date of last audited annual statement	JPLG-LDF (2017); UNDP-JPLG (2017); UNDP-SIP (2017); UNDP Somalia Office (2017)

E: RISK
Overall risk rating: Major
After mitigation, the overall residual risk is assessed as “major”, with variation across components. The controls, safeguards and other risk management systems and processes in place, mean the level of risk is still within the Team’s risk appetite given the assessment of the risk-reward balance for PREMIS.
Overview of programme risk
State-building in Somalia remains a huge challenge and the programme continues to face a range of inter-dependent political, security, delivery and fiduciary risks emanating from an uncertain and rapidly evolving operating context. To varying degrees, all of these risks have materialised in the second year of implementation. Risk registers are maintained by implementing partners for each programme currently funded under PREMIS (except the EFO, to which wider WB risk management practices apply).
Risks are regularly monitored by the SRO and risk ratings, trajectories and mitigations have been updated as appropriate. For instance, new contextual risks around political settlements in each FMS and faultiness emerging from FMS-FGS negotiations around fiscal federalism have been added. Unexpected delays in procurement of suppliers for delivering revenue reform programmes have also posed a reputational risk.
Existing and new risks are being effectively mitigated through existing risk management mechanisms. As such, they do not warrant a strategy change. Programmatic shifts are being considered as a result of delivery risks materialising (around UNDP and JPLG). Delays in contracting and procurement have also posed a significant delivery risk, which was successfully managed by the early securing of a no-cost extension.
Outstanding actions from risk assessment
The LDF ASP concluded that the overall level of residual fiduciary risk remains moderate because the design and operation of the LDF has safeguards at all stages of financial management that mitigate the risks of using government(s) PFM systems in Somaliland and Puntland. This is consistent with the overall conclusion of the last FRA as no new areas of risks have emerged. Key outstanding risks are around quality of financial reporting and transparency; and quality of external audit (time lags and scope/depth of audits performed by Somaliland’s and Puntland’s Office of Auditor General). A separate risk assessment for the Special Purpose Grant element of the PFM in FMS project has also been developed and will be reported on and updated yearly.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
Long delays in getting the two tax projects off the ground means the programme is currently off-track to deliver on its revenue component objectives as initially set-out in the BC.
However, a no-cost extension has been granted to extend the implementation period for the programme from its current Business Case end-date of May 2020, to March 2022. This will align the DFID programme cycle to the contract timeframes, and ensure delivery of the two components of PREMIS that have suffered unanticipated procurement and mobilisation delays.
The £4.75m FGS revenue component had been tendered in March 2016 and a contract awarded after a lengthy negotiated procedure, given there was only a single bidder for this work. The contract had an expected implementation timeframe of 3.5 years. This bid was subsequently withdrawn as a consequence of DFID’s Supplier’s Review process. This component is in the process of being re-tendered, which will result in a minimum one and a half year delay compared to initial predictions. Updated ToRs have been finalised in consultation with the FGS’s Ministry of Finance and other interested stakeholders. A Sourcing Strategy for the programme has been signed-off by PCD and will be submitted to Cabinet Office for approval. A new call for proposals is likely to go out in December 2017.
In order to try and attract a wider pool of suppliers to deliver this work an Early Market Engagement was organised in June, highlighting the changes to the original tender i.e. increased budget (see below) and greater clarity of the ask. The event was successful in generating more interest.

Performance of partnership (s)
Delivery of PREMIS has entailed establishing and maintaining effective working relationships with:
- Official counterparts - from a range of government institutions at the level of FGS, Somaliland, Puntland and the four new FMS;
- IPs - ASI, WB, UNDP, UN-JPLG Partner Agencies; and
- Co-funding agencies - US and EU.
The latter is indicative of positive engagement with donor counterparts, and trust in DFID’s institutional capability to effectively manage delegated funding.
Communications and information sharing – both formal and informal – have to date been productive, as have been working relationships on the whole.
The programme has also benefited from attendance of PFM and Revenue sub-working group meetings; briefings by IMF Staff on mission and by Financial Governance Committee members; as well as Capacity Development and JPLG steering committee meetings and ad-hoc donor consultations. Ensuring sufficient level of engagement with interlocutors (especially Somali government officials) across the full spectrum of PREMIS-funded activities has been a challenge due to time/capacity constraints and limited access due to security restrictions.
With regards to ASI, following some initial programme management issues (linked to protracted contract negotiations, changes to team composition, spending forecasting and agreeing an M&E framework), effective ways-of-working are now in place. The team in place is technically capable and has demonstrated flexibility in responding to DFID’s demands (e.g. on the technical scope of the project). Governance and reporting arrangement are being fine-tuned but are generally functioning well, with extent of detail in financial and activity reporting ensuring acceptable visibility of actual costs. Performance against a supplier scorecard assessing various aspects of contract management will be measured yearly and incentivised by conditioning a proportion of payment to agreed benchmarks. The first assessment will be carried out in April 2018.
More generally, private sector suppliers have demonstrated capability to deliver in a complex environment, but requiring close DFID management and engagement to ensure compliance with DFID systems and procedures, and stronger awareness of the bigger political picture and associated risks.
After a slow start, a collaborative working relationship is also taking shape with the Bank in the context of the EFO (and wider MPF). Whilst the programme is benefitting from the Bank’s strong technical expertise (in the form of quality knowledge products that are being published on Somalia), there is a need to strengthen engagement with TTLs and MPF management around ensuring strategic evidence/analysis is proactively and regularly shared with donors so as to feed into a more effective policy dialogue with government.
UN-delivered components, which represent a continuation of work previously funded under the Core State Functions programme, have continued to pose challenges. As per outputs 2 and 4 narrative, diverging expectations on programme delivery standards remains an issue, and despite significant time and effort spent engaging on these issues responsiveness to DFID demands (e.g. on strategic reporting and proactive flagging of risks and opportunities) has been mixed.
Asset monitoring and control
PREMIS partners have submitted assets registers annually according to smart rules. Any purchases above £1000 have been submitted and monitored biannually. The programme intends to monitor assets on quarterly basis alongside quarterly reporting and meetings. Assets that are not used by existing partners will be released/transferred to upcoming projects within the programme.

 CONDITIONALITY ( page)
Update on partnership principles (if relevant)
Partnership principles – for the FGS and Somaliland - are updated regularly at Office level and appraised in the context of this programme due to a partial, indirect use of government systems (via UN and under strict levels of oversight and accompanied by the deployment of high levels of TA).
This is the case for the LDF component of the JPLG and for PREMIS-PFM in FMS component, for which limited amount of funding has been earmarked as part of project design, to enable testing the functionality of core PFM systems recently introduced, with DFID support, in the Ministries of Finance (MoF) of new FMS. This support will be used as a means to demonstrate systems effectiveness, with the IP (ASI) performing the role of managing and oversight agent. A separate risk assessment was prepared to identify and manage fiduciary risks emanating from this funding instrument.

H: MONITORING & EVALUATION
Evidence and evaluation
The PREMIS ToC and underlying assumptions set out in the BC still hold.
An evaluation of TA delivered under the IMF Somalia Trust Fund for Capacity Development will be commissioned next year, and will be used to inform the next phase of the Trust Fund.
A UN commissioned joint evaluation of PREMIS funded capacity development and state formation projects implemented by UNDP is currently underway.
Under the PREMIS-PFM in FMS programme, a baseline of public administration systems in FMS was also carried out using a bespoke methodology that draws from internationally recognised diagnostic tools such as the Public Expenditure and Financial Accountability performance framework and the Tax Administration Diagnostic Tool. Political Economy Assessments were also conducted for Jubbaland and South-West. A technical review of Kismayo Port operations and governance was also commissioned.
A review of JPLG funded road rehabilitation work commissioned by DANIDA (under its Third Party Monitoring and External M&E Support for Somalia Country Programme), concluded that road rehabilitation projects financed under the LDF deliver good VfM overall, although sustainability issues around operating & maintenance costs were also raised.

Monitoring progress throughout the review period
This AR was based on regular meetings with implementing partners (and other relevant stakeholders); reviews of quarterly/yearly progress reports and of any other pertinent source of evidence.
Access constraints have meant limited field monitoring visits and interviews with direct beneficiaries have been conducted within Somalia, except for meetings with UNDP SIP/JPLG project staff at the British Embassy in Mogadishu, and with PFM in FMS official counterparts in Baidoa and Kismayo as part of a “regional flyaway” initiative. However, meetings with government officials are regularly held in Nairobi.
At the project level, implementing partners had responsibility and were held accountable for monitoring implementation and reporting to DFID, based on their own log-frames which fed into the overarching log-frame.
DFID also commissioned separately third party monitoring (TPM) support across all the governance and peacebuilding portfolio. TPM systems and processes instituted under the Learning and Monitoring Programme for Somalia – LAMPS are enabling the team to maintain oversight of project activities and outputs, independent of implementing partners’ reports.

Annex 1: Summary of output level recommendations
Output	Action	Timeframe	Owner
1	Make full use of opportunities afforded by PREMIS engagement on revenue mobilisation at federal, state and district levels to facilitate consensus across relevant stakeholders (Government, IMF, WB, AfDB and donors) on key tax policy & administration priorities and on ways to ensure a more a coherent approach to developing tax policies, systems and institutions across tiers of government. / Ensure that logframe milestones for this component are updated following the mobilisation phase for the two revenue projects, and that progress on tax reform in Somaliland is measured against quality/equity of taxation (in addition to a decreased reliance on trade taxes)	Continuous	SRO, Responsible Owners (RO) for FGS and Somaliland revenue component
1	Establish a Tax Commission in Somaliland to make the case for tax reform. This needs to include a wider range of stakeholders (e.g. politicians, businesses and clan elders) to establish a workable reform.	Continuous	RO for Somaliland component
2	Facilitate a more coherent approach to public sector capacity development, by maximising strategic focus, coordination and synergies between PREMIS supported projects, and opportunities afforded by co-chairing of relevant donor-government technical working groups. In particular, facilitate continued and strengthened coordination between the UNDP and WB programmes, as well as with DFID’s bilateral support to FMS (output 3) to ensure systems and institutions being currently developed are grounded on a shared vision about a realistic public sector model for Somalia. / Use programme and policy engagement opportunities (including through continued close collaboration with SERS) to push for accelerate progress against crucial CS policy work-streams and help address CS affordability questions.	Continuous	RO for CS reform
2	Revise the WB-related indicator and/or milestones to clarify attribution to DFID EFO / Decide on whether to support the next phase of the UNDP programme by end of Q1 2018	Q1 2018	RO for CS reform
3	Continue working closely with the Supplier in understanding and navigating political economy challenges as they arise, ensuring a timely escalation of issues at the appropriate levels. / Revise upwards the level of ambition for the selected milestones and/or consider amending the output indicators to better capture the breath of work supported through this component.	As required	RO for Federalism and decentralisation; Team Leader
3	Explore concrete options for strengthening operational linkages and complementarities with the Somalia Stability Fund (SSF) and Security & Justice programmes to maximise the aggregate impact across DFID’s programme portfolio in FMS, and DFID’s policy influence on economic governance issues.	Continuous	SROs for PREMIS, SSF and S&J programmes
4	In close coordination with JPLG and in consultation with government and donor stakeholders, decide on the most appropriate delivery route for channelling the remaining Local Governance allocation based on the feasible options identified to date. Aim to make a final decision by December 2017 and have implementation arrangements in place by March 2018.	December 2017	SRO; Team Leader
4	Consider reducing the impact weighting of this output (to 25%) to better reflect the proportionate contribution of this component to the programme’s overall objectives. / Clarify wording of output indicator 4.3 to better capture the impact of the LDF mechanism	Q1 2018	RO for Federalism and decentralisation

Annex 2: Summary of responses to issues raised in previous annual reviews
Output 1
In Somaliland, the project and contracting arrangements will need to demonstrate adaptability to the political context in this election year. The team should put in place a governance structure with clear, formally agreed communications channels between the service provider, DFID and the Ministry of Finance at the political level that includes a clear accountability structure within the Ministry (civil servants and Minister).	Ongoing. Phase 1 faced challenges in engaging the MoF politically. Phase 2’s focus around establishing a Tax Commission will help address this challenge by widening the stakeholders around this reform effort
The contractual and reporting arrangements with the Federal Government should learn from the experience set out above in Somaliland. It will also be important to keep up the time pressure throughout the procurement process to ensure no delays to the start date.	Done. Clear ToR requirements on governance arrangements and performance management expectations. Procurement had to be re-run for reasons beyond the PREMIS Team’s control.
For management purposes, Component 1.1 finances should be ring-fenced as an output within the Component 1.2 tender. The Service Provider should be instructed to contract and take Duty of Care for the IMF consultants and facilitate missions as required that assist and further the work of the Trust Fund. Components 1.1 and 1.2 should be merged on Aries.	Done. Components were merged in AMP and IMF-TF element clarified in the Revenue project ToRs
Output 2
Continue to work closely with the Bank on development of the EFO, setting a deadline for completion if necessary	Done. “Somalia Governance” EFO agreement signed in April 2017 and first tranche released
During the next performance year efforts to develop a comprehensive road map for public sector reform should initiated (and specific roles for WB and UNDP identified)	Ongoing. Findings from an ongoing UNDP SIP evaluation and the World Bank’s forthcoming CIP Mid-Term Review will be used to address this recommendation.
Output 3
Ensure timely communication with EU on their proposed Contribution Agreement once a Service Provider has been selected, in order to ensure an agreement is in place prior to contract signature	Done. Delegated cooperation agreement is in place and first tranche has been disbursed.
Focus on ensuring effective relationship/ ways of working/ expectations are set out with the service provider	Done. Effective governance arrangements and ways of working are in place.
Output 4
Future local governance support: Communicate our plans, timelines and timelines clearly. Continue to work with JPLG management, the UN leadership and key donor partners to arrive at an acceptable concept note for a possible successor programme by early 2017, based on the Mid-Term Review, the due diligence and other evidence. Start exploring other options concurrently.	Done (see output narrative). Alternative delivery route options have been appraised.