Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: MOBILISING FOR DEVELOPMENT (M4D) PROGRAMME
Programme Value: £17.5 million		Review Date: 23-25 February 2015
Programme Code: 5669	Start Date: June 2012	End Date: June 2018

Summary of Programme Performance
Year	Yr 1	Yr 2
Programme Score	A	A+
Risk Rating	Medium (to High)	Medium

Summary of progress and lessons learnt since last review
Summary of Progress:
M4D continues to stimulate processes of local governance reform and developmental change through an approach which combines experimentation with capacity and relationship building. During the last year M4D has enabled conversations and collaborations between community representatives and policy makers and service providers. M4D has helped create new space for dialogue and enhanced cooperation which has built confidence that change can happen. The flexible, locally driven approach means that multiple development possibilities are explored simultaneously. M4D remains committed to an experimental approach which explores “better fit approaches” and locally identified solutions to service delivery problems or accountability barriers. The flexible grants programme enables M4D to do this “with” rather than “for” or “to” the communities with which they work. M4D recognises the political dimensions of this work and remains alert to the incentives which drive or confound change.
Rightly, the second year of the programme has focused largely on programme consolidation, building on the learning from year one and responding to the recommendations from the first Annual Review. M4D has reached an agreement with an Independent Evaluation Manager to provide impact baseline data and endline data and support learning and programme adaptation through formative theory based case study analysis.
Recommendations have been made to address critical issues for programme scale up in the coming year. These include addressing challenges of staff churn (with the M4D programme and of local government policy makers and service providers with whom the programme works, especially at the LGA and State team levels) and knowledge management. Recommendations are also made to capture better the benefits of the programme at the outcome level, Value for Money at output level, and to identify how M4D can work, and explore opportunities to increase its engagement, with DFID programmes operating at the State level, including SPARC and SAVI and DFIDs service delivery programmes (especially in education and health). Further recommendation is given to deepen understanding on the sustainability of approaches, interventions and supported organisations.
During the year, the programme has continued to deliver against output targets and has achieved a number of notable successes.
Key areas of progress include:
- M4D has supported Community Based Organisations (CBOs) to develop and implement their own advocacy plans, and through these plans, made a series of issue based demands to the appropriate Policy Makers/Service Providers (PMs/SPs) in their Local Government Authorities (LGAs), many of which have been well received and are now being acted upon.
- The nine existing Persons with Disability (PWD) CBOs have been re-assessed and capacity gaps have been identified and strengthened through training and mentoring on organising, engaging and influencing. An unintended positive outcome of the work with PWDs was the election of a PWD CBO member as the vice-chairman of the National Union of Local Government Employees (NULGE); it is expected that this appointment will further increase the capacity of PWD CBOs to influence Local Government.
- M4D’s reach with policy makers (PMs) and service providers (SPs) has included formal and informal PMs and SPs (e.g. Traditional Rulers) in target LGAs.
- M4D has continued to seek new and innovative ‘Better Fit Approaches’ to reform which might provide a “short-cut” to better service delivery (including introduction of the Participatory Community Service Management System (PCSMS)).
- Learning events have attracted more than the anticipated number of attendees (including print and electronic media partners). These learning events contribute to M4D’s broader advocacy strategy which includes advocacy initiatives to address priority issues identified with programme stakeholders. It is expected that as the programme continues, media interaction and other forms of communication are likely to increase which will help promote the value of new approaches to old problems and the potential for collective action.
- Grants are provided by M4D to assist with the resolution of local problems by local people based on local solutions. In the last quarter of 2014, the process for awarding issues-based, targeted grants was finalised, with twenty discretionary grants awarded to CBOs and Girls Platforms (GPs). Discretionary grants are those specifically earmarked for M4D partner CBOs, Life Skills Clubs (LSCs), GPs and PMs/SPs. In total, during the year 2014 (1 April to 31 December), 20 grants, with a total value of Naira 9,295,764 (GBP 37,183) were awarded to partner CBOs and GPs across the three states. Of this amount, Naira 2,624,800 or GBP 10,499 was disbursed as of 31 December 2014.
- A Value for Money framework has been developed with indicators representing costs at output level and the introduction of qualitative measurement tools for some VFM indicators.

Lessons learned across the programme include:
1. CBO capacity assessment: It is important to explain to communities the nature and purpose of tests such as the Community Dialogue and Action Scorecard (CDAS), to ensure that they score themselves objectively and realistically.
2. Life Skills Clubs (LSCs): Translating the core curriculum into the local language significantly helped the understanding of beneficiary girls and improved their learning outcomes; the issue of local language is equally important to communicate correctly across all beneficiaries and stakeholders.
3. Girl’s needs: A curriculum that focuses only on social empowerment without addressing economic empowerment does not sufficiently address the needs of girls; and sustaining their interests over a long period of time becomes a challenge.
4. Local ownership: PMs and SPs have proved they are willing to take note of and address the demands of the community, provided these are properly articulated and are synchronised with the budget cycle.
5. PM/SPs are not all the same: Grouping formal and informal PMs and SPs together in training sessions does not work very well, given the diverse understanding and expectations of this disparate group
6. Better Fit Approaches (BFAs): There is a need for the design and administration of BFAs to be as simple as possible for all stakeholders involved.
7. Grants: There is a need for simplification of the grant making process to ensure the accessibility of funds to the community. Government budget allocations from State to LGA levels cannot be assumed.
8. Communication: There is a need for M4D to strengthen its communication effectively across various media – not only radio, TV and print media, but also social media.
9. M&E: A strong M&E system is essential for a programme of this complexity.
10. Political economy analysis: This is essential in understanding of the drivers, opportunities, and barriers to reform of LGA (and State) governance systems; this needs to be reviewed (and updated) in line with changes in the political environment and key stakeholders.
11. LGA staff churn: Understanding and thinking through the implications of the churn or turnover of government officials at State and LGA level is essential in designing and implementing reform of government systems at these levels.

Summary of main recommendations for the next year
1. Identify potential reform allies at state level who are interested in improving LGA service delivery performance, in consultation with SPARC and SAVI, and including DFID service delivery programmes
2. Develop strategy for improving budget execution from state level to pilot LGAs
3. Develop more ‘thinking and acting politically’ and coalition based advocacy strategies with CBOs, building on SAVI’s approach
4. Develop advocacy and political skills of SPs/PMs to improve upwards accountability
5. Review staff resource needs to meet scale up targets in Year 3; consider with DFID whether a reduction in grants by M4D could provide needed staff resource.
6. Develop an anti-corruption strategy for the work M4D is doing, in particular with CBOs and PM/SPs, that supports DFID’s anti-corruption efforts
7. Continuous improvement of financial management to ensure proper accountability for all spend (including travel costs and DSA) by output and sub-output and improve use of timesheets to measure time at a sub-output level
8. Realignment of programme priorities where necessary to match the new government’s development agenda (and what this means at Federal, State, and LGA levels) post the elections, including building relationships with new interlocutors at National, State and LGA level post the elections
9. Continuous improvement of knowledge management systems, including considering intra- and inter-State visits for M4D programme staff and LGA and State government officials.
10. The programme should identify development partners (including the DFID funded State Accountability and Voice Initiative (SAVI) programme) and civil society organisations with higher capacity at the state level, and support them in working collaboratively with lower level CBOs on advocacy work and to support improvements in local level governance and service delivery.
11. Appropriate capacity building for in country staff.
12. Finalise and agree with DFID the approach to measuring beneficiary reach.
13. Develop a programme of operational research which will enable cross state learning within M4D and shape thinking by the programme on which interventions are most effective and sustainable.
14. Actively seek opportunities through the programme to address key issues particularly around conflict where these relate to community cohesion – and document where the programme already contributes to this.
15. Develop a more sophisticated cost allocation system to strengthen Value for Money measurements of efficiency, effectiveness and equity including across states.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202352/doc:3716803
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202352/doc:3719395

Outline of the programme
The UK government is providing £17.5 million for the Mobilising for Development programme over the six years from mid-June 2012. M4D supports local governance with the aim of improving service delivery in nine selected Local Government Areas (LGAs) in three states in Northern Nigeria: Kano, Kaduna and Jigawa.

M4D’s Business Case states that:

the programme will strengthen social accountability and tackle social exclusion. It will work with 650,000 people, among them at least 30,000 girls in 270 community groups in 9 Local Government Areas (LGAs) in Kano, Kaduna and Jigawa. As a result of this support, these people will make faster progress towards the MDGs. Citizens will be more able to plan and control their development. They will be more aware of the responsibilities of government to deliver services more effectively and local government will be more responsive. The 30,000 girls will have their awareness and self-confidence raised, go to school for longer and marry and have children later.

Specifically, the Business Case states that support will include:

- Building the capacity of communities to identify their problems and solve them.
- The project will support research and advocacy on the policy and regulatory environment and provide match-funded funded grants for development investments.
- Focusing on excluded and marginalised groups, in particular adolescent girls.
- Involving government staff at Local Government and State level to aid understanding and the adoption of the approach by others. Promoting the approach for adoption by other development partners.

Expected Results
In response to this business case, M4D was designed to achieve an improvement in the responsiveness and accountability of policy makers and service providers which would contribute to citizens access to, use of and satisfaction with basic services – through the delivery of the following outputs:

- CBOs better organized, engaged and demanding equitable service provision and development outcomes – by 2018, 54 CBOs, (representing 650,000 people[1]) will have become better organized engaged and will be demanding services.
  [1] Note that M4D and DFID are currently reconsidering how directly reached is defined and what this means in terms of the realism of these figures.
- PWD CBOs and Platforms of Girls better organized, engaging and demanding services and accountability – both from within the community but also acting directly with policy makers and service providers across all 45 wards and in nine LGAs – at least 30,000 girls (10,125 girls via LSCs and the rest from other CBOs) will be directly impacted.
- Increased capacity of policy makers and service providers to design and deliver basic services and operate accountably – 490 individuals will benefit, registering 75 demands and producing 27 action plans over the life of the programme.
- Better-fit approaches to basic service delivery and accountability on targeted issues identified, developed and tested - 12 innovative service delivery approaches and 4 accountability approaches will be tested; at least 7 successful better fit approaches will be documented
- Solutions, innovative and better fit approaches promoted and shared with targeted stakeholders – 800 people will take part in learning events, in addition to 11 advocacy initiatives and 60 media coverage.

M4D believes that these outputs will be sufficient to lead to the outcome: “Policy Makers and Service Providers are more responsive and accountable to citizens’ better articulated demands and entitlements, especially adolescent girls and people with disability”.

Context
Northern Nigeria has some of the worst human development indicators in the world and they are particularly bad for girls and women.

In addition:

- Service provision is weak, particularly the basic services associated with education, health and water and sanitation.
- Accountability is weak and often upwards and government’s response to citizens’ demands is selective.
- The policy environment is not conducive to agricultural and business development, limiting livelihood options and growth.

Nigeria is an oil-rich and growing economy but has not translated its wealth into effective and accountable services that will lead to improved living standards. On current form, Nigeria is unlikely to meet the MDGs. The north has high levels of poverty and social exclusion. Women and girls are further disadvantaged by gender politics and gender-biased interpretations of religion.

Government underperformance is caused by political and bureaucratic patronage nourished by oil revenues, low expectations of government on the part of citizens and patterns of political allegiance and support determined by geography, ethnic identity, vested interests and personal connections. Together these have prevented the emergence of a broad-based political coalition of interests at a national level that could press for a change in government performance. In addition, control of local government resources by states through the Joint Account, and failure to make progress on LGA autonomy have stifled service delivery at the local level. Thus public sector reform is required at all levels of government.

M4D believes in supporting collective action across a range of groups, not only government bodies, in order to facilitate change. However, government clearly has a role to play and for government performance to improve, the political culture must change. Policy makers and service providers (including the state) need to be more accountable and responsive and citizens more aware of their responsibilities to them, and more demanding of their rights. However, this does not imply that development support must adopt an ‘us and them’ supply/demand perspective. With regard to government PM and SPs, for example, M4D believes that where communities and local government meet it is possible to reshape the relationship between the Nigerian state and its citizens whilst ensuring the delivery of services that matter to citizens are directly improved.

Since the programme commenced, substantial efforts have been made to strengthen relationships within the three Northern focus states of Kano, Kaduna and Jigawa – especially within the nine targeted LGAs. For example, there is now a greater level of consultation among targeted communities, and between beneficiaries and policy makers and service providers. Similarly, the level of responsiveness by policy makers and service providers to well thought through and articulated citizens’ demands have increased. The programme has learned that consultation translates best into development outcomes when articulated demands are made in a way and at a time which means that they can be included in the LGA budgetary exercise.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
M4D has laid strong foundations in 2014 to enable it to achieve the desired programme outcomes. This achievement has come through a highly positive response from citizens and CBOs to a participatory, community driven approach for formulating and articulating specific demands to policy makers and service providers. The enthusiasm and responsiveness of government officials in being better connected to people and finding opportunities to engage, being more responsive to, and opening up meaningful avenues for constructive service delivery has been equally strong. M4D has managed to establish and maintain over a hundred life-skills clubs for girls in a variety of settings, despite a high levels of cultural suspicion and scepticism and a larger backdrop of insecurity often targeted at women and girls. People, policy makers and a wide range of stakeholders have shown an extremely encouraging level of interest helping to achieve traction for new ideas and to develop real, concrete, tangible and innovative ways of working together to deliver new or better services.

A big learning point for the programme has been the increased acceptance by PMs and SPs to address community needs if demands are well thought through and well-articulated. They do not see it as a burden or requiring them to discharge additional responsibility. Rather, they welcome the opportunity to engage with the community. The more responsive among them also value the feedback that community engagement provides on the provision of various services. Earlier, a certain level of antagonism prevailed between PMs/SPs and the community. In the M4D programme areas however, there is a greater sense of partnership and recognition of the need to work together.

Better-fit approaches have disrupted the status quo in a very constructive way. Innovations such as the use of PCSMS have demonstrated the potential to dramatically increase turnaround time in terms of response by service providers to issues raised by communities. The use of Jolly Phonics is beginning to improve learning outcomes in the rural schools where it has been launched. For example, in Dawakin Tofa LGA in Kano State, children who earlier had difficulty in pronouncing words are now able to do so, thanks to Jolly Phonics. Apart from primary education, Jolly Phonics is also being used in the Second Chance Education initiative to teach girls (including those who have dropped out but who wish to continue their education). In those areas of Sumaila LGA in Kano State, where the Drugs Revolving Fund (DRF) is being piloted, reliability of supply has improved and there has been increased access by communities and by poor people to affordable and reliable drugs which in turn has saved them the cost and time associated with travel and has improved health outcomes.

At the end of year two, it is still too early to say with confidence that the M4D outcome will be fully achieved in terms of targets, but the approach and achievements show considerable promise and, if the programme can scale up effectively from the initial successes, then the prospects are good. There are concerns from external factors, such as political instability and deteriorating security, which are already constraining project activity and will only get worse. The current disconnect between the articulation of demands and the local government budgetary process (and reduced budgetary allocations) means that while demands may be accepted, they risk not being implemented. Further, the frequent rotation of policy makers and service providers undermines the significant capacity building efforts being invested through this programme. That said, the capacities and the processes that the programme is introducing to and between stakeholders will last and offer the potential for change over the longer term. There are clear challenges in scaling up the programme without losing a focus on delivering quality.

Current achievements against outcome indicators are as follows:

Outcome Indicator 1: (No. of CBOs and platforms including those of Girls and PWDs, in M4D LGAs who state that they have more influence on policy makers and service providers): M4D has commissioned a Perception Survey to establish a baseline for this indicator. An early sense obtained from the draft survey appears to suggest that while there is a high degree of recognition of the programme, the capacity of CBOs needs to be significantly strengthened before they fully understand how policy makers and service providers work, and how they can engage more effectively with them in order to further the interests of the communities they represent.

Outcome Indicator 2: (No. of targeted service provider and policy making organisations progressing along a responsiveness and accountability scale): The Accountability and Responsiveness Capacity Scale (ARCS) assessment tool has been significantly revised and applied to PMs/SPs organisations; and the baseline has been established at the outcome level. The organisational capacity gaps identified informed the broad nature of training under Output 3 (while individual pre-tests established the output baselines). Progress against the outcome baseline is being monitored annually, and tracked through focused group discussions and key informant interviews. The second round of ARCS assessment on PMs’/SPs’ organisations is now expected to be completed in early 2015 and will inform M4D of the number of organisations that have progressed along the responsiveness and accountability scale.

Outcome Indicator 3: (No. of citizens' articulated demands that are incorporated into plans or delivery of basic services and accountability): Project documents are already recording achievements against this indicator with at least 15 demands that have tangible actions being proposed as responses from policy makers. For example, these include promises around the setting up of Life Skills Clubs, the provision of Second Chance Education, and the provision of support to Ante-Natal Care through the installation of sheds.

Overall output score and description
Overall output score: A+

The details of achievements against milestones are captured individually under each Output in the sections below.

Key lessons

1. Delay in production of costed workplans delays programme implementation
2. Several interactions with Life Skills Clubs, Girls Platforms and Peer Champions shows that learning the lessons contained in the core compendium (including appreciative inquiry, leadership, financial management, and conflict management) is in itself insufficient to boost/retain membership in the absence of economic empowerment components.
3. Impact and accessibility can be further enhanced by translating the core compendium into the local language.

The assumptions in the logframe have not changed since design. However, the various changes made to the logframe since inception, reflect programmatic responses to changing operating realities. Opportunities for lesson sharing and reflection include information dissemination within the team through periodic lesson learning events, with DFID through quarterly reports and at reviews, and externally through periodic engagement with partners, or through appropriate media dissemination.

Has the logframe been updated since the last review?
Yes, the M4D Logframe has been changed since the last Annual Review.  The detail of these changes are tracked and presented in a LF Version Control Report available from the Programme Team.
The main changes are:

Change in the reporting year. Amendments to milestones and targets have been made in line with a shift of reporting year from April-March to January-December.  This change (requested by DFID) means that this year, M4D is reporting against only three quarters (April-December 2014).

Inclusion of the IEM. At DFID request, GRM has taken on the management of the IEM (to be delivered by Itad).  Consequently, an additional output has been added to the LF: Improvement in programme management and delivery built upon an independent and credible evidence based approach to accountability and learning.

Outcome clarity: M4D has changed the wording for indictor one in order to be clear of our meaning.  Outcome indicator one now states “…including those of Girls and PWDs…” rather than “…with specific reference to Girls and PWDs…” to ensure that it is clear that M4D works with all CBOs and not just those representing Girls and PWDs.

Output one changes: M4D has replaced the word communities with CBOs in output 1, since the programme is working with CBOs as representatives of the community rather than the community directly and it is CBO progress that the programme is measuring.

Output two changes: Output indicator 2.1 has been amended to state more clearly that LSCs will facilitate the emergence of Peer Champions and Girls’ Platforms.

Output three changes: Wording has been tightened to better capture the change which M4D expects to see - i.e. that the focus of PM/SP capacity building is in relation to their responsiveness to community demands.

Output four changes: Target numbers have been reduced to encourage emphasis on quality rather than quantity.

Output five changes: Numbers have been increased in line with year one experience and in order to reflect a more appropriate level of ambition.

Impact weightings: These have been adjusted based on learning - output 1 and 3 increased from 15% to 20% to reflect the perceived importance of helping the development of a critical mass of organisations and individuals capable of sustaining engagement on community demands; output 4 reduced from 30% to 15% to reflect the recognition that the programme’s capacity building efforts will have a more significant contribution to impact than had been originally suggested.

Risk ratings: the risk associated with output 3 has been increased form medium to high to reflect the fact that there are significant vested interests in maintaining the status quo; the risk rating for output 4 has been increased from low to medium since investment in new approaches inevitably involves risk; output 5 risk has been reduced  from medium to low since the level of interest in learning events from all categories of stakeholders has been stronger than anticipated and the programme is over-achieving on this target.

The programme logframe will require further modification in line with recommendations from this review. The theory of change (and key assumptions underpinning this) should be reviewed thoroughly during the next annual review process.

Recommendations:
Over the coming year, the programme will track the progress of these promises and will measure (in monetary terms if possible), the value and reach of the benefits.

The total number of beneficiaries that this programme will impact needs to be revisited, a Reach Paper is being finalised. The programme should develop an outcome level measure of beneficiary reach to show the number of people in the wider communities who are benefiting from additional voice as a results of M4D programme activities.

The perception survey meant to inform the baseline at the outcome level needs to be completed.

Both the knowledge management and the M&E system need to be further streamlined and strengthened.

C: DETAILED OUTPUT SCORING

Output Title	Output 1: CBOs organised, engaged and aiding community demands for equitable delivery of basic services and accountability
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
1.1 No. of CBOs progressing with regards to organising	Cumulative: 27	27 (Achieved) - Kano: 9; Kaduna: 9, Jigawa: 9
1.2 No. of CBOs progressing with regards to engaging	Cumulative: 18.	20 (Exceeded) – Kano: 6; Kaduna: 8; Jigawa: 6
1.3 No. of quality citizens’ demands made to service providers and policy makers by CBOs in M4D LGAs	Cumulative: 30.	32 (Exceeded) – Kano: 12; Kaduna: 12; Jigawa: 8

Key Points
The targets have been substantively and qualitatively met, and exceeded in terms of number. The partnership approach with CBOs continues to gain significant traction. Participatory processes which involve CBOs work well. This is because the communities now feel involved in the process and own their relationship with the partner CBO who has not been superimposed on them by the programme. M4D has also realised the differences in capacity between CBOs and this has enabled the programme to tailor their interventions to address varied needs.

M4D is achieving all targets in this area as well as responding to new opportunities as they arise. Key achievements for this quarter were:

- Indicator 1.1	All CBOs were reassessed using the CDAS tool twice and the results were analysed. Based on this analysis, 27 CBOs were found to be progressing on organising. This progression was brought about by capacity building for the CBOs and substantial investment in mentoring on organising. All CBOs developed action plans on inclusion and equity during the training and these have been implemented. Community stakeholders have been sensitised to familiarise them with the newly selected intervention wards.
- Indicator 1.2	20 CBOs were found to be progressing on engaging. This progression was brought about by capacity building for the CBOs and substantial investment in mentoring on engaging with the PMs/SPs. The CBOs have been supported to formulate and present new issue based demands to the PMs/SPs.
- Cross cutting across indicators 1.1 and 1.2: Conducted capacity building on organising, influencing and engaging for 18 old and 9 new CBOs based on the gaps identified in the CDAS surveys.
- Indicator 1.3	32 quality citizens’ demands were articulated, documented and presented to PMs and SPs by CBOs in M4D LGAs. This was as a result of the necessary support provided to the CBOs by the programme to formulate and present new issue-based demands and develop strategies for continued follow up of existing demands. For example in Kano State, the LGA level CBOs are collaborating with SAVI to organise interface meetings with aspirant candidates during the upcoming elections and are presenting their demands to them.

Summary of responses to issues raised in previous annual reviews
- The previous annual review had suggested that DFID’s suggested approach to measuring population reach be reviewed. A Reach Paper on population targets is being developed
- M4D has responded to the recommendation on the use of scales and criteria for judgements on indicators by building the capacity of programme staff on its application during assessment and analysis of the result through the use of the CDAS tools.
- M4D facilitated the triangulation of self-assessments as follows: during assessments, the CDAS tool is explained to respondents before scoring. Following scoring and analysis of the data, the programme utilises focus group discussions and key informant interviews among respondents to triangulate and validate the pre-scoring assessment. Subsequently, amendments as appropriate are made.

Recommendations for Output 1
More triangulation should be done through Key Informant Interviews (KIIs) and Focus Group Discussions (FGDs) as indicated in the logframe to establish the progression of CBOs in terms of organising, engaging and influencing and M4D’s value addition not just through the administration of CDAS.

Strengthen the mechanisms for measuring CBO engagement with communities to enhance M4D’s ability to measure reach.

The programme administered CDAS twice within the first year in order to demonstrate progress within year in line with programme targets. However, the programme should now change the frequency of administering the CDAS from six monthly to yearly. This will be less transaction intensive yet continue to provide sufficient data for monitoring of progress.

Strengthen coalitions between CBOs for cross-learning and collaboration.

Improve monitoring of direct engagement between CBOs and PM/SPs to better understand how and where collaboration for collective action occurs.

Consolidate programme thinking on "Approach"  to include more ‘thinking and acting politically’ methodologies with an issues focus and incorporating coalition based advocacy strategies with CBOs, building on and extending the reach of the SAVI approach.

Strengthen monitoring and reporting of independent action of CBOs and GPs to demonstrate sustainability of M4D’s effect (Output 1 and 2).

Test that CBOs are representative of the interests of all marginalised groups within the communities they work and consider putting in place grievance redressal mechanisms for groups whose interests are not identified and considered.

The selection process for LGA, ward and marginalised groups levels need to be based on clear technical criteria and these communicated to all stakeholders.

Output Title	Output 2: PWD and Platforms of Girls organised, engaged and demanding equitable basic services and accountability
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 No. of LSCs of Girls formed and supported, to the emergence of Peer Champions and Girls Platforms	Cumulative (LSCs): 108 / Cumulative (Peer Champions): 108 / Cumulative: (Girls Platforms): 6	108 LSCs (Achieved) – Kano: 36; Kaduna: 36; Jigawa: 36 / 108 Peer Champions (Achieved) - Kano: 36; Kaduna: 36; Jigawa: 36 / 7 Girls Platforms (Exceeded) – Kano: 3; Kaduna: 3, Jigawa: 1
2.2 No. of PWD CBOs and Girls Platforms progressing with regards to organising	Cumulative: 15 (6 Girls Platforms, 9 PWDs).	15 (7 GP; 8 PWD) (Achieved) – Kano: 6 (3 GP; 3 PWD); Kaduna: 6 (3 GP; 3 PWD); Jigawa: 3 (1 GP; 2 PWD)
2.3 No. of PWD CBOs and Girls Platforms progressing with regards to engaging	Cumulative: 10 (3 Girls Platforms, 7 PWDs).	14 (7 GP; 7 PWD) (Exceeded) – Kano: 5 (3GP; 2 PWD); Kaduna 6 (3 GP; 3 PWD); Jigawa 3 (1 GP; 2 PWD)
2.4 No. of quality demands made by PWD CBOs and Girls Platforms, to service providers and policy makers in M4D LGAs.	Cumulative: 18.	21 (Exceeded) – Kano: 10; Kaduna: 6; Jigawa: 5

Key Points
M4D has shown sensitivity to local customs and traditions by downplaying the use of the term ‘adolescent girls’ in response to community members’ concern about using the word to refer to their daughters. It has prevented alienation of the community and their traditional leaders; and fostered buy in by the community who are now keen to see their daughters joining the Life Skills Clubs (or Fora as they are called in Kano). Involvement and ownership of the community at large including the parents and traditional leaders have enabled girls in the community to effectively participate in the life skills clubs and gained confidence to articulate and demand their requirements – something that they normally would not have done without programme support. The confidence of programme beneficiaries’ proved so popular that it has stimulated enrolment (and attendance) in the Life Skills Clubs, as girls see what their ‘empowered sisters’ are able to achieve. Further, it has also encouraged leadership, as young women have come forward to be Peer Champions and Mentors to their sisters.

As for Persons with Disabilities, they are now being increasingly accepted in the programme areas as equal members of the community, with the same rights as others; This has fostered an awareness and increasing responsibility among PMs and SPs but also the community itself to respond to the specific needs of PWDs. For example, in Miga LGA in Jigawa State, the community on their own have put in place ramps to enable access by PWDs to engage with them and also access services.

The targets have been exceeded:

- Indicator 2.1	An additional 54 new LSCs have been formed in year 2, bringing the total to 108. The navigation of these additional 54 LSCs through the LSC core compendium with mentoring support has commenced. The 54 LSCs formed in year 1 have completed their navigation through the Life Skills Clubs core compendium resource modules. The LiSCAS progress report (the tool used to measure capacity of girls against the contents of the LSC core compendium) indicates an improvement in capacity across capacity areas for most girls. LSC members are networking with girl platforms in conducting town hall meetings to identify, understand and prioritise the needs of girls in the wider community using participatory needs analysis tools as well as knowledge acquired on their rights through the civic education resource module. Girls from LSCs will continue to interface with girl platform members in order to facilitate the “voice” of girls within local governance processes. From these 108 LSCs, a total of 108 Peer Champions have emerged.
- Indicator 2.2	The 8 PWD CBOs and 7 LGA level Girls Platforms have been assessed using the CDAS and CDAS+ assessment tool respectively and found to be progressing on organising. Girl platforms now have an improved leadership structure with improvements also seen in their capacity to facilitate and capture reports of their periodic meetings. Action planning tied to pushing for priorities of girls in the wider community has also improved. Nine LGA level PWD CBOs received training and mentoring to shift their trajectory towards the social model of disability. A key output of this training was the development of clear action plans by PWD CBOs in collaboration with non PWD CBOs and Local Government officials from the Community Department geared towards supporting PWDs (bearing in mind gender needs) to access their rights. PWD CBO leaders have also improved in confidence to take on their roles, this was seen for instance when local government officials developed action plans to drive the “equity agenda” in the delivery of basic services.
- Indicator 2.3	The assessment of the PWD CBOs and Girls platforms shows 7 PWD CBOs and 7 Girls Platforms have improved their capacity to engage with PMs and SPs (both formal and informal). Agreements on how these actors will support Girl Platforms were reached. Agreed support to Girls Platforms includes:
  - Mobilising girls in the wider community for Girl Platform town hall meetings.
  - Providing logistics to Girls Platforms’ members to hold their monthly meetings
  - Providing safe venues for Girls to meet
  - Channelling their demands to Local Government officials.
- Indicator 2.4 Girls Platforms and PWD CBOs made 21 quality demands targeting policy makers and service providers, some of which have been responded to. For example: the provision of basic literacy and numeracy skills for girls in the community, response by Local Government officials and communities included the construction of classes, provision of teachers and resource materials for girls to acquire skills in Kudan; in Dawakin Tofa LGA, teachers and resource materials have been provided to girls to receive evening classes using the classrooms within the community’s primary school. An unintended outcome regarding support to PWD CBOs is the election of a PWD CBO member to serve as the vice president of the National Union of Local Government Employees (NULGE) in Kaduna State; it is expected that this will further facilitate PWD CBOs’ capacity to influence policy makers and service providers; details on their improved capacity can be seen from the CDAS Narrative Report

Summary of responses to issues raised in previous annual reviews
All logframe targets (including for indicator 2.3) have been reviewed. Where necessary, amendments have been made.
M4D also facilitate the triangulation of self-assessments. During assessments, the LISCAS and CDAS+ tools are explained to respondents before scoring. Following scoring and analysis of the data, the programme utilises focus group discussions and key informant interviews among respondents to triangulate and validate the pre-scoring assessment. Subsequently, amendments as appropriate are made. A case study to understand to what extent girls are empowered will be carried out in Year 3 (2015) to allow for a year’s timeframe of implementation of the Girls Platform work.
- The various pathways through which marginalised groups are able to access service providers and policy makers have been mapped, and understood by programme staff.
- The programme is sensibly cautious with regard to the inclusion of Girls Clubs and Platforms within the innovation trajectory, given the conservative environment prevalent in the Northern states in which it operates, and the religious and cultural sensitivities involved regarding the role of women and girls in society.
- As regards attrition in the LSC, and its possible impacts on inclusion targets and the number of AG benefitting from LSCs, M4D is in the process of developing a database, whose analysis will inform their understanding of attrition trends. Early indicators suggest that attrition rates are low.

Recommendations for Output 2
As with CDAS and output 1, the programme should now reduce the frequency of administering the CDAS, CDAS+ and LiSCAS from six monthly to yearly. This will be less transaction intensive.

Seek to understand issues around conflict management and negotiation modules as indicated by LiSCAS results that LSC members performed least well around the contents of these modules.

More work needs to be done in terms of creating an enabling environment for girl platforms to thrive; deepening the discourse on equity including the practical and strategic gender needs of girls targeting CBOs as well as PMs and SPs.

In order to increase women’s participation within CBOs, the women’s wing of CBOs need to receive separate trainings from those being provided to male CBO members under Output 1 within communities. Trainings should be carried out by experienced female consultants and should be suited for non-literate people. Strengthening the networks between girl platforms and CBOs needs to be ensured.

PWD CBOs need to be supported to have representatives sitting on Local Government Committees (such as the fertilizer distribution committee or the education committee) in order to further increase their capacity to reflect demands within local government plans and processes as well as have a formal oversight function on the delivery of services.

Strengthen monitoring and reporting of independent action of PWD CBOs and GPs to demonstrate sustainability of M4D’s effect.

Develop and test exit and sustainability strategies for life skills clubs and Girls Platforms.

Preparation and roll-over of the M4D/Ministry of Empowerment collaboration on Girls empowerment activities; possible challenges with coordination raising questions as to budgetary issues and the ability to sustain process.

Explore possible incentives to Girls graduated from the LSC Programme through provision of seed resources or linkage to other appropriate possible programmes/initiatives where they could get such support to enable them engage in some economic empowerment activities after graduation.

Output Title	Output 3: Increased capacity of policy makers and service providers to design and deliver basic services and operate accountably.
Output number per LF		3	Output Score	A++
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 No. of targeted individuals (from service provider and policy making bodies) whose capacity has increased (to design and implement appropriate and responsive approaches to service delivery) in relation to demands of communities and marginalised groups	Cumulative: 260	382 (Exceeded) – Kaduna: 113; Jigawa: 139; Kano: 130
3.2 No. of targeted service provision and policy making bodies, who revise or develop action plans on standard based service provision or regulation with communities and marginalised groups	Cumulative: 9	14 (Exceeded) – Kaduna: 4; Jigawa: 4; Kano: 6
3.3 No. of citizens’ quality demands that are logged and initial action identified by targeted service provider and policy makers	Cumulative: 29	35 (Exceeded) – Kaduna: 12; Jigawa: 8; Kano: 15

Key Points
The targets have been exceeded.

Based on lessons learned the programme now needs to focus on specific tailor made training to further enhance the capacity of PMs and SPs. Possible areas for further training could include: citizens’ involvement in decision making processes; involvement of women, adolescent girls and persons with disabilities in decision making on policy issues and matters that affect them; and, increased sharing of information with citizens on projects being implemented through periodic town hall meetings. In addition to implementation, there is also the need to build the capacity of PMs/SPs on project monitoring and evaluation.

- Indicator 3.1	The capacity of 382 targeted individuals from Service Provider and Policy Making bodies was increased to design and implement appropriate and responsive approaches to service delivery in relation to demands of communities and marginalised groups. Targeted capacity building was conducted in the area of Participatory Planning for service delivery and accountability, as well as standard based service delivery and monitoring standards based on gaps identified by the ARCS assessments; these capacity needs are being measured using standardised pre and post test instruments, which show increased capacity of policy makers and service providers to design standard based service provision using action plans developed during the training across the 3 states. Identified and engaged formal and informal PMs/SPs in the newly selected wards. These PMs/SPs were also trained as part of capacity building since they are custodians of tradition and culture and are influential to behaviour change, especially as regards girls and PWDs accessing services. This has resulted in support for example in Igabi, where the Traditional Leader contributed N 50,000 for an Ante-Natal Care shed.
- Indicator 3.2	14 Service Provision and Policy Making bodies were provided with the necessary support through mentoring to develop and implement action plans on standard based service provision /regulation with communities and marginalised groups. For example, PMs/SPs in Kaduna have already started applying for M4D grants in order to support the implementation of action plans developed during the capacity building.
- Indicator 3.3	35 citizens’ quality demands have been logged and initial action identified by Service Providers and Policy Makers on the demands. Continued monitoring of initial actions by PMs/SPs on demands logged by citizens. For example, in Sumaila LGA, CBOs made demands that have been incorporated into the budget and responded to. This was in follow up to interface meetings conducted by PMs and SPs (for example in Garun Mallam). Following this, on-going mentoring is being carried out by state teams for individual PMs/SPs on enhancing their responsiveness to citizens’ demands and ensuring their improved accountability.

Summary of responses to issues raised in previous annual reviews
- Output 3 indicators have been revised
- As part of their approach the programme has agreed with informal leaders what is expected of them and how they are expected to relate to both communities and formal authorities, however, this is not explicitly stated in the logframe.

Recommendations for Output 3
1. The programme should look at ways of improving and deepening its work with PMs and SPs in the face of contextual challenges in this area of work. This can include:

- Develop strategy for improving sector strategies, budget formulation and execution state level to pilot LGAs; focus on participation and transparency.
- Develop advocacy and political skills of SPs/PMs to improve upwards influencing.
- Increase the understanding of Policy Makers/Service Providers on Participatory Planning and effective management skills to improve feedback mechanism.

In doing this it is critical that the programme understands the issue of churn in PMs and SPs and takes this into account when reviewing programme targets.

2. Similarly, the programme should begin to encourage PMs/SPs (both formal and informal) to cascade to their officers the training they acquire directly from the programme. This will create a multiplier effect and expand the reach of the programme.

3. Identify potential reform allies at state level who are interested in better LGA service delivery performance, in consultation with SPARC and SAVI and other DFID service delivery programmes where appropriate; work closely in one or two sectors or with regard to one or two specific issues to demonstrate potential of enhanced State-LGA collaboration. In this the programme should explore learn lessons from the DFID funded Voices.

4. Support continuous relationship between PMs/SPs and CBOs with focus on adherence to improving service delivery and promotion of access to basic services.

5. In response to LGA staff churn the programme should seek to understand how the movement of trained PMs and SPs out of M4D areas is likely to affect programme performance and goals. The programme should seek to monitor the levels of movement and the effects of lost capacity within the LGA, as well as potential gains in other areas. M4D should seek to answer and respond to the question of whether this staff churn is providing a platform for replication or a dilution of programme effect.

6. M4D should develop a better articulation of the ability of local government to deliver services and where the key barriers are to that which might be addressed.

Output Title	Output 4: Better Fit Approaches to basic service delivery and accountability on targeted issues identified, developed and tested.
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
4.1 No. of basic service delivery BFAs initiated and tested	Cumulative: 6	7 (Exceeded) – Kano:2; Kaduna: 4; Jigawa: 1
4.2 No. of accountability BFAs initiated and tested.	Cumulative: 2	3 (Exceeded) – Kano: 2; Kaduna: 1;
4.3 No. of successful Better Fit Approaches (BFAs)	Cumulative: 2	2 (Achieved) – Kano: 1; Kaduna: 1

Key Points
The targets have been exceeded.

The programme has achieved some quick wins through the promotion of what M4D calls ‘better-fit approaches (BFAs)’. These approaches are selected because they meet a range of criteria which include a fit with the local context, local ownership and the potential to generate development benefits. They enable responsiveness. For example, the PCSMS motivates not only the community but also the PMs and SPs to respond to demands to the fullest extent possible. There has already been the opportunity for some replicability in this particular instance: PCSMS was originally started in Kaduna as accountability BFA in the Education sector; it is now being used in the Health sector (Kano) and in Water and Sanitation (Jigawa). Also promisingly, the Mobile Emergency Transport Scheme using motorised tricycles, which originally started in Kaduna, is producing indications of scalability as PMs/SPs have doubled the capacity of this service.

The better fit approach shows considerable potential and initial success. However, it is currently not clear whether the initial successes are due to picking quick wins or whether they form the basis sustainable series of successes. It is also hard to understand at this stage how successfully M4D can remove themselves from the better fit approach process and whether it will be possible to train CBOs to pursue the approach independently and to find receptive policy makers.

Indicator 4.1	Seven basic service delivery BFAs have been initiated and tested: in Kaduna, on Agriculture Leasing, on Adolescent Education, a Local Emergency Transport Scheme, and Model Toilets; in Kano on Improved Sustainable Drug Supply System, and Jolly Phonics; in Jigawa on: Water and Sanitation.

Indicator 4.2	Three Accountability BFAs were initiated and tested: Participatory Community Service Management System (PCSMS) In Kaduna, Kano and Jigawa - the PCSMS application allows for reporting and feedback on local service delivery using mobile technology; Integrated Local Government Planning in Kaduna.

Indicator 4.3	With a view to strengthening the BFAs and Innovative initiatives, M4D commissioned a consultant to:
1. Revise (as necessary) BFA selection criteria, testing process guidelines and success criteria
2. Produce a report which documents the following:
- the current status of M4D BFAs with regard to processes and criteria;
- recommendations for improvement where appropriate;
- theory based learning questions and lessons learned from existing BFAs;
- recommendations for developing key advocacy strategies for successful BFAs.
Two BFAs whose piloting and testing has been successfully completed have been considered by the communities and the programme as successful.

Summary of responses to issues raised in previous annual reviews
- The BFA innovations have come a long way since last year, and significant progress is being made to address the various definitional issues in relation to innovation and BFA.
- The ‘weightage’ issue has been addressed. The weighting has now been brought down from 30% last year to 15% this year.

Recommendations for Output 4
The programme should consider how capacity building given to PMs/SPs under output 3 could help PMs/SPs to identify good BFAs.

Quarterly meetings should be held with selected PMs/SPs at LGAs ‘to identify common bottlenecks to service delivery and accountability’ that could be transformed into BFA ideas for possible solutions.

Advocate to PMs and SPs on successful BFAs that have potential for replication and scalability.

A thorough review should be carried out in order to clearly spell out the processes involved in each BFA especially in regard to the duration for piloting and testing.

Community members should be encouraged to think on some local solutions that can be tested using M4D grants as BFAs.

State teams should be supported to identify appropriate BFAs within their states for implementation.

M4D should make an assessment of the BFA approach in order to better understand the potential for BFAs and being to think about how BFA would function outside the influence of M4D.

Output Title	Output 5: Solutions, innovative and better fit approaches promoted and shared to targeted stakeholders.
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 No. of people from within and outside M4D LGAs that take part in dissemination or learning events	Cumulative: 240.	330 (Exceeded) - Kano: 142; Kaduna: 38; Jigawa: 150
5.2 No. of solutions, innovations and BFAs that are subject of advocacy initiatives.	Cumulative: 5.	5 (Achieved) – Kano: 2; Kaduna: 2; Jigawa: 1
5.3 No. of quality media coverage on solutions, innovations and BFAs in M4D	Cumulative: 25	25[2] (Achieved) – Kano:13; Kaduna: 4; Jigawa: 3
[2] This includes the preparation of five media coverage pieces on advocacy initiatives which are ready to be disseminated.

Key Points
This output is still in its early stages. However, the first two years of the programme have generated a valuable set of results which M4D will now be able to disseminate. M4D recognises the need to increase their engagement across media – not only print, TV and radio, but also social media. The programme is also in a strong position to develop advocacy strategies, record success stories and share many of the lessons of why certain aspects of the programme have worked so well, and others less so. Over the next year, the dissemination of these ideas will be vital to efforts to promote scale up and replication of the gains made in terms of demands articulated and met and the better fit approaches successfully implemented.

Key achievements include:

- Indicator 5.1	330 people from within and outside M4D LGAs participated in dissemination /learning events of the programme. The programme has convened learning events on the approach to working with girls with key stakeholders based on current findings framed by the programme’s theory of change and knowledge management approaches
- Indicator 5.2	5 solutions/ innovations and BFAs as the subject of advocacy initiatives have been identified. These include: i) Participatory Community Service Management System, ii) Life Skills Club, iii) Jolly Phonics, iv) Second Chance Education, and v) Drug Revolving Fund. In addition, advocacy action plans have been developed with all 27 CBOs with activities geared around organising, engaging and articulating demands. For example, in Kudan (Kaduna State) the girls platform through their CBOs demanded that the adult literacy class be allocated to them. This was responded to and additional teachers posted to the school to support second chance education for these girls. CBOs are currently implementing the action plans with mentoring support from M4D.
- Indicator 5.3	25 quality media coverage on solutions/innovations and better fit approaches have been completed. An improvement in the web and social media presence has been recorded: while the M4D Facebook page now has a total of 1,154 likes, the YouTube page has 241 views and 7 subscribers. The latest animation video uploaded in Hausa has 56 views. Videos have been prepared in the local language and are ready for uploading. 27 media practitioners (18 male and 9 female journalists and producers) from some of the media partners in Kano, Kaduna and Jigawa have had their capacities built on improved governance reporting. This training is supporting the immersion process of journalists and producers to deepen their understanding of the programme and the work strands; they have also.

Summary of responses to issues raised in previous annual reviews
- The programme is addressing the difference between using the media to raise awareness of on-going project initiatives, and promoting scalable models. A first step has been taken by holding media immersion activities which have sensitised journalists about the programme and on-going initiatives. Secondly, a number of learning events have also been held, which have seen a significant increase in participation by beneficiaries. Once the innovations described under Output 4 have been completely and successfully tested, further plans (for e.g. advocacy initiatives) include promoting these innovations to PMs/SPs to achieve scalability and replicability.
- Further discussions are on-going to obtain clarity on the distinction between what constitutes a scalable model, and what constitutes innovative approaches.

Recommendations for Ouput 5
1. Develop the programme’s case study approach introducing case study recording at the start of the change process for recording throughout the programme period.
2. Provide necessary support to CBOs to implement the five Advocacy initiatives developed.
3. M4D should seek to better understand the value and effectiveness of media approaches used. For example, whether YouTube views represent a count of effective dissemination.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

During this year, M4D has improved its approach to Value for Money. In response to recommendations made in the last Annual Review, improvements have been made to M4D’s FMIS in order to improve the fidelity of recording and reporting on spending. This has been accompanied by a much improved VFM framework which was based on the recommendation made in a report commissioned by the project at the start of the year and refined by the team throughout the reporting year. M4D have now completed the review of our reporting framework in time for this annual report and are able to present the results in reports for this year. Further work is needed to develop more accurate measurement of effectiveness at the output level and to be able to capture the developmental impacts/benefits of the services/projects (disaggregated as far as possible by at least sex and age) and the sustainability of these changes.

Key cost drivers and performance
M4D makes great efforts to monitor costs and ensure that they are kept to a minimum. The biggest cost driver for this programme this year was fees (75%). Through careful use of Short Term and International consultants as well as negotiation and benchmarking for rates M4D were able to ensure that this cost is kept under control. The average fee rate across the entire programme has steadily declined from £236 per day at the start of implementation to £183.

The second largest cost is DSA. This is a necessity due to the amount of travel and long travel times within the three states required by the programme, in particular from the cross-cutters and senior staff as well as the CDOOs. M4D continues to monitor unit costs for DSA and have steadily brought down the unit costs which now stand at £22 per day as well down making efforts to minimise the total number of days spent whist ensuing the proper implementation of the programme activities.

VFM performance compared to the original VFM proposition in the business case
Overall M4D continues to represent good value for money with an unchanged estimate of target beneficiary population and an unchanged cost since the last annual review. As such, the estimated return on investment is also unchanged.

VFM at the outcome level:
M4D is not yet able, at this stage of the programme to begin to report with any kind of accuracy on a cost-per-outcome indicator basis. However, the FMIS is being strengthened and this in conjunction with the baseline measures against indicators which are being developed will mean that going forward the programme will be able to begin reporting against outcome indicators. As a result, these results will be reported within the next annual report in line with the plans in the original VFM strategy. M4D has also appointed an Independent Evaluation Manager who is (at the time of reporting) conducting baseline surveys with the expectation that this will provide additional information for outcome level reporting and triggers for concern should the programme look like it will fail to deliver in the long term.

VFM at the output level:
The programme’s revised VFM framework details a series of indicators that are a useful way of beginning to assess the overall performance of each output. With the exception of Output 4 M4D which will rely on case-studies. Because of the changes to the measurement systems for spending by output, it is impossible to get a direct comparison between this year’s indicators and that of last year. An imperfect comparison between the figures for Year 2 using the new measurements and Year 1 using the old measures suggests that M4D is achieving a high overall level of efficiency.

VFM at the activity/input level:
M4D has continued to make strong efforts to ensure a high standard of cost control. The project seeks to control unit costs for technical assistance and as such relies primarily on cheaper Long Term (LT) and National staff with 93% of days for LT staff and 93% for Nationals throughout the year. During this year, the project has made no major purchases that would require the use of Crown Agents and unit costs for other items (international and domestic flights, accommodation and DSA) are monitored to ensure that they remain economical. The project has, for example, changed the hotel which accommodates international staff as a result of this measure.

Assessment of whether the programme continues to represent value for money
The programme continues to represent value for money based on the current logframe. M4D has retained all the core target beneficiaries identified in the Business Plan and is providing them with the necessary interventions. The context and political economy has not created significant new constraints affecting the cost of the programme. While some changes have been introduced via Contract Amendment, the cost per person of delivering M4D’s Outcome and Impact is £27 per person over the life of the programme.

Quality of financial management
M4D has made improvements to the quality of the programmes financial management over the review period. Most notably the programme is now reporting the total budget on output on a quarterly basis. In addition to this forecasting for annual budgets and monthly invoicing has substantially improved.

Output spend is now budgeted and reported on a quarterly basis in the Progress Reports. Over this review period the programme has updated the timesheet format so analysis can be done on allocation of time per output as well as reimbursable costs.

M4D is currently forecasting an underspend variance of annual budget of 6%. However the past 6 months has seen a significant improvement to the monthly variances of programme invoices as demonstrated by the table below:

July	August	September	October	November	December
8.00%	9.00%	5.00%	1.00%	4.00%	1.86%

Date of last narrative financial report	17th July 2014
Date of last audited annual statement	17th July 2014

* 1st and only review M4D has had to date took place in February 2014 and covered the period of 11th June 2012 – 31st December 2013

E: RISK

Overall risk rating: Medium
The overall risk level assigned to the programme remains the same as last year despite a slight increase in the external risk to which the programme is exposed. The key drivers of the additional risk are as follows:
- There is increased political instability caused by the elections. This has manifested as withdrawal of PMs/SPs to focus on political activities including national and state level changes of policy with respect to the role, responsibilities and autonomy of LGAs. Further changes of personnel and policy are expected after the election.
- There has been an overall increase in the risk of violence throughout the year both in terms of politically motivated violence coinciding with the elections and terrorist attacks such as the bombings in Kano City. Increases in both of these threats are expected. However with careful management, this should not pose a serious threat to the existence of the programme.

Overview of programme risk

Risk		Risk Assessment	RAG Rating	Comment
Endogenous
1.1	GIRLS: / Working with Girls in Northern Nigeria is challenging to the status quo.	NO CHANGE	AMBER	M4D is acutely aware of the dangers to girls, their families and the programme. M4D is ensuring active community participation in our work with girls, and are balancing the nature of demands supported and the level of engagement M4D promotes with local context. The programme also maintains a close relationship with LSC mentors to identify early warning of any changes in the level of this risk.
1.2	INNOVATION: / M4D’s approach to innovation necessarily entails some degree of failure.	IMPROVING	GREEN/AMBER	Programme learning shows that innovations are taking longer than originally envisaged to incubate and test but are being well received as a result. M4D is involving communities in innovation and experimentation through the grant programme in order to encourage earlier buy-in and ownership.
1.3	BRAND / IDENTITY: / Greater visibility of M4D as a governance programme may be perceived as a threat to ‘business as usual’.	NO CHANGE	GREEN	As well as M4D’s communication strategies (e.g. Community Theatre, newsletters, stakeholder meetings), the programme maintains close relationships at state and local level to keep explaining the programme. M4D has also requested DFID to engage its partners in government to promote the idea of a governance programme within its portfolio of programmes.
1.4	SCALE: / Policy-makers expect M4D to move quickly to more LGAs – are reluctant to engage with a ‘small scale’ programme	NO CHANGE	AMBER	M4D has identified this as an area for DFID’s support in communicating with policy-makers about the difference between a governance programme and service delivery – and the need to start small and scale up.
Exogenous
1.1	INSECURITY: / Proximity to conflict-affected states may threaten the programme’s ability to conduct activities.	DETERIORATION	AMBER/ RED	There is an overall concern that this could deteriorate further due to both political pressures caused by the election and further spill-over violence from other states. All three states face significant problems in this regard. This is starting to have an effect on the ability of the programme to manoeuvre, especially with respect to international staff.
1.2	COMMUNICABLE DISEASE	DETERIORATION	GREEN/AMBER	There has have been one outbreaks of cholera and bird flu in Kano in July northern Nigeria this year. Poor health systems mean that all programme states are ill-equipped to deal with communicable diseases. M4D ensures that health and safety standards are met within its offices.
1.3	ELECTORAL CHANGES: / Elections allow mean distraction from M4D programme aims; as political activity and change (high turnover) of key government personnel shrinks space for engagement on controversial issues.	DETERIORATION	AMBER/RED	As elections draw nearer, there are greater (and significant) changes in government personnel at local and state levels. Tensions between states and central government risk negatively impacting the programme. M4D attempts to mitigate this risk by building the capacity of institutions as well as individuals so that there can be continuity of achievements through administrative staff and not only politically appointed staff.
1.4	GOVERNMENT PRACTICES: / Reposting of personnel from M4D LGAs presents risk to continuity of programme activities.	NO CHANGE	AMBER	M4D has worked to identify new counterparts in LGAs and will factor this in when deciding on and implementing capacity building programmes. There is an upside to government turnover in the sense that as personnel move to new positions, they take the ideas secured from M4D with them.
1.5	CONSTITUTIONAL REFORMS: / Uncertainty in the policy environment could either distract stakeholders from working on M4D programme issues or induce a ‘wait and see’ approach to governance. Failure to secure enhanced local government autonomy could demotivate those PM/SPs who are committed to local government reform.	NO CHANGE: DETERIOIRATING	AMBERRED	M4D continues to monitor the National Conference Failure to secure enhanced local government autonomy suggests that in the next year M4D should give consideration to the lobbying work it can achieve at the state level on behalf of local government. Enhanced accountability between local and state government may be one area for prioritising better fit approaches.

Outstanding actions from risk assessment
Over the coming year, the programme intends to explore how stronger accountability bridges between local and state government can be built and demonstrated. This is of particular importance given the reduced chance of significant local government reform (in terms of autonomy). M4D has some useful starting points in this regard, not least the Local Government Planning Framework and the Participatory Community Service Management System.

M4D will also need to reflect on the impact on the programme, of the election outcome and associated events (including possible declining budget allocations to State and LGA levels of administration.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme continues to demonstrate that it is on track on spending the programme budget and meeting current logframe targets. The last annual review M4D had spent £2,668,165 by the end of December 2013 of the programme budget of £17,463,813. This represented that the programme had spent 15% of the budget and the programme was 26% of the way through the programme cycle.

In this review period, the programme has spent £5,441,435.84 which represents 31% spend of the budget and the programme is 43% through the programme cycle. As the first two years of the programme have focused on consolidating, testing and learning activities, programme spend was anticipated to be slower. As the next two years will be ramping up on activities, the programme spend rate is due to accelerate.

Performance of partnership (s)
M4D continues to have a range of international and local partners directly involved in the programme. The Lead partner, GRM has worked effectively with ICF and ITAD in the steering group to design and deliver a programme that is effective. M4D has used the services of INTRAC this year to develop its capacity building framework. INTRAC has continued to provide strategic reflection and learning for that component of the work.

M4D has three national implementing partners – CDD, CDRT and YOSPIS. After Dr. Jibrin’s departure from CDD, the organization has had no involvement in the programme. Both CDRT and YOPSIS are heavily involved in M4D.

CDRT has been involved in conducting a Perception Survey in 9 LGAs across the 3 programme states. The programme has found them extremely responsive in terms of delivering against their commitments within the timeframe agreed.

Over the year, YOSPIS has been very responsive and involved in the capacity building training of CBOs under Output 1, and the capacity building of PMs/SPs under Output 3.

Asset monitoring and control
A database is being maintained for all assets. All assets related documents are being scanned and will be uploaded onto a backup system for safety and security. Periodic physical verification of assets is undertaken. Assets are being identified and tracked through a system of allocating numbers and codes. In addition, asset maintenance is also regularly carried out.

G: CONDITIONALITY

Update on partnership principles
There was no Partnership Principles Assessment (PPA) in place for Nigeria at the time of the design of the M4D programme; the PPA notes that there is not a substantive direct partnership with the Federal Government of Nigeria. This is in line with our declared policy that no UK aid money goes directly to the Government of Nigeria. The M4D programme is directly addressing some key issues identified in this assessment.

The M4D programme contributes to strengthening the enabling environment for financial management and domestic accountability, primarily at the LGA level but with some reach to the State level of government administration. The PPA notes that these are important areas of work. Where there is commitment to and evidence of reform willingness, M4D engages selectively with Government at LGA and, to a much lesser degree, at State levels.

H: MONITORING & EVALUATION

Evidence and evaluation
During this last year, state teams have worked together to elaborate the theory of change by documenting and sharing their experience of ‘change pathways’. These change pathways will be explored further as part of the theory based case study research planned for next year.

A key change to the programme intervention design at the end of this year relates to M4D’s Independent Evaluation Manager (IEM). Going forward, management of the evaluation provider will be by M4D, but with controls to maintain independence of reporting. Having the IEM on board is a positive step and will start to develop the process to “identify and evaluate the causal mechanisms through which the M4D programme aims to make policy-makers and service providers in three Nigerian focal States more accountable and responsive to citizens.” Baseline surveys are currently underway and state level reports should be available in early 2015.

Given the formative nature of the evaluation, the IEM will also undertake a number of case studies which should generate learning that will help shape the programme as well as provide robust evidence of what works (or does not) and why to a wider audience.

Evidence gathered this year which has implications for programme design includes:

1. Evidence suggests that it may take more time than anticipated before capacity building initiatives help CBOs reach a state when they perceive that they are positioned and able to influence PMs and SPs.
2. BFAs have taken longer to start up than had been anticipated but the combination of contextual relevance, solution focus and relatively immediate impact appears to have inspired stakeholders with a vision for change.

It is important that M4D does not rely entirely on the IEM for research and learning. There is much value in focused pieces of operational research which will help to address questions raised as recommendations under individual outputs in this review.

Monitoring Process throughout the Review Period
M4D has a generally sound approach to monitoring and data for all logframe targets at output level was available at the time of annual review. There remains some final work to do on outcome indicators, in particular relating to triangulation.

M4D has undertaken a number of revisions to its self-assessment approaches for community based groups during the year to increase their rigor and robustness. Changes to the logframe are in line with previous annual review recommendations and are positive in terms of clarifying what is measured and how those elements work in the programme structure.

However, in the change from output 1 indicators monitoring citizens to CBOs and element of monitoring beneficiary reach has been lost. The programme has developed a draft paper on measuring reach which makes sensible suggestions. This should be finalised soon and monitoring of this element built in to the monitoring and evaluation framework.

Recommendations
- Finalising Baseline to Progress Reports against logframe indicators.
- Production of an analysis report of how LSCs are effectively building the knowledge, skills and confidence of girls to participatory engage in governance processes.
- Initiating the documentation of case stories as “success stories” to capture the M4D approach and results and development of processes for sharing this knowledge across state teams and CBOs.
- Enhanced collation of qualitative evidence to support the quantitative achievements reported by the programme – this should both evidence the results but also help explain how and why change has happened.
- Complete the triangulation of existing data sets using additional tools and approaches.
- Finalise the M&E MIS as the basis for programme performance analysis and learning.
- Continue to assess and revise the CDAS approach, in particular seeking to understand further what it means to progress as a group or organisation and whether the current aggregate scoring gives a realistic measure of this progress.
- Support to the initiation of the household survey to establish the impact and case study baselines for M4D.
- Updating the M4D MEL Strategy and VFM Strategy in line with the revised M&E and VFM Frameworks.
- Develop a research strategy to complement work being conducted by the IEM to answer questions suggested through this review around potential appetite, scope and sustainability of community approaches.

I: Annual Review Process

The review was conducted between January 15th - March 20th, 2015 by three DFID Nigeria Staff (Simon Narbeth – Senior Social Development Adviser; Michael Dunnery – Commercial Adviser; and Stuart Martindale – Results and Statistics Adviser). The Team liaised with the M4D Lead Adviser (Esther Susuyu Ali) and the V2P Lead Adviser (Wilf Mwamba). Ugonna Ajoku (Programme Officer, GSD) provided planning and logistical support.

The Results and Statistics Adviser was tasked with the responsibility of assessing progress towards achieving the logframe outputs and outcome; and identify priorities for the coming year. The Adviser also contributed to discussions and over-all scoring of the project. The Commercial Adviser assessed the performance of the project (costs versus results) to date to determine whether the project still represents good Value for Money and interrogated evidence of spin-offs, broader benefits and trends in key cost drivers over time, and their impact on unit costs. The Senior Social Development Adviser played a Lead role for the review, coordinating inputs and editing the review report, ensuring that the review questions listed in the ToR were addressed.

The Annual review adopted a light touch, self-assessment and desk review approach due to number of reasons: (a) field visits were constrained during the first half of January and most part of February and March due to the national (Presidential and senate seats) and state (Gubernatorial and state house of assembly seats) elections scheduled for February 14th and 28th respectively; and security concerns around possible pre/post-election violence; (b) low appetite for postponing the review meant that it had to happen before March 31st (the due date for upload of the report on Aries); and,(c) an office-wide six-monthly review commissioned for March 18th -19th, requiring input from all staff including those who involved in the Annual Review.

In light of these limitations, a strategy was developed to ensure a robust and credible Annual Review process. This involved the project conducting a self-assessment exercise and preparing a comprehensive report, addressing the scope of work defined in the ToR for the annual review. Reports of the self-assessment exercise, accompanied by all the relevant evidence and documentation were submitted for assessment to the Review Team. The assessment process included a two day interactive meeting in Abuja, during which relevant project Staff presented project activities and the self-assessment reports; as well as testimonies from project beneficiaries. Q&A sessions were built into the daily sessions, allowing the Review Team to ask questions, clarify issues arising from the self- assessment report and/or the presentation.

J: Persons Met

Name (M4D) Staff	Designation	Email Address	Telephone
Sachin Gupta	Programme Director	Sachin.gupta@grminternational.com	+44 20 7250 0556
Clare Santosh	National Team Leader	Santosh.clare@grminternational.com	++234 8136990126
Ahmed Mohammed	Deputy Team Leader	Ahmed.mohammed@grminternational.com	++234 8026726778
Angela Christie	Technical & Results Director	angela.christie@hotmail.co.uk	Tel: +44 1722 712355 / M: +44 7802 409901
David Cuthbertson	Short Term Technical Adviser & formerly Interim Team Leader	David.cuthbertson@grminternational.com	+44 20 7250 0556
Favour Simeon	Results, Monitoring, Evaluation & Knowledge Management Advisor	Favour.Simeon@grminternational.com	+2348037766165
Gombe Haruna Ibrahim	State Programme Manager (SPM), Jigawa	gombe.ibrahim@grminternational.com	+234 7039248009 / +234 8052729612
Sadiya Adamu	State Programme Manager (SPM), Kano	Sadiya. Adamu@grminternational.com	+234 8037022566 / +234 8098968665
Hannatu Ahuwan	State Programme Manager (SPM), Kaduna	Hannatu.Ahuwan@grminternational.com	+234 806 515 8708 / +234 8091232280
Ibrahim Muhammed Yakubu	Finance & Administration Manager	Ibrahim.Muhammed@grminternational.com	+234 803 703 8571 / +234 8094499944
Fanen Ade	Governance & Capacity Building Advisor	Fanen.Ade@grminternational.com	+234 7086400477
Mustapha Bello	Grants Manager	mustapha.bello@grminternational.com	+234 7086400477
Patricia Rowland	Gender & Social Inclusion Advisor	Patricia.Rowland@grminternational.com	+234 8023353481
Yusuf Umar	National Monitoring & Evaluation Officer	Yusuf.umar@grminternational.com	+234 8035989767

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and on-going relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VFM performance compared to the original VFM proposition in the business case? Performance against VFM measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process