Mobilising for the Millennium Development Goals (MDG)
‘M4M’

Business Case

 July 2011

Contents	Page number
Intervention Summary	1 - 2
1. Strategic Case
Context and need for DFID intervention	3 – 8
Impact and outcome	8
2. Appraisal Case
Determining critical success criteria	9
Feasible options	9 – 24
Appraisal of options	24 -29
Comparison of options	29
Measures to be used or developed to assess value for money	–29 - 30
3. Management Case
Oversight	31
Management arrangements	32
Conditionality	32
Monitoring and evaluation	33 - 36
Risk assessment	36 - 41
Results and benefits management	41
4. References	42 - 44

Annex A: Logical Framework

Acronyms

CBO	Community Based Organisation
CDOT	Community Development and Outreach Team
CGS	Conditional Grant Scheme
COMPASS	Community Participation for Action in the Social Sectors
CSC	Critical Success Criteria
CSO	Civil Society Organisation
DFID	Department for International Development
ENABLE	Enhancing Nigerian Advocacy for a Better Business Environment
ENR	Enhancing Nigeria’s Response to HIV and AIDS
ESSPIN	Education Sector Support Programme in Nigeria
FOMWAN	Federation of Moslem Women Associations in Nigeria
GEMS	Growth and Employment in States
GEP	Girls Education Programme
GoN	Government of Nigeria
J4A	Justice for All
LGA	Local Government Area
M&E	Monitoring and Evaluation
M4M	Mobilising for the Millennium Development Goals
MDG	Millennium Development Goal
NGO	Non Governmental Organisation
OJEU	Official Journal of the European Union
PATHS2	Partnership for Transforming Health Systems 2
PQQ	Pre-Qualification Questionnaire
PRRINN-MNCH	Programme for Reviving Routine Immunisation in Northern Nigeria – Mother, Newborn and Child Health
NSRF	Nigeria Stability and Reconstruction Fund
RAMP	Rural Access and Mobility Project
REVINN	Religion, Exclusion and Violence in Northern Nigeria
SBMC	School Based Management Committees
SPARC	State Partnership for Accountability Responsiveness and Capability
SHAWN	Sanitation, Hygiene and Water in Nigeria
STUMEC	Student Tutoring Mentoring Counselling
SUBEB	State Universal Basic Education Board
SUNMAP	Support to the National Malaria Programme
VfM	Value for Money

Intervention Summary - Mobilising for the MDGs (M4M)

Programme Details
Period of funding: 6 years from April 2012 to March 2018, with a review in the third year.
Why is UK support required?
What need are we trying to address? / Northern Nigeria has some of the worst human development indicators in the world and they are particularly bad for adolescent girls and women. / Service providers are not delivering. / Accountability is weak and government is unresponsive. / The policy environment is not conducive to agricultural and business development. / Nigeria is an oil-rich and growing economy. But it has not translated its wealth into effective services and better living standards. Nigeria is unlikely to meet the MDGs. The north has high levels of poverty and social exclusion. Women and girls are further disadvantaged by gender politics and gender-biased interpretations of religion. / Underperformance is caused by political and bureaucratic patronage nourished by oil revenues, low expectations of government on the part of citizens and patterns of political allegiance and support determined by geography, ethnic identity, vested interests and personal connections. Together these have prevented the emergence of a broad-based political coalition of interests at a national level that could press for a change in government performance (Utomi et al 2007a & 2007b). / For government performance to improve the political culture must change. Government needs to be more accountable and responsive, and citizens more aware of the responsibilities of the state towards them, and more demanding of their rights. This programme will demonstrate that where communities and local government meet it is possible to reshape the relationship between the Nigerian state and its citizens whilst ensuring the delivery of services that matter to citizens are directly improved. / What will we do to tackle this problem? / The project will strengthen social accountability and tackle social exclusion. It will work with 650,000 people (including at least 30,000 adolescent girls) in 270 community groups in 9 Local Government Areas (LGA) in Kano, Kaduna and Jigawa. Between them the 3 States have a population of about 20 million in 94 LGAs. In the 9 LGAs where it is active the project will have a direct impact on about 1/3rd of the population. The remaining population – over 1m - will indirectly benefit from improvements in LGA performance. / The programme will work with the Government of Nigeria’s MDG conditional grant scheme (MDG/CGS) and add value by tackling social exclusion and marginalisation. By working with the MDG/CGS the programme will prepare the way for replication and scaling-up the approach. / The approach will involve: / Building the capacity of communities to identify their problems and solve them. The project will support research and advocacy on the policy and regulatory environment and provide match-funded funded grants for development investments. / Focusing on excluded and marginalised groups, in particular adolescent girls. / Involving GoN staff at Local Government and State level to aid understanding and the adoption of the approach by others. / Promoting the approach for adoption by other development partners. This programme has the potential to enhance the way the MDG office implements the CGS at LG level across all 774 LGAs in Nigeria. / Conflict sensitivity / The project will take account of the political, economic and social aspects of its interventions. Project staff and partners will be provided with conflict sensitivity training. The project will tackle the underlying causes of conflict - social and economic exclusion - by focusing on the continuing failure of the political and economic systems to meet peoples’ basic needs (REVINN 2011). / Who will be implementing the support we provide? / A team selected by a competition will work with GoN community development staff. The team will have local community development staff with experience of working with women and adolescent girls. The team will work closely with CSOs and CBOs.
What are the expected results?
What will change as a result of our support? / 650,000 people in 270 communities will make faster progress towards the MDGs. Citizens will be more able to plan and control their development. They will be more aware of the responsibilities of government and able to effectively press the government to deliver services more effectively. Local government will be more responsive and may enforce, change or adapt policy to benefit poor people. Around 30,000 adolescent girls will have their awareness and self-confidence raised, go to school for longer, and marry and have children later. Infant mortality, fertility and maternal mortality will fall. / What are the planned outputs attributable to UK support? / Output 1: Communities empowered to better manage their own development: A programme of proven community development work to tackle social exclusion and increase social accountability and to empower local communities to take control of their own development, demand better services from government and hold government to account. / Output 2: Increased voice for and accountability by government to, excluded groups, particularly adolescent girls: A programme of support to ensure that excluded and marginalised groups are fully included in output 1. / Output 3: Policy makers and service providers able to support, and respond to problems and needs of communities identified through participatory community development processes: Involving the staff of GoN and other service providers in the programme to transform the relationship between communities and government and remove barriers to improving livelihoods. The project will also tackle the regulatory and policy environment. £1 million will be available to do further work on policy analysis, research and advocacy to support this component. / Output 4: Replicable approaches to strengthening empowerment and accountability, demonstrated: A substantial effort to communicate the approach, disseminate lessons learned and facilitate others to replicate the processes, including through targeted advice and support to potential programme partners and government. / The project will help achieve the following results in the DFID Nigeria operational plan and gender annex: wealth creation – poor people’s incomes increased, improved access to health care, increased voting in national elections, 800,000 more children in school (75% of whom will be girls), safe spaces created for 100,000 girls reduced violence against women, and 5.5m people with better water and sanitation services. / How will we determine whether the expected results have been achieved? / Impact, outcome and output indicators will be monitored throughout the programme. Supplemented by annual reviews and a major review in year 3, these mechanisms will assess the overall effectiveness, cost efficiency and equity of the programme. This programme will use evaluation as a learning tool and build in evaluation techniques from the start.

1.	Strategic Case

A1. Context and need for DFID intervention / The need for this DFID intervention is evidenced by the following factors: / Northern Nigeria has some of the worst human development indicators in the world, and mechanisms and structures of social exclusion lead to some groups being particularly badly affected. / Adolescent girls and women suffer disproportionally / Service providers are not delivering. / Accountability in Northern Nigeria needs to be strengthened to promote responsiveness of governments to the needs of citizens. / The policy environment is not conducive to agricultural and business development. / Each of these justifications is described in detail below. / Human development indicators / The Nigeria Demographic and Health Survey 2008, the Nigeria Education Data Survey (NEDS) 2010 and the National Literacy Survey Report 2010 show that northern Nigeria lags behind the rest of the country on the majority of human development indicators. / Poverty: 24% of sub-Saharan Africa’s poor live in Nigeria (UN MDG Report). 102 million out of Nigeria’s 158 million (64%) people are living on less than $1.25 per day[1]. However this poverty is not equally distributed, with the states in the north of Nigeria having 77% living on less than $1.25[2]. 64 million of Nigeria’s extreme poor live in the north of Nigeria. Women are particular victims of poverty, reflected in their access to social services: for example, 56% of women from the highest wealth quintile deliver in health facilities compared to only 7% in the lowest (Nigeria Demographic and Health Survey 2008). / ( / Education: The majority of adolescent girls have no education: over three quarters of girls and women between 15 and 49 cannot read at all; in Jigawa state the female illiteracy rate is 94% (compared to 42% for men).[3] Only 3% of adolescent girls in the north complete secondary school. / Health Care: Access to health care is similarly restricted: just 8% of adolescent girls and women in the northern states give birth in a health facility and only 11% with the assistance of a skilled provider. The northern states have by far the highest rates of under-5 mortality and the lowest rates of tetanus and malaria protection. / Water and Sanitation: Access to clean water and improved sanitation facilities is a significant concern in the north as elsewhere in Nigeria. Overall figures mask differences between regions but are still low: 46% of Nigerians have no access to improved sources of water and 30% have no toilet facility. In recent DFID surveys in five states, 35% of respondents said their access to water had actually declined (SPARC, SAVI & PATHS2 2010). Ready access to clean water is a primary concern for adolescent girls and women. / The environment for raising incomes, and providing health education and water services, are not only important for adolescent girls and women; they are also important for youth and men. However, girls and women have far less opportunities and receive poorer service than men across all four MDGs. They are excluded from the decision-making processes and they have no voice in articulating needs and determining priorities for service delivery. Since women are responsible for child care, their opportunities to raise their incomes, and their lack of access to education, health care and clean water has significant - and negative - implications for infants and children. / Adolescent girls and women suffer disproportionally / Adolescent girls and women are virtually invisible in decision-making forums around service delivery in the north. Discussions by men about local service delivery do indeed take place: in the traditional rulers palace, on the street, in local government offices and in places where men gather, but these are not spaces where poor adolescent girls and women are seen. Norms of seclusion in some cultures and traditions mean that the majority of adolescent girls and women in the north have little opportunity to meet with other women, learn about income opportunities, what services are available and why they are important, and discuss their needs and priorities. Women’s NGOs exist and are keen to do more but currently lack the capacity and funding to reach out to secluded poor women and to represent their views (REVINN 2011). / Gender related behaviour at household and community level play a major part in maintaining women’s lack of personal autonomy, visibility and voice. A first step in any intervention involving adolescent girls and women will be the identification of ‘safe spaces’ where women can work with other women to raise their awareness about their rights and entitlements, including from government, and the services they could and should be receiving. / The intervention will need to take account of the contextual barriers both to girls and women’s empowerment and to the ability of local governments and other service providers to deliver improved services. DFID’s recent research and institutional experience suggests that there are reformers and progressive thinkers in all northern states who are willing to work in partnership with new programmes and who will themselves champion change. / Service providers are not delivering / Although the 1998 Constitution sets out an extensive mandate for service delivery by local governments, in reality the majority of services are delivered by State governments. Central funding of local governments, representing 20% of the Federation Account, is channelled through State governments’ Joint Account mechanism. However, in practice, this funding is ‘retained’ by the State governments to finance ‘joint projects’ initiated and implemented by the State governments. Discretionary spending by local governments, to meet locally determined priorities, is the exception. Rules around fiscal monitoring and reporting are weakly enforced, so that in many states it is difficult or impossible for members of the public to find out whether LGA resources have been received, or if received, whether they have been responsibly used. / Contractors, NGOs and private individuals do also provide services. For example a good number of Islamiyya[4] schools are funded by wealthy individuals and some of these have no government connection. Whilst this intervention will primarily deal with government-mandated services, ways will need to be found to identify and involve all major service providers so that accountability mechanisms, informed by the views of women, can be developed with the private and voluntary sector as well. In many cases this may be through supporting the establishment and development of regulatory bodies (as we are currently doing for Islamiyya education in Kano State). / Accountability in Northern Nigeria could be better………. / Formal democratic institutions remain more responsive to demands from entrenched political elites than from voters (Drivers of Change 2005:v). In principle, elections make it possible for Nigerians to hold their government to account but, in practice,most elected representatives continue to act as patrons to whom ordinary people turn for individual favours. However, the voices of girls and women are largely absent in Nigerian politics because patronage systems are mediated through men and, if girls’ and women’s needs are articulated, then it happens largely through men. The recent experience of electoral democracy has yet to establish an accountable and responsive relationship between state and citizens. / In northern states the notion of being a citizen with rights vis-à-vis the state is underdeveloped. (REVINN study 2011) Government service provision is seen in the same light - not as a universal right that accrues from citizenship but as the result of individual intermediaries - traditional rulers, CBOs and well-placed individuals - being able to negotiate for ‘their’ community, sometimes at the expense of another that is equally deserving but has less connections. Improving accountability is therefore an essential component of governance reform. / DFID Nigeria has a strong record of supporting supply side accountability, i.e. building the capability of government at federal and state levels to plan and deliver services and to be financially transparent. This programme will complement our existing governance programmes to directly support communities to come together, articulate needs and interests, understand what they should be receiving, and from whom, identify their priorities and develop a direct relationship with service providers whom they then hold to account. The programme will also go beyond accountability for service provision. By working directly with communities, changes to the regulatory and policy environment at a local level that will improve livelihoods for poor people will be identified. Communities will then be supported in making their case to local governments for the changes. / Environment for agricultural and business development is not in place / State and local governments have failed to create an environment for improved agricultural productivity and business growth. Increased poverty and marginalisation of people in the north has led to weakened accountability of state and local government to invest in infrastructure (roads, power, irrigation) vital for agricultural and business growth, as well as promoting the right regulatory framework for business to grow (e.g. agricultural subsidies, weak land system). Public engagement in these issues is marginal at best. / Government’s performance in delivering the MDGs / The Government’s own assessment of the country’s performance in meeting the MDGs reflects a mixed picture. Real progress is being made and for each MDG there is a positive story to be told (MDG report 2010). Progress towards five MDGs has been average, but progress has been less satisfactory for the remainder. Table 1.1 below summarises progress to date and the potential to meet the targets by 2015. / Table 1.1: MDG targets – progress and potential (from MDG 2010) / MDGs and targets Nigeria progress and status at June 2010 Potential to meet target / 1. Eradicate extreme poverty and hunger Slow / Target 1: Halve, between 1990 and 2015, the proportion of people living in extreme poverty. Average / Target 2: Halve, between 1990 and 2015, the proportion of people who suffer from hunger Average / 2. Achieve universal primary education Average / Target 3: Ensure that, by 2015, children everywhere, boys and girls alike, will be able complete a full course of primary schooling. Average / 3. Promote gender equality and empower women Average / Target 4: Eliminate gender disparity in primary and secondary education, preferably by 2005 and to all levels of education no later than 2015. Average / 4. Reduce child mortality Average / Target 5: Reduce by two-thirds, between 1990 and 2015, the under-five mortality rate. Average / 5. Improve maternal health Slow / Target 6: Reduce by three-quarters, between 1990 and 2015, the maternal mortality rate. Average / 6. Combat HIV/AIDS, malaria and other diseases Average / Target 7: Have halted, by 2015, and begun to reverse the spread of HIV/AIDS. Good / Target 8: Have halted, by 2015, and begun to reverse, the incidence of malaria and other major diseases. Average / 7. Ensure environmental sustainability Slow / Target 9: Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources. Weak / Target 10: Halve, by 2015, the proportion of the population without sustainable access to safe drinking water and basic sanitation. Weak / GoN has issued its Countdown Strategy which explains the strategic initiatives that the Government will introduce to tackle the challenges and gaps, and to accelerate progress towards achieving the MDGs. One of the strategic initiatives is reinforcing local governments with a proposed increased MDG funding allocation to LGAs. Funding to LGAs for MDG spending has been less than a third of the level assessed as being needed. Furthermore, the Nigeria Vision 20:2020 Blueprint stipulates that, "A key strategy that will be used to drive the implementation of NV20:2020 will be the empowerment of the local governments to drive rural development at the grassroots." One dimension of this empowerment at the grassroots level is to mobilise and incentivise communities to achieve MDG targets. The Strategy, in addition, acknowledges the importance of collaboration across the three tiers of Government and the need for a community driven development approach. / The CGS, from 2011, is being extended to include LGAs; a selection of 113 LGAs in the first year. The main features of the Scheme are illustrated below. / Figure 1.1: CGS for LGAs – features / Objectives: Increasing investment in the MDGs at the Local Government level; supporting and empowering Local Governments to achieve improved service delivery; strengthening intergovernmental collaboration and coordination between Federal, State and Local Government / Priority areas for support: Informed by the Needs Assessment and baselines completed by the MDG Office[5], with a focus on education and health services / Funding: Federal-50%, State-30%, Local-20% / Approval: LGA Chairperson based on recommendation of LGA MDGs Planning Committee informed by inputs from communities, and traditional and religious leaders / Monitoring: LGA MDG Technical Team and civil society (using the Overview of Public Expenditure in NEEDS) / M4M and potential links with current DFID programmes in the North / There are several state level programmes being implemented in the Northern States with DFID support. These range across those MDGs relating to education, health, water and sanitation. Typically these programmes contain a strong emphasis on governance and service delivery (especially at the local level within LGAs) with aspects of civil society and community ‘demand’. All of the programmes, to varying degrees, work alongside local government. However, the experience of these programmes, working through state governments down to local service delivery units, without the full engagement of LGAs, has revealed a gap in DFID’s state level approach. LGAs are key players in service delivery as well as being the closest political and administrative interface with citizens within their communities. One of the aims of this project is to create a closer link to local government, principally by working with communities and drawing local government into that work. / M4M will help fill this gap by working with community groups and bringing LGAs into the development process in their own right and not just as a conduit for State led service provision. The potential linkages for M4M with the current portfolio fall into two dimensions: a geographical co-location in Jigawa, Kaduna and Kano and a functional link through strengthening the engagement of both communities and LGAs in planning, implementation, monitoring and reporting of mutually agreed development activities. Figure 1.1 below illustrates the nature and extent of DFID’s presence in the 3 states as well as highlighting the role of M4M in filling the gap around LGA governance, accountability and responsiveness. Although many of the current programmes are designed to improve the ‘demand’ side, in practice these efforts have been limited to ‘voice’ and have not improved processes relating to ‘accountability’ and ‘responsiveness’ (Derbyshire, H. et al 2010). / In addition, M4M’s key positioning in this complex institutional map will provide the platform for both these and additional programmes to explore and exploit the linkages. For example, both the Growth and Employment in States (GEMS) programme and the Rural Access to Markets Project (RAMP) may access M4M communities as entry points for markets related interventions. Furthermore, where existing or planned DFID programmes, such as the Girls Education Programme (GEP3), moves into these 3 states, then the potential synergies for linking with M4M’s work, say in supporting adolescent girls, can be explored. / Figure 1.1: M4M’s potential ‘fit’ with existing DFID programmes in the North / DFID programmes: ESSPIN PATHS2 SPARC SAVI SHAWN PRRINN ENR ENABLE SUNMAP J4A M4M / Alignment: / State engagement: / Jigawa * * * * * * X X X * * / Kaduna * * * * X X * * X * * / Kano * * * * X X X * * * * / Output areas: / State/sector governance / Service delivery [6] / LGA governance, accountability, responsiveness / CSO/community ‘demand’
B. Impact and outcome / Definitions / (based on DFID draft note on empowerment and accountability, 2011) / Empowerment means enabling people to have more control over their own development and supporting them to have the power to make and act on their own choices. / Accountability means ensuring that officials in public, private and voluntary sector organisations are answerable for their actions and that there is redress when duties and commitments are not met. / We are defining empowerment and accountability as interventions that enable poor people to have the resources and capability to have greater choice and control over their own development and to hold decision-makers – including governments and service providers – to account. / Impact / The proposed impact of this programme is “increased progress towards achievement of the MDGs in Nigeria”. / Outcome / The intended outcome is “Policy makers and service providers in 3 Northern Nigeria states more accountable and responsive to citizens.” / Outputs / Output 1: Communities empowered to better manage their own development. / Output 2: Increased voice for and accountability by government to, excluded groups, particularly adolescent girls. / Output 3: Policy makers and service providers able to support, and respond to, problems and needs of communities identified through participatory community development processes. / Output 4: Replicable approaches, to strengthening empowerment and accountability, demonstrated.
[1] This is calculated using 2004 Nigerian Living Standards Survey and 2010 UN Population Division population projections
[2] $1.25 per day sub-national figures were estimated using the same regional share as the national poverty line figures to adjust the national $1.25 per day figures
[3] Figures in this section are taken from the Nigeria Democratic and Health Survey 2008 and DFID Nigeria’s Operational Plan 2010 unless referenced otherwise.
[4] Islamiyya schools provide both secular and religious (Qur’anic) education. They are owned privately but can receive state support to deliver secular teaching
[5] Formally titled as the ‘'Office of the Senior Special Assistant to the President on MDGs’
[6] Service delivery in this context relates to improving the business environment

2.	Appraisal Case

A. Determining critical success criteria (CSC) Each CSC is weighted 1 to 5 where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / The options have been assessed according to the following criteria: / CSC Description Weighting / (1-5) / 1 Degree to which the programme strengthens linkages, ‘horizontally’ across communities, especially vulnerable groups including adolescent girls, and ‘vertically’ between communities and LGAs/state governments, through NGO/CSO/CBO intermediaries/partners? 5 / 2 Has the programme design made reasonable assumptions about the capacity of key stakeholders, state and non state, to engage actively in responding to, and adopting, more responsive ways of working with communities, especially adolescent girls and women? 4 / 3 To what extent does the programme have the flexibility to adopt variations in approach in different states to allow for sufficient experience to be gained; to enable ‘transformational’ lessons to be learned and to provide an informed basis for replication? 5 / 4 Degree to which the design makes reasonable and cautious assumptions about ability to recruit and deploy sufficient technical and field staff to work with a range of communities that are geographically dispersed across urban, peri-urban and rural settlements? 4 / 5 Does the approach complement and enhance participatory mechanisms being promoted by other DFID programmes, including ability to invest funds from other programmes (e.g. cash transfers, girls’ education)? 2 / 6 Degree to which the option will attract the necessary political support? 5 / 7 Does the programme provide extensive enough coverage and reach a sufficiently large target population, and also produce significant and visible enough results at a reasonable cost per capita to create interest and momentum for adoption and scaling-up? 5 / B. Feasible options / The following design principles underpin the programme outputs common to all options. / Development by all the people and for all the people. Success will be measured by the extent to which the voices and needs of excluded and marginalised groups have been heard and acted on. / This programme is designed with the aim of transforming the relationships within communities and then between communities and the government. Community-based and participatory approaches to planning that strengthen social accountability have been demonstrated to be a successful mechanism to facilitate the effective engagement of vulnerable groups with responsive service providers, especially the state agencies. There is medium evidence internationally that this approach works; and medium evidence that the approach works in Nigeria (Compass n.d.; World Bank 2008; LUPP 2006; Gaventa, J. et al 2011; Adediran & Bawa 2010; Menkiti, A. & Babatunde, K. 2008). The Nigerian Government’s MDG local government conditional grant scheme, a nation-wide scheme to accelerate the achievement of the MDGs will be using a participatory and community-based approach to planning. These interventions have shown that programmes, through appropriate institutional arrangements, can catalyse an effective partnership structure between LGAs and community groups to enhance social and economic welfare. For instance, the DFID-N, State Level Education Sector Support Programme in Nigeria (ESSPIN), has focused on the establishment and functioning of School Based Management Committees (SBMCs) for enhancing community participation in the preparation and implementation of school development plans and Improving linkages between communities and civil society in making demands for better quality, inclusive education (ESSPIN 2011a). There have also been small pilot tests of girls’ platforms in Northern Nigeria that have shown that they are feasible and can work to build girls’ assets. / There is also medium evidence that this approach – of empowering citizens - must be pursued alongside measures to strengthen the responsiveness and accountability of the State rather than as a separate exercise (Gaventa, J. et al 2011). So the programme will also work with government to strengthen accountability and responsiveness. / Empowering communities and people within them involves changing the “rules of the game”. The starting point must be the prevailing social, political and economic norms and hierarchies. These will privilege some people’s voices at the expense of others. Wealthier and more powerful people will dominate and bias the discussion towards their needs. Different approaches to public gatherings and meetings will be needed to ensure that everyone is included. Large public meetings will favour men’s voices. Smaller less public meetings with only women will be needed to ensure their voices are heard. Even among females, girls will not have their voices heard unless dedicated space for girls is created at the community level. Poorer sections of the community will also need to be consulted separately, as well as sensitivity to the need for gender segregated spaces so that women’s voices will be heard until mutual trust and respect is built in the community. / In all of the options a particular effort will be made to ensure that the voices of adolescent girls are heard. This will be through the promotion of girls’ platforms. These will contribute to empowering everyone in a community, and ensuring there is accountability to everyone. Adolescent girls, through building social, human and economic assets will be empowered to have more voice and control within their own lives, as well as a greater sense of self-worth. In addition, through building a community structure that values girls, as well as a young women’s leadership cadre of mentors, adolescent girls will have a seat at the table of the wider community development forum and communities will have a new layer of young women leaders – further changing who has ‘voice’ and to whom local governments are accountable at the community level (Jones, N. et al 2010). / However, the evidence that this approach has led to inclusive and empowered communities is currently limited. There are good examples of participatory approaches to citizen engagement leading to communities managing their development more effectively. But the next step: moving from managing their own development to a step-change in their engagement with government and outsiders - has been less frequently taken (Gaventa, J. et al 2011; Mohanty, R. 2007). This stage, moving from local management of community resources to social accountability for the delivery of government resources is a vital one. And where this has taken place, it has proved effective. Where it has been, key elements in the success of the approach have been ensuring that local communities have all the information they need to hold government to account, and also have the skills and competence to understand and use the information they have been given (World Bank n.d.). This programme will ensure that citizen participation goes beyond the boundary of the community and starts to transform the relationship between citizens and the state and promotes much greater accountability from government. / To achieve this, the programme will work in partnership with civil society and community-based organisations that have legitimacy and experience of working on increasing transparency and accountability of government to communities. A particular focus will be improving communities’ knowledge of government budget and planning systems so that communities are more able to hold government to account. / In addition, the programme will work with the media, including new media and develop approaches to community-based reporting and monitoring of government service delivery and to promote social accountability (see World Bank n.d. for examples of how this has been done elsewhere). The new Nigerian legislation on Freedom of Information also provides an opportunity to strengthen accountability. A civil society group, Socio-Economic Rights and Accountability Programme (SERAP) has used the Freedom of Information Act to obtain from the Enugu, Kaduna, Oyo and Rivers information and documents on spending on primary education (Sahara Reporters, June 2011). / There is medium evidence from a global body of adolescent girls’ programmes that use the girls’ platform approach – including rural, socially conservative, and/or Muslim settings – that girls’ platforms are a successful and critical way to create voice for girls and build their social, human and economic assets. Similar programmes have proven that not only is such a programme design possible, but they have also successfully increased girls self-esteem, increased decision making, achieved literacy and helped girls return to school, delayed the age of child marriage, increased use of family planning among married girls, and increased demand for local resources and services (Population Council n.d., Baldwin, W. 2011). / The girls’ platforms will connect directly into the wider community environment and the work of M4M at the community level. The girls’ platforms, by creating space in communities for girls to gather, and creating a cadre of young women leaders as their mentors, provide representation for girls at the community empowerment structures that will be developed, supported and strengthened through M4M. By including girls’ platforms, the mentors will provide the voice of girls at the community councils and other structures. / 2. As well as empowering communities, service providers need to be supported if they are to become more responsive and accountable to citizens / The principal focus of the programme will be working with communities to develop their capacity to build their capacity to engage more effectively and more powerfully with government to solve their development problems. This not only creates external pressure for change within government towards greater responsiveness and accountability. It also creates space for reformers inside government to push their agenda for change. The implication is that attempting to build responsive and accountable states without recognising and supporting the contributions of organised citizens to the process will do little to bring about sustainable change. So building pressure for change outside government needs to be accompanied by support to reform-minded individuals on the inside. / There is medium evidence from Nigeria that this approach can also lead to changes in government responsiveness. This is made easier when domestic pressure for reform is supported by a global campaign. In Nigeria the campaign for the right to education opened up spaces for participation at the national and regional levels for civil society organisations to participate in the development and subsequent monitoring of education policies (Adediran & Bawa: 2010; Gaventa. J, & Mayo, M: 2009). Finding suitable support for the programme, e.g. though linking with international NGOs working on budget transparency and accountability will be part of the programme strategy. / The pressure from the outside also needs to be matched with work on the inside with reformers seeking support. The programme will engage with government and other service providers so that they are prepared for and able to respond to the increased voice of and raised expectations of communities. Reform-minded people will be sought out (other DFID programmes have developed a good understanding of the political economy of states) for the adoption and replication strategy. In addition, LGA field staff will be involved in the diagnostic and mapping work with communities. The programme will facilitate linkages between LGAs within a State, as well as between LGAs and State level Governments and also between States (e.g. by using the Governors’ Forum), in order to spread lessons and best practice. Medium evidence from Nigeria that this approach is effective can be found in the Community Participation for Action in the Social Sector (COMPASS) programme, where quality improvement teams consisting of service providers and community members were formed to catalyse providers’ responses to an increased and more articulate demand from citizens (COMPASS n.d.). / DFID is well placed to engage with government reformers in the 3 programme states. There are already in place state-level programmes in health (PATHS) and education (ESSPIN) and crosscutting programmes in public sector reform (SPARC) and to promote accountability and enhance citizens’ voice at state level (SAVI). The Growth and Employment in States programme will be moving from inception to full implementation shortly. Links between these programmes and to DFID are strong and have enabled the building up of a strong and diverse network of partners both inside and outside government in the programme states. Through these networks DFID and the programmes can identify reform-minded people and departments and work with them. / DFID also has strong links with the MDG/CGS and this nationwide programme will be a significant programme partner. It will draw on the approach developed by the MDG/CGS, which provides additional funding to State and Local Governments to accelerate progress towards the MDGs. By promoting consultation and cooperation between the Federal, State and Local Governments, communities and civil society the MDG/CGS improves the responsiveness of Government to community needs, and promotes accountability by government (MDG/CGS n.d.). Linking the programme design to the MDG/CGS offers significant advantages. MDG/CGS has high visibility and significant political support through the Office of the President and the Governors’ Forum. This level of political engagement has every prospect of expanding to include the LGA chairpersons who will be key stakeholders in the implementation of M4M. Furthermore, MDG/CGS has been successful in incentivising the adoption of improved ways of working through more inclusive planning, more effective implementation and more open monitoring using civil society organisations. / The programme will add value to the MDG/CGS approach by actively tackling social exclusion and marginalisation and so as to transform not just the relationship between communities and government, but also the relationships within a community that keep particular groups excluded from, or at the margins of development. By working with the MDG/CGS the programme will prepare the way for replication and scaling-up the approach. / This programme will work closely with the existing portfolio of DFID-funded programmes and the MDG/CGS programme, making the most of the opportunities for synergy between the different programmes’ objectives. This programme will, through the fieldwork at community level (urban, peri urban and village), reveal much about how government services are performing and are perceived at community level. This information will be fed back to the state level programmes. In turn, the state level programmes will be able to provide detailed information about the scale and range of government services that should be provided to communities. This will make an important contribution to empowering local communities: by having reliable information about what services they are entitled to expect from government, they can more effectively demand accountability from government for the delivery of those services / 3. Adaptation and adoption of the approach by others to scale-up impact is not automatic / This programme has a stretching aim. The eventual impact being sought – a step-change in the relationship between citizens and the State – is challenging and cannot be delivered by the programme alone. The aim is for citizens to have more voice and power with and higher expectations of government to be more responsive and accountable to citizens even where government is not directly delivering services (through changes in the policy and regulatory environment). It will be working on a small scale when set against the size of Nigeria. To be fully successful the approach developed by the programme must be adapted and adopted on a wider scale. This will be done by working alongside other government programmes such as the MDG Conditional Grant Scheme; working with Civil Society Organisations to spread the approach beyond the target States and using networks of traditional leaders and the Governors’ forum (Governors’ Forum n.d.) along with links with other DFID-Nigeria Programmes and other donors and development partners. In addition, media and other communication networks will be used to advocate for and spread the approach. / The programme has been designed to build momentum towards a “tipping point” in the relationship between citizens and the state. Scaling up impact will not rely on other players adopting a “good idea” just because it is good. There is strong evidence that having a good idea, implementing it and telling the good news to others does not to lead to replication elsewhere. Much more effort is needed, and it needs to be much more than a communications strategy (Evans, S.H. & Clarke, P. 2011). / Delivering impact beyond the programme boundaries will comprise a combination of: / Developing approaches to participatory approaches to community and local development on a scale large enough to be noticed, and at a cost that is replicable elsewhere.[7] / Forming alliances with reform-minded people within government. / Using a range of formal and informal networks to spread ideas and create a “buzz” around the approaches being used. / Clearly evaluating what works and why. / Advocacy, coaching and consultancy, knowledge management and peer support on how to develop the approach to their needs. This activity will be properly resourced and managed and not left as an afterthought to the internal programme activity. / The options have been designed with a view to spreading the approach and scaling-up the impact of the programme. Indicative spend per head to reach direct and indirect target beneficiaries have been assessed for each option and range from £6 to £11 per capita over the life of the programme. These costs will be reviewed during programme implementation, alongside an assessment of the scale of resources likely to be available for adoption of the approach by GoN or other agencies. Periodic reviews will ensure that the programme is adequately but not over-resourced so that potential adopters can afford adoption of the approach. / Within each LGA where the programme is active there will be a direct impact on up to 40% of the population. This scale and intensity of activity will create sufficient momentum so it is likely the LGA will adopt the approach when it is working with other communities. Scaling up the impact to State level will require, getting LGA leaders and officials together and providing targeted coaching and other practical start-up support to other LGAs not directly covered by the programme. The exact modalities of this support will be developed as the scaling-up strategy is developed in the first year of the programme. / In addition to the design being cost-effective and efficient so that adoption of the approach is affordable, the programme will also support learning both within and beyond the programme. In addition to regular programme reviews and creating opportunities for LGA staff to take part in the fieldwork, the programme will do targeted outreach work with to GoN and other programmes. This work will go further than communicating the programme approach and support other agencies and programmes to adapt and re-engineer the approach to their circumstances. It will also ensure sustainability of the programme after it’s end. / 4. Alternative approaches and rationale for choosing this approach / Alternative approaches to delivering the same outputs were considered, based on different design principles. Community empowerment could be pursued by focusing on single issues, e.g. providing a pre-determined package of interventions in health, education and water or building the capacity of intermediaries rather than working directly with communities. Girls’ voice could be increased through scholarships, cash transfers or through tackling wider issues such as working on legislation against early marriage and its enforcement. Service provision could be improved through a comprehensive local government reform and improvement programme or targeted training of LGA staff. / Some of these activities are being pursued through other programmes. Legal reform and media and communications to enhance the status of women are being pursued through DFID’s national Voices for Change programme (in design), and reform within some line ministries is being done through the existing State Level programmes. / In order to become fully empowered communities and the people within them, especially girls, need to build up three types of assets: social and political assets, skills and knowledge, and economic assets (Kabeer N, 2000). The other approaches were rejected as not doing enough to build up all three types of assets. Cash transfers alone do not create social and political assets, nor do they directly lead to an increase in skills and knowledge. Educational scholarships, also do not explicitly build girls social assets, nor help girls accumulate their own economic assets. In addition, due to the lack of educational infrastructure, access to schooling in Nigeria is limited and of poor quality – therefore immediate benefits can be minimised. / The chosen approach builds all three categories of assets – both for communities as a whole and for marginalised and excluded groups within the community, among which adolescent girls have been singled out for particular attention / There is medium evidence from a global body of adolescent girls’ programmes that use the girl platforms approach – including rural, socially conservative, and/or Muslim settings – that girl platforms are not only possible, but they have also successfully increased girls self-esteem, shifted gender norms, improved communication with parents, increased girls’ decision making, increased girls’ financial literacy and access to money, increased literacy and helped girls return to school, delayed the age of child marriage, and increased use of family planning among married girls (Population Council n.d). / Current DFID-N programmes (i.e. ESSPIN, PATHS2, PRINN-MCH, GEP) have not been able to achieve what girl platforms have the potential to achieve due to their design and implementation. For instance, whilst the introduction of the Student Tutoring, Mentoring and Counselling (STUMEC) programme (under GEP) and the establishment of SBMCs (under ESSPIN and GEP) have succeeded in mobilising women for the education of the girl-child, these programmes did not specifically address issues affecting the adolescent girl. Unless an explicit attempt is made to reach vulnerable adolescent girls, experience has shown that they do not benefit from sector programming because girls are often inaccessible. While the intent may be that girls, among many others, will benefit, without explicitly creating space and asset building opportunities for girls, the benefits are captured by men, boys, and perhaps women (Bruce, J. 2007). Because girls lack structures in which they are allowed to meet, learn, develop friendships and have their own mentors and advocates, general education, health, or government programmes do not include them. Girls are not at the same starting point as other community members, therefore a programme design that does not aim to alter that will continue to leave girls behind. / Appraisal of options / The differences between the options lie on two dimensions. First, scale and speed of intervention: smaller-scale and incremental vs. larger-scale and rapid. Second, working with communities without providing funds for development investments (software only) vs. providing small-scale grant funding of development schemes. / The intensity of staffing per community and girls’ group is the same in all the options. It has been based on experience of working with communities and girls’ groups elsewhere. Reducing staffing below what has been proposed would dilute the amount of contact time with communities to the point at which impact would be threatened. / Taking these two dimensions, there are 4 options, summarised below: / Option Title Description / 1 6 States, rapid implementation, 6 LGAs per State Geographically extensive with immediate implementation in 6 LGAs in 6 states (Kaduna, Kano, Jigawa, Katsina, Zamfara, Yobe). 30 communities per LGA, 6 LGAs per State, 6 States. This would entail working in over 1000 communities, and with a population directly targeted of over 2.5 million. / 2 3 States, phased, 3 LGAs per State Work in 3 states where there are existing DFID programmes (Kaduna, Kano and Jigawa) and in 3 LGAs in each State, making a total of 9 LGAs. Begin work in 10 communities in each LGA expanding to cover an additional 20 over the life of the programme, making 30 communities per LGA, 90 communities per State, and 270 communities overall. This option would directly target 650,000 people, of whom at least 30,000 would be adolescent girls. Within each LGA where the programme is working, roughly 1/3rd of the population will be targeted for intensive fieldwork and participatory planning. In addition indirect benefits would accrue to the population of the 3 states – an additional 18milion people. / 3 3 States, phased with conditional grants As in Option 2, plus grant funding for development programmes in communities along the lines of the MDG/CGS to enable participatory planning, implementation and accountability mechanisms to be trialled and developed. / 4 Do nothing No investment of DFID resources / Summary of implementation options / Feature Option 1 Option 2 Option 3 / Coverage 6 States / 36 LGAs / 1080 communities / 2.2m direct beneficiaries / 7m beneficiaries in total in target LGAs / 175,000 adolescent girls reached / Spend per capita £6 3 States / 9 LGAs / 270 communities / 650,000 direct beneficiaries / 1.7m beneficiaries in total in target LGAs / 30,000 adolescent girls / £10 per capita spending 3 States / 9 LGAs / 270 communities / 650,000 direct beneficiaries / 1.7m beneficiaries in total / 30,000 adolescent girls / £11 per capita spending / Phasing All 36 LGAs targeted within first 2 years. Establish presence in all 9 LGAs in year 1, and commence work in 10 communities in each LGA, expanding to cover 30 communities per State by end of programme. As for option 2. / Source of funding for development investments Existing sources available from MDG/CGS programme, and from state or LGA levels and possibly from CSOs or NGOs. As option 1. Programme funded conditional grants, drawing on approach used by Conditional Grant Scheme for LGAs of MDG Office. / Key features of the approach 1. Community based participatory planning / Participation, linking communities to outside sources of support (MDG/Conditional Grant Scheme). / 2. Establishing girls’ platforms. / 3. Work with service providers and other DFID programmes where possible to strengthen service provision. / 4. Working with, and through, NGOs, CSOs and CBOs. As for option 1. As for option 1. / and / Provision of small grants to communities (up to £7k per community) for development works identified by community. / * MDG Office LGA CGS baseline/needs assessment has identified in each state the 9 LGAs which have the greatest deficiency in service delivery provision in relation to education, health and water. Year 1 (FY 2011) of the CGS will target 3 LGAs in each state (selected by Governors from the list of 9); thus leaving 6 priority LGAs in each state either to be supported by M4M and/or future interventions from the MDG Office’s CGS. / Features common to all options / For all the options, the bulk of programme activity would take place within Local Government Areas (LGAs). Each LGA will have a programme office from which fieldwork would be organised and where staff would be based. Each LGA will have a Community Development and Outreach Team (CDOT) responsible for the community development work. Dedicated staff will be responsible for the work of outreach to adolescent girls. One of these LGA offices will house the State-level coordination office. Selection of LGAs will be based on a combination of need and logistical simplicity. / This is a necessary change from the current pattern of DFID state level programmes, which are located in the state headquarters and have state level government offices as their primary programme partners. The primary GoN programme partners will be at LGA level. Also, as the bulk of the programme activity will be taking place within villages/communities, it is important for both logistical and political reasons that the programme team is as close as possible to the communities and to GoN at LGA level. / Option 1: Large Scale Coverage – six States / 6 States / 36 LGAs / 1,080 communities / 2.2m direct beneficiaries / 7m beneficiaries in total in target LGAs / 175,000 adolescent girls reached / Spend per capita £6 / Under this approach, the programme would establish an early presence in all 6 states (Jigawa, Kaduna, Kano, Katsina, Zamfara and Yobe). In each state, the target number of LGAs would be 6, giving a total of 36 LGAs - 22% of the total in the 6 states. The population in the 36 LGAs that would benefit either directly or indirectly from the programme would be ≈ 7.0m. The programme would work with a minimum of 30 communities in each LGA (a mixture of urban, peri-urban and rural). / The Community Development and Outreach Team (CDOT) will be recruited from within the state, and ideally be familiar with the LGAs the programme is working in. Contact people will be identified within each community, drawn both from traditional structures of leadership and also from marginalised and under-represented groups. Steps will be taken to ensure the diagnosis and planning work is not dominated by a narrow range of interest groups. / The first year of the programme will be spent mobilising staff, establishing programme offices in the LGAs, and selecting the communities the programme will work with. From the 2nd year fieldwork will begin in earnest. / Each community will receive 2 years of support from the programme. Each CDOT will be responsible for supporting up to 10 communities a year. The first year of inputs to a community form the CDOT will be the most intensive. It will be during the first year that the capacity is developed among the community through participatory training and workshops. Participatory diagnosis and design work is done, plans drawn up and agreed and information about GoN duties and responsibilities gathered and shared with the community. After an intensive year of inputs, the first “wave” of 10 communities would graduate to a scaled-back level of on-going support from the CDOT and an additional “wave” of another 10 communities would be brought into the programme in year 3. In year 4 an additional 10 communities would be brought in and provided with 2 years’ of inputs. / The girls’ platforms work will target the three most vulnerable segments of girls in these communities: 10-14 year old out-of-school, unmarried girls who are at risk of early marriage and have few skills and social networks, 10-14 year old girls in primary school who are at risk of school drop out between primary and junior secondary school, and 12-17 year old married girls who are socially isolated, have little mobility, and are likely to have recently given birth or to become pregnant in the near future. The girls will be identified by the programme staff and mentors going house to house to locate the appropriate girls. / In each community the programme will work with from 3 to 6 groups of up to 20 girls. Each girl’s group will have 2 years of intensive inputs and then the group will “graduate”. Additional girls who will have then reached the age at which they could benefit from the approach will join a new group. So there will 3 cohorts of girls receiving inputs from the programme in the “first wave” communities that the programme starts work in straight away, the “2nd and 3rd wave” communities will have 2 and 1 cohorts respectively. The rural communities will be smaller and the number of groups formed there will be smaller. The urban and peri-urban communities will be larger and there may be more girls groups formed in these communities. In option 1 Up to 175,000 adolescent girls could directly benefit from the programme. / Option 2: Three States / 3 States / 9 LGAs / 270 communities / 650,000 direct beneficiaries / 1.7m beneficiaries in total in target LGAs / 30,000 adolescent girls / £10 per capita spending / This option will take the same approach as option 1 but would work in 3 States (Kaduna, Kano and Jigawa) and in 3 LGAs in each State. / As in option 1, each LGA would have a Community Development and Outreach Team. This team would be staffed so as to be able to provide intensive support to up to 10 communities each year. After a year of intensive work, each community would have less intensive follow-up support. The phasing in each LGA and State would be the same as in option 1, with 30 communities in each LGA being covered by the programme. / Each LGA will have a programme office staffed by a team leader and a Community Development and Outreach Team. Field staff will be recruited from the State and ideally the LGA where possible. In addition to the field staff the programme will enlist mentors and motivators from communities themselves, who will be the regular point of contact between the programme and the communities being worked with. The approach will ensure that under-represented groups have full access and representation to in the community empowerment and planning work. The work with adolescent girls will follow the same approach as in option 1. / Option 3: Three States plus conditional grants / 3 States / 9 LGAs / 270 communities / 650,000 direct beneficiaries / 1.7m beneficiaries in total / 30,000 adolescent girls / £11 per capita spending / In this option the scale of activity will be the same as in Option 2 with the extra facility of a grant funding mechanism. Each participating LGA will have access to a budget which would be available to fund the priority investments or other development activities prioritised by communities only after following a participatory and inclusive planning process, which includes meaningful representation and voices of women and adolescent girls. This representation can include, but is not limited to, mentors participating in community forums – bringing with them the expressed needs and desires of the girls they mentor in the girls platform groups. / The grant funding mechanism made available to communities would be analogous to the MDG Office Conditional Grant Scheme. Proposals that emerge from the planning process at community level would be screened for the degree to which they respond to the needs of the poorer sections of the community and marginalised or excluded groups. / Each LGA will have an allocation of £200,000 from the grant scheme. LGAs can access this grant on the following conditions: / Evidence that the prioritised needs have been identified following a community based participatory planning process which includes meaningful representation and voices of women and adolescent girls. At a minimum this will include the direct inclusion of mentors in the community planning process. / The LGA makes a contribution towards the costs. / A commitment from LGA to meet initial and ongoing recurrent costs (staffing, maintenance and consumables). SPARC is currently developing an approach to supporting LGAs to improve planning and budgeting at LGA level in line with the MDG office selected pilot LGAs. / Adoption of the standard monitoring and reporting of physical and financial progress / Adoption of transparent procurement, contract supervision and monitoring arrangements in line with the Implementation Manual. / Where it is possible and feasible, the community contributes towards the scheme, either in cash or kind. Care will be taken to ensure that the community contributions, particularly if it is labour and time, are not only provided by the poorer and more marginalised members of the community. / Option 4: Do nothing / Under this option, no additional DFID resources would be allocated for community empowerment, for capacity strengthening in Government agencies, NGOs, CSOs and CBOs and for the creation of additional service delivery capacity. / The current trend would remain unaltered. The MDG Office LGA CGS would continue to work with an additional 3 LGAs per state per year with the likelihood that the community-based participatory processes would struggle to be embedded in such a short period of active support. By not investing funds in girls’ platforms, the status quo for adolescent girls in Northern Nigeria will remain: a significant number of girls will not complete primary school, early marriage will continue with almost half of girls will be married by the age of 15, leading to early childbearing, increased labour complications, less healthy children, and limited economic productivity. / Impact Appraisal / What needs to change / For matters to improve there needs to be a change in the political culture and the performance of government. The government needs to become more accountable and responsive to its citizens. And citizens need to be more aware of the responsibilities of the state towards them, and more demanding of their rights. / The aim of this programme is to contribute, in a modest way and at a local level to this change by demonstrating that where communities and local government meet it is possible to reshape the relationship between the Nigerian state and its citizens. / The programme will focus on the LGA level of government and its relationship with communities. This is where there is most direct contact between citizens and the state. The Local Government Area (LGA) is the 1st tier of government and sits below the State. In the 3 States the programme will work in (Kano, Kaduna and Jigawa) there are 94 LGAs. The total population is 20 million and the LGA populations range from 77,000 to nearly 600,000. The mean LGA population is 210,000. LGAs are weak. They are the most junior level of government. Underfunding and weak management has left them with little autonomy or authority to develop and implement programmes on their own. In contrast to Government, Civil Society Organisations (CSOs) are relatively thriving. Many are led by Civil Servants or ex-civil servants. In the three States the programme will be covering the CSOs are among the more vibrant in Northern Nigeria (SAVI 2009). However, there are important differences between the three states. Kaduna has more active NGO/CSOs than Jigawa. / Given the poor state of government services and the weakness of the LGA communities often take matters into their own hands. Schools have been built and equipped by communities themselves, leaving the Government to provide the teachers. And many communities have their own indigenous social and economic support systems. Some of which are specific to women: adashe is a rotating credit scheme, and biki is a reciprocal gift relationship between two women. Men are also involved in have collaborative relationships, but these tend to be in more public fora and affect activity beyond the household, where most women’s collaborative activity is confined (Abdulwahid, S. 2005). / The principal programme instrument to shift this perception will be through the use of participatory community-based problem diagnosis and design of interventions to overcome problems. By demonstrating a more participatory, transparent and rights and evidence-based approach to community development the programme will raise the expectations of communities and show LGA staff an alternative approach to working with communities that does not depend on feeding and maintaining a relationship of patronage. The programme will also recognise that demonstration alone does not induce change. Alternative channels for change using media, new technologies and other parts of government will be targeted to ensure that there is a broad set of options that citizens can pursue to strengthen accountability. / Conflict sensitivity / The programme has been designed to be conflict sensitive. During the implementation phase, planning will include an explicit focus on working with different stakeholders to recognise and manage for the potential political, economic and social impacts of proposed programme interventions. Ensuring that the mechanisms created within the M4M programme to bring different stakeholders together to plan provide adequate opportunity to address these different impacts is important. The facilitation support this programme will provide for communities, LGAs and CBOs will include conflict sensitivity training. / In directly tackling social and economic exclusion and by focusing on the weak performance and accountability of government and other service providers, this programme will have an impact on mitigating conflict. It will take a longer-term perspective by working ‘upstream’ in order to support the institutional foundations essential for managing conflict. The programme will also address the ‘continuing failure of the political and economic systems to meet peoples’ basic needs’. The programme is designed to support the emergence of structures of accountability. These will not only enable community groups to have more say in determining their own development, but provide a more systematic way for Local Government to respond to the direct needs and development priorities of communities. / The project will also draw on advice from the Nigeria Stability and Reconstruction Fund (NSRF) which has just come on stream. The NSRF aims to support and develop systems towards preventing conflicts becoming violent, provide a rapid response once violence has broken out, and promote reconciliation in the aftermath. It aims to help transform conflict prone areas into more stable environments where wealth creation, service delivery and poverty reduction can take place. / Tackling social exclusion and marginalisation / Patronage networks formed along ethnic and family lines strongly determine access to resources. Because of this, ethnic and family ties are prioritised over citizenship rights, creating the basis for social exclusion based on ethnic identity, gender or “indigeneity”. However, the situation is complex, and each state has patterns of social exclusion where are particular to the social and political history and complexion of the state. For example, in ethnically homogeneous states ties of kinship will be more important than say religion in determining access to resources. And in States that are more religiously homogeneously inclined, gender relations and politics will play a different role than in states where are more heterogeneous. In some states, the combined impact of gender relations and gender-biased interpretation of faith is particularly severe, deeply constraining women’s access to services and assets, their voice in the household, their ability to organise and have voice in communities. In contrast in some states, relative homogeneity, ethnicity and indigeneity are not significant drivers of exclusion. An example of an exception to this is the Fulani, who, through their nomadic livelihoods, face much greater challenges in accessing health and education services, as well as ensuring grazing rights (Hughes, C. et al 2008). / The key dimensions of social exclusion are: / Ethnicity and indigeneity: ‘Non-indigenes’ of a state face barriers in accessing services, encounter discrimination in employment, particularly in the civil service and, as a result of patronage-based systems for land allocation, struggle to own land. ‘Non-indigenes’ in political office are the exception rather than the rule. To cope with this discrimination, ‘non-indigenes’ tend to rely on their own ethnic networks, such as home and trade associations, for resources and assistance. / Gender relations: In the public sphere, gender stereotypes and lower female educational attainment limit women’s employment opportunities. Women’s CSOs represent one of the few channels for women’s voices. These however tend to be led by urban elites. / Religion: The impact of religion on access to services is both positive and negative. As service providers, religious organisations increase access to services. However, they also shape perceptions of what is considered appropriate services, closing down routes to other services as a result. Although religious organisations may be a major form of association in Nigeria, they may not always give voice to their members, and particularly not to all of their members. / Disability: Low social expectations of people with disabilities make households, communities and governments reluctant to invest in them, constraining access to services and assets such as employment. Public attitudes towards people with disabilities, combined with low educational attainment are significant barriers to the emergence of strong disabled people’s organisations able to influence policy and practice. / HIV status and high risk behaviours: People living with HIV/AIDS and groups at high risk of HIV infection are perceived as violating social norms and are castigated. If anonymity cannot be maintained, accessing public services can be risky. / Place of residence: Service provision and formal employment is biased towards urban centres. Residence in rural communities automatically constrains one’s access to basic services and employment, although access to land may be more plentiful. Whilst considerable numbers of CBOs are reported to exist in rural locations, few of these facilitate community mobilisation and voice. / Age: as family networks become over-stretched, there are reports of some members (children, the elderly), who are seen to bring few benefits to the family, being disenfranchised and sometimes abandoned. Such family members rarely have any voice in the household and communities are reluctant to take on additional responsibilities. / The programme will operate at village level so as to overcome these obstacles and barriers to social inclusion. / Particular efforts will be made to overcome the exclusion women and girls. Girls and women are particularly vulnerable to poverty and exclusion, especially in the States where this programme will be operating. Women and girls are regarded as subordinate to men. They have fewer rights over property. Their incomes are lower and they have less autonomy over decisions such as whether to seek health care or attend school. Men even decide whether women have access to maternal health care: a third of 15-19 year olds in Northern Nigeria have given birth without the help of a health professional, traditional birth attendant or even a friend or relative (Waterhouse, R. 2009). / The situation of adolescent girls is particularly bad: early marriage to older men (41% are married before age 15), early childbearing (women are expected to give birth within the first year of marriage), and little formal schooling (1/3rd of girls aged 10-19 have never attended school) together serve to reproduce the low status of girls and women leading to poor maternal and child health and the continued inter-generational transmission of poverty. Girls have little or no voice or mobility. They can rarely gather with other girls their age and have little say in critical issues such as whether to go to school or when to get married. Furthermore, on marriage women join their husband’s families, where they are even more isolated. The community structures that do exist do not include girls and do not include representatives (male and female) that advocate on behalf of girls. / This programme will tackle these interlocking problems: the low status of women and girls and marginalised groups, their exclusion from public live and development work, and the weak performance and accountability of government and other service providers. The work with girls’ platforms has been specifically designed to tackle the immediate practical obstacles women and girls face and also deliver the longer-term strategic change in their status. / The principal focus will be on building the capacity of poor people to have greater control over their own development and supporting them to have a greater say in how services are managed. Particular efforts will be focused on adolescent girls as achieving changes in this group have the potential to scale up impact and ensure impact of the programme is sustainable. By halting the reproduction of the low status and social exclusion of girls and women by focusing on adolescent girls, many of the underlying causes of poverty and social exclusion will be eliminated. / Moving beyond the community / Because the programme will be working directly with communities to diagnose their problems and design and deliver solutions to them we can expect a wide range of issues and possible interventions to emerge from the consultative process. For example for many poor people in Northern Nigeria an immediate concern is the slender basis of their livelihood and the difficulty of increasing their income in the short-term. These issues often interact with some of the other issues that the programme will be tackling. For example, the low status of women and in particular that of adolescent girls leads to them leaving school early to take part in hawking and trading to supplement household income while their mothers are required to stay in seclusion, which in turns leads to low-education levels among girls and in the longer-term to lower incomes for women. Breaking this cycle of the short-term pursuit of income at the expense of longer-term investment will need sensitive handling. So creative ways to preserve and grow household income will need to be developed if the longer-term opportunities for girls are to be improved. / In addition to supporting the direct delivery of services, the programme will address community needs for changes in the regulatory and policy environment by working with other programmes (both DFID programmes and other donors). The programme will have the opportunity to identify the obstacles and opportunities to increase incomes. Some of the obstacles will be local: e.g. small-scale infrastructure to improve market access and reduce transport costs; technology to help exchange market information. Other obstacles may be at State or National level. For example, subsidies serving to reduce the supply of essential inputs such as fertilizer in a form and scale at which poor people can buy them. / The programme will document these examples of how to have an impact on incomes and advocate for change at the State and national level. The programme will have available funding managed by the DFID contractor to facilitate or directly pay for analytical studies, information gathering and advocacy activities to tackle the policy and institutional obstacles and constraints that poor communities face. / The programme design consists of three interlocking components at field level that will together contribute towards shifting the political culture towards a “tipping point” and tackle some of the entrenched causes of social exclusion. In summary, they are: / Working with disadvantaged and marginalised groups to develop their capacity to engage in discussions about development and make their voices heard / Working with communities to empower them to solve their development problems and engage more effectively with service providers, particularly government / Providing Resources for small-scale development investments in the community. / Impact on climate change and environment / The programme overall will not have a significant additional impact on the environment or climate. However, the participatory diagnosis and problem solving done at community level may generate ideas to mitigate the impact on communities of environmental degradation or climate change. These proposals cannot be specified in advance as they will emerge from the planning process. / In the table below the quality of evidence for each option is rated as either A, strong, B, partial, C, limited or D, no evidence of the likely impact on climate change and environment as categorised as A, high potential risk / opportunity, B, medium / manageable potential risk / opportunity, C, low / no risk / opportunity, or D, core funding to a multilateral organisation. / Option Evidence rating Climate change and environment category / 1 C C / 2 C C / 3 C C / 4 C C / Theory of change / How will this programme deliver change? / The outcome of this programme is for government policy makers to be more accountable and responsive to citizens. The underlying theory is that in order for this to happen two things need to happen. First, citizens need to have greater capacity to understand their development needs, identify solutions that will meet their needs and enlist the support of government and other service providers in meeting them. This is empowerment. And it puts on the table what the state must respond to. / Second, the state and other service providers need to be more responsive and accountable to citizens needs. If this is to happen the state and government needs to move away from regarding citizens as powerless clients whose political support can be enlisted with periodic acts of patronage to regarding them as the people to whom they should be most accountable and responsive. This is accountability. / This should not simply be citizens compiling a wish list and presenting it to government in the expectation that it will be largely met. It needs to go further and contribute to transforming the relationship between citizens and the state and contributing to a change in the political culture, particularly at the local level. These principles underpinning this relationship should be that citizens have rights, states have responsibilities and that both citizens and the state are seen as having mutual obligations and responsibilities towards each other. / Furthermore, in order for the state to respond to all people, the heterogeneity of communities and the diverse needs of different people should to be recognised and acted on. Not everyone’s needs are the same. And different people need different types of support to enable them to participate and be empowered. Women need an approach that specifically meets their needs, and among women, adolescent girls, are a particularly important yet vulnerable and hard to reach group requiring special attention. / Enabling poor people – including poor women - to have more say in policies and the distribution of resources in the short-term can increase poor people’s access to services and resources. It can also help longer-term transformation and help eliminate more entrenched discrimination against poor people. / The evidence that external donor-funded programmes can on their own increase people’s empowerment and make governments more accountable is limited. However, one clear message is that different contexts require different approaches to donor engagement, and engagement that pays insufficient attention to context can have negative impacts. Systematic monitoring and evaluation needs to be done to find out what works and why. / Essential elements in increasing empowerment and accountability / There are three essential elements to increasing the empowerment of poor people: / Increasing their access to livelihood assets and services; / Building the ability of poor and excluded people to exercise voice, influence and agency (being able to do what they want to do); and / Changing the “rules of the game”, which refer to the formal and informal policies and institutions and conventions that mediate and regulate people’s participation, choices and options? / It is important not to assume homogeneity in the groups of poor people being empowered. A village may have a greater say, but to the advantage of only some of its inhabitants. A household may be empowered, but to the advantage of only some of its members. And women are not a homogeneous group either. What works to the benefit of adult women may not be to the benefit of adolescent girls. / Change needs to occur in all three to have sustainable impact. For example, providing food or cash for work may increase assets temporarily. But unless and until poor people can claim their rights to education and decent work, there will be no sustainable improvement in livelihoods, people will not be empowered and exclusion will remain. Processes to increase assets and access to services; to increase voice, influence and agency; and to change the rules of the game are all interlocking. Meaningful and sustainable change in each domain is unlikely to happen without change in the other domains, and change in one domain generally follows from change in other domains. / This programme will operate in all three areas. Poor people’s assets will be built up through a programme of participatory diagnosis and appraisal of their needs. Support will be provided to meet some of those needs. They will also be given help to have their voice heard outside the community and to approach government for help fulfilling other needs. The third area – changing the rules of the game - will also be tackled. Within the village particular marginalised groups will be given particular attention, in particular adolescent girls. Achieving changes in this group have the potential to scale up impact and ensure impact of the programme is sustainable. By identifying and possibly changing some of the “rules of the game” – e.g. early marriage and childbirth, rules of seclusion and fewer rights over property and personal autonomy – that lead to the continued low status and social exclusion of girls and women, many of the underlying causes of poverty and social exclusion will be eliminated. / Alongside working with communities and the marginalised groups within them the programme will also work with government to prepare them to be more responsive to needs. LGA staff will be involved in the participatory community-based fieldwork to demonstrate to them the benefits of an approach that puts the community at the centre of development efforts. The strategy for replication and scaling up incorporated a multi-stranded approach to spreading the approach. There will be active coaching and visits to other LGAs. The Governors’ forum will be used to advertise best practice and the experience of the programme. Media, including new media will be used to spread ideas. Traditional figures and structures of authority, such as Emirs and religious leaders will be encouraged and supported to become advocates for the programme approach. / Links will also be made to other programmes that are working within government to spread understanding of the approach and identify opportunities to scale up and expand the approach. The MDG/CGS office will be a key programme partner. So too will the other DFID state level programmes.
C. Appraisal of options / For each of the three options below, the total costs of each option equal (a) the running and capital costs of the programme-, state-, LGA-, and community-level activities – personnel, non-personnel, and one-time capital costs – plus (b) in Option 3 only, the cost of the LGA matching grants (a one-time £200,000 conditional grant per LGA). The number of LGA interventions is set for each option – 36, 9, and 9 for Options 1 through 3, respectively. The assumption is that for each Option, the programme will be present in each state, and each LGA, for 4 years. The estimated number of direct and indirect beneficiaries and communities is set out below: / Table 2.1: Estimated beneficiaries and communities / Option 1 Option 2 Option 3 / Direct - general 2,232,000 657,000 657,000 / of which – at least adolescent girls 175,000 30,000 30,000 / Indirect 4,800,000 1,113,000 1,113,000 / Total 7,032,000 1,770,000 1,770,000 / Communities 1,080 270 270 / Option 1: 6 States, 6 LGAs per State / Costs: Option 1 provides M4M activities in the greatest number of LGAs (36), communities (1,080) and direct beneficiaries (2.23 million). Indicative costs of the various components of HQ, state- and local-level operations suggest that Option 1 would incur costs per beneficiary (direct and indirect) of £6. / Benefits: The major benefit of this option is its coverage in terms of numbers of states, LGAs, communities and population. Such an immediate and visible presence provides for greater political support, wider access to the programme and the potential for achieving a critical scale of operations necessary to demonstrate replication. / Risks: However, this relatively large coverage highlights the quality-quantity trade-off among the three options: Option 1 seeks to extend the programme to as many places (LGAs and communities) as possible, but it offers less senior supervision of the field work than Options 2 or 3 – senior quality control staff would be stretched very thin, in particular the national and state level staff. M4M offers several multi-dimensional target activities – citizen demand for the variety of public services represented in the MDGs, plus the clearly much less clearly articulated recipient demand for the adolescent girls’ (and perhaps women’s) activities, and the admittedly uncertain acceptance by community leaders of women and girls’ participation. In addition, the programme would be operating alone in states where DFID does not have state level programmes, and the opportunity for synergy with DFID programmes would be missing in at least half the programme area. / Moreover, the management of such a programme could prove quite challenging, especially with such a variety of activities under a single programme within several states and numerous LGAs and communities. Also, given the uncertainties around the availability of appropriately skilled community mobilisers, and the untested capability of CSOs/CBOs to engage effectively, there is a greater risk of the programme failing to gain a foothold. The larger concern here is a perhaps broad failure of many individual interventions at the local level as a result of insufficient time and effort at the level of individual communities within the selected LGAs. / With such potential uncertainties, the overall payoff of the M4M intervention in a relatively large number of LGAs and individual communities might be quite low. / Option 2: 3 States, 3 LGAs per state / Coverage would be a total of 3 states and 9 LGAs with a direct population of 630,000, located in 270 communities. Indicative costs suggest that Option 2 would incur costs per beneficiary (direct and indirect) of £10. / Benefits: Overall, Option 2 offers more careful implementation at the individual community and LGA level, greater flexibility to respond to emerging implementation problems that may endanger success in the more challenging communities, and significantly greater time for lesson-learning that can improve future implementation as M4M expands. Moreover, this more intensively supervised (and more flexible) effort should enable programme management both to absorb the developing lessons learned that may save invaluable time (and avoid costly errors) as coverage extends. This slower and phased approach will enable the available skilled community mobilisers to focus their efforts and thereby help them gain experience of these new processes. / Risks: This reduced geographical coverage runs the risk of the programme being seen as small islands of success where progress is being achieved only through intensive, external support. The reduced number of LGAs per participating state represents only 10% of the total LGAs and 7% of the total population. Consequently the small scale of the proposed intervention may not prove to be sufficiently persuasive as to its replicability and adoption state-wide. Involvement with too few LGAs is likely to reduce the potential ‘spillover’ effects into neighbouring LGAs. / A major assumption underlying this option is the expectation that improved community planning will lead to government reallocating budgets to these articulated, prioritised needs. However, a constant disclaimer from LGAs is that funds are limited and there is insufficient flexibility to re-allocate budgets other than on a small scale. Consequently, in the absence of some predictable funding, the programme runs the risk of falling short if community plans are not funded, thereby undermining the credibility of communities in the empowerment process. / Option 3: 3 States, 3 LGAs per state with matching Conditional Grants / Costs: Option 3 would costs the same as Option 2 (for the same coverage) with the addition of a £200,000 conditional grant for each of the 9 LGAs. Indicative costs suggest that Option 3 would incur costs per beneficiary (direct and indirect) of £11, a marginal increase of £1 per capita on the unit costs of Option 2. / Benefits: The conditional grant constitutes a net addition beyond the overall local community-oriented support. It would be provided on a matching basis with an equivalent additional amount being funded jointly by direct state and LGA contributions. This facility could significantly ease the pressure on communities and LGAs to identify suitable sources of additional funding for their proposed community programmes – perhaps crucially helping launch them into the opportunity offered by M4M when they might otherwise be blocked at the very beginning due to the lack of resources. / Risks: Although the available matching funds might indeed stimulate local communities to a greater and more successful recruitment of non-local resources for matching purposes, some of those communities might largely give up in their search for non-local resources once the 50/50 incentive money is no longer available. There is the related risk that this DFID funding would displace government budget allocations. / Option 4: Do nothing / Option 4, the counterfactual, is the continuation of the current situation. This includes the continued general lack of community-level voice regarding expression of local preferences for locally-needed public services, and the traditional limitations on the life options of adolescent girls and women. / Foregone opportunities include forming links with other DFID State Level Programmes and using their insights and networks to promote more accountable and responsive government form the supply side of government. An opportunity to enhance the status and life chances of adolescent girls will have been missed – a particularly urgent need in Northern Nigeria. / Cost-benefit analysis (CBA) / On the basis of this appraisal, we recommend option 3 (phased approach with a focus on 3 States and 3 LGAs per State with conditional grants). This option has been evaluated further through a detailed cost benefit analysis which is summarised below. The appropriate parts of the economic appraisal (EA) annex should be consulted if further information is required. / Outcome level benefits / In order to derive measurable outcome level benefits for the CBA, two broad types of benefits have been defined. Based on the logic in the theory of change, these benefits predict changes, albeit very modest, in how state level governments spend public funds. Such data does not exist at LGA level hence why the analysis only focuses on state expenditure: / Benefit 1 - allocative efficiency: this is about an improvement in government expenditure on locally important public services (LIPS), such as education, health, water and sanitation and feeder roads as a result of community level pressure. It is defined as ‘allocative efficiency’ as the government is shifting funding away from less productive services and allocating to those that will have higher welfare impacts on citizens in response to public demand. / Benefit 2 - technical or operating efficiency: this second type of benefit is about reducing wastage and improving the efficiency in state level government spending. It is assumed that community pressure on how much public funds are spent on LIPS will also generate a wider drive to see less wastage and better use of funds across government as a whole, including non- locally important public services (non-LIPS). / A differentiation is made between: / Benefit 2a: technical efficiency improvements to LIPS related expenditure, evident in better quality or lower cost delivery of the same services and / Benefit 2b: technical efficiency improvements to non-LIPS expenditure that result in more efficient use of funds in non-LIPS areas. / Assumptions / The cost-benefit analysis rely on the following assumptions: / Scale of government spending response / Benefit 1 - leads to 2% reallocation of State Government capital development spending (SGCD) towards LIPS (only this source of State spending can be used as it is the only type of expenditure that is broken down by sector. It typically comprises less than 50% of total State Government spending) / Benefit 2a - leads to 1% efficiency improvement of SGCD spending on LIPS / Benefit 2b - leads to 0.25% efficiency improvement of SGCD spending on non- LIPS. / Longevity of benefits / Predicting the duration of benefits post-implementation is inherently difficult for this programme. However, given the strong focus on replication and institution building, it is estimated that the overall benefits should last for as long as the 6 year programme itself. There are too many uncertainties to make prediction beyond this time-frame. Thus the total programme cycle considered covers 12 years. / Evolution of benefits over 12 years / Over each state’s 4 year implementation, benefits are expected to reach 20% in year 1, 50% in year 2, 80% in year 3 and 100% in year 4. This progression is typical of a learning curve effect. Over the following 6 years, these benefits are predicted to diminish by 10% per annum. This is based on a deliberately pessimistic scenario that there could be some capacity related limitations after DFID exits, e.g organisational and human resources issues, or funding challenges, leading to a progressive reduction in benefits (see p 9 of the EA annex for more details). / What the cost-benefit analysis results show / Under the extreme assumption, that there are no post-programme benefits, the net present value (NPV) at the end of the programme (year 6) would be negative. This means that the UK taxpayer, who is the ultimate investor, would find that the costs exceed the benefits, making the programme a poor investment. In NPV terms, there would be a loss in return on DFID’s investment if all benefits end after year 6. / Four years after each state’s implementation, there is a good positive NPV or a 20.6% net return. / Six years after each state’s implementation, there is a significantly positive NPV or a 50.5% net return. / In other words, even with assumed reduction in benefits after the programme’s end, it generates good net economic returns beyond the 4 years after its completion. It should also be noted that one of the reasons that annual benefits continue to increase after year 6 is because of projections of 12% growth in real government spending (these are based on future projections of government spending growth in the 3 states based on 2004-09 relative to inflation projections provided by the Central Bank of Nigeria for 2012-17). / Table 2.4: Breakdown of number of girls covered across the programme over 6 years (based on low end estimate of girls reached) / Type of LGA Coverage across Years (number of girls) Total coverage per state after 6 years Total coverage across 3 states / 1 2 3 4 5 6 / Urban 476 476 952 952 1429 1429 5714 17143 / Peri-urban 238 238 476 476 714 714 2857 8571 / Rural 238 238 238 238 238 238 1429 4286 / Total coverage in each year 952 952 1667 1667 2381 2381 10000 30, 000 / Illustration of the potential benefits of Girls’ Platforms / There does not appear to be any cost-benefit analysis on girls’ platforms/safe spaces that can be used to generate estimates of likely rates of return. Typically, interventions tend to run for many years and on a sufficient scale to generate data that can be used for CBA. Safe spaces are a relatively new and small scale intervention so it is not surprising that CBA estimates cannot be identified. / Thus, in the absence of robust data about the economic benefits of safe spaces, secondary school education is used as a proxy for the type of benefits that may arise from girls’ platforms. This is a logical approximation, as these platforms are expected to be at least as effective as 2 years of secondary school in providing girls with skills and knowledge that they themselves believe will benefit them. Potential benefits include: / An extra year of secondary school on average boosts a girl’s income by 15-20% (World Bank 2002). / The returns on investment to secondary schooling for girls is 18% compared with 14% for boys (R Levine, CB Lloyd et al 2009) / Girls with more schooling participate in greater numbers in the labour force and earn more for their families and themselves (ibid) / For every year of schooling, infant mortality declines by 5-10% (T Schultz 1993). / D. Comparison of options / We therefore recommend option 3 (phased approach with a focus on 3 States and 3 LGAs per State with conditional grants) as the recommended option. / The same weighting is used as for CSC above. The score ranges from 1-5, where 1 is low contribution and 5 is high contribution, based on the relative contribution to the success of the intervention / Outcome and impact Option 1: 6 states, 6 LGAs per state Option 2: 3 states, 3 LGAs per state Option 3: 3 states, 3 LGAs per state + grants / CSC Weight Score Weighted score Score Weighted score Score Weighted score / 1 5 2 10 3 15 5 25 / 2 4 2 8 3 12 4 16 / 3 5 1 5 3 15 4 20 / 4 4 1 4 5 20 4 16 / 5 2 3 6 3 6 3 6 / 6 5 4 20 3 15 4 20 / 7 5 5 25 3 15 3 15 / Total 78 98 118
E. Measures to be used or developed to assess value for money / Value for money (VfM) is about obtaining the maximum benefit over time with the resources available. It is about achieving the right local balance between economy, efficiency, and effectiveness. In DFID terms, it is about: / -cost control in the use of resources (economy), / -spending in a way that delivers the greatest outputs (efficiency) and / -delivering outputs which achieve the greatest outcome and impact (effectiveness). / VfM at the Outcome level / Measuring VfM at the outcome is about judging the effectiveness in delivering the expected results of the programme. The economic appraisal of the programme concludes that Option 3 provides net economic benefits in terms of positive rates of return arising from the improved ‘allocative’ and ‘technical’ efficiency of state government capital development spending. The estimated allocative efficiency gains arise from the shift in capital development spending to higher return, locally important public services as determined by the communities. The technical efficiency gains are expected to arise from the greater public interest in the delivery of services and the resulting pressure on service providers “to do more with less”. / The economic appraisal shows that the programme benefits exceed its costs (this is what is meant by ‘positive net economic benefits’). It also shows that the rate of return on UK taxpayer money is just over 25% within 4 years of the programme’s end. This rate of return improves significantly where the benefits are assessed over a longer period. We conclude that the programme represents good value for money. / The challenge during programme implementation, however, will be to gather the financial data to confirm this initial economic appraisal through reference to actual spending data. The extent to which this might be possible will need to be explored in more detail. It may prove to be unrealistic to update the economic appraisal due to data limitations. / A complementary, albeit, subjective assessment of programme effectiveness in achieving more accountable and responsive service providers might be through the use of perception studies. Respondents, both citizens and providers, might be asked for their views on what positive changes in behaviour have occurred, whether these improvements have been worth their efforts in participating (thereby helping to inform a view on effectiveness) and whether these results have been achieved in the most productive way (thereby informing a view on efficiency) . The use and design of perception surveys will be given strong consideration during the detailed design of the monitoring strategy and plan. / VfM at the output level / In the design, assumptions have been made about the choice of delivery mechanisms without an informed understanding of the relative cost efficiencies of alternative engagement modalities. To address this issue efficiency measures, linked to indicators or proxies for productivity, will need to be defined from the outset. For instance, staff/’client’ ratios may prove a useful indicator of productivity. The number of community groups and girls’ platforms per field worker in different states, and in different types of LGAs, may provide some benchmarks against which VfM can be assessed. / Both inter- and intra-state actual cost comparisons of delivery, especially where different approaches are being tested, will provide useful guidance on alternative cost models. The collection of comparative costs per unit supported (such as cost per community group or cost per girls’ platform) across locations and over time will provide the basic information on cost comparisons. The challenge will be then to link these costs with some measure of ‘productivity,’ such as the number of times a community group has influenced the decisions made by a LGA. This may be over ambitious at this stage but further thinking will be needed to try and help answer the question “does spending this amount of programme funds, in this way, lead to the best results?” / VfM at the activity/ input level / The VfM focus here is with economy and assessing whether costs have been minimised. There are two dimensions that will need to be explored during implementation. Firstly, there is the development of unit costs. In terms of procurement, in relation to consultancy services and minor capital works, a comparison with prevailing market prices charged for these services can be used. In terms of implementation, unit costs of completing ‘packages’ of activities will need to be compiled to enable cost comparisons to be made between different delivery mechanisms. For example, the cost of deploying CSO/CBO field workers to work with community groups will be compared with alternative models. These options might include programme staff carrying out the fieldwork or training up existing community development staff within government. Another way to approach this is to compare these unit costs with any data that is available about the costs incurred by other projects that have undertaken similar interventions, either in Nigeria or in other developing countries. / Secondly there is the establishment of reasonable cost ratios and in particular administration-to-programme cost ratios. The balance of programme spending on administrative functions compared with ‘client’ focused activities will need to be kept under scrutiny both for the whole programme as well as for discrete packages of activities. More detailed costings will need to be completed to ensure that overheads are minimised and, where possible, semi-fixed costs (such as accommodation costs) are subject to regular challenge and review. / The procurement of this programme will be done in such a way as to ensure that all costs are justified on the basis of economy, efficiency and effectiveness.
[7] A rights-based approach to development is one that adheres to the three principles of participation, inclusion and obligation.

3. Management Case

A. Oversight / The primary stakeholders in the programme are the community groups and groups of adolescent girls who will be targeted for support. The Government’s community development staff (from state as well as LGA levels) will be ‘recruited’ into the programme’s activities to help ensure the transfer of skills from the service provider. Similarly, the CSO/CBO structures and their workers will be brought into the programme both as partners and also to enable them to carry out the fieldwork under the supervision of programme staff. Strengthening civil society structures will be both an objective in itself and a means through communities are empowered and service providers enabled. Ideally, over time, the CSOs should be able to provide an effective ‘bridge’ between the communities and the service providers as well as offering a useful resource for both parties. / The programme will work with the existing community structures and processes including religious and traditional structures. Over time it will seek out ways to bring the presently diverse and fragmented representation into some form of standardised and semi-formal consultative group or community council. This forum will be designed to strengthen the horizontal communication at the community level and to start to present a more united front in the community groups’ interaction with government and with service providers. / The secondary stakeholders include the staff working at the LGA as well as the councillors, including the Chairperson and the political heads of the respective sector portfolios such as health and education. At state government level, the senior staff and managers of the relevant ministries, departments and agencies will have an interest in the programme and their continued support will be vital. The key organisations will be the state ministries of Women’s Affairs, Rural and Community Development, and the key MDG ministries plus the State Universal Basic Education Board (SUBEB). / Prior to mobilising programme resources in any of the states, there will be preliminary discussions with the respective Governor and advisors to help gauge the level of commitment for the programme and to seek active support from the political leadership. Early engagement with the Governors will help to bring the state administration into the management arrangements; the exact form will need to be worked out in conjunction with states and in line with other oversight structures that exist for the SLPs. The experience of operating other SLPs in each state will be considered and especially deriving the key lessons learned from the start up period of each of the SLPs. SAVI’s experience of the CSO arena will be valuable. Similarly the experience of the MDG Office in each state, derived from implementing both the state and LGA CGS, will contribute to DFID’s planning for M4M engagement. / The programme’s principal link to the activities in each LGA will be through its contact with the LGA Committee on the Implementation of CGS programmes (or its equivalent) and the nominated focal person appointed by the MDG Office at Federal level. The exact modus operandi between the programme and this Committee will need to be worked out in the first months after mobilisation and respective roles and responsibilities negotiated. How community groups interact with this Committee and other parts of the LGA will need to be elaborated through bilateral discussions facilitated by the programme staff presents in each LGA. / In addition to the LGA level governance arrangements, there will need to be similar arrangements at the state level. This will involve the programme’s state team leader engaging with the State Committee on the Implementation of CGS programmes via the state focal person working in the CGS programme support unit. / The M4M state team leader will participate in the regular meetings of DFID’s state level programme managers based in the respective states. Figure 5.1 below depicts the proposed governance and oversight arrangements. / DFID Nigeria / M4M HQ / Kano / Kano State Office / Kaduna State Office / Community groups and Girls’ Platforms / LGA Offices / x 3 / LGAs x 3 / LGA Offices / x 3 / LGAs x 3 / LGA Offices / x 3 / CSOs/CBOs / CGS Implement- ation Committee / CGS Implementa-tion Committee / Consultative forum/ community council / DFID SLP managers’ / meetings / Figure 5.1: Oversight and governance / Jigawa State Office
B. Management arrangements / Management processes and structure within DFID / The lead advisor will be the Governance Advisor based in Kano who will work with the full range of advisory staff in Kano including the Girl Hub Advisor. The Programme Officer will be from the Governance and Social Development Team based in Abuja. / Programme management / Initially, following mobilisation, the DFID programme management team will meet with the M4M national programme manager to review progress and provide support and guidance on any major issues arising. The frequency of these meetings will become less as the programme establishes a sound foothold and as progress becomes more evident. DFID will commission an independent annual review with a more extensive review scheduled for the latter half of Year 2 to help inform the roll out into the third state in Year 3 and to assess the overall performance of the contracted service providers prior to DFID’s consideration of a contract extension beyond the end of Year 3.
C. Conditionality / Not applicable, as the programme does not involve financial aid to government.
D. Monitoring and evaluation / The programme is ambitious and complex with its emphasis on changing competencies, behaviours and relationships. This demands that a strong monitoring and evaluation (M&E) strategy is designed in detail and established early on during the programme’s inception phase. Strong monitoring and evaluation processes are required due to the size of the programme and the evidence base around some aspects of the programme (e.g. causal relationships and theory of change linking increased voice and accountability to MDG impacts). There are a number of key issues which need to be considered carefully, particularly in the monitoring and evaluation of interventions that address issues of governance, voice and accountability and empowerment. Up to £500,000 will be set aside for the purposes of an in depth independent evaluation. / The programme monitoring and evaluation will address two broad primary purposes: / internal programme management and learning; and, / accountability to a number of different stakeholders (including local communities and citizens, government at all levels, and DFID). / M&E management / M&E will be fully integrated and managed within the programme, with an external agent providing support on quality assurance, reviews and evaluations as appropriate and needed. Overall responsibility for monitoring and evaluation will lie within the programme management team. A Monitoring and Evaluation Coordinator will be recruited to the programme’s head office. A number of options will be assessed to ensure independence including steering committees, peer reviews and reference groups. / Four to five key evaluation questions will be identified in the ToRs for contracting the service provider. Potential bidders will be asked to present options on how programme design and evaluation tools could be used to answer these key evaluation questions. / The detailed monitoring and evaluation strategy will be developed during the inception phase alongside other detailed planning and design activities. At a time when other issues will be demanding prioritisation, sufficient time and resources will need to be put into this process to avoid M&E becoming an afterthought, with the resulting “retrofitting” of a framework to an already finalised programme design (or even a programme which is already being implemented). The programme management will be accountable for the final design and, following DFID Nigeria approval, implementation of the strategy. / A key principle relevant to this programme is that the monitoring and evaluation strategy will adopt a participatory approach as far as possible and appropriate. Broad stakeholder ownership of the monitoring and evaluation strategy is important if it is to be accepted and implemented effectively. This means that the final M&E approach and framework will need to be designed through a participatory and consultative process which includes as many stakeholders (including those at community and LGA level) as possible. This will be done through a more localised exercise and include establishing a baseline and appropriate targets and milestones for each indicator in conjunction with a range of stakeholders (including those at the LGA level) to ensure they are contextualised as far as possible and appropriate. / Programme design and logic / Empowerment and increasing voice and accountability (as part of a process to improve governance) are aims in themselves; but they are also expected to lead to improved development outcomes as expressed in the MDGs (O’Neill, T. et al 2007, Holland, J. & Thirkell, A. 2009). The theory of change behind this is outlined in detail in the Appraisal Case. / The evidence supporting this theory of change in Nigeria is generally medium (see Appraisal case) and a rigorous monitoring strategy and evaluation plan are required. However the nature of programmes which aim to increase voice, accountability and empowerment means that the results are often difficult to measure and not easily quantifiable; simple results chains or theories of logic are too linear to reflect complex realities; and standardised indicators may not reflect very different contexts within which programmes operate. A combination of both quantifiable and more qualitative indicators that enable an assessment of progress and process is needed, including more contextually specific indicators. / Interventions designed to contribute to empowerment, voice and accountability may well result in unexpected events and outcomes, both negative and positive, which cannot be foreseen and included within a logical framework. The types of indicator in the logframe may also not capture dimensions of empowerment most important to different groups of citizens themselves. The programme monitoring and evaluation strategy will take these issues into account and include methods to monitor and evaluate these e.g. through Most Significant Change stories (Third World Relief Fund 2010, MandE news n.d.) to provide robust evidence of programme outputs, outcomes and impact. / Communities in Northern Nigeria are not homogenous. Even within broad social groups (e.g. “women” or from a particular ethnic group), some people are more marginalised, vulnerable and/or excluded than others. The programme aims to increase the voice of and accountability towards groups that are currently marginalised and excluded. The data for monitoring and evaluation will therefore be disaggregated sufficiently to pick up differences within broad social groupings but without requiring disproportionate additional resources or time from either the programme and/or citizens. / Monitoring strategy / The business case has been developed using a thorough assessment of the available data and appropriate evidence. However, it is clear that availability of robust data is a challenge in Nigeria. The programme will be required to collect primary data and where relevant use primary data collected from other DFID/donor programmes. / The programme will be subject to a DFID annual review process and will include two independent reviews led by external experts. These reviews will be conducted at the programme mid-point and at the end of the programme (these may be combined with DFID annual reviews). / Regular monitoring will collect a range of data relevant to the programme management and the demonstration of results at different levels of the logframe. This will include the monitoring of indicators in the logframe at appropriate intervals together with more routine administrative and financial data relevant to both programme management and assessing “value for money”. / Responsibility for monitoring will be within the programme management, with a small core team at programme office level supporting the State- and LGA- level teams to implement the monitoring strategy. The programme team will be required to complete much of the baseline information during the programme inception phase and allocate sufficient resources to collecting monitoring data on a regular basis. The intervals for collecting monitoring data will vary depending on the indicator and purpose, and will be determined during the inception phase. / The programme is a new venture for DFID Nigeria because it will work at a sub-State level to increase citizens’ voice and responsiveness of LGAs. Some potentially relevant data is available at either national or state level from various sources (e.g. Core Welfare Indicator Questionnaire (CWIQ); and Citizen Perception Survey). National level surveys may not also provide data in appropriate timeframes for the programme monitoring. The monitoring strategy will require data relevant to the sub-State level and the current availability of data at the LGA level is generally low. Where it is available, the quality is variable. Some data is disaggregated at a local level by the Ministry of Health and the MDG Office, but this is not common. / Monitoring will use secondary data where available at LGA level through administrative records from LGAs and local service facilities (e.g. schools and health centres). Where this is not available or suitable, primary data will be collected. Where possible, the monitoring strategy will link with other programmes (e.g. SAVI, SPARC, ESSPIN, PATHS2 and the independent monitoring agent for the State Level Programmes) in order to create and build synergies in the monitoring strategies. The programme will also build links with national organisations (e.g. National Bureau of Statistics and the MDG Office) and civil society organisations. / Data availability and quality have influenced the choice of indicators; where data is collected primarily through secondary sources, it can also generally be triangulated against primary data if needed to ensure accurate measurement. / The programme will also use appropriately “low-tech” approaches to primary data collection that both provide useful and appropriate data for monitoring on a regular basis and also form part of an empowering approach in themselves. Two such approaches are Citizen Report Cards (CRC) and Community Score Cards. ESSPIN and PATHS2 are considering the use of CRC and the programme will explore the potential to collaborate and use these as a source of data as they may be working in the same LGAs as these two programmes. Community Scorecards are a more participatory, and potentially empowering, method, which combines quantitative data, qualitative data and a process of engagement between citizen and service providers. They involve a process that facilitates a dialogue between citizens and service providers to increase both voice and accountability. They have been adapted and used in a range of contexts and countries (MRWSP 2004; Thindwa, J. et al n.d.; Dedu, G. & Kajubi, G. 2005; Dani, A. & de Haan, A. Eds 2008) and the potential adaptation and use of these will be determined in the inception phase. / The monitoring strategy will include a process of internal review which focuses on an internal assessment progress and process, lessons learnt, and adapting and improving management. This will include the monitoring of assumptions and risks outlined in the logframe. These will be conducted on a six-monthly basis and will involve all internal programme stakeholders plus selected external stakeholders as appropriate. / Reporting, dissemination and feedback / Internally, a data management system will be established which enables the systematic management and analysis of data from all levels of programme monitoring. Internal feedback loops will be designed to ensure data and analysis are fed back to appropriate levels of the programme so as to maximise usefulness and enable changes programme course and approach if necessary. / The programme management team will submit quarterly summary reports to DFID documenting progress against the annual workplan and logframe. On an annual basis, a short report (maximum 20 pages) will be submitted to DFID outlining key achievements, progress against milestones and lessons learned. This will be based on data and information from regular monitoring activities, participatory monitoring at community level and the internal review process. / Dissemination of information and analysis derived from the elements will be undertaken in a systematic manner. The dissemination strategy will take into account the wide range of stakeholders involved, from local and national levels of government, programme implementers and partners, policy makers and citizens and include appropriate approaches for different audiences (e.g. policy makers and adolescent girls). / Evaluation plan / The size and medium evidence base of the programme mean that strong evaluation processes will be included alongside the monitoring strategy. The evaluations will also include expertise from government and civil society, including citizens in programme areas. The extent to which this is possible will be determined during the design of the evaluation and will be an explicit requirement of the ToRs for procurement of this programme. / An organisation or consortium of organisations will be commissioned through open tendering after a pre-qualification and short listing process. DFID Nigeria and the programme management team will review these together. / The evaluations will be undertaken in line with DAC (and other relevant criteria) and focus on relevance, effectiveness, efficiency, impact and sustainability. They will also assess the potential for replication and/or scaling up. This means a focus on all levels of the logframe, from inputs through to impact. In assessing impact, the evaluations will need to establish the link between increased voice, accountability and empowerment (including for those currently most marginalised) and improved development outcomes as measured through the MDGs. / Assessing impact – i.e. the positive and negative, primary and secondary long-term effects produced by the programme, either directly or indirectly, intended or unintended[8] – is an important element within the evaluations. In assessing impact, the evaluations will need to establish the link between increased voice, accountability and empowerment (including for those currently most marginalised) and improved development outcomes as measured through the MDGs. Data on the indicators at impact level will be gathered through administrative data from facilities and services in the project area where possible and supplemented by programme collected data where this is not possible. The appropriate use of controls to evaluate impact (e.g. by comparing programme LGAs with data from similar facilities/services in non-programme LGAs) will be considered fully during the inception phase so that relevant baselines are established and monitoring of appropriate data can occur. / The use of controls in assessing impacts could involve either an experimental (e.g. through randomised control trials – RCT) or quasi-experimental design. DFID Nigeria’s evaluation action plan includes commissioning at least four randomised control trials over four years and J-PAL has offered to support the assessment of programme impact through a randomised control trial approach. / RCTs are essentially a sub-set of impact assessments and have the benefit of providing statistically identical comparison groups and unbiased results, which increases confidence in causal relationships. RCTs have been used to assess impacts in programmes focussing on empowerment, voice and accountability but there are debates regarding the appropriateness of doing so (GSDRC 2011, Towards 4+5 2010, -Pal 2011a & b). A number of theoretical, practical and ethical issues will be considered to assess whether RCTs are appropriate for this programme. / The merits of this approach and the appropriate use of controls to conduct an impact assessment (e.g. by comparing programme LGAs with data from similar facilities / services in non-programme LGAs) will be considered fully during the inception phase so that relevant baselines are established and monitoring of appropriate data can occur. The extent to which the evaluation can exploit a phased implementation to learn about the impact of the programme will also be examined. The programme management will need to satisfy itself that appropriate quality controls and ethical assessments are undertaken in any evaluation and that if an RCT approach is used it will not have negative impacts on the objectives of the programme and/or citizens.
E. Risk assessment / The programme is medium risk. Table 5.1 below details the main risks and the proposed mitigation strategies. Fiduciary risk is low since all programme funds will be managed by the contracted service provider and indirect procurement by LGAs (for spending of the conditional grants) will be monitored closely. / Table 5.1: Risk assessment and mitigation / Risk Probability[9] Impact Mitigation Probability[10] Impact / Implementation risk / [1] Communities not supportive of participatory planning processes , resist the involvement of women and girls in the programme resulting in continued male dominance 2 3 Initial communication strategy to sensitise potential participating communities to the objectives of the programme and its processes. Communities’ selection informed by their confirmed support of the inclusive approach / M4M will use the inception phase to mount intensive awareness-raising campaigns to beneficiary communities on benefits of M4M / Programme also works with existing DFID’s SLPs which have developed and implemented successful participatory planning process / M4M to work actively with respected organisations in the communities (eg FOMWAN) 1 3 / [2] Partnerships / between CSOs, FBOs, NGOs and Government do not work resulting in the lack of overall capacity for implementation of programme 2 3 M4M advocates to governments on need for Government-CSO Partnerships / M4M uses existing DFID’s SLPs (eg., ESSPIN) methodology to establish CSO-Government Partnership frameworks / M4M initiates relationship improvement activities to build trust and confidence in the partnership 1 2 / [3] Individual LGA may not be interested or engaged fully in the implementation of the programme 2 2 Initial discussions with political leadership in the state, informed by political economy analysis, will target receptive LGAs / Linking efforts with SLP activities in a LGA will provide a more visible presence / The programme will take the pool of 9 LGAs identified by the MDG office as a starting point based on assumption that a level of political commitment from the MDG office, State Governors and LGA Chairmen will already have been reached. 1 2 / [4] Synergies between M4M and SLPs fail to materialise resulting in limited broadening and deepening of community engagement 2 2 M4M programme management in each state will be included within DFID’s state oversight arrangements and its MoU with Governors / Regular meetings of SLP managers to agree scope for joint working 1 2 / Political risks / [5] National elections in 2015 will, at best, slow down implementation and might, at worst , undermine the relationship between community groups and government structures 2 2 More empowered community groups will be able to reach more informed judgements during the electioneering process / Better dissemination of key information will increase the transparency of the political process 1 2 / [6] State Governments not supporting/ implementing decentralisation reform and not keen on replication of good practices 2 3 Programme to engage in both high-level advocacy (to senior state policy makers) and continuous awareness-raising and advocacy (at LGA level) on importance of making LGAs functional and having financial responsibilities / Regular communication to promote successes and benefits of combined M4M/ESSPIN/PATHS/SPARC approach in the participating states 1 2 / [7] Significant resistance of traditional and religious leaders to the processes and/or content of the programme 2 3 A series of bilateral discussions by DFID and programme staff with key leaders to explain the programme and to seek support. Endeavour to involve the leaders in the process through the consultative mechanisms / Use of existing goodwill relationships established by other DFID-supported programmes (GEP, ESSPIN, PPRINN) to engage leaders / Strong communication and advocacy efforts to disseminate (via media) the content of the programme and to report on progress made and the views of participating communities 1 3 / [8] Freedom of Information Act is implemented partially and reluctantly by LGAs 2 2 MDG / CGS for LGAs will make available baseline data on needs / Involvement of the media to heighten the pressure on LGAs to comply 1 2 / Resourcing risks / [9] Continuing weak capacity of CSOs and CBOs and their inability to become effective partners in the programme 3 3 Mapping and realistic assessment of CSO/CBO capabilities during Inception. / Implementation of a strengthening programme with those organisations assessed as key for M4M implementation 2 2 / [10] Insufficient number of LGA- technically competent staff and vested interests in LG bureaucracy slow programme implementation 3 2 Programme facilitates the establishment of CSO-LGA Partnership for mutual learning process and exchange of knowledge and ideas / M4M organises Training of Trainer (TOT)workshops to develop the competences of both groups / Programme develops continuous advocacy strategy highlighting essence and advantages of collaborative efforts to develop the LG system 2 2 / [11] Limited availability of sufficient number of competent programme staff slows programme implementation 3 2 Bidding processes encourages service providers to form links with widest networks within and outside Nigeria. 2 2 / [12] Federal Government fails to accelerate achievement of MDGs through the Countdown Strategy and limited effectiveness of MDG / CGS for LGAs 2 2 M4M implementation will provide a more intensive programme of support to help demonstrate the effectiveness and benefits of the MDG / CGS 1 2 / [13] GoN support to key MDG sectors does not continue post 2015 1 2 Dissemination of the success stories and lessons learned from M4M and MDG / CGS will provide the evidence for continued GoN targeted support 1 2 / [14] Participating state governments fail to increase spending and improve budget outcomes in key MDG sectors 2 2 Continued support by SPARC and other SLPs to strengthen the MTSS process will improve the allocation of budgets 1 2 / Commercial risks / [15] Procurement process fails to identify a suitable service provider, or that performance does not meet requirements 2 3 Wide advertisement and networking. / Pre-bid meetings, presentations from bidders that focus deeply on delivery quality. / Pro-active monitoring. 1 1 / [16] Commercial management by LGAs does not purchase cost efficient and timely services 3 2 Commercial appraisal and if necessary capacity support, monitoring and support to LGAs. / If serious problems and no improvements, ask service provider to make payments 2 1 / Impact-Probability Risk Matrix / Figure 5.2 below shows the impact-probability matrix for the risk assessment of the programme post mitigation. It illustrates that the programme is medium risk. / Figure 5.2: Impact-probability Risk Matrix / Impact → High [1], [7] / Medium [2], [3], [4], [5], [6], [8], [12], [13], [14] [9], [10], [11] / Low [15] [16] / Low Medium High / Probability →
F. Results and benefits management / The expected results include: / Up to 270 communities (involving a population of 630,000) will be more capable of planning and taking control of their own development, more able to tackle issues around social exclusion, to increase social accountability, to demand better services from government and to hold government to account. / Up to 30,000 adolescent girls will have their awareness raised, self-confidence developed and be actively involved in planning for their futures / 9 LGAs will be more responsive to the needs of their communities and be more accountable for their actions through using structured fora for engagement which are informed by greater freedom of information. / Performance in delivering these benefits will be managed through the programme’s monitoring strategy, measuring the achievement of the targets detailed in the logical framework and the annual review mechanism.
[8] Based on definition of impact in: DFID (2008) ‘(Draft) Policy statements on impact evaluation—September version.’ Internal Draft.
[9] Pre-mitigation where 1 = low probability/impact, 2 = medium and 3 = high.
[10] Post-mitigation

  1. References

Abdulwahid, S. 2005:	‘Gender Differences in Mobilization for Collective Action: Case Studies of Villages in Northern Nigeria.’ Paper presented at International Research Workshop on ‘Gender and Collective Action’ October 17-21, 2005, Chiang Mai, Thailand.
Adediran, Sulleiman & Bawa, Mohammed 2010:
 Visioning Processes for Community Participation in the design of state-specific School-Based Management (SBM) Policy in five ESSPIN-supported states: ww.esspin.org/index.php/resources/download/220/ESSPIN 413/School Based Management Committee Report No. 6
Adamu, F. n.d.	Analysis of household bargaining theory, poverty and gender dynamics in Hausa society of northern Nigeria.
Baldwin, W. 2011:	Creating “safe spaces” for adolescent girls, Population Council Brief, No 39.
Bruce, J. 2007:	Reaching The Girls Left Behind: Targeting Adolescent Programming for Equity, Social Inclusion, Health, and Poverty Alleviation. Paper Prepared for meeting on Financing Gender Equality; a Commonwealth Perspective, Commonwealth Women‘s Affairs Ministers' Meeting, Uganda, June 2007. http://www.popcouncil.org/pdfs/Bruce2007_ Commonwealth_FullText.pdf
COMPASS n.d.:	Community Participation for Action in the Social Sector. http://pf5.convio.net/site/PageServer
Cracknell, B. 2000:	Evaluating Development Aid. Sage Publications, UK.
Dani A & de Haan A (Eds) 2008:	Inclusive States: Social Policy and Structural Inequalities. World Bank
Dedu, G. & Kajubi, G. 2005:	The Community Score Card Process in Gambia. SD Note No. 100/ March 2005. World Bank.
Derbyshire, H. et al 2010:	‘Review of DFID Nigeria focus on voice and accountability’. Unpublished report for DFID. November 2010 by Derbyshire, H., Gimba, D., Methven, S., and Nwankwo, C.
Drivers of Change 2005:	Drivers of Change study of Nigeria, report for DFID.
Erdmann, G. & Engel, U. 2006:	Neopatrimonialism Revisited – beyond a catch-all concept. German Institute of Global and Area Studies, Working Paper No 16.
ESSPIN 2011a:	‘Community Engagement in School Improvement and Learner Participation – Early Impact,” ESSPIN Report 042, May 2011.
ESSPIN 2011b:	‘Conditional Cash Transfers – A Ray of Hope’. Available from ESSPIN website: http://www.esspin.org/index.php/resources/case_studies/14
Evans, S.H. & Clarke, P. 2011:	‘Disseminating Orphan Innovations’, Stanford Social Innovation Review, Winter 2011. http://www.ssireview.org/articles/entry/disseminating_orphan_innovations/.
Gaventa et al 2011:	Blurring the Boundaries: Citizen Action Across States and Societies, The Development Research Centre on Citizenship, Participation and Accountability. www.drc-citizenship.org/pages/synthesis-papers.
Gaventa, J. & Mayo, M. 2009:	“Spanning Citizenship Spaces through Transnational Coalitions: The Case of the Global Campaign for Education,” IDS Working Paper 327, Institute for Development Studies, Brighton.
GSDRC 2011:	Governance and Social Development Helpdesk Research Report: RCTs for empowerment and accountability programmes.
Governors’ Forum n.d.	http://www.nggovernorsforum.org/
Holland, J. & Thirkell, A. 2009:	Measuring Change and Results in Voice and Accountability Work. Working Paper 34. DFID
Hughes, C. et al 2008:	Social Exclusion and Gender Inequality Assessment for Nigeria, report prepared for DFID, October 2008.
Imam, A. 1993:	If You Won’t Do These Things For Me , I Won’t Do Seclusion For You: Local and Regional Constructions of Seclusion Ideologies and Practices in Kano, Northern Nigeria, D.Phil. Thesis, Department of Anthropology, University of Sussex
Jones, N. Harper, C. & Watson, R. 2010:	Stemming girls’ chronic poverty – catalysing development change by building just social institutions, Chronic Poverty Research Centre.
Joseph, R.A. 1987:	Democracy and Prebendal Politics in Nigeria: The Rise and Fall of the Second Republic, Cambridge University Press.
J-PAL 2011a:	Introduction to J-PAL’s Governance Initiative and Executive Summary of the White Paper, see: http://www.povertyactionlab.org
J-PAL 2011b:	White Paper: J-PAL Governance Initiative, see: http://www.povertyactionlab.org
Kabeer, N. 2000:	Resources, agency, achievement: reflections on the measurement of women’s empowerment. Paper presented at the conference “Power, Resources and Culture in a Gender Perspective: Towards a Dialogue Between Gender Research and Development Practice” Uppsala 26-27 October, 2000.
Lasiele, Y. A. 1999:	‘Women Empowerment in Nigeria: Problems, Prospects and Implications for Counselling,’ The Counsellor, 17 (1), August, 1999.
Lawal, T. & Oladunjoye, A. 2010:	‘Local Government, Corruption and Democracy in Nigeria’, Journal of Sustainable Development in Africa Volume 12, No. 5, 2010.
Levine, R, Lloyd CB et al, 2009:	Girls Count - a global investment and action agenda
LUPP 2006:	Luanda Urban Poverty Project Evaluation Report.
MandE News n.d.	Most Significant Change, http://bit.ly/l6wEKG
MRWSP 2004:	Operational Manual for Implementing the Community Scorecard process: Maharashtra Rural Water Supply & Sanitation “Jalswarajya” Programme. 2004. Available at: http://bit.ly/lkXAca
MDG/CGS 2009:	MDGs Conditional Grants Scheme, Implementation Manual, Published by the Office of the Senior Special Assistant to the President on MDGs.
MDG 2010:	Nigeria: Millennium Development Goals (MDGs), countdown strategy 2010-2015. Published by the office of the Special Assistant to the President on MDGs.
MDG/CGS n.d.	MDG/CGS website: http://www.mdgs.gov.ng/
Menkiti, A. & Babatunde, K. 2008:	Giant Strides of EGBENN. Uprooting the Challenges of Girls’ Education in Northern Nigeria. ActionAid, Nigeria.
Mkandawire, T. 2001:	‘Thinking about developmental states in Africa’, Cambridge Journal of Economics, May 2001, 25: 289-313.
Mohanty, R. 2007:	‘Gendered Subjects, the State and Participatory Spaces: The Politics of Domesticating Participation in Rural India’, in Cornwall, A & Coelho, V.S. ed 2007: Spaces for Change? The Politics of Participation in New Democratic Arenas, London: Zed Books.
O’Neill, T. et al 2007:	Evaluation of Citizens’ Voice and Accountability: Review of the Literature and Donor Approaches. DFID.
Population Council n.d.	www.popcouncil.org, in particular pages on girls’ platforms in Kenya and Uganda (Safe and Smart Savings Products for Vulnerable Adolescent Girls), Ethiopia (Biruh Tesfa and Berhane Hewan), Egpyt (Ishraq), South Africa (Siyakha Nentsha), Guatemala (Abriendo Opportunidades), Ghana (Smart Girls).
REVINN 2011:	Religion, exclusion and violence in northern Nigeria. Report by Sarah Ladbury for DFID Nigiera.
Sahara Reporters 2011:	‘FOI Act: Four States Asked To Release Primary Education Spending Documents’, Sahara Reporters, Posted 12 June 2011, http://bit.ly/mlEKMb.
SAVI 2009:	Project reports on State Drivers of Change (S-DOC), State 2009.
SPARC, SAVI & PATHS2 2010:	Perceptions of Service Delivery and Governance in Five States, 2010.Utomi, P. et al 2007a:	The political economy of reform: the case of Nigeria 2003-2007, Policy Practice Brief No 3. www.thepolicypractice.com
Schultz, T 1993:	Mortality decline in the low income world: causes and consequences
Thindwa. J, et al n.d.	Community Based Performance Monitoring (CBPM): Empowering and Giving Voice to Local Communities. World Bank.
Third World Relief Fund 2010:	Most Significant Change: Monitoring empowerment for the right to health.
Towards 4+5 2010:	Ethical challenges in cluster randomised controlled trials, Towards 4+5 Briefing Paper No 6.
Utomi, P. et al 2007b:	Nigeria: The Political Economy of Reform – Strengthening the incentives for economic growth, The Policy Practice, www.thepolicypractice.com
Waterhouse, R. 2009:	‘Gender and Social Inclusion Study’, Overview Report, State Accountability and Voice Initiative (SAVI), Unpublished Project Report, October 2009.
World Bank 2008:	Project Appraisal Document (PAD), Community and Social Development Project, June 2, 2008, World Bank Report No: 41634-NG.
World Bank n.d.	From shouting to counting: a new frontier in social development. World Bank. http://bit.ly/mHevnK
World Bank 2002:	Policy Research Paper 881

 ‘