Annual Review - Summary Sheet

Title: Governance Partnership Facility (GPF)
Programme Value: £4.5 million for phase 2 (out of a maximum programme envelope of £19 million)		Review Date: 20/09/2016
Programme Code: 202854	Start Date: Oct 2012	End Date: Dec 2018

Summary of Programme Performance
Year		2013	2014	2015	2016
Programme Score		A	A	A	A
Risk Rating		High	High	High	High

Summary of progress and lessons learnt since last review
This review covers the period between October 2015 and September 2016 in ongoing implementation of phase 2 of the Governance Partnership Facility (GPF) programme. The partnership between the Bank and DFID, facilitated through the GPF, is demonstrating the benefits of shared policy priority areas in Nigeria. This is ensuring that we can increase our collective impact on supporting the Government of Nigeria use its resources to attain economic and social development. GPF 2 was designed to provide additional benefits for DFID and it is starting to demonstrate this.

As planned, actitivies focussed on embedding the tools developed in phase 1 and emphasis was put on ensuring that analytical work (including lessons learned) was mobilised to not only improve the preparation and closing of projects but throughout the project management cycle. Activities also informed the preparation of a first round of Bank projects for the North-East (in the areas of health, education, social protection and agriculture) (for a total amount of over USD 575 million). They aimed also at leveraging system wide change, including to support the rolling out of social protection programmes by the Nigerian government.

The following GPF activities were pursued: 1) Operational support to project preparation and implementation was provided through innovative technical assistance to adaptable programming initiatives including setting rapid results pilots and multi-stakeholder coalition and collective leadership building around results; 2) technical assistance for system wide reforms such as the establishement of a Delivery Unit at the Presidency; 3) a Recovery and Peace Building Assessment for the North-East was completed in May 2016 and informed policy dialogue on reconstruction and the design of Bank, Government of Nigeria, United Nations, and donor planning and operations in the region; 4) policy dialogue and technical assistance was provided at state level to promote the generation of tax revenue; 5) technical assistance was provided to the federal government to strengthen the management of oil revenue (based on oil revenue modelling); and 6) the impact of conflicts on poverty in Nigeria was diagnosed so as to inform project design and policy dialogue on development challenges in Nigeria.

The following activities were completed: 1) The drafting of two discussion papers on successful Bank projects (multi-)state level operations (the EKO secondary education project in Lagos and FADAMA across the country) to help draw generic operational lessons relevant to project preparation and implementation; 2) a workshop on Internally Generated Revenue was organised in partnership with DFID and the Nigeria Governors’ Forum; 3) an assessment of the social impact of electricity tariffs reform to inform Bank projects in the power sector as well as policy dialogue with the federal government including for the preparation of substantial budget support.

Within the reporting period, three new activities have been initiated (poverty analysis in conflict areas, support to the management of social protection programmes, and the development of an implementation framework and action plan for recovery and peacebuilding activities in the North-East).

Summary of recommendations for the next year
- Continue to work closely with Federal and State Governments, UN, and donors on the operationalisation of the RPBA in the North-East.
- Continue the expansion of support to the implementation of the social protection programmes of the federal government.
- Continue to build on opportunities to systematically monitor the ‘doing development differently’ pilots in order to improve service delivery and foster institutional change in Nigeria.
- Explore opportunities for joint Bank and DFID real-time monitoring and learning.
- Further focus on state level governance reforms is needed due to the ongoing fiscal crisis.
- Maximise synergies between forthcoming Bank operations (budget support) at federal and state level (Programme for Results) and the new DFID public sector reform programme (the Partnership to Engage, Reform and Learn (PERL)).
- Constitute an Advisory/Steering Committee for the GPF to strengthen joint working on shared policy and programme areas.
- Review and adjust the programme logframe and VfM framework.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	5156319
DevTracker Link to Log frame:	4155695

Outline of the programme
The Governance Partnership Facility (GPF) in Nigeria was set up as a strategic partnership with the World Bank to pilot innovative programming approaches that were tailored to the Nigerian context and informed by evidenced based analysis for improved development outcomes. DFID funds have enabled the Bank to carry out political economy analysis, build up advisory capacity and pilot innovative projects. This work has enabled the Bank to better address governance constraints in sectors and thematic areas as well as to share good practice globally.

GPF phase 2 (from October 2015 – December 2017) provides an opportunity for DFID to continue to influence how the World Bank in Nigeria delivers the Country Partnership Strategy (CPS [2014-17]) and leverage the World Bank portfolio to enhance the effectiveness of DFID technical assistance. A review of the Bank’s performance under the previous CPS pointed to mixed results and an inability to address key governance constraints to delivery in sectors.[1] GPF 2 aims to support the World Bank to address governance constraints more directly. It aims to identify areas where there is reform traction at federal and state level and to support World Bank projects to effectively produce tangible outcomes that benefit the poor. It will also leverage DFID country programmes within World Bank operations (including on governance and public financial management (PFM), peace building, social protection and education).
[1] World Bank Nigeria Country Strategy 2014-17.

GPF 2 consolidates and builds on the gains of phase 1 by rolling out and embedding new approaches in World Bank’s ‘way of doing business’. To achieve this GPF 2 supports the World Bank to:

1. Improve development effectiveness by supporting the Bank to develop and implement projects that are informed and shaped by the political contexts;
2. Strengthen its engagement in Northern Nigeria to improve development outcomes by supporting the development and implementation of a strategy for the north; Increase its engagement in Northern Nigeria including influencing policy dialogue and portfolio design with a focus on peace building and reconstruction in the North-East; Improve its understanding of poverty drivers in conflict-affected areas.
3. Strengthen service delivery at federal and state level by supporting peer learning and exchange of experience at state level and intergovernmental coordination for social protection programmes implementation.

The World Bank approach to delivering governance is aligned to DFID Nigeria’s Business Plan (2016-2021) objective ‘to help the Nigerian Government to spend its own resources more effectively to reduce poverty’. This project provides opportunities for complementarity and peer learning as well as for synergising the two country programmes (World Bank lending operations and DFID technical assistance). The partnership will ensure that we can work on the same priorities to increase collective impact on supporting the Government of Nigeria use its resources to attain economic and social development. We will contribute to substantially guiding and collaborating with the Bank in implementing its over US$2 billion a year country programme in Nigeria.

Ministers originally approved funding in 2012 for the World Bank Nigeria Governance Partnership Facility Window up to a maximum of £19 million. The first phase of funding was for £6.7 million. In addition, USD$1.2 million was allocated in 2014 to the engagement from a previous GPF allocation to Nigeria. For the second phase DFID has provided a budget envelope of £4.5 million. Over the period under review, DFID has released a total of £2.4 million. This includes a disbursement of £1.5 million to meet ongoing activities and £900,000 for new actiivites (£200,000 for conflict and poverty analysis and £700,000 for social protection).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The outcome of the programme is ‘Improved development effectiveness of the Nigeria Country Partnership Strategy including strengthened engagement in Northern Nigeria and improved service delivery at state level’. One important output has been met: the completion of the Recovery and Peace Building Assessment (RPBA) for the North-East. This has informed a first set of five World Bank projects in the region for a total amount of over USD 500 m (with a sixth multi-sectoral operation of $200 million under preparation).

Overall output score and description
The programme has scored an A overall based on the individual output scores and their respective impact weightings. The outputs scored an A on the increased effectiveness (weighted 40%); an A for strengthened Bank Engagement in Northern Nigeria (weighted 40%), and A on effectiveness of service delivery (weighted 20%). The score also takes account of the successful integration of phase 1 initiatives such as application of the governance, conflict and gender filter and the improved generation and capture of lessons learned to inform programming within the Bank.

Key lessons
Improving investment in evidence: The programme’s theory of change is based on GPF influencing the ‘ways of working of the Bank to improve the development outcomes of its projects’ including by leveraging the DFID country programme. Given the relative small budget in comparison to the overall budget of the Bank attribution can be difficult. It will be important to have a robust system to capture evidence and show how GPF funds are making a difference across the board. But there is clear evidence that it has significantly contributed to strengthen and frame World Bank operational engagement in the North-East.

Key actions: The programme logframe should be revised to incorporate new activities initiated over the past year and make it clearer and easier to assess progress and to better reflect priority areas of GPF 2 work. Action: Review the logframe indicators and milestones after 6 months of implementation.

Has the logframe been updated since the last review?
No. As the project continues to evolve and new activities have been added, the logical framework will need to be reviewed. Action: New logframe to be submitted for approval in January 2017.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Enhanced development effectiveness of World Bank projects by addressing governance bottlenecks in sectors
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Progress against LF indicators

% of Bank projects provided with operational support either by the Governance, Conflict and Gender (GCG) filter or through the Adapative Learning pilot.
Target (2016)	Actual Progress
25%	Achieved: all projects under preparation over the year have been screened by the GCG filter and the implementation of two flagship projects was supported under the Adapative Learning pilot.

Analysis of critical factors influencing failure or success of interventions used to inform portfolio management including the programming of new operations
Target (2016)	Actual Progress
At least 3 retrospective studies prepared for selected closed or closing projects focussing on success and failure factors	Achieved: The Bank has published 2 additional case studies and lessons learned from the rolling out of the adaptive learning pilot has been documented by the Overseas Development Institute (ODI).[2]
[2] K. Bain, Doing Development Differently at the World Bank. Updating the Plumbing to Fit the Architecture., August 2016

Key Points and highlights
The Bank has mainstreamed across its lending operations support to its operational teams with innovative technical assistance to support ‘problem-driven iterative adaptation’ (PDIA) approaches. This requires: (1) a selective focus on issues with political traction, (2) a clear understanding of the local political economy, (3) a willingness to experiment, (4) well developed results-focussed monitoring and evaluation (M&E) systems, and (5) strong management systems to adapt the programme design according to lessons learned and the changing political context.

Three projects have been fully set up with PDIA processes (one of which was dropped - Staple Crops Processing Zone):

Save One Million Lives: Support is being provided to six states to pilot the State-level flexible facility to provide a network of delivery facilitators to support adaptation during implementation and was granted to the Federal level Ministry of Health for 100 day results exercises.
(see http://www.worldbank.org/projects/P146583?lang=en)
National Social Safety Net Project: Support is being been granted to the office of the Vice-President on the design of the governance and implementation framework for the social protection programmes initiated by the Government (see
(see http://www.worldbank.org/projects/P151488?lang=en)

To improve the use of evidence in programming, two additional retrospective case studies to capture operational lessons have been completed (EKO Secondary Education Project in Lagos state; FADAMA project in agriculture) and generic lessons have been drawn on the impact of the PDIA pilot in coordination with the ODI (see report noted above).

Support has also been provided to the Nigerian government to strengthen accountability mechanisms which will directly improve the effectiveness of World Bank projects: a mandate mapping was conducted for the Presidency Delivery Unit which focuses on social protection programmes; the self-assessment tool jointly developed by DFID and the World Bank for the Bureau of Public Service Reforms is being used by the World Bank to engage its counterparts (in education and health) on institutional effectiveness for service delivery.[3]
[3] The self-assessment tool has been given the African Public Service Excellence Award by the African Training and Research Centre in Administration and Development

Recommendations
- Focus increasingly on systemic changes to be leveraged by the World Bank portfolio: In addition to support to World Bank operational teams through the filter and the PDIA, there is a need to help strengthen government effectiveness beyond the Bank portfolio given the magnitude of the fiscal crisis in Nigeria. While this crisis will undermine the ability of the government to fund and implement its own development priorities this may present greater leverage to get reforms done.
- Pursue closer more focussed engagement with DFID to build on synergies with its new governance programme: The World Bank is preparing important operations at federal and state level on governance reforms which need to factor in DFID experience drawn from the extensive technical assistance it has provided under its previous governance programmes (Federal Public Administration Reform Programme (FEPAR), State Partnership for Accountability, Responsiveness and Capability (SPARC), and State Accountability and Voice Initiative (SAVI)).
- Continue to focus on opportunities to support systematic monitoring and learning throughout operational design and implementation. Adapting programme design and implementation requires continuous, systematic monitoring and lesson learning to facilitate mid-course correction, adaptation and innovation. The new DFID Partnership to Engage, Reform and Learn (PERL) programme presents a considerable opportunity for joint learning.

Output Title	Strengthened World Bank engagement in Northern Nigeria
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Progress against LF indicators

Emergency Management and Recovery Plan and a financing framework developed for the North East
Target (2016)	Actual Progress
Completion and Operationalisation of Recovery and Peace Building Assessment (RPBA) for the North-East	Achieved: the RPBA was completed in May 2016 and is already informing a first series of World Bank operations in the North-East; its further operationalisation has also been initiated in the preparation of a forthcoming multi-sectoral project and with DFID additional support (granted in August 2016).
Poverty and conflict monitoring	Achieved: the monitoring report has been finalised and leveraged into a poverty assessment released in June 2016.

Key Points
The Recovery and Peace Building Assessment was successfully completed in coordination with the EU and the United Nations. This was used for extensive policy dialogue between the federal and state governments as well as other stakeholders on the reconstruction of the North-East. The RPBA also created a momentum which both Government and partners are using to try to meet the needs in the North East. For the Bank, the RPBA is being operationalised within a first set of five World Bank projects in the region for a total amount of over USD 500 million (with a sixth multi-sectoral operation of $200 million under preparation).

The RPBA calls for an implementation strategy for which the Nigerian government has requested further World Bank support. DFID is supporting this request to operationalise the RPBA with additional funds (of £1.155 million, agreed in August 2016). This will translate the RPBA report into an implementation framework and action plan for recovery and peacebuilding (also linking humanitarian and development aid) in the North-East.

Other critical pieces of analytical work that have been initiated over the past year to inform the programming of World Bank and other donors’ engagement in the Northern part of Nigeria are about to be finalised: a spatial development assessment of the North; a feasibility study of an economic corridor between Lagos and Kano; and an assessment of governance challenges for the development of the North-East.

Recommendations
The World Bank, DFID (with other donors), the UN, and Federal and State Governments to continue to coordinate humanitarian, peace building, and recovery activities in the North East. As World Bank steps up its engagement in the North-East, including under its forthcoming multi-sectoral operation, it will be important that it works closely with DFID to coordinate and synergise activities and build on DFID’s own experience of engagement in the region (including on humanitarian work and on conflict and peace building and governance reforms). This will be important in supporting implementation of the Buhari Plan and for achievement of cross-British Government strategy and operations in the North-East.

Output Title	Enhanced effectiveness of Service Delivery at State Level
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Progress against LF indicators

Operationalisation of the Community of Practice on Public Financial Management (PFM)
Revised target (2016)	Actual Progress
Peer learning on revenue generation at state level	Achieved: all Nigerian states participated in a peer learning event organised jointly by DFID and the World Bank with the Governors’ Forum in December 2015; technical assistance provided to the Governors’ Forum for the benchmarking of state level performance in generating tax revenue.

Policy dialogue on fiscal federalism
Revised Target (2016)	Actual Progress
State budget database leveraged for policy dialogue	Achieved: state budget database populated in 2015 has been handed over to the Central Bank of Nigeria to help it exercise its macro-fiscal oversight responsibility

Improved budget planning at Federal level
Target (2016)	Actual Progress
A prototype oil revenue model developed and policy dialogue has been initiated with the Ministry of Finance for its use in budget planning	Achieved: Prototype has been developed and policy dialogue resumed with the new government for its use in budget planning.

Key Points
This work on revenue mobilisation built on the Community of Practice that was successfully launched in phase 1 of the GPF. It is a critical agenda in the ongoing fiscal crisis and is actively pursued through technical assistance to the Governors’ Forum to help it benchmark state government performance on Internally Generated Revenue and further foster interstate policy dialogue and emulation of good practices. This also supports the enforcement of the newly introduced fiscal sustainability framework agreed upon by the National Economic Council.

It also helped strengthen the oversight of the Central Bank of Nigeria on fiscal discipline at state level by providing it with a near complete database of state budget information.

GPF is helping the Nigerian Government to develop an oil revenue model to improve oil income forecasting. The model captures various taxes (petroleum profit tax, corporate income tax, education tax), royalties, production share, levies, and exemptions through Pioneer Status. It is currently undergoing further refinement to apply ring-fencing and other rules. The goal is to develop a model that can “back-cast” as well as forecast, providing a check on tax and other fiscal revenue assessments and audits.
Recommendations
- Further engage with the governors’ forum to help operationalise its peer review mechanism: A peer review mechanism was developed by DFID (under SPARC) and has been applied to a few states under the previous government; it is being revised and should be leveraged for policy dialogue at state level.
- Fiscal federalism in Nigeria is complex and suboptimal. It proves particularly contentious during the ongoing fiscal crisis. The new fiscal sustainability framework of the Nigerian government needs to be enforced and operationalised. This should be a focus for further engagement on PFM reforms at federal and state level. Action: Focus on support to the operationalisation of the fiscal sustainability framework of the Nigerian government and the effectiveness of fiscal transfers from the federal budget.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
GPF is a technical support programme, and the largest cost driver is consultancy fees and associated costs, and workshops and training costs. There is evidence to suggest that the Country Team has sought to achieve greater value for money associated with these expenses. Rates and rules around procurement of consultants follow standard Bank procedures which may limit the alternatives for the Country Team.

VfM performance compared to the original VfM proposition in the business case
The original VfM proposition noted that the GPF will i) increase DFID’s say in World Bank Nigeria’s governance portfolio activities and management of them, ii) increase the World Bank Nigeria’s concern for results-based monitoring and iii) provide sufficient scope to enable core governance areas in need of attention to get off the ground. This review suggests that this phase is delivering against these very broad VfM objectives.

In this review period the costs (for example professional fees and associated costs) to deliver outputs are comparable with other DFID Nigeria programmes. So far spend has been within budget and progress in being made towards outputs. We will be working with the Bank to ensure that they have systems to collect evidence which will demonstrate the GPF has yielding benefits commensurate with its cost.

Assessment of whether the programme continues to represent value for money
The VfM proposition of the GPF is that the GPF funding has the potential to increase the effectiveness of the World Bank’s over USD2 billion per annum investment in Nigeria. In turn there is the additional value of influencing Government of Nigeria policy and the effectiveness of its own development investment. For example, the USD1.5 million (£1 million) of DFID support through the GPF to the Bank influenced the Bank International Development Association credit of USD500m which in turn is shaping the implementation of the Federal National Social Safety Net Programme of NGN500 billion (around £1.6 billion) per annum.

An underlying assumption is that if GPF helps to improve how the Bank implements its projects, it will deliver significant development outcomes for Nigerian citizens. While this logic remains valid, with some of its components having already resulted in tangible outputs (such as improving design of projects in the North-East and the implementation of flagship projects in health and social protection), the VfM link to delivering significant outcomes for Nigerian citizens is less clear at this stage. The challenge is that attribution to GPF will not be easy to ascertain. Action: Develop a VfM framework for the GPF that more systematically captures the benefits of the programme against the 4 E’s (efficiency, economy, effectiveness, and equity). This should be done concurrently with any changes to the logframe.

Quality of financial management
Reporting requirements have been met. Progress and financial reporting requirements been adhered to as required.

Date of last narrative financial report	5/09/2016
Date of last audited annual statement	30/06/2016

E: RISK (½ page)

Overall risk rating: High
Overview of programme risk
The main risk is that the results attained with GPF support are not sustained because the Nigeria World Bank Country Office fails to leverage additional resources from core Bank funds leading to no or poor institutionalisation of reforms. The Bank has done well so far to integrate GPF activities within its operations. GPF activities have helped design new Bank operations in the North-East for an amount of over USD500m. This is a significant leverage. GPF activities also inform the preparation and implementation of flagship projects such as the Programme for Results in health and education and a Social Safety Net Programme for a total amount of over USD1.5 billion.

The reform environment may present opportunities but remains uncertain given the slow pace of change since the delayed appointment of the government (in November 2015) and the impact of a severe fiscal crisis. The programme is subject to regular Bank standards of financial management. Thus, the financial risk and risk of fraud is low. The grant also provides funding for procurement and financial management support to the Team.

Outstanding actions from risk assessment
Pursue institutionalisation of GPF ‘reforms’. The Bank needs to further ensure the institutionalisation of inputs from the GPF into its portfolio as well as into its forthcoming projects. To that effect, the GPF will need to support two main strategic thrusts of the World Bank country strategy: promoting governance reforms through budget support and/or programme for results operations at both federal and state level; ensuring the effectiveness of reconstruction and peace building operations in the North-East.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Early progress shows that the project is delivering against the agreed timeframe and within budget.

Performance of partnership(s)
The Governance Partnership Facility (GPF) is a combination of a Trust Fund and Strategic Partnership with the World Bank to support governance mainstreaming in Nigeria. In phase 2 the World Bank and DFID should further enhance collaboration. The Bank can work through Government of Nigeria (GoN) systems. The partnership will ensure we can work on the same priorities to increase our collective impact. Action: Constitute an Advisory/Steering Committee for the GPF and consider quarterly review meetings.

Asset monitoring and control
The World Bank has well defined guidelines for the selection and employment of consultants and to procure goods, works and non-consulting services. GPF follows these guidelines to ensure open and fair competition in all its tenders, so it provides high quality goods and services at the lowest cost. The country team has also been able to maximise economies of scale to get preferential rates for hotels and airline tickets with a strong focus on value for money.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The DFID assessment is that the Federal Government of Nigeria (GoN) has not demonstrated credible commitment to any of the four partnership principles. Progress towards attainment of the Global Goals and poverty reduction is proceeding at a slow pace but inequities are increasing. Substantial reform is needed in all partnership principles areas (especially on the implementation of commitments where these are in place).

The assessments shows that the GoN commitment to DFID’s Partnership Principles is weak. The GPF is fully compliant with the UK policy and no UK aid money goes directly to the Government of Nigeria.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
It is expected that during the life of the programme the evidence (and theory) base will evolve, focusing on how to tackle service delivery problems through World Bank programming. This approach requires more testing and the GPF is working to do this, and share lessons. At the same time the Bank’s approach is increasingly focused on operationalising political analysis and thinking and working politically on a routine basis. We will use this annual review report as a platform for continued engagement with the Bank.

Monitoring progress throughout the review period
This Annual Report has been a light touch desk-based review. It has involved a document review including: an internal self-assessment and Progress reports (March 2016 and June 2016); internal Bank Back to Office reports; meeting with the GPF Task Team Leader and GPF technical leads. Action: Increase field visits to GPF project sites and explore opportunities for real-time monitoring and learning in collaboration with the Bank.

This review was undertaken by the Senior Responsible Owner for the GPF.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process