Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Impact Evaluations on urban transport, transport corridors and road safety across multilateral development banks and bilateral programmes (ieConnect).
Programme Value: £7,500,000		Review Date: October 2017
Programme Code: 204931	Start Date: 4/11/16	End Date: 31/1/2022

Summary of Programme Performance
Year	2017
Programme Score	A
Risk Rating	moderate

Summary of progress and lessons learnt since last review

This is the first annual review (AR) for the project.

The project’s purpose is to: Generate a substantial new evidence base on transport policy and investments, including evidence about induced benefits, with a focus on urban mobility, transport corridors and road safety.

ieConnect is an impact evaluation programme of transport research run by DIME, a unit within the World Bank that is excellent at impact evaluations and in partnership with the World Bank’s Transport and ICT Global Practice. DFID’s Evidence Department (EvDep) have been funding the Development Impact Evaluation (DIME) unit since 2014 and we are keen to ensure ieConnect aligns with current funding and review cycles already set up by EvDep. The next AR will be completed earlier than necessary to align the ieConnect AR cycle with the existing DIME AR cycle.

The ieConnect Business Case was approved by DFID Ministers in July 2016. Due to the project cycle extending past the current HMG Spending Review period HMT approval was required prior to Administrative Agreement (AA) finalisation with the World Bank. Approval from HMT was sought in July and granted 26 October 2016. The AA was signed with World Bank and funds were disbursed by DFID in November 2016. The project has been running for 11 months to date the scoring for this AR covers the period up to July 2017 in line with the logframe targets and World Bank Fiscal Year. The narrative describes additional project progress to October 2017.

There has been limited progress in the AR period due to delays in HMT approval (and the related DFID disbursement) and ieConnect recruitment delays within the World Bank (WB). The recruitment delays within the World Bank were in part a result of the appointment of a new World Bank Chief Economist who undertook a stocktake of the WB Research Department (DEC) portfolio and staffing structure, recruitment within DEC was frozen during this stocktake.

In the design of the ieConnect programme DFID have explicitly encouraged ieConnect to work with DFID Country Office programmes and Multilateral Development Banks (MDBs) outside of the World Bank. This is noted in the logframe targets. DFID have proactively introduced ieConnect staff to the Transport directors of the Asian, African and Islamic Development Banks and colleagues within the DFID Country Offices. We are pleased that ieConnect have worked hard to develop these relationships. Conditional on availability of complementary funding from projects and technical feasibility, it looks likely that IEs under ieConnect will be undertaken with DFID-Pakistan, DFID-Ethiopia, DFID-Nepal, AsDB, AfDB and IsDB.

ieConnect fund the initial work on setting up an IE however the respective project is expected to fund the data collection which comprises the main cost. This has proved problematic in some instances of non-WB programmes as the M+E budget within a project may already be allocated to other studies. In general, this appears less problematic in WB projects as M+E project budgets are often unallocated and so available for IE funding.

SUMMARY OF RECOMMENDATIONS:

GRT will explore options for how to mitigate the potential blockage (of limited available M+E project funds) to ieConnect working outside of WB funded transport projects.

Amend logframe to explicitly note that the Output 1.9 ‘ <40% DFID burden share’ includes staff and core funding of ieConnect. Outputs 1.1 (sub-sector thematic spread), 1.6 (Gender and FCAS), 1.7 (LIC and DFID focus countries) and 1.8 (Female Economic Empowerment (FEE)) all have % targets for FY18 onwards and not solely the end total as in the current logframe.

DFID and ieConnect to continue to look for opportunities to work with DFID Country Office funded and non-WB funded transport programmes. ieConnect to proactively explore possibilities of work with the Asian Infrastructure Development Bank (AIIB).

DFID and ieConnect to agree stretching targets for 2018 onwards given 2018 targets have in some cases been met in 2017.

ieConnect, in agreement with DFID, will discuss preferred MDB engagement on the DIME Steering Committee with ieConnect inviting an appropriately senior representative. One possibility could be the chair of the MDB Working Group on Sustainable Transport or a specific MDB that works in geographical areas of interest to DFID (e.g. AfDB or ADB).

ieConnect to make recommendations of practical ways to work in the medium term with the Sustainable Mobility for All (SuM4ALL) initiative once the SuM4ALL Governance structure is clearer (mid 2018). ieConnect will help ensure that the project-level outcomes associated with transport interventions from MDBs are aligned with the global objectives and targets of SuM4ALL, which is a global network of more than 50 organisations working to develop a Global Mobility Report and Tracking Framework for the Transport sector. DFID initiated and part fund SuM4ALL.

EvD and GRT have quarterly meetings with DIME. A short progress report (covering ieConnect and i2i) to be prepared as an update prior to these quarterly meetings. The programme also prepares two budget updates per year as part of payment requests, including recent activities and planned activities for the next 6 months.

GRT next Annual Review to align with timing of EvD Annual Review (March 2018).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5627325.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5578223.xlsx

DFID is providing £7.5 million over five years from 2016 for Impact Evaluations of large transport projects across Multilateral Development Banks (MDBs) and some DFID financed programmes. In total the eight MDBs approve about $20 billion in transport investments annually.

The Impact Evaluations to be funded under this project (ieConnect) will focus on three sub-themes of relevance to economic development:

i)	Urban Mobility
ii)	Transport Corridors
iii)	Road Safety

The two cross cutting themes are fragile, conflict affected states (FCAS) and female economic empowerment (FEE).

DFID is supporting the new transport window (ieConnect) through the Development Impact Evaluation (DIME) unit of the World Bank. EvDep in DFID already support DIME which aims to reduce poverty and scale up development results by improving the availability of impact evaluation (IE) evidence and its use. 90 percent of transport programmes that are evaluated within ieConnect will be co-financed by at least two MDBs and / or other development partners. 100% of DFID funds will finance impact evaluations in low and lower middle income countries. At least 60% of funds will be spent in DFID focus countries.

ieConnect will undertake impact evaluations on large transport projects across multilateral development banks (MDBs) and DFID and facilitate learning from the findings of evaluations. More than 20% of the ieConnect DFID budget will fund impact evaluations for transport programmes which are not primary-World Bank financed, which will develop impact evaluation expertise and knowledge in other MDBs and development partners. In a significant advance on existing studies, ieConnect will evaluate the broader impacts of the transport programmes including trade patterns, job creation, urban shape and female economic empowerment (FEE). This is ambitious and innovative.

ieConnect aims to achieve significant impact by improving the selection, design, and implementation of transport infrastructure projects in DFID focus countries and beyond. Potentially this could include re-prioritizing transport investments to connect remote areas to the global economy, create new trade corridors, ensure women and children are empowered and to permit the development of bigger, denser, more productive and cleaner cities.

DFID is providing funding and guidance to ieConnect for the following aims:

•	Technical knowledge. Provide expert technical support to programme teams (including DFID teams) to use impact evaluation in transport programmes;
•	Build the capacity for evidence-based decision-making on transport investments within governments, MDBs and donors; and
•	Knowledge management. Build on existing DIME knowledge platforms and institutional structures to share transport findings.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

1. Improved awareness, demand for and use of transport evidence in decision making
2. Improved effectiveness and impact of new and existing transport interventions from DFID, MDBs and wider community

We are in the early stages of ieConnect implementation. DFID funding was disbursed in November 2016. This Annual Review scores the period up to July 2017, eight months of funding. The narrative describes progress to date (October 2017). It is too early to assess at outcome level however discussions with senior staff in the Regional Development Banks (e.g. ADB, AfDB and IsDB) has raised awareness of the dearth of IEs in the transport sector, less than 1% of Impact Evaluations (IEs) have been undertaken in the transport sector since th year 2000. Interest from RDBs and DFID Country Offices shows increased demand for IEs in the sector.

Early results include increased awareness in the research departments of the AfDB and AsDB with explicit agreements for collaboration and participation of identified researchers from those departments to work as co-investigators in ieConnect supported IEs. ieConnect met with the head of the research department at AfDB, he assigned three IE researchers to work with ieConnect. ieConnect are in regular contact with the ADB, a member of the ieConnect team is currently in the Philippines presenting the Pakistan plans to the ADB. One ADB researcher has been assigned to the Pakistan research team. ieConnect will continue to work on increasing operational demands in both AfDB and ADB.

Overall output score and description

The Annual Review scores an A overall.

Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation

Indicator 1.1: ‘Increase the number of Impact Evaluations (IEs) across key sub-sectors (total): urban mobility, transport corridors, and road safety’ is the only indicator with a target in 2017 given the long lead in time for much of ieConnect’s work. The target is 8 by July 2017. ieConnect report that 6 IEs in these core sectors have been initiated in low and lower middle income countries during the period. The six projects include IEs in Rwanda, Kenya, Nicaragua, Nigeria, Tanzania, and Ethiopia. Additionally, the ieConnect portfolio has 2 projects that are not being funded through the DFID contribution to ieConnect, since they are not in countries which are low or lower middle income by DFID's definition. These projects focus on gender-based harassment and violence on urban public transport in Brazil, and on the impact of road rehabilitation on access to market and social services in rural Peru. While these 2 projects are not funded by the DFID contribution to ieConnect, they will still contribute to the global knowledge base on transport IE. In addition to the 6 IEs which have been initiated, 29 IEs are at Expression of Interest (EoI) stage within ieConnect, with approval for seed funding due for a selection of these in November 2017.

Although other indicators did not have targets for 2017, progress has been made on the development of data infrastructure (Indicator 1.4) and the development of a measurement framework (Indicator 1.5). Progress includes the development of an extensive data infrastructure for the Rwanda rural roads impact evaluation, which includes creation of a high frequency market price and availability data collection system across the whole country. Data infrastructure in Tanzania has also been developed to collect household level data on mobility, travel times, and labour market outcomes across a large portion of Dar es Salaam at a high frequency using both traditional and cell phone based methods. In Kenya, progress is being made on developing an algorithm to measure road traffic crashes across Nairobi and to categorize hot spots for crashes. In Ethiopia, the IE team has developed a data structure which will integrate household surveys, administrative data, and remote sensing/geospatial data to estimate the impact of trade corridor upgrading on economic development, land use, and trade.

DFID and ieConnect have agreed to a reduction of DFID’s burden share of ieConnect to <40% by 2019 (Indicator 1.9). This target is being actively pursued. For example, IE teams have raised complementary funding both from client governments as well as from external, competitive research grant competitions. Most notably the Rwanda rural roads IE has raised $3,000,000 euro from the European Union. The Nicaragua rural roads impact evaluation has raised $690,000 from internal World Bank trust funds and the government of Nicaragua. The Dar es Salaam IE has raised $200,000 from the International Growth Centre as well as significant client contribution to data collection costs, while the Ethiopia Hawassa team IE has raised $44,000 from the Private Enterprise in Developing Countries fund (PEDL).

Output 1 (40% weighting) scores an A.

Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making

Indicator 2.1: ‘Number of MDBs involved at the operational level’ has a target of five MDBs. Progress has been good on engagement with MDBs outside of the WB with IsDB and AfDB represented at the July 2017 launch workshop. AfDB, IsDB, and the EU are actively involved on project teams either with an ongoing project or in the development of a new IE proposal. IADB is engaged in ieConnect through ongoing IEs on jointly funded urban transport programmes in Peru, which is part of the broader transport portfolio. ADB has been engaged during workshop planning and as a potential collaborator on a project in the EoI stage. A DIME visit to the ADB headquarters in October 2017 secured their participation in the programme. The target of five MDBs has been met. In addition to working with MDBs, ieConnect have also made progress in collaborating with other large development organizations including DFID, Netherlands, USAID, GIZ, and JICA.

Indicator 2.3: ‘Spend on non-WB IEs or co-funded IEs where WB contribution <25%’ has a target of 20% spend.
Of the 6 IEs currently eligible for DFID financing, 17% of the transport projects being evaluated have a World Bank contribution of less than 25%. Considering the broader portfolio of 8 projects, it is 38% of IEs that evaluate non-World Bank projects.

Other indicators have targets starting in 2018, however progress has been made on many of these with a workshop in Addis Ababa in March 2017 with 33 participants and the ieConnect launch workshop in Lisbon in July 2017 with 126 participants (Indicator 2.6). From the participants who were trained in IE techniques (project staff, government representatives, and development partners), 57% were from FCAS and 71% from LICs and LMICs (Indicators 2.5 and 2.4).

Output 2 (40% weighting) scores an A.

Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making

Although none of the indicators under output 3 have targets for 2017 some progress has been made. There are 64 different organizations that have participated in ieConnect workshops and 15 organisations are noted as participating in the ieConnect network as IE researchers or counterparts in the 6 IEs in the programme so far, or 20 organizations in the broader portfolio of 8 IEs.

DFID and ieConnect to agree stretching targets for 2018 onwards given some 2018 targets have been met in 2017.

ieConnect, in agreement with DFID, will discuss preferred MDB engagement on the ieConnect Steering Committee with ieConnect inviting an appropriately senior representative. One possibility could be the chair of the MDB Working Group on Sustainable Transport or an MDB with a regional focus of specific interest to DFID (e.g. AfDB or ADB).

Output 3 (20% weighting) scores an A.

Key lessons
The ieConnect budget does not pay for the actual IE costs. These are sourced from partner or transport project costs. An IE can vary significantly in cost, on large transport programmes an IE could cost in the region of $1.5million. The ieConnect budget runs the ieConnect team, assists in the identification and design of the IEs, mentors the IE project teams, assures quality of the IEs and brings together learning across the themes so that the sum of all the transport IEs adds up to more than their parts.

Whether the IE is on a WB or non-WB funded project the funding for the IE data collection comes from the project or partner funds. This constitutes the majority of the budget for an IE.

There is demand from non-WB partners for engagement in the ieConnect programme however there are constraints on access to M+E funding in non-WB funded projects. The majority of transport projects have an M+E budget however for projects already under implementation many have already allocated their M+E budget which then precludes engagement with ieConnect due to lack of available project budget for the data collection.

DFID Country Offices have responded positively to the opportunities within ieConnect however budgets for funding the planned IE have been problematic to identify. This has meant that DFID-ieConnect collaborations have in some cases not been able to move forward even in case of mutual eagerness to collaborate on a project IE.

Regional Development Banks (RDBs) have also responded positively to the opportunities within ieConnect however DFID and ieConnect will need to work with RDBs to unblock institutional and budget constraints.

DIME has been running within the WB for 12+years and has changed the mind-set of many within the WB. This will not happen overnight in other organisations and ieConnect will need to be strategic in its engagement with RDBs.

Has the logframe been updated since the last review?

This section is not relevant as this is the first annual review

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Increase the number of Impact Evaluations (IEs) across key sub-sectors (total): urban mobility, transport corridors, and road safety.	8	The programme initiated 6 IEs. Additionally, there are 2 IEs that are not DFID funded since they are not in countries which are LICs or LMICs. The target of 8 IEs has not been met, but given the delayed DFID disbursement and recruitment freeze in DEC ieConnect has made good progress.
1.2 Thematic knowledge reviews for policymaking	First targets in 2018
1.3 Increased number of cross cutting reviews: / FEE FCAS	First targets in 2018
1.4 Developed data infrastructure (with ability for scale up)	First targets in 2018	The project has developed an extensive data infrastructure in Rwanda to collect market data across the whole country as well as data infrastructure in Tanzania to collect household level data across a large portion of Dar es Salaam at a high frequency using both traditional and cell phone based methods, and data infrastructure in Ethiopia that combines administrative, survey, and geospatial methods.
1.5 Developed and validated measurement framework that is able to disaggregate impact (male / female ; rural/urban)	First targets in 2018	In Kenya, progress is being made on developing an algorithm to measure road traffic crashes across Nairobi and to categorize hot spots for crashes.
1.6 DFID burden share of IeConnect	First targets in 2019	Discussed with ieConnect and appear to be on target for <40% DFID burden share by 2019.

Key Points

The project has been running for seven months since DFID fund disbursement, overall it is too early to assess this output however ieConnect have made good progress overall on this Output.

Indicator 1.1: ‘Increase the number of Impact Evaluations (IEs) across key sub-sectors (total): urban mobility, transport corridors, and road safety’ is the only indicator with a target in 2017. The target is 8 by July 2017. ieConnect report that 8 IEs in these core sectors have been initiated, 6 of which are in DFID-categorized low income countries. The six projects include Rwanda feeder roads, Kenya matatus, Nicaragua road safety, Nigeria rural access, Tanzania urban mobility, and Ethiopia expressway impact evaluations. The target of 8 IEs in the first year has not been met however given that delayed DFID disbursement and recruitment freeze in DEC the programme has made good progress. In addition to the 6 IEs which have been initiated, 29 IEs are at Expression of Interest (EoI) stage within ieConnect, and a selection of these are due to be approved for seed funding in November 2017.

Although other indicators did not have targets for 2017, progress has been made on the development of data infrastructure (Indicator 1.4) and the development of a measurement framework (Indicator 1.5). Progress includes the development of an extensive data infrastructure for the Rwanda rural roads impact evaluation, which includes creation of a high frequency market price and availability data collection system across the whole country. Data infrastructure in Tanzania has also been developed to collect household level data on mobility, travel times, and labour market outcomes across a large portion of Dar es Salaam at a high frequency using both traditional and cell phone based methods. In Kenya, progress is being made on developing an algorithm to measure road traffic crashes across Nairobi and to categorize hot spots for crashes. In Ethiopia, the IE team has developed a data structure which will integrate household surveys, administrative data, and remote sensing/geospatial data to estimate the impact of trade corridor upgrading on economic development, land use, and trade.

The new Chief Economist of the World Bank undertook a review of all work within the World Bank’s Research Division (DEC). ieConnect is situated in DEC and were part of the review. This resulted in a recruitment freeze across DEC and slower progress on staffing the ieConnect. The recruitment freeze was in no way related to ieConnect performance but was DEC wide. This was unexpected and the ieConnect slower recruitment has, understandably, reduced overall pace of work.

Recommendations
Amend logframe to explicitly note that the Output 1.9 ‘ <40% DFID burden share’ includes staff and core funding of ieConnect. Outputs 1.1 (sub-sector thematic spread), 1.6 (Gender and FCAS), 1.7 (LIC and DFID focus countries) and 1.8 (Female Economic Empowerment (FEE)) all have % targets for FY18 onwards and not solely the end total as in the current logframe.

DFID will be updated on progress with ieConnect recruitment by end November 2017.

Output Title	Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence / tools into policy making
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of MDBs involved at the operational level	5	AfDB, IsDB, AsDB, the EU, and IADB are engaged. Ongoing work with bilaterals (DFID, USAID, NL). Target met.
2.2 Proportion of co-financed transport programmes	First targets in 2018
2.3 Spend on non-WB IEs or co-funded IEs where WB contribution <=25%	20%	Of the 6 IEs currently eligible for DFID financing, 17% of the transport projects being evaluated have a World Bank contribution of less than 25%. Considering the broader portfolio of 8 projects, it is 38% of IEs that evaluate non-World Bank projects. Target not met.
2.4 Proportion of people participating in workshops that come from low or lower-middle income countries	First targets in 2018	71% participating from LICs /LMICs in workshops
2.5 Proportion of people participating in workshops that come from FCASs	First targets in 2018	57% participating from FCAS in workshops
2.6 Number of people trained in workshops and / or by ieConnect supported teams/ researchers	First targets in 2018	159 trained at workshops
2.7 Number of workshops	First targets in 2018	One launch workshop in July 2017 and another workshop in March 2017

Key Points
DFID has introduced ieConnect staff to senior contacts in DFID-Pakistan, DFID-Tanzania, DFID-Nepal, African Development Bank (AfDB), Asian Development Bank (ADB) and Islamic Development Bank (IsDB). IeConnect is progressing the discussions on IE project identification with these organisations and also within the World Bank Global Practice on Transport. Progress is better than anticipated with regard to engagement outside of the World Bank.

Indicator 2.1 : ‘Number of MDBs involved at the operational level’ has a target of five MDBs. Progress has been good on engagement with MDBs outside of the WB with IsDB and AfDB represented at the July launch workshop. AfDB, IsDB, and the EU are actively involved on project teams either with an ongoing project or in the development of a new IE proposal. IADB is engaged in ieConnect through ongoing IEs on jointly funded urban transport programmes in Peru, which is part of the broader transport portfolio. ADB has been engaged during workshop planning and as a potential collaborator on a project in the EoI stage. There has also been progress of building links with DFID and other bilaterals. The target of five MDBs has been met.

Indicator 2.3: ‘Spend on non-WB IEs or co-funded IEs where WB contribution <25%’ has a target of 20% spend. Of the 6 IEs currently eligible for DFID financing, 17% of the transport projects being evaluated have a World Bank contribution of less than 25%. Considering the broader portfolio of 8 projects, it is 38% of IEs that evaluate non-World Bank projects. This target has not been met.

Other indicators have targets starting in 2018 however progress has been made on many of these with the Addis workshop and July launch workshop training 159 people in IE techniques of which 57% were from FCAS and 71% from LICs and LMICs. The SRO attended the July launch workshop and was impressed by the quality of participants and presentations. In discussion with other participants there was strongly positive views on the workshop.

Recommendations
DFID and ieConnect to continue to look for opportunities to work with DFID Country Office funded and non-WB funded transport programmes. ieConnect to proactively explore possibilities of work with the Asian Infrastructure Development Bank (AIIB).

Output Title	Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of organisations participating in ieConnect workshops	First targets in 2018	64 different organizations have participated in ieConnect workshops
3.2 Number of organisations, universities, research centres, and government agencies participating in ieConnect networks	First targets in 2018	15 organisations are noted as participating in the ieConnect network as IE researchers or counterparts
3.3 Number of non-WB hosted dissemination events	First targets in 2018
3.4 Active MDB participation on DIME Steering Committee	First targets in 2018

Key Points
Although none of the indicators under output 3 have targets for 2017 some progress has been made. Between the ieConnect launch workshop in July 2017 and the country-level workshop in Addis Ababa (in cooperation with DFID-Ethiopia), there were 64 different organizations that participated, these included National Road Authorities, RDBs, WB, Universities, Research Centres and Bilaterals. 15 organisations are noted as participating in the ieConnect networks as researchers or counterparts on the 6 IEs. After the approval of funding for a selection the Expressions of Interest that are currently being evaluated, ieConnect expects a large increase in the number of organisations participating in the ieConnect networks.

Recommendations
DFID and ieConnect to agree stretching targets for 2018 onwards given 2018 targets have almost been met in 2017.

ieConnect, in agreement with DFID, will discuss preferred MDB engagement on the DIME Steering Committee with ieConnect inviting an appropriately senior representative. One possibility could be the chair of the MDB Working Group on Sustainable Transport or an MDB with a geographical focus of particular interest to DFID (e.g. AfDB or ADB).

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The main cost drivers for this project are related to the staffing costs of the core research team and those carrying out the impact evaluations. Approximately one third of the costs relate to the Core research team and the Bank and one third for the specific staff recruited to undertake the impact evaluations. The staffing is managed by the World Bank using their internal systems, which are agreed by IFID and the World Bank as part of the wider engagement between the two organisations.

VfM performance compared to the original VfM proposition in the business case
We are still too early to assess this in this AR but will undertake a detailed assessment in the 2017 AR due March 2018. The business case identified a lack of information which precluded a credible cost-benefit analysis for the intervention, but the evidence since that stage suggests sufficient benefits from a coordinated programme of transport impact evaluations through DIME to justify the costs. MDBs alone approve $20bn annually on transport yet transport is a very under-evaluated area. Even though it is hard to quantify, the potential for VfM improvements from a better understanding of what works in this area is very large.

Maximising value for money in the programme depends on controlling the costs of producing impact evaluations, and maximising the probability that findings influence investment decisions.

The following indicators were to be used in annual reporting requirements.

Economy and Efficiency
- Completed impact evaluation papers/reports.
  - Average cost of final impact evaluation papers/reports <=$275,000

Cost-Efficiency
- Crowding-in of external funds
  - Amount and sources of financing for ieConnect impact evaluations coming from alternative sources. DIME have committed to achieve at least 60% by 2019. Some progress has been made on this as detailed earlier: DFID and ieConnect have agreed to a reduction of DFID’s burden share of ieConnect to <40% by 2019 (Indicator 1.9). This target is being actively pursued. For example, IE teams have raised complementary funding both from client governments as well as from external, competitive research grant competitions. Most notably the Rwanda rural roads IE has raised $3,000,000 euro from the European Union. The Nicaragua rural roads impact evaluation has raised $690,000 from internal World Bank trust funds and the government of Nicaragua. The Dar es Salaam IE has raised $200,000 from the International Growth Centre as well as significant client contribution to data collection costs, while the Ethiopia Hawassa team IE has raised $44,000 from the Private Enterprise in Developing Countries fund (PEDL).

Benefits Quantification Effort
- Innovations in design
  - Number of ieConnect impact evaluation designs that include multiple treatment arms.
- Mid-course correction
  - Number of ieConnect impact evaluations that inform mid-course policy/intervention correction.
- Informing scale-up
  - Number of ieConnect impact evaluations that inform policy scale up/down.

At this early stage it is not possible to gauge VFM performance against the business case, however the costs per activity are in line with the initial proposal and crowding in of external funds are ahead of expectations.

Assessment of whether the programme continues to represent value for money
From the information available at this point the project appears to represent value for money. The investment is enabling evaluation of what is already, with just 6 projects in the portfolio, over $1.5 billion in transport investments. The team’s early success at raising counterparts funds means that DFID’s contribution has crowded in significant additional resources for impact evaluation in transport.

Quality of financial management
The financial reporting for ieConnect and for the wider programme (i2i / DIME) managed by Evaluation Department continues to be clear and of good quality.

Date of last narrative financial report	12 September 2017
Date of last audited annual statement	WB single Audit Received October 2017

E: RISK (½ page)

Overall risk rating: Moderate

The risk rating is unchanged from the Business Case as the programme is only seven months into the funding cycle at this point.

Overview of programme risk

Risks for the main i2i project funded by DFID are set out in the detailed risks appraisal in the original Business Case produced by Evaluation Department. These are monitored at least annually and the risks appraisal updated in the Department’s delivery plan for i2i. Those risks apply generally to the ieConnect project.

The main risks to the IeConnect project fall under the Intellectual/Innovation themes and although none of these were identified as likely to occur their impact is deemed as potentially major. Due to the nature of the main risks the mitigating steps are only able to lessen the impact slightly and we will continue to closely monitor these and escalate any major issues to be resolved through the wider i2i governance mechanisms.

As mentioned above the recruitment freeze in DEC has been the main challenge to the project to this point. This issue has been mitigated by new management of DEC being brought in and the recruitment freeze lifted. The risk to the project is no longer applicable.

Outstanding actions from risk assessment
None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

We had anticipated that the programme would be behind the planned timescales due to the time taken for approval of the project within HMG and the recruitment freeze in place at the World Bank however the progress against logframe indicators is adequate as noted in earlier sections. Progress is better than expected against a few of the indicators.

Performance of partnership (s)

ieConnect and DFID have worked well together, particularly in respect of discussions with and engagement with non-WB players such as the regional development banks.

It will be important as pace of work increases to ensure DFID and ieConnect continue close monitoring of progress through the quarterly progress meetings and ieConnect produces a summary progress report quarterly to inform this discussion.

Asset monitoring and control

No assets currently associated with this project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable as this project is not funding a Government.

H: MONITORING & EVALUATION (½ page)

Monitoring progress throughout the review period

As mentioned above the project is within the DIME unit which is supported by the Evaluation team through the Fund for Impact Evaluation project. and there has been very close working between the DFID staff on these projects to ensure consistency of approach and to montitor progress.
The project has formal quarterly management meetings between the partners to monitor progress.

The governance structure of this project aligns with that of the Fund for Impact Evaluation project and there is a clearly defined route to raise and manage issues should they arise.