Annual Review - Summary Sheet

Title: Health Pooled Fund (HPF) South Sudan
Programme Value: £112 million from DFID / £134million from partners / Total £246 million		Review Date: October- November 2017
Programme Code: 203109	Start Date: October 2012	End Date: April 2018[1]
[1] The current end date of the programme is April 2018; however a further no-cost extension period has been applied for.

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A	A
Risk Rating	Medium	High	High	Major	Major

Summary of progress and lessons learnt since last review

This is the fifth annual review for the Health Pooled Fund (HPF) programme, which has been in its second phase (HPF2) since a redesign in April 2016. After several short-term extensions, new contracts with implementing partners (IPs) were signed in November 2016 to cover the period until March 2018. A further no-cost extension is currently under discussion, and it is anticipated that at the end of the agreed period HPF2 will be replaced by a successor programme (HPF3).
The context has continued to be highly challenging. Despite this, HPF has enabled lifesaving Health Service Delivery (HSD) through approximately 1000 health facilities across eight of the 10 states of South Sudan.[2] The health service delivery team has been expanded throughout the reporting period, including new specialists in areas such as Gender Equality and Social Inclusion (GESI), Quality of Care and community engagement. This is supporting HPF to monitor activities and to develop stronger thematic strategies, working alongside other actors through the cluster system.
[2] The Government of South Sudan declared that the country would be split into 28, and later 32 states, since the initial design of the programme. The UK does not formally recognise the new states, and HPF continues to utilise the language of 10 states. The programme operates in: Northern Bahr el Ghazal, Western Bahr el Ghazal, Unity, Lakes, Warrap, Western Equatoria, Central Equatoria and Eastern Equatoria.
The supply chain of essential medicines has improved in the past year, with comparatively smooth and timely distribution around the country for pharmaceutical deliveries made during the period under review. However, challenges persist, with high consumption of certain essential medicines resulting in stock outs, and irregular supply where HPF relies upon other organisations for supply of key commodities.

Due to a lack of government resources allocated to health, delivery against outputs/milestones on health systems strengthening has been lower than expected due to lack of government resources . Despite this, some progress is being made, including the roll out of Quality of Care (QoC) tools and the Human Resource Information System (HRIS) to the states along with continued support to the Health Information Management System (HMIS).

A new nutrition component was added to the programme as a result of additional funding earmarked for these activities by DFID. Progress in upscaling nutrition activities has been slow across implementing partners; nevertheless results have exceeded expectations on the measured indicators prompting us to consider more ambitious targets.

Summary of recommendations for the next year

Health Service Delivery

HPF to gather quality pharmaceutical utilisation data per item, to accurately inform future procurements. DFID and donors to explore options for HPF to better coordinate with supply chains of other actors, such as the UNFPA, GAVI, the vaccine alliance, and the Global Fund to Fight AIDS, Tuberculosis and Malaria (GFATM).

DFID and HPF to explore whether incentive payments can be re-programmed to increase staff motivation in the continuing absence of government salaries.

HPF to strengthen social mobilisation and community level training and gather beneficiary feedback on the impact of these activities.

Health Systems Strengthening

Ensure DFID and other donors are involved in the customisation of the HMIS tool (DHIS II) so that relevant indicators (e.g. on gender) can be captured.

DFID and HPF to explore how to strengthen last mile delivery for essential medicines and nutrition supplies to ensure effective use of pharmaceutical commodities.

DFID and HPF to plan ahead on procurement to ensure transition to HPF3 does not result in avoidable stock-outs of pharmaceuticals.

Nutrition

HPF to ensure harmonization of nutrition indicators with the current Nutrition Information System (NIS), working with the Nutrition Cluster to ensure coordination, and consider more ambitious targets.

DFID and HPF to ensure linkages with DFID’s Integrated Community Case Management (ICCM) programme. Partners should map out hard-to-reach communities to be targeted with ICCM, nutrition should be linked closely with health units and IPs should engage in capacity building of Primary Health Care Unit (PHCU) staff to train and supervise the community health workers (CHW) and community nutrition volunteers.

Value for Money

HPF should examine alternatives to airfreighting commodities such as by pre-positioning stocks by roads in the dry season to secure locations which are inaccessible in the rainy season;

HPF2 should robustly implement the 2016 Value for Money Strategy, and use the forthcoming process evaluation to improve attribution of costs to outputs and benefits;

Other

HPF2 should continue to strengthen work on gender and social inclusion, including through a sharper focus on reproductive health, augmented by strengthened community engagement and social mobilisation and embedding good practice on Clinical Management of Rape (CMR). This should include strengthening the Gender Equality and Social Inclusion (GESI) action plan, reporting on community engagement and women’s empowerment.

In consideration of ongoing challenges to capturing accurate health and service uptake data, due to conflict, DFID should work with HPF to amend the outcome/ impact indicators to ensure that there is accurate data to track progress over the course of the programme.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203109/documents/
DevTracker Link to Log frame:	Updated logframe is pending publication.

Outline of the programme

The intended impact of the programme is to develop a government-led health system that saves lives. The overall outcome is increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. The outputs this programme will deliver to achieve this outcome are:
1. Strengthened delivery of health services, particularly responsive to the needs of women and children;
2. Strengthened health systems at State and County level with detailed focus on: policy; HR for health; health financing; health information; leadership & governance; and
3. Increased access to nutrition services particularly for pregnant women and young children.

HPF2 brings together funding from the UK, Canada, the European Union, Sweden and USA to support delivery of the Health Sector Development Plan of the Government of South Sudan (GOSS), and to deliver the outcomes of the HPF Business Case. DFID and donors contributed £185.6m over the period 2012-2017. The programme offers coordinated support for government-led primary health care delivery in 8 of the 10 states, and additionally has supplied essential medicines to all 10 states in 2017.[3]
[3] The Essential Medicines component was designed to supply the 8 HPF2 states. However, due to the World Bank evacuation after July 2016 hampering their ability to deliver in their supported states (Upper Nile and Jonglei); HPF temporarily stepped in to procure commodities for these states.

Context

The period covered by this review (November 2016 – October 2017) saw a continuation of conflict across many parts of the country, with resultant displacement and increasing humanitarian need. By the end of the reporting period, 6 million people (56% of the population) were estimated to be severely food insecure, and there were populations in humanitarian catastrophe across the country (according to the IPC report, 6/11/2017).

Insecurity has worsened in some areas, and the pattern has shifted over time. In some areas this has hampered HPF activities and access for monitoring. On average around 20% of HPF facilities are non-functional due to security-related impact on infrastructure or staffing, and in many functioning facilities workers frequently face security risks. In August 2017, this resulted in a fatality of a CUAMM[4] (Implementing Partner) member of staff in Lakes state, highlighting the severe security risks in the area and emphasising the need for additional security provision.
[4] Doctors With Africa, Italian NGO

The economic crisis gripping the country has also worsened. The economy is estimated to have shrunk by 11% in 16/17, and high levels of inflation have pushed up prices of basic goods. Government wages have not been paid for approximately 7 months, including in the health sector, and poverty levels are rising as prices rise and economic opportunities diminish. The budget allocated to health remains minimal at around 2%, and this is of a shrinking government budget. In addition to further increasing the expectation and burden on donors to deliver basic services in South Sudan, these developments have hampered existing programme activities. The minimal budget has limited the scope for sustainable change through the HSS component, and the lack of salary payment has impacted upon morale and absenteeism in facilities, negatively affecting HSD and increasing the burden on HPF paid staff.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

At current rates of progress we expect to achieve the outcome by the end of project. The surveys utilised for these indicators run on five year or two year cycles; and we have therefore used modelling and estimate data from Unicef and WHO for these outcomes. It is recommended that DFID works with HPF to amend the outcome and impact indicators to ensure that there is measurable data demonstrating changes over the course of the programme

Impact Indicators	Baseline (2015)	Milestone / (March 2017)	Progress (2017)[5]	Milestone (March 2018)
1. Under 5 Mortality Rate (per 1,000 live births)	99/1,000	91/1,000	91/1,000 [6]	89/1000
2. Infant Mortality Rate (per 1000 live births)	88 per 1000 live births (2012)	58/1,000	59/1,000[7]	58/1000
3. Maternal Mortality Ratio (per 100,000 live births)	789/100,000[8]	789/100,000	789/100,000 [9]	710/100,000
Outcome Indicators	Baseline (2016)	Milestone / (March 2017)	Progress (2017)	Milestone (March 2018)
1. Percentage of 1-year-olds vaccinated with a third dose of DPT[10] vaccine	46.8%	55%	41.8% (175,320)	44%
2. Proportion of children under 5 with fever in the last 2 weeks who were taken to a health facility	64%	70%	2017 data unavailable (64% National Average in 2015[11])	70%
3. Contraceptive Prevalence Rate	5%	8%	5% (National Average)	6.5%
4. % of births attended by skilled health personnel	10.1%	86,930 (20%)	10.9% (47,377)	11%
5.Percentage of children 0-5 months receiving exclusive breastfeeding	45%	N/A New Indicator	N/A New Indicator	50%
[5] Progress on indicator cell coloured thus: “has been achieved”, (green) “partially achieved” (amber) or “not achieved” (red).
[6] Unicef (2017): Source: https://www.unicef.org/publications/files/Child_Mortality_Report_2017.pdf
[7] Unicef (2016): Source: http://www.unicef.org/publications/files/SOWC_2016.pdf
[8] Source: WHO (2015), Trends in Maternal Mortality: 1990 to 2015 www.who.int/reproductivehealth/publications/monitoring/maternal-mortality-2015/en
[9] Estimate - no recent data to measure performance, maintaining 2015 data.
[10] Vaccine against three infectious diseases in children: diphtheria, pertussis (whooping cough), and tetanus.
[11] Lot Quality Assessment Survey (LQAS) 2015 Survey

Outcome 1 has proven challenging due to population migration and inaccessibility from localised conflict and insecurity affecting service utilisation and access to the full treatment of vaccinations. Achievement is further complicated as cold chain support and vaccine supply is not under HPF control. This demonstrates the heightened importance of working effectively with UNICEF and the World Health Organisation (WHO) to ensure supply chains remain active and coordinated with HPF.

Outcome 2 has insufficient current data to accurately assess progress. Data from the 2015 HPF Lot Quality Assessment Survey (LQAS) has been used as the most recent available data and if the trend had continued, progress towards the milestone should be sufficient

Outcome 3 also has insufficient data. Trends indicated by the 2015 LQAS suggest that the Contraceptive Prevalence Rate has actually reduced. Whether this decline is due to inadequate supply (HPF relies on other agencies such as UNFPA to provide commodities) or demand for modern methods of contraception, should be determined and mitigation applied to speed up progress towards the 2018 target.

Outcome 4 has achieved just over half of the ambitious milestone target set for 2017, demonstrating a slight increase in deliveries by skilled health personnel.

Outcome 5 has insufficient data at this time to accurately assess progress.

Overall output score and description

The programme again scored an A (“met expectations”) on the basis of output performance data. The table below gives a summary of performance against the three outputs in the logframe.

Output number	Output Description	Impact Weight (%)	Output Performance
1	Strengthened delivery of health services, particularly responsive to the needs of women and children.	50%	A
2	Strengthened health systems at State and County level with detailed focusing on: Policy; HR for health; health financing; health information; leadership & governance.	30%	B
3	Increased access to nutrition services particularly for pregnant women and young children.	20%	A+

Key lessons

For the HPF and DFID team, several key lessons will inform the continued delivery of HPF2. For DFID, further lessons are also relevant to feed into the design of HPF3.

Given the limited government resources allocated to the health sector, continued reliance on government to deliver critical aspects of the programme (such as salaries and distribution of commodities) is no longer realistic.

DFID takes no programme funds for being the lead donor, and does not have the staffing resources to fulfil all contributing donor reporting expectations. For future implementation of HPF, widened strengthened secretariat function will be considered to more effectively manage and meet donor partner expectations, as well as clarifying the role of the lead donor with respect to the donors and fund manager.

HPF’s model of working through multiple partners in ‘lots’ has made it possible to be flexible in areas of conflict as IPs are able to change their ways of working to suit the local context. The addition of the emergency preparedness and response (EP&R) funding mechanism has proven an effective way to support this increased flexibility, and enabled IPs to scale up activities where necessary.

Despite challenges with procurement quantities and distribution, the HPF supply chain is now functioning reasonably smoothly given the context. This is not to be underestimated given challenges other partners are currently facing, and HPF is under increasing demand to support these other supply chains.

Has the logframe been updated since the last review? Yes

The logframe has been revised relatively substantially since the last review; this process began in early July and was completed in early October 2017. Outputs were amended to include the new nutrition component, and indicator targets were set and revised across the board to account for changes in context.

Due to the proximity to this review, October targets were set by DFID based on expected progress from the June 2017 data to the target date of March 2018.

## C: DETAILED OUTPUT SCORING

Output Title	Strengthened delivery of health services, particularly responsive to the needs of women and children
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (April 2016 - August 2017)	Progress
Output indicator 1.1. / Under five years outpatient consultations: 1. Curative consultations 2. Preventive/ promotive services	Cumulative / Total: 4,553,113 / 1. 3,148,023 / 2. 1,405,089	Moderately exceeded expectation. Score: A+ / Total: 5,394,235 / 3,703,999 / 1,690,236
Output indicator 1.2. / Percentage of children under five years with diarrhoea who receive ORT	Average / 90.85%	Moderately did not meet expectation. Score: B / 90.3%
Output indicator 1.3. / Percentage of women who attended at least four times or more for antenatal care during pregnancy	Average / 27.3%	Met expectation. Score: A / 28.3%
Output indicator 1.4. / Number of facilities with capacity to offer Emergency Obstetric care (disaggregate BEmONC[12] and CEmONC[13])	Using June 2017 data. / 24 (CEmONC) 37 (BEmONC)	Met expectation. Score: A / 24 / 37
Output indicator 1.5. / Percentage of ANC attendees who received IPT2 and more	Average / 51.3%	Met expectation. Score: A / 51.2%
Output indicator 1.6. / Proportion of women 15-49 years using any modern family planning method	5.8%	N/A (no data)[14]
Output indicator 1.7. / Percentage of counties where bulk consignments of medical drugs are distributed at Hospital and CHD level	Milestone relates to distribution as of June. / 98%	Met expectation. Score: A / 98%
Output indicator 1.8. / Percentage of health facilities with reported stock outs of all 4 tracer drugs supplied through HPF	Average / 49%	Moderately exceeded expectation. / Score: A+ / 40%
Output indicator 1.9. / Number of health facilities offering family planning services, with a minimum of three modern methods	338	Substantially did not meet expectation. Score: C / 124
[12] Basic Emergency Obstetric and Newborn Care
[13] Comprehensive Emergency Obstetric and Newborn Care
[14] No data is available, due to removal of data collection from government surveys. DFID and HPF are hoping to work with MoH to have this reinstated, in order to measure progress towards FP2020 targets.

The context for health service delivery has continued to be challenging. Particular challenges include insecurity hampering access; inconsistent performance of implementing partners; human resource issues limiting quality of care; inadequate health sector resourcing from GOSS and management & delivery challenges amongst IPs following the transition from HPF1 to HPF2.

Despite these challenges the programme has broadly continued to operate as expected and delivered services and results. For the period to October 2017, most targets were met. Output 1.2 was not met by a small margin, but still demonstrated improvement against 2016. However, there was significant underachievement on output 1.9 which lagged behind expectations. This was partially due to difficulties with data collection, but also reflects the substantial demand and supply side challenges to service delivery in family planning.

Reliance on external actors for commodities (e.g. UNICEF for cold chain, WHO & GAVI for vaccines and UNFPA for family planning) has presented significant challenges which are yet to be resolved. Donors and HPF have agreed to work alongside other actors to examine ways in which supply chains can be coordinated, in order to reduce these problems in future.

While it has been achieved, ambition for indicator 1.8 is noticeably low due to ongoing challenges in this area which cannot be resolved in the short term. HPF is engaging with the Ministry of Health to ensure that service delivery lessons (e.g. drug consumption rates) are utilised in amending the 68 line items and quantities for Consignment 7, which should result in more appropriate make-up of ‘kits’ for HPF3.

HPF has substantially expanded the HSD team over the past year; this is a welcome investment as the new members have significantly increased capacity for monitoring, particularly in terms of oversight of thematic areas (such as community engagement, family planning, Quality of Care; gender and social inclusion). A new Quality of Care tool (scorecard) is also being rolled out, and is proving a successful monitoring mechanism.

Summary of responses to issues raised in previous annual reviews (where relevant)

Human resources have been a key challenge for the programme this year. Recruiting and retaining government staff has been very challenging, due to low and inconsistent government salary payments, exacerbated by currency depreciation, and staff moving to non-government employment offering better terms and conditions.

Although some IPs are working on Gender Based Violence (GBV), including CMR, a severe challenge to progress is the acute lack of a national level CMR approach, including the lack of a referral system for various CMR services (such as psychosocial support), the lack of a community level system for referrals from the community to the health facilities and the lack of training resources specific to the South Sudan context. UNFPA provides some resources in this area, such as the development of a training manual and IPs bring some of their own resources. The MoH Gender Technical Working Group (led by the Director of Reproductive Health) and the GBV subcluster are engaged in discussions with HPF and UNFPA on CMR but face a significant lack of government resources to make progress.

HPF has recently added a narrative section to the quarterly reporting requests from IPs, which should enhance their ability to conduct qualitative data analysis. HPF are also looking to integrate further data collection into existing health facility collection to account for services specifically offered to displaced communities. Health workers often travel with communities when displaced and continue to offer basic services which are not recorded as they do not take place within a registered facility.

Recommendations

HPF to gather quality pharmaceutical utilisation data per item, to accurately inform future procurements. DFID and donors to explore options for HPF to better coordinate with supply chains of other actors, such as the UNFPA, GAVI, and the Global Fund to Fight AIDS, Tuberculosis and Malaria (GFATM).

DFID and HPF to explore whether incentive payments can be re-programmed to increase staff motivation in the continuing absence of government salaries.

HPF to explore providing assistance to UNFPA in distributing family planning commodities and increase community work to increase demand for family planning.

HPF to strengthen social mobilisation and community level training and gather beneficiary feedback on the impact of these activities.

Output Title	Strengthened health systems at State and County level with detailed focusing on: Policy; HR for health; health financing; health information; leadership & governance
Output number per LF		2	Output Score	B
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones (April 2016 - August 2017)	Progress
Output indicator 2.1. / Number of HPF Steering Committee meetings co-chaired by GOSS (cumulative)	Cumulative[15] / 20	Moderately did not meet expectation. Score: C / 16
Output indicator 2.2. / Number of State Oversight Committee meetings held (cumulative)	Cumulative / 48	Moderately did not meet expectation. Score: B / 46
Output indicator 2.3. / Number of counties with one comprehensive health plan + budget (government and all partners info combined)	100%	Met expectation. Score: A / 100%
Output indicator 2.4. / Number of counties in which HRIS is implemented	89% (47/53)	Moderately did not meet expectation. Score: B / 87% (46/53)
Output indicator 2.5. / Percentage of facilities with quarterly integrated supportive supervision visits conducted by county health department using the QSC tool	55.5%	Met expectation. Score: A / 56%
Output indicator 2.6. / Percentage of health facilities submitting HMIS reports through the DHIS timely (according to the data flow policy)	84%	Moderately did not meet expectation. Score: B / 82%
Output indicator 2.7. / Number and percentage of health facilities with a health committee in place for communities to give feedback regarding health services	93.5%	Met expectation. Score: A / 94%
Output indicator 2.8. / Percentage of health facilities which have documented joint meetings held between the CHD, IP, the health committee and facility staff (all 4 parties)	29.5%	Moderately did not meet expectation. Score: B / 27%
Output indicator 2.9. / Percentage of health committee representatives that are women	33%	Met expectation. Score: A / 34%
[15] From start of HPF1

The shrinking resources the GOSS has provided to its health sector has decreased the ability of HPF to effectively work on health systems strengthening in critical areas, such as financial management and staff training and remuneration. . Consequently there has been an adjustment in the ambition of the programme on this output that was reflected in the updated logframe targets, which allowed the programme to focus more sharply in direct service provision. While the above indicators show the programme overall has moderately not met expectations for this output, this is against the context of a health system in crisis and the Ministry of Health struggling to pay for basic operating costs such as electricity.

Although some HPF support for health systems strengthening (HSS) has continued over the last year there has been a recognition amongst donors and partners that expectations need to be realistic given the lack of government resources allocated to health, and the critical need to ensure continuity of service delivery. The hoped for shift in ownership of health systems to the government set out in the original HPF1 business case will not be possible in the current context of continued conflict, economic crisis and sector under-resourcing. Outcomes and outputs have been adjusted accordingly.

Despite this, some HSS activities have been able to continue to make progress including the roll out of Quality of Care tools and the Human Resource Information System (HRIS) to the states along with continued support to the Health Information Management System (HMIS). The HRIS has been used to register health workers in the two new states with this work almost completed. The strategic plan for HMIS has been supported and distributed along with training at the national level but there has not been sufficient funding to take this down to the state level.

Supply chain management has been supported through the distribution of stock cards and assisting CHDs to safely dispose of expired pharmaceuticals. The programme has also expanded the number of commodities tracked to all 68 agreed essential medicines, in order to get a better idea of consumption rates. There is some concern over whether local SMoH staff completing the tracking registers are doing so effectively given the lack of regular salaries and tools.

HPF was also able to respond positively when the World Bank paused its support in the states of Upper Nile and Jonglei by procuring pharmaceutical commodities to reduce the number of stock-outs of essential medicines. The World Bank has now resumed support for these states and so this risk should not re-occur so long as they are able to deliver consistently and effectively on their plans for future support.

Some limited support has been provided on public financial management (PFM) to help Primary Health Care Centres prepare to access government transfers but these have not been paid for over 7 months (in line with salaries). Some transfers to hospitals are still taking place but overall work on PFM has not been prioritised given the current economic outlook and after the consortium partner responsible for this left the programme in December 2016. Complementary support to PFM in the social sectors has also recently ceased through the closing of the DFID Budget Strengthening Initiative (BSI) programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

Quality of care tools were developed with the MoH following recommendations last year and are in the process of being rolled out to states. The upcoming customisation of the District Health Information System offers the opportunity to see how community based health information is integrated into this HMIS.

Some work has been done to support effective functioning of committees, such as IP training for committee members. However, there is as yet no comprehensive assessment of the quality of community participation, and this could be developed further in the quarterly reporting in the context of the Gender Strategy, the M&E Strategy and the Community Empowerment Strategy all of which are in the very early stages of implementation.

Recommendations

Ensure DFID and other donors are involved in the customisation of the HMIS tool (DHIS II) so that relevant indicators (e.g. on gender) can be captured.

DFID and HPF to explore how to strengthen last mile delivery for essential medicines and nutrition supplies to ensure effective use of pharmaceutical commodities.
DFID and HPF to plan ahead on procurement to ensure transition to HPF3 does not result in avoidable stock-outs of pharmaceuticals.

Output Title	Increased access to nutrition services particularly for pregnant women and young children
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones (April 2016 - August 2017)	Progress
Output indicator 3.1. / Number of children under five weighed and measured as part of preventative or curative consultations (total)	699,673	Moderately exceeded expectation. Score: A+ / 902,180
Output indicator 3.2. / Number of health workers trained on CMAM[16] and MIYCN[17] (disaggregated by sex)	1257	Moderately exceeded expectation. Score: A+ / 1695
Output indicator 3.3. / Number of children nutrition outpatient discharged cured six to 59 months (total)	59,103	Moderately exceeded expectation. Score: A+ / 73,226
Output indicator 3.4. / Number of Antenatal client given Ferrous Sulphate + Folic Acid supplementation	223,399	Moderately exceeded expectation. Score: A+ / 281,004
[16] Community Management of Acute Malnutrition
[17] Maternal, Infant and Young Child Nutrition

Key Points

HPF2 has performed above expectation in all nutrition output indicators and the need and rationale for this component remains strong. There are several recommendations from this Annual Review to be addressed to ensure the programme will deliver against its high-level objectives and is prepared for full scale up.

The technical leadership in the fund must focus both on the operational details and the wider strategic aims of what the project wishes to achieve, and how stated outcomes will be delivered. The fund should take steps to ensure the programme has the right mix and level of technical and strategic capability to ensure HPF is both delivering cutting-edge, high quality programming as well as drawing from global learning on multi-sector programming for nutrition.
Since the scale up of nutrition activities, the consortium has invested considerable time and resources to set up programme infrastructure, recruit and establish new staff and teams, and negotiate and set up common administrative and operational systems. This has been an important achievement given the complexity of the consortium structure.
However there are indications that the anticipated impact on child stunting as set out in the original business case will be difficult to achieve as existing systems are so weak that even prolonged strengthening activities are unlikely to push the quality and intensity of interventions above a minimum threshold for impact. In order to meet this short term need, DFID has therefore asked HPF to develop a fund mechanism by which IPs can ‘bid’ for additional funding for nutrition activities where they have capacity to do so and there are gaps in existing services.
Furthermore, there are many determinants of stunting and malnutrition that HPF will either not be addressing or that planned activities will not tackle fully, including community and domestic access to clean water and availability of sanitation facilities, as well as consistent availability of nutritional and diverse food. It is also important that opportunities to influence other key determinants of undernutrition – either directly or indirectly by working with other actors – are actively pursued by all partners and donors.

Finally, given that results considerably exceeded targets despite the very challenging operating environment, and the fact that this is the first Annual Review of the scaled up nutrition component, it is important to consider whether targets have been set too low and whether these gains adequately reflect significant improvement in service delivery or the level of improvement that is feasible in this context.

Summary of responses to issues raised in previous annual reviews

The nutrition component of HPF has been substantially expanded and there is evidence that lessons have been learnt from the ICCM programme that have been incorporated and benefitted programming. There is evidence that the HPF team has been regularly engaging with GOSS staff and IPs at various levels, however there is still a need to develop clearer objectives for collaboration. There has been a high level of staff turnover among HPF fund managers which has made implementation and scale up challenging.

Since the scale up of nutrition, significant time and resources have been spent to set up programme infrastructure and common administrative and operational systems, however there is much more to be done. Absence of nutrition-specific expertise and systems, have meant that it has been challenging for the program to fully utilise the funding that has been allocated to it. DFID and Canada have recently contracted a process evaluation that will include consideration of nutrition programming; this will strengthen understanding of how components and partners should work together more effectively.

Summary of recommendations for the next year

HPF to ensure harmonization of nutrition indicators with the current Nutrition Information System (NIS), working with the Nutrition Cluster to ensure coordination.

DFID and HPF to ensure linkages with DFID’s Integrated Community Case Management (ICCM) programme. Partners should map out hard-to-reach communities to be targeted with ICCM, nutrition should be linked closely with health units and IPs should engage in capacity building of Primary Health Care Unit (PHCU) staff to train and supervise the community health workers (CHW) and community nutrition volunteers.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The main cost drivers remain those identified in the original Business Case, namely staff costs among IPs (comprising about 62% of IPs’ spend and 36% of total HPF2 spend to date) and commodities procurement (about 25% of HPF2 spend to date). HPF2’s expansion from six to eight of the 10 original States increased the number of health workers HPF is supporting from 2,316 in Oct 2014 to 2,720 currently. Staff costs may rise further if HPF agrees to help retain public health workers, whose Government salaries are at least 6 months in arrears.

The ongoing conflict has also increased costs over the life of the programme. HPF is now meeting the staff costs of public employees in non-government controlled areas. The costs of distributing commodities around the country are budgeted to be 18% of HPF2’s total procurement costs,, increased in part by the need to airfreight to locations where insecurity or road conditions do not permit movement by vehicle.

Overhead costs have accounted for about 21% of HPF2 spend to date (against 19% budgeted). However this is a reduction over the last year when compared to the 25% of total costs reported in the 2016 AR.

VfM performance compared to the original VfM proposition in the business case

Annual Reviews under HPF1 identified weaknesses in HPF’s VfM framework. Recommendations were made in the 2016 AR to strengthen this under HPF2, including commissioning studies included in the VfM Strategy developed in May 2016. Given staffing constraints within the fund manager, due to departures and difficulties in recruiting it has not been possible to commission these as planned.
Overall VfM performance compared to the business case expectation can therefore only be estimated in qualitative terms:
- Economy: likely to be met. Although commodities continue to be procured at competitive unit costs, more attention needs to be paid to stock control and, in particular, to increasing controls at the stage when County Health Departments allocate commodities to IPs. Attention also needs to be paid to check in-country distribution costs are no higher than they need to be.
- Efficiency: not clear if will be met. It is difficult to assess HPF2’s efficiency quantitatively because budgets and expenditure reporting are not linked to its outputs;
- Effectiveness: not clear if will be met without knowing how many outcomes are being met due to surveys only being conducted every 2 to 5 years;
- Equity: likely to be met. By design, the project targets vulnerable populations e.g. women and children, low socio-economic groups and those in need of financial protection. HPF continues to deliver services in the higher cost non-government controlled areas. Whilst equity surveys have not been undertaken to date, the programme supports greater gender equity and inclusion through support and training for women in management, governance and accountability structures.

Assessment of whether the programme continues to represent value for money

In principle, HPF should continue to represent good VfM as its package of support is regarded by the WHO as the most cost-effective way of treating the most common illnesses in South Sudan. Moreover, compared with alternative options for supporting health needs in the eight former states – notably through the humanitarian system – HPF is almost certainly more cost effective, both in its delivery and in helping stabilise/maintain existing government systems.

Nonetheless, there are clearly opportunities to improve the demonstration of VfM. It is recommended that:

- HPF should examine alternatives to airfreighting commodities such as by pre-positioning stocks by road in the dry season to secure locations which are inaccessible in the rainy season;
- HPF2 to act more decisively on the 2016 VfM Strategy through utilising the upcoming process evaluation to explore the identified areas and see if costs can be meaningfully attributed to outputs and benefits;

Quality of financial management

Financial management has improved significantly over the last year with clearer reporting from the Fund Manager so that total programme expenditure can be readily viewed, improved performance from implementing partners in reporting their expenditure accurately, and a reduction in overhead costs. The burn rate has been lower than anticipated at the start of this phase of the programme due to insecurity hampering activities and the capacity of implementing partners. The fund manager has put considerable effort into ensuring that implementing partners submit robust reports to justify expenditure and has taken steps against a number of partners where this has fallen short of expectations.

It is recommended that HPF improves forecasting of expenditure, to ensure it provides accurate monthly forecasts of overall expenditure. This can be best done by adjusting implementing partner forecasts in line with experience.

Date of last financial report	November 2017 (for period to 31 October 2017)
Date of last audited annual statement	November 2017 (for period to 31 December 2016)

E: RISK

Overall risk rating: Major

Overview of programme risk

HPF maintains a monthly-updated risk register, modelled on DFID template, which assesses the shifts in risk and mitigation actions, that represent a threat to programme delivery. This is discussed at regular management meetings with DFID and with partners at donor meetings.

Over the past year, the overall risk rating has remained level at major despite contextual developments including increased fighting in some areas, and the worsening economic situation. Subsequent impact on state salaries threatens to increase this to severe, should staff abandon their posts at large scale.
Heightened insecurity remains a key risk to programme delivery, presenting a threat to the safety of staff and sometimes resulting in destruction of facilities. As a consequence, up to 20% of health facilities are non-operational at any one time. Implementing partners on the ground have so far been able to manage this by operating flexibly, using mobile clinics where necessary and returning rapidly to areas once fighting has ended.

The continued lack of resources allocated to the health sector by the government has impacted on the Ministry of Health’s engagement in the programme and ability to lead system strengthening activities leading to a scaling back of these work streams.

The economic crisis has also led to an increase in other risks such as a reduction in the provision of commercial banking facilities across the country. This has to be managed through switching banking providers and using robust security arrangements when transporting cash.

The creation of new states, counties and bomas has also made it more difficult for the programme to operate with local government counterparts and created tensions with some health centres now classified as hospitals but without the resources needed to achieve this. The programme is having to work flexibly to ensure continued delivery without offering to fund the newly created structures given the UK position on this issue.

On the positive side, management of the programme has improved with a new team leader quickly building effective relationships with the Ministry of Health and taking action on implementing partner performance.

Outstanding actions from risk assessment

Alongside continued insecurity, a key risk to mitigate over the remainder of the programme is the impact of the economic crisis and lack of regular salaries for health workers. Continued political pressure on the government to allocate a greater share of its limited resource to the social sectors should be accompanied by an analysis of how to best ensure incentives and top ups from partners support the delivery of services by front-line health staff.

Continued careful management of the procurement and distribution of pharmaceutical commodities under HPF is needed to reduce stock-outs of key items and the risks of either fraud or mis-management of resources. This will also be a key area for transition to a new phase of the pooled fund given the long lead times for drug procurement.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

As has been discussed in this review, some of the ambition outlined in the Business Case, particularly under health systems strengthening, will no longer be possible in the current context. Further, conflict has been affecting delivery of essential services across the country, with around 20% of facilities non-functional at any given time. However, the programme is proving to be flexible in responding to shifting dynamics, and overall is on-schedule to deliver objectives.

Performance of partnership

- DFID acts as the lead donor for the programme on behalf of the US, Canada, Sweden and the EU. The other donors are engaged through monthly meetings, and other frequent conversations with DFID about areas of shared interest. As noted previously, there will need to be an increase in resources to support programme management role, as this currently represents a considerable burden. Donors are looking into ways to support DFID, and the US has recently agreed to lead on looking into new ways of coordinating supply chains between different actors.
- Representatives of HPF and DFID meet regularly, including through a weekly catch-up meeting.
- DFID meets regularly with the MoH donor coordinator and other relevant officials. However, the intended mechanism for project decision-making, a jointly chaired MoH/DFID quarterly Steering Committee, has not met this year. This has limited the extent to which donors have been able to engage the MoH in key decisions.

Asset monitoring and control

Fighting continues sporadically and in concentrated areas, and as a consequence in some localities the programme suffers some small-scale losses from thefts and looting. These are monitored and reported immediately to DFID by the HPF Head of Operations, with the contracts team leading on ascertaining the value of losses. The fund manager has recently contracted an in-depth asset verification exercise, the results of which will provide a clearer picture on the situation and where particular risks exist.

G: CONDITIONALITY

Update on partnership principles

As noted in previous Annual Reviews, there are no specific conditionality requirements linked to this programme, which does not channel any funds directly to or through the partner government.
As the political and economic crisis continues the relationship between international development partners and government remains difficult in the light of the ongoing conflict and growing human rights concerns. There is however agreement amongst donors that basic service delivery remains an important goal and activity for donor support. Pressure on the government to allocate more resources to the health sector should continue along with practical measures to ensure the programme can function independently should government support to the health sector decrease further.
H: MONITORING & EVALUATION

Evidence and evaluation

To reflect the changes in context and the new outputs for the programme the logframe was revised to include new indicators and amend targets. As some of these new targets, particularly under nutrition, have been exceeded over a challenging period, these should be reviewed to ensure that they are adequately ambitious.

It has continued to prove challenging to report at an impact and outcome level. DFID should look into ways of tracking progress at this level as dependence on irregular national surveys is not producing adequate data.

DFID and Canada have recently contracted an organisation to conduct a process evaluation of HPF2, with the report expected in summer 2018. This will be a valuable resource in shaping HPF3 implementation and ensuring it learns the lessons from previous phases of HPF.

Monitoring progress throughout the review period

The central HPF team regularly visits field sites, complementing the capacity of state coordinators who are responsible for oversight of activities in their geographical area. HPF has employed deputies for all eight state coordinators to enhance their capacity. However, insecurity has limited some of the locations that HPF staff travel to.

The DFID team has faced severe challenges in monitoring activities this year due to initial travel restrictions and unpredictable increases in localised insecurity, and changes in GoSS procedures required to travel outside Juba. DFID is therefore broadly reliant on DHIS data, HPF reporting and independent reports. Additionally, a short third-party monitoring study was conducted in February-June 2017, covering 16 facilities. Plans are underway to ensure a strengthened third party monitoring component for the next phase of HPF..

Despite these restrictions, the team have visited various sites in Juba, Aweil and Unity. HPF donor partners also monitor HPF activities and facilities as part of their visit programming, and report back to DFID and HPF on their findings. These are discussed at monthly meetings and actions taken by HPF on IP performance issues.

Travel restrictions, for both DFID and HPF, limit the ability to gather beneficiary feedback. HPF is currently working with the MoH to gain approval for a new monitoring tool to coordinate the beneficiary feedback collection mechanisms of each of the IPs, which should develop capacity in this area going forwards.

This review used desk review, data analysis and in-country interviews with stakeholders (MoH, the HPF consortium). A field visit was undertaken to Aweil in October 2017.