Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Rural and Agricultural Markets Development Programme for Northern Nigeria (Propcom Mai-karfi)
Programme Value: £27m		Review Date: March 2017
Programme Code: 202098	Start Date: March 2013	End Date: December 2017

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	A+	A	A	A
Risk Rating	Medium	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review:

2016 has been a year of good progress and successful scaling up of interventions by PropCom Maikarfi (PMk). The programme has worked in a total of eighteen interventions across five agricultural markets of Northern Nigeria. PMk is currently scoping various options for Climate Smart Agriculture (CSA) to build resilience among the small farmers against the climate change in Northern Nigeria. It is also scoping for the opportunities to engage in the North East to rebuild the agricultural market systems which were disrupted due to many years of conflict and violence. A business case addendum to respond to these new challenges by extending the programme for three years and by adding £24m to its budget is in the final stage of drafting, and will be submitted for the ministerial approval in early April, 2017.

PMk had to face various challenges in 2016, which resulted in many uncertainties and disruptions. Acute fuel shortages and declining oil prices led to slow economic growth. Private sector investments and business operations were further curtailed due to restrictions on imports and foreign exchange imposed by the Central Bank of Nigeria. Lastly, the continued insurgency by Boko Haram in Northern Nigeria and the communal clashes between Fulani livestock keepers and farmers in Plateau, Benue and Kaduna states also had a negative effect on PMk’s work.

In spite of all these challenges the programme has exceeded all of its output level targets, except for the gender targets where challenges remain. Since 2012 the programme has successfully facilitated, 53 private sector actors to invest in pro-poor business models, it has already exceeded the 2019 target for total private investments leveraged in its interventions markets by over 200%. As a result, PMk has increased incomes of over 480,000 small farmers and rural traders.

The programme is now in its last year of implementation and needs to consolidate the gains it has made by building sustainable market systems through its interventions and should plan for its exit as these market systems continue on viable basis on their own.

The programme has interacted with a number of other DFID programmes during this year: with Markets Development in Niger Delta (MADE) for co-ordinating its approach in dealing with National Vaccination Research Institute (NVRI) for poultry vaccines supply, West Africa Food Markets (WAFM) for making warehousing and fertilizer swap for grain services more accessible for small farmers locally as well as for the regional trade, and with Partnership to Engage, Reform and Learn (PERL) to share its learning from the fertilizer market and the market impact of input subsidy policy as well as the restrictions on the imports.

The programme has made good progress in diversifying away from agricultural inputs, although these interventions still provide the majority of programme results. The total share of beneficiaries at outcome level in agricultural inputs market declined to 68% from about 90% two years ago, reflecting the progress made by the programme in other markets instead of relying only on the agricultural inputs market.

Access to finance remains a key constraint across a range of markets. For example, despite credit guarantees, loans for the purchase of new tractors under the agricultural mechanisation intervention come with a rate of interest of 23% making the scale up of this profitable intervention challenging for new investors at such high interest rate for the new capital.
Summary of recommendations for the next year

The programme should focus on consolidating its work in selected markets and plan for exit in the last year after creating sustainable market systems.

PMk should capture and document intervention level lessons on what has and has not worked and share these with DFID to increase learning across programmes.

PMK has made good progress in scaling up its work in the markets with higher level of women participation. The programme is encouraged to continue to invest in developing a more in-depth understanding of the constraints and opportunities in Northern Nigeria from a women’s economic empowerment perspective. The programme should strive to reduce the barriers to women’s participation in the traditional male dominated markets in addition to working in the markets where female participation is traditionally more acceptable.

Seek to understand the non-market barriers that constrain the positive impact of women economic empowerment work in the markets that PMk operates. This includes issues such as whether the women have agency over the money they make, and whether the men feel marginalised or threatened about the economic empowerment of the women. These risks should be clearly articulated as well as what the mitigating factors are.

Ensure a focus is maintained on strong programme leadership, management and continuity in staff deployment in its last year. The programme has faced the change of team leader thrice and change of programme director twice in its last three years of implementation but was able to manage the transition well.

Seize opportunities and mitigate risks around the recent oil price shocks, absence of agricultural inputs subsidy by Nigerian Government, agricultural commodity imports decline due to foreign exchange restriction and increased militancy in the Northern states.

Encourage the crowding in of new private sector partners in the focal markets during the last year of implementation to make these market systems sustainable on their own as the programme exits from them.

Promote the opportunities for attracting more impact investments in agribusiness supported by the programme, by identifying viable business models and presenting them to potential impact investors and development finance institutions.

Build small farmers’ resilience against climate change by introducing climate smart agriculture practices, integrating this as far as possible with current interventions and ensuring all current interventions are considered from a climate and environmental angle.

Look for links with other programmes and organisations to provide support in developing cooperatives and community based organisations, particularly in relation to governance and structure, so that they can better provide a link between farmer and processor / producer.

Continue the impressive refining of the results reporting system with a view to capture the results at all levels of log frame by the end of programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202098/documents/
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202098/documents

Programme and context:
Propcom Maikarfi (PMk) is an agriculture markets development programme in Northern Nigeria. It identifies constraints and gaps in rural agricultural market systems and plays the role of a facilitator to bring systemic changes through its private sector business partners’ investment, once they see value in making those investments. This operating model is called “Making Markets Work for the Poor” (M4P). PMk is following a flexible approach of deepening its presence in agricultural markets with high potential for pro poor growth, adding new market interventions where such opportunities are identified and exiting from the markets where opportunities for inclusive growth diminish due to changed market conditions, or when an intervention proves to be low value for money.

One third of Nigerians live below the national poverty line. Approximately 60 million Nigerians live without sufficient income to provide 3000 calories per day[1]. More than half of Nigerians live in poverty as measured by the multi-dimensional poverty index. Poverty rates and trends are worse in the North. Income poverty rates in the North East and North West zones are nearly 50 percent, more than 10 percentage points higher than any other zone and double those in the South West. Poverty rates in the north are also declining more slowly[2]. Given that 77% of people in the North depend on agriculture for their income, poverty will not be reduced without a focus on agriculture and rural enterprise. Northern Nigeria is also vulnerable to severe climatic impacts and, increasingly, to conflict and insecurity.
[1] World Bank Nigeria Economic Report 2014 – financial conversion using purchasing power parity conversion factors.
[2] DFID Nigeria Policy Paper on Poverty, Inequality and Vulnerability (Resilience), March 2015

Agricultural growth in Nigeria has largely been driven by agricultural expansion. Agricultural productivity has remained consistently low, particularly in the North where it is characterised by low levels of investment, innovation and use of technology. International evidence suggests that increases in agricultural productivity are usually associated with poverty reduction[3].
[3] Gutierrez, C., Orecchia, P. and Serneels, P. (2009) ‘Does Employment Generation Really Matter for Poverty Reduction’ in R. Kanbur and J. Svejnar (eds) Labour Markets and Economic Development. Abingdon: Routledge. Cited in ODI Background Note, May 2011 Jobs, Growth and Poverty: what do we know, what don’t we know, what should we do. C Meelamed, R Hartwig and U Grant.

Background to Markets:

Propcom Maikarfi is expected to work in at least 8 different markets, or sectors, over its 4.5 year implementation period. An overview of the project’s current interventions is as follows:

Poultry Health, local chicken aggregation and market linkage:

This market has a high level of women’s participation and offers significant opportunity to raise the incomes of the rural poor. Seven in 10 women owned the local chickens they brought to vaccinate during the annual review field visit.

Chickens are susceptible to many infectious diseases. One of the most important of these is the viral disease known as Newcastle disease (ND), which causes devastating losses in both commercial and village chickens. Reducing losses of large numbers of village chickens to virulent Newcastle disease is an essential first step to improving their productivity. Poultry nutrition and disease control are the primary factors affecting bird production at the small farm/household level. If the poultry is better fed and protected from disease, significant increase in profits can be achieved without added labour.

The I-2 Newcastle disease vaccine is more robust and known as a thermostable vaccine. Thermostable vaccines still require long-term storage in the refrigerator; however during transportation of the vaccine to the field, the vaccine will not deteriorate as quickly as the traditional vaccines. This makes it much more suitable for use in rural areas. Propcom Mai-karfi uses this approach to expand upon and create a platform for replication of the thermostable Newcastle vaccination method in addition to enhancing crowding in by other veterinary service companies.

A beneficiary said she will typically lose at least 6 out of 10 birds to the Newcastle disease but with the vaccinations, she is able to grow the number of her chicken without mortalities. In addition, there are more women vaccinators. One female vaccinator in Benue State saw this as a viable stream of extra income for her family, in addition to her teaching job. PMk’s field research shows that with access to affordable vaccines for controlling Newcastle disease and improved production practice, poor rural farmers can increase their flock sizes (and income) by a multiple of at least 6 in one year.

The intervention also seeks to raise the economic importance of local chickens in the minds of rural households, creating a shift towards viewing local chickens as a source of income through capacity building activities and market linkages to processors and retailers to high-end markets.

Agricultural Inputs:

Input suppliers are currently only serving a fraction of the demand generated by smallholder farmers seeking reliable access to high quality farming inputs. Nigeria’s agricultural inputs usage rates are among the lowest in the world. Currently the agricultural inputs market has been dominated by big buyers, commercial farmers and government. For the smallholder farmer, who usually requires smaller unit sizes of fertiliser and seed, traditionally there have not been appropriate products in the market. The programme has invested in companies that are breaking bulk (repackaging large units into smaller units) and are willing to sell inputs to smallholder farmers in packages that fit their needs and are affordable. These packages allow the farmer to buy what they can afford, and take into account the available money a farmer may have at a particular time.
In addition to the above mentioned supply side intervention PMk is also training the farmers in Good Agriculture Practices (GAP), to stimulate the demand for good quality inputs and their proper application.
A total of 26 market players have partnered with PMk since the start of the programme in the inputs market and a total of 306,595 small farmers including 49,320 female farmers have recorded net additional income change as a result of programme activities.

Babban Gona Agricultural Franchise Service:

Babban Gona (BG), which means ‘great farm' in Hausa, has ambitious aims of raising the incomes of one million farmers in northern Nigeria by 2025. The real attraction of the BG partnership, is that it signals to the wider business and political community that agri-business with smallholders is possible in northern Nigeria. BG operates on a unique agricultural franchise model known as trust groups where farmers come together as a unit to help each other produce high quality grains (maize and soybean) with higher than average yields achieved due to high quality agriculture inputs (fertiliser, seeds, tractor services and crop protection products) provided by BG at lower wholesale prices. An additional focus for BG is on youth unemployment in rural areas and promoting women to enter agricultural production.
Propcom Mai-karfi has continued a strong relationship with BG. In April of 2013, a development impact investment referred to as a “Raise out of Poverty (ROPO) Bond”, was made by PMk in BG, worth Nigerian Naira (NGN) 72million for a two year period with 7% per annum interest. In 2014, the programme continued to support BG through a combination of a new NGN 40million ROPO bond investment and technical assistance. In 2015 PMk rolled over the initial ROPO Bond for an additional 18 months. This additional investment has been used by BG to expand to new areas, and also to attract new impact investors notably Bill and Melinda Gates Foundation and Acumen Fund with an additional investment of $5 million made by them. In 2015, BG put greater emphasis on reaching out to women farmers and involving them in the BG franchise farming systems.

BG farmers have reportedly realised income growth in 2015 of 150% above 2014 levels. In 2016 PMk was successfully able to exit from this intervention after all the above mentioned ROPO Bonds were paid back by Babban Gona with accrued interest to PMk. BG is still continuing its work on sustainable basis after PMk’s exit.

Agricultural Mechanisation:

Nigeria is in the early stages of agricultural mechanisation and small farmers remain hesitant to adapt to change for a number of reasons, such as insufficient training and knowledge. In nearly all instances farmers are too poor to purchase or hire mechanised equipment even with government subsidies. This low level of mechanisation limits the ability of farmers to prepare their land in timely manner, expand cultivated areas and achieve economies of scale. Women farmers continue to be at a disadvantage and face enormous challenges accessing and utilising mechanised services. PMk needs to understand what is behind this disadvantage, is this financial, cultural or a gender bias? Or is it due to smaller land holdings by women making mechanisation technically unviable? PMk’s involvement in mechanisation continued in 2016 and it is currently working with Nigerian Ministry of Agriculture to provide them technical assistance to create a viable market system for a large importation of tractors being planned by them on long term concessionary credit basis from Brazil.
A total of 92,380 small farmers have been reached as a result of this intervention.

Shea:

The Global Shea Alliance (GSA) estimates that more than 800,000 rural women in northern Nigeria derive incomes from direct engagement in the shea sector, with 90% of these women involved as primary processors. Shea nut collection and processing is traditionally a woman’s activity and provides an important off-farm source of income during the dry season.
The objective of this intervention is to improve the quality of Shea kernels and to improve the supply chain efficiency in Niger, Kwara and Kebbi States. Women groups, who typically pick Shea nuts from the wild and process into kernels, need to be trained in best practices that will yield high quality kernels. This intervention is building capacity throughout the value chain by the buyer as a way of reducing cost of procurement, while offering good financial returns to the suppliers, who are all women.

Support to IFPRI (International Food Policy Research Institute):

The programme has commissioned IFPRI to conduct six research studies on various issues of importance to agriculture in the north of Nigeria, as decided by the Federal Ministry of Agriculture and Rural Development (FMARD). In 2015 three reports on nutrition, youth unemployment in agriculture, and agricultural mechanisation were submitted to FMARD and were approved by them. In 2016 PMk transitioned this intervention to DFID Nigeria’s Policy Development Facility (PDF) programme.

Electronic Warehouse Receipting System:

The majority of small farmers are dependent on prevailing market prices which tend to be lower at harvest time. In Nigeria, most farmers are smallholders who do not have suitable on farm storage to retain grain for extended periods, thus most of the grain is sold at the end of the growing season. This drives the price down, leaving most farmers with little return. Grain storage remains an ongoing problem for farmers. However, if suitable storage facilities are available this can give the farmers the option to retain their grain until prices increase.

PMk together with African Exchange Holdings Ltd (AFEX) are co-investing in an electronic warehouse receipting system (EWRS) to increase smallholder farmer’s participation. PMk’s investment is to enable AFEX to promote EWRS among smallholder farmers and encourage farmers to use the systems as a strategy to manage price fluctuations. AFEX initially aims to attract smallholder farmers to sell to the warehouse or swap their produce for fertiliser. Over time AFEX hopes to attract individual farmers and farmer groups to adopt the EWRS for storage management and as a source of finance. In 2016 West Africa Food Markets (WAFM) a centrally managed programme also formed a partnership with AFEX to invest in this activity to promote aggregation of commodities at their warehouses for cross border regional trade.

Ruminant feed finishing:

The programme has helped 1,267 small farmers including 267 women to improve their income from the livestock. The feed finishing intervention is designed to introduce better animal husbandry and a feed supplement in addition to traditional roughages leading to reduction in time and cost of finishing ruminants. Identified feed companies produce the ruminant feed supplement which they sell to farmers through their dealers and Paravets. The Paravets, sales teams of the feed companies and ruminant feed dealers are given advanced trainings in feed finishing technologies at Training of Trainers workshops by the PM appointed consultant. The Paravets mobilise farmers in various communities whom they train in partnership with the feed companies either directly or through their dealers. The feed companies provide the feed for sale to the farmers. The Paravets provide technical and veterinary services to the farmers and act as links to feed sources.

Rice Parboiling

PM’s intervention in the rice parboiling market aims at addressing some of the constraints faced by women rice parboilers to enable them to participate more effectively in the market. This is being achieved by facilitating functioning market linkages for women rice parboilers with identified rice traders in their communities, coupled with building their skills to negotiate and manage their businesses better through their collective agency.

Acha Processing

Acha (Fonio) is an important crop grown in some part of Bauchi, Plateau and Kaduna states. The crop is associated with drudgery in production and processing and farmers do not have access to mechanised methods for processing after harvest. Traditionally, producers pound the acha in a mortar to de-hull the grain, however this is difficult and time consuming.
PMk in an intervention aimed at providing cost saving due to the processing service to acha farmers using semi-mechanised methods of de-husking, grading, de-stoning and winnowing is supporting a local processor. The intervention also aims to build the capacity of the processor to serve as an off take market for acha farmers in target communities. The majority of acha producers are women who normally have limited linkages to markets for their produce. Due to this intervention women are able to sell surplus acha to the processor hence the intervention facilitates market linkage for smallholder acha farmers in order to increase their incomes.
This market has the potential of reaching more women. The programme needs to scale up its work with the processor to provide more semi-mechanised processors to the rural poor. It is focussing in the final year on encouraging inward investment for the processor to allow for expansion.

Sesame Contract farming

The intervention in 2016 seeks to leverage on WACOT’s expertise in seed multiplication, contract farming and marketing sesame in Nigeria as well as PMk’s prior experience in improving crop yields through capacity building to improve incomes of farmers.

Capacity Building of Community based organisations (CBOs)

The aim of this intervention is to help CBOs become commercial entities able to transact on behalf of their members. The CBOs then act as an efficient channel for commerce, between the private sector companies and smallholder female farmers. The CBOs are quasi-cooperatives with access to large number of smallholder female farmers who are otherwise difficult to access with goods and services. The broad aim is to build capacity of the women focused CBOs to offer some commercial services to their members in a sustainable manner.

Cooperatives Intervention

The objective of this intervention is to develop a sustainable business model that allows smallholder farmers who are members of rural agricultural co-operatives to take advantage of market opportunities that can significantly increase their incomes as well as access to markets for inputs and outputs. The intervention aims to develop a marketplace, based on an e-enabled platform, where farmers have access to suppliers of agricultural inputs, and at the same time have access to off-takers of agricultural products.

Climate Smart Agriculture

PMk initiated two assessments and intervention designs during 2016 aimed at increasing its understanding of how private sector can be engaged commercially in climate smart initiatives and whether rural communities can identify and engage in activities that creates additional incomes while conserving the environment. These assessments also enabled PM to better understand interventions with climate smart benefits to smallholder farmers. They are:
a.) Introduction of improved cook stoves and charcoal briquetting service to rural women engaged with rice parboiling.
b) Increasing climate resilience through weather data derived products. In this intervention the private sector partner will undertake baseline studies and studies of historical weather variances to develop information products, and strategies for commercialising those products among smallholder farmers.

Context for the 2016 Annual Review:

While the overall context for this review remains unchanged, important developments have occurred in 2016 that have direct implications for the programme. The low oil price is already impacting heavily on Nigeria’s economy. Federal and State Governments are finding it difficult to fully meet their spending plans. Central Bank of Nigeria has imposed foreign exchange restrictions for a long list of imported commodities and there is a wide gap between the official exchange rate and the market exchange rate of Naira with all major currencies, creating a significant disincentive for foreign investments.

Whilst the oil price shock may well have negative repercussions due to possible cuts in Nigerian government’s spending in the agriculture sector, it also represents an opportunity for PropCom Maikarfi in terms of a reduction or elimination of the agricultural inputs subsidy provided by the Federal Ministry of Agriculture and Rural Development (FMARD), allowing a bigger space for the crowding in of private sector input suppliers in this market. The rising costs of imports due to the devaluation in 2016 has also made import competing markets such as rice production substantially more cost competitive. The programme is already supporting rural retail and distribution systems from the supply side, and training the small farmers in the proper use and application of good quality inputs from the demand side.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment:

Outcome: Better performing poor farmers and small scale rural entrepreneurs in selected markets.
Indicator 1: Number of poor farmers and small scale rural entrepreneurs recording net additional income change as a result of programme activities and are therefore more resilient (number of whom are women in brackets). Cumulative

- Milestone by end March 2017: 400,000 (160,000)
- Achievement by March 2017: 480,098 (83,764)

Indicator 2: Aggregate net additional income among poor farmers and small scale rural entrepreneurs in selected rural markets as a result of programme activities (Nigerian Naira (NGN)/ Pound Sterling (GBP) Cumulative.

- Milestone by end March 2017: NGN 3,747,774,129/GBP 14,755,016
- Achievement by March 2017: NGN 5,399,201,407/GBP 17,397,880

Assessment of outcome indicators:

PropCom Maikarfi has achieved 120% of its fourth year outcome milestone for income beneficiaries, but missed it for the female beneficiaries by achieving 52% of this target. This highlights the need of sharpening the gender focus of the programme by scaling up those interventions that are showing strong results in improving the women’s participation in the selected markets. The programme should continue its practice to upscale performing interventions, exit or put on hold non performing interventions, and assess and enter into new interventions where there are clear opportunities. In case of climate smart agriculture component coming on board; there will be need to initiate completely new interventions. Lastly, the programme needs to maintain its focus in the last year to find more depth in its interventions that increase beneficiaries’ income.

There has been good progress on diversification of results, in 2014 last year the programme was highly dependent on agriculture inputs market with 90% results for outcome indicator 1 achieved in that market. Last year that share declined to 73% and this year it further came down to 66% as a result of scaling up of interventions in other markets. Although this market has three distinct value chains (Seeds, fertiliser and crop protection products), any adverse market conditions or policy actions by Nigerian Government could have resulted in quick reversal of success

Overall output score and description: The overall output score is A

The programme has significantly exceeded all its output and outcome targets except for the gender outreach targets at both levels. The programme made good progress on outcome level results as compared to the last year. (27% growth in total beneficiaries, 77% growth in women beneficiaries and 97% growth in overall income generated).

Whilst applying the quantitative weightings may provide an A+ score, due to missing the targets on women beneficiaries, the score has been moderated down to an A, recognising the positive progress but the need for PMk to do more to address this key issue in their final year.

Key lessons and actions:

A flexible programming approach and the ability to scale up or down interventions in different markets as required are key strengths of Propcom Maikarfi. This flexibility also helps the programme achieve better value for money by focusing on more cost efficient or high impact interventions. The programme avoids taking a directive approach and instead focuses on bringing private sector players together around specific market problems and supporting them to take the lead in addressing them. This approach is sustainable and addresses the long term systemic changes required in a market.

Greater investment in the programme’s capacity on gender has been late in coming, given the ambitious gender targets and a difficult context in which to work. However, considerable progress has clearly been made in this review period, such as scaling up the work in markets with high rate of female participation like poultry vaccination, acha processing, rice par boiling, shea processing, Sesame contract farming, and working with women community based organisations. Maintaining the ambitious gender targets has been beneficial in building the programme’s focus on gender so that, whilst the targets are not currently being achieved, their ambition is helping to maintain a gender focus (including non-market barriers).

Propcom Maikarfi needs to deeply understand the economic situation of women, where they are on the poverty spectrum and what their income level is?

In its final year the programme should captures the lessons of what has, and importantly what has not, worked in the interventions so that this learning is available to be shared with a wider audience.

Has the logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Selected rural market systems work more effectively for poor farmers and small scale rural entrepreneurs
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	End March 2017 Milestones	Progress
1.1: Number of market players supported to invest in pro-poor interventions/activities through programme facilitation. / Cumulative "	15	Achieved: / 53 (353% achievement)
1.2: Amount of investment leveraged through market players (NGN/GBP). / Cumulative	NGN 2.5 Billion (GBP10 million)	Achieved: / NGN 9.3 Billion (GBP 29.7 million) (370% achievement of NGN target)
1.3: Number of poor farmers and small scale rural entrepreneurs who access new inputs, knowledge, services, technology as a result of programme activities(number of whom are women in brackets) (Cumulative)	550,000 (184,000)	Achieved: / 829,260 (143,755) (151% achievement of total and 78% achievement of female target)

Key points and highlights:

PropCom Maikarfi formed new partnerships with private sector investors during the year and significantly diversified its portfolio of interventions. As a result there are 53 private sector partners currently investing in rural markets that are contributing to pro poor growth in Northern Nigeria. Last year there were 27 such investor partners. This significant achievement of almost doubling the base of private sector partners has mainly been driven by high performing interventions particularly in the poultry sector. Alongside high growth long-standing interventions, programme activity in storage, rice parboiling and commercialising Community Based Organisations has begun delivering results. This will create more competition in the focal markets and will result in wide spread gains in pro poor livelihoods and jobs creation. This increase in partnerships demonstrates an encouraging diversification and is promising for the sustainability of the economic benefits created by the programme.

The amount of private sector investments leveraged by the programme in 2016 was GBP 20.4 million.
The programme’s interventions resulted in improved access to new inputs, services and technology for 808,408 poor farmers and small rural entrepreneurs, including 137,372 women.

This output is assessed as A+ on cumulative basis.

Summary of responses to issues raised in previous annual reviews (where relevant):
The previous annual review recommended that Propcom Mai-karfi should start deepening its interventions to achieve outcome and impact level results. While the programme has made progress in deepening its impact especially in poultry, tractor and warehousing service markets, it needs to make sure that it achieves its outcome and impact level results by the end of its last year.

Secondly, it was recommended that the programme should explore new ideas to convert its outreach to female beneficiaries into stronger outcome level results, however it is still falling significantly short of achieving it, in spite of making significant efforts, this also raises the question about the validity of original assumption made in the Business case about the optimistic level of female economic participation in Northern Nigeria, and the need to revisit those assumptions
Thirdly, it was recommended that a submission should be made for ministerial approval for an additional climate smart component with additional funds and extension in programme duration. A business case addendum has been written for this purpose and it is in the final stage of drafting before the submission.
Fourthly, it was recommended that the programme should use Progress out of poverty Index (PPI) to measure equity by the percentage of poor in its total beneficiaries. The programme has developed it and is using it to measure the percentage of poor. Although it is not a part of programme’s log frame indicators.

Recommendations

PropCom Maikarfi should make all possible efforts in deepening its interventions in existing markets for achieving the outcome and impact level results including gender targets, and to bring systemic changes in existing markets as the programme enters into the last year of its implementation phase. It is encouraging to note that programme has significantly exceeded its target for number of market players supported to invest in pro poor interventions, however in the last year the programme should ensure that these private investments should support sustainability and replication of successful approaches, as opposed to only broadening out and diversification of interventions.

It is recommended that the programme should assess the differences in access that women and men have to agricultural inputs, knowledge, and training. It is commendable to note that women are reimbursed for the cost of attending the formal trainings.

DFID should make a submission for ministerial approval of an additional climate smart agriculture component, with additional funds and extension in the programme duration and should aim to get the required approvals to extend the programme in climate smart agricultural markets and also in the North East within the last year of current programme. This extension will also provide a good opportunity for the upwards revision of targets which have already been significantly overachieved.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Poor women and men engaged in selected rural markets are less vulnerable to shocks, trends and seasonality
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	End March 2017 Milestones	Progress
2.1 Number of interventions that contribute to the improved resilience of poor farmers and small scale rural entrepreneurs. / Cumulative	15	Achieved / 17 (113% achievement)

Key points and highlights: In total 17 PMk activities will help to build the resilience of the farmers against climate change, seasonality in incomes and resilience against economic shocks. PMk has also designed and submitted a climate smart agriculture bid for DFID’s approval and ministerial submission.

PMk instituted two consultancy assignment aimed at highlighting opportunities within the current interventions, as well as other opportunities within agriculture in northern Nigeria where climate smart approaches can be applied to increase resilience and reduce vulnerability of agricultural households to climate change. These two assignments are described below;

a)	Review of Current PM Interventions to identify opportunities for Climate smart approaches
b)	Assessment of new opportunities for Climate smart investment within Agriculture in northern Nigeria

These assessments also enabled PMk to better understand these interventions with climate smart
benefits to smallholder farmers. They are:

a.) Introduction of improved cook stoves and charcoal briquetting service to rural women engaged with
Rice par boiling.
b) Increasing climate resilience through weather data derived products

This output is assessed as A+ on cumulative basis.

Summary of responses to issues raised in previous annual reviews (where relevant): The 2015 annual review recommended that Propcom Maikarfi should continue to explore and analyse the new interventions to build resilience in small farmers especially among women. The programme has analysed it in detail as mentioned above and has submitted information for a business case addendum to DFID for ministerial submission as described earlier.

Recommendations

- Propcom Maikarfi should continue to explore and analyse the new interventions to build resilience in small farmers especially among women, while waiting for the ministerial approval for the extension that includes climate smart agriculture component. It should look for new models and approaches that will build farmers’ resilience against the climate change in medium to long term.
- PMk and DFID should explore the opportunities to collaborate with other development partners’ work on climate change and environment issues.
- Particular care should be given to the climate and environmental and safety considerations of agricultural inputs interventions.
- A useful climate smart and gender friendly intervention could be the introduction of solar-powered fridges for poultry vaccine vials. The female vaccinators face a problem that their 200-dose vials vaccines get wasted as they struggled to exhaust the supply. This is because in addition to domestic pressures on their time, they typically do not have as wide a client base as their male counterparts. Hence a solution of making solar powered fridges on commercial basis for the storage of vaccine vials is an example of climate smart agriculture with women economic empowerment. The programme is also working to scale up the availability of 50 dose vials.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Private investors, government, non-government organisations and development agencies make changes in their approach to northern Nigeria as a result of programme influence
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	End March 2017 Milestones	Progress
3.1: Number of businesses that buy more from, or invest more in selling to, poor women and men in northern Nigeria, due to a change in practice that can be ascribed to the programme. (Cumulative)	7	Achieved / 33 (471% achievement)
3.2: Number of actions (regulatory changes, policy reforms, practice changes or releases of funds for investment) by state and federal government, supported through programme facilitation. (Cumulative)	5	Achieved / 9 (180% achievement)
3.3: Number of development agencies, non-government organisations, farmer organisations and trade associations that have been supported or influenced through programme facilitation. (Cumulative)	5	Achieved / 24 (480% achievement)

Key points and highlights: In the agriculture inputs market Propcom Maikarfi has invested in companies that are reducing larger units into smaller units, especially the fertilizer distributors and resellers, who reach small farmers with packages that are affordable to them and suit their needs Beneficiaries mentioned that poor women can afford 1 Kg packs. PMk could do more to engage with the fertiliser companies to aggregate the demand for 1kg and ensure these are in constant supply, and on time. Some external factors such as government contracts distort manufacturers’ motivation to supply small bags. Farmers are also graduating to 10kg and 25kg bags, the programme is emphasising this to manufacturers. The programme continued to work with National Veterinary Research Institute (NVRI), a veterinary services company and village based vaccinators to sell poultry vaccines directly to smallholder farmers. The programme worked with tractor rental companies, financial institutions and Nigerian Agricultural Ministry to make agricultural mechanization more accessible to small farmers who otherwise are excluded from mechanized agriculture. These are some of the examples of changes in the approaches made by a large number of market players as a result of interventions of PMk.

This output is assessed as A+ on cumulative basis.
Summary of responses to issues raised in previous annual reviews: Last year’s review recommended to work on policy influencing with Nigerian Government to gradually phase out the agricultural input subsidies and crowd in private sector investments in this market. Due to budgetary pressures Nigerian Government stopped agricultural subsidies during 2016, allowing a much wider participation of private sector in the inputs market.

Recommendations

PMk needs to ensure that investments and partnerships are assessed with a sustainability focus. This is particularly the case as the programme moves to its final year. It needs to have clear exit plans leaving behind sustainable market systems before its planned closure by the end of 2017.

The programme should develop a sustainability plan for the women to remain engaged in the intervention markets. PMk needs to engage with regulatory bodies to ensure gender-sensitivity is brought into the agricultural policies.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance:

The key cost drivers are personnel fees and grants. This reflects the programme’s model of providing technical assistance to market players. As at January 2017, 69% of reported spend was on personnel fees. This is an increase from 55.16 in 2015.

Value for money (VfM) performance compared to the original VfM proposition in the business case:

The business case proposed that overall VFM for the programme will be calculated at aggregate level using two measures:
- The net additional income change (NAIC) as a result of increase in sales, productivity and quality when compared to the programme costs, is estimated at 1.90 by 2019
- Total private sector investment leveraged estimated at £3.59m, £0.14 investment per pound invested by DFID

The programme has identified additional VFM indicators which they have been monitoring and reporting on. The 2014 Information, Training And Development Ltd (ITAD) report on ‘Monitoring VFM in DFID’s Economic Growth Portfolio’ put forward specific recommendations to improve Propcom’s VFM indicators. The programme revised its VFM indicators based on ITAD’s recommendations. This included adding equity measures as well as making the indicators less ambiguous. The table below compares cumulative VFM values over time with the planned spend and Logframe targets. This creates indicative VfM milestones for March 2017 against which to compare the cumulative indicators.
VFM Dimension	VFM Indicator	2012	2013	2014	2015	2016
Economy	Total operational costs/total costs	0.42	0.41	0.39	0.38	0.34
Efficiency	Private sector investment leveraged per £ spent.	£0.25	£0.14	£0.60	£1.27	1.71
	Cost per farmer/small scale rural entrepreneur reached through inputs, services or technology	£9	£16	£20	£19	21
	Cost per female farmer/small scale rural entrepreneur reached through inputs, services or technology	£42	£78	£110	£127	122
Effectiveness	Cost per farmer/small scale rural entrepreneur recording an increase in sales, productivity and/or quality.	£12	£23	£34	£34	36
	Cost per female farmer/small scale rural entrepreneur recording an increase in sales, productivity and/or quality	£82	£149	£229	£267	211
	Beneficiary income gain per £ spent	£0.30	£0.20	£0.29	£0.76	1.00

On economy, the programme only reports the percentage of total operation costs; as at January 2017, this was 30.6% while the programme forecasts to spend a total of 31.8% by the year’s end (this percentage is without personnel cost which has already been calculated above)

The other efficiency measures appear to be doing well cumulatively when compared to the estimated Business Case targets; and there has been a positive trend in the VFM values. The total cost per beneficiary reached has decreased by 3.9%, while cost per female beneficiary reached has increased by 10.5% from 2015. The beneficiary income gain on the other hand shows an improvement from last year. Further investigation showed that income gain per £ spent in 2016 alone was £1.00. Reaching the ultimate effectiveness measure will require a significant increase in the level of income gained, with total cumulative value approximately doubling each year. This will require a combination of sustained income increases and outreach throughout the programme.

Recommendations

Programme should continue to develop value for money indicators and approaches, in particular to develop gender measures which reflect the true cost of achieving results for women. Some estimation will be required here as it is difficult to accurately disaggregate the costs associated with reaching the women when many interventions have beneficiaries from both genders.

Ensure that value for money measures are used appropriately and effectively when assessing investments in different market sectors, including analysis behind simple ratio measures to understand how and why interventions are proving more or less cost effective and whether lessons can be learnt.

The programme should seek to understand the opportunity cost of attracting a new female entrant into the market. This might take the form of analyzing why it is costing more to reach a woman? What these costs encapsulate and what lessons are being learned from this?

Assessment of whether the programme continues to represent value for money:

Currently Propcom MaiKarfi represents value for money. Cumulatively, value for money indicators are around the level they are expected to be at this stage in the programme. The direction of travel is positive and Propcom Maikarfi needs to consolidate on the interventions that are currently yielding the desired results, while exiting interventions that are not working and cannot be put back on track.

The programme is encouraged to explore opportunities to achieve gender targets, which remains central to its strategy. It is recognised that most of the states where the programme works are conservative and do not encourage women working outside of their homes, however there are significant variations between and within communities. However there is potential to increase women involvement through women leaders and their co-operatives. Working with village poultry and acha has the potential to increase the women participation as many women farmers and aggregators are already working in these markets.

Quality of financial management:

The initial programme budget agreed for the 2016/17 financial year was £5.5m. As compared to the budget of £4.3m, the programme has spent 89.3% as at January 2017 and it is forecasting to spend 97.4% of the agreed budget by the end of the financial year. The programme has demonstrated flexibility and an ability to respond to DFID’s requests to increase or decrease funding through certain quarters of the financial year.

	Current approved budget 2016/17 FY	Spend as at Jan 2016	%spend as at Jan 2016	Forecast spend by March 2017	% variance from Budget
Initial approved budget	4.3m	3,843,474.49	89.3%	97.4%	2.6%

Whereas the overall aggregate budget spend is good, there have been considerable variances in monthly forecasting. Programme forecasting has mostly fallen outside of the 2% target, with variance as high as 21% in October2016. This issue was also picked up in the last review. Whilst some variation is expected in programmes following Making Markets Work for Poor (M4P) flexible approach, consistently large variances show the need for improvement in the programme’s forecasting systems.

Narrative financial reports are sent as part of quarterly and annual reports. Financial performance is also reviewed quarterly as part of DFID’s Key Supplier Management review and feedback is given to service providers.

The last audit was carried out in August 2014 for the period covering December 2011- June 2014. The audit report was unqualified. In the auditors’ opinion all materials, receipts and payments for the period under review were in accordance with the international standards and the agreed terms of contract. The next audit is scheduled to take place in June 2017; term s of reference for it will be developed and agreed with DFID.

Date of last narrative financial report	January 2017
Date of last audited annual statement	August 2014

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk:

Delivery of results (Moderate) – The programme has achieved or exceeded its output milestones for 2016, except missing gender targets at the output and the outcome level.

Reputational risk (Low). The programme trains the farmers in the safe handling of agro chemicals and inputs to mitigate any risk to their health and to the environment.

Fiduciary risk (Low): PMk has successfully received the returnable funds back from Babban Gona and is recycling it within the programme. Some invoices were delayed for about 3 months when palladium was changing its financial system this year; otherwise, invoice submission times are generally good.

Context (Moderate): Reduction in Government revenue due to decline in oil price and control on foreign exchange continue to pose challenges for Nigerian Economy. The programme is working with private sector to increase their participation in agriculture markets as government subsidies are withdrawn. Restriction on fertiliser movements in the North are in place by Nigerian military and DFID is coordinating closely with Office of National Security Adviser and Ministry of Agriculture to balance the security and market needs.

Operational (Moderate): Conflict and security challenges in the North present operational risk to the programme staff travelling in the region. This risk is mitigated by sharing regular security updates with DFID and BHC security staff.

Avian Flu (Low) – Nigeria experienced an outbreak of avian bird flu in early 2015 which continued in 2016. This is not a serious issue anymore but the programme is monitoring the situation to safeguard the work it does in poultry market.

Outstanding actions from risk assessment

The Business Case described in detail the significant risk of climate change and environmental degradation on Northern Nigeria, and those risks remain. DFID should seek the ministerial approval as early as possible to implement the climate smart agriculture component of PMk as part of its proposed extension; as an appropriate response to build resilience among Northern Nigerian farmers.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is on track to deliver against the planned timeframe. The programme has spent 83% of its cumulative budget within 79.6% of its total duration. The implementation phase is for a 4.5 year period which will end on 31st December 2017.

Performance of partnership(s)

The service provider has been managing the programme well. In the review year the team leader of PMk was posted to Uganda but the programme was able to manage the transition well as Markets Group Director worked as the interim team leader. The Service provider has already selected a permanent team leader from another of its programme.

The programme is well aligned with DFID priorities. DFID constantly engages with the PMk, including through the Advisory Committee, and provides strategic guidance on programme implementation. PM works effectively through a number of private sector partners on various market development projects.

Asset monitoring and control

The programme keeps an inventory of assets owned by DFID for items valued over £1000 or which have a useful life of more than one year. The assets register is updated as new assets are procured. It is reviewed monthly along with invoices to confirm that new purchases are recorded.  Asset verification was carried out as part of the independent audit. It confirmed that the majority of assets were correctly represented on the register.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Partnership Principles were not assessed during business case design. The principles are however considered valid in reviewing Propcom Maikarfi’s approach and objectives. This project aims to support small farmers in Northern Nigeria by strengthening pro poor market systems at different stages of the selected value chains, and by working with private sector partners to increase their investment in rural commodity and services markets. The programme is implemented through a commercially contracted service provider and no funds are passed through government systems. This is in direct response to the high fiduciary risks associated with funding through the Nigerian government. As an example of this approach, the programme is currently providing policy advice and technical assistance to build market systems for a tractor importation scheme of Federal Ministry of Agriculture funded by a long term soft loan from the Brazilian Government. This engagement will ensure that a well function market system exists for small farmers to benefit from these tractors at an affordable price. However, the programme will not enter into any transactional relationship with Federal Ministry of Agriculture at any stage of this technical co-operation.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation:
Propcom MaiKarfi’s interventions are generally innovative and experimental in nature, with limited evidence before implementation. This is as expected for an M4P programme of this type. However, given the limited evidence for interventions it is extremely important that PMk records and documents lessons from its interventions and monitors the progress of interventions carefully to safeguard value for money. It is currently using Dynamic and Adaptive Monitoring System (DAM) for this purpose.

The intervention guides that PMk has for each intervention are now a strong resource, they include a detailed theory of change and results chain for each intervention. These form an important part of the results measurement process (see below). As the intervention guides become embedded in the programme documenting where these detailed theories of change have held and where they have not will provide extremely valuable lessons and evidence for the programme and others.

PMk now also has a reliable platform for designing and recording intervention assessments. The programme has conducted a large number of these assessments across interventions has a commendable focus on assessing impact. Now that this process is in place the programme is in a good position to be more strategic in planning assessments. This planning should look not only at frequency of assessment but also scale, and consider accountability issues as well as evidence for programme planning. For example, the size of the agricultural inputs results mean that more focus should be given to verifying and understanding these results than has so far taken place.

The programme had a voluntary Donor Committee on Enterprise Development (DCED) audit between March and May, 2016. The audit reviewed a representative sample of interventions contributing to the logframe and considered in the value for money reporting framework of the program. The program rates 388 out of 500 possible points for the MUST control points and 90 out of 120 possible points for the RECOMMENDED control points. This shows a good progress has been made in achieving the results and the value for money by the programme, however there is still some room for improvement in achieving these indicators.

The independent evaluation of Propcom MaiKarfi moved forward in 2016 and completed the baseline assessment in two markets for the evaluation (village poultry and Babban Gona). The evaluation has provided valuable evidence to complement PMk’s own studies.

The service provider for evaluation is Upper Quartile, which is independent of the programme’s implementation service provider and will continue its independent evaluation two years after the programme ends in December 2017. The impact assessment and the learning will be synthesised and made available to DFID by the independent evaluation service provider.

Monitoring progress throughout the review period
Propcom MaiKarfi has made significant progress in developing their results measurement systems during 2016. A comprehensive results measurement approach is now in place for each intervention with an effective system for aggregating into programme level summary results. This aggregation approach also considers potential for overlap between interventions.

PMk’s results system is now capable of providing comprehensive and regular data on programme progress. During 2017 the programme needs to embed usage of the results system across the programme and interventions – not only to provide reporting to be facilitating intervention and programme management to use the results data to understand the interventions from sustainability perspective.

Propcom MaiKarfi’s approach to on call enumerators for fieldwork exercises continues to be providing good value for money and is a model that other programmes could consider (or even look to share the on call enumerators, collaborating issues such as enumerator training).

Recommendations:

- Develop a lesson learning approach to document what has and hasn’t worked before the programme closure in 2017. This would complement the intervention guides, research / impact studies and intervention level theories of change.
- Continue to embed the results reporting process into the whole programme so that reporting and use of results is universal.
- Ensure that data protection concerns are considered in survey responses and data management (for example that only anonymised data can be accessed). PMk and DFID should develop a policy on data protection.
- Upper Quartile to ensure that Propcom MaiKarfi is able to make best use of data collected in baseline studies.
- Consider methods to improve qualitative reporting where effects are not possible to quantify – for example around displacement issues and secondary beneficiaries – to ensure that these are considered even when measurement is not possible.
- PMk should continue the good practice of publishing case studies to share their work with other programmes and ensure that monitoring and evaluation approaches and systems are not lost at the end of the programme. It should also share its DCED audit report and learning with other M4P programmes.

Beneficiaries and programme partners’ comments:

- “Propcom Maikarfi is helping us to increase our poultry vaccine production capacity by five folds with the technical assistance for our vaccine freeze dryer capacity enhancement. It is also supporting us in establishing an effective outreach and poultry vaccination programme for small farmers through our outstation posts.” Acting Executive Director of National Veterinary Research Institute.
- “AFEX has helped us in getting a better price for our crop by cutting out the middle men as we can store our crop with them and sell when the price is higher; secondly the fertiliser bags they swap for our grains are fuller and are not adulterated like the fertiliser available from some other sources.” – Small farmers using AFEX warehousing and grains for fertiliser swap services.
- “I am happy that my chickens do not die in Harmattan season anymore, thanks to the vaccine services provided by this programme.” A woman poultry farmer at the chicken vaccination event.
- “My husband is quite supportive of my work as a village poultry vaccinator, I can visit female poultry farmers in late evening and vaccinate their birds when they are free from their house hold duties.” A female poultry vaccinator trained by the programme.
- “There is a huge demand of small bags of fertiliser by the small farmers but we are not getting enough supply of it from the fertiliser companies. Small bags of fertiliser encourage women to do their small scale farming.” Fertiliser retailers and distribution partners of Propcom Maikarfi.
- “Our acha processing facility is creating livelihoods for women acha farmers and we are also planning to install small scale acha processing equipment in some communities to reach out to more farmers especially women”. The owner of acha processing plant receiving the programme’s support.
- “We will benefit from a trade by barter arrangement with AFEX where we can swap our agriculture produce for the fertiliser” Female farmers using AFEX grain for fertiliser swap service.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process