## Change Log
Version | Date | edited by | Changes
5 | 25.11.2015 | Florian F. | -) confirmed previous additions -) added output #4
6 | 18.01.2016 | Florian F., Ian MacAuslan, Matthew Powell, Victor Steenbergen | -) add examples of policy impact logs -) Clarify indicators
7 | 05.02.2016 | Florian F., Ian MacAuslan, Victor Steenbergen | -) finalise indicators
7.1 | 09.09.2016 | Florian F. | update
7.2 | 11.11.2016 | Florian F., Oladele A. | update
7.3 | 07.02.2017 | Florian F., Oladele A. | update
7.4 | 25.05.2017 | Florian F., Oladele A. | update, and added FY17/18

## Example Logs
Examples of logs to capture data for indicators:

## Logframe Outputs
Output | Impact Weighting | Indicator |  | Baseline - end March 2013 | Milestone 1 - end September 2014 | Milestone 2 - end September 2015 | Milestone 3 - end September 2016 | Milestone 4 - end March 2017 | Milestone 5- project end: March 2018
Output 1
Evaluations, reviews, and operational research studies for DFID Nigeria education programmes | 60% | Number of evaluation products signed off by DFID evaluation review processes | Planned | 0 | 2 Review of GEP3 M&R strategy, theory of change and logframe (not subject to SEQAS review) GEP3 evaluability study (not subject to SEQAS review) | 5 Reviews of GEP3 strategies, theory of change and logframe (not subject to SEQAS review); GEP3 evaluation framework; DEEPEN evaluation framework; TDP evaluation framework; DEEPEN ex ante review (not subject to SEQAS review) | 2 DEEPEN baseline report TDP baseline report | 1 GEP3 baseline report | 2 GEP3 midline report TDP midline report DEEPEN to be confirmed
|  |  | Achieved | 0 | 2 | 5 | 2 | 1
|  |  | Source | SEQAS review and DFID signoff | Strategy review and evaluability study not subject to SEQAS review | SEQAS Review and /or DFID sign-off | SEQAS Review and /or DFID sign-off | SEQAS Review and /or DFID sign-off | SEQAS Review and /or DFID sign-off
|  | Number of reviews completed and included in DFID AR system (TO BE DISCUSSED WITH DFID) | Planned | 0 | 1 DEEPEN Annual review | 2 DEEPEN Annual review 2015 TDP Annual review 2015 | 1 DEEPEN Annual Review 2016 | 2 TDP Annual Mid-term) Review 2016 ESSPIN PCR
|  |  | Achieved | 0 | 1 DEEPEN Annual review | 2 | 1
|  |  | Source | Requested by DFID not to include Annual Reviews in EDOREN Logframe, since some may be contracted through EDOREN, but are not EDOREN outputs
|  | Number of other research studies in the context of DFID-N programmes signed off by DFID | Planned | 0 | 1 FTTSS tracker study | 3 FTTSS OR study TSD study GEP3 PEA study | 3 ESSPIN Capacity Impact study TDP Teacher Supply and Demand Study DEEPEN Public-Private ("P4") Study | 1 TDP Formative Research
|  |  | Achieved | 0 | 1 | 4 - in addition a paper on aid to education in Nigeria | 3 | 1
|  |  | Source | DFID adviser confirmation/ sign off; published on EDOREN website
Output 2
Primary and secondary studies on key basic education issues in Nigeria | 20% | Number of studies signed off by DFID advisers | Planned | 0 | 2 Thematic research proposals, Review of education data in household surveys (2ndary) | 3 UBE literature review, Teacher management study, Analysis of wealth, gender and regional inequalities (2ndary) | 0 | 2 Thematic Research Study on Identifying, Recruiting, and Deploying Effective Teachers ("Teacher Quality Study") Thematic Research study on Education in Conflict | 2 Thematic Research on Evidence-based Education Policy and Practice of Teacher Recruitment and Deployment in Nigeria Thematic Research on Special Needs Education / Disabilities
|  |  | Achieved | 0 | 2 | 3 | 0 | 2
|  |  | Source | DFID adviser confirmation/ sign off; published on EDOREN website
Output 3
Education database, data tools, processes, and data reviews | 10% | Number of data quality outputs completed (reviews, workshops with programme teams) | Planned | 0 | 2 GEP3 community mapping survey review ESSPIN LGA indicator database review | 10 GEP3 survey review, DEEPEN baseline survey review; Provision of school lists for NEDS2015. 2 Zonal ASC Questionnaire workshops, support to three training workshops on UIS software for ASC. Linkage of 5 years of ASC data for EMIS states, Design of Schools Intervention database analysis tool | 4 (1) Report on effectiveness of school lists for linking ASC to NEDS2015 data; (2) support for at least 3 workshops on improving quality and timeliness of 15/16 ASC using UIS software; (3) Support for 2015_16 joint validation survey (ESSPIN/GEP); (4) support to FME in Publishing 2011/13 Digest and 2013 School Compendium online, (5) Dissemination of linked ASC data and school quality index (ISD), (6) Dissemination of SID database | 4 Kaduna EMIS workshop for LGA and state planners; NEDS OoSC report draft; Kano and Jigawa EMIS workshop for LGA planners; Kano EMIS Workshop for state planners on more advanced data use | 9 (1) Creation of School Quality Indices for All States; (2) Support to 2016/17 ASC; (3) E-Survey for factors affecting education; (4) State planners workshop for remaining states; (5) Lessons learned workshop for surveys & data gathering; (6) Learn Nigeria QA and assessment; (7) Support for at least 3 workshops on Data Use for LGA Level planners; (8) Trial methods to improve ASC coverage of Private Schools; (9) Placement of DFID school survey microdata on NBS microdata repository.
|  |  | Achieved | 0 | 2 |  | (2), (3), (5), (6) completed (1), (4) dropped due to external circumstances | 4
|  |  | Source | Reviews shared with DFID and projects; examination of SID and ASC datasets; Project reports
Output 4
Derived Knowledge and Dissemination Products | 10% | Percentage of planned communication processes delivered | Planned | 0 | Two quarterly DFIDN education portfolio meetings | 100% of outputs set out in agreed policy impact workplan completed on time (including agreed contributions to DFID strategy) 10% year-on-year growth of nigeriaeducation.org website hits | 2 (1) 100% of EDOREN-specific outputs set out in agreed policy impact workplan completed as planned on time (including agreed contributions to DFID strategy) (2) 10% year-on-year growth of nigeriaeducation.org website hits | 100% of outputs set out in agreed policy impact workplan completed on time (including agreed contributions to DFID strategy) 10% year-on-year growth of nigeriaeducation.org website hits | TBD
|  |  | Achieved | 0 |  |  | 2
|  |  | Source | Website statistics; public documents/blogs/presentations/emails; reports on meetings; comparison to dissemination plan
|  | Number of individuals participating in capacity enhancement activities | Planned | 0 | 20 Nigerian researchers trained on education research 20 Nigerian government officials attending EDOREN dissemination workshops or meetings on education research | 50 Nigerian researchers trained on education research 50 Nigerian government officials attending EDOREN dissemination workshops or meetings on education research | 3 (1) 20 Nigerian researchers trained on education research (2) 50 Nigerian government officials attending (3) EDOREN dissemination workshops or meetings on education research | 20 Nigerian researchers trained on education research 50 Nigerian government officials attending EDOREN dissemination workshops or meetings on education research | same ration growth for both; this year: 33 Teacher; +10 disability
|  |  | Achieved |  |  |  | 3 | TR5: 20; Conflict: Borno: 8; NAEC: high level of particpation 413 participants in workshops, of which at least 138 state officials | this year: 33 Teacher; +10 disability
|  |  | Source | EDOREN reporting; specific documentation; gather feedback forms (also track trajectory on some, e.g. team leaders who are in several studies)

## Logframe Intermediate Outcomes
# | Outcome | Indicator |  | Baseline - end March 2013 | Milestone 1 - end September 2014 | Milestone 2 - end September 2015 | Milestone 3 - end September 2016 | Milestone 4 - end March 2017 | Milestone 5- project end: March 2018
1 | Outputs are used by DFID and DFID education portfolio programmes to improve portfolio design and implementation | Examples of use of EDOREN evidence by DFID and DFID education portfolio | Planned |  |  |  | Methodology for production of examples agreed with DFID (joint with milestone for outcome below). Quarterly reports on the indicator submitted to DFID. | Examples of use highlighted in Quarterly reports | EDOREN qual impact studies under PI, including case study of failures to achieve impact | Note: EDOREN reports on the indicator, i.e. use cases of EDOREN evidence, every quarter, by giving concrete examples and cases; in addition, for the higher-level outcomes, EDOREN produces a case study for each of the higher-level outcomes, which reflects a detailed, specific contribution story.
|  |  | Achieved |  |  |  | completed | ongoing
|  |  | Source | EDOREN reporting EDOREN annual qualitative survey of DFID portfolio programme staff (DFID and programmes) DFID project annual reviews
2 | Outputs are used by state and federal governments to improve education policy design and service provision | Examples of use of EDOREN evidence by state and federal governmements | Planned |  |  |  | Methodology for production of examples agreed with DFID (joint with milestone for outcome above). Quarterly reports on the indicator submitted to DFID. | Examples of use highlighted in Quarterly reports;
|  |  | Achieved |  |  |  | completed | ongoing FME supprting and continuing NAEC Current Thematic Research specifically follows state-level implementation of previous recommendations from EDOREN research
|  |  | Source | EDOREN reporting EDOREN survey of relevant government staff at federal and state level EDOREN learning logs
3 | Education data collection and analysis in Nigeria is improved in key states | ASC in GEP3 states completed on time, with improved quality (coherence, coverage, etc…) | Planned |  |  | GEP3 states EMIS strategy aligned with other states Adoption of UIS software for EMIS in all GEP states and use in 14/15 ASC Adoption of new ASC questionnaire by GEP/UNICEF FME agreement to new ASC questionnaire for all States | 3 Agreement at National EMIS of new questionnaires Successful 15/16 joint validation survey for ASC Adoption of linked school quality index and SID for programme monitoring | 1 Significant quality difference between GEP and non-GEP state ASC achieved | 3 ASC in GEP3 states completed on time, with improved quality (coherence, coverage, etc…); Improved use of ASC data by LGA and state planners reported; initial state plans for improving private school coverage.
|  |  | Achieved |  |  |  | achieved | achieved
|  |  | Source | EDOREN Policy Impact log: EDOREN involvement in EMIS related decisions (concrete examples), and documentation of continuous contribution to EMIS in GEP3 states Other DFID Education Programme reports, EMIS Publications; Appearance of EMIS datasets; FME and NBS websites & publications

## Logframe Higher-level Outcomes
# | Outcome | Indicator |  | Baseline - end March 2013 | Milestone 1 - end September 2014 | Milestone 2 - end September 2015 | Milestone 3 - end September 2016 | Milestone 4 - end March 2017 | Target - March 2019
1 | Improved DFID education portfolio performance | Weighted scores from DFID programme annual reviews (GEP, TDP, DEEPEN each 30%; and ESSPIN 10% in total, and for each programme 50% for total AR score; 50% for AR score on results/evidence) | Planned | NA | NA | NA | 3 | 3
|  |  | Achieved |  |  | 2.75
|  |  | Source | See Sheet "Scoring for Int Outcomes"
|  | Contribution stories of where EDOREN work is used by DFID or DFID projects to improve performance | Planned |  |  |  | Methodology for production of case studies representing contribution stories agreed with DFID (joint with milestone for outcome below). [Note: Intermediate outcomes are evidenced by concrete examples reported every quarter; Higher level outcomes by more in-dept case studies] | One case study completed
|  |  | Achieved |  |  |  | completed | completed
|  |  | Source | EDOREN case studies; feedback from DFID portfolio programmes
2 | Improved education policy development and implementation | Contribution stories of where EDOREN work is used by government/policy makers to improve policy | Planned |  |  |  | Methodology for production of case studies representing contribution stories agreed with DFID (joint with milestone for outcome below). [Note: Intermediate outcomes are evidenced by concrete examples reported every quarter; Higher level outcomes by more in-dept case studies] | One case study completed
|  |  | Achieved |  |  |  | completed | completed
|  |  | Source | EDOREN case studies, including qualitative surveys of partners and policy makers

## Logframe Impact Statement
EDOREN Impact Statement
EDOREN's Impact is aligned with DFID Nigeria's top-level impact statement and indicators. Given DFID's current transition between operational plans, we tentatively formulate this as "Evidence informed policy and practice lead to improved education access and outcomes"

## Scoring for HL Outcomes
AR scores | Programme | 2014 | 2015 | 2016 | 2017
Total score | DEEPEN | 3 | 3
| GEP3 | 1 | 2
| TDP | 3 | 3 |  |  | placeholder!
| ESSPIN | 4 | 3
Learnig score | DEEPEN | 2 | 2
| GEP3 | 1 | 2 |  |  | doesn't have specific learning-focussed output | GEP3 suggestion: score based on knowledge-centric AR recommendations implemented
| TDP | 3 | 3 |  |  | placeholder! | #3
| ESSPIN | 4 | 3 |  |  | doesn't have specific learning-focussed output
Combined | DEEPEN | 2.5 | 2.5 | 0 | 0
| GEP3 | 1 | 2 | 0 | 0
| TDP | 3 | 3 | 0 | 0
| ESSPIN | 4 | 3 | 0 | 0
A++ = 5; A+ = 4; A = 3; B = 2; C = 1
Average scores
Total |  | 2.75 | 2.75 | 0 | 0
Learning |  |  | 2.5 | 0 | 0
Weighted score |  | 2.35 | 2.55 | 0 | 0