Annual Review - Summary Sheet

Title: Ghana Oil and Gas for Inclusive Growth (GOGIG)
Programme Value: £17,315,596		Review Date: 14/11/2017
Programme Code: 204330	Start Date: 31/12/2014 / Contract Start Date: 8/12/2014	End Date: 31/12/2019

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	B	A	A	A+
Risk Rating	Medium	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

This is the third full year of implementation of the GOGIG programme, which is at the mid-point of the total life of the programme. Significant achievements have been made over this year, as evidenced by clear policy and planning direction, increased revenue capture, and necessary legislative changes. The Annual Review stakeholder meetings all demonstrated strong buy-in from government to the oil and gas sector reform objectives of the GOGIG programme.

In this year the programme has continued to build strong relationships between GOGIG advisors and corresponding government partners, and strengthened execution and coordination among government insitutions and local planning processes. The GOGIG programme has addressed all key recommendations from the 2016 Annual Review, which included revisions to the logframe, finalising the strategic approach to development and management of projects and improving GOGIG’s understanding of and contribution to climate change and gender. GOGIG has done well to adapt to the changed environment and new governmental partners brought about by the election, and has successfully built on previous achievements and lessons learnt. The programme has established its credibility as a partner to key stakeholders in Government of Ghana (GoG), under both the previous and new administration. This increased influence and credibility is evidenced by increasingly frequent invitations by government partners to undertake more significant and strategic work across the sector. Accountability partners have also made significant inroads in their target constituencies.

The programme is performing strongly against its annual logframe targets, having met all its milestones and performed above expectations in some cases.

Highlights of key results achieved this year include:

1. Support to the new Government of Ghana (GoG) to set a clear agenda for the energy sector. The programme provided technical input and support to a comprehensive energy policy.
2. Revenue capture: This year GOGIG support to Ghana Revenue Authority (GRA) contributed to them winning a dispute with a large oil company, which resulted in capturing USD 22million of revenues that were not previously collected.
3. Macroeconomic and fiscal management: The team has engaged with the Office of the Vice President and the Economic Management Team, setting up an an inter-agency group tasked with improving macroeconomic policy-making to effectively manage the upcoming petroleum growth.
4. Improving accountability: GOGIG has supported the Ministries of Planning and Finance introduce new measures towards enabling the monitoring of progress on Annual Budget Funding Amount (ABFA)[1] funded projects, responding to reports from accountability partners Africa Centre for Energy Policy (ACEP) and the Public Interest and Accountability Committee (PIAC) who have undertaken monitoring of projects listed in government reports and reported the non-existence of many of these projects.
  [1] Annual Budget Funding Amount - the allocation from petroleum revenues which goes into the annual budget.
5. Citizen engagement: GOGIG supported greater citizen engagement on oil and gas sector by facilitating citizen critique on oil and gas content of election manifestos.

GOGIG has responded to all the key recommendations from the 2016 annual review (annex 1).

Some of the key lessons learnt which continue to inform programme delivery include:

- Coordinated cross government agency action is needed for implementation of key decisions related to management of the sector, and yet government agencies are typically averse to working collaboratively. GOGIG has learnt the need to broker high level relatonships, e.g. with the Office of the Vice President, in order to secure buy-in and oversight of implementation of key decisions that cut across government agencies.
- Government Negotiation Team (GNT)[2]: related to the first lesson, there was much feedback about the lack of coordination with other relevant government departments and the GNT. If sufficient time and consultation is not committed from the beginning, there can be a breakdown in cross-governmental coordination as has been the case with one current negotiation with an international oil company. GOGIG should consider how best to support and improve upon the GNT process.
  [2] Government Negotiating Team comprises representatives of several government agencies who are involved in negotiations with companies seeking to be awarded blocks for exploration – see annex 2 for further detail.
- The use of analysis and research as the basis for dialogue promotes openess and enables more effective targeting of GOGIG’s support. Government bureacrats are generally cautious about admitting gaps and lapses within their institutions, even where these are widely acknowledged, so evidence-based conversation is essential.
- Risk management: Whilst GOGIG successfully navigated the election and change in relevant governmental partners, the extent of change in terms of partners does not appear to be fully anticipated. It will be important to ensure such a potential risk is mitigated in future. Much of the success of GOGIG rests upon the strength of its relationships, therefore should those change it presents a high risk to the success of the programme.

Summary of recommendations for the next year

Revisiting the programme scope: Despite success at meeting programme milestones to date, GOGIG has yet to fully articulate the ‘inclusive growth’ aspect of the programme in its theory of change. Currently the ToC has a narrow focus on revenue capture leading to inclusive growth. The Steering Committee has reflected on this, particularly in relation to doing no harm, and aspects of gas-to-power. The next phase of the programme will need to not only ensure this is delivered, but also amend the logframe to ensure that inclusive growth can be accurately captured in results. The programme Theory of Change should be revisited with a view to better defining existing portfolio issues and capturing the programme’s engagement with newer issues as the context shifts.

Policy coordination: fragmentation and sensitivities across the relevant government institutions has occasionally led to reforms in silos and policy incoherence (e.g. the unpublished extractives and energy policy, negotiations, etc). With the change in government comes an opportunity to drive greater policy coherence in oil and gas reform. GOGIG should continue to play a strong coordination role and look to streamline engagement on policy and regulation reform.

Logframe: Requires changes in terms of the weighting of outputs, better encompassing a broader view on “inclusive growth”, making clear which outputs relate to which government stakeholders, and distinguishing between output indicators on “actions taken” and “initiatives delivered”. At outcome level, it would be useful to include indicators that reflect revenue being used for inclusive growth areas, and/or perception surveys or some sort of indicator that captures citizen feedback on how increased capture of oil and gas revenue is leading to real improvements on the ground.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Ghana is considered to be a politically stable country, but with economic challenges. There was a slowdown in economic growth in 2016, lower than expected oil prices and a large fiscal deficit. The general election in December 2016 brought a new government from a different political party into power. With respect to the oil and gas sector, the new government has distinct policy priorities, such as an explicit recognition of the potential developmental benefits of gas, a greater focus on revenue capture, and job creation. The economic and public finance challenges of Ghana constrain the government’s ability to maximise sustainable benefits from the good governance of the oil and gas sector.

The Ghana Oil and Gas for Inclusive Growth (GOGIG) programme is a five year programme, conceived in mid-2013 and launched in January 2015 to support Ghana to maximise its oil and gas resources for inclusive growth. GOGIG works on this objective through the delivery of four inter-related outputs.

Output 1: Regulatory mandate and policy coherence of the oil and gas sector enhanced: Clear policy, robust legislation and an effective and accountable regulatory body are necessary prerequisites to regulate private sector operations, and ensure the best possible development progress is achieved from the use of natural resources. The primary GoG partners for this output are the Ministry of Energy (MoE) and the Petroleum Commission (PC).

Output 2: Oil and gas revenue capture and oversight improved: In order to maximise direct benefits from the oil and gas sector, GoG must have the capability to collect the revenues it is entitled to from the sector. The primary GoG partner for this output is the Ghana Revenue Authority (GRA).

Output 3: Oil and gas revenue management and oversight improved: This output works to ensure transparency in the use of revenues collected. It is also supporting GoG to avoid macroeconomic policy decisions with adverse consequences, such as high fiscal dependence on revenues in times of high oil prices, or inappropriate use of the sovereign wealth fund (Ghana Heritage Fund). The primary GoG partner for this output is the Ministry of Finance (MoF), with significant collaboration with the Bank of Ghana (BoG) as well.

Output 4: Enhanced public engagement through, but not limited to, increased accountability actors' capability for oversight of the oil and gas sector: This is critical to put the necessary pressure on government to precipitate change in more contentious areas for reform. It requires strong linkages and inputs from outputs 1-3 so that actors can create an agenda for holding government to account. This output works with accountability actors including the Africa Centre for Energy Policy (ACEP), and the Natural Resources Governance Institute (NRGI), who support the Public Interest Accountability Committee (PIAC) for scrutiny of the use and management of petroleum revenue.

Output 5: Adaptive and effective programme management: This is an internal facing Output that assesses the ways in which the programme positively responds or adjusts to learning and understanding of its context. It also focuses on assessing the evidence of quality management practices that support programme delivery. This output will be removed from the logframe following this annual review, as programme management is monitored through other performance management mechanisms.

The expected impact of the programme is inclusive economic growth and poverty reduction through a well-managed oil and gas sector.

The outcome of the programme is increased effectiveness, efficiency, and accountability of the management of oil and gas resources in Ghana.

The programme has a Steering Committee, which forms a key part of GOGIG’s engagement with GoG. The SC provides direction on the programme’s contribution to its ultimate inclusive growth objective. Each of GOGIG’s key partner agencies - Bank of Ghana (BoG), Ghana Revenue Authority (GRA), Ministry of Finance (MoF), Ministry of Petroleum (MoP), Petroleum Commission (PC) - are represented on the Steering Committee.

Changes to context since last AR

In the last year, there have been a number of significant changes in the wider context within which the programme operates. Many of these changes are driven by the result of the 2016 election, which led to a change of government in Ghana. There was generally a slowdown in GOGIG’s engagement with GoG partners either side of the December election, with much of 2016 dominated by the forthcoming election and the first seven to eight months of this year taken up by the gradual formation of a new regime.

- The most significant structural change in government following the election has been the re-creation of the Ministry of Energy (MoE), resulting from a merger between the Ministry of Power and the Ministry of Petroleum.
- There is also an increasingly prominent role for the Economic Management Team, managed by the Office of the Vice President, and engagement with the newly created Office of the Minister of Planning, who have a key role in the EMT
- There was a leadership change in all the sector agencies that are relevant GOGIG partners, which has meant that effort had to be invested in rebuilding relationships with new appointees.
- A number of key civil society leaders have moved into the new government – most notably, the new Deputy Minister responsible for petroleum at the MoE is the former head of ACEP. This carries a risk of weakening civil society actors, but also demonstrates the effectiveness of the GOGIG-funded accountability actors and provides an opportunity to make progress on governance improvements in the extractives sector generally through previous relationships from the accountability sector.
- In the year under review, the programme has expanded its support to the Office of the Minister for Planning, Fisheries Commission and the Ministry of Environment, Science, Technology and Innovation. The programme also support the cross-agency Government Negotiation Team, and has also begun purposefully engaging the Office of the Vice President as part of overall efforts to improve governance in the sector.
There are also some important contextual factors that are not directly related to the election result:
- The economy is showing signs of recovery from 2016, with macroeconomic indicators such as interest rates and inflation trending positively. However, the fiscal situation remains fragile, with underperformance on ambitious revenue targets in the 2017 budget. The latest IMF Debt Sustainability Analysis in August 2017 judged Ghana to be at high risk of debt distress.
- For the oil sector, it is expected that bottlenecks to production will be reduced and production will increase significantly across Ghana’s Jubilee and Tweneboa and Enyenra, Ntomme (TEN) fields and the Sankofa project. Signs of increased production and revenues have already been observed in the second half 2017. In September, the maritime boundary dispute with Cote D’Ivoire was resolved in Ghana’s favour. This has removed a major constraint, and some associated uncertainty, to the further development of the offshore petroleum sector.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The programme’s outcome is “Effective management of oil and gas resources”. This is measured by improving scores in the Natural Resource Governance Insitute’s (NRGI) Resource Governance Index (RGI), the value of additional oil revenues captured, and the number of government actions influenced around the management of oil and gas resources. The table below indicates the progress made in the year under review:

Indicator(s)	Milestones	Progress
RGI[3] score for oil and gas	3% improvement over baseline score (approximately 66)	Exceeded: Actual score achieved: 67, which represents a 4% improvement over the baseline score of 64.
Value of additional revenue captured	$4.9 million	Exceeded: $16.6 million
Number of government actions positively influenced around the management of oil and gas resources	5	Achieved: 5
[3] The RGI measures the performance of Ghana in oil and gas resource governance through three major components - value realization, revenue management and enabling environment along five major performance ranges - Good (>74), Satisfactory (60-74) Weak (45-59) Poor (30-44) Failing (<30).

Two out of three of the milestones for the Outcome level indicators have been exceeded, and one achieved. The target for indicator 2 was set using the basis for revenue projections contained in the business case for the programme. It was significantly exceeded due to the nature of the specific opportunity that generated the additional revenue i.e. the resolution of a dispute with a major oil company on previously unpaid revenues.

Resource Governance Index
Ghana obtained a score of 67 points out of 100 for the 2017 edition of the oil and gas RGI, making it the best performer in Africa. Ghana’s score of 67 represents a 4% improvement over the 2014 benchmark score of 64. Scores on the three main components of the index, are 65 on revenue management and value realisation respectively, and 70 on enabling environment. GOGIG supported work across all the three components, with contributions to subcomponents on taxation, licenses, regulatory quality, and voice and accountability.
Additional revenue captured
Building on the gains from previous GOGIG capacity interventions for GRA, the programme continued to perform significantly on revenue capture. In this reporting year, the government successfully won a dispute over Kosmos’s use of capital allowances from its Tweneboa-Enyenra-Ntomme (TEN) field operations to minimise its corporate income tax payments on its Jubilee field operations. As a result, GRA captured an additional $22 million in unpaid corporate income tax and interest payments in 2017.
The two specific trainings that GOGIG provided which contributed to this achievement were on Petroleum Accounting and Auditing, and understand of Upstream Petroleum Law. At the time the training was delivered, the dispute with Kosmos had begun. GRA were not clear about when the use of capital allowances for pre-production costs should commence. Information provided during the trainings clarified the legal provisions on capital allowances and relevant auditing and accounting arrangements. The feedback from the former Head of the Petroleum Unit, who led the discussions with Kosmos on behalf of GRA, was that the trainings enabled him stand his ground and also convince his superiors in GRA that they should claim the revenues and the interest on deferred payment. On this basis, senior officials in GRA placed a rating weight of 75% as GOGIG contribution to the $22 million captured which translates into an attribution value of $16.6 million.
Government actions influenced
The programme continued to perform strongly in shaping government policies, priorities and practices for effective management of the oil and gas sector. Specifically, GOGIG influenced 5 key government actions outlined below:
            - With the change of the government in Ghana, there is a constitutional requirement for the President to submit his development priorities to Parliament for approval. The Office of the Minister for Planning (OMfP) leads on the development of this Coordinated Programme of Economic and Social Development policies. GOGIG provided two consultants into the OMfP, to provide input for the sections on energy, petroleum, and inclusive development.  The policy documents were developed and approved by Cabinet very quickly by historical standards.
            - There are currently regulations being developed for the implementation of the Exploration and Production (E&P) Act passed last year. GOGIG and its accountability partners have worked to ensure that these regulations include promotion of open contracting and contract transparency. Recommendations adopted by the MoE include specifying timelines for all actions specified in the E&P Act, provisions for publication of petroleum agreements, and rationale for direct negotiations in cases where competitive process is not followed.
            - GOGIG has provided a technical consultant to the MoE to provide input and coordinate working sessions that led to the draft Energy Policy for Ghana. The draft policy is undergoing initial consultations with sector agencies. It is a significant milestone as it will represent the first ever comprehensive policy for the energy sector once finalised.
            - ACEP contributed to the GoG’s prioritisation of ABFA allocations through sustained advocacy for a target of 18% of ABFA spending on agriculture. Government allocation of ABFA to the agriculture sector increased from 7% in 2011 to 20% in 2017. Expenditure data for January-September 2017, however, shows that only 8% of ABFA spend was in the sector[4], signalling the need for greater monitoring and follow up advocacy on the government’s commitments.
              [4] Ministry of Finance, Budget 2018 Statement, Table 14
            - At the end of 2016 the government announced the decision to decommission the Saltpond oil field, which responds to PIAC’s recommendations in the 2015 annual report (published in 2016). With low oil prices and a production cost of $31.22 per barrel, this decision has averted the risk of government incurring losses from a field that is no longer profitable.

Overall output score and description
The overall output score for the GOGIG programme is A+ based on the output milestones being moderately exceeded. Feedback from stakeholders shows strong government partner support, and performance on outputs is feeding through into good performance on outcome indicators.

Output	Description	Weight	Risk Level	Score
1	Regulatory mandate and policy coherence in the oil and gas sector enhanced: / two out of three indicator milestones have been exceeded, with one fully achieved.	30%	Moderate	A+
2	Oil and gas revenue capture and oversight improved: / one out of three indicator milestones exceeded and two fully achieved.	25%	Moderate	A+
3	Oil and gas revenue management and oversight improved: / one out of three indicator milestones exceeded, with the remaining two fully achieved.	20%	Moderate	A+
4	Enhanced public engagement through, but not limited to, increased accountability actors' capability for oversight of the oil and gas sector: / one out of three indicator milestones slightly exceeded, with the remaining two fully achieved.	20%	Minor	A
5	Adaptive and effective programme management: / both indicator milestones have been fully achieved.	5%	Minor	A

Key lessons

- Coordinated cross government agency action is needed for implementation of key decisions related to management of the sector, and government agencies can be resistant to working collaboratively. GOGIG has learnt to broker high level relatonships, e.g. with the Office of the Vice President, to secure buy-in and oversight of implementation of key decisions that cut across government agencies.
- Government Negotiation Team (GNT): Related to the first lesson, there was much feedback about the lack of coordination with other relevant government departments and the GNT. Whilst some departments felt this was not an issue since any negotiation would inevitably require their sign off in Parliament, therefore ensuring they would get consulted eventually, the seriousness and credibility of the negotiating process should be considered. GOGIG should consider how best to support an improved GNT process.
- The use of analysis and research as the basis for dialogue promotes openess. Government partners are generally cautious about admitting gaps and lapses within their institutions, even where these are widely acknowledged, so evidence-based conversation is essential.
- Managing turnover of government partners: Whilst GOGIG successfully navigated the election and change in relevant governmental partners, the extent of change in terms of partners did not appear to be fully anticipated. It will be important to ensure such a potential risk continues to be monitored and mitigated in future. Much of the success of GOGIG rests upon the strength of its relationships, therefore should those change it presents a high risk to the success of the programme.
- The limits of treating petroleum revenue as separate from the rest of the fiscal framework: The Petroleum Revenue Management Act creates a separate regime for the management of revenues from the sector. However, the better management of petroleum revenue is dependent on how good the broader systems are. The programme has had to engage with broader public financial management issues, such as contributing to the establishment of an Inter-Agency Modelling Team which deals with revenue management issues more broadly than petroleum.
- Capability of accountability actors – using the approach of targeted issue-based training and facilitating joint advocacy coalitions has been more effective in realising specific demands and results rather than just investing in institutional capability.
- Approach to Political Economy Analysis – the programme has moved away from relying only on externally commissioned PEA and is now using an approach of drawing on team insights and then complementing this with an external perspective. This has proved useful in harnessing the team’s knowledge of the context, validating programme direction, and strengthening the design of projects.

Key actions

Better definition of the programme’s portfolio of issues: The programme is currently defined by broad portfolio issues (inclusive growth, regulatory system, revenue capture, revenue management, accountability, and managing local impacts) which provide the framework for prioritising around which all activity is organised. However a more explicit focus on specific objectives within each issue is required. For example on the public financial management workstream (output 3), there is greater demand on the monitoring and evaluation of revenue spending from MoF and MoE, and appetite to transfer learning from petroleum revenue management to other areas.

The programme team should consult the Steering Committee and SRO on identifying more specific objectives within the portfolio issues. (Jan 2018)

New issues to consider for the programme scope: given the changing context there are new issues and shifts in GoG priorities that have implications for the programme scope and theory of change. These newer areas include local impacts (environmental and social) particularly with increased onshore activity, the role of gas in generating power, and local content and employment issues.

Any new areas in the programme scope must take into account what is achievable within the programme duration, and how it fits with the activities of other programmes such as Western Region Coastal Foundation and the DFID macroeconomic technical assistance programme. The programme team should, in consultation with the Steering Committee and SRO, consider the feasibility and additionality of GOGIG on each of these newer issues. If the decision is taken in favour of including these areas of work, the team will identify specific actions, and revisit the overall portfolio of issues and theory of change (programme team, February 2018).

Review existing partnerships in light of new opportunities and changing context. For example, the level of support for Bank of Ghana and draw back from sustaining the same support in capacity building, considering the high level of capability within the team.[5] (programme team, immediate)
[5] The 2017 capability assessment rated the team as being on level 6 of a 7 point scale

Increase focus on monitoring and use of petroleum revenues: this workstream should expand given that it is the key link from the oil and gas sector to inclusive growth in the programme Theory of Change and increased demand for this support from MoF and MoE. (programme team, immediate).

Future engagement with EITI: This year GOGIG had to fund the validation reporting of the Ghana Extractives Industry Transparency Initiative, to avoid Ghana being taken out of EITI. However, the World Bank Trust Fund on Extractives Global Programmatic Support (EGPS), which DFID contributes to, is meant to support in-country EITI initiatives, and the World Bank did not arrange for timely disbursement of funds. In future years, DFID Ghana should consult IFID and the GOSAC extractives governance adviser on matters related to EITI and EGPS. (SRO, ongoing)

Collaboration with other accountability programmes: GOGIG should continue to work closely with the Strengthening Action Against Corruption (STAAC) and Strenghtening Transparency Accountability and Responsiveness (STAR) programmes to address sensitive issues such as Beneficial Ownership. (ongoing)

Review programme resourcing and team capacity in light of newer areas of work, and the administrative burden of increasing grant-making as the accountability work stream expands its range of partners. (programme team, February 2018)

Revise approach to 10% payment modality, which is currently for specific learning milestones and link instead to a quarterly exercise in codifying learning across different programme activities. (programme team to present proposed new approach to SRO, Jan 2018)

Sustainability: Given that the current programme ends in 2019, there is a need to start planning for any continuation of programming after this time. Within the current programme, the SRO and programme team should take stock of programme activities to ensure that they are being implemented (and new activites are designed) with a view to sustaining impact beyond 2019. (SRO and programme team, early 2018).

Has the logframe been updated since the last review?

Yes. Following recommendations from last year’s annual review, revisions to the logframe were finalised and approved by the DFID Results Advisor in August 2017.

Given the potential shifts in focus or emphasis of the programme, it is recommended that the logframe undergo a further revision to be completed in conjunction with the Theory of Change revision, no later than February 2018. Recommendations for logframe revision:

  1. Consider merging some output indicators such as  1.1 and 1.2, 2.2 and 2.3, 3.2 and 3.3. This is linked to a broader point of ensuring that the difference between “actions” and “initiatives” is clear and that significant achievements of the programme can be reflected in the logframe rather than being rolled into an aggregate number on actions.
  2. Remove output 5 as programme management performance is captured through other performance management systems.
  3. Consider an output level indicator on inclusive growth that includes non-revenue pathways such as local impacts, public perceptions of benefits of oil and gas
  4. Ensure that the outcome and impact level indicators include a measure of how far oil and gas revenues are contributing to inclusive growth sectors, complementing the programme’s increased focus on monitoring the use of ABFA funds and not just overall revenue increase.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Regulatory mandate and policy coherence in the oil and gas sector enhanced
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of actions[6] taken to tackle policy, regulatory gaps, conflicts and overlaps in mandates	Two actions implemented	Exceeded: Three / Completion of energy sector policy / Petroleum Commission (PC) strategy paper on addressing overlapping regulatory functions / Analysis of Exploration and Production (E&P) law to identify consistency with other legislation and existing petroleum agreements
1.2 Number of initiatives that advance delivery of institutional mandates and cross-agency coordination in the oil and gas sector	5	Achieved: 5 / Energy Summit brought together all institutional stakeholders / Establishment of biannual dialogue between MoE and accountability actors / GNT’s role clarified and strengthened / CSOs informed MoE policy on management of liquefied natural gas / Development of business plans for all PC departments
1.3 PC’s capability[7] in sector regulation	Capability rating 3.0	Exceeded: PC attained a capability rating of 3.9 in 2017. Baseline: 1.7.
[6] Inline with GOGIG logframe definition, this indicator refers to a dynamic range of measures taken by Government partners in collaboration with GOGIG to tackle conflicts, overlaps and gaps in policies and mandates within the sector. Actions to be counted are measures considered in the generic workplan with government partners.
[7] The capability rating is a quantitative measure of changes in key capacity building priority areas with government partners. The actual scores reflect self-assessment ratings provided by the respective government institutions using a simple rating scale of 1-7, with 1 being the lowest and 7 being the highest.

Key Points

All three indicators under the Output have been achieved, with Output Indicators 1.1 and 1.3 exceeded. Highlights under this output for this year include:
Indicator 1.1: development of a comprehensive energy sector policy framework which outlines goals, implementation strategies and investment opportunities for the sector. The policy seeks to integrate the linkages between oil and gas, renewables and the power sectors, and for the first time includes a gender component. GOGIG had started work on the policy framework under the old government, engaging an expert to develop the terms of reference and scope with officials at the then Ministry of Petroleum. With the change of government, GOGIG maintained support and lobbying to complete the framework quickly, and ensure that there was public and CSO engagement on the content. The framework was completed in the first six months of the new administration, including a public and CSO engagement on the policy at an Energy Summit in June 2017. GOGIG supported the Summit and set the tone for discussions with an opening plenary session on Energy Planning for Economic Growth and Poverty Reduction. The policy framework is meant to set policy direction for the sector, and evidence of how well it is being used should be available in the coming months.
Indicator 1.2: Delivery of the MoE’s institutional mandate was supported through clarifying the role of the Government Negotiating Team (GNT), which carries delegated authority of the Minister of Energy to negotiate petroleum agreements. The GNT’s assessment of their new role emphasises the need to strengthen their capacity to (a) operationalise the competitive bidding process specified by the Petroleum (Exploration and Production) Act 919, and (b) clarify interpretation of the law through subsidiary legislation.

Indicator 1.3: Strengthening delivery of the Petroleum Commission’s institutional mandate with the implementation of a performance management system to ensure that functional remits and performance objectives across the organisation align with the mandate of a regulator. The PC’s early observations are that there is a growing culture of accountability for performance across the organisation, with staff proactively seeking clarity on how to provide evidence of their contribution to their performance objectives.

Feedback from the Ministry of Energy and the Petroleum Commission has been that GOGIG support has been very valuable in enabling them to deliver so far. However, there is a greater need to think about sustainability of its engagement. For example, the MoE suggested that beyond technical skills and support, their staff require management skills to be able to continue to deliver, coordinate and implement policy beyond the lifetime of GOGIG. The Deputy Minister of Petroleum also recommended that GOGIG should consider moving beyond its current inclusive growth focus on revenues and explore if the programme can do more on jobs and skills related work to enable the sector to create employment.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2016 annual review had 5 recommendations. In response to four recommendations on the logframe, the indicators for Output 1 were revised and strengthened in consultation with the DFID Results Advisor. The definitions were also updated to reflect the changes and to provide a common understanding of the units of measurement.

The last recommendation was for GOGIG to re-assess the requirement for the Special Adviser going forward. This was addressed by seeking the inputs of the MoP and PC on further advisor support requirements and the contract of the Special Advisor was not extended. The ministry has made requests for technical advisors in the areas of policy development and upstream sector regulation and development.

Recommendations

- Logframe review - It is recommended that the weighting of this output be revised downward reflecting shifts in the balance of GOGIG activity.
- Logframe review – The two indicators on actions taken to improve regulatory environment (indicator 1.1) and initiatives to improve multi-agency coordination (indicator 1.2) can capture similar achievements so the distinction feels artificial. Moreover, grouping actions and initiatives that are of varying degrees of significance may not reflect the programme’s achievements accurately.
- The programme should continue an increased focus on mentoring and skills transfer to officials within MoE and PC, rather than instructional, technical training, as a potential pathway to ensuring sustained impact beyond GOGIG. This has already been noted as learning from earlier capacity building work.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Oil and gas revenue capture and oversight improved
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 GRA’s capability[8] in revenue capture	Capability rating: 3.0, on a scale of 1–7	Exceeded: GRA attained a capability rating of 3.5 / Baseline - 2.5
2.2 Number of policy submissions derived from research and analyses that inform the government on revenue capture[9]	5	Achieved: 5 / Policy brief: institutional and administrative barriers along the oil and gas decision chain and measures to address them. / Policy brief: revenue collection constraints, impacts, and mitigation measures. / Policy brief: implementation challenges and measures in managing transfer pricing risk along the oil and gas value chain. / Report on petroleum revenue debts relating to surface rentals, corporate income tax, gas sales and others. / Policy brief on oil and gas revenue modelling.
2.3 Number of initiatives that identify and improve revenue capture[10]	6	Achieved: 6 / Multi-Agency Revenue Taskforce established to lead implementation of measures to address revenue losses and improve revenue capture. / GRA intra-unit coordination and operational cooperation on revenue capture initiated. / AOE model established at GRA to calculate and trigger payments. / Oil and gas revenue model operationalised at GRA to estimate expected petroleum revenue. / Inter-agency cooperation to ensure unified government position on calculation of AOE payments / Recommendations on report on ‘Potential Revenue Losses’ adopted
[8] The capability rating is a quantitative measure of changes in key capacity building priority areas with governments partners. The actual scores reflect self-assessment ratings provided by the respective government institutions using a simple rating scale of 1-7, with 1 being the lowest and 7 being the highest.
[9] This indicator measures both GOGIG’s and its partners’ policy submissions on additional revenue or losses identified
[10] The source frameworks for this indicator will be government partners' workplans, accountability actors reports and GOGIG's research framework.

Key Points

Two indicators under this output have been achieved, with Output Indicator 2.1 exceeded. Highlights for this year include:
Indicator 2.1: A major area of work has been a training programme on auditing for the oil and gas sector. According to senior officials[11] in the GRA, the length of time spent on auditing International Oil Companies has been reduced from six to two months as a result of this. Support continues to be provided in this area, with KPMG having been engaged to provide hands-on training to enhance usage of the IDEA electronic audit tool by the Petroleum Unit in GRA. It is worth noting that the baseline rating process included self assessments by government officials whose tendency is to overrate their level of competency. Although exceeded, the milestones were set to be reasonably ambitious
[11] The former and current heads of the Petroleum Unit

Indicator 2.2: A comprehensive diagnostic study of potential revenue losses along the oil and gas value chain, which identified potential losses of up to $612 million. The analysis estimates a potential loss of $1 million in surface rentals fees, $128 million in corporate income tax, and $483 million in Additional Oil Entitlement. Findings were presented to the Deputy Commissioner of the Large Tax Payers Office and heads of the Petroleum, Transfer Pricing and Customs Unit and further discussed with the Deputy Minister at the Ministry of Finance (MoF) and the Comissioner General of the GRA during the DFID Director General’s visit in September 2017. The study has directly led to the establishment of a multi-agency task force to coordinate government efforts in addressing petroleum revenue collection constraints, launched by the Minister of Finance in November 2017. Feedback from the MoF was that GOGIG had helped to improve coordination and build closer working relationships between the relevant government institutions, as well as help to mediate between differing positions of different agencies.

Indicator 2.3: GOGIG has supported the GRA to operationalise a petroleum revenue model, and facilitated engagement between the PC, Ghana National Petroleum Corporation (GNPC) and the GRA to establish an Additional Oil Entitlement model, which is the area identified as having the most significant potential revenue losses for GoG.

There have also been good synergies with the accountability work on Output 4 – GOGIG has supported PIAC’s efforts to put pressure on GoG and the oil companies to pay due revenues on surface rentals, contributing to GoG’s push for payment in this area.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2016 annual review had 4 recommendations. In response to two recommendations on the logframe, the indicators for Output 2 were revised and strengthened in consultation with the DFID Results Advisor. The definitions were also updated to reflect the changes and to provide a common understanding of the units of measurement.

The third recommendation required GOGIG to consider approaches to reducing revenue losses, in addition to efforts to identify additional revenues. A focus on reducing revenue losses was defined as a priority issue to be added to the programme portfolio, and the diagnostic study described above was a response to this recommendation.

GOGIG did not take forward the last recommendation to review the GRA Petroleum Unit audit manual, as it was learnt that NORAD was already providing support in this area. The programme has however provided refresher training this year and also provided manuals on the Computer Assisted Audit Techniques to the Petroleum Unit to instil institutional memory in the long term.

Recommendations

- This output works in a few areas that risk duplication with the DFID Ghana Revenue Reform Programme. The division of labour with GRRP requires clarification to ensure that the two programmes are building on each others’ success and not duplicating effort.
- GRA appears to have significantly weaker capacity than the other relevant government institutions. This should be adequately reflected and mitigated in the programme risk framework, given that it is a linchpin institution in the governance chain.
- Logframe revision – an upward revision of the impact weighting for this output should be considered, reflecting the increased demand from GoG in this area, which is also leading to greater focus of GOGIG effort on revenue capture and preventing revenue losses.
- Logframe revision – there are overlaps in activity between indicator 2.2 and 2.3. It is recommended that these indicators be merged and that GOGIG consider adding in a new indicator on activities to avert losses, or recover past revenue entitlements, to more accurately reflect programme activity.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Oil and gas revenue management and oversight improved
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 Capability of key institutions (BoG, MoF) engaged in revenue management	Capability rating: / BoG: 5.0 / MoF: 4.0	Exceeded: / BoG: 6.0, baseline 5.0 / MoF: 4.7, baseline 3.7
3.2 Number of policy submissions derived from research and analyses that inform government on revenue management	5	Achieved: 5 / Case Study for improving VFM in ABFA funded projects / Study on the use of oil and gas revenues for health and education sector / Policy proposal on fiscal sustainability from oil and gas sector / Brief on improving transparency and accountability on use of petroleum revenue / Proposal for coordinated modelling, forecasting and analysis
3.3 Number of initiatives that identify and improve revenue management	6	Achieved: 6 / VFM audits on ABFA-funded projects undertaken by the ACEP / Inclusive growth dialogue series for effective use of petroleum funds / Field monitoring visits of ABFA projects / Establishment of Inter-agency Modelling and Analysis Team (IMAT) / MoF improvement of due diligence process in field monitoring of ABFA projects / Initiating decentralised framework in government to improve ABFA project planning, implementation and M&E

Key Points

Two indicators under this Output have been achieved and Output Indicator 3.1 exceeded. Highlights for this year include:
Indicator 3.1: The capability of Bank of Ghana’s Petroleum Funds Secretariat has been improved through trainings in financial modelling and markets analysis, fixed income and derivatives analysis, and risk management, and through an upgrade to their Bloomberg Terminal. Feedback from the secretariat is that this support has enabled them to consider higher-return areas for investment, and make trades in real-time, which was previously not possible. The programme also supported the Energy, Oil and Gas Unit of the MoF to improve capacity in areas such as liquefied natural gas and oil and gas risk management. The capability assessments for BoG and MoF showed higher ratings than the milestones because the uptake from capacity building interventions was higher than had been assumed would be the case.
Indicator 3.2: GOGIG’s policy proposals have contributed to the harmonisation of macroeconomic modelling, policy analysis, and capacity building across responsible government agencies to ensure an effective framework for investment and management of oil and gas revenue. The programme strengthened its relationship with the Economic Management Team, chaired by the VP, to influence the establishment of an inter-agency modelling and analysis team (IMAT). The IMAT will be addressing weak coordination and lack of shared models across government agencies for the effective management of oil and gas revenue.
Indicator 3.3: GOGIG has supported the MoF to work with PIAC for the first time to undertake monitoring of ABFA projects at the national and sub-national levels this year. To consolidate these efforts, the programme supported the institutionalisation of district-level ABFA planning and monitoring through capacity building of local district planning officers.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2016 annual review had 4 recommendations. In response to all four recommendations on the logframe, the indicators for Output 3 were revised and strengthened in consultation with the DFID Results Advisor. The definitions were also updated to reflect the changes and to provide a common understanding of the units of measurement.

A baseline was also conducted and the baseline data for indicators was shared, discussed and agreed with DFID. An organisational capacity assessment tool was also developed as part of the baseline to collect base data for all indicators focused on measuring capability.

Recommendations

- Given the relatively high capability score for BoG, and the successful completion of training, the level of support to BoG should be scaled down.
- Ensure GOGIG work on public financial management and macroeconomic policy issues complements the existing support to government from other DFID and donor macroeconomic programmes
- There was consistent feedback from MoE and MoF on the need to invest greater effort in monitoring and evaluation of ABFA funding, and improving the capabilities of the ministries in these efforts rather than relying solely on PIAC, ACEP or other accountability actors. GOGIG should continue to provide support in this monitoring area and consider scaling up capacity building efforts with the ministries with a view to sustainability.
- Extend partnerships with the Budget Office of the Ministry of Finance in order to strengthen linkages between the oil and gas Unit and Budget Office to improve coordination on allocation of ABFA resources.
- Logframe revision – an upward revision of the impact weighting for this output should be considered, given the increased activity in the macro-fiscal space, and demnd for further monitoring activities.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Enhanced public engagement through, but not limited, to increased accountability actors' capability for oversight of the oil and gas sector
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of initiatives that target the inclusion of citizens' inputs in oil and gas issues	8	Achieved: 8 / ACEP’s public forums on VFM audit findings of ABFA selected projects. / PIAC’s regional-level forums to educate and elicit citizens’ inputs on petroleum revenue management. / PIAC’s district-level forums to educate and elicit citizens’ inputs on petroleum revenue management.[12] / Oil and gas content in election manifestos critiqued by citizens. / Parliamentary election debate platform sessions. / Informed citizens’ engagement on oil and gas issues in the 2016 election campaign discourse. / Citizen inputs for energy sector development collected and shared with political parties. / Citizen forum to preserve the sanctity of Heritage Fund and not be used for free secondary education
4.2 Number of joint government accountability actors' engagement on key sector issues	6	Achieved: 6 / Interrogation of government budget by sector technical specialist from CSO. / E&P regulation informed by the participation of CSOs. / CSO participation in Energy Summit / CSO and government engagement on progressing local content implementation. / Joint engagement on GRA indebtedness to Ghana Gas / CSOs’ and government’s discussion to improve transparency in counterpart funding of ABFA projects.
[12] This was a separate initiative to the regional level forums which was introduced by GOGIG for PIAC and has been institutionalized by PIAC as part of their annual public engagements.

Key Points

Two indicators under this Output have been achieved, with Output Indicator 4.3 (table on next page) slightly exceeded. Highlights for this year:
Indicator 4.1: GOGIG, through its accountability actors, created knowledge products and engagement spaces for citizens to deepen their participation and increase their inputs into oil and gas governance issues. The engagement spaces created by the election support projects improved citizens discussions and demand for better management and governance of the sector. For example, ACEP hosted public forums on audit findings on the VFM of selected ABFA projects, and PIAC hosted regional and district level forums to reach out to citizens on issues of petroleum revenue management.

Indicator 4.2: GOGIG facilitated the participation of CSOs at the MoE’s Energy Summit. The programme has also brokered a biannual engagement between MoE and accountability actors, with the first of this series occurring on 23 July 2017. These engagements became a catalyst for promoting inclusive governance and a medium for negotiating an uptake of accountability actors policy recommendations, for example improved transparency provisions in the E&P act.

Indicator(s)	Milestones	Progress
4.3 Number of step-change actions undertaken by targeted accountability actors	7	Achieved: 8 / Improvement in PIAC's capacity led to: / institutionalised engagement with relevant ministries, departments and agencies (MDAs) on its report findings; / a step change in PIAC’s public profile and visibility including securing an audience with the President for the very first time since its establishment in 2011; / communication manual developed to guide media and public engagement sessions; / independent capacity to effectively manage and account for grants received from donors; and / Other step-change actions: / effective engagement of government on contract transparency assumed by CSOs; / issue-based accountability actors coalition established / effective succession of leadership in ACEP; / coordinated accountability actors’ actions and policy recommendations on energy sector institutional alignment and local content.

Indicator 4.3: PIAC has strengthened its organisational effectiveness and the technical capability of the Committee members. This has to led increasingly confident public engagement, such as presenting their annual report on the use of oil revenues to citizens at district level. PIAC’s profile and growing visibility contributed to its meeting with the President for the very first time since its establishment in 2011. It has institutionalised engagement with relevant ministries, departments and agencies (MDAs) on its report findings. It now has independent capacity to effectively manage and account for grants received from donors.

A significant step change for the group of GOGIG accountability actors was a shift to an approach of joint issue-based coordinated engagement, rather than individual organisations having separate advocacy agendas. The programme has worked to improve coordination and build capacity for accountability actors to engage on issues beyond the traditional focus on revenue use, such as contract transparency and energy sector reform.

Last year, management of the two accountable grants to ACEP and NRGI transitioned from DFID to OPM/GOGIG. In October this year, the first phase of the contract with NRGI came to an end and handing over processes of the PIAC project to GOGIG is currently underway. Discussions are on-going with relevant parties on the nature of the second phase of support by NRGI to PIAC. The programme also provided successful support to a wider network of accountability actors and CSOs during the 2016 election. The partnership network for the accountability work has expanded to include a number of other organisations such as Ghana Extractive Industry Transparency Initiative (GHEITI), Ghana Industrial Trawlers Association (GITA), Civil Society Platform on Oil and Gas (CSPOG), Centre for Budget Advocacy (CBA), Centre for Extractive Development Africa (CEDA), and Penplusbytes.

At a meeting between the MoE and accountability actors on the General Petroleum Regulations in July 2017, PIAC, GHEITI, WACAM, NRGI, ACEP and other CSOs acknowledged the value of the platform created by GOGIG for engagement with government and enhancement on their capacity to contribute constructively to the regulations in areas outside of their main work programmes. Some of the other feedback from accountability actors included recommendations for GOGIG given below.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2016 annual review had 3 recommendations. In response to the recommendation on clarifying the definition on step-change in the logframe, the programme further refined the descriptions to address this. This was subsequently discussed in detail with the Results Advisor and approved.

The programme also finalised reporting and contractual arrangements with both NRGI/PIAC and ACEP.

Lastly, the programme updated its reporting templates for accountability actors to capture its reach, disaggregated data on beneficiaries and beneficiary feedback.

Recommendations

- The future of PIAC: support the development of a sustainability plan by PIAC to manage the replacement of GOGIG and other donor funds with GoG (ABFA) funds and support it to work more with its members, such as labour unions, who have district level constituencies. PIAC does not have any enforcement powers, only the power to make recommendations. As it continues to challenge the government and becomes more reliant on government allocation of funding, it may face political push-back to curtail its power.
- GOGIG should support the sharing of information between the MoF and PIAC for timely reporting on the use of ABFA funds, and improved monitoring and evaluation of ABFA funded projects
- GOGIG should continue to collaborate with other DFID Ghana accountability programmes to ensure coordinated action – for example, it is already collaborating with the STAAC programme on taking forward actions on Beneficial Ownership and Commodities Trading, and with STAR-Ghana on its anti-corruption call.
- GOGIG and its accountability partners should look for opportunities to raise issues highlighted through WRCF to the national policy level – particularly key given the implications of onshore exploration for managing community expectations
Policy advocacy requires flexibility in order to make a timely response and accountability partners report some experiences of GOGIG programme management processes being too lengthy. The programme should consider whether a reactive contingency fund or core grant to respond to urgent campaigns would be useful.
    - The accountability workstream should consider further work on environmental impacts of oil and gas activity in relation to other livelihoods, such as fisheries, farmers, wildlife, etc. These effects need to be captured and addressed in broader good governance picture.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Adaptive and effective programme management
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Number of strategic adaptations/responses to learning products that improve programme delivery	4	Achieved: 4 / the shift to issue-based programming through the use of a portfolio approach; / mainstreaming gender and social inclusion issues mainstreamed in programming; / partnership with STAR-Ghana to improve the capacity of parliament; and / collaboration with STAAC to advance advocacy on beneficial ownership.
5.2 Quality management practices that support programme delivery	6	Achieved: 6 / The programme adhered to the following six quality programme management practices: / captured partners’ input into programme design and implementation; / made cost savings on projects without compromising results; / assured the quality of approved projects through project idea pitching and moderation; / used PEA learnings to inform programme delivery; / held partner review meetings to improve partnership process and streamline programme focus; and / achieved 100% on-time submission of key milestone deliverables to DFID.

Key Points

All two indicators under this Output have been achieved.
Indicator 5.1: One significant adaptation has been the shift from delivering demand-led projects to strategic interventions that focus on addressing critical constraints in the sector. The programme team has successfully shed its legacy of solely responding to partner requests and moving to a model of jointly designing and delivering solutions that are issue-based. Formal and informal arrangements put in place to support regular Political Economy Analyses have been critical to timely adjustments by the programme to the context

Indicator 5.2: At the technical level, the programme has matured from discrete and independent delivery of projects to collaboration across workstreams – for example, between Regulatory and Accountability or PFM and Accountability – to meet complementary objectives.

Summary of responses to issues raised in previous annual reviews (where relevant)

Details of response to last year’s recommendations is provided in Annex 1. The strategic approach ot management and development of projects has been finalised. GOGIG’s project proposal process and templates document how each project contributes to the overall portfolio and the relevant logframe indicators.

Recommendations

Given that the programme is in a mature implementation phase, this output should be removed. The quality of programme management will continue to be monitored through quarterly meetings with the SRO and programme manager, SRO input and approval of project proposals, and monthly financial forecasting and reporting.

The payment modality, which deducts 10% of the programme flexible response fund until the quarter’s learning milestones are met has been trialled as agreed with OPM and DFID. Given that the programme should increasingly be focused on learning across workstreams rather than discrete deliverables on learning, it is proposed that this payment should be linked instead to a quarterly exercise in codifying learning across different programme activities, to be incorporated into the programme quarterly review meetings. The programme team should propose a revised approach to the milestone payment, to be adopted in agreement with the SRO in January 2018.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

In the year to August 2017 the lead cost driver for the programme for this time period was the Flexible Responsive Fund (FRF). The FRF has been the key cost driver this reporting year particularly due to disbursements made to Civil Society particularly at the end of the 2016 election year.

On a whole disbursements made through the FRF mechanism constituted 61.06% of the total expenditure within the reporting period leaving 34.40% allocation for fees (this includes management and technical staff) and 4.54% spent on expenses.

The GOGIG programme has spent about 42% of the total budget, and only 36% of the FRF at the end of Year 3. This is below the expected rate of at least 50% at mid-term and is partly related to the pro-longed slowdown in government activity in the lead up to and following the elections. However, based on the pipeline of approved project proposals, initiatives with government, and disbursement of grants to accountability actors under the and long term initiatives with government and disbursement of grants to the accountability actors, FRF spend is expected to pick up rapidly in the next year.

VfM performance compared to the original VfM proposition in the business case

The business case was approved on the basis of an estimated return of £5.50 for every £1 invested. GOGIG’s revenue capture efforts have brought approximately £50 for every £1 invested in output 2 (revenue capture) focused projects, translating into £2.11 for every £1 GOGIG has spent to date. This implies GOGIG offers good value for money even before considering the non-monetisable benefits of the programme.

Assessment of whether the programme continues to represent value for money

Based on the performance on VFM indicators as set out below, it is assessed that the programme continues to represent value for money:

Indicator	Achieved
Effectiveness
Value of additional oil revenue captured per £ invested	£50 additional revenue captured per £1 invested in revenue capture focused projects. For programme spend as a whole this measure is £2.11 for every £1 spent. / Value captured and attributed to GOGIG to date: £12,559,239 / (75% of $22,073,745. The 75% is based on an assessment provided by a Senior GRA official on GOGIG attribution. However, even if we take a lower attributed 50% this amount would exceed programme spend-to-date) / Cost of investment in revenue capture projects for the GRA to date: / £249,120 / (does not include investments in other workstreams that may impact revenue capture).
Efficiency
Flexible Response Fund spend as a percentage of total spend this year	60% / This is an improvement from last year, where the ratio was 50%. The FRF spend is a measure of how well the team translate their relationship and partnership building into project activity.
Financial and administrative processes lead to timely delivery and improved quality of outputs.	There has been significant improvement in forecast variance since last year has been documented above: +/- 3.4% (Sept. 2016–August 2017). / GOGIG was commended for its successful DFID expenditure verification exercise in January 2017. / Project proposals for new activities under the FRF undergo moderation within the GOGIG team and with the Steering Committee prior to submission for SRO approval, for higher quality and better aligned output activity. / All milestones for the 10% milestone based payments were submitted on time. / Based on data from invoices for July-Sep 2017, the proportion of GOGIG spend on management (administrative and financial staff, and office expenses) compared with programme spend is 7.9%.
Economy
% of consultants fees within benchmarks	100% consultants since Oct. 2016 fit within GOGIG benchmarks as presented in the programme proposal based on experience, national vs local, for non-oil and gas experts / A comparison with other DFID Ghana programmes shows that GOGIG’s daily fee rates are generally in a similar range.
Cost savings on project expenses and value of partners’ input into project planning and implementation	Savings since January 2017: £18,164 / Value of partner inputs: £81,997 / Examples of savings: / Savings on hotel and conference packages for events in comparison to market/advertised rates by building relationships with preferred suppliers through a local mapping exercise of costs. / Examples of partner contributions: / MoE contribution to Energy Summit - £10,000 / Pro bono analytical work by International Senior Lawyers Programme and NRGI - £40,500 / NRGI contribution to event on fiscal responsibility - £5,294
Equity
There are no indicators defined for measuring the Equity dimension of VFM. The programme has developed a gender, social inclusion and conflict (GESIC) framework looking at how these issues should be integrated into the oil and gas sector.

Recommendations for VFM framework:

- The GOGIG programme should establish comparators or benchmarks where possible for VFM indicators in order to make a better informed assessment of programme VFM.
- The programme should consistently measure the same indicators across years to establish trends.
- Equity indicators for the VFM framework should be defined
- The Efficiency indicator should be strengthened to be more quantitative rather than descriptive on improved processes.
- In Efficiency and Economy, the programme should track the breakdown of the flexible response fund, its major categories of spend, and highest value activities. This is to be incorporated in the next Annual Review, but should be tracked as part of quarterly financial reporting from the next report in 2018.

Quality of financial management

The GOGIG programme continues to improve its financial management practices. OPM has revised the financial manual to incorporate best practices to enhance proper financial management and accountability.
Payments are made monthly, with invoices setting out respective budget lines and the specific project names in the case of flexible fund response disbursements. OPM provides progress on financial performance within each quarter as part of the quarterly progress reports to DFID. OPM provides enough information on actual expenditure incurred within the quarter in comparism with what was forecasted for the quarter and goes further to relate this to previous quarter and a projection for the following quarter. OPM provides updates on their forecast information to DFID on the 25th day of every month. This helps DFID to effectively manage forecasts supplied to the DFID system as well as manage variances appropriately. OPM has been efficient in adhering to this provision at all times.

The new payment modality agreed in 2016 which allows a 10% deduction from the cost of Flexible Response Fund disbursements until pre-agreed milestones are met has successfully been implemented. From October 2016, an amount of £14,532 averagely have been deducted in the first two months of the each quarter. Based on the effective and satisfactory delivery of such milestones, the 10% deductions have been reimbursed in the final months of the quarters. GOGIG has met 100% of milestones under the new payment modality.

The programme has maintained low forecast variances for 12 consecutive months. Average forecast variance was +/-3.4% between September 2016 and August 2017, compared with +/-18.25% between October 2015 and August 2016. This demonstrates the programme’s learning and increased ability to manage its flexible-adaptable approach programme.
Forecast variance (July 2016–Aug 2017)
	Jul-16	Aug-16	Sep-16	Oct-16	Nov-16	Dec-16	Jan-17	Feb-17	Mar-17	Apr-17	May-17	Jun-17	Jul-17	Aug-17
Variance	20.2%	14.8%	6.6%	-7.2%	1.0%	-2.0%	-0.9%	2.1%	6.1%	-5.6%	0.4%	-1.1%	-6.1%	1.9%

The programme carries out periodic review and spot checks on its financial operations to minimise risk. This has greatly improved control systems such that, during the expenditure verification by DFID team in January 2017, no significant findings were made by the DFID team. GOGIG was commended for the significant improvements made in designing and updating procedures and policies manual, and making all the efforts to comply with them, as compared to the last expenditure verification exercise in December 2015 and the first Audit in August/September 2016.
At the project level, the programme conducts due diligence and cost monitoring on all project partners to confirm their ability to implement , as well as the ability to receive and efficiently manage grant funds. GOGIG uses DFID’s Due Diligence Framework to carry out its due diligence. Regular financial monitoring also helps to ensure that funds disbursed to partners are used judiciously and for intended purposes.
An external audit for this year’s financial performance has been commissioned and is due to report on 1st December 2017.
Date of last narrative financial report	23/10/17
Date of last audited annual statement	Due 01/12/17

E: RISK (½ page)

Overall risk rating:

Moderate

Overview of programme risk

The overall risk rating for the programme remains moderate.

The business case identified the main risks as being in two clusters - political support and institutional incentives. The programme has continued to manage this well by building good relations with new government appointees and strengthening its networking with technocrats. It has also used both its formal and informal PEA to keep on top of key changes within the environment and has leveraged the right incentives to deliver its objectives.
A comprehensive review of the risk register was undertaken in the first quarter of 2017. Context risks on the anticipated paralysis in policymaking in the lead up to and after the elections did materialise and were mitigated, although with a slowdown in some activities.
The programme has set up internal control systems to manage fiduciary risks associated with its grant-making. This has included the conduct of due diligence assessments and measures put in place to manage partners’ disbursements and spend.

Some of the main risks monitored in GOGIG’s risk register are presented below:

Outstanding actions from risk assessment

    - Revise GOGIG’s risk matrix to comply with latest DFID guidance, including the categories on safeguarding and operational risks. (immediate)
    - Emerging context risks such as increased on-shore activites, arrival of a supermajor company, and accelerated activity as a result of the ITLOS ruling should be considered in a revised risk matrix. Following the experience of the election, future potential losses of key relationships or turnover with government partners should continue to be monitored.
    - Finally, GRA demonstrated the weakest capacity out of all the relevant insitutions, which should be monitored as a standalone risk given its key role in delivering the programme’s objectives.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is on track with achieving its logframe milestones and therefore making strong progress towards achievement of end of programme targets. Programme spend to date is below the 50% mark, however, the programme has a good pipeline of projects to be implemented with partners.

There are currently two years remaining in the GOGIG delivery contract. Given that the petroleum sector is expected to expand production and there are new developments such as on-shore exploration, there is a need to consider options on extending the duration of the programme or other planning for sustainability.

Performance of partnership (s)

DFID’s partnership with GOGIG has remained strong. The SRO transition has been completed with no interruptions to the pace of delivery. There are regular meetings with the Team Leader, Programme Manager and Programme Director in addition to quarterly programme review meetings. .

As detailed under the relevant outputs, GOGIG has built good relations with the new government and has gone on to expand support to other key agencies within the sector. It has also initiated engagement with higher levels of decision making such as the Office of the Vice President/Economic Management Team to secure buy-in for key areas of implementation.

The programme has also expanded its support beyond its two accountable grants to ACEP and NRGI/PIAC. The programme is working with both PIAC and NRGI to define the next phase of the PIAC project.

Asset monitoring and control

Since the last review, the programme’s assets register has been updated and passed a compliance check from DFID in October 2017.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The GOGIG programme does not provide financial aid directly to the government and the partnership principles do not directly apply. However, the programme is well-positioned to support progress against the partnership principles, particularly in areas such as strengthening financial management and domestic accountability.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In line with annual review recommendations, the programme at the beginning of the year revised and finalised the programme logframe indicators, set baseline and milestone targets, and strengthened indicators definitions with support from DFID Results Advisor.

Further, the programme strengthened partners’ monitoring and reporting systems through a joint review of results framework, activity plans and quarterly reporting structure for each project. To refine the application of this system, orientation was futher provided to all new partners about these monitoring of tools and other M&E requirements of the programme. This system has so far helped to put partners on track and facilitated implementation of projects to agreed results and milestones.

The programme MEL Manager embarks on regular monitoring visits to project partners to review performance of ongoing projects, and track results. These regular visits strengthen partners accountability to project delivery and help provide real time information. Such continuous monitoring visits were also used as medium to strengthen partners monitoring capacity in results tracking and evidence gathering.

In addition to these efforts, the programme also engaged an external consultant to undertake an end of project review of the election support project.  The review has provided independent assessment of the performance, results and lessons from the election support projects implemented to heighten awareness and strengthen responsiveness to oil and gas governance issues.

Monitoring progress throughout the review period

Progress has been monitored over the year through regular (once every two weeks) meetings between the SRO and team leader, quarterly progress reports and quarterly programme review meetings.

Process for this Annual Review

The Annual Review has been completed jointly by the SRO and a DFID governance and extractives advisor. The evidence used for the review included - a desk-based review of relevant documents, including the annual progress report from the programme team, and interviews with partners and stakeholders in-country across all major GoG partners (former and current), the Steering Committee chair, and accountability partners.

ANNEX 1: TABLE ON PROGRESS AGAINST 2016 ANNUAL REVIEW RECOMMENDATIONS

Recommendation	Actions
Revise logframe	Completed: The logframe has been revised and, finalized with indicators, milestones and definitions strengthened based on AR recommendations, programme learning and feedback from DFID. DFID gave a final approval in August, 2017..
Finalise strategic approach to development and management of projects	Completed: GOGIG has finalised its portfolio approach and operationalised this into programming. Linkages and synergies to the logframe have been drawn to inform development of projects that contribute to addressing portfolio constraints and achieving LF indicators.
Formalise information sharing with WRCF	On going: This year, GOGIG and WRCF have collaborated on the following project activites: technical sessions and follow up CSO-government engagements on E&P regulations and fiscal responsibility, as well as a conference on economic growth opportunities in the western region. Information sharing also continued with a focus on getting the perspective and inputs on project proposals relating to Fisheries Impact Assessment Environmental Management Policy on Oil and Gas, Community and on the Government Accelerated Plan and the Petroleum Commision’s Guideliness on Community Relations
Undertake close collaboration and planning with government partners	On going: The programme team has held a series of planning meetings on the scope of its support with all new government appointees heading partner institutions. These included the Minster of Energy, the Deputy Minister in charge of Energy and the chief director, the CEO of the Petroleum Commission, the Commissioner General and Deputy Commissioner in charge of the Large Tax Payers Office and the head of the Petroleum Unit of the Ghana Revenue Authority. / GOGIG has also reopened discussions with the new CEO of the GNPC to explore opportunities for a partnership. / There were joint planning activities with government counterparts such as the Ministry of Energy on the organization of an Energy Summit to bring together sector stakeholders to feed into the development of Energy Policies and startegies, with the Office of Minister for Planning and the Office of Vice President on the establishment of an Interagency Modelling and Analysis Team (IMAT), with the Ministry of Finance on the establishment of a Multiagency Revenue Collection Committee (MARC) and with the GRA on addressing findings form GOGIG’s study on revenue losses along the oil and gas taxation chain. / In the case of the programme’s new partnership with the Ministry of Environment, Science ,Technology and Innovation, GOGIG engaged both Ministry staff and donor partner NORAD to identify complementaries and build synergies with supported interventions
Strengthen capacity and sustainability of partners and project interventions.	On going: GOGIG has finalized its overall capacity development plan for its accountability actors that pulls together technical capacity building, organisational development and leadership support. The plan is currently being implemented with the technical capacity development component rolled out and service providers engaged for the OD and leadership components. / In the case of capacity building for government counterparts, GOGIG has opted for on-site mentoring and accompanying practical support to complement training workshops. This is currently being rolled out for the PC with plans advanced for similar support to the GRA. GOGIG has lso contracted a TA to support the former head of the Petroleum Unit of the GRA to develop practice notes to document technical information on a range of issues based on his experiences in undertaking assessments to serve as a guide for members of the Unit. The programme has also ensured the provision of manuals for software provided such as Bloomberg to the BoG to support retention of institutional memory where capacity has been built and the provision of training manuals to serve as reference materials for workshop partcipants. / To support the sustainability of project interventions, GOGIG has deliberated with high level stakeholders to support the adoption and implementation of project interventions. This has been successful with the Office of the Vice President adopting and leading IMAT activites, the Mnistry of Finance establishing the MARC to roll out recommendations from GOGIG’s revenue losses study, and the Ministry of Energy’s decision to institutionalize GOGIG’s facilitated CSO-Government engagements.
Better align the annual reporting with the annual review and to align GOGIG’s work with partners’ planning cycles	Completed. DFID has approved GOGIG’s request to change the reporting timelines so GOGIG can submit its quarterly reports for April to June and then an Annual Report that will cover the period July to September. This is to allow the annual report to feed directly into the annual review.
Improved evidence of the application of PEA in programming	On going: The programme has revised its project proposal template and the criteria for assessing project proposals to incorporate analyses of the use of PEA in informing project designs, approaches, targetting, etc
Improve GOGIG’s understanding and contribution to Climate change and gender:	On going: A Gender, Social Inclusion and Conflict Sensitivity framework has been developed and finalized to guide programming. A project proposal to roll out Gender focused projects has been developed and approved by DFID. A maiden meeting Women in Energy meeting has been held to support the creation of a common platform for women professionals to network and make inputs into sector policy making. / The outcome of discussions with the DFID advisor on climate change has meant a change in focus from developing a climate change strategy to identifying opportunities to contribute to the DFID climate change agenda.
Finalise contractual agreements with NRGI and ACEP and review scope of work.	Completed: Contractual agreements have been finalized for both ACEP and NRGI.
Strengthen anti-corruption analysis and risk matrix to cover fiduciary risks	Ongoing: Portfolio Issues on addressing revenue loses and anti-corruption have been further developed by the programme team as part of its priority areas. / GOGIG has designed a project proposal to respond to addressing revenue losses in addition to identifying additional revenues. To inform interventions, GOGIG commissioned and finalized a diagnostic on revenue losses along the oil and gas taxation decision chain and used this as a basis for discussions with relevant government agencies. This has resulted in the establishment of MARC by the MoF to coordinate government efforts in addressing revenue collection constraints. Accountability side interventions and potential partners have also been identified and incorporated into a project proposal for approval from DFID. / GOGIG has also collaborated with the STACC programme through a series of meetings on taking forward actions on Beneficial Ownership and with STAR-Ghana on its anti-corruption call. / The programme’s risk matrix has been updated to include any fiduciary risks and mitigation plans to addres them
Strengthen targets for VFM integration in the logframe. Balance benefits against costs in VFM analysis	On going: A series of discussions have been held with DFID Advisors on strentheining the programme’s VFM analyses / The programme has updated its VFM analyses to pilot some cost benefit analyses as evident in this report

ANNEX 2 – DEFINITION OF KEY TERMS AND PARTNERS

ABFA	Annual Budget Funding Amount is the allocation from petroleum revenues which goes into the annual budget. Projects funded with ABFA must be reported on according to the PRMA

ACEP	Africa Centre for Energy Policy. A core accountability partner for GOGIG and the leading CSO in the sector. Loss of the former Executive Director to government as the Dep. Minister is a significant loss to the CSO front.

AOE	A windfall tax element of the fiscal regime which entitles the state to a portion of Contractor’s share of Crude Oil produced from each separate production area based on the after-tax inflation-adjusted rate of return
BoG	Bank of Ghana is a core partner and specifically the Ghana Petroleum Funds Secretariat which manages the Sovereign Wealth Funds

E&P Act	Exploration and Production Act is the parent law that regulates the upstream oil and gas sector. It was passed by parliament in August 2016, about 8 years after the need for the law was recognized. The law introduces a competitive bidding process for allocating oil blocks. The previous arrangement was through direct negotiation with the Minister of Petroleum. Regulations to guide implementation is being developed as the ‘General Petroleum Guidelines;

GHEITI	The Ghana Extractives Industry Transparency Initiative has recently become a GOGIG partner and is working with GOGIG on Beneficial Ownership Disclosure and a Commodity Trading Transparency initiative

GITA	Ghana Industrial Trawlers Association is an association of fishing trawler owners who are actively advocating for the protection of marine and fisheries stock. They allege that oil and gas operations are impacting the fisheries sector and are working with the Fisheries Commission to amend the Fisheries Act to make it a requirement that all projects have a Fisheries Impact Assessment (FIA) in addition to an environmental impact assessment

GNT	Government Negotiating Team comprises representatives of several government agencies who are involved in negotiations with companies seeking to be awarded blocks. Until the coming into force of the E&P Act, block awards were done solely through negotiations after the interested company has applied to the Minister of Energy. The GNT is not backed by law and the team does not have a standing composition so there have been concerns that certain agencies are sidelined. There have also been disagreements between the institutions represented during negotiations on certain government positions. GOGIG support is to ensure they have sessions as a team to discuss and agree government positions on the contentious issues before negotiations.

GRA	Ghana Revenue Authority is one of the core government partners of GOGIG. Specifically, the programme works with the Petroleum Unit

MoF	Ministry of Finance is one of the core government partners. Specifically, GOGIG has worked largely with the Energy Oil and gas Unit who lead the implementation of the Petroleum Revenue Management Act. For example, they are responsible for putting together the report on the use of ABFA.

MoP	Ministry of Planning. This was initially called the Office of the Minister of Planning (OMfP) and did not have the full status of a ministry.

NRGI	Natural Resource Governance Institute, a core accountability partner of GOGIG. Focus of their work under the GOGIG programme was institutional development of PIAC and provision of technical support. Phase 1 of the project has ended so their role is limited to provision of technical support and PIAC will not manage their own grant directly

OMfP	Office of the Minister for Planning

PC	Petroleum Commission is the regulator set up in 2011. Before then the national oil company (Ghana National Petroleum Corporation) acted both as an operator and the regulator and the PC has in some cases had difficulty in fully taking over certain regulatory functions from the GNPC. Ghana’s core competency in petroleum resides in the GNPC and a key gap for the PC was technical capability. This is the reason GOGIG has focused support to strengthen the technical functioning of the PC through the Geoscience Unit.

PIAC	Public Interest and Accountability Committee was created under the PRMA to be a statutory citizen oversight body. The committee is made up of representatives of 13 constituency groups and is funded by government through the ABFA

PRMA	Petroleum Revenue Management Act is the legal framework governing how revenue is utilized. It includes provisions for the Heritage Funds managed by the Bank of Ghana, PIAC, allocations to the ABFA and mandatory reporting on ABFA funded projects. The key challenge is that ABFA often co-matches other government revenue which is not regulated by any such framework

RGI	Resource Governance Index (produced by the NRGI) is currently the only measure of the governance of a country’s resource. In the past, it has been produced for extractives in general and 2017 was the first edition focused on oil and gas. To enable a comparison to the GOGIG programme baseline of 2014, GOGIG commissioned a 2014 Oil and Gas index, using the same methodology used by NRGI and the also the consultants whose input informed the 2017 assessments for Ghana

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process