Project Completion Review – Top Sheet

Review date:	July 2017

Title: Kenya Health Programme
Programme code: 113303	Start date: October 2009	End date: May 2017
If programme was closed >1 month early please describe in a few words why	N/A

Summary of programme performance

Year	2011	2012	2013	2014	2015	2016	2017
Programme score		A	A	A+	A+	A	A+
Risk rating		Medium	Medium	Medium	Medium	Moderate[1]	Moderate
[1] From 2016- the new DFID requirement for the risk level to be scored as severe/major/moderate/minor has been used

Financial position

Original programme value	£106.3 million
Extensions/ amendments / Cost-extension / No-cost extension	A two year cost extension (April 2015 to March 2017). £1.3 million from the International Climate Fund (ICF) was added in 2015. / A two month (April - May 2017) no-cost extension agreed in March 2017.
Logframe revisions (with dates)	Revision 1: 02 November 2012 / Revision 2: January 2016 (more indicators were added on ICF Activities). / Supplemental logframes developed by Population Services International (PSI) at the start of the programme and revised in 2015, and World Health Organization (WHO) developed at the start of the programme and then revised in 2015.
Total programme spend	£106,887,917.43 as of 31 May 2017

Follow-up actions required following closure

The following actions are required following closure of the KHP:
- Lessons learned from the programme will shared by implementing partners with the relevant Government technical working groups and to be used by DFID in designing future programmes.
- DFID to disburse final/outstanding payments to the implementing partners within the next six months.
- DFID to follow up with implementing partners to ensure receipt of final financial and audited statements and refund of unspent funds within the next six months.
- All assets will be disposed of in a way that represents value for money and efficiency and in line with DFID policy.

A. INTRODUCTION AND CONTEXT

DevTracker link to business case:	Quest ref: 3570684
DevTracker link to logframe:	Quest ref: 3570804

Outline of programme and achievements

The Kenya Health Programme (KHP) began in October 2009, to advance Millennium Development Goals (MDGs) 4, 5 and 6 on child health, maternal health and HIV prevention (originally as a five-year programme). The purpose of the programme was to increase equitable access to affordable quality basic health services in Kenya. The goal of the programme was to reduce health inequalities and to reverse the downward trends in health related outcome and impact indicators in Kenya.

The KHP was intended to end in 2015, but was extended to May 2017 to enable a more responsible exit of the malaria component and to enable successful delivery of climate change activities, which were integrated into the programme in 2015. Over the course of the programme, the distribution of DFID investment by way of accountable grants or memorandums of understanding (MoUs) was allocated to the following implementing partners: Population Services International (PSI) (68%), World Health Organisation(WHO) (20%), the MENTOR Initiative (4%), King’s College London (KCL), German International Cooperation (Formerly GTZ) GIZ, Danish International Development Agency (DANIDA ), Development Media International (DMI), Health NGOs Network (HENNET) and Family Care International (FCI) (combined, 5%).

The period of implementation of the programme has been characterised by major governance changes in Kenya. The programme has been implemented during a difficult contextual time for Kenya, commencing as the country was recovering from the post- 2007 election violence through a coalition government and the splitting of the health sector stewardship and functions across two Ministries (Ministry of Medical Services & Ministry of Public Health and Sanitation). In addition, a new constitution was passed in 2010, and subsequently health service delivery was devolved to 47 counties. Despite these changes, KHP has been able to adapt and realise the intended results due to the flexible design which enabled changes to be made over time based on the context and lessons learned. The programme design, together with the excellent working relationships between DFID and implementing partners, allowed the programme to achieve the desired results, despite the challenging environment.

The total programme value (£106.3M + £1.3M from the International Climate Fund- ICF) was allocated as follows:

Table 1: Programme summary budget
Major area of focus	Budget (£ in millions)	Partners
Malaria control and prevention	57.1	Mentor, WHO, PSI
Reproductive health and family planning	28.9	PSI
Health Systems Strengthening	12.3	WHO
Operational research and NGO work of accountability	7.5	HENNET, King’s College London, DMI, DANIDA, FCI, GTZ
Ebola virus preparedness and responses	0.7	WHO
Kenya Demographic Health Survey (KDHS)	1.1	United States Agency for International Development (USAID), Kenya National Bureau of Statistics

The 2009 KHP Programme Memorandum outlined that, of the original £106.3 million allotted to KHP, £20 million was allocated in the outer years for the programme for a sector-wide approach (SWAP), a pooled funding arrangement that was under development in the Kenya health sector at the time. However, the health sector SWAP did not go ahead and KHP funds were reallocated under a flexible accountable grants mechanism. The funding was utilised to further support malaria control, reproductive health, and health systems strengthening within the changing political and administrative context in Kenya (devolution to the counties), and to make most efficient use of DFID’s investment to the health sector in Kenya.

However, as the programme closes, there are concerns about sustaining the gains made for instance around malaria in the context of a reducing bilateral support, not just from DFID but other donors. DFID will leverage its investments in the Global Fund to push for increased national and sub-national financial resources for health, and malaria as well as improved coordination and leadership in health financing (particularly for malaria). There is a need to shift the focus to support domestic financing of health programmes both at national and county levels.

Kenya Health Context
The Kenyan government has made considerable progress in improving health outcomes with support from partners (donors, civil society and private sector providers). These include a 30% reduction in under five mortality rate over 2008- 2014. Infant mortality rate decreased to 39 deaths per 1,000 live births in 2014 from 52 in 2008 and the under-five mortality rate decreased to 52 deaths per 1,000 live births in 2014 from 74 in 2008(KDHS, 2014). The reduction of infant and child mortality rates is attributed to intensified immunization activities including mass campaigns, early detection and case management of malaria as well as proper use of Long Lasting Insecticide Mosquito nets (LLINs) to avert malaria incidences. Malaria incidence rate reduced from 32% to 22% between 1996 and 2013[2], this reduction can be attributed to the successful delivery of malaria control interventions. The increase in the proportions of births assisted by skilled health providers during delivery-(six out of ten pregnant women now receive skilled care at childbirth) and over half receive postnatal - are also cited as factors that lowered both neonatal mortality and child mortality[3]. However, despite this steady progress, the country had still not achieved the maternal and child health Millennium Development Goals (MDGs) by 2015.
[2] Kenya Health Sector Annual report 2015-16
[3] Kenya Health Sector Annual report 2015-16

In addition, health and demographic surveys showed major supply- and demand-side gaps and challenges in coverage of health services resulting in continued disparities between counties, urban and rural residents, and different population groups.[4] The shift to devolved governance in 2013, with the health sector being fully devolved, presented opportunities to support more equitable health services, but has also presented risks for delivery of some health services in some areas of the country.
[4] Kenya Demographic and Health Survey (KDHS 2014), Kenya Service Provision Assessment (KSPA 2010), Kenya Service Delivery Indicators (KENYA SDI 2013), and Service Availability and Readiness Assessment Mapping (SARAM 2014).

The delivery of services in public health facilities has been hampered in some cases due to health worker strikes. Furthermore, there are inadequate numbers of health workers and also a poor distribution of workers to rural areas. Equity and access to the poorest and marginalized groups remains an issue. Finally, basic health infrastructure is still lacking in most parts of northern Kenya.

Programme achievement: UK support through this programme was largely focused on malaria control and prevention, reproductive health and strengthening health systems including policy making and planning and encouraging the use of evidence by policy makers and implementers. The programme exceeded key results on malaria prevention, family planning and maternal health that were outlined in the DFID Kenya 2011-2016 Operational Plan and contributed to the UK’s overall international development commitments on malaria and family planning.

Although not captured in the programme logframe, KHP also supported the development of GoK’s health policy development and enactment of key pieces of legislation including the Health Act 2017. DFID staff involved in the management of KHP also played a key role in donor coordination, and alignment of donor activities to the new devolved structures on health systems strengthening, malaria and family planning. In response to devolution, DFID successfully adjusted the budget under the programme to support establishment of service delivery structures at the county level.

The programme has largely achieved its planned outcomes and there is evidence of substantial impact, in outcome areas the programme is contributing to such as the reductions in infant and child mortality rates and an increased proportion of deliveries taking place in health facilities. The specific output results are detailed below:
- 7,723,804 free long-lasting insecticide-treated nets distributed for malaria prevention, mainly to pregnant mothers and children and another 3,761,060 was socially marketed to households in malaria prone counties.
- 1,075,281 women of reproductive age received modern contraception between July 2011 and March 2015 (out of which 450,000 were additional family planning users).
- 250,000 malaria Rapid Diagnostic Test kits (RDTs) were procured and distributed.
- 64,113 additional pregnant women were assisted with skilled delivery care at birth.

B: PERFORMANCE AND CONCLUSIONS

Overall outcome assessment

Table 2: A summary of outcome performance
	KHP Outcome Indicators	Baseline 2009	End Target 2016	Result[5] 2016[6]
1.	Births attended by a skilled birth attendant	44%	50%	72%
2.	Percentage of women and men aged 15 - 24 years engaging in high risk sex who report condom use at last sex	Male:55.2% / Female: 45.3%	Males: 65% / Females: 55%	Males: 68.9% / Females: 37.5% (KDHS 2014)
3.	Proportion of under 1 year children fully immunized	70%	80%	79%
4.	Proportion of children under 5 years in endemic areas sleeping under an Long Lasting Treated Bed Nets(LLIN[7]s)	47.1%	58%	74% in endemic areas
5.	Contraceptive Prevalence Rate(modern methods)	39%	52%	53% (KDHS 2014)
[5] Progress on indicator cell coloured for -- has been “achieved”, (green) and “partially achieved” (amber).
[6] Information from the Kenya Health Sector Annual report 2015-16. The 2017 results were not ready by the time of this report was completed.
[7] LLINs are factory-treated mosquito nets that last for 3-5 years.

Description of outcome performance

On the indicators that significantly over achieved against their target:

Outcome 1: Births attended by a skilled birth attendant: The country has recorded substantial progress; in 2013 Kenya rolled-out the Free Maternity Services programme in all public health facilities which has contributed largely to this notable increase in the number of skilled deliveries in health facilities. DFID funding through WHO was used in six focus counties (Baringo, Bungoma, Kilifi, Machakos, Nakuru and Uasin Gishu). The six counties were selected with the government as a representative sample of all the 47 counties based on geographical settings including- peri-urban, pastoralist areas, agricultural with high population density and coastal areas. The six focus counties also show significantly higher skilled birth attendances as compared to other counties in Kenya. The average improvement in skilled birth attendance for the six counties from 2012 – 2016 was 62.4%, as compared to 45.8% for the rest of the counties[8]. The difference is attributed to focused support provided through KHP on strengthening health system; specifically the six counties received a package maternity equipment and ambulances for referral services.
[8] WHO Kenya Health report

Outcome 4: Proportion of children under 5 years in endemic areas sleeping under an LLIN: There was a significant improvement in regard to this indicator as results of intensified innovative behaviour change communication to promote use and maintenance of nets through mass media and interpersonal communications. This resulted in increased net usage especially by children and pregnant women. The behaviour change communication was provided alongside net distribution in the communities and health facilities across 36 counties where malaria is endemic or epidemic prone areas (see depictions in Annex 1). A World Bank study found that “increased ownership of LLITN in endemic malaria zones explained 39% of the decline in post neonatal mortality and 58% of the decline in infant mortality[9].” However, early into the life of the programme, partners reported a handful of cases where bed nets were being used for other than intended purposes e.g. room dividers or as fishing nets. However, there were increased efforts by the implementing partners to educate and socialise communities on nets usage for averting malaria. This resulted in a decrease in the incidence of misuse as reported in the Kenya Malaria Indicator Survey 2015 (see figure 3 in the annex).
[9] World Bank WP6057. ‘What Has Driven the Decline of Infant Mortality in Kenya?’)

However, Kenya failed to meet the target for Outcome 2 - on the percentage of women and men aged 15–24 years engaging in high risk sex who report condom use at last sex. The KHP contributed to a significant increase in the demand for condoms and the accessibility of condoms by vulnerable populations. As a result, there was improvement in reported condom use at ‘last high risk sex[10]’, especially among males 15–24 years, from 55.2% at baseline (Tracking Results Continually Survey (TRaC) 2009) to 70.4% (TRaC 2015). However, the trend among females peaked at 57.9% in 2011 but dropped and stagnated at 45.6% in both 2013 and 2015. Low utilisation of female condoms compared to male condoms can most likely be attributed to a shift to other contraceptive methods which have been registering high growth like implants and injections in Kenya. Use of contraceptive implants increased from 10% in 2012 to 22% in 2016(TRaC 2016).
[10] Risky sexual behaviour includes unprotected intercourse, multiple sex partners, and illicit drug use.

Output score and description: Based on the impact weighting criteria of each of the outputs, the overall output score for the KHP is A+ (outputs moderately exceeded expectation). Outputs 1, 2 and 4 received scores of A+ (outputs moderately exceeded expectation), and Output 3 received a score of A (met expectation). See more details in the Output section.

Output	Description	Score	Weighting	2017 A+
1	To strengthen delivery of Kenya's national malaria control effort	A+	35%
2	Increase adoption of safer sexual practices among 15–49-year-old men and women	A+	30%
3	National and county health service management and policy capacity developed in line with the new constitution	A	30%
4	Evidence on mental health, maternal health and fee waivers to inform national health policy	A+	5%

Lessons learned and how these have been shared
There are several key lessons learnt from the overall implementation of KHP as follows:
Importance of flexible and adaptive grant making: The KHP ‘accountable grants’ model has been flexible and adaptive to adjust to the changing demands and capacity building needs within the fluid Kenyan political and administrative environment. This included health system support following devolution of health services in 2013/14 and a communicable disease outbreak response (Ebola, malaria, dengue fever and Chikungunya[11] fever) in 2016.
[11] Chikungunya is a viral disease transmitted to humans by infected mosquitoes. It causes fever and severe joint pain. Other symptoms include muscle pain, headache, nausea, fatigue and rash. Joint pain is often debilitating and can vary in duration.

Greater attention needs to be paid to the sustainability of malaria interventions: More consideration should have been given to the sustainability of malaria activities in designing the programme. DFID support for malaria control and prevention has been instrumental but to sustain the gains and prevent possible resurgence, domestic financing for malaria will be critical going forward. It is still unclear if resources from the government of Kenya and other key partners will be adequate to sustain the gains made through this programme. DFID is working with others to ensure support for vulnerable groups(children under five years and pregnant women) within Kenya’s malaria control programme is prioritised for example through support from the Global Fund.

There is scope for more private sector participation in malaria interventions: There is some evidence from the private sector market facilitation assessment conducted by PSI that the private sector is ready and willing to play an active role in appropriate fever case management, manufacturing LLINs, and social marketing to drive sustainability. A market facilitation approach might help engender a sustainable market that meets the needs of those at risk of malaria.

Needs for greater use of malaria testing kits: Although significant gains have been made with regard to malaria prevention, implementing partners have referred to the lesson that in order to ensure that effective case management is not undermined, there should be increased access and use of malaria testing kits. Furthermore, implementing partners have learned that insecticide resistance monitoring and management ensures that insecticides are used for as long as possible.

Support for behaviour change is required to maintain or increase the contraceptive use in Kenya. The KHP contributed to a significant increase in the demand for contraceptives and their utilisation. However, more community awareness is needed to address lack of detailed knowledge about family planning, particularly among adolescents and women in harder to reach areas, and the misperceptions and social and cultural factors that limit demand for family planning. This will be included in a follow –on DFID family planning programme currently being designed.

Simple and efficient energy solutions can reduce health facility energy bills increasing providers’ profit margins and subsequently the financial viability of private health clinics: About 84 of the 309 Tunza[12] facilities have adopted efficient energy solutions ‘quick wins’, which include use of natural light (translucent iron sheets and open windows), energy saving bulbs and routine switching off of bulbs when a room is not in use.
[12] Tunza, or “nurture” in English, is a social franchise run by PSI (Tunza Family Health Network).

There are important trade-offs when implementing multi-year, programmes. The programme was approved in 2009 with ten components totalling £106.3m. Three programme extensions were approved to allow for a responsible exit from malaria, bringing the end date of the programme to May 2017. Although the programme was successful, there were complexities around programme income generated from social marketing of family planning commodities which should have been better planned at the design phase and increased administrative burden for DFID as a result of the difficulties of managing so many partners under one umbrella programme.
Lessons have been shared through workshops and conferences, as well as via peer reviewed publications. Furthermore, many of the achievements and content-specific lessons from KHP have been institutionalised into practices in various departments of the Kenyan Ministry of Health, including the revision of the Kenya Malaria Strategy and tools for monitoring and evaluation practice. There continues to be a need for the application of the implementation and results of KHP (along with further capacity building) at the county level to strengthen county-level management of basic health services.

C: DETAILED OUTPUT SCORING
Output title	To strengthen delivery of Kenya's national malaria control effort
Output number per logframe		1	Output score	A+
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since the last Annual Review		N	Impact weighting % revised since the last Annual Review	N

Indicator(s)	Targets and achievements	Progress
1.1(Cumulative) Number of socially marketed insecticide-treated nets (ITNs)/LLINs distributed (PSI)	Target: 1,860,667 / Achieved: 3,761.060	Scored: A++ / Target achievements substantially exceeded expectation.
1.2 (Cumulative) Number of free ITNs/LLINs distributed through antenatal clinics/ Child Welfare Clinics(CWCs) in endemic and epidemic malaria zones (PSI)	Target: 6,130,000 / Achieved: 7,723,804	Scored: A++ / Target achievements substantially exceeded expectation.
1.3 Percentage of households with at least one under-five child in endemic and epidemic zones with at least one ITN/LLIN (PSI)	Target: 69% / Achieved: 87% in lake endemic regions, 73% epidemic zones	Scored: A+ / Target achievements moderately exceeded expectation.
1.4 Percentage of patients with fever presenting to health facilities who are managed in accordance with national malaria guidelines (WHO)	Target: 100% / Achieved: 59%	Scored: C / Target achievements substantially did not meet expectation.
1.5 Percentage of target counties (N=47) sending timely reports (WHO)	Target: 100% / Achieved: 100%	Scored: A / Target achievements met expectation.

Key points
Through this Output the programme supported Kenya to advance malaria control and prevention efforts through three partners (PSI, MENTOR Initiative and WHO). DFID’s funding via PSI was used to purchase and distribute 11 million Long Lasting Insecticide Nets (LLINs), while technical support provided by WHO was used to develop policy guidelines for treatment, diagnosis and insecticide resistance and malaria strategic plans. Funding was provided to MENTOR Initiative to support improved malaria and febrile disease case management services in North east Kenya. The funds were used to improve access to malaria prevention and treatment services as well as malaria epidemic preparedness and response interventions in Wajir, Garissa and Mandera County.

For Output 1, two indicators scored A++ (1.1 and 1.2), one indicator scored A+ (1.3), one indicator scored C (1.4), and one indicator scored A (1.5).

Indicator 1.1 – KHP has contributed significantly to the development of the market for LLINs in the country, with achievement of over 2.2 million net sales above the target. PSI gained economies of scale in procurement of nets with pooled resources from USAID which resulted in cheaper prices for nets (unit price per bed net purchased reduced and stabilised at £2.62 compared to £3.7 from the baseline). This resulted in procurement of more nets than anticipated.

Indicator 1.2/1.3 – As part of the strategy to ‘keep up’ LLIN coverage, the KHP supported the routine distribution of free LLINs in endemic and epidemic malaria zones to target the most vulnerable groups: pregnant women and children under the age of five. Through these channels of continuous LLIN distribution, the programme exceeded its target by 2.6 million LLINs. PSI benefited from reduced prices of nets as explained in indicator 1.1 above. Similarly, DFID provided an additional £2.6m of funding to PSI in 2016 for procurement and distribution of nets to fill gaps that were identified by the government of Kenya and which contributed to the overall results. In total, the DFID supported LLINs accounted for 50% of routine nets distributed, while the other half was funded by USAID. Routine net were distributed in 4,000 health facilities in 36 counties which were classified as endemic and epidemic malaria zones.

Indicator 1.4 – DFID introduced a pilot of malaria Rapid Diagnostic Testing (RDT) through PSI in 2013 to help support malaria case management through the private sector. By the end of the programme, 250,000 RDTs kits were sold to private health providers at 145 active participating outlets in highly malaria endemic areas along the coast. An additional 160,445 RDTs were donated to the MoH for distribution to public sector facilities that were experiencing stock-outs. PSI ensured that registered private providers were competent to conduct diagnosis and manage fever cases correctly. Evaluation reports demonstrated that over 80% of fever clients received testing, and were managed correctly. The programme further influenced the inclusion of private providers in MoH training and quality assurance plans, and supported the MoH to develop a case management quality assurance plan for the private sector. This pilot further influenced the development of a global WHO roadmap on “Introduction of malaria RDTs in the private sector”. However, the indicator target was only partially met, as it required other investments that were outside the control of the programme, such as availability of rapid diagnostic kits and Artemisin Combination Therapy (ACTs)[13]. With devolution of health services, procurement of essential health commodities is the responsibility of the county governments; some counties did not prioritise essential supplies[14] such as malaria medicines.
[13] Artemisinin-based Combination Therapy (ACT) is currently recommended as first-line treatment for uncomplicated malaria in several countries including here in Kenya.
[14] DFID (2015) ‘KHP 2015 Annual Review report’.

Indicator 1.5 – For this indicator, 100% achievement was made relative to the target. The introduction of the District Health Information System (DHIS 2) has contributed to timely reports from all the counties. However, quality of reporting still varies across counties with challenges observed on incompleteness, inconsistency and timeliness of data reporting. All these areas have been identified for support and strengthening by the Ministry of Health (MoH) during the 2018 to 2022 Medium Term Plan.

Other results: The programme also enabled a total of 383,707 people (out of a target population of 400,000) to be protected from malaria in flood prone/malaria risk locations of Wajir and Garissa counties through indoor residual spraying to control malaria vector (mosquitoes).

Summary of responses to issues raised in previous annual reviews (where relevant):

Recommendation from 2016 annual review	Progress
PSI to continue to share the lessons that are coming out of RDT study with key policy makers in Kenya and beyond.	Achieved: PSI has continued to share the lessons learnt from the RDT study with key policy makers in Kenya and beyond.
WHO and MENTOR to support further strengthening of malaria and other vector borne disease surveillance services within counties and health facilities, to enable early and accurate case reporting through the disease surveillance system.	WHO and MENTOR are continuing to support further strengthening of malaria and other vector borne disease surveillance measures in the country although they are still faced with funding gaps.

Recommendations for future programmes:
Recommendations for future programmes include the following for WHO, PSI and the MoH:
1. There is a need for continued support to the commercial sector, especially in the development of local LLIN manufacturing capacity, but with a clear strategy of acting as a catalyst only- action for PSI and WHO.
2. Insecticide resistance: With increased use of indoor residual spraying (IRS) and increased coverage with LLINs, insecticide resistance has emerged. More effort is required for resistance monitoring and management to ensure mosquito vector control measures are to remain effective. There will require adequate capacity to respond to control malaria, dengue and other vector-borne disease epidemics. Action for MoH and WHO.
3. Behaviour change: Adoption and use of the proven malaria interventions is a process which has already started and needs to be maintained, otherwise, as malaria prevalence drops, communities could have less motivation to continue to use these interventions consistently and consequently reduce their effectiveness. In addition, there is still a need to achieve universal access and equity in coverage. Action for MoH.

Output title	Increase adoption of safer sexual practices among 15–49-year-old men and women
Output number per logframe		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since the last Annual Review		N	Impact weighting % revised since the last Annual Review	N

Indicator(s)	Targets and achievement		Progress
2.1 - Cumulative Number of socially marketed male condoms sold nationwide (PSI)	Target: 150,000,000 / Achieved: 173,814,653		Scored: A++ target achievements substantially exceeded expectations.
2.2 - Couple years of protection (PSI)	Target: 3,808,737 / Achieved: 4,021,443		Scored: A+ target achievements moderately exceeded expectations.
2.3 - Self-efficacy score on ability of men and women aged 25–49 who had more than one partner in the last 12 months using a condom (PSI)	Males / Target: 3.4, Achieved: 3.77 / Females / Target: 3.4, Achieved: 3.88		Scored: A Target achieved and moderately exceeded expectations.
2.4 - Cumulative number of family planning commodities sold (PSI)	Overall score for indicator 2.4: A+ - Milestone achievements moderately exceeded expectations, except for Intra-Uterine Contraceptive Device (IUCD) insertions.
	Femiplan oral contraceptives	Target: 11,083,479 / Achieved: 13,085,226	Scored: A+ target achievements moderately exceeded expectations.
	Femiplan injectables	Target: 1,624,360 / Achieved: 1,896,017	Scored: A+ target achievements moderately exceeded expectations.
	# of IUCD insertions	Target: 111,384 / Achieved: 106,393	Scored: B target not achieved.
	# of implants inserted	Target: 111,384 / Achieved: 156,919	Scored: A++ target achievements substantially exceeded expectations.
2.5 Improved efficiency in provision of health services at the facility	Target (2015–2016): 50 providers (health facilities) / Achieved: 84 providers (health facilities)		Scored: A++ target achievements substantially exceeded expectations. / 84 facilities have adopted efficient energy solutions ‘quick wins’ and have reported drop in facility power bills by between 10% and 50%.
2.6 Increased installation of low-carbon energy at facilities as a result of ICF support (PSI)	Target: 50 low-carbon technologies supported (units installed in health facility) / Achieved: low-carbon technologies installed in 22 health facilities		Scored: C targets substantially did not meet expectations. / 22 facilities have purchased and installed solar powered back-up systems, 18 of which were facilitated through the PSI Climate Change Revolving Fund.
2.7 Enhanced capacity of health facilities on health care waste management (collection, handling and disposal) (PSI)	Target: 100 facilities with knowledge and capacity to manage health care waste safely and more efficiently. / Achieved: 100 Tunza providers trained and 208 providers sensitised		Scored: A+ target achievements moderately exceeded expectations / 23 health workers trained as trainers of trainers (ToTs) on health care waste management ToTs / 100 Tunza providers trained and provided with safe medical waste disposal starter kits / 208 Tunza providers sensitised on proper health care

Key points
Through this Output, funding was provided to PSI to increase access to condoms for HIV prevention and for scaling up use of modern Family Planning (FP) services. PSI delivered this output through supporting social marketing of condoms with communication strategies to increase availability and use. PSI also played a key role in supporting MoH and the various departments in developing social and behaviour change communications for HIV prevention. On family planning services, PSI expanded access to family planning through the Tunza franchise network. The network currently has over 350 service providers in 39 out of Kenya’s 47 counties which offer wide range of services, including quality family planning counselling and services. PSI ensured that the franchise providers always had adequate contraceptive stocks of either social marketed or free government commodities. The programme also supported a voucher scheme which entitled low income women of reproductive age to partial subsidy on the contraceptive method of choice.

DFID has been funding family planning services in Kenya through this programme and Delivering Increased Family Planning across Rural Kenya Programme (DIFPARK) which started in 2013. Family planning delivery through KHP was delivered over five years ending in 2014, in line with original timelines in the programme memorandum. Activities that were not completed by 2014 were transitioned to the DIFPARK programme at the beginning of 2015 to ensure alignment and harmonisation.

The programme has exceeded most of the Output 2 targets, with the exception of sub-indicator 2.4 on IUCDs inserted, which marginally under-achieved at 95.5% of overall target and indicator 2.6 which was not met.

Indicator 2.1/2.2/ 2.4 - A total of 1,075,281 women of reproductive age received modern contraception from the Tunza franchise between July 2011 and March 2015. A voucher programme supported by KHP, resulted in increased access to Long Acting Reversible Contraceptive (LARCs) which had previously had a very low uptake in the private sector, shifting the share of implants and Intrauterine Contraceptive Devices (IUCDs) in the Tunza franchise from 12% in 2010 to 27% in 2014. The 2014 TRaC survey showed an increase in Contraceptive Prevalence Rate (CPR) to 59% among women aged 25–49 years using modern contraceptive methods, compared to 42% in 2012. The, use of modern methods also increased over the last decade, from 32% in 2003 to 53% in 2014[15].
[15] Source: Kenya Demographic and Health Survey 2014

Indicator 2.3 - The programme contributed to a significant increase in the demand for condoms and accessibility of condoms by and for vulnerable populations. As a result, there was improvement in reported condom use at last high risk sex, especially among males of 15–24 years of age, from 55.2% at base (TRaC 2009) to 70.4% (TRaC 2015). The trend among females peaked at 57.9% in 2011 but dropped and levelled off at 45.6% in both 2013 and 2015. Low utilisation of female condoms compared to male condoms can most likely be attributed to a shift to other contraceptive methods which have been registering high growth like implants and injections in Kenya. For males 25-49 years, an almost similar trend was evident compared to the younger male age group, with use moving from about 53.9% at baseline to 69.2% (TRaC 2011), and then 69.3% (TRaC 2015). This increase in use can be attributed to programme awareness and behaviour change efforts, along with Kenyan citizens’ increased awareness of reproductive health and family planning, which created a conducive and trusting environment for more beneficiaries to open up about their reproductive health behaviour.

Indicator 2.4 – During the life of the programme PSI continued with social marketing of the “Femiplan[16]” range of FP products which includes oral contraceptives, injectable contraceptive and male condom. These products mainly targeted the low income women and couples in stable relationships who wish to space or limit conception. The goal of Femiplan social marketing was to increase the appeal and access to affordable family planning products for women who can afford to pay a subsidised price for contraceptives; so that only the poorest who cannot afford to pay anything for FP, can access free products through the public sector. PSI also carried out both mass media (radio) and trade promotions. This included increasing visibility of the Femiplan brand through branding, distribution of communication materials through pharmacies and external branding, such as in public transport vehicles on both town and upcountry routes. Branding of motorbikes was also carried out to increase visibility and awareness of these products, which resulted in more sales. Health provider behaviour change efforts were also conducted to ensure that clients were screened for eligibility, provided sufficient information on how to use the method, and were equipped to deal with expected side effects which contributed to over achievement in this indicator.
[16] Brand name used by PSI.

Indicator 2.5 - Eighty-four facilities have adopted efficient energy solutions, which include use of natural light (translucent iron sheets and open windows), energy saving bulbs and routine switching off of bulbs when room is not in use, and ensuring electrically powered equipment was on standby mode/unplugged when not in use.  Facilities have reported that adoption of quick wins solutions has cut annual facility power bills by between 10% and 50%.

Indicator 2.6: This indicator was not met. The aim of the programme was to help facilities to adapt to climate change by installing solar panels that would reduce energy bills. PSI set up a revolving fund for Tunza network members to support them in purchasing solar panels and back-up solutions, the uptake of this has remained low and PSI has continued to educate health providers on the importance of adopting clean energy and responsible waste disposal.

Indicator 2.7 - A second major challenge faced by Tunza facilities is poor health care waste management, leading to increased air and environmental pollution, causing serious health challenges. To manage this challenge, PSI has implemented several capacity building efforts including a training of 23 trainers under a Trainer of Trainers (ToT) model, training of an additional 100 providers and a general sensitising of 208 other providers.

Summary of responses to issues raised in previous annual reviews (where relevant):

Recommendation from 2016 annual review	Progress
PSI needs to develop a sustainable business plan for the revolving programme income and ensure it is used to further the objectives of integrating climate change into the healthcare care service provision.	Ongoing: PSI has worked closely with DFID to develop a transition business plan for the revolving programme income to ensure it is used to further the objectives of the programme based on the lessons learnt.
Future DFID investment in climate financing should build on the lessons learnt from this programme, especially the need to build adequate time for implementation to allow proper integration of activities into health care delivery.	For consideration in DFID on-going and future programmes.

Recommendations for future programmes for DFID, PSI and the Government of Kenya:
1. There is a need for continuous demand generation to tackle community myths and misconceptions on family planning through behaviour change communication. The MoH and county departments for health should make a deliberate effort to promote full access to all contraceptives and improve the adoption of IUCDs in the public sector, where insertions remain relatively low. Action for MoH and DFID FP current and future programmes.
2. There is a need for government and partners to expand the number of health facilities with access to the national power grid, as well as back-up power systems that are of a renewable energy type. Action for MoH.

Output title	National and county health service management and policy capacity developed in line with the new constitution
Output number per logframe		3	Output score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last Annual Review		N	Impact weighting % revised since last Annual Review	N

Indicator(s)	Targets and achievements	Progress
3.1 Number of counties with functional health administration/management units, in alignment with national policy (WHO)	Target: 47 / Achieved: 47	Scored: A Target achievements met expectation
3.2 Percentage of planning units (N=47) with acceptable quality, comprehensive annual plans (WHO)	Target: 90% / Achieved: 100%	Scored: A Target achievements met expectation
3.3 Number of counties reporting health activities in DHIS 2 in a timely and complete manner over the past 12 months (WHO)	Target: 47 / Achieved: 47	Scored: A Target achievements met expectation
3.4 - Number of national and county stakeholder fora adequately functional (WHO)	Target: 47 / Achieved: 25 (53%)	Scored: B Moderately did not meet expectation

Key points
Through this Output the programme funded WHO to support the Kenyan Government to strengthen health systems. The areas of focus were on: service delivery systems, availability of health information, and governance and management systems. These were the key health system needs following devolution of health services to counties in 2013. The programme focused efforts in a select group of counties to generate lessons and experiences that were then shared across other counties.

The programme provided technical support to counties to ensure alignment of strategic directions at both national and county levels to improve overall capacity for delivery of essential services by devolved governments. Health system strengthening activities was provided to six supported counties (Baringo, Bungoma, Kilifi, Machakos, Nakuru and Uasin Gishu). These counties have reported an improvement in access to basic services. For example – the six focus counties show significantly higher skilled birth attendances as compared to other counties of Kenya. The average improvement in skilled birth attendance from 2012 – 2016 was 62.4% in the six focus counties, as compared to 45.8% for the rest of the counties. While all the counties benefited from the KHP through the national level technical support and the lessons from the focus counties, this difference suggests the interventions targeted at the focus counties clearly resulted in an improvement in access and utilisation of services.

The Output achievements were met for three of the targets (indicators 3.1–3.3), and moderately did not meet expectations under indicator 3.4.

Indicator 3.1, 3.2 and 3.3 were achieved; policy guidelines were developed with support by WHO and aligned with national-level planning, largely with support from the KHP. For example, County Health Strategies were launched in Machakos, Bungoma, Uasin Gishu, Kilifi and Baringo. The development and national roll-out of operational review and planning tools, including support to annual planning process development, occurred in the six counties of Bungoma, Uasin Gishu, Nakuru, Baringo, Machakos and Kilifi. However, at the subnational level and for each individual county, the degree of results attribution to this programme was challenging to measure largely due to inputs from other donors. A better system for assessing outputs contribution would have given us a greater sense of our results on health system strengthening.

Indicator 3.4 - The number of national and county stakeholder fora adequately functional fell short of expectations at 25 against a target of 47. This was due to the fact the counties were new and it took time for WHO and partners to facilitate the setting up of structures at the county level. It took longer time to finalise the legal framework (health act), this was finally enacted in 2017 which provided the basis for the partnership framework which spells out the stakeholder forums at the counties.

Summary of responses to issues raised in previous annual reviews (where relevant):
Recommendation from 2016 annual review	Progress
WHO to continue to advocate for and support the adoption of the electronic health records system in more health facilities in the counties to facilitate contextual learning on what works.	Ongoing: WHO is continuing to advocate for adoption of the electronic health records system in more health facilities in Kenya to help improve the quality of data and health information management.
WHO to initiate plans to support data for decision making within the context of the health data collaborative initiative which has set out the priorities for strengthening health information.

Recommendations for future programming for WHO and the Government of Kenya:
Health sector leadership and governance initiatives should be strengthened and scaled up to other counties, through bottom-up’ approach on health systems strengthening, including an evidence-based action framework, should be developed from a county health system perspective. Action for MoH and WHO.

Output title	Evidence on mental health, maternal health and fee waivers to inform national health policy
Output number per logframe		4	Output score	A+
Risk:		Minor	Impact weighting (%):	5%
Risk revised since the last Annual Review		N	Impact weighting % revised since the last Annual Review	N

Indicator(s)	Targets and achievements	Progress
4.1 Cumulative number of research papers based on the mental health Randomised Control Trial(RCT) submitted for broader dissemination (e.g., peer-review journals)	Target: 4 / Achieved: 4	Scored: A / Target achievements met expectations
4.2 Cumulative number of research papers/articles based on the malaria, immunity and mental health research submitted for broader dissemination (e.g., peer-review journals).	Target: 4 / Achieved: 7 / (two more manuscripts developed undergoing peer review)	Scored: A+ / Target achievements moderately exceeded expectations
4.3 Number of policy briefs and advocacy materials on costs of maternal mortality (FCI)	Target: 2 / Achieved: 2	Scored: A / Target achievements met expectations

Key points
Through this Output the programme funded two research studies: (i) cost of maternal mortality (FCI) and (ii) mental health Randomised Controlled Trial (RCT) through KCL. These studies were intended to produce evidence to inform health policies and decision making.

The KHP achieved all targets under this Output, with one indicator substantially exceeding baseline estimates (4.2). For example, under Output 4.1, four papers related to the mental health RCTs were published in peer reviewed journals an indicator of good quality research and results were presented to wide audiences (local, regional and international conferences). Findings from these mental health RCTs indicated that a short structured general mental health in service training programme in Kenya improved patient health and social outcomes.

Under Output 4.2, seven manuscripts/papers relating to malaria, immunity and mental health research were published, with two additional manuscripts currently drafted and submitted for peer review. Some key findings from this work indicate a strong association between malaria and depression. The presence of depression was related to a 70% increase in the risk of having malaria, and the presence of malaria is associated with increased rates of depression (but not with increased rates of psychotic symptoms, attention deficit hyperactivity disorder, post-traumatic stress disorder, and hazardous drinking or disability).

It is important to note that this research work in mental health has contributed to the development of the Kenya Mental Health Policy (2015–2030), guided the strategic investments and actions plans in policy implementation, contributed to a review of curricula in basic training for nurses and clinical officers at the Kenya Medical Training College, and commencement of training in a higher diploma for clinical officers in psychiatry..

Under Output 4.3, the study was published by FCI examining the societal costs associated with high levels of poverty, high maternal and newborn mortality, and low access to quality health services.[17] The findings from the FCI study showed that the cost of fatal pregnancy and childbirth complications is a heavy economic burden to the family. A mother’s death often begins a chain of disruption, economic loss, and pain that, far too often, leads to the death of her baby, loss of educational and life opportunities for her surviving children, and a deepening cycle of poverty for her family. The study findings have been disseminated widely both locally and internationally. Subsequently, FCI has continued its global advocacy, as evidenced by their work in collaboration with the Harvard School of Public Health to disseminate the research findings and promote use of research in decision-making[18].
[17] FCI (2013) ‘A Price Too High to Bear: The Costs of Maternal Mortality to Families and Communities’.
[18] https://fxb.harvard.edu/womens-lives-matter/

As part of KHP implementation, malaria-specific operational research was undertaken by the implementing partners and two papers have been published in peer reviewed literature, while others have been disseminated widely. These operational research questions were informed by the operational research technical working group (TWG) of the malaria Interagency Coordinating Committee (ICC) at the MoH and contributed to either confirming or changing in policy and practice.

Summary of responses to issues raised in previous annual reviews (where relevant):

Recommendations from previous annual reviews	Progress since previous annual reviews
KCL to continue policy dialogue with Ministry of Health to ensure continuation of the primary care mental health training programme, and to introduce recording of diagnoses in clinic registers	Achieved: The partners (KCL and FCI) continued to disseminate the research findings despite the closure of the operational research grant in 2014 (as planned). Two advocacy and policy briefs have been developed and shared at national and county levels to advocate for the uptake of the results.
Continue to disseminate study results at local community level, to county governments and internationally

Recommendations for future programmes
Recommendations for future programmes include the following for research partners and the Government of Kenya:
There is a need for research agencies to identify the mechanisms and pathways as regards how research done can feedback into the policy agenda of the MoH. Moreover, in addition to building research capacity, policy-makers need to be informed about the value of making evidence-based decisions. Action for WHO, DFID East Africa Research Hub and research based agencies.

D: VALUE FOR MONEY AND FINANCIAL PERFORMANCE

Overall performance

Over the course of the programme, the distribution of DFID investment by way of accountable grants or MoU (WHO only) was allotted to the following implementers to achieve the KHP stated goals and objectives, as follows: PSI (68%), WHO (20%), the MENTOR Initiative (4%), KCL, GTZ, DANIDA, DMI, HENNET, FCI (combined, 5%). As at May 2017, the total spent was £106,887,917.43.

Key cost drivers

For PSI, the largest implementer by funding, the key cost drivers included the following primary resource components: social marketed commodities (59%), personnel (11%), and behaviour change communications (9%).

For WHO, the second largest implementer by funding, the programme cost drivers were primarily related to technical operations for support to health systems strengthening and malaria control. For example, the most recent financial statement from WHO as at September 2016 indicates expenditures related to direct implementation, with the WHO Nairobi office carrying out the implementation of activities, meetings, and contracting of service providers such as consultants, along with direct purchase of goods, equipment and supplies.

Over the course of the KHP, between these two largest implementers, which received a combined 88% of the KHP budget, the performance of PSI is more easily measureable relative to WHO. PSI is directly involved in KHP implementation tied to specific outputs (i.e., distribution of LLINs) while WHO played more of an indirect and/or partner role in support to key stakeholders and decision-makers within the national Ministry of Health or to counties. WHO supported the MoH in drafting of National Malaria strategy and policy and provided capacity building of health workers.

Value for money (VfM) performance compared to the original VfM proposition in the business case

DFID’s Smart Guide to Value for Money emphasizes examining issues related to economy, efficiency, cost-effectiveness and equity as part of a programme review. Each of these issues is addressed below.

Economy

PSI, WHO and the KHP Non-Governmental Organizations(NGOs) all have procurement processes under which the principles of VfM were included in the purchasing and securing of resources for KHP implementation. For example, PSI has robust systems in place to capture market prices of equipment and supplies, actual prices paid based on procurement invoices and quotes from competitive bids. Moreover, it was observed that WHO follows economy principles of VfM by routinely conducting the following activities:

1. Procurement through the UN system catalogue;
2. Direct implementation of activities where suppliers are paid directly;
3. Reimbursement made directly to the participants electronically; and
4. Use of government and faith-based institutions for conferencing among activity participants and stakeholders.

Finally, it was observed that participating KHP NGOs pay competitive market rates for both local and international consultants and other human resource inputs.

Efficiency

The economic appraisal annex to the KHP Programme Memorandum assumed a distribution of 6.48 million socially marketed LLINs at a unit cost of US$7.50/unit, including staff and overheads. At the time, this implied an estimated total cost of US$48.6 million (£32.4 million) for this activity. Over the course of the KHP, PSI received a total of £46.24 million for this activity (including two extensions). As a result, an average unit cost of approximately £4.04 or US$5.2 per LLIN was incurred based on 11.4 million LLINs distributed against a target of 6.48 million. This represents a unit cost reduction of $2.3 per LLIN compared to what was envisaged in the original programme memorandum. The programme benefited from economies of scale and yielded a lower actual average unit cost than originally predicted in the KHP Programme Memorandum.

Cost-effectiveness

Cost-effectiveness analysis was included in the KHP Programme Memorandum. The programme’s cost effectiveness is measured in disability-adjusted life years (DALY), which applies a treatment cost (through medical intervention e.g. supply of bed nets) to reduce the number of years lost by a person due to ill-health, disability or early death. The aggregate health benefit calculation for the three programme components, under the Programme Memorandum in 2009 was a conservative estimate of 2.085 million disability-adjusted life years (DALYs) averted.  The programme achieved 3.7 million DALYs from malaria, HIV and family planning interventions. In terms of cost per DALYs averted under the malaria control programme component alone, due to the distribution of LLINs was £19.2[[1]]. This is much lower than the estimated undiscounted cost per DALY averted due to LLINs distributed of £28 in the Programme Memorandum.
[[1]] As self-reported by PSI Kenya.

Equity

The programme by design was inclusive. The malaria component targeted the most vulnerable groups – children under five years and pregnant mothers. Over 7 million out of the 11 million long-lasting insecticide-treated nets distributed for malaria prevention were provided to pregnant mothers and children. Poor women also benefitted in accessing family planning contraceptives through a voucher scheme provided by the programme.

Assessment of whether the programme represented VfM

Based on the cost-effectiveness assessment above, KHP has represented VfM.

Quality of financial management during programme unsatisfactory

Overall, financial management over the lifetime of KHP has been satisfactory. However, one project worth £500,000 committed to one of the 10 direct implementing partners, was stopped earlier on in the programme due to financial management concerns. As at the date of this review, 99% of KHP’s budget had been expended, with £106,887,917 spent. Financial management of the programme was conducted within the accountable grants mechanism associated with most implementing partners and the MoU that DFID had with WHO. The DFID team ensured internal mechanisms for reporting and investigating suspected cases of fraud and corruption were in place and suspicions of fraud were reported to DFID’s Counter Fraud Unit as per DFID guidance.
Financial reporting has been conducted either on a quarterly or bi-annual basis, depending on the contractual arrangement with the specific implementing partner. The quality of financial reports submitted by partners was acceptable. Areas that required improvement e.g. on financial forecasting were discussed with partners and corrective measures put in place. All partners submitted annual audited accounts to DFID as required. The reports were unqualified implying that partners presented fairly, in all material respects, the actual expenditure incurred for the programme. An assurance audit commissioned by DFID led to the recovery of £117,800 in ineligible expenditure from one of the partners. The audit also provided factual findings on income generated from certain interventions. It recommended that agreements by DFID and its partners should state from the onset, how income generated from programmes would be managed.

Date of last narrative financial report	WHO, September 2016; PSI, December 2015
Date of last audited annual statement	PSI and WHO, 31 December 2015, now completing 2016

E: RISK

The overall risk for the implementation of the programme and achievement of all outputs has been “moderate”. New risks emerged during the course of implementation and DFID together with partners ensured they were sufficiently identified, monitored and mitigation measures put in place. The table below summarises the major risks and mitigation measures over the course of the programme.

Overall risk rating “Moderate”
Risks	Mitigation Measures
Political instability & insecurity. / Civil unrest/terror attacks/ clan disputes in programme areas impede effective programme implementation.	The programme was designed in 2009 following a widespread political violence in Kenya in 2008. The risk of subsequent civil unrest did not materialize and the subsequent elections in 2013 were largely peaceful. However, security remained major concern in the North East and along the coast. DFID ensured that selected partners had a strong operational presence, and experience in these areas.
Human Resources for Health. / Shortage of Human Resources for Health and health care workers’ strikes undermines service delivery	DFID was represented in the Human Resources for Health Inter Agency Coordinating Committee and worked closely with county governments to strengthen governance structures. Strong links were developed with other Human Resources for Health projects including the USAID funded Capacity Project. There have been two major strikes involving doctors and nurses that over six months in 2016 and 2017. Although major results of the KHP programme had been realized by the time this occurred, it remains a major challenge for the sector going forward.
Fraud and corruption / (Including commodity loss due to theft or leakage during procurement or distribution)	Due diligence assessments were undertaken prior to funding of new projects. Spot checks were also undertaken during implementation, areas of risk identified and mitigation measures put in place. Allegations of fraud within partners did appear occasionally, but were investigated and managed. In 2016, allegations of misuse of funds and corruption were reported in the health sector and investigations are still ongoing to ascertain the status. No DFID funding is channeled through the Ministry of Health directly. / A spot-check was undertaken by the DFID Risk and Results Officer in 2015 and recommendations were followed up on, including two assurance audits which were undertaken by an external auditor and DFID’s Internal Audit Department (IAD) on the bed nets project. Recommendations were used to avert losses in the distribution chain. LLINs worth an estimated £919 were stolen from one facility which was recovered except for nets worth £275, which were replaced using partners’ own funds. No other misappropriation of assets was reported.
Devolution / Devolved Government systems, structures and functions result in service delivery interruptions and gaps.	Prioritization of health care delivery including adequate budget allocation varied significantly across counties. DFID supported capacity building of county-level administrative structures through WHO. DFID also supported family planning commodity provision by private sector providers through PSI which mitigated the risks of commodity gaps in counties.
Disease outbreaks / Spread of Ebola and other disease outbreaks further strains the health system	There were disease outbreaks such as cholera, threats related to the Ebola outbreak in West Africa and health risks as a result of El Nino rains. DFID provided additional support to WHO and Mentor Initiative to address wider disease outbreak preparedness, surveillance and response. The support enabled surveillance at all 31 ports of entry, over 10,000 air travelers were screened with daily/weekly reporting in 2015 during ebola epidemic in West Africa.
Financing gap in health sector / Inadequate resource allocation by GoK to the sector and reduced bilateral funding /or changes in financing modalities leads to gaps in critical service delivery areas.	Assessment of financing gaps was undertaken by USAID, the Global Fund for AIDS Tuberculosis Malaria (GFATM), DFID and the Government of Kenya. DFID provided health planning and budgeting support to counties through WHO and also worked with partners and the Government of Kenya to lobby for increased funding for family planning commodities. During the Family Planning 2020 summit in London in June 2017, The Government of Kenya pledged £5 million annual funding for family planning commodities, a significant increase from previous years.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
All the prorgamme’s implementing partners delivered against agreed timeframes. The overall timeframe for the programme was extended to May 2017 to allow for the integration of the climate change component and to conduct a more sustainable exit from the malaria support.

Performance of partnership(s)
The partnerships between DFID and implementing partners continued to be strong and worked well to support the realisation of the KHP outputs and outcomes. It is noteworthy that the mandates of three implementing partners were terminated earlier in the programme:
- Support to GIZ for expansion of social insurance schemes was closed in 2012 due to concerns around sustainability of the social insurance and waiver fees pilots,
- Support to DMI for media campaign on maternal and child health stopped at the project’s natural end in 2011,
- HENNET’s institutional capacity building of civil society organizations was closed in 2013 following capacity and performance related concerns.

DFID decided to maintain health policy engagement and sector planning support through the WHO Health Systems Strengthening component.

The main programme implementers, notably PSI, MENTOR, and WHO, have worked collaboratively with and with the relevant national and county health departments and divisions (Policy and planning, Division of Reproductive Health (DRH), Malaria Control, National AIDS and STIs Control Programme (NASCOP), and National AIDS Control Council (NACC) along with focus county administrations. In Wajir County for instance, these partners collaborated on the distribution of LLINs. Reporting from the Ministry of Health in Nairobi and participating counties indicated strong support for the implementing partners and their interventions.

Asset disposal and value obtained by DFID

All implementing partners have maintained satisfactory asset registers. DFID reviewed these during field visits to ascertain physical location and condition. The major assets were vehicles and IT equipment. An external independent assessor carried out a valuation exercise to determine the useful life of the existing vehicles. Partners have been asked to submit to DFID requests for retention of programme assets where they can demonstrate that the assets would be utilised in support of valid and accepted development projects and that the necessary internal controls are in place to ensure adequate control and maintenance of the assets. DFID is discussing with partners these requests for programme assets for Head of Department approval. It is expected that some of the vehicles in good working condition will be transferred to other DFID supported programmes in Kenya.

The programme generated a programme income of more than £1m through social marketing of commodities e.g. condoms. At the time of this review, DFID and the implementing partners are agreeing on a plan for returning/reinvestment of the remaining income and commodities This presents an important lesson that future programmes, we should consider an exit plan for revolving funds or programmes that generate financial assets and to ensure this is clearly reflected in programme agreements.

G: CONDITIONALITY

Partnership principles assessment

The UK Partnership Principles for Kenya were last updated in November 2015. These concluded that while the government had a strong commitment to poverty reduction, aid will not be channelled directly through Government of Kenya (GoK) financial systems until there is evidence of substantial improvements in the integrity and financial management systems. KHP worked with GoK to deliver shared goals but did not channel money through GoK systems.

H: MONITORING AND EVALUATION

Evidence and evaluation

The programme memorandum proposed a final impact evaluation for the programme. A decision was taken not to proceed with an impact evaluation as it did not present good value for money due to lack of clear evidence gaps that the evaluation would address. The programme supported a number of studies including the Kenya Demographic Health Survey 2014 which provided the first county level data on key health and broader human development indicators. King’s College London also published 4 papers on mental health and malaria immunity in open access journals. These are highlighted in Annex 2. PSI commissioned a market analysis on bed nets and disseminated the report to the Kenya Ministry of Health (MoH) and private sector players to stimulate discussion on the sustainability of routine bed net distribution in the phase of reducing donor funding for commodities.

In addition to the population level studies and smaller scale operational research, the programme has supported a range of qualitative studies to better monitor and evaluate the quality of service delivery and client satisfaction. PSI conducted a mystery client survey, an exit interview survey and a qualitative survey to assess the quality of care provided to clients who seek treatment for febrile illness from participating outlets. Evidence from the qualitative studies has been used to improve the programme.

WHO and PSI supported the Kenya Malaria Indicator Survey 2015 which is done every five years to assess malaria prevalence. Results provided an in-depth assessment of malaria control over time in Kenya e.g. an overall reduction in malaria prevalence in Kenya compared with the 2010 survey results. Other key results included an increased uptake in ownership and use of nets from 44% to 63%. Malaria is no longer the leading killer of children under 5, while data from a variety of surveys and operational research show declines in malaria transmission trends, and vector densities over the last ten years. There is evidence of a decline in infant and child mortality. A World Bank report noted that increased ownership of LLITN in endemic malaria zones explains 39% of the decline in post neonatal mortality and 58% of the decline in infant mortality.

Monitoring progress throughout the programme

The programme was monitored regularly by the implementing partners and DFID. PSI for example, has quality assurance staff and a risk and control team who visit Tunza clinics and private providers every month to monitor quality of service delivery and track bed net distribution. All partners worked closely with county governments to monitor implementation and data quality. All the partners shared data with the national and County MoH through the government health information system. DFID conducted periodic field visits to programme sites during the programme period.

This programme completion review was conducted by a team of four independent consultants with inputs from DFID Kenya’s Health Adviser, Programme Officer and the, Group Head for Human and Social Development.

Annex 1: Figures and tables

Figure 1: Trends in malaria prevalence by malaria endemicity zone, according to microscopy

Figure 2: Mosquito bed Net ownership Trends

Increasing ownership of at least 1 LLIN

Figure 3: Mosquito bed Net usage Trends

 % of people sleeping under LLIN

Figure 4: Modern Contraceptive Prevalence Rate Trends 2008/9 to 2016
mCPR

Table 1: Trends in skilled birth attendances in 6 focus counties, compared to the rest of the counties
	County	2012	2013	2014	2015	2016	Total SBA above 2012	Attributed SBA to KHP (30%)
Total number of Skilled Birth Attendances(SBA)	Baringo County	7728	8994	10875	11783	12657	13397	4019
	Bungoma County	19363	25777	32742	35723	39289	56079	16824
	Kilifi County	21960	25653	34283	36584	33988	42668	12800
	Machakos County	17490	20748	24305	25344	25737	26174	7852
	Nakuru County	32049	37981	44274	45811	47458	47328	14198
	Uasin Gishu County	15803	18576	21894	24119	26687	28064	8419
	Total	114393	137729	168373	179364	185816	213710	64113
Average number of skilled birth attendances	Average for supported counties	19066	22955	28062	29894	30969
	Average, non-supported counties	13694.6	15386.3	17718.5	19035.8	19961.4

Notes:
KMIS - Kenya Malaria Indicator Survey
KDHS- Kenya Demographic Health Survey
TRaC - Tracking Results Continually Survey

Annex 2
ANNEX 1: Mental Health Research
	Mental Health Research Paper	Key messages
	Title: Attention Deficit Hyperactivity Disorder (ADHD) symptom self-report in adults in Kenya and its associated risk factors, an analysis from a household survey in a demographic surveillance site. Authors: R. Jenkins, C. Othieno, L. Ongeri, B. Ogutu, P. Sifuna, J. Mboroki and R. Omollo Journal: Global Mental Health	The key policy messages are that ADHD symptoms are common in Kenya, therefore ADHD is important to include in the training of general primary health care workers, and that further research is needed on the prevalence and risk factors in different contexts.
	Title: Tedium vitae, death wishes, suicidal ideation and attempts in Kenya-prevalence and risk factors / Authors: R. Jenkins , C. Othieno , R. Omollo , L. Ongeri , P Sifuna , M Ongecha , J Mboroki , D Kiima David, B Ogutu / Journal: BMC Public Health	The prevalence of suicidal thoughts was 0.7 %, 4.2 %, 3.7 % and 7.9 % for last week, last year, at some other time, and lifetime respectively, while the prevalence of suicidal attempts was 0.5 %, 1.2 %, 0.7 and 1.9 % respectively. Suicidal thoughts are more common in women, those with Common Mental Disorders (CMD), recent life events and a large social group size, after adjustment for other variables. Suicide attempts are more common in those with psychotic symptoms after adjustment for other factors significant at the bivariate level. Front line health workers and social workers need regular systematic training in biopsychosocial assessment and management of suicidal risk.
	Title: Prevalence of malaria parasites in adults and its determinants in malaria endemic area of Kisumu County, Kenya / Authors: Jenkins Rachel, Omollo Raymond, Ongecha Michael, Sifuna Peter, Othieno Caleb, Ongeri Linnet, Kingora James, Ogutu Bernhards, / Journal: Malaria Journal	Malaria parasites are common (28%) in adults living in the endemic area around Kisumu, Kenya ranging from 60% at the height of the malaria season to around10% in the other months. Malaria parasites are more common in women (32%) than men (24%). / Policy implications: Epidemiological studies of malaria are essential to inform malaria eradication strategies, but most such studies continue to be focussed on children because they have the highest mortality caused by malaria.
	Title: Adult Psychotic symptoms, their associated risk factors, and changes in prevalence in men and women over a decade in a poor rural district of Kenya. / Authors: Rachel Jenkins , Caleb Othieno , Linnet Ongeri , Bernhards Ogutu , Peter Sifuna , James Kingora , David Kiima , Michael Ongecha and Ray Omollo / Journal: International Journal of Environmental Research and Public Health.	This 2013 study found that the prevalence of one or more psychotic symptoms was 13.9% with one or more symptoms and 3.8% with two or more symptoms, while the 2004 study had found that the prevalence of single psychotic symptoms in rural Kenya was 8% of the adult population, but only 0.6% had two symptoms and none had three or more psychotic symptoms. This change was accounted for by a striking increase in psychotic symptoms in women (17.8% in 2013 compared with 6.9% in 2004, p<0.001), whereas there was no significant change in men (10.6% in 2013 compared with 9.4% in 2004, p=0.582). Policy implications: It is necessary to integrate mental health services into general health Care services especially at Primary Level.