Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: African Agriculture Technology Foundation Phase III (2015-2020)
Programme Value: £10m		Review Date: 5th January 2018
Programme Code: 204988	Start Date: 5th October 2015.	End Date: 30th September 2020

Summary of Programme Performance
Year	2016	2017
Programme Score	A+	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review
DFID support to the African Agricultural Technology Foundation (AATF) aims to deliver new agricultural innovations to small-holders in sub-Saharan Africa (SSA) through a financially sustainable organisation that is responsive to the needs of small-holder farmers in addressing market failures in the development and adoption of appropriate agricultural technologies. Increasing the pace and scale of agricultural innovation is crucial to increase the productivity and incomes of poor farmers in SSA.
AATF has made good progress towards achieving its planned second year objectives in key areas, as listed below. However, progress towards institutional change has been too slow, with the new Strategy not yet finalised. Work to develop the new Strategy has identified the potential of establishing a separate social enterprise entity in which to house all AATF business ventures. This structure would enable AATF to tap into other sources of investment from organisations that prefer to invest in for-profit ventures.
- During the reporting period (Oct 16 – Sept 17) an estimated 226,000 households in seven countries benefited from AATF technologies.
- Four new technologies have been accessed by AATF, including a cassava weeder and three vegetable varieties.
- Three new projects have been initiated and started activities: Qualibasics Foundation Seed Company, Expansion of the WEMA project to Ethiopia, and a project tackling bacterial wilt in potatoes.
- Targets for deployment of inbred crops lines were exceeded, with 18 lines under WEMA and 14 under Hybrid Rice. Inbred lines are a key component of the development of hybrid varieties, which are more productive.
- AATF have increased the communications effort, particularly around the March 4 Science Event in Kenya in April 2017. This resulted in a significant increase in followers on social media and increased coverage of AATF and projects on TV and radio.
- Significant increase in resource mobilisation activity resulting in over $18 million of new investment in AATF projects from a number of donors.

Key Acronyms
AATF	African Agriculture Technology Foundation
BMGF	Bill and Melinda Gates Foundation
CAMAP	Cassava Mechanisation and Agro-processing Project
CFT	Confined Field Trials
IITA	International Institute of Tropical Agriculture
IR-Maize	Imazapyr herbicide resistant maize
MLN	Maize Lethal Necrosis
NEWEST	Nitrogen-use Efficient, Water-use Efficient and Salt Tolerant Rice
NUE	Nitrogen Use Efficient
OFAB	Open Forum on Agricultural Biotechnology in Africa ():
PBR	Pod Borer Resistant
WEMA	Water Efficient Maize for Africa

Summary of recommendations for the next year
1. AATF to update logframe targets for future years taking into account over achievement in the past year by February 2018.
2. AATF to provide information on how they use social media data analysis to adapt or target future social media engagement (By March 2018).
3. AATF to update Indicator 2.2 so that it doesn’t simply track followers, but also targets engagement with social media activity (By March 2018)
4. AATF to continue to engage with DFID as the social enterprise venture plans develop. (On-going).
5. DFID and AATF to agree performance indicators for Year 3 by the end of January 2018.
6. AATF to provide a clear plan of action with measurable indicators of progress on improving recruitment of women to improve the organisation’s gender balance (March 2018).
7. AATF to strengthen clauses in documentation issued to downstream Partners to ensure full accountability for finance and management processes (March 2018)

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204988/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204988/documents

The UK provides up to £10 million to the African Agricultural Technology Foundation (AATF) over the period 2015 – 2020 to support the organisation to tackle market failures in the development of appropriate agricultural technologies. New technologies are developed by large international private companies, such as Monsanto and Syngenta, aimed at increasing profits. These companies concentrate on large markets and the needs of the smallholder farmers in Sub-Saharan Africa (SSA) are simply not central to their technological development process. This greatly limits the access by public researchers to new ideas and tools and therefore limits the development of a pipeline of products appropriate for smallholder farmers. This is important because the poor have limited purchasing power, leaving firms with little incentive to develop technologies for them. Therefore, there is a distributional argument in favour of supporting the development of technologies that address the needs of the poor. Moreover, the fact that the poor are a user group that firms are less familiar with means it is difficult to assess the potential demand for new technologies (uncertain/unknown demands and returns), exacerbating the risk involved in developing new products for them. AATF was established specifically to address this issue by identifying and accessing technology and developing products that meet the needs of small-holder farmers in
Core funding remains at the same level as in the previous phase of funding (£1.5 million/year). In addition, a performance related component of up to £500,000/year is structured to incentivise more rapid progress in key areas: achieving and assessing impact at scale, financial sustainability and strengthening of the product pipeline.
This project builds on the UK’s previous support to AATF, an organisation with a proven track record of identifying, developing and deploying technology to increase the productivity of small-holder farmers in SSA. During the period 2010–2015, AATF consistently met or exceeded donor expectations. Among other notable achievements, AATF has delivered drought tolerant maize varieties to over 57,000 households and developed a pipeline of new products. UK support has been instrumental in AATF being able to attract significant new investment from other donor investors (BMGF and USAID) to take these agricultural products to scale.
Ongoing DFID core support will enable AATF to continue to expand both its existing programmes and also develop new technologies and enable the institution to maintain and diversify its investor base. This will prepare the ground for a transition from DFID core support as AATF adapts and embraces a more inclusive and sustainable business model.
The programme will support AATF activities in two areas; support to organisational systems and support to specific projects. The expected impact of support to the proposed intervention is increased productivity of small-holder farmers in SSA.
This impact will be achieved through two outcomes
1. Increased access/availability of appropriate agricultural technologies for small-holder farmers in targeted countries in SSA.
2. A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment
Funding to AATF aims to deliver the two outcomes set out above. AATF is making good progress towards achieving the first of these, getting new technology to smallholder farmers in target countries.
AATF have reported against one outcome indicator, with achievements exceeding the target (table below) for the WEMA project. However, it should be noted that the figure is based on extrapolation from seed sales rather than field level data collection and is therefore an estimate of adoption. AATF is aware that this is not an ideal solution, but given the diversity of seed companies they work with they face a number of challenges to provide more robust data. They are working to improve data collection and their monitoring and evaluation system to deliver better data on the update of AATF technology. During the past year, AATF staff have received training on impact evaluation and are drafting an updated M&E strategy.
Indicator	Baseline	Planned 2016/14	Achieved 2016/17
Outcome Indicator 2 Number of households using agricultural technologies accessed or developed through AATF projects (WEMA Phase II ends 2017).	50,000	145,000	226,150

The second outcome (also set out above) is that AATF is a financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers. DFID has communicated this desired outcome clearly to AATF and the performance related component of funding aims to accelerate the transition to a new business model, but linking the performance payment to key indicators such as a new strategy
Despite regular discussion with AATF, including with the Chair of the Board, the key first step in this transition process has not been completed: the drafting and approval of a new AATF Strategy, including a new business model. DFID has led efforts by the core investors (BMGF, DFID and USAID), to make our expectations clear to AATF Management and the Board. Good progress has been made in consulting for, and drafting the new strategy, but it has not been as hoped. Investors did not receive a draft for comment until the 11th December 2017. DFID had hoped that the strategy would be finalised by August 2017. DFID staff attended the AATF Board meeting in October/November 2017 and made clear that the pace of change needs to accelerate and received assurances that this would be the case. Presentations by the Director of Commercialisation and Director of Resource Mobilisation at the Board meeting highlighted that they have grasped the challenge faced in transforming AATF and a lot of thought and discussion has gone into thinking through options. A key component of the new thinking is to establish a separate social enterprise entity in which to house new business ventures. This has the potential to enable AATF to access new sources of investment and drive the uptake of proven technologies in a commercially sustainable fashion. The key question for AATF is whether they can take the best of these options, package them in to a financially sustainable, and coherent strategy and business plan and then implement the strategy rapidly. DFID will continue to monitor the situation in 2018.
This slow progress is reflected in the performance indicator assessment and the awarding of a performance related payment of £250,000. The performance indicators are specifically designed to incentivise change within the organisation and are assessed in parallel to the Output indicators. While two of the six indicators have been fully achieved, three were partially achieved, and one not achieved.
In parallel with the pressure to develop their new strategy and business model, and despite success in gaining funding to extend existing or support new projects, AATF is under considerable financial pressure due to uncertainty of funding from other donors. While this reinforces the need for the transition to a new business model, that is less dependent on a restricted number of donors, it also takes up management time to address immediate issues faced by the organisation.
At the end of the second year of funding in this phase of support, AATF is at a critical juncture. If the current difficult period can be weathered, and a good new strategy developed and rolled out, AATF will be in a strong position to become financially sustainable having changed its business model, demonstrating its value through achievement of impact at scale and attracted significant investment from diverse sources, as outlined in the original business case for funding. However, if difficult decisions are not taken, both strategically and financially, AATF risks irrelevance as others encroach on their areas of expertise, investors do not value AATF’s business proposition and they do not respond to the changing environment.
Overall output score and description A: Outputs met expectations.
The overall output score for the five Outputs of the programme met expectations. AATF have met or exceeded the majority of their targets at Output level, demonstrating their capacity in their core area of expertise – accessing and developing technology. AATF has continued to access technology, maintain a strong traditional and social media presence, obtain authorisations for product trials, manage technology licences and to be a well managed organisation.
Key lessons
Technical
Although WEMA maize varieties have demonstrated that they can deliver significantly improved yields for small holders, AATF and WEMA partners continue to face major challenges in achieving the necessary scale of production to meet demand of drought tolerant maize varieties. This is in direct contrast to the CAMAP project which has not only been running for a much shorter time, but has already demonstrated the potential to operate in a commercial manner. This suggests that there may be more quick wins for mechanisation, sourcing technology from Asia or Brazil.
Institutional Transformation
Despite goodwill on all sides, bringing about the institutional change required at AATF for it to become a more sustainable organisation is proceeding more slowly than anticipated. This is considered to be due to the inherent difficulties in developing a new business model, in a challenging environment, but also a natural resistance to change which, while it may not be voiced publically, will be in the minds of many AATF staff. The next six months will be crucial in demonstrating that there is the will within AATF to make the necessary changes. If this is not demonstrated, then DFID will need to update the overall programme risk with respect to achievement of overall programme objectives.
Assumptions
- The Business Case for funding of AATF made a number of assumptions concerning causality, programme implementation and external factors. The majority of assumptions have been shown to hold: for example, technology owners continue to share intellectual property with AATF. However, the two critical assumptions for this phase of funding have not yet been shown to be true.
  - Firstly, it has yet to be shown that “New investors exist and are attracted by the impact of AATF technology on smallholders and AATF’s pipeline of new technology”, with no new investors coming on board in the past two years.
  - Secondly, a sustainable business model for AATF has yet to be identified. This is the key assumption for both AATF and DFID funding.
Development of a sustainable business model is a challenge for many organisations. It may be that AATF ends up with a hybrid model, with a portion of their activities funded by public donors, as at present, with other activities being implemented on a commercial or social enterprise basis.
Has the logframe been updated since the last review?
The 2016 Annual Review made six recommendations on the logframe, including redrafting some indicators and recalibrating annual targets. These recommendations were addressed by March 2017 and the updated logframe agreed by AATF and DFID.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	AATF has developed a strong product pipeline (Cowpea, Maize, Hybrid rice, Newest rice, Seeds2B)
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone	Progress
Number of new appropriate agricultural technologies: a) scouted : at least 10; b) accessed : at least 4.	10 / 3	Milestone Exceeded: / a) 45: CAMAP - Cassava Hand weeder from China, SEEDS2B - 44 (26 soybean, 8 pearl millet, I sorghum, 9 tomato) / b) 4: CAMAP - Cassava Hand weeder from China SEEDS2B 3 transfer agreements.
Number of project feasibility assessments conducted.	1	Milestone Met: 1 / Any analysis of the potato project was carried out and recommended for the identification of proof of concept of the technology.
Number of new projects initiated.	2	Milestone Exceeded: 3 / Qualibasics, WEMA Ethiopia and Potato project.
Number of inbred line products deployed, 5 per year for WEMA - 2 (C. Inbred, T. inbred); 6 per year for Hybrid rice - 2 (male [p] lines) & female [s] lines.	19	Milestone Exceeded: 34 / WEMA - 8 MLN tolerant lines for hybrid make up and 10 single cross females to make 3 way MLN tolerant hybrids / Hybrid Rice - 14 female inbred lines made available for use by private seed companies for hybrid rice production
Number of products developed / deployed.	24	Milestone Exceeded: 35 / a) WEMA - 34 developed / b) CAMAP - 1 Cassava Hand Weeder

Key Points
- AATF has exceeded targets in accessing new technologies and developing/deploying products. This relates specifically to the WEMA and SEEDS2B projects where more hybrids have been released than planned (WEMA) and more seed varieties have been scouted than planned (SEEDS2B).
- Given the challenges faced in the seed sector in SSA, it is particularly encouraging to note the successful launch of the Qualibasic seed company, supported by a grant from BMGF. This company, which will be housed within AATF before being spun-out, aims to tackle the bottle-neck in the production of foundation seed in SSA. This was found to be a key constraint under the WEMA project.
- Following successful completion of the feasibility study, AATF has launched a new project, funded by DFID to develop and test transgenic potato varieties with resistance to bacterial wilt using pflp and hrap genes separately and together. These genes confer resistance to bacterial wilt.

Summary of responses to issues raised in previous annual reviews:
2016 Annual Review Recommendation	Progress
2. AATF needs to more clearly demonstrate where the commercial market outlet/‘demand-pull’ is for increased cassava production with clear downstream linkages to aggregators, processors, financiers able to sustain a commercially viable value chains into the future.	This has been completed and the CAMAP programme continues to expand. There is clear market interest and farmers now pay for CAMAP services, generating revenue for the programme.

AATF to update logframe targets for future years taking into account over achievement in the past year by February 2018.
Output Title 2	AATF positioned as a credible and responsible Go-To organization for agricultural technology transfer in SSA
Output number per LF	2	Output Score	A
Risk:	Moderate	Impact weighting (%):	20
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of requests for partnerships; specialist technical expertise/ experience and knowledge sharing on agricultural technology transfer among key targets*; requests for specific technologies (*regional bodies, policy/decision makers, farmers, professionals (researchers, lawyers, students), media, private sector e.g seed companies etc)	15	Milestone Exceeded: 26 / 0 requests for partnership / 17 Requests for specialist technical expertise/experience. / 7 Requests for knowledge sharing. / 2 Requests for specific technologies
Increase (quality and quantity) in number of mentions in both traditional and social media	Traditional Media / 720 / Social Media / 3,400	Milestone Exceeded: 10,900 / Traditional Media: 731 / Social Media / Twitter followers up by 88% (1,013 - 1,901) / Facebook likes up by 320% (2,800 - 9,000)
Number of proactive communication products on AATF experiences and successes ( Books & Booklets; Picture stories, Impact stories, Annual report; Video clips)	1 (Booklets/Booklet / 15 (Picture story books) / 25 (Impact Stories) / 1 Annual report / 6 Video Clips	Milestone Partially Met / 1: OFAB at 10 years / 2: Stories in March for the Science Campaign / 18: 0 / 1: AATF Annual Report / 32: 31 TV and 1 YouTube

Key Points
Indicator 2.1 under this output was restructured following the 2016 Annual Review to more accurately measure whether AATF is considered a “Go-To” organisation. While they had a strong social media presence, and analysed media mentions, this was not sufficient. AATF now tracks requests over the past year grouped under four categories.
  - for project partnership
  - specialist technical expertise.
  - experience and knowledge sharing on agricultural technology transfer among key targets.
  - requests for specific technologies.
- AATF have provided a full list of requests as part of their annual reporting. For example, AATF was requested to join the Intellectual Property Committee of a large international research centre and asked to present on project experiences in a number of fora.
- Media interactions have increased significantly over the year, with a significant uptick in Twitter (1000 to 1900) and Facebook (2800 to 9000) followers. This was principally a result of a March 4 Science Event in Kenya in April 2017. However, the number of followers on social media platforms is a poor indicator of engagement or impact and more work needs to be done to understand how AATF can use social media more effectively.
- In traditional media, negative mentions, where AATF or projects are portrayed in a negative tone, reduced from 5% to 1%, TV coverage increased from 6 to 31 mentions and radio mentions doubled. While AATF continues to monitor and analyse social media data, it is less clear how they adapt or focus social media activity as a result of this analysis. Additionally, current monthly visits to the AATF website are low and static. Therefore, the AATF rebrand strategy is being developed with the intention of integrating social media more closely with the AATF website to drive traffic to the site. This will be in parallel with the launch of the new strategy.
Summary of responses to issues raised in previous annual reviews
2016 Annual Review Recommendation	Update
4. DFID to link AATF with other DFID funded Centrally Managed Programmes and implementing partners in East Africa, with the potential for positive commercial synergies with AATF programming and the new ten year AATF 2018-27 strategy and business plan. Specifically, this could include Trademark East Africa, M4D - Mobile for Development and the GSMA strategic partnership projects.	DFID provided contact details for Food Trade East Africa, AgDevco and CABI. Discussions are ongoing between AATF and the DFID programmes.

1. AATF to provide information on how they use social media data analysis to adapt or target future social media engagement (By March 2018).
2. AATF to update Indicator 2.2 so that it doesn’t simply track followers, but also targets engagement with social media activity (By March 2018).

Output Title 3	Regulatory environment and capacity for testing and commercialization of modern agricultural technologies in target countries improved
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of polices/legislation for testing and commercialization of modern technologies passed in target countries	3	Milestone Met: 3 / Biosafety Regulations drafted and adopted in Nigeria; Biosafety Directives (equivalent) to Regulations adopted in Ethiopia; Biosafety Law passed in Uganda.
Number of persons trained in risk assessment and/or regulatory compliance from partner institutions	40	Milestone Exceeded 59 / Compliance Training conducted at WEMA CFT sites in Kenya, Uganda, Tanzania, Mozambique, South Africa and Ethiopia. A total of 59 (13 females and 46 males) trained
Number of permit authorizations for product testing obtained*	15	Milestone Not Met ;10 / 10 CFT permit authorizations for WEMA and cowpea projects granted.
Number of regulatory approvals for commercialization of products granted in target countries	5	Milestone Exceeded: 9 / 5 approvals for TELA transgenic maize hybrids for commercialization in South Africa; / 4 Conventional MLN Tolerant Hybrids in Kenya.

Key Points
- Ensuring a favourable regulatory environment for AATF technologies is a key part of project activities as unfavourable regulation poses a major risk to AATF (see risk section). AATF’s work in this area is funded by BMGF under the OFAB project.
- The past year has seen a positive shift in the regulatory environment in key countries, with approval of biosafety regulations or laws in Ethiopia, Nigeria and Uganda. Kenya has also approved National Performance Trials for Bt maize.
Summary of responses to issues raised in previous annual reviews.

2016 Annual Review Recommendation	Progress
8. AATF to consider how the successes achieved and lessons learned in research, certified seed production and dissemination of conventional and transgenic maize varieties can be translated to the other crop species with which AATF is now working in southern Africa (Tomatoes, Sorghum, Millet).	AATF drafted and prepared a report by 15th of March 2017. This document was shared with DFID and is now being taken forward to produce briefings at the recommendation of the AATF Board.

Output Title 4	Appropriate agricultural technologies accessed and licensed for sustainable use by small holder farmers in target countries
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of appropriate technologies negotiated and accessed	3	Milestone Exceeded: 4 / hrap, pflp and new pflp (potato) and 1 hand weeder. Currently also negotiating for access to Round up Ready (RR) from Monsanto on a royalty based
Number of trademarks/patents/PVP filed in project countries	2	Milestone Met: 2 / TELA and OFAB in Uganda.
Number of sub licenses negotiated and signed with partners	12	Milestone Not Met: 11 / 9 commercialization sublicenses and 2 research sublicenses for all projects
Number of compliance returns filed in project countries	8	Milestone Met: 8 / 3 Compliance Returns for Kenya, 2 for UK, 2 for USA and 1 for Nigeria

Key Points
- AATF activities under this output are on track. Access to and management of intellectual property and licences is key part of AATF’s business model. In order to maintain the confidence of partners who have provided intellectual property it is crucial that AATF is able to demonstrate compliance with licencing agreements.
- As part of AATF’s revised Strategy for the period 2018 – 2027, an option that is being considered is to use experience gained to-date in intellectual property management and licencing to offer consultancy and advisory services to third parties as a source of revenue.

Summary of responses to issues raised in previous annual reviews .

Recommendation	Progress
9 Dependent on the commercial trials in South Africa, AATF needs to demonstrate how it will license and contract these varieties with commercial partners that align with and support the new 10 year 2018-2027 Strategy and Business plan.	AATF has updated its Intellectual Property Management Policy and is also considering licensing options as part of the development of the new strategy.

Output Title 5	AATF is a well managed, efficient and effective organization with a diverse donor base.
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Board meetings are held twice a year with a high level of attendance.	3	Milestone Met: 3 / Three board meetings held in April 2018 (Nairobi) and July 2017 (tele con) and October 2017 ( Uganda)
Percentage of review/audit/evaluation recommendations implemented.	80%	Milestone Exceeded 100% / The internal audit has reported that AATF has implemented all the 7 recommendations (100%) though 4 are still being implemented and will be fully implemented by end of the year.
A diverse and robust funding pipeline is maintained / number of concept notes/proposals submitted / number of proposals funded / amount of funding raised / number of new donors	12 / 3 / $5m / 2	Milestone Mostly Met / 12 -IFAD ICT for Rice and Maize 3.5M, AGRA Regulatory harmonization 1.5M, Seeds2B 1.1M (USAID/SFSA), TELA Maize Project 24M, Hybrid Rice Renewal 4M, AfDB/TAAT 6M – 10M, COMESA - EU/AU/JICA 15-40M, ACCF with CIMMYT 1.1M, BBSRC with Univ. of. Cambridge 0.2K, USAID FTF (Marketing to scale) 15M Total, Innovate UK (DFID) Seeds2B etc. 300K, FFAR Sorghum and Millet 400k, and Innovate UK (DFID) Ozone 300K / 6 - Seeds2B, CAMAP, WEMA Ethiopia, MLN, OFAB, QBS / $18.3m SFSA - Seed2B re-investment - 26 July 2017 - 450,000 - Syngenta Foundation, BMGF - CAMAP - 18 June - $399,918, BMGF WEMA Ethiopia - 14 July - $4m, CIMMYT MLN - 7 February - $80,000, BMGF- QBS - 15 Nov 2016 - $8,5m, BMGF OFAB Supplement - 17 October 2016 - $4,8m / 0 No new donors though a lot of donor cultivation is currently underway
Staff turnover rate below 10%	5%	Milestone Met: 4% / Two (2) members of staff out of 54 exited the organization during this reporting period (October 2016 to September 2017)

Key Points
- A key objective of DFID support to AATF is that they become a well performing organisation with a diverse funding base. DFID staff attended the AATF Board meeting in October 2017, as part of the Annual Review process and were impressed by the engagement of Board members and the probing questions they asked AATF management with respect to financial management.
- Additionally, in the past year, AATF have recruited a new Director of Resource Mobilisation. They now have a much clearer strategy and action plan for mobilising resources. 2017 saw a number of successes, with $18.3m of new projects being awarded to AATF. However, this was entirely from existing investors. Despite engagement with a number of new potential investors and promising signs, no new investors have agreed to fund AATF projects. There are a number of proposals in the pipeline on which a final decision is awaited. This reflects the challenging funding environment faced by many development and research organisations, and is a key driver behind the need for AATF to develop a new strategy and business model.
- The new Directors of Commercialisation and Resources Mobilisation have worked closely together to consider additional options for revenue streams for AATF as part of the development of AATF’s new strategy. These options were presented and at the Board meeting in October 2017 and will be taken forward following the Board’s direction.
- Primary among these options is the establishment of a separate social enterprise entity in which to house all business ventures. This option has been chosen in order not to compromise AATF’s charitable status, having taken legal advice. All profits from the enterprise would be returned to AATF. This structure would enable AATF to tap into other sources of investment from organisations that prefer to invest in for-profit ventures. The Board responded positively to the proposals and AATF will continue to work through the details as part of the Strategy process.
- To support the transition to the new strategy and business model, the AATF Board Nominations Committee agreed to search for new Board members with the necessary skills and experience to guide AATF.

AATF to continue to engage with DFID as the social enterprise venture plans develop. (On-going).

PERFORMANCE RELATED FUNDING ASSESSMENT.
A key component of DFID funding to AATF in Phase III is the Performance Related Funding Component. This new component of funding is structured to incentivise more rapid progress by the organisation as whole in key areas of interest to DFID, including: achieving and assessing impact at scale, financial sustainability and strengthening of the commercial product pipeline. Of the total funding of £2million/year, £500,000 is Performance Related Funding and is awarded following assessment of AATF’s performance against an agreed set of performance indicators, divided into two categories: Organisational Behaviours and Technical Areas. Performance Related Funding can be awarded in its entirety, partially or not at all depending on performance. However, no specific sum is attached to each indicator they are assessed as a whole. This objective has been clearly communicated to AATF management. Progress against each indicator is reported in the table below.
Organizational Behaviours and Milestone	Milestone and progress
Commercial/Private Sector Focus / At least 50% of the professional staff trained in commercial approaches in agricultural technology commercialisation. / At least two business models developed and tested by end of 2017	ACHIEVED / A total of 28 staff trained on issues related to commercialisation of technology (7 Staff members trained in Quality Management Systems, 9 in KEPHIS Private Seed Certification and 12 in Product Stewardship and Commercial Seed Production) / The CAMAP programme has rolled out its new cost recovery model, generating $122,000 in revenue over the past year. / The Qualibasic seed company is up and running to deliver a commercial approach to the production of foundation seed.
Gender and Inclusion / Gender Specialist hired on short term assignments to train staff on Gender Mainstreaming. All concept notes and proposals have gender disaggregated data and AATF Gender Focal persons identified and spearheading the gender mainstreaming across all AATF activities.	ACHIEVED / Following the approval of the AATF Gender Strategy in 2016, it has been rolled out over the past year. The AATF focal point for Gender issues has been appointed. Training on Gender mainstreaming took place in October 2017. Collection of gender disaggregated data within all project phases, is now standard practice and the Gender Audit identified that 33% of AATF staff are female. At Board level only 16% are female and only 12% of international staff are female. In contrast, 37% of national staff are female
Development of new AATF Strategy and Business Plan / AATF strategy finalised by August 2017 and the drafting of the Business Plan underway in October 2017	PARTIALLY ACHIEVED / AATF have invested significant time and resources in the development of their new strategy. This has included stakeholder consultations and face to face meetings with core investors (DFID, BMGF and USAID). / However, the deadline of finalisation of the Strategy by August 2017 was not achieved. The Board discussed the strategy at their October 2017 meeting and it was shared with investors in early December.
Technical Areas
Impact Evaluation / Senior M&E Officer recruited by May 2017. The AATF strategic road map for M&E and impact evaluation developed. AATF staff trained on impact evaluation	PARTIALLY ACHIEVED / Regrettably, this indicator was only partially achieved as the M&E Officer left AATF in late 2016. However, a high calibre successor was recruited in July 2017. Initial discussions between DFID and the new M&E Officer demonstrated that she has a good grasp of the key issues that need to be addressed. DFID provided detailed feedback on the existing AATF M&E plan and a clear statement of expectations with respect to impact evaluation. / 25 AATF staff received Impact Evaluation training delivered by the CLEAR Initiative. / Additionally, two baseline surveys were conducted to facilitate future assessment of impact.
Reach/Scale of AATF products / WEMA - 837T / STRIGA - 200T / CAMAP – 4,500 households	PARTIALLY ACHIEVED / WEMA - A total 1,872 tons of WEMA seed were sold through seed companies and agrodealers in six countries, benefiting and estimated 187,000 households. This is substantially higher than the target due to better than expected seed production in Zimbabwe and Mozambique as a result of good rainfall in early 2017. / STRIGA - A total of 141.6 tons of StrigAway (IR) Maize seed was sold in Kenya and Uganda through seed companies and agrodealers. Reaching a total of approximately 14,000 households. This was lower than the target and reflects the ongoing challenges with production of seeds with a herbicide coating. AATF has taken the decision not to invest more resources in the Striga project. / CAMAP - A total of 3,150 households reached from October 2016 to September 2017 through private service providers and AATF’s cost recovery business model.
Fund raising / AATF has raised $5M from new investor(s)	NOT ACHIEVED / While AATF has had substantial success in fund raising over the past year (Output 5), this has not been from new investors, despite substantial efforts.

Based on the analysis above, DFID intends to award a Performance Related Funding amount of £250,000. The key issue for DFID is the slow pace of development of the new Strategy.

1. DFID and AATF to agree performance indicators for Year 3 by the end of January 2018.
2. AATF to provide a clear plan of action with measurable indicators of progress on improving recruitment of women to improve the organisation’s gender balance (March 2018).

Summary of responses to issues raised in previous annual reviews.
2016 Annual Review Recommendation	Progress
10. DFID and AATF to agree performance indicators for Year 2 by the end of January 2017	AATF reviewed the indicators which were approved by DFID
11. AATF should up speed up the development of the new strategy and business plan to provide greater clarity on key areas, particularly their approach to commercialisation and institutional sustainability by July 2017	As reported above, whilst good progress has been made, the target of July 2017 for the new strategy and business plan was not met.
12. AATF to update their Monitoring and Evaluation strategy to address the need for independent impact evaluations, with clearly articulated evaluation questions, to provide robust evidence on the impact of AATF technologies and more rigorous data on adoption of technologies.	See above

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance.
The key cost drivers for AATF are Personnel and Administration costs (including financial and audit), monitoring and evaluation and accessing technical expertise.
AATF have maintained a consistent cost structure with a major proportion of the budgets being designated for project and programmatic work with a lean budget for core functions (resource mobilization, monitoring and evaluation, governance, administration). During the reporting period, core functions made up 10.6% of AATF’s total costs ($1.92m). AATF also have robust systems in place to deliver VfM, both within the organisation and with their sub grantees.

VfM performance compared to the original VfM proposition in the business case
Since the AATF Business Case was approved in 2015, Research and Evidence Division (RED) has articulated a ‘quality and value at each step’ approach to value for money which provides a more useful framework for ensuring VfM than the original metrics proposed. This framework recognises that assessing Value for Money for agriculture research investments is challenging, as the outcomes and impacts cannot be determined. While the evidence of positive rates of return from investment in agriculture research is clear, this is not sufficient for ensuring value for money at programme level. This is a common issue for all research programmes. VfM is delivered by:-
- Picking the right problems – AATF have a robust process to identify constraints to small-holder agricultural productivity before identifying potential technological solutions to addressing the constraint.
- Working through strong partnerships – DFID has a strong partnership and working relationship with AATF and they have good track record in meeting DFID management expectations. AATF has robust systems in place to manage their delivery chain to ensure VfM and reduce risk (see Risk section below)
- Always requiring good quality – AATF ensures that their product development is of high quality, conducting robust field trials of new technologies.
- Programme Management – AATF’s programme and financial management are strong and they managed DFID resources effectively.

Assessment of whether the programme continues to represent value for money.
DFID support to AATF is through unrestricted Core Funding of £10m over 5 years (including up to £2.5m for performance related payments). AATF continues to meet the output Indicators, and strives to ensure Value for Money in both the cost of running the programme and in building institutional capacity, developing and implementing projects. AATF are in the early stages of plans to move to a sustainable business model which has the potential to improve Value for Money from a commercial prospective. AATF should consider reducing the burden on Core Funding by reflecting overhead costs in the Projects more accurately. During the period of the report AATF reported many cases of how they have delivered value for money in the past year. Examples are provided below, listed against the four E’s of the Value for Money Framework.
Economy:	AATF Introduced WebEx meetings reducing the number of costly face-to-face meetings. / Adoption of synergistic approach to implementation of activities across projects – where similar activities with same end goals were carried out together e.g media trainings under WEMA, OFAB & PBR Cowpea. / Reducing staff per diems by 20%. / IT and Cleaning services were outsourced and AATF have engaged Corporate Uber Services as additional cost saving measures.
Efficiency	AATF use a number of project management software and systems to reduce the complexity of project management and ensure the highest levels of project efficiency and effectiveness. These help manage the flow of work through the entire project lifecycle. / Contracts are now paid in instalments to ensure payment is based on delivery of quality work. If the work is not satisfactory, the instalment is not paid. / AATF has continued to publish a number of articles in high impact journals and media outlets. AATF Staff have also had chapters in books published.
Effectiveness:	AATF is partnering with a number of policy actors like AU, FARA, FANRPAN, and ABNE to assist in creating a conducive regulatory environment for agricultural development in SSA. / AATF mode of operation is through Public Private Partnership (PPP) and involves a lot of consultations and advocacy with governments to position agriculture to be transformative. AATF works with the NARS and their representatives are members of project committees to assist in advising on how best to implement projects to get better outcomes. / CAMAP piloted full cost recovery in the provision of mechanisation services and after the positive progress in Nigeria, this approach is now being implemented in all CAMAP countries ( Nigeria, Zambia and Uganda).
Equity:	AATF has a Gender Focal Person to enhance gender equity in participation and distribution of benefits to all (women, youths, men and the underprivileged). This will be done through awareness workshops, trainings and demonstrations on the importance of gender inclusiveness in agriculture.

Quality of financial management
Invoices and Financial Reports are submitted quarterly to DFID outlining the expenditure incurred against the agreed budget from the previous quarter, and the forecast for the next quarter. Payments are made on the basis of 6 weeks in arrears and 6 weeks in advance (due to the requirement to commit to expenditure) – a process agreed during the previous phase of the programme.
AATF have submitted invoices against agreed forecasts during this period to maintain spend at agreed figures for each programme year. £1.5m was paid in Core Funding during Year 2, together with Year 1’s performance related payment of £250,000. Clear milestones were set out and progress against each indicator was clearly reported.
Forecast	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Core Funding	1,500,000	1,500,000	1,500,000	1,500,000	1,500,000	7,500,000
Performance Payment	500,000	500,000	500,000	500,000	500,000	2,500,000
Disbursement
Core Funding	1,500,000	1,500,000
Performance Payment	250,000	250,000
Total	1,750,000	1,750,000				3,500,00

Just over 30% of the Core funding budget has been used. Overall DFID funding covers 9% of the project budgets and 7.3% of the total expenditure. In 2017, as well as core costs, DFID funding was spent on two projects:
- CAMAP - DFID funded 31% of Project costs ($239,443)
- Bacterial wilt resistant potato and Sweet Potato working with the International Potato Centre (CIP) using DFID Funds of $493,444 over 3 years.
The following project is at concept stage using DFID funding:
Developing MLN/Drought/Striga tolerance project . AATF is in talk with CIMMYT to develop the MLN/Drought/Striga tolerance project. The project will primarily centre on improving WEMA products for the traits of interest (stacked traits).
AATF Organisational budget is planned in US Dollars. Whilst the Pound Sterling/Dollar exchange rate stabilised during the year it did not reach the level of previous years. This resulted in reduced income from DFID as compared to the outset of the programme, and has therefore impacted on the overall financial position. AATF managed this where required by utilising revenue from overheads and a slow down in some activities to ensure financial stability.
A full audit of AATF is carried out on a yearly basis and report provided to DFID. AATF carries out an audit of Sub grantees control systems to ensure management and financial accountability and a summary report is provided to DFID. Generally the controls in place are good; however there were instances where financial controls could have been more robust. AATF follows up issues with the sub-grantees, and if necessary will withhold funds until satisfactorily resolved. AATF should stress to the Project Managers their responsibility for the financial management of their projects, and introduce some additional controls to improve accountability.
AATF to strengthen clauses in documentation issued to downstream Partners to ensure full accountability for finance and management processes (March 2017)

Date of last narrative financial report	August 2017
Date of last audited annual statement	May 2017

E: RISK (½ page)
Overall risk rating: Moderate
Overview of programme risk
While there are two risks rated as major, below, on balance the overall risk remains as moderate. However, if the situation regarding these two risks does not improve in the next quarter, overall programme risk will be increased to Major
AATF have a robust approach to Risk Management and their Risk Management Committee reports to AATF Management and the Board. AATF have a detailed Risk Register which clearly sets out Risks and Mitigation steps being implemented by Management across a range of categories, including procurement, finance and project management. Of specific interest to DFID as a core investor in AATF is the strategic risks identified by AATF Management. Their top risk at present is inability to attract new investors. A number others relate to the regulatory environment and management of intellectual property. These risks are included in the DFID risk table below, as they are considered of particularly relevance to the programme.
Risk category	Description of gross risk	Mitigation strategy	Residual risk rating / (minor/moderate/major/severe)	Risk Trajectory over next year
Context	Failure to adopt appropriate biosafety regulations in AATF target countries / A significant proportion of AATF’s technology portfolio includes traits introduced through genetic modification. If biosafety regulations and their implementation in AATF target countries prevent or ban the trialling and introduction of GM crop varieties AATF will not achieve its objectives. / As reported under Output 3, there have been positive changes in the regulatory environment in the past year.	AATF is fully aware of this risk and continues to engage partners and countries in dialogue on biosafety through BMGF funding to the OFAB project.	Moderate	Stable
Context	Lack of/withdrawal of investors funding / The funding environment for AATF is challenging, as reported under Output 5 and Performance Indicators. / The short-term risk to AATF is low, although increasing. However, the medium to long-term risk to AATF is major and increasing. / This is reinforcing the need for AATF to change its business model, but also taking management time away from the transition process.	AATF Management and Board discussed the issue at length at the October Board meeting and will implement a number of cost saving measures. If the situation does not improve, projects will need to be stopped. / AATF’s discussions with new investors (Output 5) are a key part of the mitigation strategy.	Major	Increasing
Delivery	There has been no change to risks in this category.		Minor	Stable
Safeguarding	There has been no change to risks in this category.		Minor	Stable
Operational	There has been no change to risks in this category.		Minor	Stable
Fiduciary	Poor financial management by downstream partners / This risk has not changed. However, as AATF works with 56 partners across 15 countries, issues with any of these partners could impact DFID’s reputation even if DFID funds are not directly involved.	AATF carries out regular audits of sub-grantees internal control systems at country level ensuring accountability of donor funding. AATF have provided a summary of audit findings to DFID. Findings are clearly set out, highlighting specific issues and follow on actions required. AATF follows up with partners to ensure actions are implemented.	Moderate	Stable
Reputational risk	Reputational Risk is linked to the Risks defined in other categories above		Moderate

Compliance with DFID commitments:
1. The programme complies with 2014 Gender Equality Act commitments.
2. The main supplier complies with the Equality Act 2010 according to its annual report.
3. The supplier complies with DFID branding. Branding guidance had been shared with the supplier and spot-checks confirmed that produced materials do use the DFID branding correctly.
4. Programme’s documents which fall into the 11 document types listed in the Transparency Smart guide are displayed on the Development Tracker.
5. Programme information is not published on the International Aid Transparency Initiative (IATI) website. Guidance to support partners in meeting this requirement is being developed centrally by DFID.

Outstanding actions from risk assessment
No outstanding actions from the Due Diligence assessment.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe.
The programme continues to be on track with the majority of targets being met or exceeded, with AATF continuing to develop a strong product pipeline. The key workstream that has moved ahead more slowly than hoped is the development of the new strategy and business plan.

Performance of partnership(s)
AATF continues to be a reliable and responsive delivery Partner and have a good working relationship with DFID. They respond quickly to requests for information and provide reports on time.
DFID works closely with USAID and BMGF who are the other main Investors to make sure we are all working towards agreed objectives. Investors are represented at each Board Meeting (attending on a rotational basis) and regularly engage with each other over key issues.

Asset monitoring and control
AATF provided a comprehensive asset register, updated on a yearly basis which is fully set out and well managed.

G: CONDITIONALITY
Update on partnership principles (if relevant)
Not applicable. This is a research programme and does not provide direct funding to partner governments.

H: MONITORING & EVALUATION
Evidence and evaluation
The 2014 Institutional Review of AATF supported the original justification for funding to AATF. AATF is fulfilling a role in the agricultural innovation landscape in SSA which other institutions/funding are not fulfilling by accessing and delivering agricultural innovation to small holders in SSA.
The Theory of Change is working in practice, although some assumptions are yet to be confirmed, specifically,
  1. New investors exist and are attracted by the impact of AATF technology on smallholders and AATF’s pipeline of new technology.
While AATF has invested considerable effort in identifying and engaging with investors, to date they have not been successful in winning new funding from new investors, although substantial funding has been received from existing investors. It remains to be seen whether this assumption will hold.
  1. A performance related funding component that is mutually agreed between DFID and AATF supports more rapid development of new technology and the transition to a financially sustainable organisation.
The performance funding mechanism is enabling DFID to focus discussions with AATF on key priorities for the programme.
  1. A sustainable business model for AATF can be identified and institutional development of AATF enables the transition to the new model.
Whilst AATF has made significant strides in assessing options for a sustainable business model, it is not yet clear whether they will be able to structure a clear business model and plan and transition from their existing model.

Monitoring progress throughout the review period
DFID has been in regular contact with AATF through the reporting period. DFID staff attended the AATF Board Meeting in October/November 2017 providing an opportunity to meet with AATF staff and assess the governance of AATF. The AATF Board of Trustees provides effective oversight of AATF and does not hesitate to challenge AATF staff to justify their work and future plans.
DFID also monitors progress through engagement with other key investors (BMGF and USAID) to keep abreast of progress on projects funded by them. This provides a useful cross-reference to AATF’s reports to DFID.

Approach to the Annual Review
The DFID review team consisted of Duncan Barker (Livelihoods Adviser) and Anna Kelly (Deputy Programme Manager). Both attended the AATF Board meeting in Uganda from 30st October to 1st November and the Board report was used as part of the Annual review process. An Annual Review meeting was held on 2nd November with key AATF Staff.

Review Documents.
Business case : VAULT 8066656
Logframe :VAULT 8057199
AATF Reports 2017: VAULT18707036
Terms of Reference :VAULT 1566886
Annual Review - Summary Sheet 2016

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: African Agriculture Technology Foundation Phase III (2015-2020)
Programme Value: £10m		Review Date: 5 January 2017
Programme Code: 204988	Start Date: 5th October 2015	End Date: 30th September 2020

Summary of Programme Performance
Year	2016
Programme Score	A+
Risk Rating	Moderate

Summary of progress and lessons learnt
DFID support to the African Agricultural Technology Foundation (AATF) aims to deliver new agricultural innovation to small-holders in Africa through a financially sustainable organisation that is responsive to the needs of small-holder farmers in addressing market failures in the development and adoption of appropriate agricultural technologies. Although AATF has made good progress towards achieving its planned first year objectives in key areas, as listed below, progress towards institutional change has been too slow.

- Eight new technologies, including cassava cultivation equipment and maruca resistant cowpea cultivars have been accessed.
- AATF and the International Potato Centre have initiated a new project to develop potato varieties with resistance to bacterial wilt.
- Biosafety laws have been passed in Nigeria and amended in Ethiopia and 41 permits have been obtained for conduction field trials of AATF crop varieties.
- Twenty one sub-licences have been signed for commercialisation or research through partners.
- AATF has also achieved stringent USAID environmental regulatory compliance standards.
- A number of promising commercial partnerships have been fostered that also incorporate strong farmer outreach to ensure increased access and availability of AATF supported technologies to its customers.
- AATF has also developed a strong communication platform, promotional activities, educational materials and product branding and is looking to develop these further.
- 112,975 households are using maize varieties developed under the Water Efficient Maize for Africa project.

AATF is developing a new 2018-27 ten year strategy which will incorporate a detailed business plan designed to deepen AATF’s commercial linkages with private sector agribusiness partners. These relationships must generate the future inward private sector investment and revenues to drive AATF’s long term sustainability, shifting it from an institutional donor support paradigm to a longer-term commercially grounded operational model. This is a key area where DFID needs to see a much faster transition to a financially sustainable business model that is less reliant on donor funding.

Key Acronyms
AATF	African Agriculture Technology Foundation
BMGF	Bill and Melinda Gates Foundation
CAMAP	Cassava Mechanisation and Agro-processing Project
CFT	Confined Field Trials
IITA	International Institute of Tropical Agriculture
IR-Maize	Imazapyr herbicide resistant maize
NEWEST	Nitrogen-use Efficient, Water-use Efficient and Salt Tolerant Rice
NUE	Nitrogen Use Efficient
OFAB	Open Forum on Agricultural Biotechnology in Africa ():
PBR	Pod Borer Resistant
WEMA	Water Efficient Maize for Africa

Summary of recommendations for 2016/17
Recommendations are numbered in the order they appear in the main report.
Logframe recommendations
1.	The logframe must be reviewed and indicators revised by February 2017 to more succinctly capture and monitor progress towards achieving commercial outcomes and outputs by AATF. For example, households reached should be disaggregated by dissemination channel (AATF, government, NGO, private company). This will assist in demonstrating and underpinning the commercial viability of AATF supported technologies and also the potential to generate future revenue flows, e.g. royalties and commissions for future institutional sustainability.
3.	AATF should update the logframe targets for future years to reflect better than expected progress during the past year. Targets should be stretching. By February 2017.
5.	AATF to review Output 2 and indicators as the current indicators do not enable an assessment of whether AATF is a “go-to” organisation. This could be in the form of revised output wording, or an additional indicator (by February 2017)
6.	AATF to review and revise indicator 2.1 to provide a more accurate reflection of the range of the communication products delivered (by February 2017).
7.	AATF to clarify how they assess the “quality of media mentions” and how they track new media interactions, to ensure they are able to measure “new” engagement (by February 2017)
10.	DFID and AATF to agree performance indicators for Year 2 by the end of January 2017. Specific attention should be given to strengthening the Reach/Scale indicator by including sales/distribution figures, broken down by distribution channel.

Other recommendations
2.	By February 2017, AATF needs to more clearly demonstrate where the commercial market outlet/‘demand-pull’ is for increased cassava production with clear downstream linkages to aggregators, processors, financiers able to sustain a commercially viable value chains into the future.
4.	DFID to link AATF with other DFID funded Centrally Managed Programmes and implementing partners in East Africa, with the potential for positive commercial synergies with AATF programming and the new ten year AATF 2018-27 strategy and business plan. Specifically, this could include Trademark East Africa, M4D - Mobile for Development and the GSMA strategic partnership projects (by December 2016).
8.	AATF to consider how the successes achieved and lessons learned in research, certified seed production and dissemination of conventional and transgenic maize varieties can be translated to the other crop species with which AATF is now working in southern Africa (Tomatoes, Sorghum, Millet). This could be in the form of a “Lessons Learned” brief presented in the first quarter of 2017.
9.	Dependent on the commercial trials in South Africa, AATF needs to demonstrate how it will license and contract these varieties with commercial partners, that align with and support the new 10 year 2018-2027 Strategy and Business plan (by March 2017).
11.	AATF should up speed up the development of the new strategy and business plan to provide greater clarity on key areas, particularly their approach to commercialisation and institutional sustainability (completed by July 2017).
12.	AATF to update their Monitoring and Evaluation strategy to address the need for independent impact evaluations, with clearly articulated evaluation questions, to provide robust evidence on the impact of AATF technologies and more rigorous data on adoption of technologies (by May 2017).
12.	DFID to continue to work more closely with other investors, principally BMGF and USAID, through coordinated messaging to support AATF’s transition to a sustainable business model – ongoing.
13.	AATF to provide DFID with an updated Asset Register by March 2017.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process