## 2017 logframe
PROJECT TITLE | Kenya Extractives Programme 2015-2018
IMPACT | Impact Indicator 1 |  | Baseline 2015 | Milestone 1 (Sept 2017) | Target (end 2018)
Inclusive, equitable and sustainable economic growth in the extractives sector with reduced risks of negative social, political, economic and environmental impacts. | Inequality-adjusted Human Development Index (IHDI) | Planned | 0.391 | 0.431 | 0.451
Achieved
Source
UNDP Human Development Report
OUTCOME | Outcome Indicator 1 |  | Baseline ( 2015) | Milestone 1 (Sept 2017) | Target (end 2018) | Assumptions
A better enabling environment for investment and a localised and inclusive approach to business and community development in extractives sectors. | Policy Perception Index (Petroleum) | Planned | 52.83 (or 72 out of 126 | 54/100 | 55/100 | Government commitment to extractive sector development is not negatively affected by the 2017 general electoral process and outcome. Incentives for private sector investment in the oil and gas sector are sufficiently strong and remain so over the project life.
Achieved
Source
Fraser Institute Global Petroleum Survey (1)
| Outcome Indicator 2 |  | Baseline ( 2015) | Milestone 1 (Sept 2017) | Target (end 2018)
| Significant changes in extractive sector policy, systems and practice supported by K-EXPRO (2) | Planned | 0 | 2 significant changes (1 moderate, 1 minor) | 4 (cumulative) significant changes (2 major, 2 moderate)
Achieved
Source
Beneficiary feedback; Significant Change Stories
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
| £6.3m |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline ( 2015) | Milestone 1 (Sept 2017) | Target (end 2018) | Assumptions
Increased capacity of local businesses to benefit from supply chain opportunities linked to the emerging oil and gas sector | SMEs with improved business skills, linkages, finance and information | Planned | 0 | Supply/demand gap analysis (PBO) that informs choice of five sectors and approach to supporting SMEs; Feasibility study of potential oil/gas-related business models for Northern Kenya completed. | 30 SMEs with improved capacity to employ more people arising from improved business skills, linkages, finance and information relevant to the oil and gas sector. | SMEs are inclined to capacity building and remain open to working with K-EXPRO partners over the project life.
Achieved
Source
Beneficiary (SME’s) feedback; Case studies, Review of partner reports - PBO, Lundin’s ‘Northern Kenya Growth Capital’ impact investment fund,
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline ( 2015) | Milestone 2 (2017) | Target (2018)
35% | Quality learning materials and knowledge products on key sectoral and operational issues produced and disseminated | Planned | 0 | 1 | 3
Achieved
|  | Source |  |  |  | RISK RATING
|  | PBO, Rebel Group note on impact investing, disseminated to engage stakeholders through forums, seminars and on-line channels including local and international media. |  |  |  | MAJOR
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2015) | Milestone 1 (Sept 2017) | Target (end 2018) | Assumptions
Increased county and community level influence on policy and practice to reduce conflict and investment risk in oil and gas sector | Key community and county issues that are integrated into national and county-level debate | Planned | 0 | Mechanism to deliver constructive dialogue forums involving senior government officials, civil society and industry representatives initiated. | 3 key policy issues integrated in debate (2 national level; 1 county level), including 2 instances of constructive multi-stakeholder cooperation around critical infrastructure projects | The National Government does not stifle space for policy engagement and debate by non-state actors; The County Government and private sector is receptive and responsive to citizens’ views, including those of poor men and women; Private sector, government, civil society, and citizen groups are willing to work together on oil and gas related issues.
Achieved
Source
Review of partner reports, programme documents, case studies (Trocaire, Extractives Sector Forum, Extractives Baraza)
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (2015) | Milestone 2 (2017) | Target (2018)
35% | Quality learning materials and knowledge products on key sectoral and operational issues produced and disseminated | Planned | 0 | 1 | 3
Achieved
|  | Source |  |  |  | RISK RATING
|  | Case studies; Review of partner reports and programme documents |  |  |  | MAJOR
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2015) | Milestone 1 (Sept 2017) | Target (end 2018) | Assumptions
Improved policy, systems and practice at the national level through coordinated extractive sector support | Access to credible and relevant information on extractives policies and projects | Planned | Information Centre on Extractive Sector provided online information. | Robust pathway for public outreach and education on extractives successfully launched. | 10,000 people access credible information on extractives policies and projects; and at least three significant examples of information utility. | Centrally-managed DFID projects are amenable to K-EXPRO’s coordination support; Government MDAs are receptive to DFID support delivered through OPM and other K-EXPRO partners such as UNDP and the World Bank.
Achieved
Source
Review of partner reports and programme documents, Extractives Baraza, Extractives Sector Forum (ESF),
| Output Indicator 3.2 |  | Baseline (2015) | Milestone 1 (Sept 2017) | Target (end 2018)
| Managed hand-over and transition of K-EXPRO supported interventions, including to DFID’s centrally managed programmes (CMP) and/or other partners | Planned | 2 operational CMPs with a focus on Kenya | 2 instances of successful leveraging of effort among CMPs and with K-EXPRO. | 4 (cumulative) instances of successful leveraging of effort among CMPs and with K-EXPRO.
Achieved
Source
Interviews with CMP delivery partners (British Geological Survey, Africa Legal Support Facility, Extractives Hub)
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (2015) | Milestone 1 (Sept 2017) | Target (end 2018)
30% | Progress of legacy interventions (Competency transfer in Ministry of Mines and establishment of National Sovereign Wealth Fund – NSWF) | Planned | No advisors in MoM, SWF modalities not in place | Evidence of satisfactory competency transfer from advisors in MoM, high level strategic advice based on robust analysis provided to GOK to inform the NSWF Bill. | Government White Paper on the establishment and operations of the NSWF, including underpinning analysis published and disseminated.
Achieved
|  | Source |  |  |  | RISK RATING
|  | Review of partner reports and programme documents, in particular World Bank’s Aide Memoires; Ministry of Mines satisfaction survey; |  |  |  | MAJOR
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
1 The methodology used by the Fraser Institute changed in 2016 so that a score of 100 meant the country had the most attractive policies and a country with policies posing the greatest threat to investment was assigned a score of 0. Previously, and for 2015, a higher score signified that a country would be relatively unattractive for investment. The results of the petroleum survey are released in December each year.
2 There are three foreshadowed levels of “significant change”: minor, moderate and major where, • Minor = immediate steps taken that indicates a broadened knowledge or competency base. Eg supportive language and rhetoric; new behaviour in key actors, etc. • Moderate = actions which though important preconditions for a major change, have limited impact across the institution: Eg framing debates and getting issues on the political agenda; opening up spaces for dialogue, and constructive stakeholder consultations on policy and institutional reform, etc. • Major = shift in policy, practice and capacity with a clear impact across the institution or agency. E.g. a new policy, law, regulation or guideline is formulated, a new system or procedure becomes operational, new technology is institutionalised, etc.

## 2016 logframe
PROJECT NAME | DFID Kenya: Kenya Extractives Programme 2015-2019
IMPACT | Impact Indicator 1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
Inclusive, equitable and sustainable economic growth in the extractives sector (and therefore a reduction in poverty), with reduced risks of negative social, political, economic and environmental impacts. | Higher GDP growth (disggregated by extractives and non extractives sectors) | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
National Statistics, Police Reporting and CSO/Media Monitoring Reports
| Impact Indicator 2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Increase in public expenditure from extractives revenues | Planned | To be difined at inception phase | To be difined at inception phase | To be difined at inception phase | To be difined at inception phase | To be difined at inception phase
Achieved
| Impact Indicator 3 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Percentage change in Gini Coefficient in Kenya | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019) | Assumptions
A better enabling environment for business, strengthened governance, and a localised and inclusive approach to community development in extractives sectors. | Number of new jobs created in supported oil, gas and mining industries, and their ancillary sectors (disaggregated by gender) | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be completed at inception phase
Achieved
Source
| Outcome Indicator 2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Increased FDI in extractives and ancillary sectors | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
| Outcome Indicator 3 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Improved Fraser Index rankings on 1) policy perceptions; 2) regulatory environment (for Petroleum and Mining) | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
| Outcome indicator 4 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Supported partners conducting strategic Environmental assessment (SEA)& Environmental Inpact assessment (EIA) in their interventions | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
| Outcome Indicator 5 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Reduction in days of stopped oil exploration working days lost by extractives companies as a result of local conflict | Planned | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
INPUTS (£) | £24m
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
Increased capacity of relevant GoK extractives sector institutions | Advisory facility in place to increase capacity of the Ministry of Mining to discharge policy and projects delivery functions with clear evidence of technical capacity transfer. | Planned | One gender adviser embedded in MoM by UN Women, all other technical assistance and capacity building delivered through external consultants | • Two advisers effectively embedded in MoM with a work plan to end of year agreed. • TOR for another two advisers agreed with MoM | • Four advisers effectively embedded in MoM with a work plan to end of year agreed. • Clear evidence of progress and capacity transfer on at least one major project per adviser. | • Four advisers effectively embedded in MoM with a work plan to end of year agreed. • Clear evidence of progress and capacity transfer on at least one major project per adviser. | • Four advisers effectively embedded in MoM with a work plan to end of year agreed. • Clear evidence of progress and capacity transfer on at least one major project per adviser.
Achieved
|  | Source | [5 empty] | RISK RATING
Major
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019) | Assumptions
30% | KEPTAP delivers on its agreed workplans through effective ownership and coordination by the Ministry of Energy and Petroleum of other GOK institutions. | Planned | KEPTAP rated 'moderately satisfactory' in Oct 2015, with admitted delays in planning, procurement and reporting | Two world bank technical missions undertaken with evidence of progress in delivery of KEPTAP work plans * | Three world bank technical missions undertaken with evidence of progress in delivery of KEPTAP work plans. | Three world bank technical missions undertaken with evidence of progress in delivery of KEPTAP work plans. | Three world bank technical missions undertaken with evidence of progress in delivery of KEPTAP work plans. | DFID successfully negotiates a would bank executed Trust fund. Ministry of mining welcomes DFID support through UNDP There is political will from GOK to establish a sovereign wealth fund.
Achieved
Source
INPUTS (£)
| Output Indicator 1.3 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
INPUTS (HR) | Concept for an extractives Sovereign Wealth Fund agreed at the highest level in GOK (Presidency and National Treasury) and corresponding legislative and regulatory processes ongoing to support its implementation | Planned | • No SWF in place • some SWF provisions in draft Mining Bill and Petroleum Bill | • KEPTAP has agreed a SWF workplan with NT • NT rceived technical imput/review of a SWF Bill to be tabled to Parliament | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
| Output Indicator 1.4 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Ministry of Mining has the capacity to acquire, manage and provide access to geophisical information to attract mining investors and to support other GoK institutions | Planned | Geological mapping and reports are scattered, incomplete and diffficult to access for MoM and for prospective investors | • Agreement with BGS negotiated with MoM for assistance towards the geodata bank and airborne survey • MoM effectively coordinating geophysical survey processes with other GoK institutions | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
Source
| DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 6000000 |  | 0
| DFID (FTEs) | [6 empty] | RISK RATING
Moderate
| Output Indicator 2.1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019) | Assumptions
OUTPUT 2 | Fit for purpose and self sustainable extractives information centre in place. | Planned | ices.or.ke established as a respected source of information in Kenya, but fully funded by DFID and with non-strategic obejtives and readership | Agreement with Stratmore university to effectively manage and redesign the information centre for extractives. | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | Non-state actors develop credible proposals that can be funded through the challenge fund. Information centre for extractives attracts relevant stakeholders and that the information os used to demand better governance of the extractives sector.
Improved capacity of non-state actors to demand governance and accountability and to hold authorities to account. |  | Achieved
Source
| Output Indicator 2.2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Effective demand-driven support to civil society organisations provided, industry bodies and other non-state actors with evidence of enhanced social accountability of petroleum and mining industries. | Planned | CSOs receive scant and project-based support for promoting extractives transparency and accountability | Service provider procured and tasked to set up a dedicated challenge fund and capacity building mechanism | To be defied at inception phase | To be defied at inception phase | To be defied at inception phase
Achieved
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
20% | [7 empty] | Moderate
| Output Indicator 3.1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019) | Assmptions
OUTPUT 3 | working conditions** and revenue of artisanal and small-scale miners improved in selected counties and where ASM has a significant socio-economic footprint | Planned | Provisions on ASM are included in draft mining legislation and regulations | Initial engagement to gather evidence on artisanal miners to lead to the development of a dedicated project | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | Political will from County Governement to engage. Local CSOs have the will and capacity to engage .
County engagement platforms operating effectively |  | Achieved
Source
| Output Indicator 3.2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Dialogue and development platforms supported in select counties,where oil and gas related industries have a significant socio-economic footprint leading to perceived equitable and fair sharing of revenue, of social development projects and of economic opportunities (jobs and local contracts) among County Institutions and concerned communities. | Planned
Achieved
Source
|  | Planned | Turkana community engagement pilot delivered under KEIDP | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase | To be defined at inception phase
Achieved
IMPACT WEIGHTING (%)
20% | DFID (£)
|  |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (£) | DFID (FTEs)
RISK RATING
INPUTS (HR) | [7 empty] | RISK RATING
| Output Indicator 4.1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019) | Moderate
OUTPUT 4 | Domestic enterprises improve*** their ability and number of times they bid for contracts within the oil & gas (and similar) value chains | Planned | • Initial 'local content' mapping study delivered under KEIDP • Oil&gas and mining investors develop their value chains in uncoordinated manner | Agreement with World Bank signed; work plan agreed and two monitoring missions undertaken for KEPTAP component to increase opportunities for domestic private sector in Extractives value chains. | To be defined at inception | To be defined at inception | To be defined at inception | Assumptions Private companies are incentiviced to engange in the programme. The services of the local SMEs are aligned with the demands of the extractives companies.
Increased opportunities for domestic private sector in the extractives value chains. |  | Achieved
Source
| Output Indicator 4.2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Improved alignment between SOGA plans to develop skills and qualification of Kenyan workers with KEXPRO's priority value chains and the same key investors | Planned | SOGA inception and launch in Kenya completed | at least three SOGA board meetings and one advisory council ensure stakeholder participation in selecting SOGA projects and partnerships
Achieved
Source
IMPACT WEIGHTING (%) |  | Planned | To be defined at inception | To be defined at inception | To be defined at inception | To be defined at inception | To be defined at inception
Achieved
20%
DFID (£)
|  |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (£) | DFID (FTEs)
INPUTS (HR) | [7 empty] | RISK RATING
| Output Indicator 5.1 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019) | Minor
OUTPUT 5 | Number of quality learning materials produced and presented by the service provider on key setoral and operational issues of programme implementation. | Planned |  | Service provider procured; strategic partnerships signed and inception phase launched. | To be defined at inception | To be defined at inception | To be defined at inception | Assumptions
Managing, learning & Adapting DFID engagement on Extractives in Kenya. |  | Achieved | [5 empty] | Service Provider procurement through wealth creation framework is delivered within agreed timelines. Ministry of mining accepts DFID's engagement through UNDP. The world Bank sets up a multi-donor trust fund for the petrolueum sector. Stakeholders (private sector, GOK, Civil Society and other development partners) are willing to engage in stakeholder analysis. DFID Kenya remains keen to engage with select CPMs.
Source
| Output Indicator 5.2 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
| Number of quality learning forums conducted by the service provider looking at both failures and successes involving implementers and key stakeholders | Planned |  | Service provider procured; strategic partnerships signed and inception phase launched. | To be defined at inception | To be defined at inception | To be defined at inception
Achieved
Source
| Output Indicator 5.4 |  | Baseline (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target (2019)
IMPACT WEIGHTING (%) | Number of Instances in which evidence and learning has bee used to improve programme implementation | Planned |  | None | To be defined at inception | To be defined at inception | To be defined at inception
Achieved
10% |  | Source
INPUTS (£)
* During Implementation Support Missions WB senior staff engages with GoK / MoEP to provide supervision to implementation, monitor progress, adjust plans for the work ahead and conduct policy dialogue. DFID Kenya participates officially and receives the resulting aide memoires as monitoring reports for our contribution to KEPTAP.
** Working conditions are in terms of health and safety standards, environmental standards, contractual conditions (in case of employed miners), ability to market the product at fair price (in case of self-employed or small enterprises), ability to add value in order to increase revenue, actual possibility to be regulated, compete fairly and pay tax
***Measures of improved quality of bids and the number (or value) of successful bids – and their timing – can be devised during the inception phase

## 2015 BC logframe
PROJECT NAME | DFID Kenya: Kenya Extractives Programme 2015-2019
IMPACT | Impact Indicator 1 |  | Baseline (2008) | Milestone 1 (2015) | Milestone 2 (2016) | Target (2017)
Inclusive, equitable and sustainable economic growth in the extractives sector (and therefore a reduction in poverty), with reduced risks of negative social, political, economic and environmental impacts. | Higher GDP growth (disggregated by extractives and non extractives sectors) | Planned
Achieved
National Statistics, Police Reporting and CSO/Media Monitoring Reports
| Impact Indicator 2 |  |  | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Increase in public expenditure from extractives revenues | Planned
Achieved
| Impact Indicator 3 |  |  | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Percentage change in Gini Coefficient in Kenya | Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline 2013 | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | Assumptions
A better enabling environment for business, strengthened governance, and a localised and inclusive approach to community development in extractives sectors. | Number of new jobs created in supported oil, gas and mining industries, and their ancillary sectors (disaggregated by gender) | Planned
Achieved
Source
| Outcome Indicator 2 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
Increased FDI in extractives and ancillary sectors
Source
| Outcome Indicator 3 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
Improved Fraser Index rankings on 1) policy perceptions; 2) regulatory environment (for Petroleum and Mining)
Source
Outcome Indicator 4
Reduction in days of stopped oil exploration working days lost by extractives companies as a result of local conflict
INPUTS (£) |  |  | Source
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | Assumptions
Increased capacity of relevant GoK extractives sector institutions | Improved resource management and accountability of selected institutions and agencies (including MoM, MOEP, NEMA and other key agencies)
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Kenya's score on the NRGI Resource Governance Index | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 6000000 |  | 0
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | Assumptions
Increased supply of Kenyan skilled workers and increased competitiveness of local suppliers in extractive sector operations | Number of new Kenyans trained extractives-related skills in focal TVET institutions
Achieved
Source
| Output Indicator 2.2 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
Improved capacity of trainers within focal TVET/skills institutions
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Improved Fraser Institute Ranking on labour availability and skills (in petroleum and mining) | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
| Output Indicator 2.4 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of new contracts with local suppliers in selected sectors supported by the programme (directly or indirectly) | Planned
Achieved
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1500000 |  |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 4.1 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | Assumptions
County engagement platforms operating effectively | Number of high quality platform meetings per county | Planned
Achieved
Source
| Output Indicator 4.2 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Participant satisfaction survey scores from county platforms (from all stakeholders) | Planned
Achieved
Source
IMPACT WEIGHTING (%)
30%
RISK RATING
DFID (£)
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
DFID (FTEs)
INPUTS (HR)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | Assumptions
Improved capacity of civil society and industry bodies to hold authorities to account | Number of high quality position/policy papers and reports developed by CSOs and BMOs that have multi-stakeholder uptake | Planned
Achieved
Source
| Output Indicator 4.2 |  | Baseline (2013) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of public-private dialogue meetings between industry associations and GoK | Planned
Achieved
Source
IMPACT WEIGHTING (%)
30%
RISK RATING
DFID (£)
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
DFID (FTEs)
INPUTS (HR)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.