ADDENDUM TO BUSINESS CASE

SUMMARY INFORMATION
Project Name	Market Development Programme in the Niger Delta (MADE)
Country or region targeted	Niger Delta Region, Nigeria
Type of cost extension (if applicable)
Original project budget	£14,299,000
Original project start and end dates	September 2013 – December 2018[1]
Cost extension value (if applicable)	£7,150,000
New project end date (if applicable)	February 2020
Business Case Quest Document No.
[1] The project formally closes in December 2018 – a date loaded onto Aries in error, as the business case sets Feb 2018 as the end date. Project (budget, activities and results) are planned on the basis of the expected end date in February, when the contractor will cease operations.

INFORMATION
What is the project’s purpose?
MADE’s purpose is to diversify and increase economic growth in the non-oil sectors of the Niger Delta region, for the benefit of the poor. The existing project is on track to raise the incomes of 153,000 people by February 2018 (surpassing agreed targets). It achieves its impact by supporting innovation in market systems through technical assistance and financing to private sector companies, who then invest in ways that benefit the poor, either as suppliers, clients, consumers or employees.
What is the objective of the cost extension or other changes?
The first objective of this extension is to double the income impact and other measured results of the project in half the time, and at half the cost, of the original project. It will also deliver a higher proportion of these results in the poorest and most conflict affected states in the region. A sub-objective is to build on the impact on individual livelihoods directly affected by the project, by seeking transformative, structural changes in the markets in which the project is focused, driving higher levels of productivity which will benefit many millions indirectly, and the economy more broadly. / A second objective of the extension is to exploit the presence and expertise of the project team in relation to the Modern Slavery agenda. The Delta region is a significant source of trafficking of people to Europe, and the Prime Minister and SoS have committed DFID to doubling their spend on this issue. MADE’s Market Development approach is relevant for establishing alternative livelihoods and aspirations to reduce the push factors behind migration, to complement other interventions to be developed through a separate anti-slavery business case. / Each objective is set out in more detail below: / Objective 1: Doubling project results, including increasing the incomes of an additional 150,000 people. / The prosperity of the Delta region is critical to Nigeria’s development. Poverty and instability affect not only the region’s 31 million people, but also Nigeria as a whole. The Niger Delta is one of the country’s poorest regions, second only to the extreme north. There are high levels of gender inequality; continuing instability and insecurity affecting economic activity and oil exports; low levels of education and high levels of unemployment; severe environmental degradation; and exceptionally poor infrastructure. Overall, the levels and intensity of poverty are high, and the wealth the region generates from oil leads to strong sentiments of injustice, leading in turn to criminality and eruptions of violence and insecurity, further aggravating and perpetuating the incidence of poverty. In recent weeks (November 2017), a leading Delta militia have declared an end to their ceasefire, and expressed an aim to reduce oil production in the area to zero through sabotage. / Amidst mounting tensions in the Niger Delta region, there is some evidence of increasing political enablers that justify continued intervention. The Pan Niger Delta Elders’ Forum (PANDEF) assembled to act as a mediating body between citizens and government, presented a 16-Point Agenda in November 2016, ‘Solving Niger Delta Issues by Dialogue,’ as minimum pre-conditions for peace and security in the region. Simultaneously, a series of engagements by the Office of the Vice President culminated in the issuance the 20-Point Agenda and development of a Strategic Implementation Work Plan, to address the Delta’s critical development issues. The initiative is anchored within the leadership of relevant Ministries, Departments, and Agencies, with several of whom MADE enjoy a close and collaborative relationship. / Women in particular face a number of challenges (social, economic, cultural and political) that inhibit their full involvement in economic activities in the Niger Delta. MADE has successfully worked to change harmful behaviours and practices impacting women’s economic empowerment (WEE) in the region, but significant work remains to be done. / Market development projects are high risk, delivering results at scale usually only after considerable experimentation and adaption in preceding years. MADE is at the point where several intervention areas show significant promise of expanded impact with continued work and support. The doubling of results, at half the cost and in half the time - even with a greater focus on the most frontline of the conflict affected states - is possible due to the sunk costs, experience acquired, and strong potential of established intervention areas to reach greater scale. / The programme has aimed to make the terms of engagement better for the poor in six target markets: palm oil; traditional poultry; cassava; fisheries; agricultural inputs; and finished leather goods. There is cross cutting work on improving access to finance, which will be expanded to cover all sectors during the extension, and on gender inclusion. MADE’s targets demand 50% of beneficiaries are women, and the programme has exceeded them. The project is likely to drop work in the least rewarding sector to date (leather), but start work in sectors identified as having the greatest potential of generating ‘aspirational’ livelihoods of interest to those at risk of trafficking. These are likely to include hospitality, ICT, and the creative industries, especially in the city at the epicentre of the trafficking crisis, Benin, in Edo State. / In its latest Annual Review (July 2017) MADE exceeded its targets, and is on track to further exceed final project targets set for February 2018. This indicates that many of the high delivery risks associated with market development projects have been overcome, and justifies the scaled-up targets adopted in this Addendum. / The BC addendum will also allow MADE to develop a more systemic and transformative approach to the sectors in which they work. Typically in market development projects, initial entry points into sectors are focused at the individual level, driving investments by partner businesses that have a direct impact on a measurable number of the poor. As interventions build and mature however, it becomes increasingly possible to work at a wider scale, understanding the types of investments that can shift industry wide productivity, and open up new opportunities that can benefit much larger numbers of people. For example, existing interventions in aquaculture have to date focused on training businesses, selling courses to fish farmers, and improving the productivity of trainees, and increasing the demand for higher quality inputs such as fish feed. Going forwards, the MADE team should be able to exploit this base, and the pioneering examples of a few beneficiaries, to look for further industry wide opportunities, such as establishing export supply chains, which could have a wider, transformative impact on the sector. / Objective 2: Generating ‘aspirational’ opportunities for those at risk of trafficking / The BC addendum will allow the programme to identify and address livelihood and economic factors contributing to human trafficking, forced labour and modern day slavery in the region, particularly in Edo State. Modern day slavery (MDS) is a critical issue throughout Nigeria, but most acute within the Niger Delta region, from where the majority of those trafficked to Europe originate. The presence of MADE presents a unique opportunity to apply market systems activities, specifically to increase the resilience and vulnerability of those most at risk of being trafficked. / Human trafficking can be traced back to economic ties between Southern Nigeria and Italy in the 16th century, in which Edo State women have played an important part. However, in recent decades, these women were compelled by changing economic circumstances to gradually settle into prostitution, often coming home to recruit siblings, friends and relatives. In recent years, human trafficking from Edo State has been increasing and an established channel has developed taking women and girls into forced labour both in other parts of Nigeria and abroad.[2] Today, Nigeria is the largest contributor to trafficking from Africa into Europe.[3] The weekly DFID Situation Report report on Mediterranean crossings for the week of 7th November noted 3200 people rescued and at least 40 deaths, including the deaths of 26 Nigerian girls aged 14 to 18 – press reports suggest they could have been victims of abuse and murder during the crossing. / Causes and drivers of trafficking are complex and not fully understood. More research is required[4] to understand the interplay of opportunity, law enforcement, social norms, ignorance and awareness of realities of being trafficked, and financial drivers. While perceptions of poverty may drive the desire to emigrate, for example, it is the better-off who are able to fund journeys. This interconnectivity between politics, economy and vulnerability—particularly of women and girls—has triggered a strong interest linking MADE and the modern day anti-slavery agenda of HMG and the Home Office. / Given its understanding of, and relationships with, the political and economic systems, institutions, and actors, MADE is uniquely placed to pilot interventions aimed at tackling the root causes of MDS, strengthen efforts to combat slavery and reduce vulnerability, and simultaneously build an evidence base to support DFID and the donor community’s better understanding of what works in the future. / A target of increasing incomes or providing livelihood opportunities to 30,000 people (as part of the target to add 150,000 incomes increases) within at risk geographies and demographic groups has been proposed. Ongoing research suggests care will be needed to ensure these income increases do not spur migration. MADE will focus on sectors such as ICT, hospitality and the creative industries to support investment and growth in sectors that are seen as ‘aspirational’ and attractive to potential victims of trafficking, and thus reduce drivers for emigration. / An additional £4m business case is under development to tackle wider elements of the Modern Slavery crisis, including working with Edo State’s anti-slavery task force and the Nigerian anti trafficking agency. The UK government already has a prominent operational role through its National Crime Agency, and the Home Office is rolling out a £5m programme focused on strengthening law enforcement and the rehabilitation of victims. A November review of EU donor partner funded work on Modern Slavery in Nigeria revealed a list of around 30 separate initiatives ranging in size from under £100,000 to over £15m. To date none of these are approaching prevention from a livelihoods perspective, although livelihoods support is a common response to help returned victims of trafficking[5]. / Evaluation objectives / In addition to the two main objectives above, the extension also allows for substantial improvements to the evaluative value of the project, and the lessons that can be learned. / During the extension, MADE will: / Monitor changes in the creation of local employment opportunities and any improvement in wage levels for farm labourers and employees of smallholder farms and small-scale enterprises reached by MADE interventions; / Assess how enhanced productivity leads to increased net income and enhanced profitability for beneficiaries; / Deepen assessments of programme impact, to ensure the model is leading to tangible and measurable improvement in the quality of life of beneficiaries and an increase in access to social services (i.e. education, health); / Develop and evaluate theories of change that apply to the economic drivers of trafficking / Wider strategic objectives / The MADE project continues to align and respond to DFID and HMG strategies: / Economic Development Strategy: The MADE project responds to the EDS, within which commercial agriculture is a core priority. In particular MADE reflects the strategy’s demands to “take an increasingly commercial approach to agriculture by: boosting agri-business; promoting commercially-viable agriculture by transferring knowledge and inputs to smallholder farmers and linking them to markets”. It will also “promote responsible agriculture investments”, and through its explicit targets, reach the poorest, and directly “seek to empower women and prevent them from being stuck in low return activities.” / MADE will also help enable DFID Nigeria respond to the four priorities of the Single Departmental Plan: / 1. Strengthening global peace, security and governance: MADE is conceived and operates as a direct response to the poverty and inequality that drives conflict and instability in the Delta region. Its new support on the Modern Day Slavery agenda will also challenge the incentives and motivations of victims and operators of the criminal and violent trafficking structures. / 2. Strengthening resilience and response to crisis: Market access to inputs, buyers and technology represents a critical part of increasing resilience to the economic, environmental and domestic risks facing subsistence farmers in the Delta region / 3. Promoting global prosperity. The MADE project has worked with leading global firms in agribusiness, helping their investments benefit the poor, and establishing the Delta as a place to do business. Under the Addendum, MADE will continue to deepen its close relationship with UK Department for International Trade, collaborating on investor events, market information and business linkages. / 4. Tackling extreme poverty and helping the world’s most vulnerable: MADE’s target are explicitly focused on the benefits its derives to poor, and the Modern Day Slavery agenda directly targets an extremely vulnerable group.
What is the additional and total support the UK will provide?
The extension will provide an additional £7.15m. The total cost of the project support will rise to £21.45m. The current contractor has provided a full draft budget, summarised in the tables below. / Table 1: Budget by expense category. / Fees / Management/support £1,928,770 / HO support £48,685 / Technical team £1,195,176 / STTA £735,749 / Total Cost of Fees £3,908,380 / Expenses / Total Travel Costs £126,706 / Total Living Costs £364,221 / Total Equipment Costs £57,500 / Total Other Costs £617,894 / Grants & Activities £1,993,500 / Impact Evaluation £81,800 / Total Cost of Expenses £3,241,620 / Total Contract £7,150,000 / As in the existing project, and typical of market development programmes, the main cost driver is the use and management of experts and consultants (and their associated costs), as change is facilitated by providing knowledge and brokering new partnerships. / Table 2: budget by activity component / Modern Day Slavery / MDS Commissioned Research, Studies £500,000 / Pilot Activities £1,500,000 / Scale-Up Activities £800,000 / M&E and Communications £200,000 / TOTAL MDS £3,000,000 / Market Systems Development / Agricultural Inputs £800,000 / Cassava £810,000 / Fisheries £690,000 / Palm Oil £450,000 / Traditional Poultry £690,000 / Access to Finance £390,000 / Cross-Cutting (M&E, Gender, Communications) £320,000 / TOTAL MARKET DEVELOPMENT £4,500,000 / Total £7,500,000 / Once further research is done, the MDS component will also be broken down into sub-sectors such as hospitality, ICT or the creative industries. / The Cross-Cutting budget line item covers project M&E, gender mainstreaming, as well as communications, for the Market Systems activities. A separate M&E and communications budget is included within the MDS component, as communications will be a fundamental part of the overall approach to reducing drivers of trafficking.
What are the expected results?
Recent results: / The July 2017 Annual Review of MADE sets out the recent results and the levels to which they exceeded targets: / At impact level / 79,000 smallholder farmers and entrepreneurs had achieved a 15% income increase attributable to project intervention, against a target of 77,000. This figure was measured in March 2017 and is expected to rise by February 2018 to 153,000 (against a target of 151,000 / Net additional income change of £4,128,665, representing 85% of target as most beneficiaries reached in the third year of the programme were yet to gain additional income. / At outcome level / 102,000 people had experienced increased yield/productivity and sales, against a target of 86,000. This figure was measured in March 2017, and is expected to rise by February 2018 to 180,000 (against an original target of 168,000). / At output level: / Assisted 131,658 (117% of target) small and medium-scale farmers and entrepreneurs to access new and improved inputs, products, services and technologies. This is expected to reach 230,000 by February 2018; / Partnered with 22 lead firms (122% of target) to invest in MADE piloted innovations; / Worked with 341 (124% of target) service providers and entrepreneurs that are investing in MADE pilot markets. By end of September 2017, 3 additional lead firms started investing in the different markets, giving a total of 25 to date; / Worked with 8 (160% of target) investors adopting additional pro-poor market development approaches. Currently, a total of 11 investors have adopted additional pro-poor market development approaches; and / Influenced 5 (125% of target) development agencies and NGOs to implement additional market development interventions that are attributable to the programme. Four more development agencies and NGOs have adopted pro-poor market development interventions, giving a total of 9 to date. / The project also exceeded its gender targets, achieving 110% engagement of targeted women beneficiaries, and achieved 113% for reaching beneficiaries that are poor. Targets for the end of project activities in February have recently been revised upwards (in November 2017), and it is now expected the project will reach 230,000 beneficiaries who will have accessed new and improved inputs, products, services and technologies, resulting in approximately 153,000 income increases. / Projected results 2018-2020 / Results expected under this Addendum double those expected by the end of the current activity in February 2018. / Impact: / Increased Growth and Income, especially for Poor Men and Women, in Target Markets in the Niger Delta. / An additional 155,000 poor people (of whom at least 50% will be women) will have increased incomes of at least 15%. At least 30,000 incomes will be derived from sectors considered as aspirational by potential victims of trafficking[6]; / Selected target markets in the Delta region are working better for poor people and potential victims of trafficking (qualitative indicator drawing on a set of criteria). / Outcome 1: / Small scale farmers and entrepreneurs benefit from improved engagement in selected Markets / An additional 218,000 small-scale farmers and entrepreneurs make changes in their farming or business practices as a result of the programme. These measures will focus specifically on improving the quality of income and improving product quality and competitiveness. / An additional 167,000 poor people have increased yields, productivity or sales as a result of programme interventions; / Outputs linked to Outcome 1: / 1A) An additional 320,000 poor people are reached by project interventions / 1B) An additional 10 private sector companies, 9 support services providers (private, government, non-government) and 4 development agencies make changes in their approach to the Niger Delta region. / Outcome 2: / Increased growth in sectors considered ‘aspirational’ by potential victims of trafficking. / £10million attributable to project support is invested in sectors considered ‘aspirational’ by potential victims of trafficking / Outputs linked to outcome 2 / 2A) 30 companies have agreed credible investment plans in ‘aspirational’ sectors supported by the project with a combined total value of £15m / 2B) Research and analysis identifying economic drivers amongst victims of trafficking / 2C) Action-oriented policy dialogues and partnerships with relevant research institutions, government agencies and private sector organizations promoted or enhanced / Revisions are expected as a result of forthcoming research into the economic drivers of migrants / Value for money / This cost extension is proposed on the basis of substantially increasing the value for money of the project. Sunk costs, mature interventions that offer potential for expansion, and an experienced and networked team, present an opportunity for generating additional results at much lower cost, and in shorter time, than those obtained in the original project period. / As the programme has matured, VFM improvement has accelerated. Outreach costs have reduced, particularly the cost of reaching women and the poor. The value of private sector investment leveraged by MADE has also considerably increased (£4 million more in 2017 than the previous year), which not only enhances VfM but is also an essential signal for achieving sustainability. / The indicator ‘Beneficiary income gain per £ spent’ is the project’s most important cost/benefit indicator[7]. The value achieved by March 2017 (£0.40) is lower than that projected (which was £0.46), but is on track now to reach its target of £0.86 by the end of the project. Based on the programme projections, and rapid recent delivery of results, the expected trajectory for the MADE beneficiary income gain per £ is as follows, assuming no extension, and with income gains projected into the period beyond the end of the original project: / Indicator March 2017 Feb 2018 March 2020 / (post-project projection) / Net Additional Income Change £4,128,665 £12,294,631 £36,308,801 / Cumulative costs £10,373,406 £14,299,032 £14,299,032 / Income gain per £ £0.40 £0.86 £2.54 / The extension will substantially improve these figures by delivering the same number of results again at half the cost, as the estimates below show. The gains in VFM (derived from expanding existing interventions rather than starting from scratch) are particularly noteworthy given the greater focus on frontline conflict states and the focus on modern slavery, and are based on assumptions around the scale up of existing interventions. / Indicator March 2020 March 2022 / (post-project projection) / Net Additional Income Change £ 15,245,341 £36,017,146 / Cumulative costs (of extension) £ 7,150,000 £ 7,150,000 / Income gain per £ £2.13 £5.03 / The figure of £2.13 compares positively to MADE’s sister programme PROPCOM[8], who’s recent extension proposal was approved with an equivalent figure of £1.34 – also working in a high cost, conflict affected environment in Nigeria.
What is the approach to implementation?
Market development / MADE’s core approach remains the same - a market development method that: / identifies markets that affect the poor; / identifies barriers within those markets that can be overcome by private sector investment, or policy change; / secures those investments or policy changes through technical assistance, partnership building and linkages, or reducing risks to investors; / is highly adaptive to respond to new opportunities, and to drop interventions that are not attracting investment or change; / works to crowd in other investors to replicate successful investments; / measures the impact on the lives of the poor. / This approach is designed to achieve both sustainability and widespread impact, as the changes result from decisions based on commercial reasons. If successful, those making money from the intervention will continue to invest, and be copied by others. The approach, especially at the beginning of projects, is often slow and high risk, as it is very hard to identify the right opportunities and it takes time to understand the markets you are operating in. MADE relatively slow and unsuccessful initial phase (typical in projects of this nature) has now matured and is delivering results. / Geographic outreach in conflict affected areas / MADE has steadily increased its outreach throughout the project period into the more conflict affected and volatile front line states. Under this addendum, MADE will increase the focus on those states. At the same time, it will maintain support in neighbouring, lower risk states through interventions built on existing activities, requiring relatively lower investment. / MADE will adapt its present strategy to achieve more results more conflict affected areas by: / Selecting appropriate interventions in markets where minimum efficient scale requires low upfront investment in order to minimise risk and keep a low-profile in the presence of social tensions; / Utilising more local partners as delivery channels, after careful selection and training; / Considering options of remote capacity building and technical assistance delivery; / Proactively engaging with Government and other institutions for coordination, information sharing and risk-management; / Attracting appropriate investors with a suitable risk appetite to expand their work in the frontline states; and / Where applicable, liaising with DFID/HMG to leverage their convening power for strategic dialogue with key institutional and business stakeholders in the region. / Focusing on scale-up / Under this Addendum, MADE will graduate interventions and/or sectors that have reached the tipping point for sustainable growth, focus increasingly on achieving scale and triggering more fundamental, and wider changes to market systems. There are options within most existing intervention areas to achieve this, either by supporting larger number of companies, or bigger companies, or building on pioneers successfully supported to date. Some firms or products are becoming export ready, for example, which will substantially change and widen market impact. The programme will also implement a coherent ‘corporate engagement’ strategy to develop more strategic partnerships and leverage other donor activities and market opportunities in the targeted markets. / The following table provides some examples of new opportunities to scale up, that build on existing achievement in each value chain / Interventions Highlights to date New opportunities / Inputs Partnerships with Saro, Syngenta, Candel and Contec to deliver extension services that embeds input distribution, reaching up to 98,000 farmers More partnerships with major input dealers to promote more efficient distribution of fertilizers, seeds and crop protection products; / Seed multiplication and distribution; / Strengthen the spraying service market; / Cassava Partnerships with Saro and Candel to deliver extension services to farmers with embedded input distribution systems - Investment promotion of SME processing mills to process starch and glucose / - Improving quality of supply from poor farmers to processors / Aquaculture -Pond management training and NAEC / -Delivery of commercial fish smoking services - Feed production and distribution / - Hatcheries (fingerlings and juveniles) / - Fish for processing and export / - Improved fish preservation and packaging / Poultry Partnerships with veterinary pharmaceutical companies to promote access to vaccines and vaccination services using the village level dealers model - Chicken processing for end-market / - Off-taking and retail of chickens and eggs / Palm Oil -Distribution of fertilizers, crop protection products and seeds / - Distribution of harvesting technologies / -Delivery of commercial harvesting services / - Manufacturing/fabrication of small scale processing equipment - Palm oil refining to meet international standards for exports / - Link producers of crude palm oil to international buyers. / Building Co-Facilitator Capacity. MADE will continue to support capacity development of non-governmental organizations (NGOs) and private firms to serve as co-facilitators. Working through MADE’s CAPABLE M4P Training, in conjunction with the Chevron Foundation-funded Foundation for Partnership Initiatives in the Niger Delta (PIND) programme, MADE will engage and mentor selected co-facilitators to implement various market development interventions and scale-up work in the frontline states in order to reach more target beneficiaries. This mentorship process will strengthen the organizations’ programming capacity and reach, build their credibility and promote sustainability in the market. / Government Engagement. MADE is systematically engaging with government institutions at regional, state and local levels, in order to increase the impact of its interventions. In the extension, the programme will develop an evidence-based strategy to expand advocacy to government. This advocacy will target market access infrastructure as this is a critical driver of local producers’ empowerment and better business performance, as well as a sound enabling environment. On the latter, MADE’s recent, influential research into the impact of the devaluation of the Naira on its target value chains, has identified a series of opportunities for positive government engagement. / Women’s Economic Empowerment. MADE is already exceeding its outreach targets for women through the innovative use of women oriented co-facilitators and will continue to target and empower women, particularly those who are unmarried women and those that do not own or have sustainable access to land. MADE will identify and monitor behavioural change with regard to gender stereotypes affecting women’s participation in the target value chains and influence over decision-making related to economic resources. Gender-related interventions will include male engagement and influencing of power-holders and role models in the relevant markets. / Addressing Modern Day Slavery. / Research / Much remains to be learned about the nature and extent of MDS, the underlying factors that are driving it, and how best to address the issues in Nigeria. Deepening the foundational understanding of the underlying causes and political economy of MDS in Edo State, and why it is so prevalent there, is necessary before embarking on interventions to address those underlying causes rather than the symptoms. MADE has recently initiated a research programme that will produce a political economy of the issue, as well as using surveys to understand vulnerabilities, motivations, and the aspirations of those most likely to be affected. / MADE will carry out research, build staff capacity, build stakeholder relationships, design target interventions, and initiate pilot activities that will generate knowledge about the most effective interventions for targeting vulnerable and at-risk populations. / MADE will partner with a specialised firm to design and pilot techniques for conducting MDS-focused analyses and how to incorporate the findings of this evidence-based tool into specific interventions and Monitoring, Evaluation and Learning (MEL) frameworks. These efforts will apply the market systems principles and experience of MADE, as appropriate, to target high at-risk populations. MADE will pilot work among vulnerable populations in the core states, but with a special emphasis on Edo state which is the epicentre of the MDS crisis. MADE will apply a sound MEL framework to ensure that clear objectives for pilot interventions are set, with sound theories of change, in order to test different approaches to address underlying causes. / Supporting ongoing livelihood programming / In parallel, there are many victims of trafficking who are returning to the region who need support to avoid falling back into an at-risk situation. MADE will offer market development intelligence and technical assistance to improve the programming of those currently working on providing alternative livelihoods to returnees. The current assessment of many of those programmes is that their traditional approaches are expensive, difficult to sustain and unlikely to have systemic effects. / Building aspirations to stay / It has been observed that agriculture may not be perceived as attractive as emigrating to Europe by potential victims of trafficking. In addition, it is also likely that simply increasing the incomes of potential victims, without changing their aspirations, may simply increase the propensity to emigrate. In response to these issues and risks, MADE’s approach will be support sectors defined by potential victims of trafficking as ‘aspirational’ – this might include hospitality, the creative industries and ICT, but will be validated by research. MADE will identify and analyse the potential for growth of such sectors, and take a traditional market development approach, of identifying barriers to investment and working with private sector to overcome them. This will lead to increased investment in those sectors, with a focus on employment supporting innovations. / By starting interventions with the firm, rather than the target population, MADE will seek to create aspirational opportunities, rather than starting with individuals at risk and providing them with training or grants. This reduces the risk of expensive and non-systemic programming, and also the risk of simply funding emigration. It is expected that a strong communications component to market alternative livelihoods may also be a useful and cost effective part of this work. This area of work is considered high risk and experimental, but the highly adaptive and learning based approach of market development is appropriate to minimise risk and harm, and generate the knowledge to support future programming of this type. / Managing Risk / Given that human trafficking is well-organised, often by criminal groups with strong political economy implications, few formal institutions have tried to address the problem, and the programme will have to operate with a low-profile. There are clear security risks to the programme, its staff, and its partners if political and social balances are upset. Some of the potential risks related to MDS are highlighted in the Risk Matrix below. / Monitoring, Evaluation and Learning. The programme will monitor and measure intervention impacts closely focusing on both direct and indirect impacts. MADE’s monitoring and results measurement strategy was substantially strengthened in year 3. Now, with this robust framework in place, intended and unintended results and achievements will be properly captured. Most importantly, the desired changes facilitated as a result of MADE interventions will be documented and broadly shared to facilitate systemic changes and achieve more sustainable direct and indirect results at scale.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The most significant change to the original business case is the emphasis on the economic aspects of MDS and human trafficking in the Niger Delta. This adaptation responds to the identified potential of the project to apply its market development approach to the Prime Minister’s Modern Day Anti-Slavery Agenda. These activities will require a new elaboration of the theory of change (essentially an annex to the existing theory of change, which remains valid), which covers the complexities of shifting attitudes to migration through an economic approach. It will also require adaptation to the MEL framework of the programme. The MDS component will be supplemented with innovative learning approaches, using mixed methods to assess systemic and cultural change, to improve DFID's ability to understand and analyse delivered results. MADE will set revised targets and knowledge management outputs for these activities, which will be elaborated in the first three months of the new contract. / The most important set of evidence for the project at large is derived from the success of the project so far, and its demonstration of further potential, set out in quarterly and annual reviews.
[2] Christiana E.E. Okojie et al Trafficking of Nigerian girls to Italy report of field survey in Edo state, Nigeria, July 2003; Catherine Enoredia Odorige, The Dark Side of Migration Remittances and Development: The Case of Edo Sex Trade in Europe, Pécs Journal of International and European Law - 2016/I; Geir Skogseth Trafficking in Women – Fact-finding trip to Nigeria (Abuja, Lagos and Benin City), 12-26 March 2006.
[3] Home Office, Country Policy and Information Note Nigeria: Trafficking of women, November 2016, p 12.
[4] The Home Office is currently supporting three pieces of related research, while the MADE project team is also undertaking studies
[5] MADE also plans to establish partnerships with those offering livelihoods to returned victims and strengthen the market relevance and linkages of the training.
[6] MADE will conduct market analysis to determine the Aspirational sectors and potential market size; this figure may be subject to revision. .
[7] A full table of all VFM indicators and their improvement in the last 12 months is set out in the 2017 Annual Review
[8] An agricultural market development project based in Northern Nigeria, also in a conflict affected area