Business Case

Summary Sheet

Title: Stronger Health Partnerships for Stronger Health Systems (SHP)
Programme Summary: / The UK will invest up to £30m over five years (2018 to 2023)[1] to support partnerships between UK and developing country health institutions – sharing expertise that helps developing countries build stronger and more resilient health systems, especially a better-skilled health workforce.
Programme Value: £30m		Country/ Region: Selected LICs and LMICs (TBC)
Programme Code:	Start Date: / October 2017 (additional scoping analysis); / 2018 (inception & implementation)	End Date: October 2023
Overall programme risk rating:	Moderate
Vault Number:
[1] Based on procurement timelines, the programme inception period will not start until late-2018 with up to a further 9 months for partnership grants to be awarded. This means that partnership projects should start in mid-2019 and run for up to 4 years.

Intervention Summary

The UK has world-class health expertise. A health partnership, often run by volunteers, ‘links’ a UK health institution (e.g. NHS Trust, academic institution or professional organisation) and a counterpart institution in a developing country (e.g. hospital, local authority, training college, or ministry of health). Partnerships enable sharing of expertise, e.g. through UK volunteers supporting development of improved training curricula or management practices, that helps developing countries build stronger and more resilient health systems, especially a better-skilled health workforce. This ultimately contributes to SDG3, ‘ensure healthy lives and promote well-being for all, at all ages’. Partnerships also benefit the UK NHS as volunteers bring back new skills, confidence, and motivation.

Partnerships are largely dependent on grant funding. The UK will invest up to £30m over five years (2018-2023) to support health partnerships. This builds on lessons and successes from earlier UK health partnership programmes, including the current DFID-funded Health Partnership Scheme (ends February 2019).

To deliver the expected outcome, ‘improved health worker and health service performance for poor and vulnerable populations in selected low and lower-middle income countries’, funds will be spent on:
1. Coherent and strategic partnerships supporting health workforce development and health systems priorities in 8-10 focus countries in Africa and Asia. (Approx. 6-8 ‘large’ grants in each country, c. £250,000-£350,000 per grant).
2. A larger number of smaller grants for innovative partnerships, e.g. new approaches to training in specific skills, in more countries (total of 80-100 grants, c. £25,000-£50,000 each).

Funds will be spent via a management agent, appointed by competitive tender. DFID will retain overall programme oversight and manage a performance-based contract. Costs covered by grants are expected to include travel, training materials, and volunteers’ subsistence and expenses. DFID will also commission and manage an evaluation to generate more evidence on the contribution of partnerships to strengthening health systems, and what makes partnerships most effective.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
The programme will support developing countries to build stronger and more resilient health systems. This contributes to UK Aid Strategy objectives 2 and 4, building resilience and tackling poverty amongst vulnerable groups.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
- The programme contributes to SDG 3 on good health and well-being. Strengthening health systems is high on the global health agenda. The programme approach specifically supports countries’ own health systems and health workforce priorities.
- Grant funding for health partnerships is time-bound and all partnerships will finish within the life-time of the programme. Award of grants will take plans for sustainability into account. More broadly the programme aims to support countries build institutional capacity that will reduce longer-term need for external support.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
DFID has worked closely with UK health stakeholders, including the Department of Health and NHS, in designing the programme. It will not access cross-HMG funds.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
Sharing specific UK health expertise through health partnerships complements and (by addressing specific skills/expertise bottlenecks) can enhance other DFID work to strengthen health systems through bilateral country and centrally-managed programmes. Strengthening country health systems also helps maximise results and sustainability of UK funding through multilateral organisations and global health funds such as WHO, Gavi (vaccines), and the Global Fund (AIDS, TB, malaria).

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Robust monitoring and evaluation is built into the programme and we will adapt to learning and changes in context. Suppliers’ contracts will have the flexibility to scale up, reduce, move resources between components/countries, or stop if needed – responding to need and context in countries, UK priorities, or programme performance.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
The ‘moderate’ programme risk fits with Human Development Department’s risk appetite.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
A detailed communication strategy will be developed in consultation with the Communications Team in London. The UKAid logo will be used by delivery partners in line with current branding guidelines.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
The programme has been peer reviewed, including by country teams. Experience of the existing Health Partnerships Scheme gives confidence that there is capability, resources and political will for delivery of a successful programme.

Does the SRO and team have the capability and resources to deliver this programme?
Yes. The programme will be managed by an A2 SRO and a B1 programme manager, and overseen at A1 level as part of a broader portfolio of programmes. The programme will be supported by the Health Services Team’s Programme Management Hub . DFID’s Procurement and Commercial Department has provided advice and will support the procurement process.

#### Abbreviations

APPG	All-Party Parliamentary Group
HW	Health Worker
DFID	Department for International Development
DH	Department of Health
EME	Early Market Engagement
EQUALS	Evaluation Quality Assurance and Learning Service
FCO	Foreign and Commonwealth Office
HDD	Human Development Department
HEE	Health Education England
HMG	Her Majesty's Government
HPI	Health Partners International
HPS	Health Partnership Scheme
HR	Human Resources
HSS	Health System Strengthening
HST	Health Services Team
IDC	International Development Committee
IPC	Infection prevention and control
ITT	Invitation to Tender
LICs	Low Income Countries
LMICs	Lower-Middle Income Countries
LSHTM	London School of Hygiene and Tropical Medicine
MA	Management Agent
M&E	Monitoring and Evaluation
MNH	Maternal and Newborn Health
NGOs	Non-Governmental Organisation
ODA	Overseas Development Assistance
OJEU	Official Journal of the European Union
PCD	Procurement and Commercial Department
PHE	Public Health England
PQQ	Pre-Qualification Questionnaire
NHS	National Health Service
RCM	Royal College of Midwives
RCOG	Royal College of Obstetricians and Gynaecologists
SC	Steering Committee
SDG	Sustainable Development Goal
SOPs	Standard Operating Procedures
SRO	Senior Responsible Owner
TA	Technical Assistance
TB	Tuberculosis
ToC	Theory of Change
ToR	Terms of Reference
UHC	Universal Health Coverage
VfM	Value for Money
WASH	Water, Sanitation and Hygiene
WHO	World Health Organisation
VAT	Value-Added Tax

Strategic Case

Health partnerships aim to improve health systems and services in developing countries, often focusing on the health workforce and working practices. A partnership is typically an arrangement linking a UK health institution (e.g. NHS Trust, academic institution, Royal College or professional organisation) with a counterpart institution in a low or lower-middle income country, through which skills and expertise are shared.

This strategic case considers why DFID should fund health partnerships – in terms of the global context, efforts to strengthen health systems, evidence of benefits of health partnerships to date, and key features for future support.

The Global Context – health in the Sustainable Development Goals (SDGs)

SDG3 is a global commitment to ‘ensure healthy lives and promote well-being for all, at all ages’. This includes a target of universal health coverage (UHC), i.e. all people being able to access good quality healthcare without being financially impoverished.

UHC and greater health security contribute to broader development objectives. Better health is valuable both in its own right and as a contributor to productivity, inclusive growth and economic development, and poverty reduction. The UK government is committed to driving progress towards the SDGs, and DFID’s Economic Development Strategy stresses the importance of building a healthy, educated and productive workforce for the future.

The need for health systems strengthening and a stronger health workforce

Stronger health systems are those where good quality health facilities are in place, with enough well-trained and motivated staff, with working equipment and reliable stocks of medicines and other health commodities. Stronger health systems are needed to accelerate and sustain progress towards SDG 3, especially the target of universal health coverage (UHC). They underpin and are vital in addressing other health priorities such as tackling specific diseases.

The UK invests in strengthening health systems in almost all the countries DFID works through bilateral, central and multilateral investments. Figure 1 below provides an overview of the different building blocks of a country health system and how UK support is used to strengthen these.

Ensuring health workers are trained, deployed, supported and retained is a common challenge faced by many low and middle income countries. To address the health worker challenge, WHO’s “Global Strategy on Human Resources for Health – Workforce 2030” was adopted by the World Health Assembly in May 2016 and calls for countries to take steps to strengthen their health workforces.

Figure 1 – Overview of health systems building blocks and UK support
The contribution of UK health partnerships to strengthening health systems

1. There is a long history of partnerships between UK health institutions and those in developing countries. In 2007 an influential report by Lord Crisp[2] outlined the importance and potential of UK ‘links’ or health partnerships, noting that these offer a unique approach to addressing some health systems constraints, in particular, the development of the health workforce. Following Lord Crisp’s report, successive UK governments have provided funding for health partnerships. From 2009 a DFID and Department of Health ‘International Health Links Funding Scheme’ supported partnerships focused on increasing the skills and capacity of health workers in developing countries. This was succeeded by the DFID-funded Health Partnership Scheme (HPS).
  [2] ‘Global Health Partnerships: the UK contribution to health in developing countries’. Lord Crisp (2007).
2. DFID has provided over £30m to the Health Partnership Scheme (HPS, 2011-17, and recently extended to February 2019). This programme has supported UK health institutions to share expertise and training with over 130 counterpart health institutions in more than thirty countries in Sub-Saharan Africa and Asia, resulting in additional training for nearly 84,000 health workers (mostly women).

Partnerships are varied (see examples in box below). They may involve, for example, the transfer of knowledge and skills by professional volunteers through co-working or mentoring, revision of medical curricula and development of new protocols, equipment and management support that are free of cost to the recipient country. They also often involve the development of long-term relationships that are highly valued by developing country partners.

Example health partnerships / 1) An initiative by Nottingham Trent University and Makerere University School of Public Health partnership focused on strengthening the Community Health Worker (CHW) programme for health improvement in Wakiso District, Uganda. The project provided 325 training course places for CHWs and CHW supervisors, which resulted in an increased number of home visits by CHWs to provide health care, referrals and education. The partnership achieved 40,213 home visits reaching over 127,000 community members and over 19,000 children treated for malaria, diarrhoea and pneumonia by CHWs. Of the 325 training course places, 300 CHWs were assessed at least 3 months after training, and 298 demonstrated improved performance. CHW competence and motivation were assessed through quantitative and qualitative methods, including questionnaires, focus groups and interviews. / 2) Guys and St Thomas NHS Foundation Trust and Mulungushi University Zambia received a small Strategic Start-up grant to develop a partnership to improve quality of training and delivery of health services targeting adolescents, a key beneficiary group, in the Central Region of Zambia. This built on a relationship and partnership since 2009 between Guys and St Thomas and two hospitals in the Zambia. The grant resulted in a formal MoU to guide this collaboration, including intended deliverables and how the partnership is aligned with Zambia’s Ministry of Health and Higher Education priorities and plans. The partners are working together to develop health workers’ knowledge of adolescent health, improve access and suitability of adolescent health services, and secure stronger policies for improving adolescent health in Zambia.

There is a range of evidence to show that partnerships and volunteering have contributed to DFID’s overall health goals and health systems strengthening work – especially through high quality training and education. An external evaluation of HPS, completed in 2016, found that partnerships can be very effective at strengthening the capacity of health workers and institutions in developing countries and that the scheme contributed to building human resources capacity at country level[3]. Where suitable measurement is possible and data available, many partnerships (37 in the HPS evaluation) demonstrated improved health outcomes for patients. Similarly, another DFID programme (“Making it Happen”, 2009-2016) supported UK volunteers from the Royal Colleges of Obstetrics and Gynaecology and of Midwives to improve Maternal and Newborn Health (MNH) training, supervision and quality of care in 11 countries, resulting in improved healthcare around child birth and helping to reduce associated maternal and newborn deaths[4].
[3] Independent evaluation of the DFID Funded Health Partnership Scheme. (Final report, October 2016)
[4] Making it Happen, Project Completion Review, DFID, August 2016

In 2015 the All Party Parliamentary Group for Global Health report, “The UK’s Contribution to Health Globally”, highlighted further potential to strengthen partnerships between UK and developing country health institutions to help address some of their health sector challenges.

There is also rich history and increasing international evidence of the benefits of health partnerships. For example, WHO has an established an ‘African Partnerships for Patient Safety’ (APPS) programme based on international hospital-to-hospital partnerships, and the ESTHER alliance promotes partnerships between European and developing country health institutions to tackle HIV/AIDS and other global health priorities. A recent WHO report showed how twinning partnerships between health organizations, hospitals, primary care facilities or health authorities can support the re-establishment of safe, effective health service delivery in the aftermath of a shock to health services, such as the Ebola outbreak[5]. A ‘Global Catalyst Group’ for institutional health partnerships promotes learning across different partnership schemes[6].
[5] ‘Twinning Partnerships for Improvement: Building capacity to reactivate safe essential health services and sustain health service resilience’. WHO, 2016.
[6] http://www.who.int/patientsafety/implementation/apps/global-catalyst-group/en/

Why should DFID intervene?

The UK is a leading global actor in health. UK health institutions have a lot to offer and there is significant demand for UK expertise from developing countries.[7] As described above, there is a long and successful history of UK partnerships and DFID support – and support for partnerships complements other DFID work to strengthen health systems. There is therefore a strong rationale for DFID support that creates the enabling environment, and provides funding, for sharing of UK expertise for the benefit of developing country health systems.
[7] The UK’s contribution to health globally. A report by the All-Party Parliamentary Group on Global Health, June 2015.

Heath partnerships are also beneficial to the UK. In addition to the wider contribution of better health to prosperity and security, the HPS evaluation found that the UK health system benefits from the increased skills, learning on how to improve current practice from other contexts, and motivation that UK health workers acquire when working overseas.

A stronger UK health partnerships approach: Building on successes and lessons learnt

The evaluation of the Health Partnership Scheme demonstrates the effectiveness of the partnership and volunteering approach in strengthening health worker capacity, and recommends its continuation, building on its successes and strengths[8]. It shows there are many partnerships which have led to improvements in service delivery and quality of care and that most projects have been aligned with government strategies and been supportive of developing countries’ priorities.
[8] Health Partnership Scheme – Summative Evaluation, HPI, October 2016

The evaluation also identified opportunities to be more ambitious and more strategic, based around larger and more coordinated partnership approaches in some countries. These could achieve larger and more sustainable impact by ensuring stronger coordination with other partnership projects and long-term and larger aid programmes. It also identified the need for rigorous monitoring and evaluation from the outset, to ensure continuous learning and feedback to refine the proposed revised approach and maximise benefits (and sustainability) of the health partnership model in strengthening health systems.

Considering the lessons from the evaluation, reports on the UK contribution to date and wider efforts to strengthen health systems[9] [10] [11], consultations with senior health leaders, and informal discussions with partners (including with the NHS International Group[12] and Academy of Medical Royal Colleges), any future DFID investment in health partnerships should have the following features:
[9] The UK’s contribution to health globally. A report by the All-Party Parliamentary Group on Global Health, June 2015
[10] Strengthening Health Systems in Developing Countries: Fifth Report of Session 2014-15 - International Development Committee
[11] Ruchi Baxi, October 2015: “Health Systems Strengthening in low and middle-income countries: UK partnerships at the systems’ level”.
[12] This group, co-chaired by DFID and Health Education England, comprises the main NHS (including devolved administrations) stakeholders with an interest in supporting global health work.

- Greater focus on a smaller number of countries where there is most likely to be maximum gain (e.g. where UK already has a significant footprint);
- Greater “country ownership”, i.e. more engagement from partner governments and stakeholders and clearer alignment with national plans;
- More explicit linkages to progress on Sustainable Development Goal 3, particularly the target on universal health coverage, and the need to “leave no one behind”;
- A holistic approach to health systems strengthening, involving different parts of the health sector and the involvement of different cadres of health workers (e.g. managers, other institutions such as NGOs and the private sector) and much better coordination between partners;
- Ongoing commitment to high quality research and learning to inform health partnership policy and practice and, where appropriate, including research capacity as one of the parts of the health system to be strengthened;
- Focus on areas of UK comparative advantage such as education, accreditation, curriculum development, patient safety, hospital management and leadership, clinical guidelines and research [13], depending on partner country needs and demands;
  [13] McKinsey analysis to inform the health Prosperity Fund bid indicates the following UK comparative advantages: education and training, life sciences, patient safety, quality of care and clinical research. The 2015 APPG Global Health report, ‘The UK’s Contribution to Health Globally’, also highlights these as UK strengths.
- Volunteering opportunities need to be expanded and supported by the UK sending organisation, and recognised as a skills building experience when volunteers return from overseas;
- Support maintained for some small health partnerships, as these can make significant contributions to health services and have potential for innovation and learning[14].
  [14] For example, some small grants have successfully piloted innovative training approaches, generating evidence as a basis for then implementing similar training at greater scale.

The DFID team developing potential future support for partnerships concluded that a successor programme to HPS should therefore include a combination of i) large, long-term partnerships (or sets of coordinated partnerships) focused on particular countries, and ii) smaller partnerships, focused on innovation and learning, in a wider selection of countries. The larger partnerships should focus on expanding health partnership initiatives to whole health facilities and communities and be well-embedded in wider health systems’ work and national dialogue. The smaller partnerships should test and support new initiatives with potential for innovation, learning and scale up. These smaller partnership grants would also allow flexibility to focus partnership activity on specific emergent priority areas (for countries or for DFID, e.g. addressing specific priority diseases or health needs, or tackling antimicrobial resistance).

Building on successes to date, this approach will enhance the effectiveness of partnerships work by ensuring links and synergies with other health systems strengthening initiatives and a more focused country approach. At impact level the programme will contribute towards SDG 3, to ensure healthy lives and promote well-being for all at all ages, and the target of universal health coverage. The expected outcomes are improved health worker and health service performance for poor and vulnerable populations in selected countries.

It will do so by delivering the following outputs (and the appraisal case considers options for delivering these results):

Accelerated progress on health systems priorities in (8-10) focus countries (delivered by larger strategic health partnership approaches that are aligned with national health plans) – including, but not limited to, improved health worker training, skills mix and motivation, retention and human resource planning.

UK expertise shared and new initiatives tested to address specific health systems constraints (delivered by smaller partnerships with potential for innovation, learning, and scale-up).

Ensuring the right conditions for sufficient NHS volunteers with the right skills to meet developing countries’ priority needs.

Increased evidence base on the effectiveness of health partnerships as a contribution to strengthening health systems.

Current thinking is that larger grants to support partnerships would enable expanded partnering with multiple health facilities (hospitals, community centres, medical schools) plus those responsible for health planning and decision-making at sub-national and national levels. This would bring together collaborations of existing and new partnerships in a more structured and coordinated way, responding to partner countries’ overall health needs and aligned with other health systems’ work and national priorities and plans. It could also support scaling up health system improvements from individual partnerships (in one health institution or district) to have greater impact at national level. Based on experience from the current HPS, these larger grants would indicatively be in the region of £250,000-350,000. Support would be focused on 8-10 priority countries, with an expected 6-8 grants per country.

Alongside this new support modality, there remains need for smaller grants to support partnerships with particular strategic impact, for example testing innovative approaches (e.g. new surgical procedures or patient protocols) and supporting learning and scale up. Size of these grants would vary based on need (e.g. number of volunteers involved, duration of partnership); an indicative estimate is £30,000–£50,000 per grant. Partners could vary from individual hospital or local community health care providers to Ministries of Health; partnerships would typically be focused on a particular health need (e.g. maternal and child health) or aspect of health worker training. Support for these partnerships would not be restricted to particular focus countries (although, depending on demand, may be prioritised to these).

Some further analytical and scoping work will be undertaken during the inception phase of the new programme to provide further information that informs the detailed design of implementation approaches:

A detailed analysis of opportunities to ensure the right conditions are in place to support sufficient NHS volunteers with the right skills to meet developing countries’ priority needs. This will consider opportunities and challenges around volunteering. While the potential availability and appetite to share UK expertise is well-established, a strong partnerships offer is dependent on consistent and better-coordinated availability of UK volunteers with appropriate skills to help meet developing countries’ priority health needs. Volunteers sometimes face barriers such as difficulty getting permission to go overseas from their employer or time spent abroad not counting towards training. This analysis will inform an action plan for strengthening the UK volunteer offer in a sustainable way (including ensuring that volunteering does not, and is not perceived to, divert NHS resources from UK needs). This plan might include, for example, ensuring evidence for mutual benefits of partnerships is communicated clearly to senior managers and other key stakeholders, and campaigns to recruit volunteers with particular skills/expertise.

Building on the evaluation findings, further analysis to summarise factors that make health partnerships most successful. This will consolidate evidence for best practices to achieve policy uptake, sustainability, and results (e.g.improved health worker skills). This will entail analysis by country and health theme of the portfolio of projects supported under the current Health Partnership Scheme.

Focus countries will be selected in consultation with country offices and the NHS International Group as soon as the business case is approved so that bidders can develop proposals accordingly. Criteria for selecting priority countries may include: DFID focus country with a health sector programme; existence of enabling human resources for health policies/plans; specific needs/demand can be matched by UK supply, government ownership and likely influence on wider health system; existence of health partnerships with a strong record and opportunities for synergies. Potential focus countries include Uganda, Zambia, Kenya, Malawi, Ethiopia, Ghana, Tanzania, Rwanda, Sierra Leone, Mozambique and Myanmar.

Links to UK’s strategic policy objectives for poverty reduction

The proposed health programme will support the implementation of the 2015 UK Aid Strategy, contributing to strategic objectives 2 (Strengthening resilience and response to crises) and 4 (Tackling extreme poverty and helping the world’s most vulnerable).

Within Human Development Department’s operational plan objectives, the programme provides an opportunity to ensure that UK expertise is strategically aligned to countries’ own plans and complements DFID bilateral and centrally managed programmes – including, within Human Development Department’s portfolio, a new programme to make health systems stronger in developing countries. It is also in line with DFID’s forthcoming position paper on strengthening health systems. The programme would be a strong part of the UK’s overall UK offer on global health, as a key instrument for sharing of UK health sector expertise.

Gender Equality. In accordance with the 2014 International Development Act (Gender Equality) Act, the programme will ensure any institutional partnerships supported and established under its remit consider impact on gender equality, including disaggregation of data by gender and the inclusion of gender-based targets in results measurement.

Gender is a key factor to consider in health workforce interventions. Women make up 67% of health and social sector employment but gender biases persist within the health workforce. For example, health systems rely heavily on unpaid and informal work that disproportionately falls on women and girls. Work in health care is often poorly paid and male health workers typically earn more than their female counterparts, especially in higher-income occupational categories. Women are also underrepresented in positions of leadership and decision-making relative to their share of employment in health[15].
[15] WHO (2008) ‘Gender and health workforce statistics’.

The APPG Global Health’s 2016 report on the role of nurses[16] also highlights the importance of strengthening human resources for health in terms of economic gains and increased gender empowerment, given that women are disproportionately represented in the health workforce. The HPS evaluation recommended strengthening gender considerations in the establishment of partnerships and the programme will actively seek to do this (e.g. ensuring management and leadership training for women, promoting human resource policies that take into account women’s needs and roles as family carers).
[16] ‘Triple Impact - How investing in nursing will improve health, improve gender equality and support economic growth’, APPG Global Health (2016). http://www.appg-globalhealth.org.uk/download/i/mark_dl/u/4009611296/4630077385/DIGITAL%20APPG%20Triple%20Impact.pdf

1. Disability and Inclusion. DFID will ensure the programme promotes equitable access to health services regardless of ethnicity, religion, gender, disability and social status – with particular focus on ensuring that vulnerable populations are able to benefit from DFID-funded activities. According to WHO, people with disabilities experience poorer health than people without disabilities, and face widespread barriers in accessing health services particularly around affordability of services and discrimination by service providers. DFID will ensure that programme funding (and work with downstream delivery partners) supports inclusiveness and provides additional benefits to those working on people/programmes which benefit disabled people (for example by allocating some funding for partnerships to focus on disability).
2. The programme will also comply with the Public Sector Equality Duty by ensuring that: 1) harassment and discrimination are not tolerated and 2) promoting equal opportunity between people who share different characteristics.
3. Climate and environment. This programme will not count against climate finance. All appraisal options proposed have similar climate and environmental considerations. As the intervention will be focused mainly on technical assistance, the impact of the delivery of the intervention is low. Carbon emissions will depend mainly on frequency of meetings and travel to countries that are being supported.

Climate and environment opportunities within the programme include promotion of adequate water and sanitation in health care facilities[17] , best practice from the NHS current drive towards sustainability, and improved waste management in health facilities.
[17] Note: the programme would support this by sharing technical knowledge (e.g. how best to integrate water and sanitation in health facility and sector planning), not by funding capital works.

Terrorism and financing. The overall risk of programme funds being diverted for terrorist related activities is low. Most of the financing goes to supporting volunteers’ travel and costs which will be managed by UK health partners (grantees) with oversight from a management agent. DFID will ensure that appropriate steps are followed and checks are undertaken in line with the Counter-terrorism guidance to mitigate the risks of aid funding terrorist organisations. In addition, DFID will make decisions and judgments on when it is appropriate to suspend or withdraw funding for any given project.

Appraisal Case

The strategic case sets out key features of future DFID support for health partnerships (paragraph 18), and indicative programme outputs (para. 21). This appraisal describes feasible delivery options for these, and summarises a multi-criteria decision analysis that was used to appraise them.

Delivery options identified are based on DFID’s past programme management experience (e.g. current management of the Health Partnership Scheme by a third party, bilateral management of different health, including health partnership, initiatives), discussions with regional and country teams about whether partnerships could be supported through DFID bilateral programmes, and wider discussions with UK stakeholders in international health (such as Health Education England, NHSTrusts, Royal Colleges and Public Health England ). The option of discontinuing support to partnerships and “doing nothing” was also considered.

Options

Four programme options were identified, and are described in the following paragraphs:
1. Do nothing: no further DFID support for health partnerships once the current HPS ends in February 2019.
2. Manage health partnerships through DFID bilateral (country) programmes.
3. Manage health partnerships through a new central UK government management platform (to be set up by DFID with other government departments).
4. Manage health partnerships through a management agent contracted by DFID.

‘Do nothing’. This option would mean a discontinuation of DFID funding to support health partnerships once (the extension to) the current HPS comes to an end in early 2019.

In the absence of DFID funding for partnerships, it is not expected that other UK government funding would fill the gap (e.g. the Department of Health’s ODA funding is already allocated to other priority areas). However, given the long history of health partnership activity, ‘doing nothing’ would not mean that all health partnership activity in the UK would stop. Voluntary activity would likely continue along with other sources of funding, albeit at a lower level than in recent years. Opportunities would likely be missed to harness UK (especially NHS) expertise to strengthen institutions in developing countries, improve progress towards UHC, tackle global health challenges, and make a valuable contribution towards ‘Global Britain’ – and the UK health sector would not fully realise the benefits of partnerships and volunteering.

Manage health partnerships through bilateral programmes. This option would involve DFID country offices directly supporting a mix of large and small grants for new or existing partnerships, for specific projects that align with national plans and DFID country priorities. Based on specific country needs, projects would entail a mixture of interventions and address multiple health system constraints, largely through UK technical assistance/volunteers working on leadership and governance, health workforce performance and retention, information and research and service delivery.

Manage health partnerships through a UK central government centre/platform. Under this option DFID would work across government to establish a new government centre with cross-cutting expertise to coordinate health partnerships work. The centre would manage information, support and funding for volunteering opportunities and partnerships. This option is based on Wales’ approach to managing international health work: a ‘Wales International Health Coordinating Centre’ coordinates a diverse set of international health links and partnerships across Wales. The Welsh model includes a guiding framework and a “Charter for International Health Partnerships” that is signed by all NHS Wales Boards and Trusts. The Welsh centre/platform is structurally, managerially and financially embedded in the International Development Division of Public Health Wales and comprised primarily of NHS staff. Appropriate governance and management arrangements for a new UK partnerships platform would need to be agreed with the Department of Health and relevant agencies (NHS, Public Health England, etc), including those for the devolved administrations.

Manage health partnerships led by DFID centrally through a contracted management agent. This option, similarly to the existing HPS, would entail a formal procurement to appoint a management agent (private/non-governmental sector). DFID would retain overall oversight of the programme (and apply usual programme management processes to hold the management agent to account for delivery of agreed programme activities and outputs). The contractor would be responsible for coordination of health partnership activities and programme management of grants, including fiduciary control, capacity building support, monitoring and evaluation.

Multi-Criteria Decision Analysis: Appraisal Criteria and Scoring

In order to select the preferred option, a Multi-Criteria Decision Analysis (MCDA) was undertaken. MCDA is typically adopted when it is not possible to quantify the benefits of particular interventions in a way that is comparable across the alternative options. MCDA involves identifying chosen objectives and appraisal criteria, and a scoring scale and weighting of criteria.

The MCDA follows guidance developed by the Department for Communities and Local Government, which is recognised as the accepted cross-HMG approach to undertaking MCDA. Although MCDA has some limitations (e.g. scoring is often still subjective), it is a more effective analytical tool for appraisals than informal judgement. It is an open and explicit process, that also generates an audit trail for decision-making.

1. The options and criteria for the appraisal were developed through consultations with DFID policy, health and commercial advisers. Agreed criteria summarise capability and capacity requirements identified as critical for the delivery of the programme – and implicitly also include feasibility of delivery based on these. The criteria, and their relative weights in the appraisal (see para. 48 below) are:
  1. Ability to manage and coordinate work with a wide range of UK (across HMG, inc. Health Education England and NHS) and developing country institutions;
  2. Ability to foster a stronger enabling environment for UK health volunteers’ supply of technical assistance;
  3. Understanding of country operating environments - ability to provide support on the ground and ensure alignment with country priorities;
  4. Programme management capacity – grants, fiduciary risk management, and technical (health sector) expertise;
  5. Monitoring and evaluation capacity, and ability to learn and disseminate lessons from the programme;
  6. Value for money and costs.

Scoring was conducted by a panel of four DFID staff, who were either already involved with or thoroughly briefed about the programme, key issues, and rationale for the selection criteria.

Appraisal scoring. Each of the criteria was given a subjective weighting (1-4, with higher scores meaning more important) and scored (1-5, with higher scores meaning criteria better met). Table 1 shows the scores for each option, and the following paragraphs summarise key points for each of the criteria. The ‘do nothing’ option was appraised and would not meet these criteria in any meaningful way, so scoring is not included for it.

Table 1: Outcome scores from the MCDA process

Appraisal options	Option 1 – Do nothing	Option 2 – bilateral programmes	Option 3 – central UK government platform	Option 4 – DFID-contracted management agent
Total Score / (maximum possible: 105)	N/A	40	69	92

(a) Ability to manage and coordinate work with a wide range of UK (across HMG, inc. HEE and NHS) and LIC institutions. [Weight: 4/4]. The UK government platform scored highest (with caveats below); the management agent option also scored highly.

A well-designed UK government platform could help underpin a coherent and coordinated UK health offer across a range of areas of expertise, responding to the needs and interests of different countries at different levels of development and transition. However, the panel noted that establishing such a platform would likely be a lengthy process, requiring buy-in from multiple stakeholders over an extended time period – and it would be vital to ensure that any additional coordination work would not (and would not be perceived to) divert resources from core NHS delivery in the UK.

The management agent option also scored highly, based on experience of managing the current HPS and other DFID central programmes. Building on learning from the current HPS, a contracted management agent could facilitate coordination of UK health institutions – and alongside this, development of a potential future central-government platform could be explored further.

The ‘DFID country office’ and ‘do nothing' options would risk fragmentation of support to health partnerships without an overall strategy or coordination of UK efforts. The absence of a central fund would likely mean that support for partnerships would be on an ad hoc basis with a risk of doing harm and not encouraging best practice.

(b) Ability to foster a stronger enabling environment for UK health volunteers’ supply of technical assistance. [Weight: 3/4]. This would be best done from the UK – it is expected to entail the development, implementation and oversight of an action plan for coordination of UK health institutions to strengthen the volunteer supply side. It would also require in–depth knowledge of the NHS, including opportunities and risks for volunteering. The UK government platform scored highly for its potential role in helping create the conditions for volunteering, though based on current capacity would be unlikely to provide this in the near-term. The management agent also scored highly and was assessed as the most feasible option to do this, in coordination with the UK government.

DFID country offices would not be well-placed to do this – and the “do nothing” option would mean that partnership efforts would continue to be led by individual trusts and NHS institutions on an ad hoc basis without consideration of the overall enabling environment for volunteering of expertise.

(c) Understanding of country operating environments - ability to provide support on the ground and ensure alignment with country priorities. [Weight: 4/4]. The management agent option scored highest, and the direct bilateral option also scored well. A management agent (or consortium) with a track record and relevant high level contacts in selected countries and/or region would have the capacity and capability to provide support on the ground. DFID country offices could play a supporting facilitatory role.

Given DFID’s access to high-level government officials in country and knowledge of the context, the bilateral approach could enable even greater government ownership and alignment with national priorities. However, leading partnerships support at country level would likely require significant DFID staff time. Consultation with DFID country offices found that, whilst most are keen to engage with the successor to the HPS (and DFID Burma has included grants to UK health institutions to support medical training and curriculum accreditation as part of a larger health programme), capacity among most Asia and Africa country offices to manage large health partnerships directly is very limited at present given other programmatic priorities. In addition, this approach would not support coordination between projects and partnerships across countries or learning across UK stakeholders.

Providing support on the ground and ensuring a good understanding of local political economy in different contexts would be difficult for a broader UK government platform. The “do nothing” option may allow for strong individual partnerships to continue, but would be unlikely to provide mechanisms to strengthen and share understanding of country operating environments or ensure wider alignment of multpiple partnerships with countries’ own priorities.

(d) Programme management capacity – grants, fiduciary risk management, and technical (health sector) expertise. [Weight: 4/4]. The management agent option scored highest, and all the other options got medium scores. Competitive procurement allows for a wide range of delivery options, including public, private, or not-for-profit bodies (or consortia/alliances) with a demonstrated track record in programme management, financial management and technical expertise. This approach also offers greater capability to resource staff flexibly as demand/need fluctuates. A new government platform would likely take time to establish programme management expertise, and while DFID country teams have the relevant expertise it would require disproportionate efforts for them to programme manage individual partnerships grants. The “do nothing” approach would not strengthen overall programme management of partnerships in any strategic and coordinated way. (The panel also noted that larger and smaller, and not-for-profit vs private sector providers are likely to have different strengths and weaknesses, for example across scope, including number of countries, and specific areas of niche expertise. A combination through a consortium may offer the strongest approach­­).

(e) Monitoring and evaluation capacity, and ability to learn and disseminate lessons from the programme. [Weight: 3/4]. The management agent was considered the best option to do this. Provision of M&E support would probably need to be outsourced by a UK government platform or country offices, while a management agent could more easily include M&E capacity in the team, e.g. staff who can provide direct support to grantees. The “do nothing” option would be very unlikely to provide any coordinated M&E, or associated learning mechanisms, across partnerships.

(f) Value for money and costs. [Weight: 3/4]. The management agent option scored highest: although the procurement process will take time, one centralised procurement and one negotiated management fee will cover support for multiple countries. Economies of scale are anticipated in a more coordinated and coherent offer, with further opportunities to drive VFM through lesson-learning across countries.

The HMG platform option might also realise economies of scale in the longer term – but a lengthy process (and substantial initial transaction costs) would be anticipated in setting it up. Country offices would need to invest their own resources and potentially run multiple procurement processes with separate administration costs. The “do nothing” option would entail no additional costs to DFID but would be unlikely to generate any additional efficiency and effectiveness benefits for work on health partnerships.

Preferred option

The outcome of the MCDA is that option 4, ‘Manage health partnerships led by DFID centrally through a contracted management agent’, is the preferred option.

Scoring was agreed on the basis of current capacity and capability. The panel noted potential longer-term benefits of establishing a government platform if requisite capacity could be developed, and agreed that further exploration of feasibility of this approach should be considered as part of programme implementation.

Strength of the evidence

Evidence for appraising the delivery options is described above and based largely on DFID staff experience of delivering relevant programmes. There is strong evidence for the preferred option, based on experience from the current HPS and widespread other use of third parties to manage grants and programme delivery. Evidence for appraising the bilateral country delivery option is also reasonably strong based on extensive DFID experience of bilateral programmes plus a small number of cases of country teams supporting individual institutional partnerships. There is less direct evidence for consideration of the new UK coordinating centre option – which would be a new mechanism – although relevant learning from the Wales experience has been drawn on.

1. Overall evidence for the health partnerships approach is described in the Strategic Case. There are two key questions:
  1. Can health partnerships improve health worker and health service performance?
  2. Can health partnerships strengthen health systems and health institutions?

Regarding the first question: the external evaluation of the existing health partnerships scheme documents positive human resource results, e.g. improved skills and confidence of staff, and improved service delivery (e.g. in Uganda, Burma and Sierra Leone)[18] . The HPS evaluation and experience from other programmes also provides some evidence that systems interventions such as training health workers to improve service quality, including equipment maintenance, and strengthening community systems can reduce both illness and premature death[19].
[18] In Uganda, several projects showed a significant contribution to strengthening the capacity of the workforce; in Burma, teaching and training capacity has been built among 75 senior paediatricians, nurses and university professors and the whole of the urology surgery cadre is been impacted through the establishment of a new curriculum; in Sierra Leone all projects reviewed in-depth shown significant contributions to improved quality of care.
[19] Making it Happen programme final report, 2016

This evidence shows that health partnerships contribute to stronger health systems through improving health workers’ skills. While documented evidence of overall impact on strengthening health systems (e.g. longer-term institutional change) is more limited, there are valuable lessons pointing to what factors are conducive to greater impact. There have been examples of partnerships that perform less well, characterised by supply-driven, short-term interventions, or where ‘best practice’ is transferred in an unsustainable way. Conversely, stronger interventions are typically implemented as part of a wider reform strategy, with a “whole systems” approach, championed by effective leadership and often targeted on a specific issue. Exploring this further and strengthening the evidence base on what makes health partnerships most effective is an important evaluation question for the programme. (Also see the hypothesis and assumptions in the theory of change below.)

Theory of Change for the Preferred Option

The Theory of Change for future support to health partnerships is presented in Figure 2 below. This is based on a theory of change developed, in consultation with UK health sector experts and international counterparts, as part of the external evaluation of the existing Health Partnerships Scheme. It includes some new areas that are needed to strengthen partnerships and achieve the intended outcome and impact, as set out in the Strategic Case.

Three interrelated ‘output to outcome’ change pathways are central to this theory of change:

  1. The Partnership change pathway. This describes how well-targeted, more strategic and coordinated partnerships with synergies with wider health systems strengthening activity can potentially improve health worker and health service performance in a more systematic way. The expectation is that funding and associated technical support for more mature partnerships, with greater experience of joint collaboration in the country and with linkages with national and institutional priorities, can strategically address key health systems requirements. In addition, funding and support to smaller, early stage partnerships can add value in terms of innovation and proof of concepts to be taken to scale.

  1. The Volunteer and UK Health system change pathway. This describes how a stronger approach to UK volunteering will enable the development of more strategic partnerships by better matching supply and demand (supplying the right skills and expertise to different partnerships based on national and institutional priorities), and contribute to improved health worker performance in developing countries. The pathway also describes the benefits for UK health volunteers and the UK health system through their learning, acquisision of new skills and leadership development opportunities. It is expected that positive experience of UK health workers will in turn encourage more volunteering and a better supply of volunteers, and might also contribute positively to recruitment and retention of health workers in the UK. The volunteer change pathway interacts with the partnership pathway through health partnership projects, recruitment and placement of volunteers.

  1. Host country health system change pathway. This shows how health partnerships projects and volunteers enhance the knowledge, skills, attitudes and behaviour of host country health workers and this should result in a strengthened health workforce, delivering higher quality health services. Projects that manage to influence policies (e.g.accreditation of improved curricula and guidelines) and provide wider support to system issues (e.g. infection prevention and control, leadership and HR management approaches) are more likely to lead to sustainable changes in the partnering institution. An improvement of health workforce capability and status should lead to a strengthened health workforce if the overall management and funding of human resources is improved. This is more likely to happen if there are specific government strategies to address wider barriers (education, recruitment, deployment, retention) – identifying these strategies, and/or opportunities to support development and implementation of them, will be an important part of the more strategic partnerships approach. The interaction between country actions/ownership and the larger, more strategic partnerships should lead to changes in the host country health system.

Overall assumptions underpinning the ToC include:
Health workers and institutional partners not only have improved clinical capacity and skills but can also address a range of health system constraints in order to improve service delivery (need to have a wider enabling environment); / Health workers use new skills to improve the quality of care and inclusiveness of services they deliver to men, women and children;
Activities are delivered in cost effective ways to maximise the outcomes for the investment; / Monitoring and evaluation are used at project and programme level to inform learning and improve effectiveness.

There are also individual pathway assumptions, including:
- Partnerships pathway: More mature and better functioning partnerships have a better understanding of health systems needs in the host country and deliver better and more sustainable projects;
- Volunteer pathway: Health workers can access information about volunteering opportunities; volunteers share their learning with their own institution and influence others and so service delivery improves;
- Host partner health systems pathway: There are specific government strategies to address wider barriers related to education, recruitment, deployment, and retention (such as ensuring health workers stay in remote areas), and/or the programme engages to shape these.

+
+
+
+
(3) The right conditions for sufficient NHS volunteers with the right skills to meet developing countries’ priority needs.

(2) UK expertise shared and new initiatives tested to address specific health systems constraints (delivered by smaller partnerships with potential for innovation, learning, and scale-up).

(4) Increased evidence base on the effectiveness of health partnerships as a contribution to strengthen health systems
(1) Accelerated progress on health systems priorities in (8-10) focus countries (delivered by larger strategic health partnership approaches that are aligned with national health plans).
Evaluation & sharing of lessons
Smaller grants
Larger grants
Partnerships pathway
- More mature and established partnerships have a better understanding of countries’ health systems needs and deliver better and more sustainable projects
- Linkages with other projects, institutional and national priorities are made
- Small & innovative partnerships can evolve into mature ones
Host partner health systems pathway:
- There are specific government strategies to address wider barriers related to education, recruitment, deployment, and retention (such as ensuring health workers stay in remote areas).
- Partnerships effects on HRH are potentially sustainable & scalable

Volunteer and UK health system pathway:
- UK volunteers get support & information about volunteering opportunities
- UK supply of expertise & skills matches countries’ demands
- Volunteers gain skills, confidence & expertise and this benefits the NHS

Figure 2: Theory of Change
Inputs to Outputs
- Institution led projects are developed and implemented
- Management agent and other UK organisations support and advocate for a UK enabling environment for volunteering
- Volunteers provide training and skills, and system inputs, mentoring
- Scoping studies better match UK volunteer supply with demand (and inform programme design)
- Robust monitoring and evaluation system embedded

Scoping & analytical work

Adviser and Programme Manager time
PROGRAMME INPUTS & ACTIVITIES

Outputs to Outcome
There are three main, interrelated change pathways;

 OUTPUTS
OUTCOME
Improved health worker and health service performance for poor and vulnerable populations in programme areas
IMPACT
SDG 3: Ensure healthier lives and promote well-being for all at all ages with a focus on Universal Health Coverage

Outcome to Impact
Health workers and institutional partners not only have improved clinical capacity
and skills but can also address a range of health system constraints in order to improve service delivery (need to have a wider enabling environment)
- Health workers in partner countries use new skills to improve the quality of care and inclusiveness of services they deliver
- Service users and communities are engaged
- Monitoring and evaluation are used at project and programme level to inform learning and improve effectiveness
- Leadership, management & QA processes are established

What measures can be used to assess Value for Money for the intervention and preferred delivery channel?

Health partnerships encompass a broad and complex range of interventions in different health care settings and this makes it difficult to measure their overall impact and cost-effectivenes. The value for money of partnerships can nevertheless be assessed by looking at different aspects in a systematic way – including the cost of expert volunteers, the efficiency and effectiveness of partnerships, and the value to the partner country, the volunteers and the UK health system.

The cost of sourcing high quality expertise through volunteers is relatively low compared to other types of technical assistance, as most volunteers are only paid a small subsistence and expenses. Where appropriate and feasible, providing support remotely (e.g. by video-calling) can further reduce costs.

In addition, the external evaluation included a value for money assessment of health partnerships and found that there is a strong culture and practice of cost minimisation, including through the use of low cost transport and efficient approaches to training (e.g. conducting training in health facilities and combining different cohorts of trainees to avoid extra costs).

In terms of the value of partnerships, there is value to the partner countries and value to the UK volunteers. The value of technical assistance using a partnership and volunteering approach is rated highly by developing institutions and health workers compared to other comparable approaches. There is also value to UK volunteers: the evaluation found that they return to the UK with strengthened technical and clinical skills, increased soft skills (confidence, motivation, leadership), international exposure and improved cultural awareness. Less tangible non-monetary benefits for both volunteers and the host country are derived from partnership itself, e.g. through commitment and relationship on both sides.

The effectiveness of partnerships is significant in terms of health workforce capacity improvements. Overall effectiveness in terms of health system strengthening is more difficult to measure – and for partnerships may not be as scalable and sustainable as for larger (and more comprehensive and much more costly) aid programmes that target several areas of the health system. Nevertheless, there are partnership examples that show considerable potential – and the programme evaluation will develop further evidence.

Table 2 below summarises proposed value for money measures for the programme; these will be finalised and clearly defined indicators agreed with the management agent during the programme inception phase. A value for money plan will be developed setting out how to measure, monitor and seek improvements in VFM.

Table 2. Proposed value for money measures for new health partnerships programme

Economy	Supplier performance on fees and expenses, fund utilisation, and time spent on technical assistance, advocacy, M&E / Monitoring of key costs: travel, subsistence and training costs, costs of volunteer support (and compared with commercial TA costs) / Value of in-kind contributions.
Efficiency	Development and delivery of projects i.e. training curricula and education systems / Development and implementation of M&E/data collection and analysis / Training costs per health worker that demonstrates improved clinical knowledge/practice (across similar projects) / Use of volunteer time, e.g. amount of training (and numbers trained) relative to volunteer time inputs / Delivery reflecting established development assistance and health systems strengthening best practices. / Better coordination – i.e. VFM of linkages/synergies with other partnerships and other health projects/plans / Partners’ qualitative feedback on supplier performance.
Effectiveness	Partner performance against a set of Partnership Principles / Impact on HSS in partner countries / Impact on service delivery in partner countries / Impact on gender equality/social inclusion / Value of volunteering for UK health workers / Benefit /value to UK health system/cost to UK health system

Summary Value for Money Statement for the preferred option

The external evaluation of HPS looked at multiple health partnerships and concluded that the value for money of volunteering and partnership approaches is strong. In terms of efficiency, the use of expert volunteers enables provision of specialist expertise to developing country partners at a relatively low cost. In terms of economy, there is also a strong culture and practice of cost minimisation across health partnerships, using low cost transport, conducting training in health facilities, and combining different cohorts of trainees to avoid extra costs. In terms of effectiveness, focusing on a selection of countries and supporting larger, long term partnerships that aim to develop synergy with other programmes through coordination and integration, should lead to increased impact and sustainability.

Value for money in the new programme is further increased through a more strategic (and potentially more sustainable) approach. In addition, the preferred delivery channel will achieve economies of scale through one centralised procurement process (relative to smaller, multiple bilateral contracts), efficiency, by ensuring the selected management agent has strong programme and grant management capacity and effectiveness by better coordinating a range of UK stakeholders, ensuring the right volunteers are deployed, providing support on the ground and ensuring alignment with country priorities in synergy with other initiatives

Commercial Case

Programme delivery – supplier sourcing approach

To successfully oversee the preferred option, delivery through a contracted management agent, the DFID SRO and programme management team for the programme (in DFID’s Health Services Team) will work closely with DFID’s Procurement and Commercial Department (PCD) to ensure a well-planned and rigorous procurement approach.

This will include two commercial competitive tenders, to appoint (i) a management agent, or consortium, for the overall management of the programme, and (ii) a supplier for the programme evaluation.

Commercial competitive tender to appoint a management agent or consortium for the overall management of the programme. The MA/cosortium will be responsible for overall programme management and due diligence (including development of a detailed delivery chain map and risks), awarding and administering grants, providing support for monitoring, evaluation and learning, responding to demand, raising awareness and programme communications in the UK and in HMG partner countries. The MA will also work to strengthen the enabling environment for partnerships in the UK – e.g. by working with relevant stakeholders to ensure volunteering is sustainable and fostering relevant professional recognition of volunteering work in the UK.

Consultation in underway with DFID’s Procurement and Commercial Department (PCD). The procurement will follow Official Journal of the European Union (OJEU) procedures and will consist of a Pre-Qualification Questionnaire (PQQ) stage and an Invitation to Tender (ITT) stage. The Health Services Team will work with PCD to develop rigourous evaluation criteria to be used at each stage of the tender process to ensure that a supplier with an appropriate track record/skills/expertise can be identified, and value for money ensured. DFID will also conduct a due diligence assessment of the preferred supplier.

The supplier will need to demonstrate a set of technical and programme management competencies. Specific technical skills include expertise in stakeholder co-ordination at national government and institutional level, health expertise, and understanding of the partnerships model/approach. Other core (and potentially less specialist) competencies will include programme and grants management (including management of grantees), logistics administration, monitoring and evaluation, and financial management. An Early Market Engagement is already being initiated, and EME findings, including capacity and supplier base will be used to refine programme design and the procurement process.

The Health Services Team (HST) will develop Terms of Reference for the contract in consultation with PCD, setting out expected scope of work and deliverables. Sufficient flexibility will be built into workplans to enable the supplier to manage risks and contextual changes. Payments to any external supplier will be linked to demonstrable achievement against programme outputs and outcomes to ensure value for money. PCD will lead the tender process for this work in partnership with the HST. PCD will develop a comprehensive Contract Delivery Plan setting out the timescale, risks and mitigation measures, evaluation criteria, roles and responsibilities for all involved in the procurement process.

Programme evaluation. A commercial competitive tender will also be carried out to contract an evaluation provider. It is anticipated that this will use DFID’s Global Evaluation Framework.

1. In addition to these two main procurements, the Strategic Case (paragraph 24) describes the need for further analytical and scoping work, to address existing information gaps and inform detailed design of implementation approaches during the inception phase of a new programme:
  1. Detailed analysis of opportunities to strengthen the enabling environment for sharing of UK expertise. DFID’s ‘Knowledge for Development’ (K4D) resource centre framework will be used to review available evidence.
  2. Analysis of factors that have contributed to making health partnerships successful in terms of policy uptake, sustainability and impact. So far as possible, this will entail analysis by country and health theme of the portfolio of projects supported under the current Health Partnership Scheme by the existing management agent (as part of the programme extension). If needed, further associated evidence summaries may be sourced through K4D.

HST and PCD will act to prevent potential conflicts of interests or risks to integrity of the programme procurements. For example, information from the existing HPS programme and from any further analytical/scoping work will be made available to all potential suppliers, and suppliers interested in the evaluation would not be able to bid for implementation.

Supplier Performance Management
The contract terms will be designed in collaboration with PCD to maximise value for money and to incentivise supplier performance through the use of payment by results, service level agreements or key performance indicators as appropriate.

This is a 5 year programme with a 6-month inception phase. The management agent will be required to set out a six-month inception-phase plan, including plans for transitioning existing health partnerships projects into the new programme, as well as a detailed first-year workplan and high-level summary of activities for the remaining years. Suppliers will be expected to agree indicators, metrics and a template for reporting on value for money, gender and progress results at the beginning of the programme.

To mitigate the risk of poor supplier performance, DFID will retain formal break clauses after the inception phase, and after a mid-term review. Where necessary actions will be taken based on findings of formal annual reviews and the mid-line evaluation. Supplier performance will also be considered as part of the project completion review, and the endline independent evaluation may also generate lessons about supplier management. In addition to these formal review points, DFID will carry out regular programme management monitoring and oversight (see Management Case).

Key Cost Drivers
Cost drivers will fall into two categories:
- Management costs: fees and expenses for the management agent, such as salaries, travel, subsistence, equipment, monitoring, evaluation and learning, communications and engagement, stakeholder coordination, and finance costs. The management agent will be appointed by competitive tender and given the variability in the potential supplier market of costs and overheads for grant management, benchmarking of costs will be important.
- Grants for partnership projects. These will be the costs for grantees to deliver partnerships – e.g. travel, in-country subsistence, training materials, project administration and monitoring.
Fee rates are expected to be in line with standard DFID programming. The Supplier will comprise of a mixture of generalist and technical specialist staff. The supplier will be expected to demonstrate that their daily fee rates, as well as their overall management charges, have been benchmarked against existing or precedent DFID programmes and represent value for money. Commercial bids will be submitted with detailed costs and a breakdown of how these are calculated. Bidders will be required to demonstrate how they will achieve value for money over the lifetime of the contract. The competitive process will drive value for money between potential suppliers.

Financial Case

Funding

To achieve the scale of ambition envisaged for the programme, the overall resource requirement is up to £30 million.

Indicative funding allocations for the 3 components are:

1. Strategic, large partnerships with selected priority countries REDACTED
2. Small grants to support new and existing innovative partnerships REDACTED
3. Independent evaluation REDACTED

Any potential management agent for the programme will need to demonstrate capability to deliver the programme’s ambition and to manage this level of funding.

Spending
The financial structure of the programme will include (also see cost drivers above):
- Management costs: fees and expenses such as travel, subsistence, equipment, monitoring, evaluation and learning (including annual conference), communications and engagement, stakeholder/partnership coordination and support, grants management, VAT and finance costs
- Grants for partnership projects
- Evaluation of the programme

Budget and Profile
Up to REDACTED is allocated for additional design and scoping work in 2017/18 (para. 24). The programme is expected to start Q3 2018 and expenditure is anticipated to be relatively low in 2018/19 which will include the managing agent inception period and design work for the independent evaluation. Significantly higher spend is expected from 2019/20 as the programme starts to award grants for partnership projects.

Table 2 below sets out the approximate budget profile by year for the independent evaluation, management costs, and grant awards. These estimates may change (up or down) depending on progress and allowing for a flexible approach. 2018/19 inception costs will be incurred in third and fourth quarters for both evaluation baseline work and managing agent inception activities. Contracts for both managing agent and evaluation suppliers with be based on monthly arrears payments and payments by results, and will consider ODA spend commitments.
Table 2: REDACTED

Monitoring and compliance
DFID will conduct due diligence assessments of all suppliers contracted for the the programme.

The managing agent for the programme will be required to:
- initially report on a monthly basis with a strong focus on programmatic risk, including financial and fraud risks before reducing this to quarterly reporting if deemed satisfactory;
- provide detailed project financial reports that set out in both cash and resource terms actual expenditure to date against the approved project budget and quarterly forecast expenditure for DFID’s financial year (1 April-31 March);
- provide progress reports on the execution of the programme that describe performance against indicators contained in the logframe and, where possible, the associated receipt and utilisation of the resources used to deliver these;
- provide, within six months of the end of their financial year, audited independent assurance that DFID funds have been used for the intended purposes;
- establish and adhere to international best practice on procurement, fraud bribery and corruption, both for their own administration of the programme and for all partners receiving grant funding.

Programme risks and their mitigation, including fiduciary risk, are set out under the Risk section below. The managing agent will be required to apply robust grant award and grant management processes. This includes robust due diligence and risk assessment of health partnerships before grant award, followed by monitoring and support on project design, budgeting, governance, financial controls, fraud management and duty of care. Grant holders will be required to provide regular detailed financial and narrative reports to the manging agent, with payments contingent on verification of expenditure, performance and evidence-based results. The managing agent will be required to carry out reviews of programme and grants-level risk on a monthly basis and rolling audits of grants projects. Any poor performing grants will be required to carry out prompt remedial actions and where they fail to deliver on agreed remedial action plans, these grants will be closed. The managing agent will be required to keep DFID fully informed throughout the process.

The value for money and results achievement of the programme will be continuously assessed during programme implementation and financial statements will be subject to annual audit by an independent external auditor. No significant assets are expected to be procured or held by the programme. Any office equipment purchased for the programe will be subject to periodic asset spot checks by DFID. No return of funds is expected from the programme, except at a minor level in case of programme underspend or underperformance. No special accounting considerations are expected to arise.

D.	Management Case

DFID will lead overall programme oversight. The Senior Responsible Owner (SRO) will be a Health Services Team Health/Policy Adviser, supported by a project manager/officer. Managing the two procurements, contracts and inception phases will initially require significant staff time (REDACTED). Thereafter routine inputs are expected to include quarterly programme management meetings and administration of performance-based payments in the contract. More intense inputs will be required during annual reviews. Anticipated overall level of effort is approximately REDACTED for both the adviser and programme manager.

Inputs from other teams and staff, including Economic Advisory support and from PCD will be required annually for programme reviews, and possibly more often as specific issues arise. It is important that sufficient capacity (DFID staff time) is allocated to oversee the programme and ensure robust programme performance management and DFID leadership. The SRO will report to Ministers through the Head of the Human Development Department.

A steering committee (SC) will be established to provide oversight over programme implementation and lesson learning. Membership will include the managing agent, the SRO, the relevant hub lead (A1) from DFID’s Health Services Team (chair), and DFID health advisers from each of the selected priority countries as required. Participating UK and partner country health institutions such as NHS Trusts, Royal Colleges and PHE representatives will be invited as needed or through the NHS International Group. The DFID SRO will convene the SC with administrative assistance from the managing agent. The SC will have a strategic oversight role, assessing performance, opportunities and challenges and recommending any directional change needed. It will play an important role in agreeing the criteria for grants (and monitoring that these are followed), and potentially be involved in approval of the ‘large’ grants.

DFID and the managing agent will meet fortnightly during the inception phase to discuss progress and agree approaches and workplans. This will shift to monthly, then quarterly over time; as agreed by DFID and the managing agent. The managing agent will report in writing, initially monthly and then quarterly on progress against workplans, and the logframe. Reporting on budgets and financial expenditure will be monthly and in line with contract requirements. In addition, DFID will carry out Annual Reviews and a Project Completion Review in line with the Smart Rules. These will include in-country verification visits by the Health Service Team and inputs obtained from the DFID health advisers in priority countries.

DFID Communications team will also be involved as appropriate to ensure programme results are communicated to stakeholders and the public (working closely with programme suppliers who will also be required to develop appropriate communications materials).

Risk

Overall the programme is considered to be moderate risk. This is largely based on experience with the current Health Partnership Scheme. Table 3 below presents main risks identified, their probability and mitigating actions. The overall risk under each risk category is the residual risk. The risk matrix will be refreshed when the management agent is appointed, and regularly reviewed with the management agent and also as part of every Annual Review.

Table 3 – Risk matrix
Making Health Partnerships Stronger – Risk Register
Risk	Inherent Risk Level					Mitigating actions	Residual Risk
	Probability				Impact				Probability		Impact
Probability / Burgundy – almost certain Red- likely Orange - possible Yellow – unlikely Green – rare / Impact / Red- severe orange - major Yellow – moderate green – minor
Strategic/external context - Overall Minor
Programme fails to align with national priorities, establish links with other HSS initiatives and have a more holistic approach to HSS / &/or / UK volunteers are not able to provide adequate and appropriate training for country context and needs					A key strategy of the programme is for all partnerships to align with national priorities and respond to specific requests from partners. High level dialogue with national government and coordination with other initiatives will be prioritised as part of grant selection / The programme’s management agent will be required to ensure the right volunteers (with the right skills) are deployed to the right projects, based on country partners demand. / The selection process for grants will include a review of country and project needs, other relevant initiatives and potential barriers to successful delivery of grants
Programme implementation suffers threats from raised security levels and political instability					The programme (MA) will monitor risks and ensure adequate Duty of Care. Also, the programme has built in flexibility to adapt according to the political and economic context. Grantees will be required to undertake risk assessments and apply robust policies/procedures to address security issues. / Good and regular assessment of political economy will be conducted by the MA with inputs from DFID country offices and other partners as relevant
Delivery – Overall Minor
Projects are not effective due to: level of UK partner's project management experience, lack of LMIC partner engagement or other contextual factors (lack of co-presence of health workers in participating institutions)					MA will select grants based on previous performance and dialogue with relevant government authorities to ensure buy-in and that enabling conditions exist. MA will support project design, budgeting, monitoring and evaluation. Progress and spending will be reviewed quarterly and funds withheld or redeployed to other partnerships if necessary
Insufficient availability of UK expertise – e.g. if other demands on UK public sector and constraints to volunteers working overseas (eg pension, backfill, revalidation costs) make sharing of UK expertise by volunteering and partnership approaches less feasible.					Programme explicitly includes an output on enabling environment for volunteering and partnerships. Scoping/analytical work will consider risks in detail and outline an action plan to strengthen the enabling environment for volunteers.
Safeguards – Overall Moderate
The programme activities have unintentionally detrimental impact on developing country, including potential replacement of local staff without necessary co-development					The programme will ensure close engagement with national institutions and governments. Criteria for MA to award grants will include mutual understanding of roles and responsibilities and of the requirements necessary for the partnership to go ahead. Regular monitoring and feedback from partners and beneficiaries will be undertaken. If necessary, MA will terminate relevant activities/ or funding
Operational – Overall Moderate
Competing DFID priorities result in insufficient resources to support the programme or hinder close DFID oversight					The SRO for this programme will be supported by other programme and advisory personnel and regular communication will be held between DFID and the MA / In the event of shifts in priorities, DFID will ensure proactive management of any impact on grantees, including stakeholder, political and media management. / (NB the programme is strongly aligned with established DFID priorities including work to strengthen health systems and contribute to the health SDGs, and complements other DFID programme investments.)
Fiduciary – Overall Minor
Grants do not meet adequate financial and project management standards. Multi-partnership arrangements and complex governance structures create challenges in effectively accounting for DFID funds					Demonstrated performance and capacity will be included in criteria for MA to select grantees; MA will ensure they have robust financial and control policies/systems in place. MA will also build capacity in this area as necessary. Payments are dependent on performance and adherence to robust financial reporting requirements, and the MA will conduct regular audits
Reputational – Overall Minor
Perceived or actual impact of volunteering on NHS health service delivery (e.g. gap filling, hidden costs to sending organisation)					There is no evidence that partnerships have negative impact on NHS service delivery – studies and evaluations have identified benefits to the NHS of volunteers’ enhanced experienced skills. Any new evidence of detrimental impact on the NHS in the UK will be assessed in detail and acted on.

Monitoring and Evaluation
The monitoring and evaluation approach includes i) monitoring of partnerships by the management agent, ii) programme monitoring and reporting to DFID, and iii) an independent evaluation.

(i) Monitoring of partnerships by the management agent. The managing agent will be responsible for monitoring and evaluating the peformance of partnerships and their projects through appropriate M&E frameworks and regular stock-taking consultations. The MA will also be responsible for coordination amongst partnerships, maximising synergies, reporting back and sharing lessons with all other stakeholders. A monitoring plan will be agreed during the inception phase and reviewed every six months to begin with.

(ii) Programme monitoring and reporting to DFID. The managing agent will need to capture information for assessing performance in a timely, effective and efficient way. Some of the key targets at outputs, outcome and impact level are provided in the draft Logical Framework (Annex 1), which is based on the theory of change set out in the appraisal case. This will also be finalised during the inception phase, and considered as a living document during programme implementation (updated as required following Annual Reviews each year), to enable adjustments according to shifting contexts and priorities.

The management agent will submit quarterly narrative reports on progress, including risk monitoring to DFID (this will be based on a compilation of monthly activity reports).

In line with the Smart Rules and associated guidance, DFID will conduct Annual Reviews against logframe outputs and main outcomes. DFID will undertake a Project Completion Report at the end of the programme.

(iii) Independent evaluation. The current HPS included a rigorous evaluation conducted towards the (anticipated – the programme was subsequently extended) end of the programme. This resulted in many useful lessons to inform future support for partnerships. To further increase the evidence base on the effectiveness of health partnerships compared to other approaches to strengthening health systems, DFID’s Evaluation Department rcommended that any future health partnerships programme should have an independent evaluation from the programme outset (allowing for baseline, midline and endline data).

An early evaluability assessment will be conducted as soon as the business case is approved to develop detailed ToR for the evaluation contract. The assessment will be done using DFID’s Evaluation Quality Assurance’ s facility (EQUALs) support service and will help confirm the scope and most relevant approach for the evaluation. Findings and recommendations from the evaluation will be shared with UK international health stakeholders through the the NHS International Group. Additional opportunities to disseminate the findings in relevant fora will be identified. The evaluation will feed into programme implementation and inform any future support for partnerships. It will be done in line with DFID evaluation policy and will be appropriately quality assured throughout.

At this stage it is anticipated that the evaluation would focus on a selection of large, strategic country focused partnerships, and that key evaluation questions might include:

- Have the strategic country partnerships  (linked up, with synergies with other initiatives) been effective at improving health worker performance as a result of the capacity building provided?
- Have the strategic country partnerships been effective at improving health service delivery?
- If health worker and health service performance have improved, how likely are changes to be sustainable (i.e. result in long-term change that goes beyond the programme)?
- Have the strategic partnerships been able to influence wider health system constraints? Or have they been able to contribute to health systems’ strengthening?
- What factors have been likely to contribute to their effectiveness or lack of effectiveness?
- Have partnerships led to improvements in the quality of health services and health outcomes of populations served?
- Have partnerships /UK expertise and models been adequately adapted to be relevant to different (low income and lower-middle income) settings?
- How has the volunteering experience affected performance on return to the UK?
- Have partnerships been able to positively address gender and equity considerations? What evidence is there for this?
- What is the value for money of health partnerships compared to other types of technical assistance in selected countries/facilities?

All programme monitoring and evaluation will need to recognise that development of meaningful and productive partnership relationships requires significant time investment upfront. The focus in the early phases will therefore be more heavily on outputs, with attention turning to longer-term impacts as the programme and supported partnerships mature.

Responsibility for overall programme accountability/oversight
DFID retains overall accountability and oversight for all elements of the programme.