Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Supporting Economic Transformation
Programme Value: £4.467m		Review Date: December 2017
Programme Code:	Start Date: 18/11/14	End Date: 30/09/2018

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	A+	A	A+
Risk Rating	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

The SET programme, which is being implemented by the Overseas Development Institute (ODI), made good progress this year and exceeded or met all milestones at output and outcome level, moderately or substantially exceeding all expectations except one on private sector engagement. An impressive achievement in the face of a 30% (£370,000) budget cut.

SET has demonstrated direct and indirect impact on DFID’s programming and policies, such as the Economic Development Strategy, CDC’s strategy as well as influencing a number of central and country offices. It is important to note that policy impact is subject to time lags from the time of the original intervention.

In response to last year’s annual review SET has shown flexibility by increasing their focus on working with the private sector. This has involved supporting the private sector directly, such as the support to the Kenya Association of Manufacturers as well as facilitating dialogue between governments and the private sector. This should improve coordination between businesses and government to support economic transformation.

While the increase in the number of SET engagements is impressive, this may come at a cost of delivering significant policy impact. Economic transformation is unlikely to come from one or two policy changes. Economic transformation is more likely to happen with a sustained policy focus on a smaller set of strategic areas.

Following the steering committee meeting, it was clear that SET had already had significant engagements with some partner government officials and stakeholders. This made it difficult to shape the work plan in line with the recommendations of the steering committee and DFID.

There are still some key improvements to be made, as set out in the priority recommendations below.

Summary of recommendations for the next year

Recommendation	SET Response	Implemented by
1. Focus on turning outputs into outcomes, supporting governments and development partners to design and implement better economic policy. This should include building on extensive support to the Governments of Tanzania and Rwanda with a view to improving their ability to analyse policy decisions more effectively to prioritise economic transformation.		Plan in place by February 2018
2. SET does not broaden support to DFID central departments in the final year. SET should work closely with the DFID team to agree any work with central departments this year. Resources should be freed up to deepen work with low income country partners.		Ongoing interaction with DFID programme team on workplan.
3. Private sector strategy is reviewed and revised building on the experiences of this year’s scale up in working with the private sector. Should identify priorities for the final year in terms of work with the private sector.		January 2018
4. SET should continue to ensure all policy briefs are targeted to policy makers with recommendations stated clearly, such as the SET paper ‘are sectoral labour markets in Nepal helping firm growth.’		SET to submit first 3 briefing papers to DFID programme team ahead of release.
5. Milestones should be revised to ensure they remain challenging and focus on developing longer term, more impactful relationships in partner countries as opposed to more.		Milestones revised by end of January 2018.
6. The Management Committee meeting, to discuss the work plan should be held in January/February 2018 and agreed with the DFID Programme team by mid-March – before any work commences		Agreement by end of December 2017.
7. SET should develop a transition plan/ strategy for sustaining the website after the programme closes		Plan in place by February 2018

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	204254
DevTracker Link to Log frame:	204254

Economic transformation is a central part of DFID’s Economic Development Strategy and of the relationship between economic growth and poverty reduction. But we do not know enough about the policies and programmes that promote transformation in particular contexts. The debate remains too theoretical, and we do not know enough about the political economy of transformation.

SET was designed to overcome shortfalls in this area as identified by the Growth Portfolio Review and ICAI’s review of DFID’s work with the private sector. It is well aligned to new priority areas, such as DFID’s Economic Development Strategy, the emerging prosperity agenda and Global Britain.

SET is a 4 year accountable grant, bringing together country level policy and advisory work, high quality policy analysis, support to DFID on growth diagnostics, knowledge and programme design to support economic transformation. It is intended to help bridge the gap between aspirations on transformation and the practical actions needed to achieve change.

It has three interdependent outputs:
Policy advice to DFID, governments and other development partners, including;
1. Support to DFID country offices and central departments with analysis to inform policy and programme work
2. Analysis to help understand potential patterns of transformation and how to orient policies and programmes to unlock this potential;
3. Support to country governments on strategies to accelerate economic transformation

Promoting economic data for transformation including a portal to sources of data bases on economic transformation; and

A communication component to promote evidence from the programme and important policy issues on the quality of growth processes.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

In order to assess the performance of SET the progress against milestones is assessed via beneficiary feedback, quality assurance throughout the year and discussions with DFID country offices who have worked directly with SET. A summary of progress is presented in the table below that demonstrates the strong progress SET has made this year. SET exceeded expectations against all but one outcome indicator. Stakeholder feedback and interviews with DFID country offices commended the flexibility and quality of SET analysis and confirmed influence. There were some concerns about the variable quality/clarity of reports.

Outcome	Outcome Indicator	Milestone	Progress
1. DFID, governments and other development partners design and implement economic development investments to foster structural transformation in order to give rise to stronger, more inclusive growth and poverty reduction in the long term	1.1 Number of DFID country portfolios influenced by SET research and advice, in design or delivery	6 by Oct 2017	8 - Moderately Exceeded Expectations / Already achieved: 4 / New cases: 4 / DFID Nepal / SET research papers influenced the design of DFID Nepal’s Skills and Employment programme. / DFID Rwanda / SET’s work informed DFID Rwanda’s choice of interventions for the Invest Africa programme, and has helped DFID Rwanda rethink how to best support Rwanda’s economic growth. / DFID Mozambique / SET’s paper informed ongoing conversation with Govt and other partners. It will be embedded in DFID M’s portfolio narrative. / DFID Zimbabwe / SET’s central recommendation (to develop a research consortium to support development of policy and debate about economic renewal was included in DFID Z’s 'Flexible Governance and Stability Fund
	1.2 Number of DFID centrally managed programmes influenced by SET research and advice.	6 by Oct 2017	7 - Moderately Exceeded Expectations / Already achieved: 5 / New cases: 2 / Diagnostics analysis (GRD) / SET’s analysis has influenced GRD’s approach to developing country diagnostics and helped improve its coordination and influence with the World Bank through this work. / World Bank infrastructure analysis (GRD) - / The report was shared with the World Bank and the DFID team working on integrating the findings of the latest World Development Report across World Bank Group operations.
	1.3 Number of other donors, governments or multilateral agencies adopting policy or programming choices through SET programme influence	2 by Oct 2017	6 - Moderately Exceeded Expectations / Already achieved: 1 / New Cases: 5 / United Nations Economic Commission for Africa (UNECA) / SET provided research that informed the framework for UNECA country strategies. The work helped UNECA prioritise and shaped their definition of structural transformation. / World Bank / SET influenced the Bank’s methodology for its country strategies. Analysis on the limited extent to which existing WB strategies prioritised economic transformational objectives was used by DFID to influence then to make significant changes. / Government of Liberia (GoL) / SET facilitated an investment event between the GoL, national investment promotion agency, the Liberian National Investment Commission (LNIC), CDC, and UK-based private investors. The event improved the GoL’s understanding of foreign direct investment and they are considering bringing in expertise to support them further. / TradeMark East Africa (TMEA) / TMEA requested SET peer review their model used to evaluate the impact of their interventions. SET’s peer review was very well-received by and influential on TMEA, with its recommendations adopted: / Government of Rwanda / The Ministry for Industry was positive about SET’s guidance note appraising policy options and will influence the GoR’s new Economic Diplomacy Programme by informing the action plan for its development.
2. Better coordination between private sector/business and government on economic transformation	2.1 Policy processes being changed by private sector participation	3 by Oct 2017	4 - Moderately Exceeded Expectations / New cases: 4 / Government of Tanzania: FYDPII drafting / SET included the domestic private sector through a consultative workshop, which contributed to the emphasis on the private sector in the FYPDII / Government of Tanzania: FYDPII implementation / SET facilitated the involvement of associations including, the CEO’s Roundtable, the Tanzanian Business Council and the Leather Association of Tanzania to support engagement by the private sector. / Kenyan election manifesto development (through support for KAM) / SET jointly produced a 10-point plan with KAM which helped shape the Jubilee, NASA and Thirdway Alliance election manifestos. / DFID Nepal: development of Skills for Employment programme / SET interviewed over 40 domestic private sector firms for a research paper that influenced the design of DFID Nepal’s Skills and Employment programme.
	2.2 Private sector firms/associations operations/plans influenced by the SET programme	1 by Oct 2017	1 - Met Expectations / New cases: 1 / Kenya Association of Manufacturers (KAM) / SET’s support helped KAM shape their advocacy priorities through the co-development of a 10-point policy plan for manufacturing, job creation and industrialisation.
3. Better global knowledge on how policies can support growth by accelerating economic transformation	3.1 SET demonstrates it is a centre for knowledge on ET through media mentions (and citations).	50 media hits by Oct 2017	Substantially Exceeded Expectation / New cases: 106 / 83 tracked media hits in both UK national outlets (such as the Financial Times and the Economist) and local and national media in SET countries (such as African Business Magazine, the Myanmar Times, the Guardian [Tanzania] and the Reporter [Ethiopia]). / 23 tracked citations of the SET programme, SET data and/or research in research or communications outputs of external organisations (such as the OECD Development Centre, the European University Institute, the IGC and New Climate Economy).
	3.2 SET demonstrates it’s a centre for knowledge on ET through meaningful collaborations with research outlets and prominent economists (including following direct requests to work with SET).	4 cases by Oct 2017	8 - Substantially Exceeded Expectations / New cases: / Collaborative with Louise Fox, Chief Economist at USAID / Co-authored two research papers (here and here) and Dr Fox later joined SET’s Advisory Board and spoke on the panel of the launch event for the programme’s anchor paper in March 2017. / Collaborative research with New Climate Economy (NCE) / Co-authored a research paper. / Collaboration with Bernard Hoekman, Director, Global Economics at European University Institute / Co-edited an essay collection featuring contributions from over 19 economists including Dani Rodrik, Margaret McMillan and Ritwika Sen. / Collaborative work with UNECA / Peer review on UNECA country profiles and economic transformation. / Collaboration for SET anchor paper / SET’s anchor paper was co-authored with economists Maggie McMillan (Tufts University) and John Page (Brookings). Maggie later presented her work on the paper at the launch event held at ODI. / Collaborative work with Dani Rodrik / Economist Dani Rodrik partnered with SET for an event on the future of economic transformation in developing countries. / Collaborative work with the World Bank / Collaboration to improve the prioritisation of economic transformation in the World Bank country strategies. SET was approached in 2017 by the World Bank to host the launch event for the future of manufacturing-led development. / Collaborative work with Justin Lin and CNSE / Collaboration has resulted in Justin Lin requesting to work with SET to launch his new books at a public ODI event, and in further research partnerships with The Centre for New Structural Economics (CNSE).

Overall output score and description

A+ (moderately exceeded expectations). SET has exceeded expectations in all but 1 indicator and substantially exceeded expectations against 2 indicators. This strong performance merits an A+. SET has provided evidence of numerous cases where their work has influenced policy decisions of partner country governments and DFID departments. They have also responded well to feedback last year to focus on bringing the private sector into policy discussions. SET have again produced a number of high quality knowledge outputs working with a significant number of other high profile research outlets and economists.

Key lessons

As we move into the final year of the programme, we need to focus on delivering the project outcomes and leaving a sustainable change in LIC policy making and approach to analysis of economic transformation. While the number of SET relationships are commendable, this is likely to be delivered with sustained engagement with fewer policy makers. Logframes and KPIs should be revised to incentivise this, and recognise when SET are delivering above expectations.

Key actions

SET focuses on delivering project outcomes in the final year and leaves a sustainable footprint behind, following closure in October 2018.

DFID determine what if anything should follow from SET.

In the final year set should maximise the impact of their body of work by ensuring strong communication of the key lessons from the last 3 years of work.

Has the logframe been updated since the last review?

The logframe was amended due to SET exceeding expectations on previous milestones. There was also some ambiguity about success indicators for the private sector. The following changes were made to the logframe:

Outcome Indicator 1.2 – Number of DFID centrally managed programmes influenced - the milestone was increased to reflect SET’s achievement the year before.

Outcome Indicator 1.3 – Number of governments, other donors or multilaterals adopting policy programming choices through SET programme influence – the milestone was reduced to reflect the difficulty in providing tangible evidence of impact on government.

Outcome Indicator 2.1 – Policy processes being changed by private sector participation – the milestone was slightly reduced to reflect the challenge in showing evidence of change.

Outcome Indicator 2.2 – Private sector firms/associations operations/ plans influenced by the SET programme – the wording of this indicator was amended from ‘changed’ to ‘influenced’ and the milestone reduced to reflect the challenge of influencing the private sector.

Outcome 3 – It was agreed to have two indicators for this outcome – one on media hits and citations of SET’s work and the other on collaboration between the SET programme and prominent economists and research bodies.

Output Indicator 1.1 – DFID country offices and central departments supported – milestones increased to reflect SET’s success in the previous year.

Output Indicator 1.2 – Thematic analysis focused on specific issues – milestones increased to reflect SET’s success in the previous year.

Output Indicator 2.1 – Support to country governments on strategies to accelerate economic transformation – milestone increased to reflect SET exceeding milestone in the previous year.

Output 3 – Private sector and business engaged on the role of economic transformation in policy dialogue - New language agreed for output indicators 3.1 and 3.2, to make them more challenging.

Output 4 – The indicator was changed from ‘quality of the data portal’, which was difficult to measure to ‘better use of economic data in analysis of economic transformation.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Policy advice to DFID
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 DFID country offices and central departments policies and programmes supported by SET research outputs, including support with growth diagnostics.	9 cases to country offices by Oct 2017	11 - Moderately Exceeded Expectation / Already achieved: 8 / 3 New offices: / DFID Nepal (skills and employment programme) / DFID Mozambique (economic transformation and job creation in Mozambique) / DFID Zimbabwe (flexible growth and governance fund) / 6 Ongoing offices: / DFID Burma (FDI in Burma’s garment sector) / DFID Kenya (10-point plan for manufacturing and industrialisation) / DFID Nigeria (avenues for economic transformation) / DFID Rwanda (public-private collaboration, and financing for manufacturing sector) / DFID Tanzania (implementation of the FYDPII) / DFID China (manufacturing employment in China)
	6 cases to central departments by Oct 2017	10 - Moderately Exceeded Expectations / Already achieved: 5 / New cases: 5 / DFID GRD (Diagnostics) / DFID GRD (Fragile States) / DFID GRD (DFIs) / DFID GRD (World Bank infrastructure) / DFID TPU (WTO 2017 on fisheries, e-commerce and agricultural subsidies)
1.2 In-depth and thematic analyses focused on specific issues proposed by DFID and other partners.	22 thematic analyses by Oct 2017	27 - Moderately Exceeded Expectations / Already achieved: 19 / New cases: 8 / Trade in services: essay collection (Feb, 2017)(DFID) / Financing manufacturing: mobilising finance (June 2017) / Financing manufacturing: macroeconomic conditions (June 2017) / Financing manufacturing in Rwanda (June 2017) / Development finance institutions / Diagnostics / World Bank: infrastructure / Manufacturing: factors for success (with ACET)

Key Points

SET has exceeded all milestones and there is strong evidence that SET’s work is having an influence on the design and implementation of DFID programmes, as confirmed in interviews. Therefore this output has moderately exceeded expectations (A+). For example, SET’s research has influenced the design of DFID Nepal’s Skills for Employment programme and informed DFID Rwanda’s choice of interventions for the Invest Africa programme.

DFID Tanzania, Nigeria and Trade Policy Unit confirmed SET’s work is of high quality and relevant to DFID programmes. DFID country offices also expressed the usefulness of SET’s work in enabling DFID teams to engage with and influence partner governments. Stakeholders have given positive feedback for SET events since they provide opportunities for engagement with SET’s research and other stakeholders, and facilitate ongoing communication with SET when reports are yet to be completed.

Despite positive feedback interviewees highlighted concerns regarding the quality of policy briefs and the delay in reports being received after initial research. Both DFID Nigeria and Tanzania highlighted this long delay between research and receiving the final report. Centrally GRD expressed a similar issue with a delay to a paper on economic development in Fragile and Conflict Affected States. DFID country teams also raised the variability in clarity of reports and policy briefs. Although it should be noted this was against other high quality SET reports and policy briefs so potentially reflects consistency/quality assurance problems as opposed to any other issue.

Issues raised in previous annual reviews, and summary of responses (where relevant)

SET to produce policy briefs with key takeaway messages for DFID staff on economic transformation, from January 2017.
2.	SET to use more experts outside of its own network (e.g. IGC, where they are in country), to provide a challenge function to their approach and findings, from January 2017.
3.	DFID and SET to scope what has already been done before proceeding with any new work, to minimise the risk duplicating other products, from January 2017.

SET Project Director to sign-off the reporting guidance and send to DFID Senior Responsible Officer, from January 2017.

SET has responded well to the recommendations made in the previous annual review. SET has produced ten policy briefs and activities generally complement rather than replicate existing pieces of work. Interviews with DFID colleagues confirmed that SET has engaged a broader network of experts.

Recommendations

Focus on turning outputs into outcomes, supporting governments and development partners to design and implement better economic policy. This should include building on extensive support to the Governments of Tanzania and Rwanda with a view to improving their ability to analyse policy decisions more effectively to prioritise economic transformation.

SET should not broaden support to DFID central departments in the final year. SET should work closely with the DFID team to agree any work with central departments this year. Resources should be freed up to deepen work with low income country partners.

Milestones should be revised to ensure they remain challenging and focus on developing longer term, more impactful relationships in partner countries as opposed to more.

Output Title	Policy advice to governments and other development partners
Output number per LF		2	Output Score	A+
Risk:		Moderate/	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Support to country governments on strategies to accelerate economic transformation	7 cases to 5 governments by Oct 2017	8 cases to 6 governments - Moderately Exceeded Expectation / Already achieved: 6 cases to 5 governments / New cases: 2 / Government of Rwanda (2nd case) / Government of Liberia (new)

Key Points

SET has supported two additional governments and is assessed as moderately exceeding expectations (A+). Support was provided to the Rwandan Government on financing manufacturing and private-public collaboration for export-based manufacturing both received positive feedback. The Presidential Advisory Council is keen to follow up with SET with a view to setting clear policy implications.

A guidance note to the Rwandan Ministry of Trade and Industry (MINICOM), appraising policy options, may contribute to the development of the GoR’s Economic Diplomacy Programme. This paper is currently being used in training sessions by the Africa Governance Initiative (AGI) with the government.

A qualitative study of the domestic business community, based on interviews with private firms, is near completion, will be presented to the GoR once finalised. This aims to support their thinking around strategy for engagement with the private sector.

SET organised an investment event that facilitated engagement between the Government of Liberia, the Liberian National Investment Commission (LNIC), CDC, and UK-based private investors in Liberia.
The event resulted in relations being forged between investors including CDC and the GoL and improved the Government’s understanding of foreign direct investment.

These outputs all have the potential to generate policy impact, however, it is too soon to expect demonstrable policy impact. SET should continue to work closely with partner governments and follow up on advice/engagements to understand how it influenced policy impact.

Issues raised in previous annual reviews, and summary of responses (where relevant)

No evidence was provided that SET better targets and messages to key government ministers (e.g. easy to read summary version of main points). However, we have seen a general improvement in the quality of policy briefs and this is moving in the right direction.

Recommendations

Focus on turning outputs into outcomes, supporting governments and development partners to design and implement better economic policy. This should include building on extensive support to the Governments of Tanzania and Rwanda with a view to improving their ability to analyse policy decisions more effectively to prioritise economic transformation

SET should ensure all country engagements are aligned with UK policy objectives and priority countries.
The Management Committee meeting, to discuss the work plan should be held in January/February 2018 and agreed with the DFID Programme team by mid-March – before any work commences

Output Title	Private sector and business engaged on the role of economic transformation in policy dialogue
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Policy processes in which private sector participate due to SET’s facilitation	3 cases by Oct 2017	5 - Moderately exceeded expectations / Already achieved: 2 / New cases: 3 / Kenya election manifesto development (through KAM support) / Liberian government investment promotion strategy / DFID Nepal: development of Skills for Employment programme
3.2 Private sector firms/associations supported by the SET programme	1 case by Oct 2017	3 - Moderately exceeded expectations / 3 cases / Kenya Association of Manufacturers / Nigerian Economic Summit Group / Liberian National Investment Commission

Key Points

SET’s engagement with the Kenya Association of Manufacturers (KAM) was strong. SET produced a 10 point policy agenda for manufacturing and industrialisation, which influenced the policies of the campaigning political parties during the pre-election period. Both parties shifted policies to acknowledge the importance of the manufacturing sector for Kenya’s economic prospects.

Although SET has exceeded the milestones, engagement with other private sector organisations has had less impact. The work with the Nepal skills for employment programme, ensured the views of the private sector were included in the design of a DFID programme. Several stakeholders intimated the analysis will inform their future interventions. We assess that, overall, SET has moderately exceeded expectations.

SET supported the private-sector umbrella organisation, the Nigerian Economic Summit Group (NESG). Their research was launched at the NESG’s annual Summit in Abuja, and digitally published. The NESG referenced the work in a presentation to the government on providing tax rebates to manufacturers. Again it is too early to tell if this work will influence tax policy, and SET should continue to follow up with NESG.

SET raised the Liberian National Investment Commission’s (LNIC) knowledge and understanding of how development finance institutions such as CDC can help them achieve their foreign investment goals. CDC have confirmed they are going to follow up meetings planned with both agriculture and infrastructure contacts to explore potential investments.

Issues raised in previous annual reviews, and summary of responses (where relevant)

1. SET to produce a 2 page strategic action plan on engaging the private sector for DFID approval by February 2017.
2. SET and DFID to consider how to measure influence on the private sector by February 2017.
3. SET to give DFID more feedback on its engagement with the private sector from January 2017.
4. DFID and SET better track the impact of the private sector and what has changed as a result of their engagement.
SET produced a 2 page strategic action plan on engaging the private sector and provides DFID with more feedback on its engagement with the private sector. In the logframe, private sector indicators and milestones have been modified to better track and measure impact.

Recommendations

Private sector strategy is reviewed and revised building on the experiences of this year’s scale up in working with the private sector. Should identify priorities for the final year in terms of work with the private sector.

Output Title	Better use of economic data in analysis on economic transformation in policy dialogue
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Briefing papers to illustrate and promote the use of SET economic data	1 by Oct 2017	Met Expectation – 1 case by October 2017
4.2 Number of citations of SET economic data by DFID and other organisations (including in the media)	5 by Oct 2017	Moderately Exceeded Expectations / New cases: 7 / Data on export-based manufacturing cited in: / - article in The Economist / - column in the Business Daily / - opinion piece by Liberian Minister Axel Addy and the WTO in the African Independent / - article in African Business magazine / - article in ‘How we made it in Africa’ / Data cited by DFID Nepal in presentation on structural transformation / Data cited in DFID’s IGD for Uganda

Key Points

The number of citations has moderately exceeded expectations. The evidence that they have strengthened policy dialogue is not strong, but we accept that this is likely to be subject to significant lags. There is strong evidence of good awareness of the data portal amongst DFID staff. At a recent SET run training session, 70% of DFID participants reported that they were aware of the portal and others signalled their intention to make use of it in the future. The programme is assessed as having moderately exceeded expectations.

A two page briefing paper on the findings of the SET data portal was produced and includes top-line messages and a link to the data portal itself. The intended audience for the portal is economists and other analysts, and while the data is not in easy to use table, it more than meets the requirements as set out by DFID. It also follows best practice by making data sets from SET papers and analysis readily available.

It is not evident that the media citations demonstrate an improvement in data use. Two compare the levels of manufacturing in Africa and are fairly generic compared to the type of information held on the data portal. An article in the Economist is a quote from the SET Director’s about why manufacturing would shift from Asia to Africa rather than hard data analysis. All media citations quote the ‘Overseas Development Institute’ rather than ‘SET’. There are no references to citations from governments and other development partners.

Summary of responses to issues raised in previous annual reviews (where relevant)

The revised Data Portal Strategy was submitted in April 2017 and was accepted by DFID. It is not clear what value will be added by making the data portal as complex as originally envisaged, especially at this point in the programme.

Recommendations

Stronger evidence that governments and development partners are referring to SET data in economic transformation policy dialogue and decisions.

Output Title	Implementation of a communications strategy including events to promote understanding of economic transformation.
Output number per LF		5	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Development and implementation of a communications strategy	Update of communications strategy by Oct 2017	Met Expectation / Revised, updated communications strategy submitted to DFID and agreed in April 2017. / Implemented on a rolling basis as part of the dissemination of SET research. SET have a strong track record of organising dissemination events, they are well attended and feedback is overwhelmingly positive.
5.2 Results of multi-event assessment tool show good responses from participants	70% of attendees surveyed rate event as ‘good’ or higher	95% - Substantially Exceeded Expectation / Averaging feedback from 9 events, 95% of attendees rated the event ‘good’ or higher (or equivalent question) / PDF2 Embedded Advisors workshop (02/12/16) / FDI and the garment sector roundtable (14/03/2017) / Approach paper launch (22/03/2017) / ACET PACT manufacturing chapter launch (05/06/2017) / Entrepreneurship and African industrialisation event (26/06/2017) / Launch of 10-point plan with KAM (05/07/2017) / DFID economist training (12/09/2017) / UK-Liberia investment event (14/09/2017) / Pathways to prosperity launch event (26/10/2017)
5.3 Uptake of SET products by the global community, through downloads from the SET website.	20k downloads by Oct 2017	46k - Substantially Exceeded Expectation / Over 46k downloads / SET has seen a significant increase in downloads over the course of the year, over 200% compared to last year. SET publications now feature on the ODI website, increasing visibility and driving downloads.
5.4 Briefing papers to summarise and promote key messages of SET research	5 cases by Oct 2017	10 - Substantially Exceeded Expectation / 10 New cases: / -Economic transformation: a new approach to inclusive growth / -Why economic transformation? / -Rwanda: financing for manufacturing / -FDI and economic transformation in Myanmar / -Rwanda: coordinating public and private action for export manufacturing / -Local content policies and backward integration in Nigeria / -Economic transformation and job creation in Mozambique / -Pathways to prosperity and inclusive job creation in Nepal / -Are sectoral labour markets helping firm growth in Nepal? / -Using SET data to identify opportunities for economic transformation in low-income countries

Key Points

SET has either met or exceeded all milestones, therefore this output is scored an A+. Stakeholder interviews did identify a number of areas where improvements could be made around tailoring key messages to different audiences and ensuring all policy briefs have clear recommendations and policy implications sections.

The number of SET events, blogs, tweets, research reports, and policy briefings demonstrate SET is implementing its communication strategy. Although an initial mailing list was established for SET’s e-newsletter there is no evidence SET has added a widget to their website to engage a broader set of stakeholders through e-newsletter updates.

Kenya Association of Manufacturers, DFID Trade Policy Unit, and DFID Tanzania confirmed positive feedback for SET events and highlighted the value of these events for engaging with additional expertise and forming relationships with potential stakeholders for future projects.

Stakeholders have welcomed the two-page briefings and the number of downloads for SET products is very positive. Despite positive feedback interviewees highlighted concerns regarding the variable quality of some policy briefs and felt being clearer about intended audience would help. SET could consider producing different products for different audiences.

Issues raised in previous annual reviews, and summary of responses (where relevant)

SET has responded well to the recommendations however scoping of their website indicates e-newsletter widget is yet to be integrated. Both the revised communication strategy and logframe indicators for implementation of the communication strategy were agreed in 2017.

Recommendations

SET should continue to ensure all policy briefs are targeted to policy makers with recommendations stated clearly. A good example of a brief with clear policy recommendations is SET’s briefing paper ‘Are sectoral labour markets in Nepal helping firm growth’

Milestones should be revised to ensure they remain challenging and relevant, an indicator that assesses the clarity of policy recommendations should be prioritised.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The table below shows a breakdown of the key costs for the SET programme for the past year by quarter.
	FY16-17 Q3	FY16-17 Q4	FY17-18 Q1	FY17-18 Q2
0 Core costs	40,000.00	40,000.00	40,000.00	40,000.00
1 Policy Advice and Research Support	295,766.63	372,878.12	301,406.27	189,813.04
2 SET Portal website	18,748.80	6,815.20	4,720.00	4,000.00
3 Networking / Public Affairs	19,148.51	21,431.30	22,548.32	17,315.51
Total	373,663.94	441,124.62*	368,674.59	251,128.55**

The total spend for the year was £1,434,591.70.
*The higher than average spend in the final quarter of FY16-17 was the result of agreed spending of the remainder of unspent SET funds from the four previous quarters
**The lower spend in the second quarter of FY17-18 is explained by the £370,000 cut to the FY17-18 budget, which has been spread across the three final quarters of the FY (the budget cut was not a reflection on project VfM, performance or effectiveness).

Key cost for SET are; fee rates, management costs, travel costs for fieldwork and dissemination and hosting events.

Cost drivers are the type of specialist advice required by each project, and whether there are deep markets for this expertise. SET agreed to cap daily fee rates at the outset of the contract and this is one way of managing this cost. Where networking/dissemination occurs is another key cost driver, which in turn drives travel costs. SET have made progress on controlling these costs by better planning, and visiting more than one focus country in each trip to reduce the costs of travel to Africa.

Fee rates were agreed at the outset of the programme in 2014 and have been held constant over the course of the programme. These were rigorously benchmarked across a range of DFID programmes before being agreed and compare favourably to similar programmes. Subcontractors who work on SET projects are also assigned a fee rate in line with these benchmarks based on their experience. By using reasonable fee rates, below general ODI staff rates, SET can consistently deliver work at a lower cost and ensure value for money.

SET management fees for the year are 11% of total spend. This is a fixed amount each quarter and covers only staff fees for the programme director and project/communications management at the rates outlined in the SET business case.

Travel Costs. SET follows ODI’s expense policy, which provides guidelines for subsistence and accommodation allowances, which are more stringent than those used by DFID. All flights must be booked economy class and well in advance. This year SET included detailed information on travel expenditure for fieldwork, dissemination events and overseas SET events as part of the quarterly invoice. Spot-checks have been carried out throughout the year and no issues were found.

Efficiency

SET has demonstrated efficiency this year by meeting and in most cases exceeding milestone targets even following a 30% reduction in budget. SET were able to reduce some project budgets, and still deliver high quality work that was influential. Some of the delays in the timeliness of work are due to budget constraints on SET, however, this could be more clearly communicated to key stakeholders.

This was done by re-assessing the extent to which new extensive research was required and focusing on producing more short briefing papers. Shifting to producing briefing papers as opposed to research is not a long term answer to VfM, however, given all the analytical work they have done to date it was a good temporary shift to still deliver on the logframe and budget. It demonstrates an ability to be flexible and build on strong relationships with developing country partners to ascertain the right quality and quantity of input to policy processes.
SET also made greater use of in-country consultants to deliver work at significantly reduced costs. For example the KAM project in Kenya had high levels of impact and was carried out in large part by an in-country consultant. They also used local researchers to carry out fieldwork in Rwanda.

Working closely with the DFID programme team SET agreed to reduce expenditure on the SET data portal, but still improve the number of data citations.

Travel and dissemination costs were reduced significantly (23% in the final quarter). This was achieved by combining trips to Africa across projects as internal flights are often much cheaper than return flights to the UK. SET were also opportunistic and planned high level events when prominent speakers were already in the UK, for example hosting Justin Lin in September 2017. Key dissemination events were also hosted in country as opposed to flying over several key stakeholders to the UK.

Effectiveness

The effectiveness of the programme is evaluated on the basis of evidence of impact on DFID country offices, central programming, national government policymaking or knowledge, quality of analysis, visits to SET’s website and events. These indicators are measured through the programme’s logframe and SET’s has developed a track record of success against these indicators as it continues to meet or exceed all targets through the year.

As part of our ongoing efforts to improve VfM, this year SET started providing more detailed breakdowns of spend as part of the quarterly reports. This has greatly improved transparency, and allows DFID to challenge any suspected high costs.

Assessment of whether the programme continues to represent value for money

SET continues to represent strong value for money. Costs and fee rates are highly competitive and SET continues to deliver and in most cases exceed logframe milestones. SET have fostered strong relationships, both within DFID and with partner country governments and we have convincing evidence that SET analysis and support in influencing policy and programming.

In the final year the challenge for SET will be to continue to strengthen these key relationships and demonstrate significant development impact as a result of their ongoing support. For example some cases of demonstrable policy change in LIC partner countries or examples where LIC policymakers have changed/augmented their analytical approach to policymaking and transformation.

Quality of financial management

The quality of quarterly financial reporting has been satisfactory, ODI has accounted for expenditure for quarterly spot checks. No financial issues have been raised during the year. Quarterly forecasting has been within under the 5% variance and invoices are submitted on time. While the quality of financial management has been good, next year, we will be looking for SET to demonstrate that they are pursuing continuous improvement, especially in relation to travel and dissemination events, as set out in DFID’s supplier review

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

As we move into the final year of the programme the main riskis around successfully leaving a lasting legacy, embedding stronger analytical capacity and approaches in LIC partner countries. We also need to ensure that remaining funds are used effectively and maintain the quality of reporting to help understand the impact SET is having on key stakeholders ability to deliver better policies and/or undertake stronger analysis.

The project fails to leave a lasting legacy after October 2018 (moderate risk/ major impact)

High priority should be given to SET’s work with the Government of Tanzania, which has received extensive support on its five year development plan. This is where we want to see SET leave a lasting legacy.

Quality of SET’s reports does not meet DFID expectations (moderate risk/ major impact)

The quality of reports produced this year has been good and we will continue to monitor. The SET Project Director should continue to quality assure and be held accountable for the quality of reporting.

SET fails to become a ‘centre of knowledge’ for economic transformation

The SET communications strategy needs to consider what will happen to website and the data portal when the project is due to finish in October 2018. As SET winds down this bank of knowledge and readily accessible database should not be lost.

Resources for April – October 2018 is used effectively.

The Management Committee meeting, to discuss the work plan should be held in January/February 2018 and agreed with the DFID Programme team by mid-March – before any work commences.
F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

SET is on track to deliver outputs and meet milestones within agreed timeframes. Given the high demand and limited resources for SET services, it will be important that the 18/19 work-plan is agreed with the DFID programme team. As we enter the final year of the programme, it is important that SET leaves a lasting legacy that demonstrates the programme clearly impacted LIC partner policymaking or approach to policy analysis.,

Performance of partnership

SET is receptive to DFID’s feedback and was a co-operative and constructive partner in helping us to amend the logframe. They worked well with us to reduce the annual budget and finalise the work-plan and budget for 2017/18. However, it was difficult to amend the workplan following the Management Committee Meeting. In part his reflected DFID’s late engagement on the workplan but we should ensure this does not happen again this year.

Asset monitoring and control

Not applicable

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The evidence that policy advice to governments and DFID will result in better investments in economic programmes remains medium. DFID will commission a short-term desk based evaluation in early 2018, to assess the impact of the programme.

Monitoring progress throughout the review period

SET and DFID meet quarterly to review quarterly reports and monitor progress against the annual work-plan. Progress is monitored by requesting feedback from the DFID country offices and DFID departments that receive SET support. The DFID programme management team regularly engage with recipients of SET services to check on quality and timeliness as well as peer reviewing a sample of SET outputs throughout the year.

In the next (and final) year, it will be important for ODI to track how outputs and outcomes are being used and what impact they are having, given the reliance on beneficiary feedback for this review.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process