Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: The Queen Elizabeth Diamond Jubilee Trust: UK Contribution
Programme Value: Up to £50 million matched funding		Review Date: December 2017
Programme Code: 203754	Start Date: 25 Nov 2013	End Date: 30 June 2019

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	A	B	A	A
Risk Rating	Moderate	Major	Minor	Minor

Summary of progress and lessons learnt since last review

This is the fourth annual review of DFID support to the Queen Elizabeth Diamond Jubilee Trust (the Trust), which was set up with the specific aim to tackle avoidable blinding diseases and strengthen and increase the capacity of eye health care systems across the Commonwealth. The Trust initiatives address: trachoma in Africa and the Pacific; diabetic retinopathy in India, Pakistan, Bangladesh, Caribbean and the Pacific; retinopathy of pre-maturity in India, and focuses on improving eye healthcare systems across the Commonwealth by strengthening knowledge, tools and people.

This year the Trust’s partners have been implementing the findings from the mid-term reviews conducted in 2016. As part of the Trust’s mission to be transparent and accountable, the Trust has produced public-facing versions of each of the evaluations and published them on its website.

The Trust has used its convening, advocacy and influencing role to increase the profile of avoidable blindness and secure support from partners and national governments. The Trust has also been working with partners in the eye health sector to create a ‘common platform’ that will feature at the Commonwealth Heads of Government meeting in April 2018.

The Board of Trustees approved an additional £1m to support a national school eye screening programme in Botswana using the mobile technology PEEK. Working in close partnership with the Government of Botswana, between 2017 and 2020, the programmes aims to deliver screening services to 500,000 children including treatment for 50,000 children, of whom 30,000 will benefit from being provided with glasses to correct their vision.

Summary of recommendations for the next year

The focus of the next year will be ensuring the programme is effectively completed, that the Trust ensures that the lessons learned are effectively captured and disseminated and that support is provided to help the Trusts key partners to transition to a post programme environment. Much has been delivered so far but its sustainability and legacy need to be assured and lessons and evidence need to be properly captured. The team have demonstrated the value of strong communications and adaptive programming to deliver results and it is important that these are not lost as the Trust closes its doors.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203754/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203754/documents

The Queen Elizabeth Diamond Jubilee Trust was formally established on 6 February 2012 under the chairmanship of the Rt. Honorary Sir John Major KG CH, former Prime Minister of the United Kingdom. It was set up to celebrate The Queen’s sixty year contribution, as Head of the Commonwealth and leave a lasting legacy through programmes on avoidable blindness and youth leadership across the Commonwealth.

DFID is providing up to £50 million in matched funding over 5 years (November 2013 to June 2019) to support the Trust’s avoidable blindness programme. International efforts are underway to eliminate the main causes of avoidable blindness worldwide, providing a unique moment to join and help progress the global Vision 2020 initiative (a joint programme of the World Health Organization and the International Agency for the Prevention of Blindness).

The Trust’s avoidable blindness programme comprises four initiatives:

Trachoma management in Africa (£41.4m) and the Pacific (£2m). This is managed through a partnership with members of the International Coalition for Trachoma Control (ICTC), including Sightsavers, working in 6 African countries; eliminate trachoma in Kenya, Malawi, Mozambique, Uganda and Zambia, and make significant progress towards elimination in Nigeria and Tanzania. Trachoma is a neglected tropical disease which affects the eyes, if left untreated, it can lead to blindness - 1.2 million people are irreversibly blind because of the disease[1]. Elimination of trachoma is possible through the adoption of the World Health Organisation’s SAFE strategy (Surgeries, Antibodies, Facial cleanliness and Environmental components). In the Pacific, the Trust it is working with ICTC and the Fred Hollows Foundation to, support elimination in four countries; Fiji, the Solomon Islands, Vanuatu and Kiribati (the Trust also supports work in Australia but not with DFID funds).
[1] 2017 QEDJT Annual Report

Diabetic retinopathy (DR). Diabetes increases the risk of many eye health problems, with DR predicted to become the leading cause of blindness as rates of diabetes reach epidemic levels globally[2]. The Trust is supporting a partnership between the London School of Hygiene and Tropical Medicine (£1.4m) and the Public Health Foundation of India (£2.6m) to improve prevention, detection and treatment of DR in India. The Trust is also supporting the London School of Hygiene and Tropical Medicine (£0.75m) to reduce DR in the Caribbean and the Fred Hollows Foundation to reduce rates of DR in Bangladesh, Pakistan and the Pacific (£1.65m).
[2] As above.

Retinopathy of prematurity (ROP). The major stream of this work is in India through a partnership with the London School of Hygiene and Tropical Medicine (£1.7m) and the Public Health Foundation India (£1.7m), who is working with federal and state governments to establish sustainable and scalable services that are integrated into India’s health system. The initiative covers supporting strategy, developing guidelines, training physicians, new patient record management and systems and the development and testing of more affordable equipment for ROP diagnosis.

Strengthening of knowledge, tools and people to improve eye health care across the Commonwealth managed by the International Centre for Eye Health (CEHC), hosted by the London School of Hygiene and Tropical Medicine (£11.4m). The Consortium supports fellowships to increase eye care expertise in low income Commonwealth countries, provides a knowledge platform to tap into expertise and facilitate learning and information exchange, and supports research and the development of technology to strengthen eye care throughout the Commonwealth.

In addition, the Trust has established The Queen’s Young Leaders Programme; delivered in partnership with Comic Relief, the Royal Commonwealth Society and the Institute of Continuing Education at the University of Cambridge. The programme honors inspirational young people each year for the life of the programme (youth working on a wide variety of important issues including tackling climate change, providing education for girls and improving maternal health) and awards grants to organisations in selected Commonwealth countries that can demonstrate that they are improving the lives of young people.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The evidence for this annual review reflects our assessment that the Trust is very firmly on track to achieve the outcomes agreed for the programme. The programme is well managed and kept under active review to ensure it is able to adapt and adjust to reflect on the ground realities.

Overall output score and description

A – Met expectations

Key lessons

The programme continues to benefit from a highly responsive and engaged management team and from forward leaning, positive and proactive adaptive management processes. The team is very strong in ensuring effective and open project communications – with project funders as well as project partners at all levels – and this has fostered a practical and pragmatic approach to problem solving that has served the project well. Challenges are met head on with a focus on the programmes outcomes and on managing towards solutions as reflected in the detailed output scoring sections below,

Key actions

As the programme begins to enter its final year the Trust should be looking to ensure the lessons of the programme are effectively captured and are disseminated widely (both through formal and informal mechanisms). As the Trust winds up at the beginning of 2020 it will be important that what it has developed is not lost as its on-line presence diminishes. The Trust will also want to help ensure the sustainability of the programme by supporting its partners to transition and graduate smoothly from the support they have been providing. The partnerships developed under the programme are an important part of its legacy.

Has the logframe been updated since the last review?

Yes, two indicators have been combined and updated to match the reporting used for another DFID programme.

Output Indicators 1.3 and 1.4

2016 Indicators:	1.3 Number of endemic districts where Facial cleanliness is implemented through effective behaviour change programmes.

1.4 Number of endemic districts where environmental improvement is implemented.

2017 indicator:	1.3 Number of endemic districts benefitting from behaviour change communication activities to increase facial cleanliness and environmental improvement

This new indicator has been provided by Sightsavers, the implementing partner and grant manager for the Trust’s Trachoma Initiative and the DFID SAFE Trachoma Programme. This new indicator captures the same data as the previous two indicators, and enables the outputs and impact of DFID’s trachoma portfolio to be more easily aggregated.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective implementation of selected elements of the SAFE (Surgery, Antibiotics, Facial Cleanliness, Environmental Improvements) strategy
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Percentage (%) reduction in Trachoma Trichiasis (TT) surgery backlog target	Expected reduction: 80% / Kenya 80% / Malawi 100% / Mozambique 80% / Nigeria 34% / Tanzania 92% / Uganda 90%	78% reduction in TT surgery. / Kenya 75% / Malawi 100% / Mozambique 86% / Nigeria 21% / Tanzania 87% / Uganda 90%
1.2 Percentage (%) of endemic districts achieving >80% coverage of mass drug administration (MDA) in the year.	Expected MDA coverage: / Kenya 100% / Malawi 100% / Pacific Islands 100%	Met expectation. / Kenya 50% / Malawi 100% / Pacific Islands 100%
1.3 Number of endemic districts benefitting from behaviour change communication activities to increase facial cleanliness and environmental improvement	Expected target: / Kenya 12 / Malawi 17 / Uganda 17	Met expectation. / Kenya 12 / Malawi 17 / Uganda 17 / Tanzania 8

Key Points

Africa
- The Trachoma Initiative is now operating in seven African countries. It is likely that Malawi will become the first Trust country to achieve its elimination goals, estimated to be sometime in 2018. The Trust also anticipates reaching elimination goals in Uganda and Zambia, and there is a likelihood that elimination goals will be reached in Mozambique by 2019.
- Malawi is already starting work on its dossier to submit to the World Health Organisation to obtain validation that they have eliminated trachoma as public health problem. The programme is working with countries to make sure they have the expertise and capacity to complete their dossiers. Most countries will submit their dossiers after the lifetime of the Trust.
- Since the start of the Initiative in April 2014, more than 74,000 Trichiasis surgery cases have been managed and more than 16.7 million doses of antibiotics have been distributed to 11.6 million people living in trachoma endemic areas.
- The programme has improved the quality of data on trachoma prevalence. Building upon the DFID-funded Global Trachoma Mapping Project, the programme has used standardised practices and mobile technology to build up a more accurate picture of the burden of trachoma in African countries.
- The progress to date, and new data, has enabled the Trachoma Initiative to expand to more states in Nigeria and to commence operations in Zambia, in coordination with the existing DFID SAFE programme in that country.
- Only two counties had mass drug administration in Kenya and so with one country in Western Kenya not achieving 80% the indicator achieves only 50%. The mass drug administration was hampered by severe drought and famine, migrating populations and politically instigated ethnic clashes and cattle rustling. The political instability on the last day of mass drug administration forced health workers from rural health facilities close the facilities to evacuate for safety. The situation, though volatile, is much calmer however no mop-up distribution was possible. Security personnel are consulted on a regular basis but it continues to affect outreach work. Results of recent and planned mass drug administrations conducted in Kenya and Malawi are expected in early 2018.
- For both Nigeria and Kenya, upcoming mass drug administrations are affected by delayed drug shipments from Pfizer. Hurricane Maria caused extensive damage in Puerto Rico, where Zithromax® tablets are manufactured in September 2017. One site experienced moderate damage to parts of the facility, and Pfizer is working to repair the facilities as soon as possible. This has meant that shipments have been impacted and the earliest expected shipment of Zithromax® will be February 2018. Currently Nigeria and Kenya have drugs in country for the next round of mass drug administration but Nigeria’s 3rd shipment of 2017 will be delayed. Sightsavers continues to monitor the situation.
- Through engaging with the other NGOs involved in water and sanitation activities the Malawi programme has seen NGOs outside of the Trust programme look to adopt community based materials about hygiene behaviours. This has helped to scale up facial washing and environmental improvement activities, going beyond the scope of the planned activities.
- The programme has developed a ‘transition checklist’ to enable Ministries of Health to ensure that capacity built during the Trachoma Initiative become embedded into health systems. The Initiative is working to capture learning around mobile health technology in order to inform other disease programmes.

Pacific
- Mass drug administration, targeting the whole population, has been completed in Kiribati. In Vanuatu and Solomon Islands, 6-month post mass drug administration impact surveys have been completed. These surveys will help identify what further actions are required to reach trachoma elimination goals in these countries. These surveys were completed using smartphones and Tropical Data – an app that has been developed with the support of the Trust’s Trachoma Initiative.
- Despite concerted efforts by the Fred Hollows Foundation and the Trust over 18 months, an agreement was not able to be signed with the Government of Fiji to implement mass drug administration. The Ministry of Health and Medical Services have confirmed that the mass drug administration will not proceed. The Trust is still supporting facial cleanliness and environmental improvement activities in Fiji. The funding available for the mass drug administration will now be reallocated to the Trust’s other avoidable blindness work in the Pacific, including support required for further rounds of mass drug administration in Kiribati.

Summary of responses to issues raised in previous annual reviews (where relevant)

2016 Annual Review Recommendation	Response/Action
Support the implementation of the recommendations from the mid-term review	Recommendations have been actioned by Sightsavers as grant manager. There is renewed focus on cross-border collaboration, improving the quality of surgery provided and ensuring that patients attend follow-up appointments.
Increase efforts/support in Nigeria to enable it to achieve the WHO GET2020 target. The mid-term review noted that Nigeria has one of the highest burdens of trachoma in the Commonwealth and will need concerted, sustained efforts over the next two years to meet the SAFE targets	The grant manager, Sightsavers, have spent considerable time in Nigeria working with the state government and the local implementing partner to improve programme outcomes. Outreach activities were suspended in November 2016 to allow time for in-depth planning and updating of the Trachoma Action Plan. Activities re-commenced in July 2017 and the surgery outreaches were a considerable improvement on previous work.
Focus on planning for the end of the project, its lasting legacy and sustainability of the programme. The Trust should have a clear idea of who will finish the job it has started on the trachoma initiative (looking to other donors).	The Trust has been working with Sightsavers and the ICTC to increase the profile of trachoma and raise more funds. This has included developing materials and messaging for CHOGM 2018 and helping to develop a funding proposal for the accompanying fund. / Sightsavers have developed a template for transition planning – moving trachoma surgeries from dedicated outreach services back into standard eye health care managed by the State. Initially, this will be used in Malawi, Mozambique and Tanzania.

Recommendations

The Trust should continue with the highly effective adaptive programming that has been a feature of the programme to date. The pragmatic and practical response to project challenges – for example the impact of last year’s Caribbean Hurricane season – has been a welcome feature of project delivery and provides an important focus for the monthly project meeting with the DFID programme team. The lessons learned in managing this adaptive programming model needs to be properly captured and highlighted in the Trusts reporting and legacy documentation.

The Trust should continue to work with its key partners on transition and legacy planning and in supporting the development of any post programme proposals for potential funding partners.

Output Title	Increase in the number of patients with sight threatening retinopathy treated in targeted Commonwealth countries
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of patients with diabetes screened for diabetic retinopathy annually.	Expected total: 46,900 patients	Exceeded expectation. / 69,902
2.2 Number of screened patients with diabetes treated for diabetic retinopathy annually.	Expected total: 6,170 patients	Exceeded expectation. / 6,516
2.3 At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system.	Public Health Foundation India (PHFI) - Operational guidelines for screening and treatment adopted by the government / FHF - Diabetic Retinopathy Coordinators recruited and employed in each country	Met expectation. / PHFI - Second draft of operational guidelines reviewed by Technical Expert Group and due for printing / FHF - DR Coordinators recruited and employed in each country / Bangladesh – A national DR taskforce, chaired by the Ministry of health, has been established

Key Points

India

- On 12 April 2017, the Indian Ministry of Foreign Affairs cancelled the Public Health Foundation India’s (PHFI) Foreign Contribution Regulation Act (FCRA) licence with immediate effect. This prevented PHFI from receiving or spending funds from any foreign donor. The Trust has set up an arrangement with the London School of Hygiene and Tropical Medicine who are able to transfer funds to state-level partner hospitals. This has ensured that programme delivery has continued and that patients continue to receive treatment.
- The Initiative is underway in 10 states across the country. Each month approximately 2,700 patients are screened for diabetic retinopathy and 100 received laser treatment.
- Successfully referring patients for follow-up appointments or detailed evaluations continues to be a challenge. Partners are working with health workers at the block (community) level to improve compliance with referrals.
- Public service advertisements on diabetic retinopathy have been produced in three languages, English, Hindi and Telugu. The advertisements raise awareness about the importance of patients with diabetes attending annual eye screening.
- Operational guidelines are being finalised that will codify the learnings from the Initiatives and will enable other states to replicate the Trust’s model.

Caribbean

- In March 2017 the Trust transferred management of the Caribbean Diabetic Retinopathy Initiative from the Caribbean Council for the Blind to the London School of Hygiene and Tropical Medicine. Each country is being integrated into the Diabetic Retinopathy Network, a network of hospital-based training links between overseas and UK partners that forms part of the Trust-funded Commonwealth Eye Health Consortium. Links have been formalised between Belize, Dominica and Brighton and Sussex Hospitals. It is anticipated that these links will be able to provide long-term support and advice for the partners beyond the lifetime of the Trust’s funding.
- The London School conducted a needs assessment of the four countries in July 2017 to meet local stakeholders, identify challenges and recommend priority actions. Progress among the countries has been mixed, and the limited pool of ophthalmic expertise in each country remains a challenge.
- In September 2017 Hurricane Maria caused catastrophic damage in Dominica. This is likely to significantly impact upon the Diabetic Retinopathy Initiative in that country.
- A workshop was held in Jamaica from 25 to 27 September to enable each country team to develop a detailed action plan and define the activities they will implement over the remaining two years of the Initiative.

Bangladesh and Pakistan

- The Countess of Wessex visited the Trust’s projects in Bangladesh in November 2017 to advance the Trust’s policy influencing agenda. The visit launched a task force of government and eye health sector representatives to strengthen and broaden access to diabetic retinopathy screening and treatment.
- In Bangladesh establishing effective referral systems has been a challenge. New referral slips, referral books and patient cards have been developed to improve tracking of referrals.
- In Pakistan 10 medical officers from primary level eye health facilities in Lahore were trained on using a funduscope for diabetic retinopathy. 18 Arc lights were provided to the medical officers. The concept of Arclight usage is still new in Pakistan, and training was provided to the medical officers.

The Pacific

- Diabetic Retinopathy Coordinators have now been recruited in all six countries involved in the Trust’s programme.
- 6 students from Fiji, Kiribati, Samoa and Solomon Islands completed their Postgraduate Certificate in Diabetic Eye Care and have returned to their home clinics. Fiji successfully completed the country-wide training of public health workers in diabetic retinopathy awareness.
- New equipment has been procured and is now being used by trained staff in eye clinics in Fiji, Kiribati and Vanuatu.

Summary of responses to issues raised in previous annual reviews (where relevant)

2016 Annual Review Recommendation	Response/Action
Support the implementation of the mid-term review recommendations	Key recommendations have been implemented. Task force meetings include more representation from government and the diabetes sector. Community health workers are being trained to increase the number of patients attending screening. Information materials have been developed and translated into local languages.
Create opportunities for cross-learning and communication between partner institutions so that knowledge transfer between States can happen	Meetings with the Health Secretary provided a common platform where partners came together to present briefly on the DR project activities in their respective areas. PHFI have constituted a state level project steering committee that has a comprehensive representation from Government officials from the partner states, partners, members from Taskforce, ophthalmologists and endocrinologists. The first meeting is tentatively scheduled early next year. This will set stage for cross-learning and knowledge transfer.
Undertake cost-benefit analysis as part of its exit strategy, to inform other donors/stakeholders of operational benefits in DR (and retinopathy of prematurity). Cost effectiveness data could also be a valuable input to decisions regarding scale up.	The Trust has commissioned PwC to conduct an economic analysis of the Trust’s programmes and the benefits of investing in avoidable blindness. The analysis will particularly focus on diabetic retinopathy. This analysis will help inform governments, as well as other donors, of the value of investing in diabetic retinopathy.

Recommendations

The delivery of the cost benefit work commissioned through PwC will be an important deliverable this year. It is welcome that they and QEDJT have been able to establish a strong steering committee and reference group. As the technical work is being undertaken QEDJT should develop the dissemination strategy for its findings to ensure it targets those making resource allocation decisions.

Output Title	Increase in the number of infants treated for retinopathy of prematurity (ROP)
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of infants screened for ROP in Special Newborn Care Units (SCNUs) in quality improvement programme area annually	Expected number screened: 6,360	Moderately short of expectation. / 5,777
3.2 Number of infants treated for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area annually	Expected number treated: / 260	Moderately short of expectation. / 166
3.3 At least two examples of how the Public Health Foundation of India (PHFI) have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system	Expected outputs: / Ministries of Health in non-Trust States issue advice that government neonatal care providers initiate ROP screening and treatment / State Ministries of Health issue documents advising that government eye care service providers initiate ROP screening and treatment of ROP	Met expectation. / Operational guidelines for prevention of blindness from ROP have been developed and are being shared with the Trust states and pilot units. / National Ministry of Health programme has included all components of the operational guidelines into National guidelines for prevention of childhood blindness.

Key Points

- As noted earlier, PHFI have not been able to receive or spend any foreign funds since April 2017. Routine screening and treatment of premature babies has continued uninterrupted throughout this period. The ROP Initiative is now being supported through the London School of Hygiene and Tropical Medicine. This transition did not cause any gap in services for patients and programme implementation is continuing.
- Screening and treatment of premature infants is now taking place in four states. Programme targets were based on five states working at full capacity. An agreement was unable to be signed with the government of Rajasthan, the fifth proposed state, before the ruling on PHFI’s foreign funds was made. The freeze on PHFI’s funds has significantly curtailed their advocacy and monitoring activities, making them unable to meet with state governments. A decision was made to focus efforts on the four current states where activities are underway. Learning from the unsuccessful experience with Rajasthan will help inform key findings for how to work effectively with state governments in India, such as identifying factors that will provide an enabling environment for collaboration.
- Since the start of the Initiative in 2015, 77% of infants recommended for laser treatment have received treatment. This figure is constantly reviewed and more counselling and information is being introduced for parents with infants in danger of ROP in order to increase this figure.
- To improve long-term sustainability, the ROP national task force is now being organized by a child health initiative from the Ministry health, called the RBSK https://rbsk.gov.in/RBSKLive/. RBSK is developing guidelines and an activity plan to expand the ROP services across all the states in a phased manner based on the learnings from the Trust supported pilot and other existing models in the country. The first draft of the plan was shared with Ministry of Health and other stakeholders by end of November 2017.
- Insufficient availability of ophthalmologists has provided a challenge in some areas. Ophthalmologists have been unable to attend trainings due to high existing clinical workloads. The Initiative is working with partner hospitals to identify suitable mentor institutions and fit training around ophthalmologists’ busy schedules.

Summary of responses to issues raised in previous annual reviews (where relevant)

2016 Annual Review Recommendation	Response/Action
Support the implementation of the mid-term review recommendations	Key recommendations have been implemented, including: working with the national taskforce, piloting educational materials and working with the Ministry of Health’s national initiative on childhood health.
Exploring new strategies with State Governments to address the limited availability of ophthalmologists at the district level	The Trust’s partners in India are planning to implement a neonatal care team led retinopathy of prematurity screening model using wide angle retinal imaging systems to address this issue at the district level in few districts in the state of Madhya Pradesh.

Recommendations

The Trust should look to ensure that the lessons learned through the programme are effectively captured in the work of the ROP national task force as its activity plan to expand ROP service are developed.

Output Title	Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools
Output number per LF		4	Output Score	A+
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Number of health care professionals trained	Expected results: 70 / Clinical Fellowships: 55 / MSc students: 15	Exceeded expectation. / Results: 111 / Clinical Fellowships: 98 / MSc students: 13
4.2 Number of countries with domestic institutions that have agreed and implemented national frameworks for diabetic retinopathy screening and treatment	Expected results: / 4 countries agree national DR framework / 2 countries establishing their DR framework / 2 countries working towards national DR framework	Exceeded expectation. / 9 countries agreed national DR framework. / 3 countries with DR framework in place.
4.3 New eye care technologies developed	Expected results: / Public release of Peek Retina (smartphone attachment) / Community trial for Peek screening underway	Met expectation. / Peek Retina (smartphone attachment) was publically released in April 2017 and community trial for Peek screening is underway. Preparations for Botswana school screening trial is also underway.

Key Points

- In June 2017, the Board of Trustees approved funding for Peek, through the Commonwealth Eye Health Consortium, to conduct a national school eye health service in Botswana. In October 2017, the Trust’s Chief Executive travelled to Botswana to finalise agreements with the Government of Botswana. Running up until 2020, this strategy will deliver screening services to 500,000 children including treatment for 50,000 children, of whom 30,000 will benefit from being provided with glasses to correct their vision.
- Massive open online courses on eye care continue to be developed and delivered. In the next few months, courses will be run on diabetic eye disease, eliminating trachoma, global blindness, and ophthalmic epidemiology. Close to 14,000 participants across the courses from over 140 countries have been involved in the courses.
- New team training networks have been developed for retinoblastoma and retinopathy of prematurity. The Retinoblastoma Network involves seven institutions in Kenya, Tanzania and Uganda partnered with four institutions in India and the UK - LV Prasad Eye Institute in Hyderabad, Sankara Netralaya in Chennai, the Royal London and Birmingham. In June a workshop was held in Hyderabad with 64 attendees including ophthalmologists, paediatricians, oncologists, pathologists, nurses and Ministry of Health officials. The first planning meeting for the Retinopathy of Prematurity Network was held in London in September.
- The clinical fellowship programme continues to provide 3-month and 12-month subspecialty training for ophthalmologists from 19 Commonwealth countries. A Mentorship Programme has been developed for overseas ophthalmologists who have completed their fellowships. Mentors will assist fellows with the challenges of implementing their training and establishing subspecialty services in their home institutions.

Summary of responses to issues raised in previous annual reviews (where relevant)

2016 Annual Review Recommendation	Response/Action
Support the implementation of the mid-term review recommendations	The Consortium has implemented key recommendations from the mid-term review including: a targeted approach to promoting scholarship opportunities in each Commonwealth region, maintaining strong links with graduates, providing accreditation for online courses, and working with regional colleges to develop research capacity.
Reviewing programme monitoring and evaluation tools to ensure they capture the impact of returning health care professionals on service delivery, and the impact of DR-Net LINKS services	The Consortium has periodically reviewed and updated the tools they use for capturing the impact of the training that returning health professionals have. These have all been reviewed since the mid-term evaluation and updated where needed. In addition to this, the PhD research fellows are enrolled at the LSHTM which has a highly structured system for monitoring the progress of students.

Recommendations

The Trust will want to continue the support, advice and access it has been to offer for the development of Peek’s forward, and post programme, strategic planning and development and to ensure the lessons learned from supporting innovation are well captured in the material it develops to capture its success.

Output Title	A robust, responsive and supportive Trust
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
5.1 Unqualified audit of accounts received and annual results reporting aligned to common indicators presented in a manner consistent with results-based management principles	Expected results: / Compliant accounts and reporting. Clear lines of communication.	Met expectation. / Thorough good clean audit. The Trust’s 2017 Annual report and accounts for year ending 30 June 2017 have been approved by the Board of Trustees, and will be countersigned by the Trust’s Chairman in January 2018.
5.2 Proportion of grantees satisfied by implementation and value added by the Trust	90% positive grantee responses to satisfaction question included in reporting to the Trust	Exceeded expectation. / 100% positive grantee responses to satisfaction question included in reporting to the Trust.
5.3 Development of monitoring indicators and evaluation reports showing capacity building and lessons learned	Expected results: / Mid-term evaluations completed	Met expectation. / Mid-term evaluations were completed in 2016 and the Trust is now in the process of implementing the findings/recommendations. / Summaries of the mid-term evaluations were published on Trust's website.
5.4 At least two examples of how the Trust has influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes	Avoidable blindness to be included for the Commonwealth Health Ministers meeting 2017 / The Trust contributes to a side event at the World Health Assembly 2017	Exceeded expectation. / Avoidable blindness was included in the Commonwealth Health Ministers meeting 2017 / The Trust contributed to a side event at the World Health Assembly 2017 on avoidable blindness / The Trust funded a brief on avoidable blindness in the Commonwealth, conducted in coordination with the Commonwealth Secretariat / The Trust has formed a coalition of eye health organisations (A Vision for the Commonwealth) to effectively lobby on issues related to blindness at CHOGM 2018

Key Points

- At the Commonwealth Health Ministers’ Meeting in Geneva in May 2017, avoidable blindness was on the agenda; the Trust presented a short video about its programmes across the Commonwealth and the results achieved. The delegations of Malawi and Australia and the Commonwealth Secretary General spoke in support.
- The Trust contributed to a side event on avoidable blindness at the World Health Assembly on 25 May 2017. The event was well attended with at least 24 delegations present – some one hundred people. The delegation of Malta, as Commonwealth chair in office, presented the Commonwealth Secretariat brief “A sustainable approach to control avoidable blindness and vision loss”. The Trust had funded the short placement in the Commonwealth Secretariat Health Unit of a Nigerian ophthalmologist to compile this brief. She was supported by a cross Commonwealth group of experts. The brief is available on the Commonwealth Secretariat’s website at this link: http://thecommonwealth.org/sites/default/files/events/documents/PolicyBrief-ASustainableApproachControlAvoidableBlindnessVisionLoss.pdf
- The Trust’s senior staff continue to use the opportunities presented by in-country events and monitoring visits to engage with Government representatives to this end. Examples this year include the Chief Executive’s visit to Uganda in June to mark the expansion of the trachoma programme to the whole of Uganda; a monitoring visit to Trust diabetic retinopathy and retinopathy of prematurity programmes in India.
- In Commonwealth Week in March 2017 the Trust’s Vice-Patron, HRH The Countess of Wessex, visited Trust programmes in Malawi, accompanied by the Minister of Health. The visit celebrated Malawi’s rapid and successful progress towards the elimination of blinding trachoma. It aimed to strengthen collaboration between the many organisations involved, to encourage continued efforts to reach full elimination, and to set an example to other countries in the Trachoma Initiative working towards elimination. Trachoma elimination in Malawi, including an interview with The Countess, was the subject of a BBC TV film, shown during the BBC’s coverage of the Commonwealth Observance at Westminster Abbey on Commonwealth Day.
- In November 2017 The Countess is due to visit the Trust’s diabetic retinopathy (DR) programme in Bangladesh. This will be an opportunity to highlight how the programme is reaching very poor people and to present the benefits of a sustainable, integrated model of care, supporting advocacy efforts underway by a group of INGOs in Bangladesh to strengthen DR services across the country with Government leadership.
- An important part of the Trust’s advocacy is to highlight and celebrate positive steps taken by Governments to end avoidable blindness, to increase engagement and as examples for others to follow. A particular milestone this year is the Government of Botswana’s initiative with Peek Vision to provide universal eyesight screening for all schoolchildren and teachers across the whole country: a first for any country. The Trust will attend an event to mark the initiative and will feature it as a positive example in its communications in the run up to CHOGM 2018.
- The Trust has convened and is leading a coalition of eye health organisations with a common platform for CHOGM 2018. This coalition, Vision for the Commonwealth, is advocating for the ending of avoidable blindness and vision loss to be part of CHOGM 2018. It is lobbying Commonwealth governments and raising awareness through coordinated communications activities.

Summary of responses to issues raised in previous annual reviews (where relevant)

There were no specific recommendations for the Trust.

Recommendations

The Trust should continue to provide the invaluable convening and advisory support it has offered to the coalition of eye health organisations but with a view to ensuring they are able to exit effectively as the project starts to wind down.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The Trust does not directly implement programmes itself, but contracts delivery partners to deliver programmes and services. Partners and grantees were sought strategically according to experience, capacity to deliver on a value for money basis (rather than by open competition, which would be time consuming and transaction-heavy).

The main cost drivers for the programme are: human resource and logistics costs incurred through implementing partners. These vary by initiative and the delivery channel (for example, clinic-based services or outreach teams). Pharmaceutical costs for prevention of trachoma are met by the International Coalition for Trachoma Control. Costs for surgical equipment, training materials, and diagnosis of diabetic retinopathy and retinopathy of prematurity vary by country programme.

VfM performance compared to the original VfM proposition in the business case

Value for money (VfM) is well understood amongst the Trust’s implementing partners. Sightsavers has developed a VfM strategy that looks at cost per case managed, cost per mass drug administration treatment and implementation, and is integral to everything they do on the Trust’s trachoma initiatives (and the DFID SAFE programme). Close attention is paid to volume, schedule, cost and quality and a visual dashboard focusing on key metrics enables project managers to identify trends in the delivery of project objectives and in the unit costs of achieving these objectives.

Assessment of whether the programme continues to represent VfM

The Trust has met or exceeded the expected output results and is therefore offering good value for money for our contribution. The DFID business case noted that 15 successful retinopathy of prematurity interventions would be required for the programme to break even – this figure has already been exceeded.

The Trust has also commissioned PriceWaterhouseCoopers (September 2017) to conduct an analysis of the economic and social impacts of the Trust’s avoidable blindness programmes. This analysis is intended to examine the return on investment for eye health services in the Commonwealth using data from the Trust’s initiatives and will be presented to Leaders at the Commonwealth Heads of Government meeting in April 2018.

Quality of financial management

The Trust is governed by a Board of Trustees who set the Trust’s strategic direction and approves all operational and financial plans. The Audit Committee is a sub-committee of the Board of Trustees and is comprised of two Trustees, the Chief Executive and four external advisory members.
The Audit Committee meets up to three times a year to consider matters relating to financial control, organisational effectiveness and risk management, reporting to the Trustees accordingly.

The spend profile for 2017/18 was £10m, paid in two six-monthly disbursements; £5m in April 2017 and £5m in October 2017. Last year, DFID worked with the Trust to improve the quality of financial reporting; the Trust is required to supply a certified letter with any payment request setting out the detailed actual expenditure to date (committed and spent), a forecast of funds to be disbursed or committed during the next 6 months, a statement supporting new funding raised (to which DFID will view as eligible to match) and an explanation (if any) of the disparity between the forecast commitments and disbursements and funding already held by the Trust.

All of DFID’s funding is restricted to ODA eligible activities and the Trust maintains a separate bank account for DFID funds to ensure that this funding is accounted for separately. The Trust also provided downstream delivery chain mapping through to the level of the implementing partner for each of its initiatives as part of the 2017 due diligence exercise undertaken by DFID[3]. This shows the flow of funds through The Trust and provides visibility on the number of downstream partners and the contract value of the work they are delivering on behalf of The Trust.
[3] DFID Due Diligence Assessment Refresh – August 2017 [internal use - Vault ID – 15423355]

The Trust’s Auditors (Crowe Clark Whitehill LLP) gave a clean audit opinion for the financial period 1 July 2016 to 30 June 2017 and confirmed that there had been no evidence of any financial risk or fraud. The Trust’s 2017 Annual Report and Audited Financial Statements will be published on the website in January 2018, once it has been countersigned by the Trust’s Chairman.

Date of last narrative financial report	15 September 2017 (certified financial letter from the Trust)
Date of last audited annual statement	Audited up to year ending 30 June 2017

E: RISK (½ page)

Overall risk rating: MINOR

DFID conducted a due diligence assessment of the Trust in August 2017[4]; which was a refresh of the previous due diligence exercise carried in October 2013. Due diligence is one of the key tools in DFID’s overall risk management framework to help identify and manage risks, and obtain a sufficient level of assurance of an implementing partner’s internal control framework, capacity and capability to deliver DFID programmes prior to entering into a formal agreement.
[4] DFID Due Diligence Assessment Refresh – August 2017 [internal use - Vault ID – 15423355]

The purpose of the due diligence refresh was to assess the continuing capacity and capability of the Trust and identify any changes/risks which could have an adverse effect on programme implementation or DFID’s relationship. Overall, the Trust is assessed as being a minor risk, being in its fourth year of programme implementation. Assessment against each individual due diligence category is shown below:

- Governance and Internal Controls – Minor
- Ability to Deliver – Minor
- Financial Stability – Minor
- Downstream Partners – Minor

Overview of programme risk

Day-to-day risk management processes are embedded across The Trust through effective implementation of policies and procedures. A central risk register is maintained at a corporate level, and each individual programme and initiative has its own risk register. The corporate risk register is reviewed and updated monthly by the Trust’s Executive Team and it is shared with the Audit Committee. The Board of Trustees formally reviews it and approves it annually. All grantees are required to have their own policies on risk management which are included in their grant agreements. The Trust has conducted due diligence assessments on all grantees.

Outstanding actions from risk assessment

Most of the risks identified in the DFID Business Case and the first Due Diligence Assessment (October 2013) were linked to The Trust being a new entity and therefore no track record of delivery and programme/financial management. These risks have now reduced/been mitigated, having been in operation for four years; The Trust no longer falls into the ‘new’ bracket. The mid-term reviews of each of the programmes[5], state that they are on track to meet or exceed all initiative targets.
[5] QEDJT Mid-term Evaluation Reports http://www.jubileetribute.org/publications

With the programme due to be completed in June 2019 and The Trust due to be wound up soon after, the main recommendation from the due diligence refresh assessment is ensuring that the Trust prepares appropriate exit strategies to build programme sustainability and leave a lasting legacy.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The Trust’s programmes are all underway, delivering results and on track to deliver intended outcomes as reported in the Trust’s 2016/17 Annual Report[6] and the mid-term Evaluation Reports for each of the initiatives[7]. Progress Reports from grantees are delivered in a timely manner to the Trust and to the expected standard of performance and financial reporting.
[6] 2017 QEDJT Annual Report
[7] Same as footnote no.5 above.

Performance of partnership (s)

Feedback from central and country level implementing partners, and reports from national symposia, taskforces and launches, suggest that excellent partnerships have been established for each initiative and within each country. The Scientific Advisory Group provides an excellent complementary specialist resource that has helped build the relationships with key Commonwealth eye health organisations.

The partnership between the Trust and DFID is delivered through a formal process of monthly programming meetings with day to day contact as needed. DFID are represented on the Scientific Advisory Group and in the steering group for the cost-benefit analysis work on diabetic retinopathy and the retinopathy of prematurity.

Asset monitoring and control

Not applicable.

G: CONDITIONALITY (½ page)

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In 2016 mid-term reviews were conducted on all four of the Trust’s main avoidable blindness initiatives. In 2017, as part of its commitment to transparency, the Trust worked with the evaluators and coordinating partners to create public-facing summaries of each review. These summaries provide an overview to a non-technical audience and show clearly the accomplishments that have been achieved and the challenges that are being addressed. The summaries are hosted on the ‘Publications’ page of the Trust’s website: http://www.jubileetribute.org/publications

The Trust has commissioned PwC to conduct an analysis of the economic and social impacts of the Trust’s avoidable blindness programmes. The analysis is intended to examine the return on investment for eye health services in the Commonwealth using data from the Trust’s initiatives (as well as other sources). The analysis will focus on diabetic retinopathy, which is likely to be an increasing cause of blindness in the Commonwealth in the near future. The analysis will be utilised as part of the Trust’s wider advocacy strategy at CHOGM in April 2018, providing evidence and statistics to back up the Trust’s communications materials and other activities.

Monitoring progress throughout the review period

As The Trust will be primarily working through partners, rather than running programmes themselves, they are responsible for ascertaining capacity and capability of those relevant actors. They have highlighted this in their grant procedures guide and have drawn up a grantee assessment process compatible with DFID’s monitoring and evaluation requirements. Partners for the main avoidable blindness initiatives have monthly calls with the Trust’s programmes team and submit monthly written reports. Partners also submit detailed narrative and financial reports every six months, which provide feedback on the implementing partners’ relationship with the Trust and any suggestions on how the Trust can increase the impact of the avoidable blindness programmes.

DFID officials have monthly programme meetings with the Trust to discuss programme and financial management issues (including progress against the logframe and review of risks). In addition, DFID participates in the Trust’s Scientific Advisory Board, which meets twice a year (in May and October 2017). At the May 2017 meeting, Professor Matthew Burton, Professor of International Eye Health at the London School of Hygiene and Tropical Medicine, presented to the Board on the status of the Commonwealth Eye Health Consortium. At the November 2017 meeting, Dr Andrew Bastawrous, Co-founder and CEO of Peek Vision, presented on Peek’s strategy and how smartphone technology can be used to improve eye health systems.

Annual review process

This was a desk-based review undertaken by the DFID Commonwealth Senior Responsible Owner with inputs from the DFID Deputy Programme Manager and the Trust Programme Manager. It was informed by regular project monitoring meetings and participation, alongside project delivery partners, in the Scientific Advisory Group and in discussion with members of the Commonwealth eye health platform as they’ve developed their proposals for the Commonwealth Heads of Government Meeting in April 2018.