Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: New Alliance (ICT) Agriculture Extension Challenge Fund
Programme Value: £2,800,000		Review Date: 1 September 2017
Programme Code: 204423	Start Date: 12 August 2014 (date agreement signed)	End Date: 31 March 2018

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	A	A	B
Risk Rating	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

Current agriculture systems and policies are not meeting global food demands and not supporting agriculture to reach its full potential in contributing to economic growth and poverty reduction, especially in sub-Saharan Africa (SSA). For agriculture to increase its productivity and meet sub-Saharan Africa’s food demands, new approaches are required for developing technologies and even more important to get these into the hands of farmers.

Easy and timely access to information, knowledge and technologies is one of the key elements of agricultural innovation. Yet too few farmers and public and private advisory agents can easily access all information they need. In SSA, public funded agriculture advisory systems have generally been characterised by inefficiency and have a poor track record of delivery.

ICT offers great potential to address some of the problems of inefficient agriculture advisory systems because of the great improvements worldwide in affordable and accessible telecom services. Sub-Saharan Africa accounts for nearly a tenth of the global mobile subscriber base and is expected to grow faster than every other region over the next five years. Over the past years, there have been several efforts to design and implement ICT- enabled advisory services by NGOs, businesses, governments and public-private partnerships. Most of these have not yet gone to scale and tend to focus on one particular type of ICT such as mobile phone based messages or low-cost video. As a result, there is increased interest in looking at ways to combine various ICT-enabled channels to support more effective information delivery and exchange. Doing this would involve using a wider range of communication channels best suited to different target audiences, and packaging information in various ways depending on content, purpose and audience. Despite the wide potential of integrated ICT enabled services, limited evidence exists of the effectiveness of such services.

The aim of the New Alliance Information and Communication Technologies (ICT) Agriculture Extension Challenge Fund is to develop and scale up the delivery of agriculture extension services in sub-Saharan Africa using sustainable information and communication technologies (e.g. radio, mobile services, video and web-based applications). It aims to reach 3 million smallholders with extension services through ICT and to improve the knowledge and farming practices of 1 million of those farmers and, in turn, generate improvement in their agricultural productivity and food security. As well as reaching poor people with new agricultural technologies and getting smallholders to take up new technologies such as better fertilisers, the programme will conduct an evaluation to provide evidence on the effectiveness of different ICTs and their impact on extension services.

The programme does this by providing six grants in six sub-Saharan African countries: Ethiopia, Ghana, Malawi, Mozambique, Senegal and Tanzania. The project is one of the commitments of the New Alliance for Food Security and Nutrition (NAFSN). The NAFSN was launched at the G8 summit in 2012 and aims to reduce poverty for 50 million people over the next ten years by increasing private investment and boosting agriculture-led growth in the nine NA countries. The grants are awarded to consortia of organisations, led by an ICT company or NGO (e.g. Catholic Relief Services or Farm Radio International), working with public agriculture extension officers to provide information to farmers on agricultural techniques and products such as new seeds and fertilisers. The services include a range of digital applications – radio, video, text messages – for extension agents and farmers.

The programme is delivered by the United States Agency for International Development (USAID). The UK is providing £2,800,000 over four years. The total fund is $12m over four years. The other donors are USAID (U$ 3 million plus U$ 1.6m in kind for managing the fund and grantees); the Bill and Melinda Gates Foundation (BMGF) (U$ 3m) and the International Fund for Agricultural Development (IFAD) (U$ 1.5 million). Grants are fully operational in all six countries.

Though the programme has made moderate progress on achieving its milestones for 2017, the programmes scores a B because of a number of issues with the programme this year. Due to the reporting cycle of USAID and the Monitoring and Learning contractor, data for numbers reached is only available to September 2016, with data for the last year due in October 2017. It is therefore only possible to report that the programme has reached an estimated 2,040,000 smallholders with ICT-enabled extension services. Other issues with the programme, which are expected to be overcome in the coming year include:-

- delays to the implementation of the evaluation (which is now underway)
- agreeing the ownership of the Intellectual Property of the content generated by the service, which is an urgent priority; and
- lack of evidence about the robustness of the methodology for the existing data (which DFID are reviewing with USAID and with the newly appointed evaluation team)

The programme operates in a challenging environment, for example, inefficient agricultural input markets for seeds and fertilisers, as well as in countries facing political and civil unrest, which are constraining the ability of the programme to go to scale. Mitigating actions are being taken by grantees e.g. the grantee in Ethiopia redistributed its activities to stable regions, in coordination with the public extension system. As originally designed, this project was expected to act as an accelerator – providing service providers with incentives to improve and scale up some of their existing services – but there is clearly variability amongst the capacity of the grantees to deal with the contextual circumstances of ensuring demand for new technology is met by supply.

With the data collection for the past year unavailable for this years, review, it is not possible to analyse the differences in the quality of reporting between the grantees. A recent workshop held by USAID with grantees has sought to agree timelines and standards for data reporting. Together with the start of the independent evaluation, this should further help to reduce previous disparities between the grantees on data reporting and reach a greater level of harmonisation across the grantees in terms of reporting.

Partnerships with public/private partners and Civil Society Organisations to develop and deliver agro-advisory services have been critical to the implementation of the services, particularly where the grantees are providing convincing data for policy makers that the intervention can reach smallholders farmers in a beneficial way. Strong local partnerships also help to develop the best, localised content for the services, tailored to farmers’ needs, that articulates their preferences for different ICT services (e.g. radio versus text messages) and is presented in local languages.

National governments who are partners of the project need to take note of the regulatory or policy barriers to the uptake of new technologies. One of the projects in Malawi also had to deal with an outbreak of fall armyworm (FAW). The grantee has worked with the Ministry to work towards including information about FAW in their mobile phone extension service.

Lessons Learned:

Reaching women has been a particular challenge. Grantees have had to be very deliberate in their targeting of women and tailor their implementation approaches across the various country contexts accordingly. For example in Mozambique, the implementing organisation has found that women farmers listen to radio programming at different times of the day to men, so the implementer has planned repeat broadcasts in order to reach women. Existing levels of extension support has a bearing on how well the programmes are reaching women, with some extension services e.g. in Ethiopia better developed through a public system.

Data collection and reporting remain challenging. Grantees and sub-grantees have varying levels of capacity for collecting and using quality data to inform learning. Following a competitive procurement process, DFID awarded a contract to Landell Mills in August 2017 to conduct an independent external evaluation of the programme, including its impact on agricultural productivity, land under cultivation, and behavioural change, particularly opportunities afforded to women smallholders.

The external evaluation contract presents an opportunity for the grantees to work with Landell Mills, and with the existing Monitoring and Learning provider (appointed by USAID), to explore ways to improve the robustness of data collected by the programme. This should be considered alongside a review of some of the differences in the context faced the grantees. One of the strengths of Landell Mill’s approach to the evaluation was the insights into the differing contexts and the ability of grantees to deal with challenges such as inefficient agricultural input markets. In providing smallholders with better information about agricultural practices and technology, this leads to more informed, effective demand, but the programme is not able to ensure that this is met by supply. The programme therefore needs to capitalise on the partnerships established at local level to further overcome these challenges.

Recommendations from last year:

#1 In Ghana and Malawi, the country grantees should continue to build on opportunities for synergy with the DFID funded mNutrition programme which focuses on promoting behaviour change through mobile phone based services. There is also an opportunity to share lessons with the mNutrition programme on how to achieve financial sustainability. DFID should facilitate contact between Groupe Spéciale Mobile Association (GSMA), USAID and country offices to ensure that a working relationship is established by end of October 2016.

Progress: In Malawi, the New Alliance ICT Challenge Fund Project and the mNutrition project established a working relationship in 2016. Both projects worked closely with the Scaling Seeds and Technologies Partnership in Africa (SSTP) (a $47 million partnership between USAID and the Alliance for a Green Revolution in Africa (AGRA)) on content development. The coordination with the mNutrition project allowed key nutrition experts to help develop the SSTP nutrition messages and the Malawi New Alliance ICT Challenge Project manager became a member of the mNutrition content review team. This working relationship enabled the two projects to share experiences thus improving on previous ICT extension service delivery. The Ghana New Alliance ICT Challenge grant concluded in January 2017.

#2 USAID should reinforce to grantees the importance of timely and consistent reporting of data. Where grantees are unable to provide information, USAID should insist upon a plan of action to address late reporting and withhold or withdraw payments if necessary. This should be undertaken on a case by case basis and reported on in the monthly meetings with DFID.

Progress: USAID has recently assembled an expanded team of managers and advisors with expertise across agricultural extension, ICT, scaling, and monitoring and evaluation to quickly and smoothly provide grantee oversight and support. This team has reviewed the implementation and monitoring and learning plans across all of the grantees and is working closely with the Monitoring and Learning provider to strengthen grantees' capacity for quality data collection and monitoring. In the upcoming months, the team will engage more closely with the Monitoring and Learning provider to build on the monitoring and learning activities of the past year. These activities focused on helping grantees to (1) capture both the breadth of access to information provided through ICT enabled extension and (2) provide learning about the comparative effectiveness of different ICT-enabled approaches.

USAID and the Monitoring and Learning provider have discussed previous challenges with grantees in reporting and prioritised a systematic approach to supporting grantees in effective annual indicator reporting. This year’s learning event with all six grantees in Tanzania in July 2017 included a day dedicated to data collection practices and plans, monitoring techniques as well as a discussion of the challenges grantees face in collecting and reporting quality data. During the event, grantees developed data collection plans and made commitments to adhere to data quality standards. They also committed to a data reporting timeline for this year. The Monitoring and Learning provider also had one on one meetings with each grantee to discuss their data collection plan and challenges in order to ensure they can meet their data reporting deadline this year. There was also an interactive session to review data quality assessments and standards with grantees. Until the data is available in October, it is not possible for DFID to state whether this has led to improved reporting.

#3 USAID should produce a plan to ensure that the projects are gender sensitive and that grantees are effectively targeting women. Additionally, there needs to be a much stronger emphasis on disaggregating the data by gender and figures need to be reported before the end of the calendar year to demonstrate evidence that this information is being collected and communicated. The M&L contractor needs to demonstrate how each grantee is doing this in the quarterly report due in December 2016. A workshop should be arranged with project partners to focus on this issue. This should be held before December 2016.

Progress: Last year USAID guided the Monitoring and Learning provider through the development of a gender plan. They have since conducted various activities related to gender and how to improve the gender sensitivity of grantee projects. These activities included a virtual learning event focused on gender as well as a gender session at last year’s face to face event held in Addis Ababa.

#4 A formal but light-touch lessons learnt exercise should be conducted so that all the donors and grantees can make improvements to the monitoring and implementation of the programme and that everyone is aware of roles and responsibilities, particularly around timely reporting from the grantees. This should be completed by February 2017.

Progress: The programme hosted a webinar on January 27, 2017 geared towards a review of lessons learned the year before. During the event, the Monitoring and Learning team also provided a recap on data collection expectations and provided the grantees an opportunity to ask questions about their projects.

Summary of recommendations for the next year

#1 As the annual data for 2018 will not be available until October 2018, DFID should seek approval to change the Annual Review date to 31st October, so that next year’s review has access to the data and time to review the quality of the data with the independent evaluation team. This will enable a fairer and more transparent analysis of the programme in 2018.

#2 The logframe target for indicators 1.2 should be removed as grantees are not reporting on this indicator. This was agreed after discussion between grantees and USAID about which indicators were most appropriate. 1.3 should be amended to ‘number of farmers who have applied a new technology or farming practice’.

#3 USAID should develop a lessons learned paper on the key regulatory and policy barriers to the successful uptake of new technologies, to help national governments and donors better understand the failures in the supply side once farmers are equipped with better information. Though these barriers are unlike to be overcome during the course of the programme, it is an important set of lessons for the programme’s public and private partners in the provision of future extension services. This could include how to responding to outbreaks of pests and diseases e.g. FAW and how to co-ordinate with key donors and international organisations. The programme can also draw on lessons from other similar programmes such as the mNutrition programme. USAID should agree with DFID the best approach to commission this paper by end of December 2017.

#4 There have been discussions with DFID’s Research and Evidence Division about intellectual property (IP), but it currently unclear who ‘owns’ the content and whether it is publicly available for this programme. As an urgent priority, DFID should work with USAID to agree the legal ownership of the data and confirm that it is publicly available after an agreed period of time. There are lessons to be learned from the mNutrition programme on this issue, where the IP rights have been agreed. DFID should arrange a discussion with USAID with a view to getting agreement by end of December 2017.

#5 USAID should work with grantees to share more information about the types of content that work best through different ICT channels, and present this to national ministries as a way to promote the innovation of the programme. USAID should work with the newly appointed External Evaluation team and agree a plan with the Monitoring and Learning provider by December 2017.

#6 Landell Mills have been awarded a contract to conduct the external evaluation component of this programme. DFID need to closely monitor the progress of the external evaluation against the agreed timetable and outputs of the evaluation, and ensure that the governance and management arrangements are clarified so that problems can be dealt with quickly. DFID will host an introductory meeting with the supplier in September 2017 and will agree the management and governance arrangements. In the interim, DFID will liaise with the other three donors to agree arrangements for a multi-donor ‘review group’ for the review of evaluation outputs. A DFID Evaluation Adviser will be a member of that group to assist with Quality Assurance; inception, mid-term and final reports will the quality assured by DFID’s Evaluation Quality Assurance and Learning Service (EQUALS).

#7 The independent evaluation team should prioritise an analysis of the quality of the gender disaggregation of date being provided by the grantees, to understand the impact of the programme’s interventions on women farmers. DFID should highlight this in the meetings with the independent evaluation team and followed up as a priority issue over the course of the evaluation.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204423/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204423/documents

DFID is providing £2.8m over four years to support the New Alliance ICT Agriculture Extension Challenge Fund.

The project aims to get technology to poor people and evaluate the effectiveness of different ICTs for use in agricultural extension.

The project will improve extension services delivered by public and private sector providers (state-funded extension services and NGOs/commercial enterprises providing ICT-enabled support) for three million smallholder farmers, farmer organisations and agribusinesses. By utilising the potential of information and communications technologies (ICT), the project will help farmers and agribusinesses make informed decisions about farm management, enhancing their food security. In line with UK government’s commitment to supporting ICT-enabled innovation, UK funding will take to scale existing initiatives and generate high quality evidence on the effectiveness of ICT-enabled agricultural extension services in increasing the adoption of improved agricultural technologies.

It will operate in six New Alliance (NA) countries, Ethiopia, Ghana, Malawi, Mozambique, Senegal and Tanzania. The project is one of the commitments of the New Alliance for Food Security and Nutrition (NAFSN). The NAFSN was launched at the G8 summit in 2012 and aims to reduce poverty for 50 million people over the next ten years by increasing private investment and boosting agriculture-led growth in the nine NA countries.

The project is financially supported by Bill and Melinda Gates Foundation (BMGF), DFID, the International Fund for Agricultural Development (IFAD) and USAID, who have jointly formed a Steering Committee to oversee project implementation. The total fund of U$12 million will be channelled through and managed by USAID. By engaging through the fund, DFID will be able to do three things that it would be unable to achieve on its own:

- Access other ICT Agriculture Extension Challenge Fund Steering Committee members’ wider portfolio of improving technologies’ uptake through improved agricultural extension services;
- Attract additional finance and foster public-private partnership in strengthening ICT-enabled extension services across six NA countries; and
- Generate lessons learned and evidence from six different countries which is needed to build up a robust evidence base.

DFID is also funding an independent external evaluation of the programme (£300,000). The aim of the evaluation is to provide a rigorous and independent assessment of the quality and relevance of the range of interventions undertaken by the programme and the extent to which it has helped smallholder farmers improve agricultural productivity

The expected impact of the programme is ‘Improved agricultural productivity in targeted food crops by smallholder farmers in six New Alliance countries in Africa’. This will result from improved advisory and information systems for smallholder farmers, farmer organisations and agribusinesses through harnessing developments in ICT. In this way, farmers can benefit from results from agricultural research and development and make informed decisions about farm management including technology adoption.
The desired outcome of the programme ‘New knowledge and practices adopted by at least one million smallholder women and men farmers with access to financially sustainable ICT-enabled extension services in six New Alliance countries in Africa’.
This will be achieved through the delivery of the following three outputs:

Improved access to ICT enabled extension services for at least three million smallholder women and men farmers in six NA countries, with particular attention paid to women;

Improved content adapted to specific needs, context and available ICT channels; and

Development of high quality evidence on (cost)-effectiveness and impact of ICT-enabled services.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Progress is being made toward the outcome (uptake of new technologies) and on the key outputs (reaching smallholders with information)

Data has been provided on progress towards the outcome of new knowledge and practices adopted by smallholders. By September 2016, 425,000 smallholders reported that they had taken up new seeds, fertilisers or adopted new farming approaches. Given that this figure is nearly a year old and does not include figures for Mozambique (because the grant was only awarded in December 2016), it can be assumed that the programme is making progress towards the outcome target of changing farming practices of 1 million smallholder by the time the programme ends in 2019.

All six grantees are operational and the programmes reached over 2m users by September 2016, though this falls short of the output target of 3 million because of USAID’s data collection cycle and the timing of this review. The grantees are working well with partners, particular Government extension workers, with interest from national level Governments in the potential of ICT to reach smallholders.

Data collection is a key issue, with lack of robust data from some grantees who still vary in their capacity and capability to undertake data monitoring. The external evaluation, which will start in September, will be well placed to assess this issue over the coming year. There are also issues regarding the ownership of the intellectual property of the content of the services, which requires urgent resolution between DFID, USAID and the grantees.

Overall output score and description

The overall output score for the programme is a B.

Output 1: B - Improved access to ICT enabled extension services for at least 3 million smallholder women and men farmers in six New Alliance countries with specific attention paid to women.

Output 2: A - Improved content adapted to specific needs, context and available ICT channels

Output 3: B - Development of high quality evidence on (cost)-effectiveness and impact of ICT enabled extension services

Gender

Though the programme was approved in 2013 prior to the implementation of the Gender Equality Act 2014, it integrates gender across its service provision and in its monitoring and evaluation.
There are examples from the grantees regarding efforts to target female users.

Some grantees have made gender sensitivity an integral part of their activities from design to implementation, by either: i) setting quotas e.g the Tanzania and Ethiopia grantees stipulated women’s outreach of at least 40%, and 20% respectively; or, ii) anchoring the design and delivery of their services on a sound understanding of the social context through the assessment of needs, preferences, user experience, product usage for female and male farmers e.g. the Grameen Foundation in Ghana.

The grantees’ initial gender strategies have mostly focused on reaching male and female farmers equally with the services provided. However, project implementation has demonstrated the practical difficulties in reaching women farmers, largely due to the gender gaps in access and use of ICT devices such as mobile phones.

Key lessons

As the programme is underway or even completed in some countries (e.g. Ghana), the contextual differences in the six countries matter significantly. They vary in terms of their cultural attitudes towards technology, agricultural practices and gender relations. Existing levels of extension support also have a bearing on the success or otherwise of the progamme. One of strengths of the chosen supplier for the evaluation was their awareness of the contextual issues and the application of these insights in their proposed approach to the evaluation.

Messaging around ICT services needs to be consistent and accurate, with clear guidelines provided to project partner staff and to radio station journalists. For example, it is particularly important to provide information on a) the actual cost of calls from different networks and b) the utility of the services (i.e. what justifies the cost of calling in).

In order to meet desired gender outcomes, grantees have had to be very deliberate in their targeting of women and tailor implementation to the country contexts. For example in Mozambique, the implementing organisation has found that women farmers do not have much control over the radios they own and thus tend to listen to radio programming at a different time of day from men. As a result of these findings, the implementer has planned repeat broadcasts for radio programming to reach both men and women when they might be listening, in addition to advising women to organise themselves and listen to the radio during their savings and credit group sessions.

In any new investment donors should ensure the early selection of a monitoring and learning contractor and an external evaluator, so that they can begin work to facilitate early agreement on the common indicators. However, ensuring evidence-based learning across the six countries assumes the presence of adequate capacity, resources, and systems to collect and use quality data amongst the grantees. Grantees must have the adequate capacity and capability to undertake monitorting and learning from the start. Through this past year, donors have learned that grantees and sub-grantees have varying levels of capacity for collecting and using quality data to inform learning. USAID have sought to overcome this through extensive work with the independent Monitoring and Learning contractor. The project is working to develop a more deliberate process for learning. At the face to face learning event in Tanzania in July 2017, USAID and the Monitoring and Learning provider helped facilitate a discussion around practical data collection methods between grantees. This helped grantees learn from each other and started a channel by which grantees help each other build capacity. Meetings with each of the grantees to discuss their data collection challenges were held to help them produce data collection plans. An interactive session on expected data quality standards received positive feedback from grantees.

Has the logframe been updated since the last review?

No; however, in response to data collection issues flagged in this Annual Review, the logframe indicators will be revised as a priority in the coming reporting period (see recommendation #2).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved access to ICT enabled extension services for at least 3 million smallholder women and men farmers in 6 NA countries with specific attention paid to women.
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (for 2017)	Progress
1.1 Number of smallholder farmers accessing ICT enabled agriculture advisory services across 6 New Alliance countries disaggregated by gender	3 million	An estimated 2,040, 000 smallholder farmers have been reached as of September 1 2016. Note that data will be reported in October 2017, so it can be assumed that given progress so far, the 3 million target is broadly on track.
1.2 Number of extension staff and other service providers making use of the ICT enabled advisory information services	1,600	This indicator was not reported on and has not been achieved.
1.3 % of users stating that ICT enabled advisory services provide relevant and timely information and advice	60%	This indicator was not reported on and has not been achieved. However, grantees have reported on ‘number of farmers who have applied a new technology or farming practice’ – 425,000 of total reached through the programme (20%). See below on recommendation to review this indicator.
1.4 Number of innovative partnerships between public and/or public sectors and CSOs that deliver agro-advisory services across 6 New Alliance countries	At least six awarded services operational	All six country grantees have partnerships with public/private partners and Civil Society Organisations are working to develop and deliver agro-advisory services.

Key Points

A summary of the grantees’ main activities is below.

Country Grantees	Sub-Grantees	Main activities	Start Date	End Date	ICT Challenge Fund
Ethiopia: Digital Green	Farm Radio International, Awaaz.De, DiMagi	Radio; low cost video; IVR (with SMS option) extension services	9/30/2014	9/29/2017	$1,700,000
Ghana: Grameen Foundation	Digital Green, Farm Radio International (FRI)	Services are a range of digital application (AgroTech) for agents connected to farm aggregators in north. / Includes radio too (FRI) and low cost video (DG) on agents devices	9/30/2014	1/31/2017[1]	$1,699,951
Malawi: Catholic Relief Services	Self Help Africa, / Human Networks International (HNI), Mzuzu CADECOM / (Airtel is partner of HNI, but no funding from grantee, nor HNI)	IVR, SMS and radio extension services	9/30/2014	9/29/2017	$1,682,838
Senegal: Concern Universal	SB Conseil, Practical Action, UC Davis, ADG	Uses mix of radio programs and related mobile services (e.g., IVR) managed by a social enterprise (Jokolante) and provided via cooperatives and radio stations as customers	3/25/2014	3/24/2018	$1,698,019
Mozambique:	National Cooperative Business Association: Cooperative League of the USA (CLUSA) is the international arm of the (NCBA CLUSA) - 3 years / HNI and FRI	Offering mix of IVR (with Vodafone) (voice and SMS) + FRI’s participatory radio programs	2/12/2016	2/12/2019	$1,700,000
Tanzania	FRI and Centre for Agriculture and Biosciences International (CABI)	Used FRI’s approach to designing radio programs including research on listenership and farmer knowledge of crops and integration of mobile tools to tie farmers to radio stations	01/11/2015	01/11/2018	Funded by IFAD not through DFID/USAID and Gates
IBTCI	None		08/03/15	08/02/18	$810,379.60
[1] This grantee opted for a 2-year grant period, not 3 years.

Due to the timing of this review and USAID’s data collection, the latest figures that can be reported are from September 2016. USAID’s data reporting requirement for grantees is that data is reported on a fiscal year basis. This last year’s data is expected to be reported in October 2017. At the recent grantee workshop the upcoming data collection and reporting cycle was discussed with grantees.

Furthermore, grantees have worked with the Monitoring and Learning provider to develop common indicators over the last 2 years, which has been very challenging. They have not continued with the DFID logframe indicators 1.2 and 1.3 but have reported on data that they have agreed is more meaningful to the project’s implementation. The logframe should be amended to remove 1.2 and amend 1.3 to better reflect the information that is being collected.

Over this year, the relevance and feasibility of collecting data for these indicators was discussed and agreed amongst the grantees, the Monitoring and Learning provider and USAID, to ensure a harmonised framework and improve accountability and transparency. Methods for data collection and timelines of each indicator for respective grantees for 2017 reporting have been outlined in the Data Collection Plan and Schedule form.

External factors beyond the project’s control can affect the ability to take it to scale, in particular, poorly functioning seed markets. A key challenge is that the demand created through the new services is not met by supply. Supply is not available near farmers’ locations; farmers are not informed where to access the technologies; suppliers are not informed when technologies become available to buy, and supplies are delivered to farmers late without recognising the seasonality of agricultural practices. For example, in Senegal, services are built on the assumption that the certified seed is ready to go to scale and that farmers simply need to be informed and desire to purchase this seed but this is not always the case. Often the new seed was not available for purchase.

Pest and diseases are an ever-present challenge, but this year the service has been tested by an external shock. Malawi experienced a devastating Fall Army Worm (spodoptera frugiperda) outbreak that attacked many maize crop fields including the project’s on-farm maize demonstration plots. Unfortunately, the pest was new in the country and was not included in planned maize pest control messages. The project is now working to engage key stakeholders through NACDC to develop Fall Army Worm control content and upload it on 321/212 platforms (the mobile service through which farmers access information) once information has been gathered from the Ministry of Agriculture, Irrigation and Water Development (MoAIWD). DFID, through support to the Centre for Agriculture and Biosciences International (CABI) is working on the response to FAW and how DFID’s central and country-led programmes can support affected countries.

Partnerships with public/private partners and Civil Society Organisations to develop and deliver agro-advisory services have been critical to the successful implementation of the services and to overcoming the challenges of poor seed markets. Where the grantees are providing convincing data for policy makers that the intervention can reach smallholder farmers in a beneficial way, national and local governments have maintained commitment to engaging with the programme. Partnerships at the local level also help to develop the best, localised content for the services. This helps to mitigate some of the external factors outlined above as it means information and advice is tailored to farmers’ needs, such as their preferences for different ICT services (e.g. radio versus text messages) and made available in local languages.

All six country grantees have developed effective partnerships with public/private partners and Civil Society Organisations to develop and deliver agro-advisory services. For example in Malawi, to achieve sustainability, the project enhanced non-donor resource investments in its ICT enabled services initiative. Besides investing in ‘212 services’, Airtel Malawi also invested in developing the content of messages by hiring a company to record dialogue content for its Interactive Voice Response (IVR) service. It also conducted user experience field research that showed ever-increasing use of the IVR services. The government has mainstreamed the initiative within the Department of Agriculture Extension Services to ensure continuity after the project ends, which should ensure that farmers continue to access information through ICT-enabled extension services in the future.

Alongside the financial commitment of the private sector, one of the key partners in ensuring the sustainability of the projects is clearly the participation of the national government which has responsibility for publicly funded extension services. An effective working relationship with national and local government is based on project’s results providing convincing data for policy makers that the intervention can reach smallholders farmers in a beneficial way. For example, in Ethiopia, Digital Green and its partners have worked closely with the Government of Ethiopia’s Ministry of Agriculture and Natural Resources (MoANR), regional bureaus of agriculture (RBoAs), and extension agents. Four partnering RBoAs are demonstrating their commitment to institutionalise the video-enabled approach by pledging $590,000 in the coming year to purchase ICT equipment to scale to at least 40 local districts. This is the first time that the Government of Ethiopia is allocating its own resources to procure equipment. Working with national and local state partners who are primarily responsible for extension services will ensure the sustainability of the programme’s ‘accelerator’ effect on the quality and reach of those services, and how ICT is enabling extension services to reach more farmers.

Grantees reports over this year show that some of the grantees have sought to commission additional evaluations of the programme. For example, Grameen Foundation commissioned GeoPoll to conduct an evaluation to understand how the interactive radio programming affected uptake of various promoted practices. Overall, the evaluation concluded that there are some encouraging signs that the interactive radio programme had an effect on the uptake of SSTP technologies among listeners of the radio stations surveyed versus non-listeners. The evaluation found that maize farmers in one district have used radio as a valuable source of information for both method, type of seed, storing their seed, as well as maintenance of their maize fields. Listeners seemed more likely to adopt promoted practices e.g. use of tarpaulin for protecting crops when compared to non-listeners.

Sustainability of the programmes does not necessarily depend on the development of a purely commercial model. Some of the private sector project partners see value in taking forward the programme from a research perspective, to further test the viability of the ICT solutions for extension services. In Ghana, research undertaken by the Grameen Foundation expects the scale-up to reach an additional 10,000 farmers through 170 aggregator agents by continuing to embed the solution into the marketing and input/service credit operations of commercial aggregators in the maize, rice and soyabean value chains.

Recommendations

#1 As the annual data for 2018 will not be available until October 2018, DFID should seek approval to change the Annual Review date to 31st October, so that next year’s review has access to the data and time to review the quality of the data with the independent evaluation team. This will enable a fairer and more transparent analysis of the programme in 2018.

#2 The logframe target for indicators 1.2 should be removed as grantees are not reporting on this indicator. This was agreed after discussion between grantees and USAID about which indicators were most appropriate. 1.3 should be amended to ‘number of farmers who have applied a new technology or farming practice’.

#3 USAID should develop a lessons learned paper on the key regulatory and policy barriers to the successful uptake of new technologies, to help national governments and donors better understand the failures in the supply side once farmers are equipped with better information. Though these barriers are unlike to be overcome during the course of the programme, it is an important set of lessons for the programme’s public and private partners in the provision of future extension services. This could include how to respond to outbreaks of pests and diseases e.g. FAW and how to co-ordinate with key donors and international organisations. The programme can also draw on lessons from other similar programmes such as the mNutrition programme. USAID should agree with DFID the best approach to commission this paper by end of December 2017.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved content adapted to specific needs, context and available ICT channels
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (for 2017)	Progress
Number of agricultural content country frameworks developed and adapted to specific country, target group and ICT channels across 6 New Alliance countries.	At least six agricultural content country frameworks developed and adapted to specific country context while ensuring a level of harmonisation	Achieved.

Key Points

All six grantees and their partner have produced the ‘content’ for their services i.e. have developed the information on new farming practices and inputs such as seeds, which is provided through the various ICT channels.

The process of developing and updating the content frameworks (the overarching document of topics and information) works best where the grantee has formalised a partnership to deliver the best content. For example, in Malawi, the National Agriculture Content Development Committee (NACDC) oversees content development and involves the Department of Agriculture Extension Services (DAES) under the Ministry of Agriculture. Content is scrutinised by all parties before being uploaded onto the ICT platforms for public consumption.

Making sure that content is designed for local users has been critical, but it requires the engagement of a range of partners e.g. in Senegal, grantees include NGOs, producer cooperatives, seed companies and business advisory services to develop a communication plan to refine the content for local requirements. Content is sourced from SSTP partners, and ICT tools adapted using a variety of languages and specific modalities (voice, offline smartphone apps).

Another key lesson is that all messages delivered through different ICTs are prepared in a harmonised way and captured in formal documents, to which everyone can refer. Ethiopia is a good example of this. Content development started with the selection of topics. New technologies or knowledge and/or practice gaps in a given technology were then identified with the extension agents. Extension agents then referred their observations and the farmers’ feedback collected at different events including dissemination sessions back to the grantee. The content was then organised into the Package of Practices (PoP) document. The PoP was the document prepared by the regional agricultural office, and is now updated with recent research findings. This document is used as a reference during the promotion of new technologies and reinforces existing technologies and practices. The information is then adapted for radio, video and IVR. The project has found that key to this process is the participation of extension actors and partners in the production and updating of the PoP, which ensures the harmonisation of messages and modalities with the extension system.

Recommendations

# It is unclear who ‘owns’ the content and whether it is publicly available. As an urgent priority, DFID should work with USAID to agree the legal ownership of the data and confirm that it is publicly available after an agreed period of time. There are lessons to be learned from the mNutrition programme on this issue. DFID should arrange a discussion with USAID with a view to getting agreement by end of December 2017.

# USAID should work with grantees to share more information about the types of content that work best through different ICT channels, and present this to national ministries as a way to promote the innovation of the programme. USAID should agree a plan with the Monitoring and Learning provider by December 2017.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development of high quality evidence on (cost)-effectiveness and impact of ICT enabled extension services
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (for 2017)	Progress
One theory-based impact evaluation combining qualitative and quantitative methodologies completed in at least 3 target countries demonstrating the sustainability, impact and effectiveness of ICT enabled agriculture extension services in enhancing the uptake of technologies disaggregated to capture impact on different target groups including poor smallholder farmers and women.	Three country impact evaluation reports finalised and one overall synthesis evaluation report finalised, peer-reviewed and widely disseminated.	Not met
Documentation of lessons learnt on what works and doesn't work in scaling up ICT enabled extension services across 6 New Alliance countries.	Paper published highlighting key lessons for launching and scaling up ICT enabled agriculture extension services / Paper published highlighting key lessons learnt for developing relevant content and using appropriate ICT channels	Not met

Key Points

DFID tendered the evaluation contract in June 2017, and a winning bid has been selected. The bid evaluation team comprised representations from each of the four donors to the Fund (USAID, IFAD, BMGF and DFID). The contract will then run for just over a year and a half, with the final report from the evaluator due by January 2019.

The specific focus of the evaluation is to provide a rigorous and independent assessment of the quality and relevance of the range of interventions undertaken by the programme and the extent to which it has helped smallholder farmers improve agricultural productivity.

The evaluation will generate high quality evidence on the effectiveness of ICT-enabled agricultural extension services in enhancing farmers’ livelihoods through increased adoption and uptake of improved agricultural technologies. It will produce insights in what works and what does not work in scaling up ICT-enabled extension approaches through working with both the public and private sectors.

The scope of this evaluation covers the period of the NA ICT from July 2014 to the end of data collection for the evaluation (a date in second half of 2018 to be confirmed in inception).

In assessing the overall programme, the evaluation will be expected to encompass all grantees (who will make more or less of a contribution to overall programme targets as set out in the logframe). The evaluation should provide a comparative analysis of the design and performance of the grantees, so that lessons can be learned for this and other interventions. However, an assessment of the performance of each individual grantee (and sub-grantees) will not be required.

A specific paper on lessons learnt has not been produced because the evaluation contract has only just been tendered and a preferred supplier agreed within the last six months. However, lesson learnt activity has been co-ordinated with between USAID, the grantees and Monitoring and Learning provider.

Recommendations

# Landell Mills has been awarded a contract to conduct the external evaluation component of this programme. DFID need to closely monitor the progress of the external evaluation against the agreed timetable and outputs of the evaluation, and ensure that the governance and management arrangements are clarified so that problems can be dealt with quickly. DFID will host an introductory meeting with the supplier in September 2017 and will agree the management and governance arrangements. In the interim, DFID will liaise with the other three donors to agree arrangements for a multi-donor ‘review group’ for the review of evaluation outputs. A DFID Evaluation Adviser will be a member of that group to assist with Quality Assurance; inception, mid-term and final reports will the quality assured by DFID’s Evaluation Quality Assurance and Learning Service (EQUALS).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The ICT Agriculture Extension Challenge Fund is a four year multi-donor programme. Funding is provided by USAID ($3m), the Bill & Melinda Gates Foundation, BMGF ($3 million), the International Fund for Agricultural Development, IFAD ($1.5m), and DFID (£2.8m).

In addition to monetary funding, each donor makes in-kind contributions to the programme. USAID manages five of the six grants on behalf of the donor group, including reporting requirements and handling receipt and disbursement of funding from the other donors. IFAD manages the Tanzania grant, with the USAID fund manager serving as technical adviser. DFID will manage the independent evaluation contract (contract award pending). All four donors participate in the Steering Committee.

USAID does not charge DFID or the other donors any overhead or transaction costs for their role in managing the programme. This management model was identified as the best value for money option for implementing the fund at the business case development stage. The key cost drivers for the programme are, therefore, the costs associated with each grant project, including personnel costs and expenses. All grants were awarded through a competitive procurement process, using a range of selection criteria including track record, technical expertise and value for money. All grantees set out their budgets and spending plans as part of that procurement process, and costs have been maintained within agreed ceilings.

VfM performance compared to the original VfM proposition in the business case

The business case outlined a number of ways in which value for money would be secured through the programme. These are listed below, with a brief progress update from this reporting period.

1. Grantees will be selected through a competitive process with VfM an important selection criterion: As mentioned above, all grants were awarded through a competitive process.
2. DFID will directly procure and contract the evaluation provider: Following a competitive process initiated in June 2017, a provider has been selected, and the evaluation contract is expected to be awarded in August 2017. The procurement process was robust and value for money was assessed as part of the selection criteria. The commercial award criteria accounted for 40% of the overall score, ensuring that economy and efficiency measures of value for money were influential in determining the procurement outcome.
3. In addition to donor investments, grantees will bring in their own investments, gradually increasing these during programme implementation: Some grantees (notably Ethiopia and Senegal) are making progress towards financial sustainability. Approximately 43% of the costs of institutionalising ICTs within Ethiopia’s public extension structure during the reporting period were covered by non-donor sources. In Senegal, the Jokalante social enterprise signed its first service contract with an external partner in 2017.
4. The programme will include performance-related awards to incentivise strong performance and innovation: Three adaptation grants were awarded to enable country grantees to adapt their approaches based on changes in services available and local circumstances (Ethiopia, Mozambique and Tanzania).
5. The programme will generate quality, robust evidence of relevance for other actors interested in promoting effective extension services through using ICTs: The evaluation contract, to be awarded in August 2017, will generate robust evidence on the quality and relevance of the range of interventions undertaken by the programme, including the extent to which these interventions have helped smallholder farmers to improve agricultural productivity.

Assessment of whether the programme continues to represent value for money

The table below assesses the programme against the ‘4 E’ framework, and presents an overall conclusion on the value for money of the programme during the reporting period.

4 Es	Summary of performance
Economy	The programme is strong on economy. USAID manages the grantees directly and does not charge DFID for any overhead or transaction costs. Each grantee has a budget and spending plan which was assessed as part of a competitive process before each grant was awarded. During the reporting period, all grantees have maintained costs within agreed ceilings although some have requested no-cost extensions.
Efficiency	The working relationship between the four donors to the Fund is strong and operating well. During the reporting period, there was a personnel changeover on the USAID side, with the lead Adviser retiring and a new Adviser taking over. The DFID management team has been in regular contact with the new Adviser since she began in the role.
Effectiveness	‘Effectiveness’ in the DFID value for money framework relates to how well programme outputs achieve their desired outcomes. As outlined earlier in this Annual Review, on the data available from September 2016, the programme is performing moderately against the output indicators, but without data for 2017 it is not possible to state that it has achieved its milestone for this year. All grantees have plans for financial sustainability that they are currently working through.
Equity	Gender considerations have become increasingly well integrated into programme delivery. A key highlight from the reporting period was the development of a gender plan by IBTCI, the monitoring and learning contractor. IBTCI has since conducted various activities to improve the gender sensitivity of the grant projects, including a virtual learning event focused on gender, and a gender World Café session. IBTCI will shortly be delivering a case study report on gender integration, including a set of best practices on gender and ICT. / Several grantees have made gender sensitivity an integral part of their activities from design to implementation, by either: i) setting quotas and working at meeting them e.g. in Tanzania and Ethiopia stipulated women’s outreach of at least 40%, and 20% respectively; or, ii) anchoring the design and delivery of their services on a sound understanding of the social context through the assessment of needs, preferences, user experience, product usage for female and male farmers e.g Grameen Foundation in Ghana.
Overall	The DFID review team concludes that this programme represented value for money over the reporting period.

#7 The independent evaluation team should prioritise an analysis of the quality of the gender disaggregation of date being provided by the grantees, to understand the impact of the programme’s interventions on women farmers. DFID should highlight this in the meetings with the independent evaluation team and followed up as a priority issue over the course of the evaluation.

Quality of financial management

DFID made its final payment to the Fund in July 2017, for onward disbursement to the grantees and IBTCI. DFID has set aside up to £300,000 for the evaluation contract, the payment schedule of which will be agreed prior to contract award.

USAID provided the DFID management team with a cashflow analysis and financial report for the Fund in February 2017, with DFID contributions duly recorded.

Date of last narrative financial report	February 2017
Date of last audited annual statement	Not applicable

E: RISK (½ page)

Overall risk rating: Moderate

The programme risk remains moderate. Details on individual risks are included in the table below, organised by the DFID risk category headings.

Overview of programme risk:

Risk category	Gross risk description	Mitigation	Residual risk rating	Likely trajectory of risk severity over coming year (to September 2018)
Context	The competitive environment for extension services in agriculture and the pace of change in technology combine to create a moderately risky environment within which the programme must not only deliver but also become financially sustainable.	Some grantees (notably Ethiopia and Senegal) are making progress towards financial sustainability. Approximately 43% of the costs of institutionalising ICTs within Ethiopia’s public extension structure during the reporting period were covered by non-donor sources. In Senegal, the Jokalante social enterprise signed its first service contract with an external partner in 2017. However, financial sustainability remains a key risk for the programme. The three year timespan of the programme is a relatively short timeframe in which to achieve sustainability. It is hoped that the external evaluation and the IBTCI monitoring and learning activities will strengthen the evidence base, including on what makes a financial success out of these types of services.	Moderate
Context	Political unrest and other environmental factors may delay the progress of some grant projects.	Civil unrest in Ethiopia affected progress of the Ethiopia grant during the reporting period. In response to the October 2016 government-decreed ‘state of emergency’, the grantee in Ethiopia redistributed its activities to stable regions, in coordination with the public extension system and SSTP.	Moderate
Delivery	Data collection is an ongoing challenge for several grantees, due to capacity, resource and system constraints.	USAID has been working closely with IBTCI – the monitoring and learning contractor – over the reporting period to strengthen data collection, monitoring and learn support to the grantees. USAID assembled a team of managers and advisers with expertise across agricultural extension, ICT, scaling and monitoring and evaluation to review the monitoring and learning plans of all grantees and to work closely with IBTCI to increase the level of support with data collection and monitoring given to grantees. / In addition, the procurement of the evaluation is now complete, and DFID expects to award the contract in August 2017. The winning bidder submitted a strong technical and commercial proposal, including data collection approaches to ensure the evaluation delivers on its objectives.	Moderate
Operational	Last year’s annual review noted a risk that communication between DFID and USAID, while effective and regular, was ad hoc rather than on a regular meeting schedule.	DFID and USAID have held quarterly meetings during the reporting period, and will continue to do so over the coming year.	Minor
Safeguarding	There is a risk that grantees do not give due regard to gender considerations in their programme design and implementation, negatively affecting the programme’s potential positive impact on women.	As outlined earlier in the Value for Money section, gender considerations have become increasingly well integrated into programme delivery. Several grantees have made gender sensitivity an integral part of their activities from design to implementation. Data is gender disaggregated.	Moderate
Fiduciary	There is an inherent risk in all commissioning activity that funds are not used for the intended purposes.	USAID has a strong track record in financial management of programmes, and has demonstrated capacity to implement and manage the financing of this fund.	Minor
Reputational	As DFID is leading the evaluation component of the multi-donor programme, the key reputational risk for DFID over the coming year will be the quality of outputs delivered by the evaluation contractor.	The evaluation contract is expected to be awarded in August 2017, and DFID will establish monthly meetings with the evaluation supplier to monitor progress and emerging risks and issues. DFID will maintain regular contact with the other donors to the Fund on matters relating to the evaluation. While it is too early to report against this risk, the bid evaluation panel had very good confidence in the proposal submitted by the winning supplier, and expects the evaluation contract to deliver against its objectives.	Moderate

Outstanding actions from risk assessment

None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is performing moderately well; however, as outlined elsewhere in this Review, some delays and challenges have been encountered in reaching milestones.

Performance of partnership(s)

The DFID management team and USAID continue to have a good working relationship. During the reporting period, there was a personnel changeover on the USAID side, with the lead Adviser retiring and a new Adviser taking over. The DFID management team has been in regular contact with the new Adviser since she began in the role.

The working relationship between the four donors to the Fund is also operating well. All four donors were represented on the bid evaluation panel of the evaluation tender.

Asset monitoring and control

All grantees have provided asset registers, in line with DFID Smart Rules.

Supply chain mapping

Delivery chain data on the six grantees has been logged centrally with the Director of Research office.
The winning bidder for the evaluation contract was selected in June 2017. Once the contract is in place (August 2017), the DFID review team will log delivery chain data for the evaluation component with the Director of Research office and/or on AMP.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not relevant. The partnership principles were not used in monitoring this project as it does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The evidence set out in the business case for funding the New Alliance ICT Agriculture Extension Challenge Fund remains pertinent.

The overall project and its contribution to the wider goals of the New Alliance will be evaluated by an independent service provider. The evaluation contract is expected to begin in August 2017, following the successful conclusion of a competitive procurement process led by DFID.

Monitoring progress throughout the review period

During the reporting period, the DFID Senior Responsible Owner (SRO) and Deputy Programme Manager for the New Alliance ICT Agriculture Extension Challenge Fund have been in regular contact with the USAID lead for the programme through regular email exchanges and quarterly phone calls. As outlined earlier, the USAID lead retired during the reporting period. Since then, the DFID management team has been in regular contact with the new lead Adviser, who began in post in May 2017.

Country grantees report progress on a quarterly basis.. Each has set a target for the full project period for the number of smallholder farmers to be reached by the ICT-enabled services and the sub-set of those that will apply one of the target new technologies.

Approach for this Annual Review

This Annual Review was conducted by an internal DFID team, involving the Senior Responsible Owner/Livelihoods Adviser, and the Deputy Programme Manager.

The annual review team drew upon: the 2017 Annual Progress Report submitted by USAID, including two Annual Review meetings with USAID staff. Regular review meetings and presentations from USAID and the Advisory Committee have been held during the reporting year.

Key documentation
- New Alliance ICT Agriculture Extension Challenge Fund Business Case
- 2017 Annual Progress Report (from USAID)
- Review meeting notes and presentations from USAID

Annual Review 2016 - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: New Alliance Information and Communication Technologies (ICT) Agriculture Extension Challenge Fund
Programme Value: £2,800,000		Review Date: 1 September 2016
Programme Code: 204423	Start Date: 12 August 2014 (date agreement signed)	End Date: 31 March 2018

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A
Risk Rating	Medium	Moderate

Summary of progress and lessons learnt since last review

The aim of the New Alliance Information and Communication Technologies (ICT) Agriculture Extension Challenge Fund is to develop and scale up the delivery of agriculture extension services using sustainable information and communication technologies (e.g. radio, mobile services, video and web-based applications). The programme is delivered by the United States Agency for International Development (USAID) and aims to reach 1 million users to help improve agricultural productivity and increase food security for smallholders in sub-Saharan Africa. The UK is providing £2,800,000 over 4 years. The total fund is $12m over 4 years. The other donors are USAID (U$ 3 million plus U$ 1.6m in kind for managing the fund and grantees); the Bill and Melinda Gates Foundation (BMFG) (U$ 3m) and the International Fund for Agricultural Development (IFAD) (U$ 1.5 million)

The multi-donor New Alliance ICT Extension Challenge Fund is now in full implementation with six country grantees (Ethiopia, Ghana, Malawi, Mozambique, Senegal, and Tanzania) and a monitoring and learning contractor (M&L). 2,865,465 smallholder farmers have been reached by the ICT-enabled services and 566,853 smallholder farmers have adopted a target technology (e.g. improved fertiliser blends) to date.

Since September 2015 USAID, the Fund Manager, has successfully coordinated the competitive procurement of the fifth country grantee, Mozambique, as well as the M&L contractor, IBTCI (International Business & Technical Consultants Inc). IFAD (the International Fund for Agricultural Development), one of the donors, completed its comparable agreement with the sixth country, Tanzania.

USAID also conducted a competition for supplemental “adaptation” grants among the country grantees to allow them to apply for additional funding to adapt to changes in ICT products and services that have occurred since they began work. Such changes include reductions in prices of devices or services, or availability of new services or new partners. Three adaptation grants were awarded to enable country grantees to adapt their approaches based on changes in services available and local circumstances (Ethiopia, Mozambique and Tanzania).

The grantees are aware of the importance of complementarity with existing agricultural programmes promoting improved farming practices, in particular, AGRA’s Scaling up Seeds and other Technologies Partnership (SSTP) and the DFID funded mNutrition programme in Ghana and Malawi.

The programme will undergo a performance evaluation. Terms of Reference for the evaluation are currently being designed and agreed and the procurement process will begin in September. The Terms of Reference will specify that there are 2 years remaining for the programme to deliver. The procurement process should take no more than 4 months. The contracting with the successful supplier will also ensure that a manageable but strict timetable is followed so that the evaluation is robust but expedited.
Two key lessons learnt since the last review include:

- Effective co-ordination of the timing and content of ICT-enabled services delivered via different “channels” (e.g. radio, interactive voice response and video) is essential; and
- How important and challenging it is to define common results indicators precisely across country grantees.

The overall risk ranking for the programme is rated moderate.

Summary of recommendations for the next year

#1 In Ghana and Malawi, the country grantees should continue to build on opportunities for synergy with the DFID funded mNutrition programme which focuses on promoting behaviour change through mobile phone based services. There is also an opportunity to share lessons with the mNutrition programme on how to achieve financial sustainability. DFID should facilitate contact between Groupe Spéciale Mobile Association (GSMA), USAID and country offices to ensure that a working relationship is established by end of October 2016.

#2 USAID should reinforce to grantees the importance of timely and consistent reporting of data. Where grantees are unable to provide information, USAID should insist upon a plan of action to address late reporting and withhold or withdraw payments if necessary. This should be undertaken on a case by case basis and reported on in the monthly meetings with DFID.

#3 USAID should produce a plan to ensure that the projects are gender sensitive and that grantees are effectively targeting women. Additionally, there needs to be a much stronger emphasis on disaggregating the data by gender and figures need to be reported before the end of the calendar year to demonstrate evidence that this information is being collected and communicated. The M&L contractor needs to demonstrate how each grantee is doing this in the quarterly report due in December 2016. A workshop should be arranged with project partners to focus on this issue. This should be held before December 2016.

#4 A formal but light touch lessons learnt exercise should be conducted so that all the donors and grantees can make improvements to the monitoring and implementation of the programme and that everyone is aware of roles and responsibilities, particularly around timely reporting from the grantees. This should be completed by February 2017.

Annual Review 2015 - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: New Alliance Information and Communication Technologies (ICT) Agriculture Extension Challenge Fund
Programme Value: £2,800,000		Review Date: 1 September 2015
Programme Code: 204423	Start Date: 12 August 2014 (date agreement signed)	End Date: 31 March 2018

Summary of Programme Performance
Year	2015
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt

This has been the first year of implementation of the New Alliance ICT Extension Challenge Fund, which will operate in six countries in total (Ethiopia, Ghana, Malawi, Senegal, Tanzania and Mozambique).

To date, USAID, as the Fund manager, has successfully coordinated the competitive procurement of grantees for five countries (excluding Mozambique). In four countries (Ethiopia, Ghana, Malawi and Senegal), the grantees are developing and strengthening agricultural extension services, bringing together different communication channels including radio, TV, mobile phones, video and web-based applications. In these four countries, the services will become operational and scaled up during the second year, with the aim of encouraging farmers to adopt improved farming practices to increase their agricultural productivity. Tanzania will start launching and scaling up services towards the end of the second year. The competitive process for selecting a grantee is underway in Mozambique and a grantee should be selected by the end of 2015.

The type and range of ICT enabled advisory services varies significantly across the different countries. This will be a good opportunity for learning across the grantees, while taking into account the specific country context. A monitoring and learning support service provider has been procured and contracted to ensure lessons learning takes place and informs an improved service delivery. It has become clear that the grantees need strategic guidance to think through a financially sustainable business model from the start and throughout implementation. This is to ensure that ICT enabled advisory services can go to scale beyond lifetime of the grant. USAID is well positioned to provide this strategic support and oversight.

The grantees are aware of the importance of complementarity with existing agricultural programmes promoting improved farming practices, in particular AGRA’s Scaling up Seeds and other Technologies Partnership (SSTP) and DFID’s funded mNutrition programme in Ghana and Malawi.

Summary of recommendations for the next year

USAID to continue to provide strategic guidance to all country grantees to ensure that they are aligned and complementary to the SSTP country activities and focus on integrating different ICT tools with a clear financially sustainable business model in place. (ongoing)

In Ghana and Malawi, the country grantees should build on opportunities for synergy with the DFID funded mNutrition programme which focusses on promoting behaviour change through mobile phone based services. (ongoing)

USAID to ensure that the monitoring and learning partner supports cross-country learning about content development and the delivery and effectiveness of cross-communication channels (mobile phones, radio, TV, video’s) across the six countries. The insights should inform an adaptive programme management and implementation approach. The evidence and lessons learnt should be documented for wider dissemination. As a first step, USAID should prepare a short presentation of the lessons learnt and share this with project partners by December 2015.

USAID to ensure that the content developed and the communication channels are gender sensitive and that both men and women have access to relevant and timely advice and can apply the advice to improve their farming practices. USAID to provide evidence of how this is happening and develop a plan on how to share this across the project partners by December 2015.

If the re-competition for Mozambique does not result in the selection of a high quality bid, the Steering Committee should look into options to re-allocate some of the available resources by December 2015.

The development of a common logframe and reporting framework is needed to ensure effective monitoring and reporting across all implementing partners and development partners. DFID, in close consultation with USAID and the Monitoring and Learning service provider should make this a key priority for the second half of 2015.

In line with above recommendation, DFID should conduct the second annual review within 6 months from this Annual Review to align the reporting timeframes of all co-funding partners.

DFID should develop the Terms of Reference (ToR) for the final, external evaluation as soon as a revised joint logframe and monitoring framework has been developed and agreed upon. After the ToR has been agreed by the SC, DFID should start the procurement for an external evaluation service provider to ensure a timely start for the final evaluation. This will be a different provider to the M&L service provider. ToR to be finalised by January 2016.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N)….
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process