Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	31 January 2018

Title: Humanitarian Emergency Procurement Project (HEPP)
Programme Code: 203416	Start Date: August 2012	End Date: November 2017
If programme was closed >1 month early please describe in a few words why.	The end date of the project was brought forward to align with the change of the Humanitarian Emergency Operations Support Services (HEOSS) contract

Summary of Programme Performance

Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A	A
Risk Rating	Moderate	Moderate	Minor	Minor	Minor

Financial Position

Original Programme Value	£3,000,000
Extensions/ amendments	£7,250,000 (2013) / £12,000,000 (2014 uplift) / Final total programme value: £12,500,000 (2014 migration crisis)
Log-frame revisions (with dates)	October 2014 major logframe revision following uplift; annual updates thereafter following Annual Reviews
Total programme spend	£11,681,065 (awaiting final invoice – this will be updated on final receipt.Total will not exceed approved programme value)

Follow up actions required following closure

- CHASE- HRG (Conflict Humanitarian and Security Department - Humanitarian Response Group) to consider the recommendations here and define the future scope of DFID’s engagement on the stockpile and emergency procurement in support of its humanitarian response capacity.
- CHASE- HRG review the recommendations made in this PCR with Palladium and DHL to define the future direction of DFID’s stockpile capacity, supply chain management and procurement under the new Humanitarian Emergency Response Operations and Stabilisation (HEROS) Business Case.
- CHASE- HRG defines a time line to implement changes to the current configuration of DFID’s stockpile capacity in close collaboration with Palladium and DHL.

Recommendations for future programmes

- HRG and the Humanitarian, Stabilisation Operations Team (HSOT) to co-ordinate a strategic review of the stockpile, including location and commodity makeup. This should be complemented by an understanding of HEROS procurement and logistics expertise and DHL capabilities in order to recommend the most appropriate approach to stockpile and supply chain management, use of new technologies, and coordination with international partners which maximises value for money under HEROS and supports delivery of UK humanitarian policy.
- Ensure that stocks allow for branding and traceability, with one third of DFID’s NFI’s UKAID branded and two thirds unbranded.
- HSOT to continue to lead on research and innovation in Non-Food Items (NFI’s), piloting new materials and designs (e.g. solar lamps and batteries), based on evidence from the field and drawing on DFID’s monitoring and evaluation capability.
- In liaison with DFID’s cash advisers, and in support of DFID’s Grand Bargain commitments, HSOT to build the capacity of the Procurement and Logistics team to enable them to assess the suitability for the provision of cash based responses (such as conducting market feasibility, identifying suppliers, negotiating contracts), to be able to recommend to DFID when it would be appropriate to deliver cash instead of NFIs.
- HSOT to work with DFID to undertake pilot market feasibility scoping exercises with the private sector with the aim of developing a baseline to determine the resilience of key commodity supply chains and the extent to which they would be likely impacted by disasters. This will provide DFID with greater understanding of how to prioritise and or combine the use of cash or in kind at different points in an emergency response.
- In liaison with the Disability Team, HRG to commission HSOT to undertake a study to review appropriateness of the NFI’s currently held that meet the needs of those people with disabilities, and make recommendations for new items that could be adapted or added to the stockpile. This work should be led by HSOT in close collaboration with CHASE Humanitarian Advisers.
- HRG and HSOT to commission independent review to recommend how HSOT and DFID can provide support to OCHA to improve the information and access agencies have on NFI stockpiles globally, its shortcomings, and make recommendations where improvements can be made.
- HSOT to take advantage of new technological developments in the sector, and with M&E support, bring new items to the stockpile that will continue to improve and enhance it, using new technology to track performance of items and learn lessons from the field.
- HRG and HSOT to continue to collaborate with RED (Research and Evidence Division) and EPIC (Emerging Innovation and Capabilities Department) to explore how block chain technologies can be deployed in the humanitarian supply chain. This work is currently in the pilot phase and should be continued if found to be beneficial.
- Improve and enhance the deployment module, taking advantage of new innovations and technologies, particularly communications equipment, and train deployable DFID staff in its use.
- HSOT should continue to provide support and share best practice with the Global Logistics cluster’s standard training to ensure that humanitarian responders have the right skills for emergency logistics operations.
- Scope out and make recommendations for a replacement for DFID’s air broker contract by the end of 2018 to enable a successful procurement process to be undertaken which complements capabilities provided under HEROS.
- HRG to devote a greater proportion of a Humanitarian Adviser’s time to stockpile, procurement and logistics under HEROS programme.

A. Introduction and Context

DevTracker Link to Business Case:	Business Case

Outline of programme and what it has achieved

The Humanitarian Emergency Procurement Project (HEPP) has over the past 5 years supported, maintained and improved DFID’s emergency response capacity to humanitarian disasters in both rapid onset and protracted contexts, through its stockpile of non-food items, mostly held in Dubai and Kemble. It has allowed the UK to launch bilateral responses to emergencies quickly and effectively, delivering humanitarian relief supplies to meet the immediate needs of affected communities, saving lives and reducing suffering. The stockpile has been managed by the CHASE Operations Team (OT) Procurement and Logistics Team under the Humanitarian Emergency Operations Support Services (HEOSS) project.

The Humanitarian Emergency Response Review (HERR), which was published in 2011, highlighted the increasing number of people affected by emergencies and called for a change in the way DFID approached humanitarian responses. This included a requirement to innovate and bring best practice to its supply chain and stockpile.

Following the Independent Commission for Aid Impact (ICAI) review of the Typhoon Haiyan response, and further reviews of UK government humanitarian stockholdings in 2014, Ministers agreed that DFID should increase its range of emergency supplies to be able to meet the needs of up to 75,000 people by April 2017. Much of the focus of the HEPP programme has been on building this increased capacity, whilst also responding to numerous humanitarian crises over the same period.

To reflect the increased ambition for the stockpile, the budget for the HEPP has increased significantly over the project timeframe. Originally £3 million, it was increased in 2013 to £7.25 million to meet the needs of 38,750 people, and then again in 2014 to £12 million to meet the needs of 75,000 people. This increase also triggered adding an additional 2 years to the project. The budget was increased by a further £0.5 million in 2014 to provide emergency relief supplies in response to the migration crises in Europe and the Middle East and North Africa (MENA) region.

The HEPP has focused on constantly improving the quality and range of items held within the stockpile. CHASE has undertaken regular testing and review of items to ensure that DFID is taking advantage of new products available in the marketplace and capitalising on the latest innovations. CHASE lab and field testing has helped develop new quality standards that have been shared with the rest of the humanitarian community, which has helped drive improvements in the sector. This has included monitoring and evaluating the performance of items in the field, and making changes and improvements following feedback and lessons learned from responses. As the stockpile has increased in size, new capabilities have been added, such as Air Cargo Handling Equipment (ACHE), which allows items to be unloaded quickly from aircraft, unblocking busy airports during emergencies, as used in Nepal following the earthquake in 2015.

Obtaining good value for money (VfM) has been a key feature of the programme. Tenders and competitions have been held by CHASE OT to ensure that DFID is procuring items at competitive prices that meet DFID’s quality standards and specifications. CHASE OT has also set up numerous Framework Agreements to allow the rapid and direct procurement of items during emergencies. In some instances, manufacturers and suppliers have agreed to store items on our behalf, reducing costs. The humanitarian stockpile works in parallel with a similar Stabilisation Unit support package, sharing warehousing, labour and maintenance services, helping to reduce costs.

An important component of the stockpile is the deployment module, which is designed to support up to 20 DFID personnel (and / or those of partners) in the field during an emergency response, providing a portable office, communication and life support equipment. It has also evolved over the project’s lifetime, taking advantage of technological advances to improve communications equipment, provide more comfortable accommodation, and better lighting. It was thoroughly tested at Triplex 2016 (the International Humanitarian Partnership large scale simulation exercise in Norway), and was also called upon recently during the Hurricane Irma and Maria responses.

Loading UKAID NFI’s onto aircraft is often one of the very first visible actions undertaken during a response. A significant proportion of DFID’s NFI's are branded, clearly showing that assistance has come from the UK. This is helpful for communications purposes, and clearly demonstrates that our assistance is reaching those people most in need. All stockpile items are also discretely marked so they can be tracked back to the manufacturers, and their performance monitored in the field. This means once NFIs are deployed they can be assessed for performance over their life allowing DFID to see and react to any issues on product performance.

DFID has drawn upon the stockpile numerous times to support emergency responses over the duration of the project. Table 1 below gives an idea just how extensively. The stockpile remains a very important tool for DFID and UK Government when responding to crises overseas and has been used in a wide range of contexts. Looking ahead the stockpile will need to be managed in an increasingly flexible way. The demand for rapid access to NFIs is expected to continue, despite the increasing use of cash, as global humanitarian needs rise and the UK aims to be to respond to up to 6 crises per year under the HEROS contract.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The Outcome of the project is that:

(i) UK Government humanitarian stocks enable DFID to respond quickly, effectively and appropriately to humanitarian crises. Exceeded expectations. DFID’s stockpile is now up to full capacity, able to meet the needs of up to 75,000 people, with some commodities exceeding the target quantities. It has formed the backbone of many UK responses, and been called upon for numerous humanitarian emergencies to rapidly provide lifesaving assistance to vulnerable people, giving them some basic degree of shelter, comfort, safety and dignity. See Table 1 below for a full list.
(ii) The International system is better prepared to respond quickly, effectively and appropriately to humanitarian crises and their changing nature and scale. Partially achieved: Progress by the international system to be better prepared and respond quickly and appropriately to disasters has been slower than hoped, but there has been some progress. This is an area that needs to be led by OCHA, and DFID should assess what further support it can provide to encourage better progress. Good progress has been made on developing DFID’s stockpile and sharing innovation and best practice with the wider humanitarian community.

(iii) Innovations in shelter materials and NFIs assessed properly and brought into routine use as part of the humanitarian response. Met expectations. Testing, lessons learned from the field, and utilising new and innovative products have enhanced the stockpile and ensured affected populations receive appropriate high quality items. DFID’s stockpile has been shared with partners and standards for some items adopted by partners.

Key Lessons

- Whilst the stockpile has formed a very important component of UK humanitarian responses, and will continue to do so in the future, it will need to flex and adapt as DFID increasingly provides cash based assistance;
- The expectation in the original Business Case to influence and improve the stockpiles held by others in international humanitarian community was ambitious and DFID should explore what further support it can provide under HEROS.
- The need to ensure onward distribution plans for NFI’s are discussed and agreed and followed up upon in advance of sending NFI’s by air, to avoid items becoming held in partner’s warehouses and not reaching the intended beneficiaries;
- The need for greater HRG Humanitarian Adviser time, involvement and advice on the stockpile going forward in order to ensure this programme supports UK humanitarian policy objectives.
- Improve financial management of the stockpile under the HEROS project, with more timely presentation and payment of invoices.

Output Score and Description

Output 1: UK Government humanitarian stocks and agreements with suppliers in place so that the UK can meet the needs of affected communities across a wider range of humanitarian crises. A+ moderately exceeded expectations
Output 2: DFID's Global Stockpile(s) appropriately located and complements the International System's own stockpiles. Implementation of agreed recommendations to support, improve and replace existing international systems. – A - met expectations
Output 3: Implementation of agreed recommendations on standards and dissemination and compliance. A – met expectations
Output 4: DFID held stocks support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments. A – met expectations

## C: DETAILED OUTPUT SCORING

Output Title	UK Government humanitarian stocks and agreements with suppliers in place so that the UK can meet the needs of affected communities across a wider range of humanitarian crises
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	50%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones Target (31/10/17)	Progress
1.1 UK stockpile (quality, content, volume) kept under regular review to ensure it is able to meet humanitarian needs on an on-going basis and respond to emerging needs.	Stockpile Uplift is complete. Ambition for further stockpile changes continually reviewed based on the lessons learning outcomes of past responses and monitoring reviews (such as Ethiopia).	The stockpile is now able to meet the needs of up to 75,000 people, and for some items where turnover is high, the threshold has been exceeded. A full list of current items and quantities held can be found in Table 2 below.
1.2 Effective links made with private sector suppliers and public sector/NGO's that enable rapid access to goods, equipment, materials not held in UK stockpile. Links made with potential private sector suppliers and innovators of international humanitarian products. Effective system in place to enable innovation in NFIs to be properly assessed and, where appropriate, brought into standard practice for both DFID and the international community. Ensure supplier agreements allow DFID to access the most effective and proven innovations and inventions available.	Sufficient new and innovative products held to ensure the UK can meet the basic needs of 75,000 people. Supplier Framework Agreements in place. New and innovative products regularly tested and assessed.	CHASE OT has regularly assessed the marketplace for potential new and innovative products to enhance and improve the stockpile, taking advantage of new technological developments. The team has reviewed, tested and ranked 65% of stockpile line items. 14 Framework Agreements in place (covering 36 commodities) to secure rapid competitive procurement and replenishment of goods. Research, testing and feedback from the field ensure items are fit for purpose and meet internationally agreed standards.

Key Points

DFID has called upon the stockpile extensively over the past five years to support numerous emergency humanitarian responses, and it has almost always been used for DFID’s major humanitarian responses. The list below, whilst not exhaustive, gives an idea of how heavily it has been drawn upon.

Table 1: Summary of responses utilising DFID’s stockpile over the past 5 years

Year	Location	Items / Purpose
2013
	Cayman Islands & / Overseas Territories	Hurricane preparedness
	Syria	Crisis preparedness
	Lebanon	Blankets, tents and shelter kits
	Libya, Nigeria and Syria	Armoured vehicles and body armour
	Sierra Leone	Medical consumables for cholera response
2014
	Philippines: Typhoon Haiyan response	Tents, shelter kits, blankets, solar lights, water purification equipment, mechanical handling equipment
	Gaza	Logistics advice and information
	Iraq	Various non-food items
	Sierra Leone: Ebola response	Deployment equipment and ACHE
	South Sudan	Armoured vehicles
2015
	Nepal Earthquake	Over 230 tonnes of NFI’s transported by air, 115 tonnes by road, including over 23,000 shelter kits
	Europe Migration crisis	Over 800 tonnes of aid including blankets, sleeping mats, sleeping bags and tents
	South Sudan	Buckets
	Syria	Solar lanterns and tents
	Iraq	Tents, shelter kits, blankets, lifesaver cubes, solar lanterns, kitchen sets, buckets
	Sierra Leone	Shelter kits, boats and training
	Malawi	Kitchen sets, shelter kits, pole and peg sets
	Vanuatu: Cyclone Pam	Shelter kits, solar lanterns
	Yemen	Armoured cars
2016
	Djibouti	Family tents
	Libya	High Thermal Synthetic Blankets
	Somalia	Pole and Pegs sets, shelter kits
	Haiti: Hurricane Matthew	813 tonnes of aid, including shelter kits, buckets, solar lights, water purification jerry cans and cubes,
	Ethiopia Flooding	808 tonnes of aid, including blankets, shelter kits, buckets, sleeping mats, kitchen sets, water purification cubes and hygiene kits
2017
	Bangladesh: Rohingya crisis	Shelter kits, blankets, sleeping mats
	Overseas Territories and Dominica: Hurricane Irma and Maria responses	Food, water, timber, hygiene kits, solar lanterns and lights, shelter kits, plastic sheeting, buckets, family tents, kitchen sets, water purification cubes, fuel, generators, aqua tabs, flat pack school, trucks, fire trucks, car crusher, VHF radios, VSAT. Restocking RFA Wave Knight and RFA Mounts Bay with shelter kits, jerry cans and hygiene kits.

The size and composition of the stockpile has evolved and increased over the life of the project. It is now up to full capacity and is able to meet the needs of up to 75,000 people. Table 2 below shows the current level of stockholdings.

Table 2: Current Stockholdings (Dubai / UK / India)

Item	Target Stock	Stock Oct 2017[1]	Status
High Thermal Synthetic Blanket	75,000	75,000	Target Met
DFID Kitchen Set	15,000	15,000	Target Met
Pole & Peg Set	15,000	15,000	Target Met
Water Purification Cube	15,000	15,000	Target Met
DFID Tents V4	6,500	6,500	Target Met
14L Buckets (Oxfam spec)	30,000	30,000	Target Met
DFID Shelter Kit	35,000	35,000	Target Met
Solar Lanterns	12,500	12,500	Target Met
Solar Lights	15,000	15,000	Target Met
Sleeping Mats	15,500	15,500	Target Met
Hygiene Kits	15,000	15,000	Target Met
[1] Once replenishment is complete

In addition to the NFI’s listed above, DFID has also procured Air Cargo Handling Equipment (ACHE) which was successfully deployed to the Philippines, Sierra Leone and Nepal. The ACHE is designed to facilitate the quick unloading of aircraft during emergencies when airports can become blocked due to a very large volume of incoming flights with humanitarian assistance. The ACHE is made up of forklift trucks, loading / unloading conveyor belts, cargo dollies and pallet trucks, amongst other things, and is currently stored at Doncaster airport.

CHASE OT established Framework Agreements with suppliers and manufacturers to allow DFID to rapidly procure items during emergencies and to facilitate swift replenishment. Following the 2017 Hurricane Irma and Maria responses all items were replenished through Framework Agreements. In addition to the Framework Agreements CHASE OT holds a Procurement Database of approximately 50 suppliers to facilitate the purchase of low value goods or niche items at short notice during an emergency.

September to November 2014 saw unprecedented emergency procurement in response to the Ebola crisis as the existing Framework Agreements did not cover the specific requirements of the response. New hospital equipment, Personal Protective Equipment (PPE), medical consumable and medicines all had to be procured at very short notice and in huge quantities. This required the use of existing procurement tools and the creation of new ones, heavily emphasising inspection of goods and the use of structured contracting for delivery against demanding timescales. It also required the rapid expansion of warehousing and consolidation facilities, and the control of thousands of inbound line items.

CHASE OT developed an Innovations Filter to assess the products and services presented to DFID on behalf of manufacturers and suppliers for potential use in humanitarian emergencies. Items were assessed to determine if they are fit for purpose, meet relevant international specifications, and offer value for money. Recommendations were then made whether to purchase for the stockpile, or whether the supplier could be approached if needed during a response. A study was also conducted in 2014 to assess the appropriateness of NFI’s held in the stockpile to address violence against women and girls in emergencies with the recommendations resulting in changes to the hygiene kits to better address the needs of women and girls with the inclusion of a menstrual hygiene kit and portable solar light.

Output Title	DFID's Global Stockpile(s) appropriately located and complements the International System's own stockpiles. Implementation of agreed recommendations to support, improve and replace existing international systems.
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones Target (31/10/17)	Progress
2.1 That the UK is assured that the location of the items in the stockpile programme are optimally situated to reduce suffering and morbidity, offer value for money and are resilient.	The UK's Global Stockpile appropriately located to enable the quick deployment of stock to meet the basic needs of 75,000 people anywhere in the world.	The location of the stockpile was reviewed in 2014. Based on access and value for money, Dubai, Kemble, India and Doncaster airports were decided as the best locations. These locations allow DFID to rapidly send relief internationally and at scale.
2.2 DFID held relief items linked effectively with DFID air service provider operations and those of other logistics/transport providers to ensure a seamless supply/deployment process.	New Air Broker Agreement established and utilised for all DFID Air Freight requirements, including passenger services. Innovative solutions considered and established, including direct contact with Aircraft owners.	Industry Day held in July 2015 to inform re-tendering of new Air Broker Agreement that came into effect in February 2016 for cargo, passengers, helicopters and emergency passenger deployments. Agreements made with 7 new providers, so DFID can contract directly, saving time and money.
2.3 Support the development of a system that ensures all members of the international humanitarian community can quickly identify and access NFIs and deployment equipment held by individual organisations in the community.	DFID supports establishment and implementation which substantially improves the information and access agencies have to information about NFI Stockpiles globally.	Progress by OCHA to develop a system allowing all members of the international community to identify and access NFI’s held by others has been slower than originally hoped. The OCHA chaired Emergency Supplies Prepositioning Strategy (ESUPS) Working Group is working to bring about greater cohesion amongst the humanitarian community. It has identified a pilot project that will be the focus of 2018. Improvements made to the NGO Portal has provided accurate and up to date information on DFID stockpile to RRF partners.

All stockpile locations have been kept under regular review throughout the lifetime of the project. The stockpile is currently split across 5 sites: Kemble Disaster Response Centre, East Midlands Airport, Dubai Jebel Ali Free Zone, New Delhi, India and Doncaster Airport. Warehouse facilities at Kemble are currently leased, and storage at Dubai is provided by a third party logistics provider, with the cost of storage varying depending on volume of goods stored at any one time.

The location of the stockpile was reviewed in 2014 to check that stocks were stored in strategic locations based on their proximity to DFID’s regions of interest and at risk countries; transportation and warehouse hubs; flexibility and knowledge of our business needs; and value for money. The review concluded an agile and flexible approach was required and that Dubai remained the optimal location for the majority of DFID’s NFI’s. Hong Kong, Malaysia, and Singapore were all considered, but ultimately rejected in favour of Dubai based on its warehousing costs and customs procedures.

Dubai is a favoured location for many humanitarian organisations due to its central location, the country's excellent reputation as freight and logistics hub, its large Freezone area (allowing storage of goods without duty / taxes imposed) and relatively good value for money for storage and labour costs. DFID’s current policy to store its NFI’s outside the UN system has proved sound and allowed DFID to avoid bottlenecks experienced by the UN, whilst allowing DFID the independence to respond on its own terms and to its own time lines. Some of DFID’s NFI’s are now being stored with suppliers, generating savings for DFID on storage costs. For example, some shelter kits and High Thermal Synthetic Blankets are currently stored with the supplier in New Delhi, India.

Following confirmation that Dubai remained the best location for DFID’s NFI’s, CHASE OT investigated options to strengthen transport arrangements and how to make greater use of scheduled airlines to move items from suppliers and to provide a more integrated response capacity. In July 2016 CHASE OT held an Industry Day for airlines and air brokers to discuss and present ideas about how DFID’s air logistics requirements could be best met. The aim of the day was to get the air industry to present new and innovative solutions to enable DFID to achieve faster, more effective and efficient responses by air. The findings from the day were used to inform the re-tendering of a new Air Broker Agreement, designed to be able to quickly and reliably deliver DFID’s emergency relief stocks. The new contract came into effect in February 2016 and includes agreements with 7 providers based on their skills, aircraft capabilities and geographical coverage. Work will need to begin in 2018 to put in place a successor arrangement.

During the recent response to Hurricanes Irma and Maria five international air charters and twenty inter-Caribbean air charters for the movement of goods were organised under the Air Broker Agreement. These charters allowed DFID to provide reliable freight movements to bring goods to the affected communities. These flights added capacity to the overall HMG response, in support of MOD assets. Additionally, DFID was able to provide passenger movements, and for a number of weeks the inter-island capability was the only movement option for staff (internal and external), and became the ‘go to’ airline for aid workers travelling to the affected areas. The international charters to the Caribbean also reduced the stresses and bottlenecks around the region, thereby complimenting the response.

The option of storing some goods at airports in the UK was explored to reduce overall storage costs and to speed up response times when using civilian and military aircraft. Doncaster and East Midlands airports were chosen based on: their ability to offer secured covered low cost or free storage; security screening; ability to repackage goods, dispatch aircraft internationally; and dispatch pre-screened stocks to alternative airports (including MOD sites) in secure vehicles. Trailers have now also been situated at Doncaster airport containing shelter kits, ready for loading on to aircraft. They can also be quickly transported to an alternative airport such as RAF Brize Norton, minimising handling delays.

CHASE OT has regularly reviewed the NFI’s held by the international community but has identified a number of common shortfalls, including: (i) lack of global buy-in, meaning that not all agency’s stock is mapped which reduces the accuracy and scale of reported stocks; (ii) a lack of commodity standardisation, making it difficult to compare stocks as they are not like-for-like; (iii) the lack of a platform where up-to-date or real time information can be recorded and shared; and (iv) no real system to enable inter-agency use of the different stockpiles.

OCHA has undertaken its own Stockpile Mapping review, which included consultation with stakeholders from across the humanitarian community, including DFID. The issue was also discussed at the Emergency Supply Chain (ESUPS) working group at the Humanitarian Networks and Partnerships Week (HNPW) meeting in Geneva in 2016, when it was clear that many of the same challenges still remain. OCHA are planning a small scale regional pilot to address the shortcoming identified. This is an area that has not seen as much progress as originally hoped, and it was ambitious to attempt to rectify this through a programme focused on stockpile management. Going forward, under the HEROS contract, DFID should commission HSOT to propose what further support it can offer OCHA in this area, and where HEROS can have maximum effect on international stockpile management.

In the absence of an effective international mechanism, DFID has worked to improve awareness amongst others about its own stockpile. In 2017 Rapid Response Facility (RRF) partners were provided with information about DFID’s NGO portal, including information about how to access and request items held in DFID’s own stockpile. Improvements have also been made to the DFID NFI catalogue, and DFID regularly liaises with other donor organisations, including USAID. During the recent Hurricane Irma response in the Caribbean DFID requested information on movements from others to better understand other donor’s pipelines, reducing the risk of duplication.

DFID regularly shares performance testing with partners on items held within the stockpile to encourage improvements to partner NFI specifications. An example of this is Save the Children who had adopted DFID’s Family Tent as their standard tent. Throughout the life of the HEPP, DFID has shared its improvements and innovations within its own stockpile with OCHA and other appropriate partners to demonstrate good practice and encourage improvements across the community.

Output Title	Implementation of agreed recommendations on standards and dissemination and compliance.
Output number per LF		3 low	Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones Target 31/10/17	Progress
3.1 Effective system in place to establish and monitor minimum acceptable standards for shelter materials and NFIs provided in response to emergencies.	Any recommended changes are made to DFID's funding policies. Influence humanitarian community to improve standards, promote best practice and quality in the sector, collaboration and coordination through regular one-to-one and cluster meetings.	Items held in DFID’s stockpile developed over time to meet or exceed internationally agreed quality specifications. Testing, inspection and monitoring ensure standards are maintained. CHASE testing shared with rest of humanitarian community to encourage improvement and best practice in the sector. For example: DFID tent technical specifications have been shared with NGO partners.

The composition of the stockpile has been developed from extensive experience over the duration of project (and before). Items that are held are those most frequently required in disasters that are cost effective to store and transport. Items such as hygiene kits and water purification equipment have been developed following consultation with DFID’s WASH advisers. The specifications of items are related to minimum standards such as Sphere, with commodities brought in to the stockholding reflecting DFID’s policy priorities e.g. Violence Against Women and Girls (VAWG).

The NFI’s that are held in DFID’s stockpile must meet certain quality specifications, and stocks are regularly monitored and inspected by CHASE OT to ensure standards are maintained. DFID stocks meet, and often exceed, international standards and specifications. For example plastic sheeting, blankets and kitchen sets are all procured to the specifications set out in the International Federation of the Red Cross (IFRC) catalogue. Buckets are procured to Oxfam’s specification, which is generally regarded as the benchmark. As well as inspecting goods before delivery, stocks are also regularly rotated to ensure shelf life is not exceeded.

CHASE OT undertake detailed lab testing, sampling, batch inspection and monitoring visits to the field to ensure all goods are up to standard and perform as expected. All goods are benchmarked against relevant standards, and pharmaceuticals must adhere to Medicines and Healthcare Regulatory Agency (MHRA) licensing standards. Health and safety law, Sphere and European and British standard must also be complied with.

Where common standards do not already exist, CHASE OT has undertaken laboratory and field testing to help develop new standards. During the project testing was conducted on: solar lights, fire retardant tents, clean cook stoves, and lightweight insulated mats. The results of this testing is regularly shared with the wider international community to help improve the quality of items procured by others. DFID has commissioned research and testing into a number of commodities in order to make improvements and take advantage of new technologies or innovations in the sector. This has included testing the fire retardency of plastic sheeting, water filtration devices and deployment communications.

All NFI’s within the stockpile carry a DFID ID mark to ensure specifications are adhered to. This allows goods to be traced back to the manufacturer or supplier, and includes information such as location, batch number and expiry dates. This helps improve accountability, allowing the performance of items in the field to be monitored and assessed. The ID mark also allows the commodity to be inspected at source.

Output Title	DFID held stocks support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments.
Output number per LF		4 low	Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones Target 31/10/17	Progress
DFID has the equipment and resources in place to enable the immediate deployment of up to twenty people to a range of environments and which can be scaled up in line with changing UK response capability. Instigate on-going review and testing of innovations and emerging technology in deployment platform holdings to ensure they are properly assessed and, where appropriate, brought into standard stock holdings - and referred to other relevant actors in the international humanitarian community and UKTI as appropriate.	DFID deployment equipment continually improved and is kept current and up to date with the latest technology available, including review of deployment module post Triplex exercise.	The module now has greater communications capability and is able to operate VHF security networks and DFID phone networks over the comms system. The module has cleaner, more sustainable power supplies through the use of solar generators, and CHASE OT has developed new solutions for Water, Sanitation and Hygiene (WASH) and catering, enhancing life support and reduce likelihood of illness. The modules can support 20 people for three months.

CHASE holds equipment to deploy up to twenty DFID staff and its contractors during emergencies. This is comprised of:

- Personal Protective Equipment (PPE), first aid and vehicle trauma kits;
- Personal communications, such as sat phones;
- Vehicles, including armoured vehicles (petrol and diesel), trucks, 4x4, minibuses, and forklifts;
- Field support equipment such as radios, sat phones and generators, accommodation, office, cooking and washing facilities
- 1 large office module and 3 smaller modules as well as a fleet of vehicles and a pool of smaller scale deployable equipment such as first aid kits.

The Deployment Kit is kept under regular review with changes and improvements made following lessons learned from responses during the project include:

- The deployment module is now mounted on remote controlled trailers, reducing the risk of damage by manual handling (the module is designed for ease of aircraft loading).
- The introduction of a solar generator and power pack, allowing the generator to be shut down at night, saving fuel;
- Battery powered solar LED lighting, enabling night time lighting of the camp;
- Digital VHF radios, which include a tracking system for staff;
- An easy to erect radio mast usable with multiple frequency bands simultaneously
- Lightweight and portable VSAT (2-way satellite communications system), giving broadband and videoconferencing capabilities, integrated into the Vodaphone ECHO network allowing DFID’s telephone system to be used;
- Remote controlled, battery powered turnable trailers, which facilitate packing and unloading;
- Quicker to erect waterproof tents with cold weather insulation and semi-rigid flooring;
- Shower cubicles with solar heated water bladders and manual foot pumps.

The deployment module was tested effectively during a simulated emergency exercise in 2016 (Triplex) with lessons learned leading to introduction of protocols for using satellite communications. Items from the module were also used during the recent Hurricane Irma and Maria responses.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The principle cost drivers for the project remain in line with those set out in the original Business Case, namely the costs of the additional items procured to increase the capacity of the stockpile, and the cost of warehousing and routine maintenance at Dubai and Kemble. The cost of warehousing at Dubai varies depending on the amount of stock stored, so some savings can be made following a response when stocks are low.

Where increased quantities of NFI’s have been procured, CHASE OT have done this through open competitions and tender processes, testing the market to ensure DFID is receiving good value for money. The Framework Agreements have facilitated the swift and cost effective procurement and replenishment following a response.

Cost: Most items in the stockholding have been procured through competitive tender procedures or Framework Agreements to ensure fair pricing. These have produced some significant savings, as detailed below:

- Sleeping Mats: following rigorous independent testing of framework providers for sleeping mats, the cheapest supplier was also judged to offer the best overall performance, producing savings of £236,596 over the original cost estimate of £300,000;
- Hygiene Kits: by splitting the contracts and awarding contracts to 4 different suppliers instead of purchasing as a full kits, savings of £185,000 were made against the original cost estimate of £450,000;
- Kitchen Sets: competition under the Kitchen Sets framework agreement produced savings of £118,000 against original cost estimates.
- Water purification: negotiated a discount for refurbishing Lifesaver Cubes with new owners ICON Lifesaver, saving £128,265;
- EU Rebates: working closely with the Cabinet Office to secure rebates of up to 85% on humanitarian freight movements from the EU. For the Irma & Maria response alone this amounted to £195,000.

Building up the stockpile to its current capacity, and maintaining it, is however not cheap. Whilst costs associated with the uplift have been met from the HEPP, costs for replenishment have generally been met from response budgets. There may be potential to make greater cost savings in the future by storing more items with suppliers and manufacturers.

Speed: Most emergency relief items need to reach affected communities rapidly in order to relieve suffering and save lives. Once a decision to send UK NFI’s from the stockpile items can be in the affected country within 48 – 72 hours if transported by air. The location of Dubai, where most DFID items are held, as well as being a transportation hub, is advantageous as it is geographically close to many countries in Asia or Africa that are likely to need assistance. Kemble and its proximity to East Midlands airport also facilitates swift transportation by air, and if military assets are being used Brize Norton is also relatively close. Once the items have arrived in-country swift clearance through customs and rapid onward transportation is essential to justify the cost of air transportation. There have been occasions, such as the Ethiopia flooding response, where items were flown from the UK and ended up held in warehouses in-country for long periods of time, arguably not justifying the additional air transportation costs. Ensuring there are clear plans for the onwards transportation and distribution is a lesson for future responses.

Quality: As previously set out, an important feature of the HEPP has been improving the quality and range of NFI’s held within the stockpile. This has been achieved through reviewing and testing commodities in the lab and field, learning lessons from responses, and taking advantage of new technology. All NFI’s held in DFID’s stockpile meet certain quality specifications and are monitored and inspected by CHASE OT. Sphere and European and British standard must be adhered to. DFID’s plastic sheeting, blankets and kitchen sets all meet IFRC specifications, and buckets meet the Oxfam standard. CHASE OT also undertakes sampling, batch inspection and monitoring visits to the field to ensure all goods perform as expected. All goods are also discretely marked, allowing their performance to be assessed in the field and the item traced back to the original manufacturer. Feedback from the field in Ethiopia, and also following the Irma Response, praised the high quality of UK NFI’s.

Assessment of whether the programme represented value for money

The programme is considered to represent good value for money for DFID and the UK taxpayer. The stockpile remains the backbone of many UK Government humanitarian responses, evidenced by the long list in Table 1. It is an important tool for UK bilateral responses and has provided lifesaving assistance to vulnerable people in emergency situations giving them some basic degree of shelter, comfort, safety and dignity.

Quality of financial management during programme

DFID and CHASE OT meet monthly to discuss the progress of the project, including monitoring expenditure against the budget. CHASE OT produced monthly forecasting and expenditure reports upon which DFID’s forecasting was then based. At times it has proved a challenge to determine an accurate spend position for the project, partly due to the time that it takes Crown Agents to pay suppliers and then pass these costs on to DFID for reimbursement. When queries arose, DFID and CHASE OT would sit down and work through the figures in order to agree an accurate spend position.

E: RISK

Quality of risk management over the life of the programme

The risk level of the project has reduced from moderate during the first two years of the project to minor now. The moderate assessment was linked to the ambition to drive up the quality of procurement in the overall humanitarian system. This is clearly a challenge. Whilst DFID has shared the results of its testing and best practice with the rest of the humanitarian community, as stated earlier, progress by OCHA to develop a system allowing all members of the international community to identify and access NFI’s held by others has progressed more slowly than originally hoped. As a result DFID has done what it can to improve its own stockpile, share best practice and make it open and available to others.

The minor assessment reflected the fact that the project was being managed and delivered by an experienced and competent Crown Agents Procurement and Logistics team. Crown Agents was one of DFID’s three approved procurement agents with stringent anti-corruption and anti-bribery policies in place. The project also built upon a series of earlier projects known as Stockpile projects 1 -5, which were also managed by the same CHASE OT team.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The uplift to the project agreed in 2014 has been delivered (or exceeded) on time and as planned, and the stockpile now has the capacity to meet the needs of up to 75,000 people. The uplift triggered the 2 year extension, as set out in the original Business Case. The end date for the project was brought forward to 31 October 2017, to align with the end date of the HEOSS contract.

Performance of partnership(s)

Crown Agents Procurement and Logistics Team have delivered the project on behalf of DFID on time and on budget. The team has consistently demonstrated its depth of experience and expertise over the duration of the project, organising the delivery and onwards transportation of NFI’s to many remote corners of globe, often under extreme pressure, political scrutiny, and working to very tight deadlines. The recent Irma and Maria response showcased the team at their best, procuring a large range of diverse and often non-routine items for the Caribbean response. This was achieved whilst also concurrently responding to emergencies in Somalia and Bangladesh.

Crown Agents agent status has had both positive and negative consequences in terms of commercial risk. Being an agent has provided DFID with assurances of Crown Agents implementing competitive procedures, however, in times of response it has also led to the need for waivers for single sourcing. CA’s agent status has also left DFID liable for supply chain risks (e.g. product liability) which is not DFID’s preferred position, and has been changed under the new HEROS project.

Asset disposal and value obtained by DFID

Ahead of the end of the current HEPP programme CHASE OT recommended the disposal of various items in the warehouse at Kemble that were no longer needed or required. Use by dates had either expired, items had never been used, or they were taking up valuable storage space. Any items that were potentially useful were donated to local groups (such as the scouts), with the rest disposed of responsibly at minimal or zero cost to DFID (the value of item often equalling the disposal cost). Assets procured under the HEPP have now been transferred to the new HEROS project, and a stocktake was undertaken to check accuracy of the inventory which was found to be 99.5% accurate.

G: CONDITIONALITY

Partnership principles assessment
N/A

H: MONITORING & EVALUATION

Evidence and evaluation

Throughout the duration of the HEPP programme, CHASE OT has worked with DFID to collect evidence of the impact that DFID’s NFI’s have had in enabling CHASE to deliver on its mandate to save lives and protect vulnerable people in the aftermath of humanitarian crises. Through a regular field presence of both civil servants and Crown Agents staff, DFID has been able to collect evidence of the impact NFI relief items have delivered demonstrating that the project has delivered value for money. Previous Annual Reviews present evidence of both employing rigour in contracting, value for money in goods and services, and nurturing innovations in NFIs. Much of this evidence is summarised in this PCR and should be taken into consideration as DFID moves forward with the HEROS contract.

Monitoring progress throughout the programme

DFID teams have provided consistent monitoring of the NFI’s delivered during rapid onset responses. Members of the CHASE OT Procurement and Logistics team have deployed alongside DFID Humanitarian Advisers to ensure that NFI reaches the targeted communities. DFID has also been able to ensure consistent post distribution monitoring, conducting beneficiary feedback on the quality and appropriateness of NFIs distributed. Joint DFID, CHASE OT monitoring teams have followed the NFI’s to the end user and verified that our partners targeted assistance appropriately. Field monitoring fed into lessons learning, allowing HRG to adjust programmes. Regular monitoring has also permitted the Procurement and Logistics team to improve the quality of NFI’s which DFID provides. This rigour has extended to regular visits to suppliers to quality assure NFI items which DFID procures and monitoring reports have contributed to CHASE’s learning processes.