## Impact
PROJECT NAME | Programme for Improving Mental Heath Care
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (12m) | Milestone 2 (Year 4) | Target (end RPC) | Milestone 2 (end year 7) | New Target (end of Extension)
The widespread implementation of mental health programmes which improve the health and socio-economic status of individuals, particularly women and those living in poverty. | # of programmes in study countries and other countries which have used PRIME evidence to inform their implementation | Planned | 0 programmes using RPC evidence | Completion of draft integrated mental health care plans | 1 programmes using RPC evidence per study country | ≥3 programmes using RPC evidence per study country, ≥3 programmes in mhGAP countries using RPC evidence | ≥4 districts using RPC evidence per study country, ≥ 7 programmes in other countries using RPC evidence or methods | ≥4 districts using RPC evidence per study country, ≥ 9 programmes in other countries using RPC evidence or methods
|  | Achieved |  | 0 programme per study country | PRIME MHCPs implemented in one district/sub-district per study country | Between 3 and 51 districts per study country and at least 5 programmes in non-PRIME countries
|  | Not applicable | Source
Ministry of health and WHO partners; survey of awareness, adoption and utilization of RPC evidence by key audiences
| Impact Indicator 2 |  | Baseline | Milestone 1 (12m) |  | Target (end RPC) |  | New Target (end of Extension)
| % of national health budget spent on mental health in study countries | Planned | Ethiopia= 1.7% [1] Nepal= <1% [1] India(Madhya Pradesh) = 2.03% [1] Uganda=1% [1] South Africa: 2.5% [2] | As per baseline |  | 20% increase in mental health funding as % of national health budget (Ethiopia=2.04%, Nepal=1.2%, India (MP)=2.5%, Uganda=1.2%, SA=3%) |  | There is evidence for increased mental health spending by the Ministry of Health in four PRIME countries (e.g. additional psychotropic medications or staff, buildings, training, etc.)
|  | Achieved |  | As baseline |  | There is strong anecdotal evidence for an increase in budget in Ethiopia , Madya Pradesh, India and Nepal (see report for details).
Source
[1]WHO AIMS 2006 , Lund et al. 2010, WHO Atlas, MoH partners if available
| Impact Indicator 3 |  | Baseline | Milestone 1 (12m) | Milestone 2 (Year 4) | Target (end RPC) | Milestone 2 (end year 7) | New Target (end of Extension)
| Extent to which PRIME outputs contribute to mental health aspects of international development targets beyond 2015 | Planned | Mental health not currently mentioned in the MDGs | As baseline | PRIME research products are cited in at least one mental health policy document which contribute to development goals by international development agencies | PRIME research products are cited in at least ≥2 mental health policy document which contribute to development goals by international development agencies | PRIME has evidence of impact at the international level with PRIME evidence cited in ≥10 key documents ( policies, guidelines, practise, plans, strategies, roadmaps and/or leadership initiatives, and products included in treatment guidelines) | PRIME has evidence of impact at the international level with PRIME evidence cited in ≥12 key documents ( policies, guidelines, practise, plans, strategies, roadmaps and/or leadership initiatives, and products included in treatment guidelines)
|  | Achieved |  | As baseline | PRIME cited in 2013 WISH report and the Disability and Development Inquiry in April 2014 | PRIME research products are cited in 8 policy document which which are likely to contribute to development goals by international development agencies
Source
Analysis of policy documents for MDGs and new international development targets beyond 2015

## Outcome
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end RPC) | Milestone 2 (end year 7) | New Target (end of Extension) | Assumptions
World class research evidence on implementation and scaling up of treatment programmes for mental disorders is adopted by policy makers & practitioners for the benefit of the poor including mothers. | Use of research evidence from PRIME in key policy documents, plans, speeches in the study countries | Planned | No evidence from PRIME is available. | 4 citations in key documents | 2 citations in key documents | Changes made to policy and practice in mental health reflect RPC evidence | Additional changes made to policy and practice in mental health reflect RPC evidence | PRIME has influenced at least one policy, guideline, practise, plan, strategy, roadmap and/or leadership initiative, or product inuded in treatment guidelines at the sub-national level or national level in each PRIME country (A1) | Governments and other stakeholders in study countries have the commitment, resources, and infrastructure to implement appropriate evidence based policies, programmes and practices. Programme improvements based on RPC evidence are sufficient to drive changes in impact of this magnitude, if other factors affecting these indicators remain constant.
|  | Achieved |  | PRIME evidence used in 1 key policy document | PRIME cited in 4 key policy documents and speeches. | Changes to policy and practice in all study countries have been influenced by PRIME evidence (see report for details)
Source
Assessment of key policy documents, plans, speeches and media reports, as documented in annual reports. Survey of awareness, adoption and utilization of RPC evidence by key audiences reported in RPC final report.
| Outcome Indicator 2 |  | Baseline | Milestone 1 (4 years) | Milestone 2 (Year 5) | Target (end RPC) | Milestone 2 (end year 7) | New Target (end of Extension)
| % men and women suffering from priority mental disorders in study AHUs who receive evidence-based treatment. | Planned | Accurate data not available | 25% more men and women with priority disorders in primary health care clinics in PRIME study AHUs receive evidence based treatment compared to baseline | 25% absolute increase in % treated in PRIME AHUs | 50% absolute increase in % treated in the PRIME AHUs | There is an average 120% relative increase in the number of people identified with a mental illness in heath facilities the scale up areas after 12 months compared to baseline | (Data collection no longer ongoing in year 8)
|  | Achieved |  | There has been an average increase of 239% in monthly mental health visits in the PRIME Implementation facilities | 115% increase in % treated in PRIME health facilities | There has been a 590% relative increase in monthly mental health visits between baseline and the end of implementation. |  |  | Strategies are in place to manage staff turnover and ensure the sustainability of the programme
Source
PRIME AHU intervention evaluations
| Outcome Indicator 3 |  | Baseline | Milestone 1 (4 years) | Milestone 2 (Year 5) | Target (end RPC) | Milestone 2 (end year 7) | Target (end RPC)
| Key stakeholders (including policy makers, donors) attribute a change in their policy and practice to PRIME | Planned | Nil effect |  |  | Key stakeholders (including policy makers, donors) attribute a change in their policy and practice to PRIME | Policy makers attribute a change in their policy and practice to PRIME | (Data collection no longer ongoing in year 8) | Research uptake can be appropriately assessed
|  | Achieved |  |  |  | Preliminary data from Nepal show evidence that PRIME has influenced policy. Formal research uptake evaluaiton in process.
Source
Interviews with key policy makers (year 6 and 7)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| £8m |  | Still to be confirmed. | New resources to be mobilized | Expected to exceed £12M | 50%
INPUTS (HR) | DFID (FTEs)

## Output 1 RPC Management
OUTPUT 1 -RPC MANAGEMENT | Output Indicator 1.1 |  | Baseline | Milestone 1 (6m) | Milestone 2 (Year 1) | Target (end year 6) | Milestone 2 (end year 7) | New Target (end of Extension) | Assumption
Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose. | Proportion of the following key RPC deliverables completed in consultation with all consortium partners: - Contracts between partners - PRIME country personnel recruited - M&E framework including logical framework refined - Detailed financial management plan for Phases 2 and 3 - Capacity Building Plan agreed - Research uptake Plan agreed | Planned | None | MoU completed. PRIME personnel recruited Financial plan finalised Capacity building strategy finalised Communications strategy finalised Log frame finalised | 100% inception phase documents/ activities completed. Annual activity plan and inception phase report completed and approved by DfID. | Key programme documents have been reviewed and revised as needed during project to improve progress towards achieving outputs, purpose and goal of RPC. | Key programme documents have been reviewed and revised as needed during years 7 and 8 to improve progress towards achieving outputs, purpose and goal of RPC. | Key programme documents have been reviewed and revised as needed during years 7 and 8 to improve progress towards achieving outputs, purpose and goal of RPC. | Transitions to new staff are managed when staff move to other countries/settings/roles
|  | Achieved |  | Financial plan finalised, contracts with partners drafted | Contracts between partners completed, PRIME country personnel recruited, M&E framework finalised, research uptake and capacity building plan finalised, annual activity plan and inception phase report submitted to DFID | Key programme documents (publication policy, expresison of interest policy) and processes (meeting structure, lines of accountability) have been reviewed and revised as needed during project to improve progress towards achieving outputs, purpose and goal of RPC. | Progress at end of year 6: Key programme documents (publication policy, expression of interest policy) and processes (meeting structure, lines of accountability) have been reviewed and revised as needed
Programme documentation, Tracked by RPC and reported annually in annual reports.
| Output Indicator 1.2 |  | Baseline | Milestone 1 (4m) | Milestone 2 (6m) | Target (12m) | Milestone 2 (end year 7) | New Target (end of Extension)
| Number of meetings held during inception phase of key governance groups (PMG; CAG; CMG) | Planned | None. | All groups constituted with TORs | At least one meeting, either face to face or by teleconference | At least two meetings, one of which is face to face | All groups have continued to meet as planned during the life of the consorotium ( 4 meetings annually of the PMG, 2 meetings annually of the CAG and monthly CMG meetings) | All groups have continued to meet as planned during the life of the consorotium ( 4 meetings annually of the PMG, 2 meetings annually of the CAG and monthly CMG meetings)
|  | Achieved |  | PMG:constituted with ToR, 1 face to face meeting | PMG: 2nd meeting; CAG: constituted with ToR, 1 teleconference, CMG constituted in all countries | PMG: 3rd meeting (1 Face-to-face) , CMG: at least one meeting in each PRIME country | Progress at the end of year 6: We have conducted 4 meetings per year of the PMG (with monthly meetings of a core group), 2 meetings annually of the CAG and monthly or more frequent meetings of the CMG. |  | Stakeholders /beneficiaries available and interested in participating in meetings.
External governance groups are capable of providing effective oversight to RPC.
Terms of reference available and agreed, meeting minutes
| Output Indicator 1.3 |  | Baseline | Milestone 1 (6m) | Milestone 2 (10 m) | Target (Year 1) | Milestone 2 (end year 7) | New Target (end of Extension)
| Draft mental health care plans for priority disorders in primary care and maternal care available. | Planned | Recent synthesis and reviews of the evidence. | Six articles involving PRIME members for the new Lancet series on global mental health are submitted | Formative research studies completed with decision makers. Completion of modelling of the delivery of packages of care in primary care. | Completion of a draft integrated mental health care plan comprising packages of care for mental disorders for delivery in primary care. | Data analysis of outcome data from implementation phase completed towards revising integrated mental healthcare plan | Completion of a revised integrated mental healthcare plan based on results from the implementation and scale up evaluations. | RPC partners are able to give sufficient time to the project and are able and willing to fulfil their commitments.
|  | Achieved | PRIME partners participated in review of evidence for Lancet 2011 series on GMH, Plos Medicine series and mhGAP | PRIME partners were authors on 4 papers and the series of six articles was edited by Prof Patel | The formative research process has been extended to include some of the research from the initial part of the implementation phase - the formative research plan has been completed and is underway. We anticipate the research will be finished in May | Each country has completed a draft mental health care plan based on the situational analysis and initial theory of change workshops. This will be refined with the results of the situational analysis. | Progress at the end of year 6: The PRIME Mental healthcare plans were finalised prior to the implementation phase. Data analysis of our evaluation data is underway so we can use this to refine the PRIME MHCPs.
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
100% for year 1; thereafter 10% |  |  | Lancet 2007 series on Global Mental health, PLoS Medicine series, WHO-WONCA review and mhGAP. | Draft papers for the Lancet series on global mental health 2011. | Draft publications on formative research and modelling. Lancet 2011 series launched | Draft mental health plan comprising packages at each level of health care . |  |  | High impact and low probability of occurrence.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 1500000 |  | n/a |  |  | 100%
INPUTS (HR) | DFID (FTEs)

## Output 2 Research
OUTPUT 2 -RESEARCH | Output Indicator 2.1 |  | Baseline | Milestone 1 (12m) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | New Target (end of Extension) | Assumptions
A coherent body of high quality, peer-reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders | Research project is implemented in countries (d1) | Planned | Research proposal agreed on by all partners | Formative research plan finalised and under way in countries | Cohort studies complete in all PRIME districts by the end of year 5 | Evaluation of scale up completed in additional districts in 3 PRIME countries | Contributions to the WHO mhGAP Operations manual, including use PRIME tools and examples and contributions to content and structure of manual. Scale up data collection completed in three countries. Data analysis completed for main outcomes of PRIME implementation phase. (Target: 84% of projects in analysis phase or completed) | Evaluation of scale up completed in 4 PRIME countries. All research projects completed or at analysis stage. (Target 45% projects completed and 53% in analysis stage) | MoH partners are willing and able to participate in the scaling up phase.
|  | Achieved |  | Formative research plan finalised and under way in countries | Baseline studies have been completed in all study countries and MHCPs implemented in all five countries. Cohort recruitment is ongoing and endline studies due for completion end 2016 | Evaluation of scale up has been completed in South Africa. Baseline data collection has been completed in Ethiopia, Nepal and South Africa. |  |  | Any turnover in health staff is well-managed and does not impact on the programme implementation or quality
Source
|  | Programme documentation, meeting minutes and results of evaluation. | [6 empty] | Political buy-in is obtained despite competing priorities.
| Output Indicator 2.2 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | New Target (end of Extension)
| # of high quality policy relevant primary research papers by RPC partners published in peer reviewed publications (A3).# of conference presentations by RPC partners. | Planned | None | 4 papers published, 3 conference presentations | 20 papers published, 10 conference presentations | 65 papers published, 55 conference presentations | 75 papers published (80% with a LMIC home institution lead or co-author; 80% with a Female lead or co-author; 70% with a Female LMIC home institution lead or co-author, 70% open access) (A3), 65 conference presentations | 85 papers published 80% with a LMIC home institution lead or co-author; 80% with a Female lead or co-author; 70% with a Female LMIC home institution lead or co-author, 70% open access) (A3), 70 conference presentations | The countries and their health systems remain stable enough to implement, evaluate and scale up the programme
|  | Achieved |  | 11 papers pubished and 12 conference presentations | 26 papers published, 19 conference presentations, 4 conference poster presentations and 1 conference film presentation | 62 papers have been published and we have presented at 59 conferences.
|  | Source | [6 empty] | Ethical approval and other clearances are obtained as necessary throughout the programme
PRIME Quarterly reports, minutes of meetings
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | Target (end RPC)
50% | No of partner insitutions who collaborate and publish with each other. (E7) | Planned | Average no. of partner institutions who have collaborated and published together =2.4 in 2010 | No. of partner institutions who have collaborated and published together increases to 7 | All partners have collaborated on publications between 2013 and March 2015 | The number of partner instiutions who have collaborated on a non-PRIME output >5 |  | The number of partner instiutions who have collaborated on at least 2 non-PRIME outputs >5
|  | Achieved |  | All 9 partner insitutions have collaborated and published a paper together | The majority of partners have colloaborated with each other (see details in annual report) | All nine PRIME partners have collaborated on a non-PRIME output with another PRIME partner.
Source
Citation analysis of published papers using Scopus database
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  | RISK RATING
| 2500000 |  | Still to be determined | Still to be mobilised | Expected to exceed £6000 000 | 50% |  |  | High impact and low probability of occurrence
INPUTS (HR) | DFID (FTEs)
13.2417

## Output 3 Research Uptake
OUTPUT 3 -RESEARCH UPTAKE | Output Indicator 3.1 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | New Target (end of Extension) | Assumptions
Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle-income countries. | # of PRIME products disseminated to policy makers and donors across relevant sectors via multiple channels (conferences, high level briefings, workshops etc.) at the following levels: Local, National, International (A4, D2, D3) | Planned | None | At least 5 PRIME products disseminated to policy makers and donors | At least 15 PRIME products disseminated to policy makers and donors | at least 50 PRIME products disseminated to policy makers and donors. At least 2 PRIME research results adopted into policy in the study countries | At least 95 PRIME products disseminated to policy makers and donors; At least 18,500 page view (disaggregated by UK based, LMIC based or other) since the start of the RPC. PRIME team describe what they have identified as the top 5 most effective research uptake (e.g. engagement/dissemination) activities that they have been carried out in the reporting period. | At least 110 PRIME products disseminated to policy makers and donors; At least i) 20,000 page views and ii) 200 downloads on websites and blogs (disaggregated by UK based, LMIC based or other) since the start of the RPC. (Downloads will only be counted from the revision of the website in Sept-Nov 2017);PRIME team describe what they have identified as the top 5 most effective research uptake (e.g. engagement/dissemination) activities that they have been carried out in the reporting period.
|  | Achieved |  | 11 PRIME products were disseminated to policy makers (11), and donors (5) | 21 PRIME products disseminated to policy makers and donors | 80 PRIME products (these include policy briefs, website articles, research tools, newsletters, posters, brochures and infographics) have been disseminated to donors, policy makers and other relevant stakeholder groups. As described above, in terms of influence on written policy, Ethiopia is using PRIME evidence to inform their input on the revised National Mental Health Strategy, the national mental health policy in Nepal and South Africa, PRIME partners are currently using PRIME evidence to inform their input into the implementation of the National Mental Policy Framework and Strategic Plan and the Western Cape Provincial Policy and Plan. |  |  | Prime research is relevant to other LMIC
Source
|  | Quarterly reports and programme documentation | [6 empty] | PRIME is able to attract policy makers to key events.
| Output Indicator 3.2 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | New Target (end of Extension)
| Participation of mental health service users and community groups in mental health care | Planned | No mental service user groups exist in districts, minimal participation of service users in planning or delivery of mental health care | At least two specific engagement activities occur with service users at the district, including participation in the community advisory board | MH service users represented on the Community Advisory Board in all districts | MH service users taking an active role in service planning or delivery of mental health care in all the districts | MH service users taking an active role in service planning or delivery of mental health care in all PRIME countries | MH service users taking an active role in service planning or delivery of mental health care in all PRIME countries | MH service users are well enough to participate in service planning and delivery of mental healthcare
|  | Achieved |  | 8 engagement activities amongst service users, including participation in community advisory board | Caregivers of people with mental illness have attended or plan to attend CAB meetings in Ethiopia, India and Uganda | MH service users have been involved in service planning or delivery of mental health care in all the districts (see report for details)
|  | Source |  | Quarterly reports, monthly implementation logs, communication with partners
Situational analysis, CAB minutes, possible interviews with service planners/users, Most Significant Change Method
| Output Indicator 3.3 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | New Target (end of Extension)
| # of PRIME citations in the media | Planned | None | At least 6 media citations of PRIME or PRIME outputs | At least 50 media citations of PRIME or PRIME outputs | At least 160 media citations of PRIME or PRIME outputs | At least 200 media citations of PRIME or PRIME outputs | At least 225 media citations of PRIME or PRIME outputs
|  | Achieved |  | 32 Citations in Print, Web, Radio and TV. | 61 citations of PRIME in the Media | We have achieved 173 media citations of PRIME and PRIME outputs in local and international media.
Source
Media citation analysis, google analytics
| Output Indicator 3.4 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) | Milestone 3 (end year 7) | New Target (end of Extension)
| # of citations of PRIME outputs in research articles or other academic publications, curricula or training materials | Planned | None | 5 citations of PRIME outputs | 150 citations of PRIME outputs | 650 citations of PRIME outputs | 950 citations of PRIME outputs | 1100 citations of PRIME outputs | Press releases match media priorities
|  | Achieved |  | PRIME outputs have been cited 116 times in academic publications (Google Scholar) | PRIME research publications have been cited 428 times according to Google Scholar and 228 times according to Scopus | PRIME has been cited 1606 times in Google scholar and 861 times in Scopus.
IMPACT WEIGHTING (%) |  | Source | [6 empty] | There is a demand for new knowledge
20% |  | Scopus database citations analysis, review of recent relevant academic publications or curricula
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  | RISK RATING
| 1000000 |  | Still to be determined | Still to be mobilised | Expected to exceed £2 400 000 | 50% |  |  | Medium impact and medium probability of occurrence
INPUTS (HR) | DFID (FTEs)

## Output 4 Capacity Building
OUTPUT 4 -CAPACITY BUILDING | Output Indicator 4.1 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) |  | New Target (end of Extension) | Assumptions
Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care | Number of externally funded policy-relevant research grants successfully applied for; and level of funding achieved. (E2) | Planned | None | 2 externally funded research grants sucessfully applied for. > £1,000,000 in value |  | 4 externally funded research grants sucessfully applied for. > £10,000,000 in value | At least 1 externally funded research grants successfully applied for or received from 2017 onwards. | At least 2 externally funded research grants successfully applied for or received from 2017 onwards. | Capacity that has been developed, in particular individual, is retained.
|  | Achieved |  | Multiplier funding succesffully applied for including EU-FP7EMERALD Health Systems Strengthening, NIMH Collaborative Hubs for Africa and South Asia, Value > £10,000,000 |  | We have received 26 externally funded research grants to the value of £26 402 032 |  |  | Differential research capacity in countries is managed through capacity building initiatives; Where partners have successfully applied for supplementary funding for activities related to the PRIME project, these relationships do not affect PRIME activities.
Source
Programme documentation: quarterly reports, PMG meeting minutes, emails
| Output Indicator 4.2 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) |  | New Target (end of Extension) | Capacity to supervise PhD students is retained within institutions
| Number of researchers who complete higher training and/or successfully apply for fellowships (E7 & E7.1) | Planned | None | 2:5(M:F) PRIME researchers register and begin PhD studies*, 25 register and begin masters studies** | 4:10 (M:F) PRIME researchers registered and PhD program started* , 50 registered or completed masters program started**, 1 succesfully applied for fellowship | 2:5 (M:F) PRIME researchers successfully graduate with PhD*, 130 registered or completed masters**, 5 sucessfully applied for fellowships | 2:5 (M:F) PRIME researchers successfully graduate with PhD* | 3:6 (M:F) PRIME researchers successfully graduate with PhD*
|  | Achieved |  | 4:9 (M:F) PRIME researchers registered or in the process of completing resgitration for a PhD; 36 register and begin structured Masters programs**; 2 researchers sucessfully apply for fellowhsips | 5:8 (M:F) PRIME researchers registered or in the process of completing resgitration for a PhD; 104 register and begin structured Masters programs**; 3 researchers sucessfully apply for fellowhsips and 1 fellowship for PhD studentship awarded (student selection in progress) | 2 Female students submitted and graduated with PhD; 1 female and 2 male students submitted and 15 currently registered for a PhD. 190 registered or completed masters; 5 successfully applied for fellowships |  |  | PhD students who are involved in PRIME research activities are able to allocate time to PhD studies
Source
Programme documentation: quarterly reports, PMG meeting minutes, emails
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 (2 years) | Milestone 2 (Year 4) | Target (end year 6) |  | New Target (end of Extension)
20% | Number of research publications and other research outputs by PRIME partner groups (E7) | Planned | Research publications per partner group have been calculated up to 2010 (available on request) | Research publications by partner groups increase by 10% | Research publications by partner groups increase by 10% sice end year 2 | Research publications by partner groups increase by 20% since end year 5 | Research publications by partner groups increase by 10% since end year 6 | Research publications by partner groups increase by 5% since end year 7
|  | Achieved |  | Research publications increased on average 41% per year across partners | Research publications by partner groups increase by 20% since end year 2 | Research publications by partner groups have increased 28% from 2015 to 2016.
Source
Scopus database search
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  | RISK RATING
| 1000000 |  | Still to be determined | Still to be mobilised | Expected to exceed £2 400 000 | 50% |  |  | Low impact and low probability of occurrence
INPUTS (HR) | DFID (FTEs)
5.2967
* PhD studies will be funded both directly (through PhD fellowships and the small grant's initiative) as well as indirectly (supervision by PRIME members, salary of junior researchers in other project roles)
and in-kind contributions which are accesible due to PRIME
** Masters students will be supported only indirectly through PRIME (additional teaching and supervision capacity)
Updated May 2017