Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	February 2018

Title: The Asian Development Fund (ADF 11) for the period 2013 - 2016
Programme Code: 203547	Start Date: 19 July 2013	End Date: 16 February 2018
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2014	2015	2016
Programme Score	B	A	A
Risk Rating	Low	Low	Minor[1]
[1] Revised as DFID introduced a new Risk Management Approach in early 2016 with a different methodology.

Financial Position

Original Programme Value	£200m
Extensions/ amendments	None
Log-frame revisions (with dates)
Total programme spend	£200m

Follow up actions required following closure
Ensure that lessons from implementation are applied to our ongoing project management and monitoring of ADF 12. Ensure that the ADF 12 logframe reflects the ADB transitional results framework and that DFID priorities continue to be measured.

Publish this Project Completion Review (PCR)

Undertake financial closure of the Project on DFID’s systems within three months of the date of this PCR.

Whilst all promissory notes due relation to ADF have been deposited we will continue to manage the remaining scheduled encashments of ADF 11 promissory notes.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203547/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203547/

Outline of programme and what it has achieved

The UK contributed £200m to the Asian Development Fund (ADF 11) which was negotiated in 2012 for the period 2013 – 2016.[2] The total ADF 11 budget was US$12.4 billion. The UK contribution was paid over financial years 2013/14, 2014/15, 2015/16 and 2016/17. ADF 11 was approved by Ministers in March 2013 and by Parliament in June 2013.
[2] The DFID review cycle runs slightly behind the ADB funding cycles to allow time for the processing of results.

The ADF has long been the concessional loans and grants facility of the Asian Development Bank (ADB).[3] It is an important source of development finance for the poorer countries in Asia and the Pacific. The fund plays a key role in helping these countries tackle poverty reduction and achieve the Sustainable Development Goals (SDGs). During the ADF 11 period, ADF finance was available to 16 countries that were eligible for only (ADF) concessional finance and also 14 countries that were eligible to receive a mix of both ADF and ADB non-concessional Ordinary Capital Resources (OCR) funding (known as blend countries).
[3] Though as of 1 Jan 2017 ADF has become a grants only fund. FAQs on ADF–OCR merger can be found at: https://www.adb.org/news/features/frequently-asked-questions-enhancing-adbs-financial-capacity-50-reducing-poverty-asia

The ADB has delivered both direct development results through the ADF 11, and internal reforms agreed as part of the ADF 11 Replenishment negotiations. These reforms strengthened effectiveness and systems, improving performance during the ADF 11 period and beyond. The development outputs, results and internal reforms are set out below.
In 2012, the Bank outlined the expected development outputs and results offer for the ADF 11 period 2013-2016:[4]
[4] https://www.adb.org/sites/default/files/institutional-document/33603/files/adf-xi-donors-report.pdf
Energy: 576,300 new households connected to electricity, 1,900 MW installed energy generation capacity, 2,300 km transmission lines installed or upgraded, 4,600 km distribution lines installed or upgraded.
- Climate change and renewable energy: Reduction of 1,191,000 tons of carbon dioxide equivalent greenhouse gas emissions (tCO2-equiv/year).
- Transport: 20,852,000 beneficiaries of road projects and 15,700 km of roads built or upgraded (highways, districts and rural roads).
- Water and sanitation: 562,000 new households served with water supply, 363,600 new households served with new sanitation and 626,000 hectares of land improved through irrigation services, drainage and flood management.
- Education: 2.57 million students benefiting from school improvement programmes, or direct support to, primary and secondary education, 211,200 teachers trained and 12,200 classrooms built or upgraded.
- Microfinance: 325,000 microfinance accounts opened or end borrowers reached and 57,600 loan accounts opened by small and medium-sized enterprises or end borrowers reached.
We specifically report on the achievement of a subset of these results at the outcome level in Section B. An assessment of individual outputs is undertaken in Section C.

Reforms and Improvements to Organisational Effectiveness

At the operational level, we pushed the ADB to implement its internal reforms, to improve the effectiveness of its programmes, the efficiency of its operations, and thereby contribute to improved outputs and results. This is the main theme in the theory of change logical chain in the Business Case for the ADF 11. The Bank demonstrated its commitment to these reforms during the ADF replenishment process which was integral to the successful outcome of the negotiations.

Reforms implemented over the ADF 11 period include: the adoption of a 17-point Gender Action Plan, an increased focus on project preparation as highlighted by the introduction of a board document review process and efforts to improve the procurement readiness of projects.

The Bank monitored the progress of its outcomes and reforms through the annual Development Effectiveness Review (DEfR) process and the ADF 11 Implementation Update. Progress on the 2011 MAR recommendations was reviewed in the 2013 MAR Update. Based on these assessments, key reform areas for the UK in relation to organisational effectiveness are:

- Reducing the amount of time required from project concept to first disbursement
- Reducing the amount of time spent on internal process
- Aligning human resources to strategic priorities (inclusive growth, gender and climate change, and improving project design, implementation, monitoring and evaluation)
- Strengthening resident missions in partner countries, especially fragile and conflict affected countries
- Refining and mainstreaming of results-based management approaches

The performance of ADF projects over recent years has improved relative to other areas of ADB operations. Project success rates for the ADF from 2014-2016 were 82%, outscoring the OCR for the first time, though there is an encouraging positive trend across all of ADB’s operations.[5] The countries in which ADF operates include some of the most challenging in the region so it is encouraging to see such high success rates for projects.
[5] https://www.adb.org/documents/2017-annual-evaluation-review

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

We assess that ADB responded generally well to the development challenges over the period of this PCR, albeit with remaining weaknesses in some of its operational performance such as slow project readiness and implementation. It has achieved a solid set of development outcomes during the period of our review. ADB early on adopted poverty reduction as its overarching goal and centred its work on the MDGs. The Bank’s Strategy 2020, launched in 2008 and revised in 2014, recognised the gains from the economic growth of the last few years and focused efforts on remaining development challenges and poverty reduction. ADB has been an important development partner for the UK in working towards achieving the MDGs, and now SDGs, in Asia and the Pacific.

The cumulative results for the outcome indicators that we measured across the period of this review are presented in the table below. This summarises the expected and achieved results in ADF operations completed during the period 2013-2016:

Cumulative achievement of selected development result indicators (logframe)

Annual achievement rates for selected development indicators

The Bank has amended the way it measures development results. They now measure achievement rate on an annual basis with the annual performance standard for the core operational results indicators set at 85%. The ADB’s Strategy, Policy and Review Department and Board have deemed 85% to be a reasonable and realistic level of achievement given that in all projects there are a number of factors influencing achievement which are outside of the ADB’s control. It encourages the setting of ambitious targets that are both challenging and achievable. For the cumulative results achieved in 2013-2016, three out of the six indicators in the table are above the 85% benchmark (1, 5, and 6), and the results almost met the target in two indicators with achievement rates at 84% (2 and 3). Only indicator 4, the number of households served with improved sanitation was well below the 85% benchmark, at 72%.

Output Score and Description

- Output1: Achieving operational effectiveness, quality portfolio performance; we score an A
- Output 2: Strengthening its focus at country and project level on gender equality, inclusive growth, private sector development and climate change and environment; we score an A+
- Output 3: Improves its operational efficiency for human and financial resources; we score a B
- Output 4: Improves its organisational efficiency at operational and project level; we score a C

Lessons and how these have been shared

Three main lessons have been learned over the course of the ADF 11 replenishment period and these have informed ADF 12 replenishment negotiations, discussions around the ADB’s Strategy 2030 and the design of the ADF 12 logframe.

The changes to the way in which the ADB assesses quality at entry, moving from ex post scoring of a sample of documents to an ex ante review process, is one of the reasons that the processing time from start of loan fact finding to Board approval has not improved over the ADF 11 period and remains behind the target. However it has led to an improvement in the quality of board documents. It is important in this situation and others like it, to understand that changes which may impact negatively on the scoring for selected indicators selected may have broader benefits.

Specifically, the ongoing concerns around the pace of delivery which were raised during the ADF 12 replenishment negotiations led to the ADB committing to tackle these issues in its implementation plan for ADF 12. However, as has been seen in areas such as the % of women international staff, strong action plans do not always lead quickly to results. Whilst there is unlikely to be a quick fix for the slow start up time, this will be a key area for DFID to hold ADB to account going forward and should be reflected in discussions on Strategy 2030, Results Framework and future revisions to DFID’s ADF 12 logframe.

Adapting the logframe to accommodate the recent changes to the ADF is also a key lesson from this review. As the ADF focuses on the most challenging geographies and changes its operations to grants only, the indicators and targets used to hold ADB to account will need to be revised. [6] Crucial to this getting this right will be a deeper understanding of the implications of these changes. The ADF 12 logframe is due to be finalised in February 2018, following this review and consultation with the ADB. It is somewhat delayed as a knock on effect of the delays in securing parliamentary approval for the UK commitments to ADF 12.
[6] From 2017 ADF will be a grant only facility to finance ADF country operations in Fragile Conflict Affected Situations (FCAS) and Small Island Developing States ( Afghanistan, Kiribati, Maldives, Marshall Islands, Nauru, Samoa, Tuvalu), regional operations, reserves for changes in debt distress, the Disaster Response Facility , and administrative expenses

Changes to the ADF will also mean that indicators pertaining to the ADB as a whole will become less useful for monitoring ADF. As far as possible these indicators should be supplemented with ADF specific ones, unless there is a strong rationale otherwise.

The findings of this review will be shared with DFID staff working with other RDBs and the World Bank, where they will inform similar discussions with those institutions.

## C: DETAILED OUTPUT SCORING (1 page per output)

The source of these results is the Asian Development Bank’s Development Effectiveness Review. [7]
[7] https://www.adb.org/sites/default/files/institutional-document/296441/defr-2016-main-report.pdf

Output Title	ADF achieving operational effectiveness; quality portfolio performance
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		no	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Quality at Entry of Country Partnership Strategies (CPS) rated Satisfactory (> %, performance standard, minimum threshold)	Target: >90% (2016) / Baseline – 100% (2012)	2016 – stopped measuring in 2014 / 2015 – scored every second year / 2014 – 100% / 2013 – scored every second year
1.2 Quality at entry of sovereign projects rated satisfactory	Target 90% (2016) / Baseline – 85% (2012)	2016 – stopped measuring in 2014 / 2015 – scored every second year / 2014 – 92% / 2013 - scored every second year
1.3 Performance of sovereign operations at implementation rated Satisfactory (> %, performance standard, minimum threshold)	Target: > 85% (2016) / Baseline – 89% (2012)	2016 – 96% / 2015 – 95% / 2014 – 96% / 2013 – 94%
1.4 Completed sovereign operations rated Successful (%); Projects and Policy-Based operations	2016 target for projects and policy based operations 80% / Baseline 58% projects, 41% policy based operations (2010-12)	2016 - 78% projects and 80% policy based operations / 2015 - 71% projects and 77% policy based operations / 2014 - 68% projects and 68% policy based operations / 2013 - 65% projects and 65% policy based operations

Key Points

Overview: The Output 1 targets were met in 2016. Over the course of the ADF 11 replenishment period there has been significant progress, particularly in relation to the number of complete projects and policy based operations rated “successful” at completion, though the indicators on quality at entry have not been measured since 2014. This output has consistently been scored as A or A+.

Indicators 1.1 and 1.2: ADB previously measured Quality at Entry of a sample of projects every two years. However in 2016 this ex-post monitoring process was discontinued and replaced in 2017 with an enhanced front-end project review process. In this new approach, the Strategy, Policy and Review Department reviewed the Project Concept Paper and Report and Recommendation of the President for a strategic sample of projects in order to further ensure that documents coming to the board are of the highest quality. An internal review carried out by the Strategy, Policy and Review Department at the end of 2017 found that the results focus of project documents (i.e. the connection between the project’s problem analysis, rationale of the proposed solution, and projects’ Design and Monitoring Frameworks) was significantly improved after being reviewed by the Strategy, Policy and Review Department.

We will work with the Bank to find other appropriate indicators for future replenishments.

Indicator 1.3 Performance of Sovereign Operations during Implementation: This indicator has shown consistently good performance and has been well above the target in each year of the ADF 11 replenishment period. There has been a significant improvement over the baseline with 96% of sovereign operations at implementation rated satisfactory in 2016.

Indicator 1.4 Success Rate of Completed Projects: ADF’s operations overall and the subsets for project and policy based operations have made significant progress towards the 80% target. There was a good improvement in the projects indicator which is now just two percentage points below the target and has increased by 20 percentage points over the baseline. The indicator for Policy based operations has improved substantially from the baseline (41%) and met the target of 80% in 2016.

Summary of responses to issues raised in previous annual reviews
Despite concerns in previous annual reviews, the ADB broadly achieved its targets under indicator 1.4. It is hoped that this indicator will increase further in future years as projects started after recent reforms reach completion.

However the concerns raised around project readiness and speed of implementation, covered in more detail under output 4, have not been sufficiently addressed.

The ADB continues to expand its offer on technical assistance through the technical assistance special fund (TASF), to $461m for the ADF 12 replenishment. The success rate of ADF technical assistance projects has improved in recent years and is now at 87%, well above the target.

Recommendations for future programmes

The logframe for ADF 12 will need to be updated as information on indicators 1.1 and 1.2 will not be available during the ADF 12 period. We will work with the ADB to understand which alternative indicators will be available and which would be best placed to assess the effectiveness of the ADF, an issue that remains important to DFID and other donors. Appropriately challenging yet achievable targets will be set alongside these indicators.
As the TASF has expanded, to support the ADF as it increasingly focuses on the most challenging geographies, we will consider including an indicator to measure the success rates of technical assistance projects.

We assess the score for Output 1 as: A - Outputs met expectation

Output Title	Bank strengthening its focus at country and project level on Gender Equality, Inclusive Growth, Private Sector Development and Climate Change and Environment.
Output number per LF		2	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Projects with gender mainstreaming (% G) and completed sovereign operations delivering intended gender equality results (% C)	Target (2016) – (G) 55% and (C) 70% / Baseline 58% G, 53% C (2010-2012)	2016 (G) 56% and (C) 76%; / 2015 (G) 57% and (C) 70%; / 2014 (G) 58% and (C) 59%; / 2013 (G) 60% and (C) 63%;
2.2 Operations supporting inclusive growth focusing on pillars: 1) growth and creation of jobs and opportunities, or 2) Inclusive access to jobs and opportunities (%).	Target (2016) - N/A (monitor only) / Baseline 1) 45% 2) 45% (2010-2012)	2016 – Pillar 1) 34%, Pillar 2) 66% / 2015 – Pillar 1) 33% & Pillar 2) 66% / 2014 - Pillar 1) 44% & Pillar 2) 55% / 2013 Pillar 1) 43% & Pillar 2) 55%
2.3 Operations supporting private sector development and private sector operations (%)	Target (2016) 40% / Baseline 29% (2010 - 2012)	2016 – 47% / 2015 - 41% / 2014 – 34% / 2013 – 29%
2.4 Operations supporting climate change mitigation and/or adaptation (%) Note: target for 2016 was adjusted by ADB in 2014 to be in line with other MDBs on climate change. The UK and others supported this change.	Target 40% (2016) / Baseline 27% (2011-2012)	2016 - 44% / 2015 - 43% / 2014 – 38% / 2013 – 32%

Key Points

Overview: Most indicators across this output have made significant progress over the ADF XI replenishment period, exceeding targets where they have been set. This output has generally performed well, scoring A in all but one of the previous reviews.

Of the indicators under output 2 for which targets were set, all targets were achieved or exceeded. For output 2.1 both targets were exceeded by 0-10%. For output 2.3 the target was exceeded by 17.5% and for output 4 the target was exceeded by 10%. We do not set targets for indicator 2.2, although had performance been measured against previous ones, the Bank would have exceeded it by 11%.  These achievements are deemed to “moderately exceeding expectations” and therefore worthy of an A+ score. It would be unreasonable to expect significantly higher percentage scores in any given sector as it would alter the balance of the ADF portfolio and be inconsistent with planned operations.

2.1 Gender: Across the replenishment period, ADF met its targets for our indicators on gender mainstreaming and projects achieving gender equality targets at completion. There has been significant progress on the % of sovereign operations delivering intended gender equality results. This was largely due to ADB's intensified efforts to promote gender equality and women’s empowerment through its operations since 2010, as well as better gender disaggregated reporting on benefits. This was noted by DFID’s 2016 MDR which observed that over the last few years, ADB has strengthened its policy statements, results monitoring, capacity and internal incentives on gender.

Despite strong, and improving, policies it is concerning to see that the % of projects with gender mainstreaming, whilst remaining slightly above target levels, has actually fallen over the ADF 11 replenishment period. However it is important to note that the quality of these projects has made significant progress over the course of the ADF 11 replenishment period, with the project success rate up from 63% in 2013 to 76% in 2016.

There is a risk that as the ADB increases the volume of projects it supports and the ADF moves into increasingly challenging geographies, that there will be a further drop in the percentage of projects with gender mainstreaming due to limited staff capacity.

2.2 Inclusive growth: ADB’s support for inclusive economic growth is determined by the specific country context and borrowing countries’ requirements. Because of this, the results framework does not set overall ADB targets for the first two pillars of this agenda—growth and creation of jobs and opportunities, and inclusive access to jobs and opportunities. In addition to the two pillars in the logframe, ADB also monitors the % of projects which support Social Protection. This was measured to be 7.2% from 2014-2016. This indicator reflects the increased emphasis put on social protection by the Strategy 2020 midterm review to shield and strengthen the resilience of society’s poorest and most vulnerable members.

The share of operations supporting growth and creation of jobs and opportunities (pillar 1) has fallen from a baseline of 45% to a low of 33% in 2015 but slightly improved again in 2016 to 34%. The ratio for operations supporting inclusive access to jobs and opportunities (pillar 2) rose significantly from 45% to 66% by 2016. It is encouraging to see this increase in the relative number of projects supporting inclusive access to opportunities.
2.3 Private sector: In 2016, the share of ADB’s operations supporting private sector development and operations continued to exceed the 2016 target of 40%. Significant progress has been made each year of the ADF 11 replenishment period.
2.4 Climate change: The 44% share of ADF operations supporting tackling climate change exceeded the 40% target for the third year running, having made significant progress of the ADF 11 replenishment period.
In 2015, ADB committed to doubling its annual climate finance from $3 billion to $6 billion annually by 2020. Of the $6 billion in climate change financing ADB plans for 2020, $4 billion will be for climate mitigation and $2 billion for adaptation. However, the share of ADB’s overall financing that went to climate change mitigation and/or adaptation projects during 2014–2016, remained steady at 19% for ADB overall, and decreased by 7 percentage points to 14% for the ADF subset.

Summary of responses to issues raised in previous annual reviews

Previous annual reviews have raised issues around the Bank’s indicators for inclusive growth, recommending that they take into account marginalised and vulnerable groups, including women and girls, in relation to access to jobs and other livelihood opportunities. The ADB is exploring considerable revisions to their current methodology in relation to the update of the results framework. We should continue to engage proactively on this issue, as it will be a key area in achieving our reform priority of encouraging the bank to focus more on Leave No-one Behind.

Previous annual reviews have stressed that the Bank needs to improve its reporting around the amount of private sector finance that it catalyses. The ADB is now working with other MDBs to harmonize the method for measuring this.

Previous annual reviews have encouraged DFID to push ADB to embed climate change in all interventions. Across the ADB the share of operations supporting climate change mitigation and/or adaptation was 45% in 2016. This is an improvement on previous years but it is concerning to see that the % of ADF financing directed towards climate mitigation and/or adaptation projects has actually fallen despite bank wide commitments to boost climate finance. However it was good to see that the ADB gained accreditation to access funding for climate change adaptation and mitigation from the United Nations-backed Green Climate Fund (GCF) in March 2015. It was the first multilateral development bank to do so.

Recommendations for future programmes

Gender will remain a key priority for DFID, both in relation to the ADF 12 and ADB operations more broadly. We should closely note the 2017 figures on the percentage of projects with gender mainstreaming, due early 2018, and act accordingly, pushing ADB to do more if the negative trend is not halted. The targets for gender mainstreaming in the ADF 12 logframe should be set at 55%, pressuring ADB to reverse the recent negative trend. We should also consider monitoring the percentage of “projects addressing gender concerns”.[8]
[8] “Projects addressing gender concerns” includes all projects with some gender elements, whereas “gender mainstreaming” is a more rigorous benchmark. There is value in both measures.

ADB are changing the way that they measure inclusive growth and it will be important for DFID to engage proactively in consultations on the next iteration of the ADB results framework to ensure that the ADB continues to report in line with DFID priorities. In the meantime interim indicators around social protection will be used.

As ADF focuses more narrowly on increasingly challenging geographies and focuses only on grants it will likely become more challenging to support private sector development. However this remains a DFID priority and, in the ADF 12 Donors Report, the ADB committed to expand private sector operations in concessional assistance countries, setting a target of 40% by 2020. This will be reflected in the ADF 12 logframe.

DFID should continue engage proactively with the ADB at all levels, pushing our reform priorities. Forthcoming discussions on Strategy 2030 and the revised results framework present an opportunity to make progress on these issues, and those raised by previous annual reviews, for example in relation to the measurement of private sector finance catalysed, Leave No-One Behind and the inclusion of an indicator relating to work in fragile states.

We assess the score for this output as: A+ – outputs moderately exceeded expectations

Output Title	ADB improves its operational efficiency for human and financial resources
Output number per LF		3	Output Score	B
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Representation of women in the international staff category (%)	Target 37% (2016) Baseline (2012) 34%	2016 – 34% / 2015 – 34% / 2014 – 35% / 2013 – 35% (ADB overall)
3.2 Internal administrative expenses per $1 million of disbursement ($’000)	Target 56,100 - 57,200 (2016) Baseline 59,000 (2010 - 2012)	2016 – $48,400 / 2015 - $53,700 / 2014 – $60,700 / 2013 - $63,100
3.3 Share of operational expenses for portfolio management (% of total operational expenses attributed to portfolio management and processing of operations)	Target 64% (2016) / Baseline 59.8% (2012)	2016 – 54.6% / 2015 - 56.9% / 2014 – 59.8% / 2013 – 61.5% (ADB overall)
3.4 Sovereign operations administrated with substantial resident mission involvement (%)	Target (2016) 80% Baseline 72% (2012)	2016 – 80% / 2015 - 75% / 2014 – 73% / 2013 – 69%

Key points

Overview: Indicators across this output have had mixed progress over the ADF XI replenishment period, some meeting or exceeding targets but other failing to achieve. This output has consistently underperformed, scoring B in each of the previous reviews.

3.1 Women in International Staff: The result for this indicator in 2016 remained the same as in 2015 at 34%, from a high point of 35% in 2014. It has failed to meet the 2016 target of 37%. This result has remained roughly stable across the replenishment period and the main reason for this is that the recruitment of women for the international staff has not kept up with departures.

Previous reviews have rightly raised the lack of progress in the representation of women in the international staff category. DFID has raised these issues as part of the ADF 12 replenishment meetings and at the Annual Meeting in May 2016. Responding to these concerns, ADB adopted a new 17-point gender action plan in 2016 to strengthen gender equality in the institution. The plan was based in part on the findings of an independent assessment by EDGE (Economic Dividends for Gender Equality), an international foundation specializing in best practices in workplace gender equality. The gender action plan focuses on three pillars—recruitment and gender representation, career management and retention, and training and development. The aim is to make ADB more attractive for potential and existing women employees to support recruitment and retention of women international staff members. In addition to setting up a Respectful Workplace Unit, ADB attained the first level of EDGE certification in December 2016, which acknowledged its public commitment to a strong gender balance and its concrete action plan to making further progress. Furthermore, ADB has stepped up its efforts to increase applications from women through assistance from recruitment agencies. Internally, ADB provides gender training to all and special support to women with potential for promotions. In 2016, ADB set new gender targets for different levels of international staff and an overall 40% target for women international staff by the end of 2022.

However the results of this have yet to be seen. Many of these interventions will have significant lead times before impacts are evident.

3.2 Internal Administrative Expenses per $1 million of Disbursement: Despite an initial rise above the baseline of $59,000 to $63,100 in 2013, the results for this indicator have since moved in the right direction, falling below the target in 2015. In 2016 the result is $48,400 is substantially better than the target of $57,000.

This is mainly result of slow growth in administrative expenses at the same time as the volume and spending have increased. At the ADB level, it is likely that this trend will continue due to the ADF/OCR merger in early 2017. However for the ADF, the increasing focus on the most challenging geographies and change to grants only will likely lead to an increase in internal administrative expenses per $1million of disbursement. This higher administrative budget should enable ADB to work more effectively in difficult environments.

3.3 Share of Operational Expenses for Portfolio Management: This measures operational expenses incurred through project delivery including salaries, benefits, staff development, relocation, consultants and business travel as a percentage of overall portfolio management and processing costs. Performance on this indicator has been disappointing over the review period. . In 2013 it was 2.5% above the baseline of 59% but has since declined reaching a new low of 54.6% - which is over 9% short of the 2016 target of 64%.

The drop is partly due to more spending in 2016 on preparing projects and building a stronger pipeline for the planned scale-up of operations. It was also a result of more work to make projects procurement-ready at approval and ensure better quality at entry. The number of approvals exceeded the planned work program as well.

3.4 Sovereign operations administrated with substantial resident mission involvement: Scoring on this indicator has increased from 69% in 2013 to 80% in 2016, hitting the target. ADB is implementing an action plan to give country offices more decision making power, and we are pleased to see that this has impacted the result. The increase in staff on the ground in Afghanistan has already led to improvements in the relationship between DFID and ADB.

Summary of responses to issues raised in previous annual reviews
Previous DFID annual reviews have recommended that we closely monitor the Bank’s reform plans for improvement in both its operations and administration. They recommend focusing on key issues that make the Bank fit for purpose in ADF countries including strengthening staff capacity for policy engagement at country level, coordination with other partners, procurement and overall portfolio monitoring. DFID’s 2016 Commercial Expertise Review showed that the ADB is making good progress in relation to procurement. We will continue to monitor and engage with the Bank at various levels, including through the Board and through high level Strategic Dialogues.

Recommendations for future programmes

The ADF 12 logframe should reflect the new 2022 target of having 40% women in the international staff category. Increasing the target to 38% by 2020, the end of the ADF 12 replenishment period will encourage ADB to remain focused on this issue. We should also consider how best to monitor the gender balance at different levels within the ADB as they begin reporting to the Human Resources Committee on the gender balance at a wider range of grades and at the point of recruitment. If possible, we should consider setting a target for point of recruitment as this will provide a more instantaneous assessment of whether or not the policy reforms are having the desired impact.

As the ADF becomes increasingly focused on the most challenging geographies and only disburses grant finance, we will review the appropriateness of targets for the ADF 12 internal administrative expenses per $1 million of disbursement and on the share of operational expenses for portfolio management. The last time DFID compared this indicator across MDBs the ADB was among the top performers, this analysis will be updated in early 2018. These findings will inform the target setting for future logframes. In setting new targets we will seek to understand the reasons behind the falling share of operational expenses for portfolio management. In line with our reform agenda across the MBDs we will continue to push the ADB to achieve maximum budget efficiency, including minimal administrative expenses per $1 million of disbursement.

We assess the score for this output as B – outputs moderately did not meet expectation.

Output Title	ADB improves its organisational efficiency at operational and project level (sovereign and non-sovereign)
Output number per LF		4	Output Score	C
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Average time from approval to first contract in sovereign operations (months)	Target (2016) <9 Baseline 13.7 (2012)	2016 – 16.2 months / 2015 – 15.0 months / 2014 – 16.0 months / 2013 – 11.5 months
4.2 Sovereign operations processing time from start of loan fact-finding to Board approval (months)	Target (2016) 6 month Baseline 6.8 (2012)	2016 – 7.1 months / 2015 - 6.6 months / 2014 – 7.3 months / 2013 – 5.8 months
4.3 Processing time for procurement contracts for sovereign operations (more than $10 million, days)	Target (2016) <40 Baseline (2012) 64	2016 – 44 days / 2015 – 49 days / 2014 – 74 days / 2013 – 62 days

Key points

Overview: Indicators across this output have had mixed progress over the ADF XI replenishment period. Whilst all failed to achieve their targets one made progress, one was stagnant and the other deteriorated. This output has consistently underperformed, scoring B or C in each of the previous reviews.

4.1 Average time from approval to first contract in sovereign operations: The average time from approval to first contract has increased significantly, from 11.5 months to 16.2 months, over the course of the ADF 11 period. Not only have targets not been hit, but the 2016 level is higher than the 2012 baseline.

This is somewhat explained by the fact that Scores for the time-to-first-contract indicator are based on projects with first contracts awards in 2016, but some of these operations were approved as far back as 2011–2014 and might not have fully benefited from ADB’s efforts under the midterm review action plan to streamline business processes, improve project readiness, and reduce implementation delays. These reforms have led to a significant increase in procurement readiness and this in turn should lead to a drop in time to contract approval in future years.

4.2 Sovereign operations processing time from start of loan fact finding to Board approval: This has fluctuated slightly over the course of the ADF 11 replenishment period, with a low of 5.8 months in 2013 and a high of 7.3 months in 2014, but there is no clear pattern of improvement. Targets have failed to be reached, generally by around 1 month for each of the last three years.

The most common reasons for longer sovereign operation processing times were lengthy government approval procedures and changes in DMC governments, including as a result of national elections. Performance on this indicator is also influenced by ADB’s focus on quality at entry, including an increased emphasis on project readiness and safeguarding.

4.3 Processing time for procurement contracts for sovereign operations: Despite significant improvements, falling from 62 days in 2013 to 44 days in 2016, the target for processing time for procurement contracts has not been achieved.

The better results for this indicator were mainly due to continued information technology reforms in online procurement systems, the posting of more procurement specialists to ADB’s resident missions, close scrutiny of larger contracts, and continuous capacity building of executing and implementing agencies in the DMCs.

Summary of responses to issues raised in previous annual reviews (where relevant)

Previous Annual Reviews identified the ADF 12 replenishment negotiations as the key opportunity for influencing the slow delivery which has affected ADF XI. During replenishment discussions this was one of the key issues repeatedly raised by the UK. As a result, the ADB committed to focus further on operational improvements in regards to speed and quality of programmes as part of the ADF 12 implementation plan.

Recommendations for future programmes

This output has performed consistently poorly over the course of the ADF 11 replenishment period. The issue of slow project delivery was raised by DFID as part of ADF 12 replenishment negotiations, with ADB committing to focus on further improvements. Given the fact that this is a DFID priority we will consider increasing the weighting given to this in future logframes. Any increase in the weighting for this output would have to be matched by revisions in the weighting of different outputs.

We will continue to work closely with ADB to understand the causes of delays and continue to monitor the impact of recent reforms. Any new targets should be realistic and make sure not to put undue strain on important processes such as safeguarding or influence variables such as instrument choice.

We assess the score for this output as C – outputs substantially did not meet expectations.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for the ADB are the administrative costs associated with projects; this includes factors such as staff salaries. Over the course of the ADF 11 replenishment period, the internal administrative expenses per $1million of disbursement have fallen dramatically. However this cannot entirely be put down to administrative improvements. The number of large projects and non-project loans (eg PBLs), which tend to have a lower admin expense per $1million disbursed, has increased. Staff salaries continue to increase at a rate above that which we are comfortable with and this will continue to contribute to high levels of administrative expense, despite efficiency savings made. DFID, as part of our constituency, voted against a proposed salary increase in December 2017.

VfM performance compared to the original VfM proposition in the business case

DFID’s Business Case for the ADF 11 (2013-2016) includes details on value for money (Section D, page 26 onwards). It includes examples of what the UK is doing to push the Bank to improve its cost efficiency and demonstrate better value for money. The Bank scored “Satisfactory” (on cost and value consciousness) in DFID’s 2011 MAR, which assessed that administrative costs were low compared to comparable multilateral development banks and that administrative budgets had been controlled as volume of loans and grants had increased significantly. However, there was limited evidence of emphasis on securing efficiency gains or driving down costs in the design of development projects. The MAR summarised the ADF as a relatively low cost operation, with good internal controls, but needing to concentrate more on project level VfM. As evidenced in the 2013 MAR Update, the Bank had responded positively to the MAR recommendations and had incorporated work on cost efficiency at project level (including procurement) as part of improving its business processes. The 2013 MAR Update assessed the Bank’s work on VfM as “some progress”. The 2016 MDR found that ADB had taken steps over the last few years to improve efficiency in the use of the Bank’s resources as outlined in the 2020 Strategy and based on close monitoring of costs, including key cost drivers such as salaries, cost of country missions and the overall usage of consultants. Despite this significant progress of the ADF 11 replenishment period, there is scope for the Bank to demonstrate more evidence on systemic operational and administrative value for money and cost efficiency as a complement to the budget process.

Assessment of whether the programme represented value for money

Overall, the tenth replenishment of the ADF (ADF11) represented good value for money. During this period, the Asian Development Bank used its local knowledge and expertise in areas such as infrastructure to deliver strong development results that would have been very difficult for DFID to achieve directly. The ADB remains an effective organisation, delivering quality projects in countries and sectors where it has a comparative advantage. In terms of efficiency, some good progress has been made in areas such as internal administrative expenses per $1 million of disbursement, but in other areas progress has been less satisfactory. Long delays in programme delivery will have implications both on cost and results and minimising these must be a focus for ADF 12.

Quality of financial management during programme

There is good financial control. ADB has robust financial oversight mechanisms and provides externally audited annual accounts, as noted in the recent MDR (review launched in 2016) and the earlier MOPAN reviews of the ADB (2013).

Date of last narrative financial report	31/12/2017 / (Approved by Board of Governors May 2017)
Date of last audited annual statement	31/12/2017 / (Approved by Board of Governors May 2017)

E: RISK (½ page)

Quality of risk management over the life of the programme

In its operations, the bank faces different kinds of risks, including financial, operational and organisational risks. ADB has a comprehensive risk management framework that is built on the components; governance, policies and processes. The bank also maintains an independent risk management group and has various management-level committees with oversight responsibility for and decision-making authority on risk issues.
As noted in the 2016 MDR, the Bank has good internal risk processes. It takes account of the risks that inadequate project readiness, delivery and monitoring of programmes, including the risk of projects involved in fraud or corruption, could lead to reduced development outcomes and slow procurement and disbursement, and insufficient preparation of robust project pipelines could lead to underutilisation of ADF funds as happened in 2015. The Bank has an institutional action plan to improve its performance and mitigate those risks, but we will push the Bank to demonstrate improvements over the ADF 12 period. The increasing focus on the most challenging geographies and switch to grant only ADF may reduce the pipeline of projects and accentuate risks around underutilisation; this is something we will monitor.
Overall, replenishment of the ADF is a low risk programme. The ADB is an established delivery partner with strong risk management processes, financial controls, anti-corruption policies, transparency and accountably, as noted by the 2016 MDR. Residual risks remain at the project level and DFID, through the Board constituency will continue to engage with projects that represent the highest risk both to the reputation of ADB but also to DFID.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Yes.

Performance of partnership (s)

The ADF as a funding instrument has been tested and successfully used for several decades. The ADF represents a good option for delivery of development finance to the poorest and most fragile and vulnerable countries in Asian and Pacific. DFID has strong and established relationship with the Bank and it engages at various levels: the Board, through policy leads in London and at the country level. As evidenced in the ICAI 2012 review of our engagement with the ADB, this provides good levels of engagement to influence reforms and performance.

Procurement: As noted in the 2016 MDR, the Bank uses international competitive bidding for procurement and procurement guidelines stress the value for money components. DFID also completed a Commercial Expertise Review (CER) of ADB. This confirmed that the Bank’s procurement guidelines and procedures are in line with the international standards and are consistent with other multilateral development banks, i.e. World Bank and African Development Bank. The Bank has completed a first stage of procurement reform which resulted in some improvements for example procurement risk assessment at three levels: framework, project and delivery capability. These changes are intended to result in proportionate, yet robust, procurement decisions taking full consideration of the risks associated, this should make the Bank more efficient in its procurement operations.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Although DFID is not formally using its four bilateral partnership principles for the ADB, they do have policies and procedures that live up to the requirements in practice (e.g. in regards to basic rights through their charter and policies such as safeguards).
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The Bank has good sources of evidence, including the annual Development Effectiveness Reviews, the Annual Review of Evaluation Report, Annual Portfolio Performance report and the Annual Report for the Bank as a whole. Data collection however continues to be weak in partner countries where capacity remains weak overall. The Bank conducts project evaluations regularly through its independent evaluation department and is now moving towards real-time evaluations, impact evaluations and formative evaluations. No DFID specific evaluations were conducted during the reporting period. Prior to the upcoming ADF12 Replenishment, ADB conducted an independent evaluation (ADB Independent Evaluation Department) of the ADF over the last ten years. DFID and others used the findings and recommendations from that evaluation as key evidence in our discussions on how to make the ADF more effective. This included for example evidence of weaknesses in support to fragile situations such as in Afghanistan, were the Bank has now agreed to strengthen its staff capacity.

We will continue to engage with the ADB on the issue of results, where we seek to ensure that future editions of the results framework have a greater focus on ADB’s impact and efficiency.

Monitoring progress throughout the programme

In addition to conducting formal Annual Reviews and this Completion Review, there have been a number of opportunities to periodically take stock of operational and institutional reform progress at the Bank. These have included the Bank’s Annual Meetings in May of each year, the ADF 12 replenishment negotiations (concluded in May 2016) and quarterly ADB update meetings including inputs from UK-Del Manila and DFID country offices on specific programmes, policy and operational issues. Senior officials from DFID periodically visit the ADB, and vice versa, including an Annual Strategic dialogue, most recently held in November 2017. This provides an opportunity an opportunity to raise concerns at a high level and as part of a constructive dialogue.