COUNTDOWN: Implementation Research to Inform the Effective and Sustainable Scaling-Up of Integrated Neglected Tropical Disease (NTD) Control Initiatives
Impact	Reduced morbidity, mortality and poverty associated with NTDs from application of new evidence for cost effective scale-up of sustained control and targeted elimination of disease in line with the 2020 WHO NTD Roadmap and the 2030 Sustainable Development Goals
OUTCOME	Outcome Indicator 1	Milestone 2016		Milestone 2017	Milestone 2018	Milestone 2019	Assumptions
Increased effectiveness of NTD programmes, with a focus on gender and reaching poor and vulnerable groups, highlighting inequities, resulting in more people accessing appropriate interventions and receiving necessary treatments	Improved availability, acceptability affordability, and accessibility of NTD interventions to individuals and communities / Outcome A1	Not assessed as too early in the programme’s development / N/A		An example of COUNTDOWN evidence influencing expanded access or more effective programming / Achieved	Two or more examples of COUNTDOWN evidence influencing expanded access for more effective programming	Three or more examples of COUNTDOWN evidence influencing expanded access for more effective programming	- Outcome will depend on overcoming any resistance to change and future financial bottlenecks to health stakeholders, especially at the national level, even if integrated scale-up can be shown affordable e.g. costs per person treated. - Access to treatment costs might also increase when hard-to-reach communities are targeted owing to increased demands on logistics and transportation resources.
	Outcome Indicator 2	Milestone 2016		Milestone 2017	Milestone 2018	Milestone 2019
	COUNTDOWN research influences improved consideration of gender, equity, and the most vulnerable in NTD programming / Outcome A2	N/A		N/A	4 case studies demonstrate how research activities improve gender equality, equity and/or the situation of the most vulnerable in the research context	8 case studies demonstrate how research activities improve gender equality, equity and/or the situation of the most vulnerable in the research context
	Outcome Indicator 3	Milestone 2016	Milestone 2017		Milestone 2018	Milestone 2019
	COUNTDOWN evidence engages and influence national or international expert panels/policy makers in the scale-up of pro-poor, effective and efficient approaches / Outcome A1	Knowledge gaps identified through a collaborative process at National/ State/ District level involving MoH partners, multi-sectoral policy makers and key stakeholders in 2 COUNTDOWN countries / Achieved in 2 countries	Seminars involving a panel of research experts discussing the latest research findings have been facilitated within relevant National / State/ District policy-making institutions in 4 COUNTDOWN countries / Achieved		Among the COUNTDOWN countries, at least 3 policies, guidelines, plans, strategies updated to apply research evidence generated from COUNTDOWN	Among the COUNTDOWN countries, at least 6 policies and/or guidelines updated to apply research evidence generated from COUNTDOWN
		Source
		The number of revised international, national or district policy documents that include COUNTDOWN's recommendations

Output 1	Output Indicator 1.1	Milestone 2016	Milestone 2017	Milestone 2018	Milestone 2019	Assumptions
COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers	NTD implementation research gaps identified	Research begins in two countries (Ghana & Cameroon) in response to priority needs of NTD policy makers and programmes. / Achieved in 2 countries	Research begins in two additional countries (Nigeria & Liberia), the on-going research in the two initial countries (Ghana and Cameroon) identifies 3 evidence based strategies in response to priority needs of NTD policy makers and programmes. / Achieved in 4 countries	Implementation research conducted to address 5 knowledge gaps for NTD policy makers and programmes	Implementation research conducted to address 10 knowledge gaps for NTD policy makers and programmes	- Ethical committees in respective countries and LSTM sign-off on research protocols in a timely manner. / -There are no risks of disturbance to proposed research and research uptake activities in selected countries albeit from natural or man-made disasters or confounders. / - There is coherence of communication technologies available in each of the four countries during the lifespan of COUNTDOWN and that visibility and access to Open Access Databases are not restricted.
	Output Indicator 1.2	Milestone 2016	Milestone 2017	Milestone 2018	Milestone 2019
	Number of approved research projects / Output D1	N/A	N/A	i) Design: 4 / ii) Implementation: 8 / iii) Analysis/Dissemination: 2 / iv) Completed: 1 / Total: 15	i) Design: 0 / ii) Implementation: 4 / iii) Analysis/Dissemination: 8 / iv) Completed: 3 / Total: 15
	Output Indicator 1.3	Milestone 2016	Milestone 2017	Milestone 2018	Milestone 2019
	Open access research publications: / - Peer reviewed journal articles / - lead or co-author with home institution in LMIC / - female lead/co-author / - female lead/co-author with home institution in LMIC / Output A3	3 peer reviewed articles / Achieved 4 articles	8 peer reviewed articles / Achieved 11 articles	16 peer reviewed articles	22 peer reviewed articles
	Output Indicator 1.4	Milestone 2016	Milestone 2017	Milestone 2018	Milestone 2019
	Open access knowledge products (presentations, blogs, briefs) produced and disseminated / Output D2 and D3	40 products developed and geographic dissemination mapped / Achieved 59	70 products developed and geographic dissemination mapped / Achieved 147	150 knowledge products, including 5 policy briefs, developed and geographic dissemination mapped, including through website download and page views	200 knowledge products, including 10 policy briefs, developed and geographic dissemination mapped, including through website download and page views
Impact Weighting		Source
60 %
		Management Reports, Work Plans, Quarterly Progress reports, Research Uptake Strategy, Web Analytics

Output 2	Output Indicator 2.1	Milestone 2016	Milestone 2017		Milestone 2018	Milestone 2019		Assumptions
COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control	Involvement of key stakeholders at national, state and district level in developing linkages, partnerships, across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming / Output D4	Achieved	Achieved		COUNTDOWN expands stakeholder network into 2 COUNTDOWN countries to advocate and manage multi-disciplinary research at national, state and district levels	COUNTDOWN expands stakeholder network into 4 COUNTDOWN countries and at an international level that advocate and manage multi-disciplinary research		- Ethical committees in respective countries and LSTM sign-off on research protocols in a timely manner / -There are no risks of disturbance to proposed research and research uptake activities in selected countries albeit from natural or man-made disasters or confounders / - COUNTDOWN stakeholders including policy makers and decision makers engage with COUNTDOWN and have sufficient time and capacity to process information delivered and understand it
		Source
		Management Reports, Work Plans, Quarterly Progress reports, Research Uptake Strategy
	Output Indicator 2.2	Milestone 2016	Milestone 2017	Milestone 2018			Milestone 2019
	COUNTDOWN undertakes research uptake and dissemination activities effectively / Output A4	N/A	N/A	5 effective activities which led to research uptake/ dissemination			5 effective activities which led to research uptake/ dissemination
Impact Weighting		Source
25 %		Management Reports, Work Plans, Quarterly Progress reports, Research Uptake Strategy, Web Analytics

Output 3	Output Indicator 3.1	Milestone 2016	Milestone 2017	Milestone 2018	Milestone 2019	Assumptions
COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country based research communities	COUNTDOWN stakeholders engaged in implementation research training / Output D4	COUNTDOWN stakeholders establish implementation research and research uptake capacity building goals at national, state and district level for scale up of integrated NTDs / Achieved	Prioritised recommendations for improved NTD Implementation research capacity at appropriate levels (district, state, national) in least 3 COUNTDOWN countries / Achieved	Institutions in at least 3 COUNTDOWN countries demonstrate the impact of improved research capacity through new knowledge, skills, networks, collaborations, funding	Institutions in at least 4 COUNTDOWN countries demonstrate the impact of improved research capacity through new knowledge, skills, networks, collaborations, funding	- Partners dedicate sufficient time and attention to COUNTDOWN-sponsored activities.
Impact Weighting		Source
15 %		Management Reports