Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	December 2017

Title: Democratic Governance Support Programme(DIALOGO) - DIÁLOGO Local para a Boa Governação
Programme Code: / 201958	Start Date / 14/10/2010	End Date: / 31/12/2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A+	A+
Risk Rating	Minor	Moderate	Major	Moderate	Moderate

Financial Position

Original Programme Value	The Business Case approved budget is £10 million while the original DIALOGO Programme value was £8,141,994.19 million. A budget of £150,000 was set aside for the design component.
Extensions/ amendments	A cost- extension of £1,496,931.00 was granted in September 2016 and the duration of the programme was extended by one additional year up to December 2017 to consolidate the good work done under the Project.
Log-frame revisions (with dates)	Several logframe changes took place most notably in 2013 after the 2012 inception phase and in 2016 following the Mid Term Review (MTR) recommendations. Changes to the logframe were supported by a strong rationale. / The most important recent additions relate to the 2016 MTR and 2016 Annual Review recommendations to focus on the implementation of the Gender Strategy as well as building sustainability to the project and consist of the following: / • Indicator 1.2.: The project will expand its civic engagement approach to new non-DIÁLOGO partners in new neighbourhoods and around new issues that are a real concern to citizens. / • Indicator 2.6: # of interactive media transmissions and articles (radio, newspapers) disaggregated by gender and group ( women, youth and another vulnerable groups) / • Indicator 3.5 # of municipalities’ initiatives prioritising vulnerable groups
Total programme spend (to date)	To date £9,639,578.96 have been spent

Follow up actions required following closure

1. Programme Manager ensures publication, in the development tracker, of the Project Completion Review
2. Programme Manager archives final key documents, and SRO shares with donors active in the sector
3. SRO and Programme Manager ensure that key recommendations are considered in subsequent DFID programming and share lessons across DFID office within three months of programme closure.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-201958/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-201958

Outline of programme and what it has achieved

The Democratic Governance Support Programme – DIÁLOGO Local para a Boa Governação – is a five-year local governance programme in Mozambique which started in 2012 and ended in December 2017. It was managed by DAI, in partnership with COWI, through a Programme Management Unit (PMU). Other partners of this consortium include the Institute for Development Studies (IDS) in charge of the monitoring and evaluation component, CESC (Centro de Aprendizagem e Capacitacao da Sociedade Civil) working mainly with civil society organisations and providing the key community facilitators on the ground, and IREX focusing on media.

The DIÁLOGO programme aimed to improve municipal governance, focusing on encouraging engagement of, and constructive dialogue between, citizens, civil society, the media and municipal institutions on issues raised by communities with municipalities. It worked in five urban municipalities of Mozambique - Nampula, Tete, Quelimane, Beira and Maputo. The Programme was extended in 2016 for a 10 month period following a positive MTR to consolidate what worked well and institutionalise best practices, as well as step up the sharing of lessons, and focus more on gender and inclusion.

Despite a substantial deterioration in the political, economic and social context for municipal governance in Mozambique since the programme began, as well as delays in implementing a decentralised policy (on the devolution of primary health and education services to the municipalities), all DFID Annual Reviews met or exceeded all of its output indicators, on 1) the increase in citizen participation in municipal governance 2) media coverage and public debate around municipal governance related issues and 3) regular and consistent municipal institution engagement with citizens around municipal governance issues which delivered concrete improvements. .

DIÁLOGO contributed greatly to municipal-level civic engagement in targeted municipalities through its support to NGO platforms and civic groups as well as increased the scale of its impact by reaching out to more organisations and other municipalities. This was evidenced by the “Ripple Effect Study” that looked at whether civic groups and other grassroots actors, such as neighbourhood representatives with a problem-solving remit supported by the programme - through the community engagement component - are influencing other groups and individual citizens at the neighbourhood level that do not directly benefit from this Programme. The study concluded that the community engagement component has had a significant impact on the knowledge, attitudes and behaviour of a large number of members of pre-existing civic groups who had not previously received support from Diálogo, and of a smaller number of individual citizens who had not previously belonged to a civic group. “People reported “having their eyes opened” about their rights and duties (as well as the responsibilities of municipal institutions) and learning about how to channel their concerns to the relevant authorities” (IDS Ripple Effect Study, December 2017).

The Programme went beyond its original remit and worked closely with CSOs’ competencies to help them better understand municipal governance which are likely to continue beyond the lifetime of DIÁLOGO. For example already several national organisations such as CESC, and Parlamento Juvenil (Youth Parliamentary organisation) managed to mobilise funding and plan to work on municipal governance as evidenced in their 2018 strategic plans.

A Final Evaluation (FE) carried out by the Institute of Development Studies (IDS) concluded that the programme has improved its value for money, level of outreach and quality of learning significantly since the Mid-Term Review (MTR) in 2015. It has contributed to improving municipal governance in five of Mozambique’s most important cities – very significantly in some, more marginally in others. However, it did note that sustainability was not easily achieved with financial sustainability being difficult given the current difficult economic context and DFID funding ending to the 4 municipalities and respective media partners.

Various sharing and learning events were organised in 2017 most notably: A final DIALOGO Event was organised on 8 November which was well attended by the CSO community and donor community. On 7 December DFID organised a meeting for donors with DAI and IDS specifically on lessons learnt of DIALOGO and the Ripple Effect Etudy carried out by IDS.

The FE concluded that the programme has made a significant contribution to municipal-level engagement of women and youth in governance debates in terms of awareness-raising, mobilising and accessing places were decisions affecting municiplaities are made. The Programme also provided support to innovative approaches towards urban gender issues (e.g. sexual violence, unemployment and livelihoods). For example in Maputo, DIÁLOGO inspired Horizonte Azul, an organisation that focuses on women and girls empowerment, to implement a “safe neigbourhood for girls” project that tackles security and safety in Maputo. While in Tete, CAPAZ set up an extensive network of local activists working to address social protection and gender violence in cities.

However the FE suggested that more differentiated analysis would have been useful and more might have been done to narrow gaps between male and more senior powerful actors and female, younger less powerful actors.

The programme worked well to manage the risks associated with the changing context in Mozambique using an adaptive management approach, which included a robust risk management framework jointly updated with DAI and DFID.

The programme exceeded DFID’s expectations, especially regarding Output 2, which sought to strengthen the use of media to engage, empower and communicate to citizens on key governance issues. The introduction of a media component was an innovation in governance in Mozambique and led to increased participation in public debates on service delivery leading to large improvements in transparency and accountability of providers. For example, participation[1] increased from 3,519 people in year 1 to 55,605 people during year 4 exceeding the 33,850 expected target. Municipal institutions now use the local media as a mechanism to inform and sensitise citizens.
[1] Participation in the media space is measured through different ways (radio programme debates, phone calls, SMS and Facebook statistics).

More specifically, the following results have been achieved by municipalities:
- Nampula was one of the most successful municipalities to work with as a results of its leadership and commitment to engage with citizens. For example, the municipal assembly approved the use of participatory budgeting which gave citizens more decision making power in the use of a portion of the budget. The Municipal Council also used other participatory tools, such as the community score card to evaluate how service delivery in municipalities was perceived
- In Quelimane, DIALOGO introduced a fiscal mobilisation strategy and campaign to increase its revenue collection which will help sustain the budget and participatory budgeting as a result.
- The introduction of a new participatory planning model in Beira is allowing thousands of citzens to participate in the municipal decision process.
- In Tete the programme promoted a more open and collaborative environment between municipal institutions, civil society and the media, that has been instrumental for improving service delivery in areas such as, water and sanitation, and waste management.
- In Maputo, the programme managed to promote an extensive network of partners working on safe neighbourhood for girls, participatory budgeting and monitoring of health services performance.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Outcome Statement: Several actors interact effectively around municipal governance issues
Indicator	Baseline / 2012	Annual Target 2017/	Achieved 2017		Progress
Sub-Outcome 1: Organised citizens engage with municipal institutions around specific issues Indicator
1.1. % of respondents that say that they know municipal Council plan and municipal work.	8.4% know the municipal plan, 16.5% know the municipal work plan, 12.5% thought it was easy to find and 14% thought it was easy to understand	N/A	N/A		This indicator is a survey indicator measured only during the baseline/inception phase and Mid Term Review. During the MTR,10.3% knew the municipal plan, 18.8% knew the municipal work, 15.4% thought it was easy to find and 16.1% thought it was easy to understand. Awareness of municipal government plans is growing significantly, and more citizens find information about municipal government activities to be both accessible and easy to understand.
1.2. % of survey respondents who consider that help in addressing problems affecting the neighbourhood is always or usually forthcoming from CSOs	Average of 0.61% of respondents across all categories of CSOs; ranging from 1.5% for community associations to 0.2% for labour unions	N/A	N/A		This indicator is a survey indicator measured only during baseline/inception phase and Mid Term Review. During the MTR, an average of 1.8% of respondents across all categories of CSOs, ranging from 2.8% for community associations and 1.8% for labour unions. The overall level of confidence in civil society organisations as valuable allies for neighbourhood problem-solving remains low. There is however a growing perception among citizens that CSOs can help to champion local concerns, but starts from a very low base, and trust in CSOs is actually declining in some areas.
1.3. % of survey respondents who feel that their opinion is fully, very or often taken into account in those community meetings (dissagrehated by gender and youth)(MoV Q 7.8, responses 3, 4, 5 VOICE)	52% of survey respondents (M:56%, W:48%, Y:52%) felt that their opinion was fully, very or often taken into account in community meetings;	N/A	N/A		This indicator is a survey indicator measured during baseline/inception phase and Mid Term Review. At MTR, 44.9% of survey respondents (M:52%, W:41%, Y:43%) felt that their opinion was fully, very or often taken into account in community meetings. Perceptions of community voice are increasing but perceptions of government responsiveness are decreasing.
1.4 Level of CSO (including civic groups) engagement capacity on municipal governance (Outcome Mapping)	0/5	4.2/5	3.9/5		Not met / Although targets were consistently achieved each year, the target was not met in the final year. CSO have been empowered to understand how to encourage change of municipal governance. Final targets show that CSOs capacity to change municipal governance remains a difficult challenge.
Sub-Outcome 2: Media promote public debate around municipal governance issues
2.1. % of survey respondents who agree fully or partially with the statement ‘The media provides valuable information about local issues that concern my community’	57% of survey respondents agreed fully or partially with the statement	N/A	N/A		This indicator is N/A because it is a survey indicator measured only during baseline and Mid Term Review. In the MTR, 66% of survey respondents agreed fully or partially with the statement, increasing then the use of media to have information by people. There has been a significant increase in perceptions of the local relevance of media programming, with two-thirds of respondents now agreeing that the media is a source of valuable information about local issues.
2.2: # of people that participate in media space for citizen voice on municipal governance (project reports)	Total: 0 / Maputo:0 / Beira: 0 / Tete:0 / Quelimane:0 / Nampula: 0	Total: 7,400 / Maputo:1,250 / Beira:1,000 / Tete: 750 / Quelimane:2,500 / Nampula: 1,900	Total: 10,750 / Maputo:2,222 / Beira:1,524 / Tete: 3,017 / Quelimane:2,518 / Nampula: 1,469		Exceeded / The only municipality that did not achieve the target during last year was Nampula, because in the last progress report, Radio Encontro (one of the grantees), did not include the people that participated in the programmes broadcast in local languages. If the grantee had included that information, the target would have been achieved.
2.3: # of media outlets that use ICT to support citizen participation in media debates (project reports)	Total: 0 / Maputo: 0 / Beira: 0 / Tete: 0 / Quelimane: 0 / Nampula: 0	Total:10 / Maputo:2 / Beira: 2 / Tete: 2 / Quelimane: 2 / Nampula: 2	Total: 2 / Maputo: 2 / Beira: 2 / Tete: 2 / Quelimane: 2 / Nampula: 2		Met / This indicator was met. All media outlets use ICT.
2.4: Level of Media capacity to promote public debate around municipal governance issues and to work together with municipal institutions and CSOs (Outcome Mapping)	0/5	3.7/5	4.1/5		Exceeded / DIÁLOGO media partners clearly improved their capacity to engage with citizens, CSOs and particularly with public institutions in order to promote a political debate around municipal issues.
Sub-Outcome 3: Municipal institutions engage different stakeholders into municipal governance
3.1: # of participatory events organized by municipal institutions (project reports)	Total: 0 / Maputo: 0 / Beira: 0 / Tete: 0 / Quelimane: 0 / Nampula: 0	Total: 79 / Maputo: 22 / Beira:7 / Tete: 2 / Quelimane:12 / Nampula:36	Total:89 / Maputo:23 / Beira:10 / Tete:3 / Quelimane:17 / Nampula: 36		Met / All municipalities achieved their targets by carrying out several participatory events in order to implement different governance tools, such as participatory planning and budgeting.
3.2. % of survey respondents who feel that decisions taken in these meetings are acted on always or mostly (disaggregated by gender and youth)(MoV Q 7.13 responses 4 & 5, INFLUENCE, RESPONSIVENESS)	22% of survey respondents ( M: 20%, W: 23%, Y:22%) felt that decisions taken in these meetings were always or mostly acted on	N/A	N/A		This indicator is a survey indicator measured only during baseline/inception phase and Mid Term Review. At the MTR, 11% of survey respondents (M: 10%, W: 12%, Y:10%) felt that decisions taken in these meetings were always or mostly acted on. Women’s perceptions of both voice and responsiveness have improved strongly since 2012, while youth perceive they have greater voice but less responsiveness. Men have become more sceptical about both voice and responsiveness.
3.3 Level of Municipal Institutions capacity engagement with several municipal actors on municipal governance	0/5	4.5/5	4.1/5		Not met / In 2013 Municipal Institutions self-scored with a 2.4, and in 2017 with a 4.2. They clearly think that they are now more open and are including citizens’ demands in the decision-making process, and are more transparent communicating with citizens. However, during the Extension Phase, the increase was less significant. This is because institutions have become more aware that it is possible to do more for a more inclusive and participatory governance. When perceptions change, scoring changes with it.
Sub-outcome 4: Local and national actors implement joint advocacy actions to influence national urban agenda
4.1 # of advocacy initiatives to influence municipal decisions at national level	0	5	6	Met / 1.A National Network of Participatory Budgeting; 2. In partnership with GIZ and Cities Alliance a National Urban Forum; 3. ANAAM Participatory Governance Strategy; 4.Water provision services Advocacy Initiative in Tete; 5. Decentralisation Policy debate around improving Municipal service delivery; 6. In partnership with Municipal Women Authorities Network, a Gender Equality Promotion Plan
4.2 Non-Target Municipalities more aware of participatory, transparent and responsive governance through the intervention of ANAMM in partnership with DIÁLOGO and other programmes.	0	Non Target municipalities show interest for Diálogo municipal pratices	18 Non Target municipalities show interest for Diálogo municipal pratices[2]	Met / Although it is difficult to measure this indicator as influence is hard to measure because of attribution problems, DIÁLOGO has monitored evidence that learning events were effective in influencing municipal institution attitudes and behaviours.
[2] Matola, Boane, Dondo, Moatize, Mocuba, Nacala, Ulongue and Pemba municipalities participated in the last two DIÁLOGO municipal seminars and introduced some elements of DIÁLOGO approach in their governance. Lichinga, Xai Xai, Inhambane, Chimoio, Gurué, Montepuez and Chokwe participated in the challenges of municipalization Seminar together with MAEFP, MEF FIPAG and EDM. The municipalities of Inhambane, Vilankulos and Mandjakaze are being supported by DIÁLOGO and ANAMM to improve participatory governance practices. Women members of 53 municipalities undertake to implement the Plan for the Promotion of Gender Equality.

Overall Outcome Assessment

Overall the programme is assessed as meeting its outcome. Most outcome indicators have been met or exceeded.
The programme measured 4 outcomes indicators around citizen and civil society empowerment (outcome 1), working with the local media (outcome 2) and municipal government to address and engage more effectively on local issues (outcome 3) and in the last year of the Programme, local and national actors implement joint advocacy actions to influence a national urban agenda (outcome 4). DIÁLOGO advocated for a more open and participatory dialogue based on issues raised by communities. Its Theory of Change considered that to improve municipal accountability, transparency and responsiveness it was important to work at all levels for improved collective action and change.
The programme was built on a strong inception phase and baseline study that was carried out in 2012 which provided the framework for implementation. It set out the milestones, target municipalities, but also documented the lack of participatory governance practices and, consequently, an extremely low level of citizen participation in decision making processes and a lack of mechanisms to ensure accountability.
At the end of the programme’s implementation, DIÁLOGO has strengthened the voice and accountability by transforming the institutions and power relations in each of the five municipalities, although with different degrees of success depending on initial conditions and on the political and socio-economic municipal context. In the five municipalities, citizens, civil society organisations, media and municipal institutions worked together around specific municipal issues such as water provision, waste management, urban transport and other issues of concerns.
More specifically:
Sub-outcome 1: Organised citizens engage with municipal institutions around specific issues:
The civic engagement component achieved important results in all five municipalities, with civic groups (local associations, local committees, change agents such as youth activites.) becoming more empowered to engage with municipal authorities, to advocate for citizen demands and to monitor municipal activity. Various participatory tools and practices were used to engage with citizens and inform citizens of their rights such as the use of score cards, theatre groups, and public debates.

The civic engagement component is related to two other components – municipal engagement and media engagement – through which the programme supports municipal institutions to adopt participatory and inclusive governance practices, and media institutions to promote public debate on municipal governance and opportunities for dialogue with municipal actors. These are reported below.

Indicator 1.4 is measured during municipal seminars held each year and is based on CSOs self-evaluation. At the beginning of the programme, civic engagement actors self-evaluated their capacity with a score of 1.9 out of 5. At the end of the programme, their final score was 3.9. This increase stems from an increase of citizens’ self-confidence to interact with institutions, and their improved knowledge and capacity to engage with municipal institutions.

The focus of the last year of the project for the civic engagement component was to achieve a ripple effect via the dissemination of best practices and ways of working among other non-Dialogo beneficiaries. The project in the last year reached out to 33 new neighbourhoods and targeted a total of 132 new civic groups and organisations.

Success stories include better waste management for Quelimane and Tete, joint solutions on primary health care in Beira and electricity and water management and participative budgeting in Nampula. Many citizens and civic groups are now engaging through their own intiative in DIÁLOGO activities, which is a significant step towards the programme’s sustainability.

Sub- outcome 2: Media promote public debate around municipal governance issues

DIÁLOGO encouraged media outlets to be interested in issues of concern to citizens, and to interact directly with civil society actors and municipal institutions. The results show that local media has become an efficient channel to amplify the voice of citizens and as a catalyst for engagement between citizens and the municipal institutions. The media contributed significantly to a critical and vibrant public debate, and promoted transparency and accountability as essential elements of good municipal governance. Media outlets are recognised as a true source of information on municipal affairs in the five target municipalities.

DIÁLOGO trained its media partners on issues of municipal governance, using social networks such as Facebook, SMS, as well as improved techniques for live streaming using a mobile handset. DIÁLOGO also developed new digital platforms, including websites and mobile apps for its media partners, radio and electronic newspapers, as part of a digital marketing strategy to increase its outreach and audience, visibility and financial sustainability. It worked in training both male and female journalists to make journalism more inclusive. It also supported better journalistic quality and media content that addressed the concerns of citizens. The three indicators related to this component over achieved or were met:

2.2: # of people that participate in media space for citizen voice on municipal governance (project reports) reached 55,605 participants against an expected 33.850 participants through the life of the Programme.
2.3: # of media outlets that use ICT to support citizen participation in media debates meeting the target of 10. All 10 media partners now use ICT to support citizen participation in media debates.
2.4: Level of Media capacity to promote public debate around municipal governance issues and to work together with municipal institutions and CSOs over-achieving with a target of 4.1 against 3.7.

Sub-Outcome 3: Municipal institutions engage different stakeholders into municipal governance

The third outcome of this project prioritises municipal engagement mainly by engaging with and demanding more transparency and responsiveness towards citizens’ needs and demands. It measures the # of participatory events organised by municipal institution. The overall indicator was over-achieved with 221 against 217 but under achieved for Beira and Quelimane. Beira and Quelimane saw delays in implementing all planned participatory events.

The priority in the final year managed to institutionalise best practices and ways of working with communities that will continue after the closure of the project. One of the tools that will continue to be used is the participatory budgeting, which can easily be monitored and has gained traction in Nampula, Beira and Quelimane. DIÁLOGO supported other non-target municipalities such as Inhambane, Xai Xai and Mandjakaze, to improve their participatory planning models. Municipal institutions clearly think that they are now more open and are including citizens’ demands in the decision making process, and are more transparent communicating with citizens.

Sub-outcome 4: Local and national actors implement joint advocacy actions to influence national urban agenda

This outcome was added in September 2016 but implemented during 2017. This sub-outcome was intended to respond to DFID’s Annual Review recommendation to increase the programme’s “learning for policy influence”. DIALOGO designed a Learning for Consolidation and Influencing Strategy.

The indicator measured the “# of advocacy initiatives to influence municipal decisions at the national level” to gauge the capacity of DIÁLOGO’s policy influence. DIÁLOGO promoted six advocacy initiatives as planned, some of them will have follow up actions:

A National Network of Participatory Budgeting: In collaboration with ANAMM and the World Bank, DIÁLOGO promoted and influenced the set-up of a national network for participatory budgeting and the expansion of its use by a larger group of municipalities. This initiative brought a vibrant debate around the need to increase the sustainability of municipal resource management.

A National Observatory of Participatory Democracy: DIÁLOGO contributed to the set-up of a National Observatory of Participatory Democracy in collaboration with ANAMM and other key governance programmes . This mechanism has the potential to promote values and principles of good municipal governance, and offers the opportunity to influence the adoption of good practices by a range of local municipalities.

A National Urban Forum: In partnership with Germany/GIZ, Cities Alliance and ANAMM, DIÁLOGO established a National Urban Forum as a space to discuss and address the main challenges faced by Mozambican cities with Government with the objective to have a Joint Urban Action Plan.

Debate on Mozambican Municipalisation Challenges: DIÁLOGO commissioned a Policy Brief about the “Challenges of Mozambican Municipalities”. The document was presented and discussed with several representatives of municipalities, national Ministries, public companies and international donors. The discussion identified main challenges that the municipalities are currently facing as a decentralised and independent institution for providing effective service delivery.

Round tables around municipal governance structural blockages: CESC produced four studies about the challenges regarding water access in the municipality of Tete, urban resettlement in Maputo, double-administration in Nampula and solid waste management in Quelimane. The four studies were presented at four round tables in respective municipalities with all relevant stakeholders. In each municipality, civic groups, CSOs and media are continuing to advocate to resolve identified problems.

A Plan for Gender Equality on Municipal Governance: DIÁLOGO supported the Rede Nacional das Mulheres Autarcas (National Women Authorities Network ) to promote a Gender equality agenda and Action Plan for all 53 Mozambican municipalities which committed to implementing key activities in their municipalities.

Output Score and Description

During the period of the programme, the outputs overall scored A from 2013-15 and A+ in 2016 to 2017.

Overall output score for the programme’s PCR is an A+. The Programme has received an A+ in Civic Engagement (40%), an A+ in Media (30%) and an A+ in Municipal Engagement (30%).

Lessons and how these have been shared

One key lesson is to conduct evaluations earlier in programme. The programme’s mid-term evaluation was finalised late with final findings only being shared early 2016. Even with a 10-month extension it was not possible to invest in new areas such as a more focused approach to gender inclusion and policy influencing as much as the project would have liked to.

Urban issues are becoming more prominent and it will be important for future DFID sector programmes to focus on urban municipal problems as they can support/block problems in a province.

The Political Economy is different in each municipality which is reflected in the different scores. The project understood early on that it is important to work with local partners that understand the context and to adapt the support and expected results to each context. The Facilitators were helpful as a catalyst actor in that they acted as impartial supporters, and had the informal contacts and understanding to create the linkages to problem solving.

Key to the success was to continue engaging with municipalities’ leadership and communities and the media to help triangulate successful collective action.

The Programme made contribution to the development of an enabling environment for more decentralisation and therefore effective local governance in the country as a whole. Without government’s commitment to reform, projects alone will not have an impact on the country’s development. Support therefore needs to be targeted to municipalities and its communities where progress can be achieved and change measured.

The programme looked at mitigating risk as much as possible, with a robust risk management framework in place and a close coordination with partners who faced such challenges. Nonetheless, decentralisation remains a contentious topic and the programme had to work hard to build commitment and buy-in to its objectives. Its core focus on citizen engagement, rather than on the decentralisation policy itself, was crucial not only to mitigate risk but also to open up the space for discussion about the municipal governance agenda.

The overall biggest success story is the media component. Throughout the project, this has been a great tool to communicate and discuss issues, and also educate and empower citizens and municipalities to work together.

Another issue was the current institutional framework for service delivery at the municipal level, in which several entities (local and national ) compete for the provision of services with limited coordination and alignment. In other words, the municipality is not the only public entity that provides services in the municipal space. The central government, through its local governmental (districts and provincial government) and administrative entities, such as public companies and trusts, also provides services in the municipal space. In functional and assignment terms the central government competes with, or complements, the elected municipal government, but follows different institutional logic and approach. That competition is most common in areas such as water provision and land management, as well as, roads maintenance and taxation, which results in extremely complex, conflicting, expensive and ineffective service delivery.

Various learning events were organised in 2017 most notably: A final DIALOGO Event was organised on 8 November which was well attended by the CSO community and donor community. On 7 December DFID organised a meeting for donors with DAI and IDS specifically on lessons learnt of DIALOGO and the Ripple Effect Etudy carried out by IDS.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Civic Engagement: Mobilising, sensitising and supporting citizens to engage on municipal governance
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
1.1. # of civic groups and individuals assisted on engagement practices	150 groups and 2,226 individuals assisted on engagement practices: / Maputo:24/307 / Beira: 19/452 / Tete: 21/271 / Quelimane: 41/407 / Nampula:45/789	Milestone exceeded / 261 groups and 4,859 individuals assisted on engagement practices: / Maputo:45/833 / Beira: 51/587 / Tete: 30/375 / Quelimane: 66/1695 / Nampula: 69/1369
1.2. # of NON-DIÁLOGO partners informed on DIÁLOGO approaches, methodologies and adopting DIÁLOGO approaches	79 NON-DIALOGO partners trained and involved with DIALOGO: / Maputo: 35 / Beira: 3 / Tete: 10 / Quelimane: 14 / Nampula: 17	Milestone exceeded / 132 NON-DIALOGO partners trained and involved with DIALOGO: / Maputo: 37 / Beira: 35 / Tete: 12 / Quelimane: 15 / Nampula: 33
1.3. # of coalition/ synergies between municipal actors working around priority issues	84 coalition/ synergies between municipal actors working around priority issues: / Maputo: 19 / Beira: 14 / Tete: 12 / Quelimane: 25 / Nampula: 14	Milestone met / 94 coalition/ synergies between municipal actors working around priority issues: / Maputo: 22 / Beira: 16 / Tete: 15 / Quelimane: 25 / Nampula: 16
1.4. # of municipal actors that engage with municipal institutions on current priority issues (disaggregated by type of organization - youth and gender focused)	173 municipal actors engage with municipal institutions on current priority issues: / Maputo: 22 / Beira: 20 / Tete: 25 / Quelimane: 51 / Nampula: 55	Milestone exceeded / 212 municipal actors engaged with municipal institutions on current priority issues: / Maputo: 26 / Beira: 30 / Tete: 33 / Quelimane: 65 / Nampula: 58

Key Points

As shown by indicator 1.1, DIÁLOGO promoted a strong civic engagement around specific issues with several civic groups, NGOs and individuals. The project uses various accountability tools (such as community score cards and community action plans) to gather communities’ needs and provide advice on how to prioritise and address them. 261 community groups and 4,859 individuals participated across the 4 municipalities. The expansion of civic engagement was introduced in the last year of the Project hence the reason for the significant increase of the number of civic groups (associations, committees, individuals, informal groups, etc.) that engaged in municipal governance.

Box 1 summarises the main tools and methodologies adopted by Diálogo to foster community-level civic engagement.
Box 1: Tools and methodologies of the civic engagement component at community level
Action	Tool/Methodology	Description
Awareness Raising and mobilisation	Door-to-Door	Awareness raising and mobilisation of citizens about their rights and duties in their homes.
	Community Debates	Debates in the neighbourhoods, with municipal institutions, about issues that concern citizens.
Advocacy	Public Petition	Position paper to denounce irregularities in the provision of municipal services and violations of citizens’ rights or to demand accountability from municipal institutions.
	Community Action Plan	Outlines citizen priorities and is used as an advocacy tools with local institutions.
	Citizen Scorecard	Allows direct dialogue between citizens and service providers with a view of promoting social accountability and the capacity of municipal institutions to respond to citizens’ demands.

Source: Abordagem do Diálogo 2017, Final IDS Report 2017

Indicator 1.2: This indicator was introduced after the MTR in 2016 to encourage the civic groups to work more openly. The project expanded to non-DIÁLOGO partners in new neighbourhoods which was a great success. There is a real appetite to understand how municipal governance works and how best to engage with municpalities. Two new partners working on the Gender and Social Inclusion Strategy mobilised a huge number of people, social groups, community and religious leaders, and institutions in Maputo and Tete. In Beira, the land tenure advocacy campaign mobilised many organisations for the participatory planning process, and in Maputo, partners mobilised organisations around waste removal and urban resettlement.

Indicator 1.3: This indicator assesses the extent to which DIALOGO partners are working together. It measures the types of coalitions that actors were articulating in order to resolve a specific problem in the community or to influence a policy. In Maputo, Beira and Tete, the coalitions focused on influencing policy and management decisions, such as water, lighting, urban transport and land management. Meanwhile in Quelimane and Nampula, the coalitions focused on resolving immediate problems such as transportation routes, water provision, elimination of illegal garbage deposits, and the rehabilitation of bridges.

Indicator 1.4 This indicator was pre-existing, but required disaggregated data as of 2016. DIÁLOGO expanded its engagement, not only with municipal institutions, but with services providers such as in charge of electricity (EDM), water (FIPAG). While the PMU wanted to add disaggregated data during the last year, it was not practical to collect this information given the work load of the PMU and the challenges around the collection of data, and the data was later considered irrelevant. Some organisations have different mandates and therefore the results of their work was considered more important to measure and less so the quota of workers working in respective organisations.

Summary of responses to issues raised in previous annual reviews (where relevant)

DAI produced a report on the implementation of the Gender Strategy on 2 October. It also touched upon the challenges women and youth face from participating meaningfully in governance issues at a municipal level. The analysis looked how the programme is addressing these concerns mainly through the media and civic engagement component. More details are outlined under each relevant output.

Recommendations for future programmes

- Governance programmes need to include a capacity-building component - In Mozambique, very few CSOs have experience and capacity around advocacy or civic mobilisation and engagement.
- Advocating at local and national level - Although the municipal administration is decentralised from the central government, there are several municipal services that still depend on public companies and the central administration. In order to influence and improve municipal governance and management fully, it is necessary that governance programmes act at both levels.
- Focus on enhancing actor synergies - In Mozambique the competition for funding limits the capacity of NGOs to establish synergies. Governance programmes need to invest time and resources to build trusting relationships among civil society actors.
- Promoting community development around local issues - Citizens are more motivated to engage around specific issues that affect their direct life. Civic engagement needs to have a community development approach that guarantees the promotion of social changes at the community level.

Output Title	Strengthen and Engage Media: Building capacity to promote media coverage, interaction and public debate around municipal governance.
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
2.1. # of interactive media transmissions and articles / (radio, television, newspaper) on municipal governance	215 interactive media transmissions and articles: / Maputo: 35 / Beira: 35 / Tete:35 / Quelimane:35 / Nampula: 75	Milestone exceeded / 265 interactive media transmissions and articles on municipal governance: / Maputo: 47 / Beira: 52 / Tete:39 / Quelimane: 43 / Nampula: 84
2.2. # of journalists trained on several issues (1st year on electoral process)	25 journalists trained on several issues	Milestone exceeded / 140 journalists trained on several issues
2.3 # of media programmes and articles about electoral process from media grantees	n/a ( Target measured during year 1 of the implementation of the programme)	n/a
2.4 # of investigative journalism pieces on priority issues reported by media	n/a (target measured during year 2 and 3 of the implementation)	n/a
2.5 # media outlets where ICT were set up	No milestones set this year. Milestones exceeded last year. No new radio stations therefore no ICT introduced.	n/a
2.6 # of interactive media transmissions and articles / (radio, newspapers) on women, youth and another vulnerable groups issues	40 interactive media transmissions and articles on women, youth and another vulnerable groups issues	Milestone met / 61 interactive media transmissions and articles on women, youth and other vulnerable groups’ issues

Key Points

All indicators under this component were achieved and exceeded.

This component was seen as the weakest in terms of gender inclusion. A lot of effort was put in 2016 and 2017 to include a shift in culture so that women participate in news making as well as more generally across all other components of the project. Capacity training was provided to ensure more equality and gender training in journalism. Journalists were also encouraged to champion greater gender equality and social inclusion, and to introduce the principle of positive discrimination when covering municipal governance related issues, in favor of women’s and youth related issues.

As per the 2016 Annual Review, media was seen to promote public debates around municipal governance but was not fully considered as a tool to resolve local problems. However as of 2017, media is clearly seen to promote an opporuntity for citizens’ voice in order to put forward their demands and influence policy makers.

2.1 Exceeded. The target number was set for 215 interactive media transmissions and articles on municipal governance issues but was exceeded with 265 achieved transmissions. This is largely as a result of the capacity training initiatives with local radio stations and newspapers. DIÁLOGO built the capacity of 10 media partners. Media partners also increased the number of live transmissions out in the communities using portable equipment, in order to increase the participation of women, youth and other vulnerable groups. In total, 1,502 transmissions and articles were completed throughout the life of the Project.

2.2 Exceeded. 140 journalists received training against the target of 25. The training was on radio editing, radio journalism, governance, social media and digital tools, and taught how to prepare a business plan and financial management. At the end of the programme, 365 journalists received training.

Indicators 2.3, 2.4 and 2.5, were no longer measured in 2016 and 2017. These were met in earlier years and formed the baseline for future indicators. However to record all that was achieved during this Project:

Indicator 2.3 # of media programmes and articles about electoral process from media grantees.
This indicator was used only during the first year of the programme coinciding with last municipal elections and was met.

Indicator 2.4 # of investigative journalism pieces on priority issues reported by media (target measured during year 2 and 3 of the implementation). This target was achieved during year 3 of the Programme. , 5 journalists, one in each municipality, produced one invetsigative journalism piece.

Indicator: 2.5 # media outlets where ICT were set up. Milestones exceeded in 2016. No new radio stations therefore no ICT introduced. At the end of the programme all 10 media partners are using ICT.

Summary of responses to issues raised in previous annual reviews (where relevant)

None were raised in the last AR

Recommendations for future programmes

A key take away from the Programme and MTR is that when working with the media, it is important to factor in gender equality in the media sector. In sum, this means introducing an equal representation of women in journalism, having guidelines on reporting gender issues or specific with a gender lens, and empower the voices of women when covering stories.

Output Title	Engagement of Municipal Institutions: Supporting municipal institutions on participatory governance and actor’s dialogue.
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	30
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
3.1.# of communication initiatives to disseminate municipal institutions’ informations	10 communication initiatives to disseminate municipal institutions’ informations: / Maputo: 2 / Beira:1 / Tete: 0 / Quelimane:4 / Nampula: 3	Milestone met / 21 communication initiatives to disseminate municipal institutions’ informations: / Maputo: 4 / Beira: 3 / Tete: 6 / Quelimane:5 / Nampula: 3
3.2. DIALOGO Municipal Technical support Plans designed and agreed	5 Municipal Technical support Plans designed and agreed	Milestone Met / 5 Municipal Technical support plans were designed and agreed for the final year of the project.
3.3. # implementation of Municipal Technical Plans (% annual activities)	Met last year. No milestone this year.	n/a
3.4. # of dissemination/advocacy activities on lessons learnt/best practices/ municipal studies / beyond target municipalities	8 dissemination/advocacy activities on lessons learnt/best practices/ municipal studies / beyond target municipalities	Milestone exceeded / 13 dissemination/advocacy activities on lessons learnt/best practices/ municipal studies / beyond target municipalities
3.5 # of municipalities’ initiatives prioritising vulnerable groups	5 municipalities’ initiatives prioritizing vulnerable groups	Milestone exceeded / 7 municipal initiatives prioritising vulnerable groups

At the aggregated level for each indicator, all have been met or exceeded. This output is about improving municipal government’s approach and responsiveness to citizens’ demands. In a way it is about introducing good governance and better service delivery practices through relationship building, raising awareness and educating municipalities on peoples’ rights to better services. The project has worked with municipal institutions - both councils and assemblies - to help them improve their governance approach. During the last year of the project, the aim is to continue disseminating: DIÁLOGO best practices; its tools and tactics for capturing citizen’s needs (e.g. participatory budgeting); as well as its lessons learnt, both for its target municipalities and other groups, including NGOs and media stakeholders working on municipal governance.

Details

3.1 Met. Activities under this indicator included the production and dissemination of the municipal activity plans, budgets and key legislation through the production of a municipal newsletter, website, and a hot line. DIÁLOGO helps municipalities increase their communications capacity in order to promote transparency and accountability to citizens, as well as to promote awareness campaigns on citizens’ rights and duties. In Quelimane, Nampula and Maputo, several communications activities were facilitated, such as a tax campaign to introduce revenue collections and pamphlets on participatory budgeting in Maputo and Nampula.

3.2 Met. The targeted number of Municipal Technical Support Plans designed and agreed upon was met (1 in each municipality[3]). These plans included actions such as support to improve the respective municipality’s communication capacity and their ability to deliver services including their work on participatory budgeting. This activity was largely supported with technical assistance.
[3] The plan for Tete was designed but not formally agreed yet. Activities have started.

3.3 Met. % of implementations of Municipal Technical Support Plan. During the last year all Municipal plans were implemented in the five municipalities.

3.4 Exceeded. This indicator captures DIALOGO activities that aim to disseminate lessons learnt and best practice studies in order to promote exchanges among target and non-target municipalities. Activities include workshops, meetings, publications, newsletters, and websites with resources for municipalities. In 2017, 13 dissemination/advocacy activities on municipal governance were carried out in order to share DIALOGO’s best practices with non-target municipalities and to encourage a dialogue with the national government and other involved stakeholders on municipal governance. Some examples include: The Participatory Budgeting Network with ANAMM that was set up in 2016, The First Urban National Forum in 2016, and introducing Gender Equality Actions Plans in municipalities in 2017 (exception phase).

Indicator 3.5 was added in 2016. This indicator measures the number of municipal initiatives that prioritise vulnerable people. Each target municipality has at least one new initiative that prioritises vulnerable groups, such as the introduction of budgeting for women and youth quotas that benefit from urban poverty funds.

Some of expected results include: In Nampula and Quelimane DIÁLOGO supported the elaboration of gender mainstreaming policies in partnership with MUVA, a DFID funded programme, which will ensure womens’ participation in all levels of governance (planning, budgeting, monitoring). In Tete, the municipal council is supporting the initiative of “good neighbours” that involve social activists and local authorities to solve local problems. It works well at local level and reinforces the sense of citizenship based on values of social justice. Other interventions that were reported in last year’s Annual Review as beginning:

•	A quota for women and young people has been introduced so that they too benefit from the Urban Poverty Reduction Fund in Quelimane and in Beira.
•	Nampula is implementing the Safe Cities Plan to reduce crime. This Plan involves various actors such as the police, municipal institutions and CSOs.
•	A Gender Budgeting Guide for the 5 municipalities produced and published.

Summary of responses to issues raised in previous annual reviews (where relevant)

PMU produced a Gender Budgeting Guide.

Recommendations for future programmes

•	Programme objectives and donor agendas need to be coordinated with the government and municipalities to ensure buy in from all parties.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The programme spent a total of £9,639,578.96 including £154,797.48 for the design phase. Payments for the Programme were milestone based primarily.
The original contract was agreed on the basis of fixed payments linked to deliverables and output milestones. The programme has performed well against respective targets and all milestones have been met.

VfM performance compared to the original VfM proposition in the business case

The Business Case set out a detailed framework for monitoring VfM which is reported against in the table below. There is room for improvement in equity and sustainability.
The programme spent within its agreed budget. It met or exceeded all of its VfM targets and objectives. Through following strict procurement rules and working to achieve results that leveraged funds at every turn, DIÁLOGO outperformed DFID’s expectations.

Assessment of whether the programme represented value for money

The Final Evaluation produced by IDS concluded that DIALOGO performed reasonably well against the
indicators. The programme responded well to the MTR and previous Annual Review recomendations to improve the ripple effect and learning of the Programme.

DFID’s investment in DIALOGO was strategic and contributed to the changes that validated key assumptions and value propositions in the original business case, despite limitations concerning sustainability and the difficult political and economic context.

Overall the programme represented good value for money.

VfM measure	Evidence/Analysis
Economy: A measure of what goes into providing a service where unit costs are typically used as an economy measure. DIÁLOGO’s VfM framework contains two indicators to measure the programme’s economy:
Cost per major cost driver: 1) domestic RT airfare (per trip); 2) municipal learning workshops (per workshop); 3) PMU staff costs (as % of overall spending for period); 4) external consultant costs (total per day of consultancy); and 5) Maputo office administrative costs (as % of overall spending for period)	The programme has historically performed reasonably well in areas of economy, meeting most cost drivers targets and using competitive procurement processes. / The average cost per airfare was £161 below the £500 target for the life of the project. / The average cost per workshop was £5,146 slightly above the £5,000 target. / The average costs for the PMU staff for the entire project was 34%, well below the agreed target of 42%. / When the MTR was completed the average consultant cost per day was above the £450 target, throughout year 4 and year 5 was significantly below this figure, and under £250 during the final 3 quarters.
Efficiency: DIÁLOGO’s VfM framework contains four indicators to measure programme’s efficiency. All outputs have been met or exceeded.
Cost per civic group supported and per person participating in media space for citizen voice on municipal governance issues during the reporting period	The cost per civic group per quarter has consistently been under the £10,000 target since the start of year 3, reaching under £7,000 in the last 2 quarters. The outreach strategy and exchange rate fluctuations have contributed downward pressure on this indicator. / The cost per person engaging/cost per engagement in the media space has fluctuated in line with grant disbursements and implementation costs linked to efforts to increase the sustainability of the media component. Costs were higher in Year 4 following the MTR and at the start of the Extension Phase,. then dropped in the Extension Phase, and were within the expected range for the last four months of the programme. The overall average was £21.28 against the £15 target.
# of days to process a grant (from announcement to first fund transfer, for Challenge Fund grants; from presentation of initial proposal to first fund transfer, for non-competitive grants)	The average figure for grants processing time was 47 days. For the last new grant processed, in Y3Q3, the time taken to process it was only 28 days which is efficient. No new grants were created in Year 4 during the extension Phase.
% of DIALOGO budget spent on direct programmatic support versus administration and other overhead costs / *Note that all PMU administrative and finance support for grantee activities are included in "Administration Costs".	The programme administration rate averaged 28.8% over the whole programme compared with the internal VFM target of 33%, having dropped to under 20% for the last three quarters. The decrease in administration rate reflected an increase in programme spend in Year 4 and the Extension Phase, with an average rate of 78% against a 67% target. This meant that more DFID funds were efficiently directed towards interventions, so as to achieve more results for the same contract amount. This was possible due to savings made and because the PMU became better at managing their finances and developed better relationships with vendors.
Cost per beneficiary per major objective included in annual municipal engagement action plans	This VfM calculation began in Year 2 Quarter 3, once the municipal action plans were created and there was enough data on beneficiaries to make reasonably useful calculations. The cost per beneficiary averaged £6.55 for the entire programme, well below the target of £12.50 whereas the costs per person benefiting from accountability practices has fluctuated on a quarterly basis and dependent on the focus of each municipality, here the programme averaged £99.19 per citizen for the life of the project (well over the £35 target) but was within the target range nearly 60% of the time.
Effectiveness: Qualitative and quantitative measures of increase or decrease in outcomes that show that a programme ‘is effective in delivering its intended objectives’. This examines the relationship between outputs and outcomes.
# of activities developed in collaboration with complementary programmes / implementers	Throughout the life of the project, the PMU developed 81% of its activities in collaboration with complementary programmes/implementers, thus surpassing target of 48% by a healthy margin. By partnering and collaborating with other donors and programmes allowed DIALOGO to share costs of some of the larger events, which was a cost saving. The nature of the collaborations and their relative effectiveness include sharing various training, partnerships to deepen work on gender, social inclusion and equity; co-convening meetings where experiences were shared; numerous activities with ANAMM and providing technical assistance to PRODEM and MASC.
% of grant-funded projects implemented successfully	Performance against the project success rate indicator which targeted an average score of 8 was still below the target set at project completion. The final score for the 19 projects completed was 6.7, a slight reduction from the score in year 4, when the 11 grants evaluated achieved an average score of 7.4, which marked an increase of previous scores. The failure to achieve this target largely reflects challenges grantees experience with grant management and getting reports in on time. Also, each period had different grantees, which were of different quality and thus capacity levels. Media grantees had the lowest capacity, and therefore the lowest scores. The PMU tried new grant management tactics to improve their capacity and focused on improving capacities for each next quarter which they did.
Equity: Finding optimal means to ensure that the interests of the most marginalized are represented directly or indirectly in participatory planning and budgeting activities.
	The programme has made considerable efforts to follow the MTR and the 2016 AR reccomendations on Equity. The PMU hired technical assistance to revise its gender and inclusion strategy and work with partners. More specific actions taken include gender training for the various civic, media and municipal actors involved in the programme; new partnerships with emerging feminist groups; a new project with an existing partner, Parlamento Juvenil, which had a specific focus on fostering young people’s involvement in municipal governance; and assisting media partners in the design of tailored programmes for women and youth amongst others. In addition the PMU revised the logframe to include new indicators to measure women’s participations in activities and number of interactive media transmissions and articles on women, youth and other vulnerable groups. However the programme could have done better at presenting sex and age-disaggregated data in its quarterly and annual reports and in its annual learning workshops (a MTR reccomendation) and in gathering data on the effects of the investments made on gender. The only data that has been systematically reported since the MTR is the percentage of female activists. It is possible that this issue with data is related to partners weak capacity/experience with data collection and/or the quality of the data itself.
Sustainability:
	The MTR and subsequent Annual Review stated that, in order to achieve a broader impact, DIÁLOGO should address some immediate challenges and deepen its focus on long-term sustainability. In response to this DIÁLOGO prepared an Extension Activity Plan that included three strategic lines 1) Consolidation and sustainability of the DIÁLOGO approach 2) Learning and policy influence and 3) Gender and social inclusion. The programme was reasonably successful in intensifying learning and in strengthening capacity development for existing partners and in the outreach to new partners both within and beyond the target municipalities but it is questionable whether they will be able to embed these after funding from Diálogo ends in the absence of other resources. Large CSOs appear better able to sustain engagement with the full suite of Diálogo approaches than small civic groups while the sustainability of media stations looks less certain. The Final Evaluation found evidence of a change in knowledge, attitudes and behaviour in relation to municipal governance across a range of stakeholders that may well continue beyond longer-term Diálogo partners, and it claims that that the “systemic engagement capacity” first identified at the MTR may prove sustainable within target municipalities. At the national level, the final evaluation considers that the sustainability of the influence achieved by Diálogo is likely to be limited, though some of the publications produced in the last phase of the project are likely to prove useful for some time to come, and some of the initiatives developed with ANAMM (such as the participatory budgeting network) may well continue with support from other donors.

Quality of financial management during programme

The financial management for the programme followed DFID-DAI contract procedures. DFID’s contract with DAI Europe was divided into monthly payments for grantees which varies and agreed milestones which were out in an agreed work plan.

As highlighted already, DAI financial reports had limited detail of information because of the nature of milestone linked payments that did not demand for costs details. This is a lesson that will feed into future contracts and is already being addressed by the new way of contracts management by PCD.

The initial contract value was £7,987,196.71 and end date was 28 February 2017. The programme was extended on the 20th of July 2016 by ten months, at a cost of £1,496,931. This brought the total value of the contract to £9,484,127.71.

Quarterly and annual reports were received on time, concise and of decent quality. DAI demonstrated good procurement management practices and built equally strong partnerships with stakeholders at various levels including the downstream partners.

Financial management processes and controls were detailed in the project’s field operations manual and grant manual. The PMU provided training to grantees to ensure compliance through the delivery chain. DAI keeps all grantee financial reconciliation documents. All grantees were audited by DAI with some grantees such as Kukumbi, Livaningo, Facilidade and Parlimento Juvenilproducing their own annual audits which were shared and approved by DAI.

DFID undertook more than annual spot checks. During the final year, there were two asset spot checks, in April and September 2017. The spot checks ensured that assets were being properly managed. Physical verification of the assets also informed DFID for decision making for final assets disposal.. DAI sent a request to DFID to dispose of various assets to grantees and to keep other assets required for the functioning of the FSD Moz project, another DFID programme, which shares office with DIALOGO. DFID followed the procedures for project closure and DFID Head of Office approved DAI’s request for the disposal of DIALOGO assets in a way that represents best value for money. Computer equipment were transferred to the DIALOGO grantees and Local NGOs, IT equipment was transferred to FSDMoc for the remaining of period of the Project. The vehicle was transfered to Save the Children and Helen Keller International for the Linking Agribusiness and Nutrition programme. This was a great way to save money on the Nutrition programme, delivering VFM for DFID. Availability of the vehicle also allowed the new programme a quick set-up time as they avoided the procurement of two new vehicles.

With the contract extension, DAI shared additional financial information through their quarterly reports. DAI carried out yearly external independent audits which found no significant financial risks and previous audit recommendations were timely implemented. DAI commissioned a final external audit report covering the period 1 March to 20 December 2017 which was submitted to DFID in January 2018. No major issue was raised apart from a vendor having to refund a total of £7,002.23 to DIALOGO. The full amount will be reimbursed to DFID by 31st March 2018.

Date of last narrative financial report	20/11/2017
Date of last audited annual statement	9 January 2018

E: RISK (½ page)

Quality of risk management over the life of the programme

The overall risk rating for the programme was moderate. Programme risks were reviewed on quarterly basis and major risks were escalated to management. Programme team also tracked major risks to ensure all was under control.The ratings for existing risks have been changed to the new risk format, but there was no change in the perceived level of risk. The risk matrix is attached as Annex B.

The PMU conducted municipal learning and Theory of Change workshops on an annual basis which were attended by all of DIÁLOGO partners in order to review programme implementation, and to assess contextual changes and risks. Risks were updated in March 2017 with the PMU to cover the last year of the programme and then in December for the PCR. Below is a summary of risks mitigated as well as those that materialised during the life of the programme.

The risk matrix outlined risks related to the external context. The peace process and possible civil unrest in urban areas were a constant risk throughout the Programme. Even though there was instability and low-conflict in some remote areas, it did not affect Programme’s delivery.

A challenge that was taken donors by surprise is the recent murder of the mayor of Nampula, one of the great champions of DIÁLOGO’s governance approach. The municipal level tensions among parties has increased polarisation and intolerance which has resulted in a more restricted space for dialogue such as in the case of Nampula.

Key challenges related to the lack of decentralisation which remains a contentious topic. The programme had to work hard to build commitment and buy-in of the Programme. Its core focus on citizen engagement, rather than on the decentralisation policy itself where there was little traction with Government, was crucial to mitigate risk and to help open up the dialogue with Government.

The end of the Programme means that there may be a gap in support to local municipal governance. Other donors are interested to take onboard some of the good practices of the Programme such as Germany. Other donors are designing new programmes which may focus on urban governance and citizen engagement. Lessons learnt from this Programme will be communicated across the DFID office for future sector programming and shared more widely with the donor group.

A new risk indentified in 2016 was the financial crisis which constrained municipalities’ budgets and therefore space for citizens to encourage prioritisiation and spending for the next couple of years.

Political context and enabling environment risks were addressed by working with all stakeholders, ensuring programme buy in, through stong partnerships with both communities and government. DIALOGO focused its intervention on municipal institutions and not on political parties.
To prevent fiduciary risks, DAI undertook due dilligences on all new grantees before they were awarded funds and, where the due diligence assessments suggested that there were insufficient procurement systems in place, the PMU procured on behalf of the grantees and provided assets in kind. It then also provided training in asset management as a follow-up. The program also opted to procure and make direct payments to the service providers. Annual audits were carried out and the PMU has had a good track record on having strong financial control systems in place which was confirmed by the MTR.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme delivered its targets according to the planned timeline. The Project was extended in September 2016 for another year, taking the project completion date from 28 February 2017 to 31 December 2017. The overall purpose of this extension was to ensure that the gains made by the programme would be sustainable in terms of participatory governance at municipal level. The extension period also provided space for learning and informing any future governance programming by DFID and other donors.

Programme closure concluded with a Final Event on 8 November to share lessons learnt and knowledge gained from the DIÁLOGO experience among different actors, political institutions, governance programmes and donors. This lessons learning event also helped to inform the external evaluation conducted by the Institute of Development Studies (IDS). DFID also organised a meeting with donors active in CSO engagement on 7 December to share the lessons of the programme and recommendations for future Programmes.

Performance of partnership (s)

DFID staff developed good relations with DAI and the Programme Management Unit and consortium partners, COWI and CESC. DAI was very responsive, shared work plans, objectives, budgets and review processes openly and collaboratively with DFID.

The Quarterly management meetings with DIALOGO were held on a timely basis during the course of the project to monitor progress, discuss AR recommendations, major milestones and presented a good opportunity for deliberation and decision-making. DAI responded well to challenges, adjusting as necessary, the Mid-Term Review findings and subsequent DFID Annual Reviews as well as the Final Event are testimony to that.

Throughout the implementation years, the project consolidated partnerships at various levels and built credibility within the municipalities which helped getting buy-in to the project objectives and encouraged partners to adapt their exisiting approaches and adopt new ones as when necessary. For example, the project collaborated with ANAMM to produce a set of guidelines which provide clear indications on what, where and how municipalities can mobilise more revenues. The investement in this area has resulted in various tax education initiatives, in the municipalities of Nampula, Quelimane, Tete and Beira, being carried out by the municipal council in partnership with civil society and media, independently of the programme. Feedback from partners has been very positive. PRODEM, MUVA, MASC, and other programmes are interested in integrating DIÁLOGO’s approach into their interventions. Up to 60% of DIÁLOGO’s civic and media partners already have or are coordinating funds to continue to implement DIÁLOGO inspired projects in target municipalities. ANAMM is mobilising funding to follow up on the work started by DIÁLOGO on participatory budgeting and other similar good governance initiatives.

Asset disposal and value obtained by DFID

DAI maintained asset registers during the project and an asset disposal and transfer plan was developed bertween DAI and DFID as part of the close out activities. The total initial value of the assets was £73,417.31 (including a vehicle) and the current value is only £1,677.15 after normal depreciation. In 2016 DFID approved the PMU’s request for early disposal of iPads and chairs and the write-off of stolen and damaged iPads.

DFID Head of Office approved transfer of a vehicle, which wast the bidggest asset of the programme. The vehicle was transfered to Save the Children International and Hellen Keller International, implementing partners for the Linking Agribusiness and Nutrition programme. DFID advertised availability of this vehicle across the office and selection of the benefitting programme was based on VFM criteria. .The remainder of the assets ( mainly computers and other IT equipment) were transferred to FSDMoc, DIALOGO grantees and other public institutions.

Branding: Not all assets and materials procured with DFID funds were branded with the UK Aid logo in accordance with DFID guidance and policy. However DFID worked with DAI to improve branding on operational and public communications or events during the course of the Project.
G: CONDITIONALITY (½ page)

Partnership principles assessment

The Partnership Principles Assessment was not used in the monitoring and management of this programme. The delivery mechanism for this Project is through a Service Provider and civil society and has a lower degree of proximity to government.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

A Mid-Term Review (MTR) was conducted by IDS at the end of 2015 and was finalised early 2016. Some of the main recommendations included the need for DIÁLOGO to achieve broader impact, consolidate its gains in the five municipalities, as well as to refine its approach to sustainability. In order to respond to those recommendations, DIÁLOGO extended the programme to December 2017 in which learning took a central place.

A Final Evaluation was contracted out by DAI and led by IDS and is being finalised. Its draft findings on each of the key elements of DIALOGO Theory of Change (Civic Engagement, Municipal Engagement and Media Strengthening and Engagement) are reported in the first section of this PCR. The FE confirms that DIÁLOGO has contributed to improving municipal governance in five of Mozambique’s most important cities – very significantly in some, more marginally in others – and made a useful albeit relatively minor contribution to the development of an enabling environment for more participatory, transparent and effective local governance in the country as a whole.

A Ripple Effect Study was also finalised and reports on the impact at the organisational, neighbourhood, municipal and national levels of the Programme.

Monitoring progress throughout the programme

Robust programme monitoring was enabled through routine reporting from, and meetings with, the PMU.
The PMU reports on progress every quarter to DFID by providing a narrative report which is discussed at quarterly management meetings with DAI, DFID and COWI. DFID SRO and DFID Programme Manager chair and attend all quarterly meetings with DIALOGO to monitor progress and regularly follow up on recommendations from Annual Reviews. Minutes and actions points are agreed at the meetings and followed up in the following meeting to ensure progress on agreed actions. An Annual Report was submitted covering March 2016 to February 2017 and the more recent Final DIALOGO Report covering the last year and entire life of the Programme.

Individual recommendations from the 2016 AR were monitored through close level engagement with a dedicated staff from DAI and the PMU.

The PCR builds on the April 2017 Annual Review, field visit to Nampula in February, and recent field visit in Maputo in October 2017. Meetings were held with six down streem partners and beneficiaries which included; Parlamento juverul, Livaningo, ECAM, Horizonte Azul-Girls and Radio Voz Coop. The meetings helped to generate beneficiary feedback that was triangulated with the reports from DAI, the main implementing partner submitted to DFID. Beneficiary feedback showed that the programme had led to significant positive changes especially in capacity building of youth groups to demand for their rights. One example that was presented was on primary school infrastructure refurbrishment that happened as a result of the youth demand for better education infrustructure. Due to youth empowerment by the programme, the youth were granted better education facilities which was construction at the time of the visit. There were many stories of change as a result of programme support for more citizen engagement in democratic activities.

The PCR Review mission team also discussed with DAI and the PMU to finalise additional inputs to this PCR and conducted a desk-based review of all key documents (such as the DIALOGO Final Report, Vfm Strategy, IDS draft Final Evaluation, IDS Ripple Effect Study). The PCR was conducted during November to December 2017 by a core team of DFID staff including the SRO for this Programme (Governance Adviser), another Governance Adviser, an Economist, a Programme Manager and Programme Officer from DFID Mozambique. Other DFID staff attended the learning session that was organised on 7 December for donors and DFID.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process