 Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Family Planning Outreach II
Programme Value: £22,030,000		Review Date: January/February 2017
Programme Code: 204266	Start Date: November 2014	End Date: December 2018

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A+	A
Risk Rating	Medium	Low/Medium	Moderate

Summary of progress and lessons learnt since last review
This programme has completed its second year and is meeting expectations and the family planning and training outputs have exceeded expectations. However, while Comprehensive Post-abortion Care (CPAC) and Gender-based Violence (GBV) training has taken place, the numbers of these services provided are below milestone levels, particularly for GBV. This is new and challenging work for both Implementing Partners and involves close work with the public sector; also, both CPAC and GBV are highly stigmatised services.

The findings of the Tanzania Demographic and Health Survey 2015-16 (TDHS 2015-16) show only a limited increase in contraceptive use. The survey showed that use of modern contraception among married women has increased to 32%, up from TDHS 2010 where the contraceptive prevalence for modern methods (mCPR) was 27%. The use of traditional methods (an indication of a lack of knowledge of family planning) remained relatively stable at 6%, down from 7%. There was an encouraging finding, however, in the changing contraceptive method mix. The use of implants increased from less than 1% in 2004-5 to 7% in 2015-16. As this programme is a key provider of implants, this change can be attributed largely to this initiative.

Two FP outreach models continue to complement one another. Marie Stopes Tanzania (MST) has 24 outreach teams (including four Zanzibar 3-wheeler, ‘tuk-tuk’-type taxis, called ‘bajajis’) and continues to use an outreach model whereby outreach teams snake through rural areas and offer services in government dispensaries and health centres. This model has the flexibility to go anywhere and reach the most remote areas. The Population Services International (PSI) model, in contrast, is more static and uses a ‘hub and spokes’ model. The hub is a Government of the United Republic of Tanzania (GOURT) health centre where public sector workers have received more intense training in FP, CPAC and GBV. Three to four ‘spoke’ facilities (commonly dispensaries) surround the hub. PSI outreach teams operate in a large area around the hub and spokes unit, offering family planning outreach services in health centres and dispensaries (as arranged with the district reproductive health coordinator). The PSI outreach teams can refer people to the ‘hub’ for CPAC and GBV care. Finally, MST also assists in training public sector providers, in consultation with GoURT. Each model offers distinct advantages and complementing each other for example, PSI does not provide permanent methods of family planning and hence relies on MST to do that in some regions.

PSI has scaled up to full capacity (10 outreach teams). PSI scale up was delayed until June 2016 while waiting for government evaluation and approval for four of their sites. Therefore PSI did well to achieve its targets while also scaling up their services.

Emphasis on youth continues to be successful. Both MST and PSI have surpassed their youth milestones in year 2. A further analysis of both implementing partners is needed to determine how this scale up was achieved.

Comprehensive Post Abortion Care (CPAC) is a critical addition to the FP outreach model. The data show that, while CPAC training is meeting its milestones, the CPAC service provided by the public sector in PSI sites is lagging behind the expected log-frame estimates. This is because publication of the CPAC training guidelines slowed progress in Year 1. In addition, the CPAC services are not yet widely publicised and women are not aware of their availability. There is also evidence of healthcare provider reluctance because of the stigma attached to ‘abortion’ services. Publicising national policy on CPAC, as well as making sure people are aware of this service is needed. This should be the role of the community mobilisers of both implementing partners.

Gender-based Violence (GBV). The programme is behind in delivering these interventions, particularly in the MST sites. While the training has taken place, the numbers of women served or referred has not met expectations. There are many reasons for this. Awareness of GBV issues is growing in Tanzania but women may not be making themselves known to providers as they are reluctant to be identified. This GBV activity (weighted at 10% of the overall project) is a new activity for the implementing partners and should be reassessed during the year ahead to see if the approach should be changed.

Continued collaboration with Government of Tanzania. Collaboration with government continues to be good with excellent collaboration, especially at regional and district levels. At national level, the partners continue to engage with participation in the Family Planning Technical Working Group (FPTWG), Commodities Security Technical Working Group, and collaborating on government guidelines. Engender Health (a USAID-funded IP) is currently the secretariat for the FPTWG and Marie Stopes Tanzania is the secretariat of the Outreach Committee. Meanwhile, PSI is the secretariat for the National Adolescent Reproductive Technical Working Group (ASRH).

Collaboration and learning between and among Implementing Partners (IPs) remains positive. The two implementing partners continue to maintain a healthy collaboration and with positive ‘competition’. MST’s new data collection system (called CLIC) will allow client-centred data collection – a system which PSI has already had long experience of – and MST should learn from PSI the best ways to mine this rich new data source. In turn, PSI will be adding tubal ligation to its method mix in the coming year and must learn everything they can from MST’s long experience in delivering permanent methods in Tanzania. The collaboration within the PSI team with Intrahealth and Restless Development continues to be strong, with good working relationships. Intrahealth has placed two staff members within the PSI offices has resulted in improved working.

Contraceptive commodities. Both implementing partners rely on the government Medical Stores Department (MSD) for the majority of their contraceptive supplies (80-85%). In addition, each implementing partner has access to commodities supplied to them by their mother offices (MSI in consultation with UNFPA) or via other donors. Even these two systems left contraceptive commodity gaps of 10 to 15% in 2016. This gap has been filled by a third mechanism set up by DFID which is a DKT-run contraceptive commodity back-up stock system. DKT has warehouses in different zones and can fill identified commodity gaps quickly. This back-up stock system was set up as a short term measure while government improved it supply chain management. The government and medical stored department have requested that DFID continues this back up mechanisms for at least the next year. One of the major reasons for stock outs in the past were that public facilities were not ordering sufficient commodities in advance of outreach team visits. This has improved significantly as MST and PSI have coordinated more closely with district officials, informing them well in advance of their visits. As a result stock outs have been reduced, but still not removed.

Public sector capacity building leaves sustainable services. Both implementing partners are training public sector providers in long and short-term family methods, CPAC and GBV. Both implementing partners work with, encourage and mentor public sector providers while on outreach visits and this is critically important for the sustainability of this programme. It is essential that this programme must not substitute for any family planning services the public sector is already able to provide. Trained public sector providers complained that they often lacked the equipment (particularly IUD insertion sets and, in some cases, MVA kits) that they need. DFID will continue to advocate with the Government of Tanzania for appropriate budget allocation.

Urban health services are even more crowded than rural ones. While health centres in the rural areas the team visited were very busy, the urban health services visited were overcrowded - packed with women and their babies. Rapid urbanisation in Tanzania has resulted in services being unable to cope with the increased demand. The recent demographic and health survey has shown increased urban fertility and no increase in contraceptive prevalence rates. This programme focusses on rural provision, however it may be appropriate to consider adding urban services in the future DFID work.

Summary of recommendations for the next year

Both Implementing Partners
- Informal mentoring for public health providers, especially in FP counselling and service provision, should continue to be encouraged. Public sector providers should be encouraged to participate in group & private FP counselling sessions.
- Both implementing partners should put an increased emphasis on both dual protection and counselling on side effects in their FP counselling.
- Implementing partners should train sufficient numbers of staff to account for attrition (approximately 150%).
- Implementing partners should continue to collect and then provide data for next year to allow reviewers to comment on differential effectiveness, efficiency or economy between different geographical locations.
- In new budgeting for scale up, ensure adequate numbers of IUD insertion sets in public sector facilities.
- Both implementing partners should remain active members in the Family Planning Technical Working Group.
- Both implementing partners should be trying to reach more young people before those young people have their first child. It is acknowledged that the programme is reaching more young people and it would be helpful for the IPs to review and write up their methods used so that others can learn.

MST
- MST needs to carefully keep track of what interventions to reach youth are the most effective and document results in the next Annual Report (including cost breakdowns).
- MST should continue its provider-initiated HIV Counselling and Testing (HTC) for all clients.

PSI
- Continue CPAC training in all spokes facilities.
- As PSI adds tubal ligation to its method mix, they should work with MST to understand its tubal ligation protocols, experience, and lessons learned.
- Ensure that spokes are referring women to the hubs where the trained providers are (as much as possible).
- There needs to be attention put into analysing the Restless Development youth voucher scheme in order to understand its patterns and what drives it.
- PSI needs to use Provider-initiated HIV testing and counselling in its outreach services (as MST is already doing) or it is a serious missed opportunity. Lack of HIV test kits is an obstacle so provision for these must be included in the DFID scale-up budget.
- PSI should continue to train providers in both MVA and medical CPAC.
- PSI should ensure that Restless Development have in place transport to enable them to supervise staff in remote areas.

DFID
- In future projects, consider working on GBV prevention at the community level either as another component or a larger separate programme, given the complexities. Multiple partners will be required in order to meet the varied needs of the survivors.
- Maintain a back-up commodities supply system for at least the next year, however with explicit plans for exit.
- Consider reaching urban as well as rural women in future FP work.
- DFID needs to consult with its fellow donors about an upcoming condom shortage in Tanzania.
- DFID needs to monitor other development partner plans over the coming year, most notably the US with their change in policies in relation to sexual reproductive health and rights and possible changes in funding.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204266
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204266/documents

Outline of the programme

DFID Tanzania is implementing Phase II of a Family Planning outreach programme over 4 years (2014-2018) to increase family planning use in Tanzania. (Phase I covered 2011-2015.) The outcome of the programme will be to increase women's use of family planning and availability of comprehensive post abortion care (CPAC) services across Tanzania. The impact will be to reduce maternal mortality and improve women's lives by giving them control over their family formation.
Specific outputs are as follows:
- Private sector family planning outreach services to rural areas (particularly long-acting and permanent methods-LAPM) in consultation with Government public sector services;
- Strengthened national comprehensive post abortion care (CPAC) in both public and private sectors (including policy work);
- GoURT supported to strengthen its family planning programme, including training of public sector providers in LAPM;
- Young people (<20) reached with family planning and CPAC; and
- Integrated RH services for women who are victims of violence (GBV) work in the public or private sectors.
The TDHS 2015-6 showed that fertility is coming down only very slowly. The total fertility rate (which can be interpreted as a snapshot of average family size) reduced from only 5.4 in 2010 to 5.2 in TDHS 2015-16. Trends in fertility by urban/rural residence show that urban TFR has actually increased from 3.2 in 1999 up to 3.8 in 2016. The review team saw evidence in its urban clinic visits that urban facilities appeared unable to cope to this influx.

Figure 1. Fertility trends, by residence.

Source: Tanzania, Demographic and Health Surveys, 1991-2016.

The DHS 2015-16 showed that adolescent pregnancy was actually increasing in Tanzania (after a decrease in 2010). Teenage pregnancy is now higher than in 2004-5. While this programme has shown good success with reaching young people, addressing youth remains a challenge throughout Tanzania and this programme will ensure that this underserved group are able to access services. This will be an area that continues to require testing and learning, ensuring that youth preferences are taken into account in designing accessible family planning services for them.

This programme has just completed its second year of Phase II of DFID-supported family planning outreach. The programme was bid in two lots and Marie Stopes Tanzania (MST) won one lot while PSI, in collaboration with Intrahealth and Restless Development, won the other. MST has 24 outreach teams and PSI (and its subcontractors) has 10. All programme activities are carried out in collaboration and coordination with the Government of Tanzania. MST and PSI were contracted in December 2014 and January 2015 respectively and MST continued seamless services between the two phases of this programme. PSI started with four new teams for year one, using their new model; since this was deemed a success, they scaled up to ten teams this past year (2016).

Description of each model:

MST’s outreach model involves 20 five-person outreach teams ‘snaking’ through the countryside to continually different public sector health facilities, including dispensaries. (There are four additional 2-person teams run out of tuk-tuks.) Teams include MST staff (2 MST nurses and a driver as well as a MST tubal-ligation surgeon) and a public sector nurse, appointed by the District Medical Officer. In a few cases, the MST outreach teams use a public sector LGA tubal ligation surgeon instead of an MST employee. MST returns to each facility only about every five to six months. In addition, MST has been training public sector providers using the government FP, CPAC and GBV curricula.

PSI’s outreach model is a public sector hub and spoke model and is more static than the model of MST. The hub and spoke facilities have considerable training in FP, CPAC, and GBV. PSI outreach teams operate out of PSI offices in a large area surrounding each hub and include one PSI healthcare provider and one public sector nurse (recommended by the District Reproductive and Child Health Coordinator). The outreach teams go to rural areas surrounding their corresponding hub and spoke and refer more complicated cases to these. PSI began with four teams in the first year and scaled up to 10 teams in Year 2, somewhat later than initially planned.

It is not expected that one model will necessarily be seen as superior to the other. Each model works best in the areas in which the implementing partners are working and each model has its strengths and weaknesses as shown in the following table.

Table 1. Strengths and Weakness of the MST and PSI models
	Strengths	Weaknesses
MST model	Full method mix including sterilization / Reaches large numbers of women with unmet need / Reaches many facilities in remote areas / Also provides HIV testing & counselling (HTC) / One organization with no subcontractors means single organisation coordination / Able to refresh the training of public sector workers / Refers GBV survivors to strengthened public services	Less time at facilities leaves less time to build capacity and supervise public sector trained workers. This compromises the sustainability of this model / Only able to refer to regular public sector facilities (which may or may not have had additional training) / Harder to follow up post- operative problems if they were to occur / CPAC excluded from outreach / Risk of overuse of facility commodities, if District Pharmacist does not receive notice of visits and act to allow appropriate stock accumulation (although this has improved in 2016)
PSI model	In-depth work in fewer facilities / Better training supervision / Additional partners for new work brings new ideas (CPAC, training & youth) / Static model is able to refer to trained & strengthened public sector services / Leaves sustainable and well trained public sector providers and facilities at end of project / Allows for GBV referral to hubs and makes patient follow-up easier	Does not currently include sterilization or HIV Testing and counselling in outreach services (although they do refer clients) so does not provide a full method mix (this will change next year) / Reaches fewer facilities / CPAC excluded from outreach
Both	Incorporates public sector healthcare providers on its outreach teams / On-the-job training of public sector staff / Have a misoprostol product sold in pharmacies / Offer training in FP to public sector providers / Maintains strong relationships with Government of Tanzania	Could mean that public sector facilities ‘wait’ for the outreach team to arrive, and therefore are not incentivized to train providers in the full range of family planning services.

Further detail on differences between models is given in the Value for Money section, below.

Background. Phase I (2011-2014) had just one provider, Marie Stopes Tanzania, delivering family planning outreach services only, nationwide over 3.5 years. Funds were channelled through USAID to provide programme management and technical expertise. Phase II includes CPAC and GBV as additional services, with an increased focus on youth as well as capacity building of public providers. Two suppliers – MST and PSI – have been contracted to provide services in the interest of sustaining a competitive market and fostering innovation and challenge.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Table 2. Estimated Couple Years of Protection (CYPs), Year 2

	Logframe (net)	Actuals (gross)	Actuals adjusted for late scale-up (gross)	Actuals (net)	% of LF
Programme	1,102,565	1,270,989	1,337,929	1,102,843	100.03%

The estimated CYPs delivered by the programme were very slightly ahead of the logframe outcome milestone. Several adjustments were made to the CYPs reported by the implementing partners. First, the conversion of service delivery volumes to CYPs was undertaken. The CYPs were slightly different to those presented by the implementing partners, reflecting Sub-Saharan African, rather than global figures. In addition, evidence of factors such as discontinuation rates, was taken into consideration. Second, an additional adjustment was made to allow for the fact that PSI only received clearance to scale up several months after had been planned in the log-frame. Finally, the CYPs generated by the implementing partners were converted from ‘gross’ to a ‘net’ basis by accounting for inputs not paid for by the programme, mainly those commodities that are paid for under other programmes and received free of charge by these implementing partners.

Table 3. Proportion of clients who are new adopters of FP, Year 2

	Year 2
Logframe	38.0%
Actuals reported	47.0%

Once again, the implementing partners reported a greater share of new FP adopters than their milestone[1].
[1] Note that DFID’s Africa Division in the UK is currently consulting IPs about setting a new definition of ‘additional FP users’.

Overall output score and description: A

Key lessons

PSI has successfully scaled up to ten outreach teams, as well as managing to deliver most of its milestones. The hub and spoke model would appear to be working.

PSI was requested by the Government of Tanzania to concentrate its hub and spokes in one district within a region and this ‘saturation’ model would seem to be successful, despite initial PSI doubts. PSI can see that the district concentration makes the programme easier to supervise, more inspirational with adequate coverage, and encourages greater district ownership. However, this model does mean that there are several districts within the regions that are currently left unserved.

Both MST’s and PSI’s work is even more effective with its closer working with the government health system at all levels. Both implementing partners are working with the government to deliver joint provider supervision, to provide better government health data (DHIS-2), and to aid facilities in improving their commodity ordering. PSI is also developing joint annual work plans with the Ministry of Health assisting facilities with commodity forecasting, and carrying out joint supportive supervision.

Reaching youth continues to be possible and continues to be encouraging. Both implementing partners are using innovative models.

The review team have also found that both implementing partners outreach models demonstrate good VFM.

Key actions

Continue back-up stock until the end of the programme and continue to encourage implementing partner planning with districts to ensure adequate commodities are in the district facilities on the arrival of the outreach teams, as well as on their exit.

Has the logframe been updated since the last review? Yes

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	FAMILY PLANNING. Private sector family planning outreach services to rural areas (particularly LAPM) in consultation with Government public sector services
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of FP services delivered by the project (Long Term & Short Term methods, disaggregated by age)	MST: 217,095 / PSI: 165,182	MST: 295,036 / PSI: 149,607
1.2 Proportion of clients classified as poor	MST: 62% / PSI: 64%	MST: 73% / PSI: 63%
1.3 Cost per CYP (efficiency)	MST: £4.80 / PSI: £7.24	MST: £4.89 / PSI: £4.42
1.4 Client satisfaction with the service they received (PSI: would you recommend a friend?)	MST: 90% / PSI: 99%	MST: 99% / PSI: 99.6%

Key Points

Urban health services even more crowded than rural ones. The health centres in the rural areas the team visited were very busy. The urban health services visited by the review team were absolutely packed with women and their babies. This programme focusses on rural delivery and DFID will consider including urban areas in future work.

DFID should be monitoring USAID’s family planning plans. Given the new US administration’s changes in policy relating to sexual and reproductive health, it is possible that there may be changes to funding of these services. In collaboration with the Government of Tanzania, DFID will monitor the situation for possible gaps in service delivery.

MSI and PSI must have in place mechanisms to ensure that there is adequate family planning counselling with all clients. This must include side effects, dual protection and informed choice. It is encouraging to see the large number of women coming for family planning services. There are risks that with large numbers and long queues that service providers may dedicate insufficient time on discussing on side effects and ensuring that women have sufficient information to make informed choice. This is particularly important for long acting and permanent methods. In addition, dual protection is critical for Tanzania with a  HIV prevalence of 4.7% (UNAIDS, 2015) among people aged 15-49. For women who opt for a hormonal method (slightly increasing their HIV risks), should have a full understanding of the importance of dual protection and, ideally, leave with condoms as well. DFID expects to see MSI and PSI report on how they have been monitoring this.

PSI to add tubal ligation to its outreach method mix next year. Offering the full range of contraceptive options—including permanent methods—is an ideal family planning programme. Up until now, PSI has not offered tubal ligation as part of its method mix. This will change in the coming year. PSI needs to learn everything it can from MST in offering this operation in more challenging outreach situations. PSI clinical staff should meet with MST clinical staff and study protocols and discuss challenges. MST has been offering tubal ligation on outreach successfully for many years, with low complication rates. It should be noted that tubal ligation has higher risks than any other method.

Access to equipment limits service delivery. As discussed in last year’s annual review, limited numbers of IUCD insertion sets for teams limits the rate at which services can be offered as time is required for sterilisation between clients. There was also evidence of Government facilities having incomplete and/or inadequate numbers of IUCD sets and this needed to be addressed. Budget for these inexpensive sets needs to be built into future budgets.

Supervision of Community-based mobilisers. Community based mobilisers are now managed by the Government Liaison Officer along with the outreach team leaders and the district reproductive and child health coordinator. Better and closer supervision of these mobilisers is happening under this programme. 60% of these mobilisers under 25, and provide opportunities to increase youth participation. Messages should be tailored to young people and their work should include making sure people are aware of CPAC, GBV as well as family planning services.

Clinical quality must remain high. MST and PSI must have mechanisms in place to monitor clinical quality and report of this in each annual review.

Client flow in busy outreach sites needs addressing. There could be more attention paid by the outreach teams to the client flow. While the review team appreciates that every outreach situation is different, ensuring that women know where to go and always move in the same directions keeps the process smoother. Some of the women were given numbers in some of the outreach sites—a good idea to ensure a smooth system.

Efficiency is strong, as measured by cost per CYP. MST achieved close to its milestone and PSI’s cost per CYP was well below its milestone, as it adjusted to full roll out of services more easily than expected.

National Guidelines for Family Planning Outreach Service. National guidelines for family planning have been developed and disseminated across the country by MST, setting service standards, reporting, and management of clinical incidents.

The Family Planning Outreach Technical Working Group needs to remain strong. A recent Government reshuffle has meant that the previous family planning head has moved elsewhere and been replaced by new staff. There is need for developing continued commitment to sexual and reproductive health. Engender Health is currently the Secretariat but the Family Planning Outreach Technical Working Group is run by the Ministry of Health.

Collaboration at regional and district level is good and continues to show improvement. The review team saw good cooperation and appreciation at the regional and district level for the support of both MST and PSI

Commodity planning at district level improved since last year. The review team heard of no instance where the implementing partners left a facility without contraceptives after an outreach visit. Continued good planning is required. Both implementing partners are working within districts to build capacity in family planning commodity quantification and ordering.

Reliance on outreach services. There is still some evidence that women are put off by overworked public sector providers and asked to wait for the outreach services. This is concerning and should be an issue that is discussed with district and regional governments by the implementing partners.

Implementing Partners continue to rely on DKT back-up stocks about 10-15% of the time, implying that the back-up is still needed. Both implementing partners rely on the government’s Medical Stores Department (MSD) for the majority of their contraceptive supplies. In addition, each implementing partner has access to commodities supplied to them by their mother offices (MSI in consultation with UNFPA) or via other donors. Even these two systems left contraceptive commodity gaps of 10 to 15%. This gap has been filled by a third mechanism set up by DFID which is a DKT-run contraceptive commodity back-up stock system. DKT has warehouses in all zones of Tanzania and can supply any identified commodity gaps very quickly. Ideally, this back-up stock system should be phased out as quickly as possible. However, for at least the next 1 to 2 years, government has requested that this continues. .

Condom shortage in Tanzania. There is a possible serious condom shortage in Tanzania in the coming year as donor priorities change. This needs to be discussed by government and partners given condoms importance in HIV prevention.

HIV Testing and Counselling needs to be offered by PSI. PSI needs to deliver Provider Initiated Testing and Counselling services (as MST is already doing). This is particularly important for young people. Adequate HIV test kits must be sourced and available, ideally from public facilities to ensure sustainability. This is part of the integration services included in the National Guidelines for Outreach Services.

Incident management, in consultation with the Districts, is improving. Clinical complications must be treated quickly and at local level, requiring team work between the public and private sectors. MST managed three clinical incidents well in 2016.

District Health Information System (DHIS-2) data continues to need improvement. Many gaps in data quality continue to be observed. MST has been comparing this data with their own service statistics and finding many discrepancies. Currently, implementing partners are holding ‘data summits’ where they look at the data together with the Government and see where the gaps are. As a result, key government officials are beginning to pay more attention to these issues at regional level.

Access to DHIS-2 data. Implementing Partners still need to obtain the DHIS-2 passwords. They have however been able to use this data, but it would be better if they were granted access to the passwords.

MST Clients Information Centre (CLIC). By the end of the second year, 19 MST teams were routinely using the CLIC system. In the next year, all teams will be moved to CLIC. PSI already has client-centred data collection.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- MSI and PSI must have mechanisms to ensure that all family planning consultations include adequate counselling including on side effects and dual protection.
- Informal mentoring for public health providers, especially in FP counselling and service provision should continue to be encouraged. Public sector providers should be encouraged to participate in group & private FP counselling sessions.
- Adequate numbers of IUCD insertion sets should be available in public sector facilities.
- Implementing partners should take into consideration staff attrition when training staff.
- Implementing partners should continue to provide data to allow evaluators to comment on differential effectiveness, efficiency or economy between different geographical locations.
- PSI needs to use Provider-initiated HIV testing and counselling.
- As PSI adds tubal ligation to its method mix, they should work with MST to understand its tubal ligation protocols, experience, and lessons learned.
- Both implementing partners should remain active members in the Family Planning Technical Working Group.
- DFID needs to consider maintaining a back-up commodities system to ensure no family planning stock out.
DFID needs to consult with government and other donors about an upcoming condom shortage in Tanzania.
DFID needs to monitor implications of changes in US policy on family planning services in Tanzania.

Output Title	CPAC. Strengthened national comprehensive post abortion care (CPAC) in both public and private sector (including policy work)
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of facilities (public and private clinics) equipped and supplied to deliver CPAC	MST: 120 / PSI: 120	MST: 122 / PSI: 392
2.2. Number of public and private health workers trained and certified (at least 80% of those trained) in CPAC using MVA (80% of these will be public sector providers and will include government certification)	MST: 190 / PSI: 50	MST: 194 / PSI: 50
2.3 Number of women accessing safe post abortion care (through this programme of support)	MST: 4,517 / PSI: 3266	MST: 4,941 / PSI: 1,779[2]
[2] This lower figure is because of the delayed CPAC training in hubs and spokes.

Key Points

CPAC services are still low in the public sector facilities where training has taken place. Women are not yet aware that CPAC is available in public sector facilities. Numbers should increase as PSI completes its training in its ‘spokes’. Another reason might be that the PSI untrained spokes staff members are referring women to closer hospitals that are not the ‘hub’. This might be because of overcrowding or because the other hospitals are actually nearer and more convenient for the women.

CPAC awareness needs to be raised by community based mobilisers and outreach teams. CPAC is a new service to be offered in the public sector facilities and many women do not know that it is now available in facilities where training and equipping has taken place.

CPAC training is beginning in PSI spokes. It was recommended in last year’s Annual Review to carry out CPAC training in the PSI spoke facilities. This training has begun and will continue into Year 3 and should increase service numbers.

CPAC attribution is likely to be a problem as there are many partners training providers. Implementing partners should avoid training in CPAC where other development partners may be providing this training.

CPAC has high stigma for both providers and users of the service. MST carried out a CPAC baseline needs assessment in Year 2. The assessment showed that many facilities lacked trained staff and equipment to carry out CPAC. In addition, many healthcare providers indicated that they were ‘uncomfortable’ delivering the CPAC service citing ‘widespread stigma and negative attitude’ on CPAC. MSI and PSI are already using Values Clarification in their CPAC training, improving provider attitude--and this should continue.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- Continue CPAC training in all PSI spokes.
- PSI needs to ensure that spokes are referring women as much as possible to the hubs (where the trained providers are).

Output Title	TRAINING. GoURT supported to strengthen its family planning programme, including training of public sector providers
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of GoURT healthcare providers trained LAPM/LARCS and certified (with supervision)	MST: 200 / PSI: 174	MST: 283 / PSI: 175
3.2 Total number of women accessing FP services in public facilities (derived from aggregation of district data)	MST: 900,000 / PSI: 110,080	MST: 2,613,275 / PSI: 120,708
3.3 Average QTA score for project teams	MST: 90% / PSI: 90%	MST: 87% internal; 91% (external) / PSI: 94%
3.4 All clinical incidents properly investigated and clearly communicated to all levels of Government in a timely fashion (within three days)	MST: Yes or no / PSI: Yes or no	MST: Yes - Achieved / PSI: Yes – None

Key Points

Both MST and PSI have met or exceeded their Long acting and permanent methods of family planning raining requirements. Training public sector providers is a critical piece of this programme’s sustainability strategy. As private sector family planning outreach is not sustainable, it is key that long-lasting family planning skills are left in the public sector.

Ministry of Health have finalised certificates to trained public sector providers. The certificates have been distributed by PSI and MST was about to distribute their certificates.

Training Tracker is functioning well and training organisations are keeping it up to date. Training Tracker is a database that includes healthcare providers training records and it is maintained by the Clinton Health Access Initiative.

In the future DFID work, attrition should be factored into training plans and budgets. This will mean training 30 to 50% additional staff.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Output Title	YOUTH. Young people (<20) reached with family planning (likely to be ST methods) including CPAC and SGBV
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Proportion of all family planning services to clients aged under 20 through the outreach teams [also PSI data on youth attending the hubs]	MST: 7% / PSI: 8%	MST: 11% / PSI: 9%
4.2 Number of (public and private) programme staff specifically trained to work with or provide information, education, or family planning services to adolescents under 20 (no certification)	MST: 20 (Milestone for Year 2 completed in Year 1) / PSI: 18	MST: Completed / PSI: 35 (24 peer educators; 5 Restless Staff; & 6 youth promoters)

Key Points

MST surpassed its youth milestones comfortably and PSI also slightly exceeded their milestone. This represents a real achievement for both implementing partners. Further work will be needed to reach 2018 targets.

MST is using a variety of interventions to reach youth. These interventions include a Two-Day Outreach (whereby team members remain to meet youth on Day 2), specific outreach events aimed at youth, youth events and ‘bonanzas’, and reaching vocational institutions. It is clear that MST are improving at reaching youth given that 11% of MST users are under the age of 20. The MST 2016 Annual Report, however, does not yet give a sense of what methods might be the most effective, nor of different sorts of challenges in reaching rural versus urban youth. Some additional analysis is needed, especially since a level of at least 12% is expected in 2018. Also, youth groups should be given a different message in a different way to adult women. All providers should be prepared with a youth message.

Restless Development reaching in school and out-of-school youth in different ways. The review team observed the real differences between reaching young people who are still in school and those that have left. While this is a challenge, running these different programmes is an example of good practice.

Comprehensive Sexual and Reproductive Health Education. In the work of Restless Development, the youth commented on the need for better sexual and reproductive health information in schools. This is something that not currently government policy and is being followed up in other DFID education programmes.

Restless Development voucher scheme. Young people reached by Restless Development peer educators are given vouchers that they turn in at health centres when they go for services. 5411 vouchers have been redeemed in hubs from young people in the surrounding regions, close to Restless Development’s projection from last year. Restless Development records show that 88% of the vouchers given out were redeemed – meaning a highly successful intervention. The review team noted that many young people came for HIV counselling and testing rather than family planning. While coming for HIV counselling and testing is positive, staff must use the opportunity to educate the young people on their family planning options too. Also, these referrals change from quarter to quarter and it would be helpful to know what drives these changes.

MST remains a leader in the MSI partnership in reaching youth. This makes the need for analysing just how they are being successful at reaching youth all the more important, as their experience can probably be rolled out more easily throughout the international MSI network.

What services do young people use? Restless Development report that 87% of the vouchers were redeemed by young people. For those who came for family planning services, mainly opted for injectables, condoms, and some for implants. Young people are much less likely to present for either CPAC or GBV services, despite data showing their need for these services. Finally, Restless Development reports that many young people are also accessing the private sector. Interestingly, MST reports a significantly higher share of its young clients using long-acting reversible contraception than does Restless Development, e.g. 76% of under 15s, 81% of 15-19s. Additional analysis is given in the Value for Money section, below.

How much does it cost to reach youth? Reaching youth is important, and this review has shown the unit costs are decreasing from previous years (see value for money sector). Reaching a young woman at the beginning of her reproductive career is more likely to lead to continued practice of family planning throughout her life.

Family planning myth that women will be infertile if they use family planning before having a child. The review team heard a myth a number of times, that young people believe that family planning before a first birth will yield the woman infertile. This myth needs to be counteracted with facts and awareness raised by both implementing partners.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- MST needs to analyse its methods of reaching youth and give DFID a sense of what is working best and where (including cost breakdowns).
- Both implementing partners should be trying to reach more young people before those young people have their first child.
- PSI should ensure that Restless Development have in place transport to enable them to supervise staff in remote areas.
- There needs to be more analysis of the Restless Development voucher redemption to determine why there are peaks and troughs across the year.

Output Title	GBV. Integrated Reproductive Health services for women who are victims of violence (GBV) in the public or private sectors
Output number per LF		5	Output Score	C
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Number of survivors receiving post GBV care services	MST: 11,519 / PSI: 5415	MST: 1504 / PSI: 5883
5.2 Number of public (80%) and private providers trained with good competency assessed in trainee follow-up	MST: 117 / PSI: 92	MST: 122 / PSI: 54[3]
5.3 Number of survivors referred for clinical and non-clinical services	MST: 5760 / PSI: 1624	MST: 483 / PSI: 2032
[3] PSI delayed training while waiting for GOURT approval to expand its services. PSI plans to complete the training for the remaining 38 providers in the first quarter of 2017.

Key Points

Gender-based Violence (GBV). The programme (particularly MST) is substantially behind its logframe milestones in delivering these interventions. While the training has taken place, the numbers of women served or referred has not met expectations. There are many reasons for this that might or might not be the responsibility of the IPs. Awareness of GBV issues is growing in Tanzania but women may not be making themselves known to providers in their actual numbers as they are reluctant to be identified. This GBV activity (weighted at 10% of the overall project) is a new activity for the implementing partners and should be reassessed during the year ahead to see if the approach should be changed.

Women who are GBV survivors must self-identify and there is little awareness. There is low awareness of service availability after victimisation. Most women wait at least two days before reporting to health centres. Government response is still lacking in most areas.

GBV prevention in the community is not built into this programme. The programme screens for survivors and treats them and/or refers them on to other services. Government and partners should consider more work on prevention of GBV.

GBV survivors are more likely to be complex cases. GBV survivors are more likely to have multiple issues including unintended pregnancies and sexually-transmitted infections including HIV. For example, evidence has shown that abortion rates are twice as high for women who have experienced partner violence (Population Reference Bureau, 2015). Implementing partners therefore need to factor this into their work load as these clients are likely to require more time and effort.

Healthcare providers need care and consideration. A healthcare provider might need to appear in court within their communities and even testify against someone known to them. This can be very challenging. In addition, there is difficulty in caring continually for survivors and provision such as Caring for Carers should be built into any GBV work. This usually involves teaming up existing staff and need not be expensive.

MST and PSI continue to link GBV survivors to government services— however there is limited availability of these services. MST has a Government Liaison officer who links survivors with local Government services. This person researches the most appropriate and closest government service available. PSI reports a limited number of social welfare officers; in addition, these officers are housed in district council offices, making access for many women difficult. This will need to be taken into consideration in future programmes.

PSI continues to refer GBV cases to the trained provider at the hub. Public sector healthcare staff members in spokes are given the short version of the GBV training so that they can screen, treat and refer the more difficult cases to the hub. In the hub, the GBV provider has received the longer version of the GBV curriculum and can work with the more complex cases.

GBV survivors are charged for their health services in public sector facilities. There was little progress to report.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
Providing GBV services is complex, and more prevention is needed. Government together with development partners need to consider further prevention work at the community level.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
As part of the first Annual Review it was agreed that IPs should place their data in a common format for ease of analysis and comparison:

Table 4. Cost categories

	Cost category	Description
1	Own labour costs	Salaries and per diems for IP operational staff
2	Transport costs	Fuel and maintenance for vehicles
3	MoHSW costs	Per diems for MoHSW staff, and person-day data for application of salary cost
4	Commodity costs	Service delivery data for application of commodity procurement, storage and distribution costs
5	Support costs	Estimates of support provided by both local and international offices of the IPs
6	Other costs	Any other costs related to the FP outreach

IP cost data availability has improved, yielding the following representations:

Figure 1: Cost drivers, based on MST cost data, Year 2

Figure 2: Cost drivers, based on PSI cost data, Year 2

The data still provides a good guide for DFID as to where outreach costs lie. As with most health sector activities, labour costs are the key driver, dwarfing transport costs. ‘Assumed commodity’ costs – i.e. the cost of commodities used that are not borne by the programme – are also a major contributor, and not one that is visible in IP accounts. The slightly smaller ‘assumed MoH outreach’ is separate from MoH staff per diems (paid by IPs) and represents the salary cost to MoHSW of their staff who are working in outreach teams – which again is not visible in IP accounts and has been estimated. Costs to clients, such as transport and any foregone income, have not been included, but recent evidence[4] suggests that these are minimal.
[4] E.g. in the recent Annual Review of DFID’s multi-country PMDUP SRH programme.
Value for Money indicators, and their ex-ante (i.e. Business Case and Inception Report forecasted) values. The following table shows key selected VfM indicators for each IP and, with their values in the initial Business Case and Inception Report respectively in brackets, for the programme as a whole:

Table 5: Estimates of VfM indicators for FP outreach, Year 2
	MST	PSI	Programme
Effectiveness
cost/DALY	£5.32	£4.76	£5.20 (£10.81; £5.21)
cost/maternal death averted	£4,658	£4,133	£4,546(£9.435; £4,548)
cost/unwanted pregnancy averted	£11.79	£10.53	£11.52 (£24.01; £11.57)
Efficiency
Cost per CYP	£4.89	£ 4.80	£4.79 (£5.01; £4.80)
Services delivered/team/year	12,293	18,701	13,895
Economy
Cost/team/year	£204,464	£148,032	£190,356

. Note: PSI and programme actuals both exclude costs and benefits of Restless Development and Intrahealth.

All indicators suggest that the programme offers good value for money, and are comparable to results in FP outreach in other Sub-Saharan African countries. This is not unexpected, as the Long Acting and Permanent Methods provision which is at the heart of the programme is an inherently cost-effective intervention, offering many years of protection from a range of costly and unhealthy outcomes (e.g. unwanted or risky births) at a modest cost. Note that the marked difference in the effectiveness measures from the Business Case is due the modelling approach of the Business Case which looked only at impacts during the programme years (and not at the protection of long term methods to women in the years immediately after the programme ceases). The significant differences apparent between PSI and MST results in Year 1 - which were due to PSI’s start-up costs - are now gone.

There was no specific value for money indicators to cover the programme’s training activity. Such indicators can be challenging because training quality is hard to gauge and because the Government of Tanzania has a major influence over training costs. At present, only limited data has been gathered from implementing partners on differential effectiveness, efficiency or economy between different geographical locations, particular differential cost data (i.e. how much is spent on teams in different localities), though it is recommended that the IPs provide this next year. MST’s SUN accounting system, for example, is already in place to provide cost data per outreach team.

Model testing: MST v PSI. One of the objectives of the current programme is to compare the two implementing partners’ family planning outreach models. While this is useful for DFID (and for the Implementing partners), it should also be recognized that the two models are to a large extent complementary. MST’s model is better designed to reach rural facilities, far from a facility functioning well enough to serve as a hub. PSI’s model is better designed to engage intensively with an MoH hub facility, exerting a more positive capacity building influence. With that proviso, both are compared over 2016. Note that the service delivery numbers are somewhat deceptive because PSI usually provides condoms with a second family planning method (dual protection) to each client, but the standardised family planning analytic approach records each method supplied as a separate service delivery. Dual protection is not standard practice with MST. The other ratios indicate more realistic differences between the two models. MST’s teams are more effective in delivering Long acting reversible contraceptives as well as permanent methods (and hence CYPs); but PSI teams reach more under-20s. MST records a higher share of its services going to under-20s, because of the ‘double’ service delivery aspect of PSI referred to above creating a higher denominator.

Table 6: Comparative team/year data, Year 2
	MST	PSI
Services delivered/team/year	12,293	18,701*
LARCs per team/year	7,913	5,103
CYPs per team/year	41,801	33,470
Under 20s services/team/year	1,352	1,683

Note: PSI’s results have been adjusted to take account of the later start of their scale up than expected

*This counts each family planning commodity supplied to a woman as a separate service, consistent with standard family planning analysis. But excluding PSI’s dual protection condom provision, the number of services would be half = 9,350.

It was decided at the start of the programme, for convenience, to treat MST’s 20 mainland teams and four Zanzibari tuk-tuk teams equally for analytical purposes. But it should be noted that this is a simplification, as tuk-tuks are not able to serve such large client volumes.

Reaching youth: Restless Development. Delivering sexual and reproductive health services to youth remains a global challenge, suffering from a lack of consensus about what approaches work best as well as a lack of data. Restless Development’s model of informing youth, issuing them with referral vouchers and recording where those vouchers are redeemed, and for which services, seems to be an effective one, and it also generates useful data, which may be of interest outside of Tanzania, as well as within this programme. Analysis of Restless Development’s data, from the start of operations in July 2015 until the end of the 2016, and summarise it in the following table.

Table 7: Restless Development data on youth FP services, 2015-16
	2015-Q3	2015-Q4	2016-Q1	2016-Q2	2016-Q3	2016-Q4	2016
Referrals issued	1427	2041	1441	1747	1956	1012	6156
Referrals redeemed	1065	1612	1126	1585	1764	936	5411
Issue growth		43%	-29%	21%	12%	-48%
Redeem growth		51%	-30%	41%	11%	-47%
Redeem rate	75%	79%	78%	91%	90%	92%	88%

This shows that a large majority of young people (<20 years of age) given referral vouchers do indeed redeem them at Ministry of Health facilities within a short space of time (the ‘redeem rate’). Moreover, this proportion is growing, from 75% in Q2 2015 when the service began to more than 90% in the last quarter of 2016. This shows that the referrals are well-targeted/persuasively provided, and increasingly so. Yet at the same time, the volume of referrals issued is quite volatile, falling strongly in two quarters (Q1 and Q4 of 2016) just as it rose strongly in three others (Q4 of 2015 and Q2 and Q3 of 2016). It would be helpful to know what drives this variation. PSI believe that peer educator drop-out rate explains some of the variation.

Over 2016, 87% of redemptions were for family planning services (up from 56% in 2015). So while there is still some demand for GBV, CPAC and HIV/STI counselling, this initiative is working primarily as FP demand creation, although the review team also observed significant HIV testing and counselling interest.
.
The following table shows estimates of the value for money being delivered by Restless Development:

Table 8. VFM for youth activities, Restless Development
	2015*	2016
Cost per redeemed FP referral	£40.59	£31.98
Cost per CYP	£63.75	£37.76

Last six months only.

As noted in previous review, reaching youth is a significantly higher unit cost that for non-youth. This is because of the effort required to attract and create demand among youth, and secondly because they tend to choose shorter terms methods (such as pills and condoms). However, what is encouraging this year is the reduction is cost per CYP and per service. The positive trend is due to two factors. First, a greater proportion of referrals are for FP; and second there is a shift from condoms and injectables towards implants. This data is rare (few FP programmes are able to report on the cost of reaching youth) and encouraging in its trajectory. With better understanding of volume variations it may be possible to produce even better figures in future. MST should produce youth cost data in future.

Table 9. Method mix: data from MST
Services/Age	10-14	15-19	20-24	25 and over	Total
Contraceptive pills	2(7%)	338(4%)	1,014(4%)	1,897(3%)	3,251(3%)
Emergency contraceptive pills	0(0%)	0(0%)	0(0%)	1(0%)	1(0%)
Female Condom	0(0%)	1(0%)	9(0%)	36(0%)	46(0%)
Implant - 3 years	12(41%)	3,878(42%)	9,309(37%)	14,545(23%)	27,744(28%)
Implant - 5 years	10(35%)	2,557(28%)	7,193(29%)	14,261(22%)	2,4021(24%)
Injectable - 3 month	1(3%)	702(8%)	2,387(10%)	4,576(7%)	7,666(8%)
IUCD - 10 year	0(0%)	1,008(11%)	3,777(15%)	10,166(16%)	14,951(15%)
Male condom	4(14%)	684(8%)	1,550(6%)	4,441(7%)	6,679(7%)
Tubal Ligation	0(0%)	0(0%)	20(0%)	13,902(22%)	13,922(14%)
Vasectomy	0(0%)	0(0%)	0(0%)	29(0%)	29(0%)
Total	29(100%)	9,168(100%)	25,259(100%)	63,854(100%)	98,310(100%)

Interesting MST data show a higher proportion of young clients using longer term methods than with Restless Development. It would be interesting to understand this further, and MST should make this data available at future reviews.

Quality of financial management

Both PSI and MST have robust financial management systems. Since the implementing partners have a number of sources of funding, some for similar activities, DFID have asked them to ensure open-book accounting with financial reports showing the contribution of funds for major line items. Both MST and PSI have been open and cooperative with financial data. DFID will also check audit reports during the life of the programme.

The spend rate of the programme is on track and partners have improved in terms of providing their financial forecasts. They have even been able to provide approximations of what they spend each month.

Both organisations have continued giving stipends to government health providers in their outreach teams and health providers during trainings. For better monitoring and accountability purposes, all these payments are made through mobile money.

Both organisations have whistle blowing policies. During this reporting period, PSI has experienced fraud involving PSI staff. PSI immediately notified DFID and has taken actions to strengthen their financial and programme management, including suspending staff involved in the incident. PSI is currently in the process of refunding the whole amount that was involved in the incident.

Date of last narrative financial report	May 2016
Date of last audited annual statement	May 2016

Date of last narrative financial report	May 2016
Date of last audited annual statement	May 2016

E: RISK (½ page)

Overall risk rating: Moderate

Table 10. Overview of programme risk

RISKS	MITIGATION 2016
Measuring impact. One challenge of the last project has been measuring impact and the on-going changes in measurement models (e.g. the MSI Impact Calculator). This has meant that although the project has been meeting targets in terms of services delivered, the estimates of impact have fallen significantly. It is hoped that the models are now stronger and that this programme will be able to estimate impact accurately from the start. If only the most basic monitoring and evaluation metrics are used (e.g. couple years of protection and pregnancies averted), this would provide no incentive for providers to fully target under-served groups, such as the young and the rural remote, who are more costly to serve.	This risk has largely been managed by the DFID peer review of the MSI Impact Calculator.
Government commitment. There is a risk that government commitment will be reduced, and that there is increasing resentment at the reliance on NGO provision. This in turn can create operational difficulties and blockages for service providers, as well increasing the likelihood that NGO provision will be substituting for, rather than building, government capacity. These risks can be managed somewhat with public sector capacity building by the NGOs. The Government of Tanzania could continue to insist on lengthy training that ideally should be streamlined to increase its efficiency.	This risk continues to pertain although the implementing partners have been working closely with government.
There is much sensitivity around abortion. There is a continuing risk of a political backlash against the scale up of post-abortion care (which remains controversial). Marie Stopes International is experienced in managing the politics surrounding post-abortion care.	Risk remains, with more evidence of high abortion stigma this year in MST’s CPAC Assessment. If anything, Tanzania is becoming more conservative.
Reaching women under 20 years of age. Whilst the feasibility of delivering outreach services has been clearly demonstrated in phase I, most clients are still married women and attempts to increase uptake by adolescents has been slow. Meeting the needs of young and unmarried women remains a huge challenge. Young people do not always want to use long-acting methods as their sex lives may be sporadic and outreach services are not very private.	The implementing partners have done very well this year in reaching more young people. However even more needs to be done, and still too many young girls are only starting family planning after having their first child.
Women who have experienced violence. Approaches for reaching women with sexual and reproductive health services are still being developed and there is much to be learned. It is possible that these women will not come forward or shun offers of service as gender-based violence carries a high stigma.	This risk pertains and is even more pertinent as the programme learns more about GBV.
Sustainability. There is a danger that relying on NGOs for service delivery will result in little improvement of the public sector, which in the long term should be increasingly the responsible for health services. Thus genuinely effective training of public sector staff and initiatives to transfer skills and motivation to the public sector are vital.	Close work with the public sector is an attempt to mitigate this risk.

MST has been carrying out family planning outreach services for many years and their long experience ensures a reasonably reliable programme. PSI is working in a relatively new area for them and has just scaled up from 4 to 10 outreach teams this past year. The biggest challenges are: finding adequate public sector staff of the right cadre to train; hiring and training private sector staff; and continuing to collaborate closely with GoURT (which can slow progress even if the collaboration is good). Commodity risks remain but are managed to a great extent with the back-up stock. These risks are manageable. Work with CPAC and GBV and public sector provider training requires close collaboration with GoURT and sensitive engagement. This has been good so far and regional and district staff appear to be enthusiastic and grateful for the assistance of the implementing partners. The national Government would be unlikely to change the FP outreach, CPAC or SGBV guidelines but this remains possible.

The risk matrix should have two new risks added:

Women are unwilling to identify themselves as survivors of sexual or gender-based violence. There are also risks that staffs do not want to identify or refer clients because of the huge time and financial costs associated with follow-up, particularly if cases are taken to the courts. In addition there are social and personal costs to health workers who may need to testify against people in the community who committed a sexual assault.

The changes to the US administration are likely to change US funding for sexual and reproductive health services in Tanzania. This risks needs to be monitored by government and partners.

Outstanding actions from risk assessment

None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

PSI’s scale up was slowed as the Government insisted on evaluating their programme in their initial four districts. This slowed the choice of districts in Year 2 for the scale up to 10 teams. DFID approved scale up in February and PSI began outreach services in March. The GOURT did not give permission to work with public sector hubs and spokes until June, slowing down the scale up. Despite these setbacks, PSI moved quickly to set up their programme and to catch up with their service delivery. PSI gave reassurances that they would be able to catch up further in the next year and produce their total numbers by the end of the programme.

Performance of partnership (s)

Overall, the relationships between all partners seem to be positive. The review team found only positive relationships between government and the implementing partners or between the two implementing partners or their subcontractors (Intrahealth and Restless Development). Both implementing partners have continued to attend joint partners meetings led by DFID, and share key lessons and challenges of the implementation of the programme. DFID should continue its quarterly meetings with the implementing partners as these meetings are building good relationships, ensuring a lack of duplication, and encouraging joint problem solving (e.g. tubal ligation lessons learned from MST by PSI).

MST has specific key performance indicators as part of the contract which has incentivised better collaboration and coordination with GoURT and other implementing partners, improved communication and proactive problem-solving.

Asset monitoring and control

The asset verification was done by physically visiting MST and PSI Supporting offices in Dar es Salaam. Moreover, interviews were held with MST’s Finance Manager, PSI Asset Manager and Programme Officers.

For MST, an asset register consists of items of above Tshs 4 million. Al items below this value are recorded as inventories. Both assets and inventories register are twice per year through physical verification including those in the regions. MST has comprehensive cover insurance for all of its assets and inventories. During the review, it was found that 4 laptops were stolen and the office was in the process to recover them from the insurance company. Majority of MST’s assets are cost shared by other donors except for laptops and vehicles. All assets ad inventories have tag no.so as to keep good truck of the records of the assets.

For PSI, the last physical asset verification was done in 2015, including physically verifying assets in the regions. However, regional office managers send the status of assets in their respective regions annually. The same was updated in December 2016. All assets have tag numbers to enable record keeping. However it was found that the Tablets recently purchased do not have tag numbers which makes it hard to truck on records. During the review, one laptop was found to be missing (PSI/LPT/182 with serial No. 6B7ZN32). However the office is aware and is making following up to replace it.

Recommendations
- PSI should consider updating their asset register at least twice a year. Spot checks should be conducted in the regions to cross check what is reported by regional managers.
- PSI should include any missing assets in their asset registers

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

FP and CPAC continue to have a strong evidence base with huge public health impacts. The Tanzanian DHS 2015-16 yielded much rich information for this programme.

Monitoring progress throughout the review period

The programme team, have had quarterly review meetings with both IPs, have conducted four field visits during the last year, and have spoken directly to beneficiaries to learn about the progress of the programme. Observations have been used to improve the quality of programming, particularly in how the needs of beneficiaries are met, commodities management and health worker training. Joint IP review meetings facilitated by DFID have also been fruitful in supporting IPs in bottlenecks on larger technical, operational and policy issues. This has facilitated collaboration. DFID has also kept updated and shared learning on developments with other development partners and IPs through relevant forums, including technical meetings, donor groups and working groups.

Team & Field Visits. The review team consisted of Carol Bradford (Team Leader) and Dan Whitaker (Economist); participation from DFID included Gloria Ngaiza (Health Advisor), Jane Miller (Human Investment Team Leader), Suse Matamwa (Programme Manager), and Joseph Payne (Senior Programme Manager). The Team saw an outreach activity at Misungwi Hospital in Misungwi district and CPAC and GBV activities in Sangabuye Health Center (both in the Mwanza Region). The Team also visited MST tuk-tuk outreach at Hananasif dispensary in Kinondoni District, Dar es Salaam. With PSI, the team visited Urban Dar es Salaam and saw two hubs (Tabata A dispensary in Ilala district and Kimara Health Centre in Ubungo district) and three spokes (Segerea & Kinyerezi dispensaries & Mbezi dispensary) and youth activities in Ubungo. The team visited the Regional Medical Officers and District Medical Officers at each field site. In addition, the team met with Ministry of Health Reproductive and Child Health staff, USAID, Kfw, DANIDA, Engender Health, USAID’s new Global Health Supply Chain Programme, DKT, Pathfinder, and all IPs and their respective downstream partners.

ACRONYMs

ASRH	Adolescent Sexual and Reproductive Health
CPAC	Comprehensive Post-abortion Care
GBV	Gender-based Violence
CLIC	Client-centred data collection
CPR	Contraceptive Prevalence Rate
CYP	Couple Years of Protection
DALY	Disability Adjusted Life Year
DFID	UK Department for International Development
DHIS	District Health Information Software
DRCHCo	District Reproductive and Child Health Coordinator
FPTWG	Family Planning Technical Working Group
GOURT	Government of the United Republic of Tanzania
HIV	Human ImmunoDefficiency Virus
IPs	Implementing Partners
IUCD	Intrauterine Contraceptive Device
LAPM	Long Acting and Permanent Methods
LARCs	Long-acting and reversible contraceptives
LGA	Local Government Authority
MOHCDGEC	Ministry of Health, Community Development, Gender, Elderly and Children
MSD	Medical Stores Department
MSI	Marie Stopes International
MST	Marie Stopes Tanzania
MVA	Manual Vacuum Aspiration
PMDUP	Preventing Maternal Deaths through Unwanted Pregnancy
PSI	Population Services International
SRH	Sexual and Reproductive Health
TDHS	Tanzania Demographic and Health Survey
TFR	Total Fertility Rate
UNFPA	United Nations Population Fund
USAID	United States Agency for International Development
VfM	Value for Money

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process