Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: MOBILISING FOR DEVELOPMENT (M4D) PROGRAMME
Programme Value: £20 million (of which 17.5 million are managed by Palladium)		Review Date: February 2017
Programme Code: 5669	Start Date: May 2012	End Date: 16 May, 2018

Summary of Programme Performance
Year	Yr 1	Yr 2	Yr 3 (MTR)	Yr 4
Programme Score	A	A+	A	A
Risk Rating	Moderate (to Major)	Moderate	Moderate	Moderate

SUMMARY OF PROGRESS AND LESSONS LEARNT SINCE LAST REVIEW

M4D made good progress in 2016; exceeding targets in five of the six outputs for the year under review. As a result, M4D is on track to demonstrate broader outcomes relating to collective action on increased community involvement in decision-making and the responsiveness of policy makers and service providers (PM/SP) to citizens. However, challenges remain around the political environment, state level institutions and the programme’s ability to document and share lessons and learning.

In 2016 the programme expanded to 9 new wards to reach a total of 45 Wards across nine focal LGAs in 3 states and thus achieve the total expected lifetime coverage. Alongside this expansion, the programme has consolidated progress made in previous years institutionalising systems and embedding processes – both with partner CBOs and, to a lesser extent, with Local Government Authorities (LGAs).

A key area of success for M4D is the continued, improved, organised dialogue and collaboration between community representatives and PM/SP. Beneficiaries in partner CBOs and communities in M4D supported LGAs reported increased ability and skills to shape policies, improved access to decision makers and better engagement on issues concerning their lives. For example, the Kano Girls Platform collaborated at state level with PWD CBOs in Jigawa and this resulted in uptake of the Community Based Rehabilitation into state level plans. On the local government side, there is increased receptiveness and engagement with community demands, with beneficiaries and PMs and SPs all seeing better dialogue and improved understanding. However, the resources, space and capacity to address the issues raised at local government level remain a challenge.

The programme has also established and strengthened strategic partnerships with a broad range of Civil Society Partners (CSOs); other DFID funded programmes and with relevant state level Ministries to deliver programme activities. This has helped to institutionalise and embed reforms in LGA and state policies, laws, plans and budgets. It has also supported replication of M4D supported accountability and service delivery initiatives in non-M4D areas. For example, M4D supported innovations such as Second Chance Girls Education and Mobile Vetenary Clinics have made their way into state plans and are being replicated across the states. There is also some evidence of CBOs and LGAs embrassing change and adopting M4D’s social accountability approaches; with small numbers of more systemic changes, notably participatory budgeting in Kano and disability law in Kaduna.

M4D’s main challenge remains that local government in Nigeria is highly politicised (often subject to direct state control) and under resourced (with limited budget releases and low staff capacity). Many of these constraints come from the state level and it is not clear that M4D has engaged sufficiently broadly or politically at state level to foster champions or ensure support. There is also a challenge for coordination and approach at local government level that DFID needs to address across programmes. There is evidence that work at local government level does not conform to a consistent view of how local government should be engaged in a state; for instance, LGA have embraced citizen’s participation in planning and monitoring of programmes such that LGA plans are based on citizen’s prioritised needs; but has not been able to shift State governments’ view of LGA as incompetent and lacking necessary skills to operate independently of state government interference.

On financial managment, M4D needs to address some internal issues identified in the draft audit report conducted in May 2017.

Key Lessons
Post MTR, the programme organised an internal meeting to reflect on its Theory of Change, revised its Logframe (in line with recommendations of the MTR) and concluded, based on the understanding that the State rather than the Local Government is the locus of development planning and resourcing in Nigeria, a much greater strategic focus would be needed for working with State level institutions in year 4.

1. There is a disconnect between policy makers’ and service providers’ willingness to be more responsive and accountable to citizens and improvement in service delivery. This is likely to be in large part due to lack of resources and control over resources at LGA level.
2. Peer-learning has continued to influence states to adopt ideas from each another. An example is support to Jigawa Rehabilitation Board’s visit to Lagos, the only state to have passed disability legislation. This resulted in some refinements to the Jigawa Disability Bill and a push for its enactment in the Jigawa House of Assembly.
3. Participation of higher level state policy makers in learning events for successful M4D initiatives and getting their buy-in can result in accelerated replication of such initiatives across the focal state(s). The Executive Deputy Governor of Jigawa State participated in M4D’s 2016 Annual Stakeholders’ Learning event and was impressed by the Mobile Vetenary Service (MVS) BFA. He directed NGN44million be approved in the 2017 budget for replication of the BFA in all 27 LGAs of the state. Equally, the involvement of the PMs of Kano State Ministry for Local Government in a learning event on Open Budget Initiative (OBI) resulted in a Ministerial directive to all 44 LGAs in the state to replicate OBI during the 2017 budgetary process.
4. Resource constraints such as the current limited flow of funds for capital projects from federation account via state to LGAs have accelerated Partner PMs/SPs openness to new ideas for generating revenues to support their commitments to their citizens.
5. Changes in government can have a positive and a negative effect on programme work and capitalising on that can lead to conflicting support and approach. For example, a new reformist governor in Kaduna State signed a new tax law which harmonized and centralized the collection of all revenues in one agency - the Kaduna State Internal Revenue Service (KADIRS). This is aimed at raising the efficiency of tax collection and making it easier to pay taxpayers. However, the constitutional responsibilities of the LGAs to collect taxes was usurped and the state still has a major control over the finances of the LGA; thus making it impossible for LGAs to respond effectively to citizens prioritised demands.

Actions on previous recommendations
The Mid Term Review made seventeen recommendations; fifteen of which were accepted; while two were rejected with explanations. Of the fifteen accepted recommendations, fourteen have been fully responded to while one (‘M&E should also be linked more clearly to learning objectives and should be used to strengthen the way in which overlap is managed. Based on this, M4D should consider an output on learning’) has not been fully met. M4D has framed an output on learning (output 5 in the revised logframe); but the M&E has not demonstrated its ability to strengthen the way overlap is managed. There remains a huge expectation (though not explicit) on the Independent Evaluation Manager (IEM) to respond to all programme learning objectives. Specific breakdown of the recommendations are addressed under each area/output.

Summary of recommendations for the next year
1. M4D was developed as an experimental programme designed to test a supply and demand side approach at local level as a route to improving service delivery. The programme has either achieved or over-achieved all milestones (in some cases exceeding programme lifetime targets) in five of its six outputs and also seen significant achievement at outcome level in terms of capacity and reach indicators. However, the extent that these achievements are being translated into widespread service delivery improvements or systemic changes in governance approach is not yet clear; and it may take a year for evaluation results and programme lessons to sufficiently prove this. It is therefore recommended that during the last year the programme should limit the amount of time spent on supporting specific interventions and instead focus on support to limited specific areas of significant importance and above all to seek to really understand, demonstrate and document where the M4D approach has worked and has not worked to strengthen the system of service delivery in each state (rather than the delivery of individual interventions or results). Continuing to overachieve on already delivered indicators and doing more of the same is of less importance than maximising the learning from the experimental approach. The value that remains to be extracted from M4D is in understanding what the value and potential of a programme such as M4D is and could continue to be beyond individual achievements. This focus should be reflected in a revised LF that ensures the programme is judged against these governance changes and that provides appropriate stretch for the last year of implementation.
2. Kaduna State has formulated a goal to reposition and make LGA more effective. The Governor issued a directive to assess and develop improvement plans for all 23 LGAs in the state by end March, 2017. It is recommended that the programme seeks to insert its influence into Kaduna’s reform process by focussing on and supporting the Governor’s agenda (where it makes sense); and exploring the best ways for engaging with the government to ensure increased citizen engagement.
3. State Ministries, such as Finance, Budget & Planning, Education, Women Affiars and Local Government still control the Local Government apparatus. The programme needs to build stronger relationships with these ministries to ensure sustainability, lesson learning and potential replication of programme interventions/approach.
4. There are several cases from programme intervention that demonstrate collective action can lead to improved accountability and responsiveness of PM/SP to citizens as well as increased citizen involvement in governance. However, the programme has not been able to successfully tell its stories. There is the need for significant effort on lesson generation and success story documentation (including stories to demonstrate achievements and successes with people with disability, adolescent girls and Mobile Populations (Fulanis)). These should be developed with a view both to documentation and communication targeted to various audiences.
5. Overall M4D has achieved some significant successes in building the capacity and strengthening the voice of community level organisations, including those for adolescent girls and people with disabilities. There have also been notable successes in supporting specific better fit (service delivery) approaches in communities; but it is not clear how these all translate into improved services for citizens in the focal LGAs. It is recommended that the M4D makes significant progress with the evaluation and building from this (rather than relying on it) to an assessment of how service delivery and accountability has been improved, and the potential for this to be sustainable and scalable.
6. The programme is in its last year of implementation. This requires a strategic reflection and a plan for ensuring sustainability of the approach in M4D partner CBOs, focal Local Governments and States. This requires achieving the right balance between capacity building/training and supportive mentoring to prepare partner organisations to operate on their own, and embedding M4D’s current support to institutionalisation of programme results on reforms, innovations and new ways of working.
7. Programme supported political economy analysis and BFA case study recently prepared by the IEM proved the impact of engaging with traditional leaders to the successful outcome of M4D initiatives/interventions. It is recommended that the Programme doubles its efforts and deepen its engagement with key Religious and Traditional Leaders (RTL) e.g. Emir of Kano who has demonstrated a long term passion for girl education to strengthen the adoption and replication of its approach/interventions as well as ensuring their sustainability.
8. M4D’s approach (working simultaneously on both demand and supply sides of governance – building collective action) is quite innovative and has performed well on most VFM areas (Economy, Effectiveness, Efficiency and Equity); with its best achievements in the fourth E – Equity; leading the Review Team to conclude that the programme continues to represent value for money for DFID. However, there has been a significant gap between programme delivery and budget execution, continued staff turn-over and underspend against programme workplans. It is recommended that the programme works at improving its financial management and closing the gap between programme delivery and budget execution.
9. M4D should ensure appropriate rigour in its financial management procedures to reduce errors in invoicing to DFID and in management of foreign exchange. It is recommended that DFID and Palladium discuss the full findings of the audit with a view to Palladium preparing an action plan to ensure issues raised in the report are fully addressed and lessons learned as needed across DFID-funded Palladium programmes.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202352/doc:3716803
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202352/doc:3719395

Outline of the programme
Mobilizing for Development (M4D) is a £20 million programme scheduled to run over six years from June 2012 to June 2018. It aims to support policy-makers (PMs) and service providers (SPs) to become more accountable and responsive to citizens’ better articulated demands and entitlements, especially adolescent girls (AGs) and people with disabilities (PWDs), with the aim of improving service delivery and accountability in nine selected Local Government Areas (LGAs) in three states (Kano, Kaduna and Jigawa) in Northern Nigeria.
The programme aims to reach 650,000 people (among them at least 30,000 girls) in Kano, Kaduna and Jigawa states; and seeks to strengthen social accountability and tackle social exclusion to ensure citizens more able to plan and control their development, more aware of the responsibilities of government to deliver services more effectively and a local government that is more responsive to its citizens. The programme also has a specific focus on reaching people with disabilities.

Programme support includes:
- Building the capacity of communities to identify their problems and solve them.
- Support research and advocacy on the policy and regulatory environment and provide match-funded grants for development investments.
- Focusing on excluded and marginalised groups, in particular adolescent girls.
- Involving Government of Nigeria staff at Local Government and State level to aid understanding and the adoption of the approach by others and promoting the approach for adoption by other development partners.

Context
Continuing low levels of federally administered allocations brought about by the global crash in oil prices and a growing domestic debt situation have severely impacted the core capacity of all three M4D partner states and their ability to deliver basic services to their citizens. While M4D worked extensively with citizen groups and decision makers to ensure citizen priorities were captured in state and local government budgets and strategic plans in 2016, levels of implementation of these were still relatively low due mainly to inadequate resources.
This resource constraint is most apparent in Kaduna where M4D supported partner CBOs across its three LGAs conducted extensive processes of community mapping, mobilisation and Town Hall meetings to feed into the Kaduna State Integrated Local Government Plans (ILGP) and budgets. However, the supported LGAs were unable to deliver as resource transfers from the state level were severely depleted, often not even sufficient to meet basic overhead costs. Early commitments of the El-Rufai administration to enhance the fiscal autonomy of local governments and efforts by the Federal APC government to review the constitutional status of local government have both stalled. Electoral incentives for local policy makers to commit and follow through with citizen demands remain weak, with LGAs being run by appointed Interim Management Committees (IMC) in Kaduna and Jigawa and an uncertain future for local government councils in Kano.
The convergence of ‘demand’ and ‘supply’ side actors (currently known as ‘Collective Action’ in Social Accountability circles/discourse), which is a key programme principle, has become more important in the context of severe resource constraints. While the economic and fiscal crisis poses immense challenges to efforts to improve governance and service delivery, it also offers new opportunities. Across M4D’s focal states, there has been an increased focus on cutting down the cost of governance, reducing leakages and inefficiencies in public administration and service delivery processes and generating new sources of revenue. This creates an opportunity for M4D and M4D supported CBO/PM/SP to insert their influence in the reform processes.
While resource constraint is a big issue in performance of Local governments across the three states (and indeed in Nigeria) the position of local governments in the eyes of states and its governance structures creates a bigger challenge to local governments’ ability to function effectively. Although local governments are theoretically the third tier of governance and have a high level of independence, in practice state governments have a firm grip over and shape decisions on spend and activity at the LGA level. Generally allocations from the Federation account are deposited into a ‘joint account’ (owned by the state and LG) and not released directly to local government with state government taking the view that LG lack skills and capacity to manage the resources. In Kaduna, for example, the State can disburse only staff salaries to the LG accounts. Also, all internally generated revenues from the LG are deposited into accounts that are controlled at the State level. Across all states the state governments have powerful oversight of local government budgets and all other spend has to be vetted and approved by state governments through a system of ‘submission of proposal’. The State has noted that significant leakage has been identified at local government level and these actions are required to address this issue.
While most LGs mention this arrangement as constraining their ability to respond effectively to citizen’s demand and deliver improved services; other progressive Local Government Chairmen (e.g Kudan LG in Kaduna State) have found a way of investing the little resources that have been released to them from the State to provide services for its citizens. This probably shows that individual attitudes have implications for service provision at the local government level.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
M4D’s outcome is "Policy makers and service providers are more responsive and accountable to citizens' better articulated demands and entitlements, especially adolescent girls (AG) and people with disability (PWD)’; and the programme has been working simultaneously on both demand and supply sides of governance to deliver this outcome. So far all outcome indicators have been achieved or over-achieved (Table 1).
Indicators	No. of CBOs and platforms including those of Girls and PWDs, in M4D LGAs who state that they have more influence on policy makers and service providers.	2. No. of targeted service provider and policy making organisations progressing along a responsiveness and accountability scale.	3 No. of citizens' articulated demands that are incorporated into plans or delivery of basic services and accountability.	4 No of citizens' demands incorporated into action plans or service delivery that have been implemented.	5 Cumulative numbers of citizens benefiting from M4D interventions disaggregated by sex and location.
Planned Dec 2016 Milestone	49 (31 CBOs / 9 GP / 9 PWD)	38	80	10	450,0000
Achieved	65 (47 CBOs, 9 PWDs and 9 GPs	45 (including 6 informal PMs)	116	20	534,642

Looking at the logframe milestones and cumulative results the programme demonstrates that it is possible to achieve considerable results on both the supply and demand sides at a local governance level. It also demonstrates that parallel but tailored capacity building on both supply and demand sides is an effective strategy for building collective action. There is evidence of significant improvement in the ability of citizens to make demands, the quality and number of those demands and of demands reflecting the needs of marginalised groups. There is also evidence of improved and increased responsiveness of policy makers to those demands.
However, whilst M4D has delivered well against these outcome indicators the question still remains about whether high levels of success in these areas will lead to the types of sustained improvement in service delivery and inclusion that M4D is working towards. It is important, and not always easy, when considering the performance of M4D to distinguish individual achievements and specific interventions from the system and approach by which those interventions were brought about. M4D needs to be judged on both areas.
There are also two possible routes by which the M4D approach might be validated and one clear criteria by which it would prove invalid. It would be validated if either:
1. it could be demonstrated that the service delivery improvements and increased inclusion delivered under the programme were good value for money and provided sustainable approach to delivering those improvements (compared to other delivery approaches)
2. It is shown that the M4D approach has catalysed systemic change in governance systems with evidence of achievement from that and of long term improvement.
The approach would be invalidated if it is shown that M4D is not an effective way of improving service delivery or inclusion and it is shown that other approaches are more cost effective or work better.
At the moment, the evidence that can answer this question is not yet collated and documented but reaching a conclusion on this point must be a major focus of the programme during its final year.
There are positive signs:
- M4D supported approaches such as the Town Hall Meetings, Mobile Veterary Services and Girls Second Chance Education have broken into mainstream government policies and programmes in M4D focal states.
- Increased institutionalisation of town hall meetings as a major vehicle for articulating community issues and demands; and voices of previously excluded groups such as PWDs and adolescent girls are now visible.
- Supported PM/SPs report that the programme’s approach of capacity building for PMs and SPs as well as combining training workshops with on-site coaching and mentoring have contributed to a high level of buy-in and adoption of participatory planning and budgeting processes at both state and LGA levels.
- State governments have committed to developing LGA-wide action plans in consultation with community members and have continued to mandate LGAs to work with their communities to develop plans. This clearly demonstrates that any interventions that may eventually be funded by LGA/State governments are those that have come from the communities; hence, have the potential to respond to communities prioritised needs.
- Community demands have been incorporated into plans and budget and so far 20 community demands have been implemented as against the milestone target of 10. This is a new outcome indicator added in response to recommendations of the Mid-Term Review; hence is considered as a good result considering the current resource constraints at local government and State levels.
- Better fit approaches and grants continue to enhance M4D’s experimental approach. 4 new BFAs (focussing on community sanitation, tax for services and community participation in local governance) were introduced in 2016. These bring the total number of BFAs to 16 (from the previous 12) across M4D’s focal LGAs and states.
However, whether these will coalesce into a collection of achievements and body of evidence to justify the approach and demonstrate value from £18m of spending is the question that has to be answered between now and the end of the programme.

Overall output score and description: A (Outputs met expectation)
	Output	Score
Output 1	CBOs better organised, engaged and aiding community demands for equitable service provision and LGA accountability	A
Output 2	PWD CBOs and Platforms of girls organised, engaged and demanding equitable basic services and accountability	A
Output 3	Increased capacity of policy makers and service providers to design and deliver basic services and operate accountably.	A
Output 4	Better-fit approaches to basic service delivery and accountability on targeted issues identified, developed, tested and refined	A
Output 5	Lessons from M4D initiatives identified and effectively shared.	A
Output 6	Improvement in programme management and effective delivery built upon independent and credible evidence based approach to accountability and learning.	B

Key lessons
1. Skills enhancement of partner CBOs can have a rippling effect. M4D supported CBOs who received training on PEA/ Power Mapping formed PEA-driven coalitions in their LGA and were able to network and engage with appropriate PMs/SPs on issues of common interest to all of them. Similarly, M4D supported CBOs are taking initiative to mentor non-M4D CBOs to improve in organizing, engaging and influencing, sharing what they have learned. Six M4D partner CBOs, including 3 PWD CBOs are mentoring non M4D supported CBOs.
2. Capacity building and facilitating engagements alone are not enough to move from enhanced community voices in governance to increased accountability and transparency, particularly at the local levels; and, Local government level PMs/SPs willingness to respond to community demands may not translate into improved service. This is mainly due to limited access to resources to implement the demands. Any effort at building collective action (working on demand and supply side of governance) needs to be accompanied by a robust financial support and/or opportunities for generating national/international revenue to respond to community prioritised needs.
3. The draft findings of the IEM case study on Better Fit Approaches (BFAs) indicated that whilst BFAs are responding to community needs and gained political traction at different levels of government and created platforms for communities to come together to work with LG, there is a need for a more systematic approach to testing and advocating for scale up and replication of the BFAs, taking into account the current fiscal crisis.
4. The programme is making progress and has delivered significant results in building the capacity of demand side actors to mobilise, engage and demand for their rights. There has also been progress in implementing community demands resulting in benefits to communities in focal LGAs. However, M4D has been so poor at communicating these results in a format that is accessible to DFID and the wider audience.
Key actions
1. M4D needs to ensure a focus on the approaches and systems through which it is working, rather than the development and implementation of specific interventions such as the BFAs.
2. Programme needs to improve on narratives around its results. The programme should document its success stories with a focus on presentable, easy to communicate narratives (short and with pictures). It should also, as part of telling its stories show clearly what the programme can and cannot do.
3. There is a need to further implement learning and communications strategies to proactively identify and share suitable lessons with a full range of stakeholders, so as to share and embed best practices and successful innovations.

Has the logframe been updated since the last review?
Yes. The last review made recommendations about revising the logframe; these included revisions to some of the output statements in order to highlight critical aspects of the programme such as capacity building and lesson learning whilst taking into account the stage of the programme and the technical strategy required delivering. These revisions have been made, including changes to some of the indicator statements. New targets were set for many of the indicators because such targets have either been met or exceeded. Table 2 below provides a summary of the revisions made to the logframe, and a full paper was prepared to describe the changes proposed to DFID.
Summary of logframe revisions
Programme Logic	Revisions Made
Impact and super impact	No revisions to statement or to existing indicators
Outcome	No revisions to statement or to existing indicators. However, indicator targets revised and two additional indicators proposed including for “REACH”
Output 1	Revisions to output and indicator statements; indicator targets revised
Output 2	No revision to output statement; minor rewording of indicators and one indicator target revised
Output 3	No revision to output statement; slight revisions to indicator 1 statement; all indicator targets revised
Output 4	Slight revision to output statement; no revision of indicator statements; slight revisions to targets for all the indicators
Output 5	Revisions to output and indicator statements; indicator targets revised
Output 6	Slight revision to output and indicator statements

## C: DETAILED OUTPUT SCORING

Output Title	CBOs better organised, engaged and aiding community demands for equitable service provision and LGA accountability
Output number per LF		Output 1	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Dec. 2016 Milestones	Progress
1.1. No of CBOs showing improvements in the ability to organise themselves	54 (9/45)	53 / Milestone target almost met. On track to meet Lifetime target.
1.2. No of CBOs showing improvements in the ability to engage around community demands.	50	53 / Milestone target slightly exceeded. On track to meet lifetime target.
1.3 No. of quality citizens' demands made to service providers and policy makers by CBOs in M4D LGAs.	160	304. / The cumulative milestone target (160) and lifetime target (180) both exceeded

Key Points
1. According to the Community Dialogue and Action Scorecard, 53/54 partner CBOs are showing improvements in their ability to organise themselves and advocate effectively on behalf of their constituents. The more experienced organisations are also now acting as mentors to newer CBOs, some of which are not within the scope of the project. Programme beneficiaries spoke in unison on how M4D has “built their capacity” to “articulate demands” and to know their rights.
2. CBOs are proactively involving groups previously excluded from community planning and negotiations. Youth, PWDs and women/girls are consciously being targeted to participate in community agenda setting and receive benefits. One ward in Kano (Tumfafi) spoke of targeting the children of PWDs to receive tuition-free education at the local elementary school. The involvement of religious and traditional leaders in the implementation of activities has enhanced the acceptability and credibility of the programme.
3. Both citizens and policymakers report a much more streamlined process for articulating the demands from communities, many of which continue to centre on basic services and infrastructure. Communities report feeling empowered to demand what they consider to be a right to basic services, and policymakers are reassured that the demands reflect community priorities. In the target states, the local government authorities reported favourably on the organised manner in which the M4D-supported LGAs have tabled their demands, to the extent that Kano state government has asked all 44 LGAs to use the model/template submitted by the Dawakin-Tofa LGA in their 2017 budget submissions.
4. All community representatives spoke to the value of being able to engage on budget policy as being new, empowering and the ‘best result of M4D’, and all attested to seeing their demands reflected in the LG and/or state budget. However, that does not necessarily translate into having most of their ‘quality demands’ met. There have been improvements in communication between communities and local government authorities, but financial constraints continue to be cited as the primary reason for unmet demands. There is a risk that citizens will eventually disengage if the level of responsiveness (i.e. implementation of demands) does not seem to validate the efforts invested in these processes.
5. The ward-level CBOs seem more active than LGA-level CBOs, but this could be a reflection of a greater level of ownership of specific issues at the community level. There is a broader question on whether the CBOs will be able to sustain their engagement beyond the life of the programme. There were very few examples of communities using self-help methods such as co-opting private sector support, or demanding to be trained in light maintenance work on pumps, which would reduce reliance on LG authorities to action all demands. Without the programme staff marshalling efforts and, in some instances, providing small grants, it is not clear that momentum will be maintained.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous AR recommended a revision of the output statement to capture the depth and quality of engagement, as well as the extent to which the CBOs themselves are organised. Milestones were also increased as lifetime targets had been exceeded at the MTR juncture. The logframe was amended accordingly.

Recommendations
R1: The output indicator milestones have again been met or exceeded. Consideration should be given to whether the final year of the programme should focus on increasing those quantitative values (not recommended) or whether the actual indicator(s) of the output should be revised to reflect a deepening of the CBO engagement. More fundamentally, it could be considered whether the output itself has outlived its usefulness. There is a need to define the focus of the CBOs for the next year to ensure their sustainability, as well as institutionalisation, of the M4D approach.
R2. M4D needs to keep an eye on the effects of lack of implementation of demands on communities’ willingness to continue to engage in M4D supported processes/approach; including an assessment of thresholds at which communities would opt to disengage from the process.

Output Title	PWD CBOs and Platforms of girls organised, engaged and demanding equitable basic services and accountability.
Output number per LF		Output 2	Output Score	A
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Dec. 2016 Milestones	Progress/Actual Result
2.1. No. of LSCs of Girls formed and supported, to the emergence of Peer Champions and Girls Platforms	LSCs: 360 / Peer Champions: 360 / Girls Platform: 9	LSCs: 366 / Peer Champions: 366 / Girls Platform: 9 / Milestone target for LSCs and Peer Champions exceeded.
2.2. No. of PWD CBOs and Girls platforms showing improvements in the ability to organise themselves.	18 (9 GP, 9 PWD CBOs)	18 (9 GP, 9 PWD CBOs). / Milestone target met. Lifetime target met.
2.3. No. of PWD CBOs and Girls platforms showing improvements in the ability to engage around community demands.	12 (4 GP, 8 PWDs)	18 (9 GP, 9 PWD). / Milestone target exceeded. Lifetime target already exceeded.
2.4. No. of quality demands made by PWD CBOs and Girls platforms, to service providers and policy makers in M4D LGAs.	80	96. / Milestone target exceeded. Lifetime target (90) already exceeded

Key Points
The number of Life skills clubs planned for the end of the programme has been exceeded and all Peer Champions have now emerged.

18 PWD CBOs and Girls platforms (as against milestone target of 12) have been formed and supported to engage with PM/SP on their issues. These PWD and Girls Platforms are showing improvements in their abilities to organise themselves and advocate effectively on behalf of their constituents. Further, Girls Platforms have demonstrated their ability to engage directly with Local government institutions by-passing the previous arrangement where they were expected to engage through their Community Based CBO. Such direct engagements amplify girls’ voices and ensure better understanding of their issues and experiences.

Participation of women in CBO management and activities has increased; 10 CBOs have taken steps to institutionalize women’s participation in their constitutions and address barriers to women’s participation. Women have been appointed to key executive positions such as treasurers, and secretaries. Most CBOs have adopted the 30% women representation stipulated in the National Gender Policy.

Institutionalisation of the girl platform strategy has gained traction and is breaking through to the state level. For example, Jigawa State Ministry for Women Affairs & Social Development (SMWASD) has allocated NGN3.5million in the 2017 budget to scale up girl platform work (building skills and self-esteem, providing seed money for livelihoods; and increased numeracy and literacy) to 5 additional LGAs (Roni, Gumel, Dutse, Babura, and Kafin Hausa).

Adolescent girls are acquiring new skills and have demonstrated their ability to use them with good result. In Garum Malam (Kano State), girls used their newly acquired skills in participatory needs analysis and problem tree analysis to analyse the root cause(s) of lack of female teachers in Islamiyya LGA schools and found - “an unwillingness of husbands to let qualified wives to teach” as the main reason. Working with CBOs, traditional and religious leaders and SUBEB (the local education authority) they built consensus and agreement that now allows qualified women to teach in the Islamiyya schools. In Kaduna, LSCs analysed the causes of the problem of girls low school attendance and took appropriate actions such as community rallies to advocate for girls’ education. This led to increased girls enrolment in school in their area. But the main focus of girls is on hard skills needed to improve their livelihoods (learning how to sew, make body creams, soap and numeracy skills) not intrinsic soft skills.

PWDs have expressed their enthusiasm and spoke to the value of engaging with M4D supported initiatives. They are more able to stand-up for themselves and feel better placed to contribute and shape development agenda in their communities. Their demands are being met; and their voices heard. While PWDs and their members no longer feel excluded from their communities; a new form of challenge still remains; that of discrimination. Products made by PWDs such as blind people are sparsely patronised (due mainly to superstition that using things made by a blind man or a leper will make one blind or contract leprosy). These are essential lessons for potential programmes on disability –the need to build in a strong behaviour change strand into skills acquision for PWDs;without which there would hardly be any improvements in their standard of living.

The programme also ensured that appropriate stakeholders including PWD CBO partners in Jigawa state effectively engaged with the Jigawa State House of Assembly on the Disability Bill to ensure that their issues and needs are reflected in the Bill, based on the proactiveness of the legislature to give speedy hearing on and passage of the Bill. This and the efforts of the legislature supported by the programme resulted in the passage of the Disability Act that incorporates the CBR framework.

Summary of responses to issues raised in previous annual reviews (where relevant)
MTR recommendation for this output was to ‘Explore innovative ways of expanding and strengthening the spaces for inclusive engagement between citizens and policy makers/service providers. The programme has supported innovative ways such as problem tree analysis and power mapping to create spaces for adolescent girls/PWDs to engage with PM/SP.

Recommendations
R3. The programme should expedite action on implementation of the institutionalisation strategy; and explore ways of raising the profile of intrinsic skills and values of adolescent girls’ participation in decision making and governance.
R4. M4D should work with the relevant institutions at LGA and state levels to address the issues of discrimination and superstitions around products made by PWDs.

Output Title	Increased capacity of policy makers and service providers to design and deliver basic services and operate accountably.
Output number per LF		Output 3	Output Score	A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Dec. 2016 Milestones	Progress
3.1. No of targeted individuals from SP/PM bodies with increased skills to respond to demands of communities and marginalised groups.	527	607 / Milestone target exceeded. Lifetime target (557) already exceeded
3.2. No. of targeted service provision and policy making bodies, who revise or develop action plans on standard based service provision or regulation with communities and marginalised groups.	30	50 / Milestone target exceeded. Lifetime target (36) already exceeded
3.3. No. of citizens' quality demands that are logged and initial action identified by targeted service provider and policy makers.	104	113 / Milestone target exceeded. Lifetime target (110) already exceeded

Key Points
1. Policymakers and service providers demonstrate a clear understanding of the M4D vision; their uptake and its impact on how they operate is less evident. In Kano and Kaduna, PMs Spoke glowingly on the benefit of M4D to their ability to engage effectively with communities, and on the ability of CBOs to present coherent, validated priorities rather than multiple/competing demands. This was of particular importance when budgets are being crafted as PM/SPs understand the demands being made and have been able to “change orientation” to attempt delivery of what is required. PMs also spoke about the oversight role that CBOs provide by highlighting service gaps and challenging authorities to deliver on what communities now consider to be a right. For example, Kachia LGA representatives reported being called when nurses do not turn up for work, and neighbouring LGAs are also slowly adopting these practices.
2. Regular town hall meetings provide the primary forum for community demands to be made directly to policy makers and service providers. These are public meetings to discuss community concerns as well as an opportunity LGAs to respond. The review heard how women and girls have been able to use these meetings to make demands that are specific to them. PMs in Kano also referenced SERVICOM as a platform supporting service delivery improvements that would benefit from M4D’s support to replicate across the state.
3. Particularly at the state level, there is recognition that local government should have autonomy over their affairs, but there are concerns that LGAs do not have the capacity to manage efficiently. Notwithstanding, the states insist that resources are provided in line with constitutional requirements. On the other hand, LGAs consistently cited financial constraints from shortfalls in allocation as the major barrier to responding to community demands. For example, one LGA reported receiving only 56% of the requested allocation, of which more than a half was for salaries.
4. Significant changes are being contemplated in Kaduna but there is a sense that these are being imposed, rather than being driven by an organic, inclusive process. Unless there is buy-in by those required to implement the changes, any reform (however game-changing) will not likely outlast current state leadership.
5. With few exceptions, traditional and formal leaders expressed an interest in a continuation/expansion of M4D. So also from the PM/SP perspective, the level of ownership of the approach and how it might be replicated is not embedded. There was less emphasis on how PMs/SPs may be able to institutionalise the practices and BFAs and more expressions of interest in having M4D continue to lead the engagement. Exploring ways of empowering the Traditional Leaders to lead M4D type approaches in their own communities will go a long way to ensure sustainability of the approach (Post M4D).
6. DFID sector and service delivery programmes are very aware of M4D but coordination in Kano has been limited to using M4D structures as entry points to target groups (PERL/ECP, MAFITA). Coordination in Kaduna is even more limited, with only V4C reporting any practical points of collaboration. However, the programmes do not all work in the same LGAs and that can make collaboration more difficult.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2016 AR recommended a refinement of the output statement to “better-fit approaches to basic service delivery and accountability on targeted issues identified, developed, test and refined”. The logframe was amended accordingly.

Recommendations
R5. As with Output 1, the output indicator targets have been surpassed but there is no evidence that the programme will be able to make any claims of attribution at the outcome level. The current output/indicators should be reviewed for relevance to the final year of implementation.
R6. Local Government Reform is happening in Kaduna (and quickly) and there may be opportunities to support gaps and initiatives falling out of the comprehensive assessment being done. M4D is respected by state-level officials and should seek to influence the process at that level to increase the likelihood of lasting reform. This could be focus of the final year in Kaduna: how to support the reform process to ensure changes are understood, accepted and embedded.

Output Title	Better-fit approaches to basic service delivery and accountability on targeted issues identified, developed, tested and refined.
Output number per LF		Output 4	Output Score	A
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2016 Milestones	Progress
4.1. No. of basic service delivery BFAs initiated and tested	11	11 / Milestone target met. On track to achieve lifetime target
4.2. No. of accountability BFAs initiated and tested	5	5 / Milestone target met. On track to achieve lifetime target
4.3. No. of successful better-fit approaches	7	8 / Milestone target slightly exceeded. On track to achieve lifetime target.

Key Points
1. The better fit approaches (BFAs) are aimed at strengthening engagement and interaction between PM/SPs; with each BFA focusing on specific aspects, for example, participatory community Service Monitoring System (PCSMS) strengthens the ability of communities and excluded groups to make requests and report complaints which require a PM/SP response; phonics aims to stimulate better demand and generate responsiveness as government adopts appropriate approaches in education; work on sanitation provides space for citizen participation in service delivery and requires service providers to adopt and adhere to standards.
2. M4Ds better fit approaches exist across a broad range of sectors and issues, from education to agriculture as well as more specific direct accountability interventions. Some are genuinely innovative whilst others mirror approaches and interventions from sector programmes.
3. BFAs could be viewed as a testing ground for community demands and service delivery approaches which would be replicated if deemed as successful. It is important that they are seen as a tool rather than as an end in themselves (but at the same time the individual results for beneficiaries should not be neglected). There is also a risk (as evidenced by the way communities describe the benefits of BFA products) that the focus on these mini development interventions becomes the intervention itself and not the process by which the intervention is developed and supported.
4. The recent evaluation case study looking at BFAs generally found the better fit approaches to have been a success, noting that “it is evident that BFAs provide better, and in some cases innovative, solutions local problems … albeit in different ways” and “The implementation of BFAs has contributed to PMs and SPs increased responsiveness and accountability as a result of improved communication and transparency”. The evaluation highlighted concerns about sustainability, particularly given current funding constraints. The evaluation report also highlights potential issues around government ultimately relinquishing control where that would be required for a successful BFA.
5. There have been generally good examples of coordination of M4D with other sector programmes that were relevant whilst working on BFAs. However, cross sector coordination is an area where M4D could do more and which would make a great deal of sense.
6. There have been some examples of replication of M4D BFAs, for example with second chance education, but these are limited, at least partly due to resource issues as noted elsewhere.
7. There is generally a positive reaction from policy makers to the better fit approaches, with evidence that policy makers and service providers are positive about successful and innovative approaches. However, there may be an element in this enthusiasm due to the issues being addressed with little cost to the public purse and the fact that BFAs provide tangible outcomes that can boost PM/SP’s credibility, influence and visibility within the communities.

Summary of responses to issues raised in previous annual reviews (where relevant)
The MTR recommendation was to refine the BFA output statement to to read “better-fit approaches to basic service delivery and accountability on targeted issues identified, developed, test and refined”. This has been done. However, this review is of the view that the recommendation on knowledge management ‘Knowledge management capacity within the programme needs to be enhanced and linked more explicitly to communications and learning’ is of relevance to the BFAs. Programme’s response to the knowledge management recommendation focused mainly on its partner NGOs cross learning events; programme engagement with the media and its state level staff. As indicated in this year’s recommendations below, there is need for the programme to generate critical information on lessons coming from the development and implementation of the BFAs and its implications for future interventions for building collective action.

Recommendations
R7. M4D to focus on the process and sustainability of BFAs rather than generating more new interventions.
R8. M4D to support more varied approaches for the required support to sustain BFAs. This might mean looking directly to state level, or supporting CBOs to use developed skills to seek other sources of non-governmental funding.
R9. Alongside the overall recommendation to build the evidence base for M4D, relating to BFAs it is important to understand further the relationship between BFAs and other community demands, looking at the demonstration effect for the supply and demand accountability approach of M4D.
R10. M4D should conduct a realistic VfM assessment of BFAs. This should look at all inputs (M4D and others) and consider these in relation to services achieved. If possible this assessment should also look further towards other delivery approaches where similar interventions exist to derive a comparison of cost of delivery.
R11. M4D also needs to consider the implications of some of the BFAs as they are implemented – from the sector and service delivery perspective, to ensure that interventions are appropriate and being delivered well. For example, the demands that second chance education puts on teachers and school resources and the potential for this to implemented at scale needs to be considered. M4D needs to consider that schemes with M4D support behind them will carry significant weight and to be cognisant of what that means in terms of potential credibility and scrutiny.
R12. M4D to do more to support promotion, replication and scale up of better fit approaches, whilst considering the issue around relevance and replicability of the BFA.

Output Title	Lessons from M4D initiatives identified and effectively shared.
Output number per LF		Output 5	Output Score	A
Risk:		Minor - Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No but is a new output that replaced the earlier one	Impact weighting % revised since last AR?	No but is a new output that replaced the earlier one

Indicator(s)	Dec. 2016 Milestones	Progress
5.1. Number of M4D lessons shared through appropriate media channels and/or learning events	7	13 / Milestone exceeded. Lifetime target exceeded
5.2. Number of good practices replicated through advocacy, learning and dissemination activities	5	6 / Milestone exceeded and on track to achieve Lifetime target
5.3. Number of development partners with whom relevant lessons learned by M4D and its local partners have been shared	10	13 / Milestone exceeded and on track to achieve Lifetime target

Key Points
1. This output and indicator statements are new, developed to replace the former output 5 and its indicators based on MTR’s recommendation that “ ... a clear learning and dissemination strategy for the programme, including a distinct element aimed at encouraging scale up and roll out of the M4D approach to areas which have not directly benefited from M4D support that all output measures under Output 5 are revisited following the development of this strategy to ensure that they are reflective of planned activities, and the specific learning objectives identified”.
2. There has been a significant increase in the level and quality of media coverage of M4D supported governance related issues. The programme organized its first Annual Stakeholders’ Learning event (December, 2016) with partner CBOs, PMs and SPs from the 9 focal LGAs and appropriate state ministries and agencies across the 3 focal states. It used the forum to share lessons from Second Chance Education, Mobile Veterinary Services (MVS), Integrated Local Government Planning (ILGP) and PCSMS and achieve more coverage, understanding and interest about M4D initiatives
3. PM/SP indicated that M4D and its Partner NGOs’s advocacy and knowledge sharing efforts influenced them to accept, adopt and replicate M4D supported BFAs and approaches such as the Girls Second Chance Education, MVS, Open Budget Initiative (OBI) and SERVICOM.

Summary of responses to issues raised in previous annual reviews (where relevant)
MTR recommended the development of a dissemination strategy and revisit all output measures under Output 5 to ensure that they are reflective of planned activities, and the specific learning objectives identified. Output 5 has been reframed, with new indicators.

Recommendation
R13. It is not clear if the programme has responded to the Mid-term Review recommendation to develop a dissemination strategy. This recommendation needs to be carried forward.
R14. The programme should improve documentation and sharing of lessons coming from its interventions. It should focus on telling the overall M4D narrative using key evidences (human stories, audio/visual materials, issue briefs) to create awareness on and visibility for the lessons and promote replication of key interventions of the programme across non M4D supported LGAs and States.
R15. M4D should seek to demonstrate VfM of individual service delivery achievements from its interventions versus larger scale reforms; focussing on whether or not M4D approach is a good investment from a cost and sustainability point of view (i.e responding to the question: what is the M4D value added as opposed to doing this work in sectors?)

Output Title	Improvement in programme management and effective delivery built upon independent and credible evidence based approach to accountability and learning.
Output number per LF		Output 6	Output Score	B
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Dec. 2016 Milestone	Progress
6.1. Number of key information products delivered by IEM on agreed timeline and based on consultation with M4D implementers	Case study 4, 5 and 6 Annual Report	Case study 4 completed and draft report produced and shared by end of the year / Annual Report for 2016 produced
6.2. Number of quality Evidence and Learning workshops led by IEM to support reflection with DFID and M4D on results achieved and learning generated.	2	Not achieved; Following a red tag review (twice) of the IEM Evaluation design document from SEQAS; the IEM Steering committee advised to suspend further case studies until a revised design document is received.
6.3. Formative/summative evaluation/research questions identified and agreed with the ESC and addressed in four briefing documents	2	One evaluation question was identified and addressed through the BFA case study

Key Points
1. The independent evaluation of M4D has had a difficult history and the legacy of those challenges continues to present itself through the evaluation process. There have been some significant issues, such as the failure to conduct an adequate baseline household survey, that have challenged both the validity of the evaluation and the ability of M4D to establish an evidence base at outcome and impact level. Whilst many of the primary failings fall before this review period the fallout and implications continued to impact the evaluation during 2016 and has slowed delivery of important evidence and learning.
2. The IEM was due to carry our research into three further evaluation questions in 2016 and deliver information products and learning events to share the findings and lessons. However, due to a SEQAS review of evaluation products produced in 2015, including the household survey baseline study and three case studies, which raised serious concerns about the products themselves and the overall IEM design, a decision, was taken that these issues needed to be addressed before proceeding with the planned 2016 activities. Much of 2016 was taken up with the IEM Evaluation Steering Committee overseeing a process of the IEM responding to the concerns of SEQAS and producing new and revised documents – including a revised Evaluation Design Document, and case studies as well as synthesis reports.
3. It appears a viable way forward on the evaluation has now been agreed which should provide answers to the important evaluation questions about the validity of M4D’s approach and potential (though not quantified) impact. This includes the production of a fully revised evaluation design which will finally allow all parties (DFID, M4D and evaluators) to have a common understanding of the exact approach and deliverables. The approach and design of the evaluation, with a focus on qualitative research supported by mini-surveys seems appropriate to the evaluation of a programme such as M4D.
4. This year has seen the production of just one case study report (on better fit approaches). The majority of work on the evaluation has involved resolving past issues and preparing for future work (including readying for case studies 5 and 6). Overall, the slow progress on the evaluation has contributed to the challenge noted elsewhere through this review of being able to adequately tell the story of M4D. It should be expected that delivery of evaluation evidence and products should significantly ramp up in 2017. This is necessary to understand the effectiveness of M4D’s experimental approach.

Summary of responses to issues raised in previous annual reviews (where relevant)
There is an unresolved question about the measurement of M4D’s impact following the removal of a full household survey from the evaluation design. This needs to be addressed quickly. The most sensible approach would be to reconsider the impact level measures of M4D in light of the current evaluation work and to draw out suitable indicators that can be taken from that ongoing work.

The previous review recommendation on additional case studies has been addressed through the evaluation process considerations. The outcome of that process is that more case studies are not practical nor is it necessary for an effective evaluation.

Recommendations
R16. Move quickly to agree the final, full version of the evaluation design document
R17. Move forward with learning notes and other dissemination activities that have been delayed from 2016 to ensure that value from the evaluation is maximised.
R18. Resolve issues around M4D impact measurement, drawing out success criteria that can be checked from the evaluation work. This should be agreed alongside the final evaluation design.
R19. Continue to review evaluation activities to ensure that delivery of the evaluation work is being done on a timely basis.
R20. Consider the approach required for completion of any evaluation work required after M4D formal closure given that the IEM contract is a third party contractual arrangements with M4D.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Over the past two years, M4D has comprehensively reviewed and updated its value for money (VfM) framework. Last year, the project reviewed and assessed the project’s VfM framework, resulting in a proposal to reduce the total number of indicators from 50 to 20. The selected indicators provide coverage across the 4Es (economy, efficiency, effectiveness and equity).
The main cost drivers for the programme within the year is activities with output 2 (PWD CBOs and Platforms of girls organised, engaged and demanding equitable basic services and accountability) contributing the highest share to programme costs (Table 3). The programme recorded, as of February, 2017, a total expenditure of £3,673,429 against a projected budget of £4,287,978. This implies that M4D realised an 86% utilisation rate in the period under review (well below the expected utilisation rate of 90% by December 2016). Percentage split of expenditure per output in the year under review based on spend is shown below:
Breakdown of 2016 Programme Costs
	Jarawa	Kaduna	Kano	Project
Output 1	£ 229,895	£ 43,396	£ 194,620	£ 55,485
Output 2	£ 299,440	£ 197,803	£ 217,170	£ 745,079
Output 3	£ 97,959	£ 89,964	£ 70,750	£ 495,975
Output 4	£ 29,916	£ 4,818	£ 61,133	£ 89,982
Output 5	£ 25,986	£ 9,310	£ 23,172	£ 175,892
Admin	£ -	£ -	£ -	£ 348,801
IEM	£ -	£ -	£ -	£ 67,506
Milestone	£ -	£ -	£ -	£ 317,140
TOTAL	£ 683,195	£ 345,292	£ 566,845	£ 2,295,860

VfM performance compared to the original VfM proposition in the business case
M4D’s business case had no specific VFM indicators at design stage. This is due mainly to the innovative nature of the programme. However, it did provide a statement to guide VFM considerations: ‘evidence that it represents value for money can be determined by the extent to which the activity it funds enhances the accountability of governments to their people…. If the programme has no impact on strengthening empowerment and accountability in Nigeria then it would no longer represent value for money’. During the course of the programme, a number of VFM indicators were developed to determine the VFM of the programme.

There have been steady improvements in key areas of efficiency and effectiveness over the last two years. The average costs of establishing and supporting Programme Life Skills Clubs and testing service delivery and accountability BFAs decreased significantly. While the cost per CBO influence on policy makers and service providers has decreased, the costs of demands made and addressed remains high; and needs to be addressed going forward.

Life Skills Clubs: The average costs of establishing and supporting the programme’s Life Skills Clubs have decreased from £3,325 in 2014, to £1,682 in 2015 to £1,124 in 2016 (below Fig.1). While this decline is encouraging and shows enhanced value for money when compared to the start of the programme, further significant declines are not expected in the final eighteen months of the programme except in limited efficiency savings where possible. Decline in cost are attributed to a number of factors that include: (i) a review of the main cost drivers in 2014 that pointed to some possible areas of savings without compromising impact; (ii) pay-offs from early investments in standardised products such as development of the LSC Core Compendium which is now being used as a standardised resource across all LGAs; and, (iii) the benefits of achieving economies of scale throughout the programme. So far 366 Life Skills Clubs have been formed at a total cost of £2,243,784.96.

Fig. 1: Average Cost of Establishing a Life Skills Club

Organising and engaging: CDAS assessment provides an assessment of M4D partner CBOS against key capacity areas. In M4D’s VFM assessments, this indicator is used to measure progress made in ‘organising’ and ‘engaging’. A total of 12 PWD CBOs and Girl’s Platforms showed varying degrees of improvements with regards to key organisational capacities, and 18 with regards to engaging citizens and decision makers. While the average costs of improvements per PWD CBO and Girls Platform in organising show a considerable increase; the costs of improvements in engaging is within an acceptable range and has shown a significant improvements, (Fig 2a and 2b respectively). This may be due M4D’s recent efforts at institutionalising the programme supported initiatives through pieces of operational research and high level advocacy and policy engagements.

Figure 2a: Average cost per PWD CBO/Girls Platform of increasing CDAs/GP organising

Demands Logged: In 2016, total number of demands logged, rose from 214 to 402. Of the demands logged, 25% were from Girls Platforms or People with Disabilities (PWD). The Review notes that the programme has done very well in terms of reach and coverage of marginalised groups like People Living with Disabilities and Adolescent girls; and, Life skills clubs and second chance education models are being replicated in other local government areas by the government. The Review therefore concludes that programme is on track to achieving its objectives with regards to equity.

The MTR recommended that the average cost of demand addressed be developed to add depth to the VfM assessment offered around community demands. As this is the first year this VfM indicator is measured, a trend analyse is not feasible. 116 demands were addressed (25% of all demands logged) at a cost of £1,365.05.

Testing BFAs: The table 4 below shows the average annual cost of testing BFAs.

Average Cost to DFID per BFA
Year 1	£54,667
Year 2	£39,776
Year 3	£126,102
Year 4	£72,458

In 2016, the average cost of testing service delivery and accountability BFAs was £72,458. This figure is lower than the year before for two key reasons:
- Lower cost of selected BFAs - The Jolly Phonics BFA (November 2013 – December 2015) demonstrated the importance of low cost in determining whether and to what extent a BFA would be replicated. This is even more relevant in the current economic climate of Nigeria since June 2016.
- Leveraging of resources - a number of Year 4 BFAs were operated via cost-sharing agreements with local and state government, therefore reducing the overall cost to DFID although not necessarily the overall cost of the BFA.

The MTR shade light on the need to be aware of diversity of the BFAs and pursued the different levels of inputs required to get them fully operational and delivering the anticipated results (with the risk of loss of details of each component of a BFA in the calculated averages); hence, the need to track the cost of individual BFAs instead of the cost of all BFAs tested within the year. This recommendation has not been fully met; but efforts are being made to track reimbursable costs per BFA to better understand resources required for different BFAs.
Analysis of the new sets of indicators, completed for the first time in the year under review, shows strong performance across all four VFM areas (economy, efficiency, effectiveness and equity); and demonstrates that M4D is delivering good VFM over-all.
Quality of financial management
M4D tracks overall budget execution rate to ensure budget implementation is in line with programme progress and results. The programme underspent in 2015 (spent 49% of the budget as against the expected 60% spend through the contract). This gap has been narrowed and is now at 72% (spend through the project is expected to be 76%). This means the programme remains behind execution rate overall (Table 5).

Y1
Y2
Y3
Y4
TOTAL
TOTAL
TOTAL
TOTAL
Spend to Date
2,668,165

5,441,436

8,618,720

12,509,911.64

% of the overall budget spent
15%
31%
49%
72%
% of the way through the programme
26%
43%
60%
76%
% Variance
11%
12%
10%
4%

Quality of financial management dropped over the period preceding July 2016, but is steadily improving. This was due to a change in personnel, but the level of mentoring and support has paid off. A new system of invoicing was introduced during the year under review. This has been very useful as invoices are now easier to approve with clearer understanding and better articulation of reasons behind variances. The revision of workplans for the 2016/17 FY and subsequent reduction of the programme budget within the period to a realistic figure made it easier for performance to be monitored. Standard DFID procurement processes have been adhered to and Conflict of Interest issues highlighted, with mitigating actions put in place. Staffs are all aware of anti-corruption and fraud issues and their implications on the staff and the project. Programmes Assets have been well managed and are in good condition.

Palladium introduced a new Enterprise Resource Planning (ERP) system in the later part of last year; aimed at boosting financial capabilities of the programme. While any attempt at strengthening staff capabilities is applauded, the risks and impacts of this system on financial reporting to DFID were not initially foreseen. The new system did cause some concern for the programme and DFID as large numbers of invoices were accrued. This required tact and placed an unnecessary demand on DFID programme financial management team to resolve the issue and bring the financial systems on track; even then, tracking paid and unpaid invoices is still a challenge. It is hoped, as Palladium reflects on and addresses challenges around roll-out of the new systems, its effects will become easier to reconcile.

A financial audit for the programme was conducted during May and June 2017. The draft report shows that M4D need to improve their procedures in some areas (including invoicing and management of foreign exchange) to avoid errors that cost DFID money. It is recommended that DFID and Palladium discuss the full findings of the audit with a view to Palladium preparing an action plan to ensure issues raised in the report are fully addressed and lessons learned as needed across DFID-funded Palladium programmes.

The programme is in its final year of implementation. As such, it is perfectly right to expect staff migration. The review recommends Palladium takes steps to better manage its human resources as the programme moves into its final year of implementation in order to minimise disruptions to the programme delivery. This also includes the management of the relationship within the consortium.

Date of last narrative financial report	28 April 2017 for January – March 2017
Date of last audited annual statement	Palladium audited accounts dated 16 March 2017 for the year to 30 June 2016
Date of last DFID audit	Draft report received on 29 June (dated 30 May) for the period 30 October 2015 – 31 March 2017

E: RISK

Overall risk rating: Minor/Moderate/Major/Severe
M4D’s overall risk rating is Minor to Moderate - minor with the highest programmatic risk being that the Theory of Change (ToC) does not hold true and the programme does not achieve its outcome. This risk is reduced through strategic reviews of its systems, approaches and technical input from national and international specialists in social accountability.

Overview of programme risk
M4D has an established risk register, and reports on a regular basis against risks including at annual reviews. The risk matrix; guided by DFID’s risk management framework, categorises programmatic risks based on risk probability, its likely impact, mitigating measures and resultant residual risk across the programme (indicating the level of risks and where it fits within DFID’s risk appetite – as indicated in the risk framework).

Top three risks to the programme are: (i) Security and safety of operating environment due to proximity to conflict-affected states may threaten the programme’s ability to conduct activities. There has been violent clashes between herders and farmers; and the ongoing tension relating to the arrest and continued detention of the Nigerian Shia group leader are potential risk; (ii); Continuing weak capacity of CSOs and CBOs and their inability to become effective partners in the programme (iii) The innovative nature of the programme, both in programme approach and having a gender inclusion focus, means that risk is inherent to the design.

Mitigating actions are in place for all of the risks including (i) advocacy and constructive engagement with stakeholders that are likely to be opposed to interventions that promote social inclusion to change potential resistance into critical partnerships for a positive result; (ii) Ongoing situation analysis and timely adaptation based on outcome of security briefings and assessments; and (iii) implementing a robust monitoring system, including regular assessment of the extent to which approaches are contributing to expected programme outcome and to make course corrections.

There is a new risk -limited flow of resources from the state to local government level due to the current fiscal crunch in the country. This may results in failure of PMs/SPs to put into effect commitments to meet demands from citizens arising from programme activities. This in turn can result in “demand fatigue” on the part of CBOs who are demotivated from generating further demands, or, on occasion, are reluctant to engage in participatory processes, when demands and plans already submitted have not yet been met. These have now been framed as the top three programme risks for the next 15 months of implementation.

Outstanding actions from risk assessment
No outstanding actions from last annual review.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The Mid Term Review found that M4D had been able to reduce its variance during FY2015-16 and at the end of the financial year marginally missed the 5% target for annual budget variance; with a 6% underspend overall. Throughout FY2016-17, the project has underspent against the annual workplan; and as of end February 2017, the programme had an underspent of 14%.

Key reasons given for the variances in the costed workplan spend are:

1	Prior to the October workplan revision, Programme Activities was M4D’s largest driver of variance in the first two quarters. This variance was attributable to a number of factors, including delayed activities, restricted availability of stakeholders, and the devaluation of the NGN. The costed workplan was reviewed and revised significantly in October 2016. From this revision, variance was reduced to 2% overall, but the project acknowledges that this remains a budget focus for FY2017-18 to ensure the improvements in Programme Activities forecasting accuracy since October are maintained and strengthened.

2	Variance in the Personnel budget line was driven largely by ST Personnel. M4D did not commence STTA mobilisation as quickly as hoped, due to delays in finalising the contract amendment. Additionally a number of STTA assignments commenced in November and December, but deliverables were not completed and approved in time for payment by the end of the year, notably larger pieces of work in this category included the Kaduna Gender Policy Specialism, and the ARCS/CDAS work.

3	Throughout the year, the IEM has been a key driver of variance as the project has not fully resolved contract and delivery issues, although this looks to be resolved in early 2017.

Although the programme is slightly behind on spend, it is on track to meet current logframe targets. Additionally, despite underspend against the costed workplan this year, M4D has significantly increased spend in 2016 to narrow the budget execution rate. At the MTR point, M4D had by the end of December 2015 spent 49% of the budget, at a point when the programme was 59% of the way through the programme cycle. As at the end of December 2016, the programme has spent 72% of the budget, at a stage of 76% through the programme and so has closed the gap between programme delivery and budget execution. In 2016 the total spend on the project was £3,891,191.64 for the year and a total spend of £12,503,983.72 to date.

Performance of partnership(s)
M4D has a range of international and local partners directly involved in the programme. The lead partner, Palladium (formerly known as GRM International), works with ICF and ITAD on the strategic implementation of the programme. Palladium has developed new governance arrangements for the international partners to outline their continued involvement in the strategic direction of the programme and has restructured the Steering Committee membership to be limited to only consortium members and role to only focus on consortium related matters.
M4D has two national implementing partners – Centre for Development Research and Training (CDRT) and Youth Society for the Prevention of Infectious Diseases and Social Vices (YOSPIS). During the year under review, CDRT has continued to be involved in conducting progress perception surveys of CBOs and platforms including those of Girls and PWDs in M4D LGAs across the three programme states. YOSPIS continued to be involved as part of the team for the capacity re-assessments of partner CBOs and PM/SP organizations (LGs).
M4D continued to work closely with other appropriate state level DFID programmes, most notably Voices for Change (V4C), as well as State Partnership for Accountability, Responsiveness and Capability (SPARC) programme and State Accountability and Voice Initiative (SAVI), the three state level governance programmes (and began discussions with their new follow-on programmes – ARC and ECP) as well as GEMS3. This has enabled some synergies, particularly in the area of programme learning of good practices and complementarity in programming at the state level. The close working highlighted the potential synergies from more purposive collaboration and the need to ensure that collaborations are captured in logframes, for example in the process indicators as a way of incentivising such actions for programmes with the same donor(s).
Asset monitoring and control
In January 2016, the findings from a programme audit covering the 21 months between January 2014 to September 2015 were shared with M4D. The audit found that significant improvements in asset management had been demonstrated since the previous audit. Small amendments to the asset register and the processes for reporting stolen assets were recommended. M4D has continued to work on the asset register throughout 2016 to ensure completeness. The review assessed programme assets and is of the opinion that programme assets sighted were well taken care of and in good shape. However, the move to co-locate with the MNCH2 programme means that there are a large number of assets that were not in use at the time of the review. It is recommended that the programme makes a decision as to what it wants to do with assets that have not been put to use as soon as possible so that they do not go to waste in the event that they get soiled by rain or sunshine.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
M4D is implemented by a commercially contracted Service Provider (Palladium – formerly GRM). The programme and DFID has no financial or technical partnership agreement or programme with the Federal Government or state government of Nigeria. This is in line with DFID-N declared policy of no UK aid money going directly to the Government of Nigeria. The Supplier adheres to UK Aid money policy for Nigeria.

The M4D programme continued to contribute to strengthening the enabling environment for financial management and domestic accountability, primarily at the LGA level but with some reach to the State level. The PPA notes that these are important areas of work. Where there is commitment to and evidence of reform willingness, M4D engages selectively with Government at LGA and, to a much lesser degree, at State levels. For example the programme continued to make follow up with the Governor of Kaduna state, Nasir El-Rufai, who had previously shown interest in strengthening local governance in Kaduna State. Discussions are in progress with the State Bureau for Public Service Reform on how to jointly support the state government on the proposed LGA reforms. Equally, the Jigawa State Government through the State Deputy Governor has indicated interest in collaborating with the programme in the replication of Mobile Veterinary Service (MVS) BFA in all the 27 LGAs of the State and has already made provision for it in the approved 2017 state budget. Further, the Kano State Government through the state SERVICOM Directorate and Ministry for Local Government has commenced the replication of SERVICOM BFA in 6 non-M4D LGAs of the state with technical support from M4D. All these have provided an entry point for the M4D programme to build relationships and support implementation at LGA level. However, no programme money goes directly to any of the states, or to the individual Governor of the state.
In engaging with state level PM/SP for replication of M4D supported initiatives, it is recommended that M4D plans to enhance accountability through dialogue and due diligence in the selection of its partners; as well as demand for proper accounting of grant money disbursed to its grantees. Partners would be managed closely and would be required to submit monthly spends and activity reports. In addition, Partners would be incentivised through positive feedback and capacity building events to work together and/or share experiences. This active monitoring during Partner delivery is appreciated by Partners (as is currently done with the Grants programme) who say their management practices have improved as a result of the support received during monitoring sessions.

H: MONITORING & EVALUATION

Evidence and evaluation
As highlighted elsewhere in this review adequate generation of evidence and evaluation remains a key challenge for M4D. Whilst tools are in place for monitoring of attendance and capacity at community and policy maker level there remains an absence of an effective overall strategy for bringing this and other data together to tell the story of M4D, its achievements and it’s challenges. There is a significant body of information and data generated through the CDAS, CDAS+ and LiSCAS, along with the perception surveys but it is not clear that this data is being used fully. There is more that could be done with this data both to inform the overall picture of programme delivery but also to support that delivery and generate useful feedback.

The issues around the independent evaluation (noted under output six above) also contribute to the strategic issue of evidence collection and evaluation. Whilst the progress towards an effective evaluation is promising past issues mean that delivery of the objectives remain a concern.

Ultimately it will be a combination of work from the evaluators with work from M4D that gives the complete picture of what has been achieved through the M4D programme and the lessons that should be drawn for the future. This is an area of critical focus for M4D through the final year of implementation.

There also remain issues around the approach to measurement of beneficiary reach under M4D. It is likely that many of the more than 500,000 people noted as having benefited from M4D will have done so in only a very limited way. It would be useful to see more about in what way the beneficiaries have been reached and the type of benefit they have received via M4D.

Monitoring progress throughout the review period
This annual review involved extensive fieldwork and meetings with beneficiaries, and DFID has engaged with M4D activities through a range of visits and meetings throughout the year. Generally routine monitoring of the programme has been done well and none of the issues identified by this review has come as a complete surprise.
Feedback received from beneficiaries and stakeholders (community members, CBO members, traditional leaders and policy makers at local and state government levels) during the review process was almost universally positive with many requests for continued and expanded support. Beneficiaries were able to identify M4D supported areas unprompted and to recognise benefits that M4D had brought to their community or their work. It was clear from beneficiaries that M4D has worked in a way which ensured transparency and a good understanding of programme approach and work.
The Annual Review is an internal process conducted by DFID. The team comprised of a Social Development Adviser, Governance Adviser, Results and Statistics Adviser and a Programme Officer. The review included meetings with M4D Partner CBOs and the Programme Team in Kano, including a comprehensive presentation to the Review Team by the Programme Team. The Review Team met and consulted with a broad range of stakeholders, including service providers, policy makers and CBOs (including PWDs) and Girls Platforms as well as beneficiaries of M4D grants.