Evaluation Report Title: / Partner-Led Evaluation of the International Forestry Knowledge Programme / (KNOWFOR) 203034

Response to Evaluation Report (overarching narrative)
The International Forestry Knowledge Programme (KNOWFOR) provided policy makers and practitioners in developing countries and the international community with comparable evidence, reliable tools and systematic analysis on forests, trees and climate to help them make informed decisions and design better policies and interventions. DFID places strong emphasis on evidence based policy and programming so the knowledge generated from this programme has also been used across the forest portfolio of the UK International Climate fund (ICF). / The programme was delivered by three trusted partners that generate knowledge in the forest sector - The Centre for International Forestry Research (CIFOR)[1], The International Union for the Conservation of Nature[2] (IUCN) and the World Bank Programme on Forests (PROFOR)[3]. / The intention was to address gaps in knowledge and evidence, where knowledge was often fragmented and not reaching the right audiences in the right way at the right time. To close this gap, KNOWFOR built on existing research, generated new evidence and focused strongly on improving how partners designed, monitored, evaluated and learnt from knowledge by translating knowledge into use – known as the uptake pathway. / An evaluation was carried out in 2017. This was led by partners, with the participation of DFID, facilitation from Clear Horizon[4], and independent quality assurance from ODI. The purpose of the evaluation was organisational learning – for DFID and partners, and to fulfil accountability requirements; to demonstrate effectiveness and impact[5]. / The KNOWFOR simplified Theory of Change (ToC) set out in the business case holds true. / Deforestation is a major contributor to global greenhouse gas emissions. International efforts to reduce deforestation are gaining pace and with these efforts demand for high quality knowledge on what makes for effective forest polices is increasing; / The stock of knowledge and research on forests and land use is increasing but at present much of this knowledge is not effectively disseminated and so does not reach practitioners on the ground; / This intervention will improve the value and impact of forestry research by improving dissemination, knowledge pathways, and uptake; / Improved uptake of forestry knowledge will enable policy makers and practitioners to implement effective polices that quicken the pace by which deforestation is reduced. / The KNOWFOR programme approach is based on four assumptions of what is needed to create policy and practice change: user-focussed design and planning, engagement, adaptive management and collaboration. In the evaluation, the evidence was strongest for the first two programme assumptions. User-centred design using ToC and stakeholder analysis appears to have increased the likelihood of knowledge being used. Dialogue, engagement and the exchange of ideas and knowledge co-production with decision-makers played an important role in influencing policy and practice. Adaptive management was explicitly raised, particularly in relation to DFID. Other success factors included understanding the context, building trust, utilising champions, and being strategically opportunistic. These factors worked together in different contexts to trigger change and support the achievement of outcomes. / Because this was a highly participatory partner–led evaluation, with high levels of engagement from DFID and from an independent quality assurer, there is broad agreement with the findings and recommendations of the evaluation. / The final evaluation of KNOWFOR carried out in 2017[6] suggests that, overall; KNOWFOR played a modest but important role in influencing policies and practices which have the potential to lead to broader impacts on poverty reduction, biodiversity conservation, the protection of climate and other ecosystem services. / Policy and practice changes in forestry are influenced by many factors beyond knowledge. Attributing change to research and knowledge is therefore difficult. This is a challenge recognised by other DFID research, knowledge and influencing programmes such as The Climate Development Knowledge Network (CDKN)[7]. / Since the programme is now closed, future actions are focused on the partner’s further integrating the lessons and recommendations from the evaluation into their continuing work and for DFID, future actions focus on the dissemination of lessons learnt from the programme and the evaluation process. / For all recommendations addressed to the KNOWFOR partners, they have responded on an individual basis how they will take forward the recommendations within their respective organisations.
[1] https://www.cifor.org/
[2] https://www.iucn.org/theme/forests/our-work/forest-landscape-restoration and http://www.forestlandscaperestoration.org/
[3] https://www.profor.info/
[4] https://www.clearhorizon.com.au/ specialists in theory based approaches to evaluation, recruited to provide support to KNOWFOR partners on DMEL.
[5] Since evaluations of this type are rare in DFID, a paper on the partner led evaluation experience is under development - Partner-led evaluation for policy research programmes: A thought piece on the KNOWFOR programme evaluation - forthcoming
[6] https://devtracker.dfid.gov.uk/projects/GB-1-203034/documents (forthcoming Final Evaluation KNOWFOR Nov. 2017)
[7] Climate and Development Knowledge Network Year 7 Review, June 2017, IOD Park

Evaluation Report Title: Partner-Led Evaluation of the International Forestry Knowledge Programme (KNOWFOR)

Recommendations (targeted at programme partners)	Accepted or Rejected			If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
Recommendation 1: / Each partner organisation could benefit by refining their ToC and knowledge uptake strategies to take better account of the success factors identified through KNOWFOR, which were specific to each partner. These partner-specific factors should be tested progressively over time to enhance the effectiveness of knowledge programming practices. This may involve further consideration of the knowledge-to-action literature, which provides a rich body of existing knowledge on this topic.	Accepted			PROFOR: As part of its early actions on Knowledge Management (KM), PROFOR has organized one-on-one discussions with the Bank Task Team Leaders (TTLs) on developing a ToC and a log-frame. As a result, all the forest-smart programmes supported by PROFOR (agriculture, mining, energy, land-tenure, etc.), under implementation, have well- articulated Theories of Change (TOCs) and log-frames embedded into these programmes. / PROFOR has put central importance on mainstreaming the ToC among, staff of the Country Management Units, and staff of the PROFOR Secretariat. These actions will be continued in the Phase I of the KM strategy, which is being rolled out over the next year. Training material will be prepared, change agents identified, and customized workshops, clinics, knowledge fairs, etc., organized to sensitize the target audience. To improve uptake of ToC, various incentives will be offered, such as the availability of a dedicated KM budget and recognition of “KM-ToC citizens”. / Additionally, this KM strategy will help improve targeting of policy makers and practitioners and get PROFOR products into the hands of decision makers, who can influence change. That effort applies to PROFOR's existing library of tools and analytical reports, as well as to new knowledge products. / CIFOR has an on-going research collaboration with Royal Roads University designed specifically to enhance the theoretical grounding of their theories of change (at the institutional and project level) and conduct rigorous cross-case analysis of specific change theories commonly applied in research for development. / IUCN: Knowledge uptake is an iterative, dynamic, and complex process. Hence, IUCN follows a learning through doing approach to test, analyze and learn from various approaches to support programmeme design, strategy, implementation, evaluation and impact assessment. Several important lessons from the KNOWFOR programmeme have already been integrated into the design of new projects (such as a clear and distinct focus on planning for, and monitoring and learning from knowledge uptake among target audiences). Also, in a recently completed evaluation of a 5-country DANIDA Pro-Poor REDD+ programme (use of light touch, country-level episode studies complemented by an overarching global evaluation).
Recommendation 2: / Partner Design Monitoring Evaluation and Learning (DMEL) leads should continue to support and encourage the use of Theory of Change (ToC) as a Design, Monitoring, Evaluation and Learning (DMEL) tool in their respective organisations to maximise the effectiveness of programming. Appropriate incentives and support should be offered to encourage its use. Despite progress and considerable interest from partners in ToC as a DMEL tool, there was limited evidence that they used it in the case studies developed for this evaluation.	Accept			PROFOR: As Above / CIFOR is committed institutionally and through the CGIAR to the use of theory of change as a framework to guide design, monitoring and evaluations. CIFOR has a suite of evaluation case studies (seven in total) that use theory of change as a guiding framework and our ability to apply this tool and analyse findings in a sophisticated way is improving over time. / IUCN’s Programmeme Guidance and Standards (PGS) and Project Appraisal and Approval System (PAAS) mandate for and provide guidance on the use of TOC in the design and implementation of all IUCN projects. We agree that ToC provides a means by which our intervention and change process can be better measured and articulated. It is also important to recognize that often the policy contexts in which we operate are shaped by a multitude of interacting forces and actors and hence are highly complex. We are actively exploring ways to integrate TOC into our work better, and have submitted a journal paper for consideration, titled “Using theory of change to improve the evaluation of policy influence” based on our experience of using TOC in the KNOWFOR programmeme.
Recommendation 3: / Partners should continue to contribute to the Gender Working Group. The group should continue to explore ways to better integrate gender into the knowledge programming cycle and DMEL. In particular, the group has the opportunity to provide an important cross-institutional link and forum for partners to continue to learn from one another. Gender Working Group members should explore opportunities to sustain and resource this valuable partnership so it can continue to provide benefits	Accept			Whilst all partners agree in principal that they wish to continue collaboration on Gender – this will depend to some extent on finding available resources to co-generate information and share findings. Gender has however become much more clearly defined as a priority area within each partner/s systems. / The PROFOR Gender Advisor has been in regular discussions with her counterparts in IUCN and CIFOR. A source of funding, to support future collaboration among the partners, is being explored / CIFOR welcomes this recommendation and notes that clear plans are already in place for on-going collaboration, focusing specifically on gender and forest landscape restoration. Collectively the gender working group are seeking to influence how gender is integrated into the planning and implementation of national FLR pledges and reflected within international agreements. They are working to identify good practices where they exist and forming consensus on the way forward amongst relevant stakeholders. / IUCN engaged with the other KNOWFOR partners to create a Gender Working Group (GWG) and continue facilitation through 2017. This has promoted and strengthened the KNOWFOR actions and results broadly, but also particularly on gender, among the partners by informing and collaborating in various aspects. IUCN’s Global Gender Office (GGO) will continue to engage and work with GWG partners beyond KNOWFOR.
Recommendation 4; / Efforts to monitor and evaluate gender in knowledge programming by all partners should shift from a focus on output (i.e. participation) to a focus on impact (i.e. on the lives of men, women and girls as well as on systems and institutions). A good place to start is by clarifying gender standards and expectations for knowledge programming. This could be progressed by the Gender Working Group in consultation with the DMEL leads from all three partner organisations. In particular, PROFOR should continue to improve its gender monitoring systems. KNOWFOR gender monitoring findings indicate the need to increase the participation of women and girls in PROFOR programming, both as participants and users of PROFOR communications.	Acceptance but with qualification from PROFOR.			PROFOR aims to build further on this up-trend and raise the target to 25% or higher. Thus, to assist the inclusion of gender analysis and gender transformative actions in PROFOR supported activities, guidance notes and tools are being developed. / The information available to date can be accessed on the PROFOR gender page: / http://www.profor.info/knowledge/catalyzing-gender-forests-actions. / Training workshops are being organized to help TTLs and Country Management Units better understand the gender gaps, actions, and ways to monitor change. The first of these was held for country audiences of the Forest investment Programme and Forest Carbon Partnership Facility in October. / The systems and guidance that PROFOR has set in place to improve gender focus, will require time for their uptake. Thus, improvements can be expected to fully manifest themselves in 1-2 years. / CIFOR welcomes and endorses the recommendation to focus on outcome and impact level monitoring of gender work, as well as the call to link this with clear process indicators and quality criteria. This is an agenda that the gender working group in committed to progress in the shared area of gender integration in FLR and that CIFOR will continue to invest in institutionally through the Gender Equity in Research Scale (GEIRS). / IUCN’s Global Gender Office (GGO) is continually addressing this issue.
Recommendation 5: / All partners need to conduct further work to consolidate and extend DMEL across their organisations, especially monitoring tools and capacity. All partner organisations should continue to invest in their approach to monitoring and to ensure that the organisational enablers of DMEL (such as resourcing and structures) are in place. In particular, the IUCN Global Forests Climate Change Programme (GFCCP) M&E team should continue to interface with M&E teams in other parts of the organisation to build the consistency of M&E across the organisation.	Accept			PROFOR has been working closely with the M&E expert for the Environmental and Natural Resource Global Practice (GP). This has led to a healthy two-way interaction, with PROFOR’s influence being transmitted to M&E practices in other programmes in the GP, and, in turn, PROFOR learning from other programmes PROFOR expects that this two-way influence will be strengthened through the implementation of its KM strategy. / CIFOR will continue to invest in and support DMEL. In coming years this will focus largely on deliberately integrating the approaches and principles refined during KNOWFOR into large project grants to ensure alignment with institutional and FTA planning, monitoring and learning strategies. The recommendation correctly identifies that strengthening the systematic use of monitoring tools is our highest priority in improving our practice in this area. / IUCN: KNOWFOR has been successful in catalyzing a change in IUCN’s GFCCP DMEL approach, and it has also influenced our global, regional and national programme. In the past two years, significant effort has been made including enhanced financial support to integrate use of ToC and enhanced DMEL requirements at the very early stage in various projects across the IUCN Secretariat.
Recommendation 6 / All partners need to improve the way they track audiences and reach – especially when using social media. Tracking segmented audience penetration through web-based engagement and social media was not achieved because monitoring systems did not support audience identification. This should be done by DMEL leads in close cooperation with their respective media teams, who bring valuable expertise in communications tracking and outreach.	Accept with some challenge from IUCN and CIFOR			The PROFOR Communications Team will explore the feasibility of applying monitoring systems which allow for audience identification. PROFOR will also look into including a window to ask the reason for downloads to have better understanding of who is using PROFOR’s knowledge products. / CIFOR acknowledges the benefits of tracking segmented audience participation and already has tools in place to do this for key internal, online knowledge dissemination platforms (Forest News audience and paywall surveys). As CIFOR consolidates its communications and outreach approach to focus on communication strategies crafted around specific, known audiences and an understanding of how these groups receive information, the importance of tracking generic social media statistics will decline. CIFOR’s engagement with knowledge uptake literature has driven a move towards greater engagement with audiences across the research cycle, a focus on co-production of knowledge and provision of ‘just in time’ resources and advice as key knowledge dissemination strategies. The principle of enhancing what we know about how these key audiences are receiving and integrating knowledge is important, however social media monitoring will provide only limited insights into this given CIFOR’s emerging approaches. / IUCN recognizes the need to improve the monitoring of online knowledge uptake by target audiences. IUCN is actively exploring the use of Altmetrics, Kudos, and other enhanced online audience engagement identification tools to achieve this objective. / This recommendation is context specific however, and while IUCN agrees on the need for tracking audience and reach, they are unclear about the conclusion that it was not achieved under the programme, just because monitoring systems did not support audience identification. IUCN’s work on knowledge uptake was more focused on direct engagement with key stakeholders and use of social media, while useful was limited in the early stages of the programme. IUCN did strengthen its social media presence and tracking in the later stage of the programme.
Recommendation 7: / Each partner and DFID could benefit from conducting further work to assess the value for money (VFM) of research-to-knowledge programmes more comprehensively. The VFM case studies tentatively uncovered a high rate of return. Partners should further verify these rate of return claims where possible.		Acceptance but with some qualification from PROFOR	VfM studies are expensive and are of limited use as a diagnostic for programme improvement; because they involve large numbers of (contestable) assumptions. / PROFOR will undertake VfM studies in the future, strategically, when we think that they can be prepared with few assumptions, and can be completed with marginal incremental effort. We will consider including a question in PROFOR’s progress and completion reports that TTLs could respond to, on the feasibility of conducting a VfM study for their activity. / CIFOR is progressing work to assess our value for money. The Research to Impact team is already leading some work exploring new approaches to assessing the return on investment from our research. This work to establish the value for money of investment in research for development is being complemented by ongoing institutional efforts to reduce operating costs. / IUCN: VFM methodologies for research to knowledge programmes, like KNOWFOR, are an emerging field. There is need for further work on improving the methodologies and verifying the results. IUCN commissioned work on this that far exceeded what had been asked of KNOWFOR partners. A peer-reviewed publication is planned in early 2018 on Guatemala FLR Value for Money assessment. A new VfM assessment, of IUCN’s contribution to El Salvador’s forest landscape restoration processes, is currently underway and funded by USAID. It builds on the experience and lessons learned from the Guatemala VfM assessment and should be completed in Q1 2018. A VfM assessment component has been built into a new SIDA marine plastic pollution programme, the IUCN-led GEF-supported The Restoration Initiative (TRI), and the methodology has been integrated into the design of a study of policy and institutional impacts in Latin America related to forest landscape restoration.
Recommendation 8: / All partners should promote opportunities to learn from failure and be more open about what did not work. It was not always possible to discuss failure openly in cross-partner forums because of the competitive nature of the relationship between partners. However, there is further potential to do this more within each partner organisation. DMEL leads in each organisation in conjunction with their executives should encourage more opportunities to share instances of failure to promote a deeper level of learning that has the potential to accelerate programme effectiveness		Accept	PROFOR will look into organizing mid-term and final assessment workshops to maximize the learning from various activities. / CIFOR: In response to researcher demand, CIFOR has implemented a ‘learning from failure’ reflection process to balance the success-factors focused outcome story monitoring tool. A number of research teams have already volunteered to document their experiences for internal discussion and reflection. We acknowledge that internal funding competition and a climate of increasing donor accountability have made candid discussions of this challenging. We are optimistic that our new leadership’s focus on internal collaboration and commitment to fostering open internal dialogue will continue to encourage reflective practice within our research portfolio. / IUCN: Failures can happen in complex knowledge to research programmes. Learning from failures is anything but straightforward. There is need for change in attitudes and incentives both from the donor side and from our organizations to move beyond the lessons learned approach. IUCN has integrated a specific “notable failures, and lessons learned” section into its new 4-year institutional reporting framework for donors and Council, to be rolled out in 2018. IUCN will work to ensure that this important culture change takes root.
Recommendations (targeted at DFID)		Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
Recommendation 9: / The KNOWFOR approach to programme planning and management is an exemplar for how to adaptively manage a complex programme. This includes the DFID Rapid Response Mechanism that was part of the design as well as the flexible management approach. This is important for DFID as it represents a move towards management by outcomes and a greater focus on learning. The KNOWFOR approach to adaptive management and co-learning between implementers and the donor should be considered in the design of other similar programmes. Learning and reflection from adaptive learning in the programme should be shared by the DFID SRO across sectors (among forests, land use and climate change specialists) and thematically (with those working in the knowledge uptake space).		Accept	A number of knowledge products to share the learning from KNOWFOR have been prepared including a you tube video and slide pack and a think piece on the partner led evaluation https://www.youtube.com/watch?v=I6-RtRvSe0c / https://www.odi.org/publications/11016-partner-led-evaluation-policy-research-programmemes-thought-piece-knowfor-programmeme-evaluation / Recommendations for future design are noted and will be communicated with the Better Delivery team by the SRO by June 2018. / Departmental dissemination of findings within the International Climate Finance Team (across Whitehall). / Explore the use of Yammer groups for internal dissemination within DFID
Recommendation 10: / DFID should continue to endorse the use of ToC in knowledge programming. The KNOWFOR approach to ToC and user-centred design is of direct relevance to other knowledge uptake programmes more broadly.		Accept	Theory of Change is commonplace across DFID programme design and all aspects of management.
Recommendation 11: / When DFID invests in future knowledge programmes such as KNOWFOR, it needs to better pitch performance targets. Without appropriate targets, it is difficult to judge the effectiveness of programmes like KNOWFOR. The initial design of KNOWFOR did not provide a basis for the development or measurement of meaningful performance indicators, largely because intermediate outcomes between outputs and impact were not made explicit		Accept	The design implications are noted for future programming
Recommendation 12: / DFID should ensure that future programmes do not expect large global players to collaborate in core programming without careful consideration of the costs and likely benefits of doing so; and, if pursued, this needs to be incentivised. However, there is clear merit in bringing communities of practice together to develop shared knowledge on good practice process, in particular around ToC, DMEL, user-centred approaches to knowledge programming, and gender. DFID should be more explicit in articulating expectations for partnership at the outset.		Accept	The design implications are noted for future programming
Recommendation 13: / The evaluation methodology is of interest to a wider audience and should be shared. The quality assurers will conduct an evaluation of this evaluation. Following this, the M&E contractor/quality assurers should write an accessible practice note about the evaluation process itself. This could be presented at the UK Evaluation Society Conference in 2018, as well as through a seminar for DFID partners.		Accept	This is underway and an abstract has been accepted for presentation at the UK Evaluation society Conference 2018 / The issue of lack of independence and selection bias in a partner-led evaluation and how this can be mitigated is a key one. There are lessons to be learnt from the KNOWFOR experience.
Recommendation 14: / An accessible paper/think piece should be written on the management approach taken in KNOWFOR, recognising the importance of the factors unique to KNOWFOR which enabled programme flexibility, such as the role of the SRO in facilitating flexibility. This should potentially be led by partners and the SRO, who really led this partnership.			This has been written and is available to view here : https://www.odi.org/publications/11016-partner-led-evaluation-policy-research-programmemes-thought-piece-knowfor-programmeme-evaluation