Annual Review - Summary Sheet

Title: Private Sector Development in DRC
Programme Value: £102.5m		Review Date: March 2018
Programme Code: 203161	Start Date: 27/1/2012	End Date: 30/9/2024

Summary of Programme Performance

Year (that review was undertaken)	2013*	2014**	2015	2016	2017	2018	2019
Programme Score	A	A	B	B	A	A
Risk Rating	Major	Major	Major	Major	Major	Major

* This was a review undertaken in 2013 of initial progress during the inception phase.
** This was a review in 2014 of inception phase performance in 2013.
Summary of progress, lessons learnt and action on previous recommendations
ELAN scores an A+ not only because it exceeds expectations on almost all its delivery against output and outcome milestones but also because there is clear evidence that these changes appear to generate impact-level results at a scale consistent with the project’s founding vision. For instance, the average Net Attributable Income Change (NAIC) per beneficiary exceeded £30 for the first time in 2017. Strong performance against targets at output level and, increasingly, also at outcome and impact level reflects the fact that pilot interventions often need some time to generate and accumulate results. The dramatic acceleration of higher level results in 2017 reflects the ability of pilots to scale up.
Essor scores a B despite scoring relatively well against the intermediate outcome and some output indicators. This is because, the majority of the project’s workstreams did not perform well in 2017 – out of 7 workstreams which comprised the opening portfolio in 2017, only two have been functioning well – Organisation of harmonization of business law in Africa (OHADA) and Access to Energy (A2E) and one partially - Access to Finance (A2F). Whilst it is true that DRC is a challenging environment and OHADA is a particularly large workstream in the Essor portfolio, to have 2½ effective workstreams out of seven is some way below expectations. In order to ensure improved performance and value for money ESSOR will go on a performance improvement plan (PIP).
The Decision Support Unit (DSU) scores an A. Although delivery in the first quarter of the year was below standard, it has improved significantly since then. Following the previous Annual Review (AR), a PIP was agreed between DFID and the DSU to address performance issues in 2016 and the first quarter of 2017. The DSU took DFID’s feedback on board and improved performance in the last three quarters of the year. The DSU delivered the verification reports, which had some challenges. The DSU’s report captured lessons learned and provided recommendations for the next verification report. The other most significant deliverable of the DSU was the Mid Term Evaluation (MTE), which was delivered on time and was given a “good” rating by the Evaluation Quality and Assurance and Learning Service (EQUALS) reviewers. The tone of the MTE was sometimes not very helpful and diverted effort that could have been used to discuss important recommendations in the report itself.
Summary of response to recommendations of previous annual review
More details on the recommendations can be found in annex I.
ELAN has been highly responsive to the recommendations of the 2017 AR, with 4 out of 6 completed and 2 showing significant progress.
Essor has been less effective in implementing the recommendations of the 2017 AR. Only two of the 14 recommendations have been completed with significant progress in another three. Essor, at the behest of DFID, has been effective at closing workstreams, developing the MRM system, revising the logframe and drafting a much-improved Annual Report.
The DSU has been responsive to the recommendations of the 2017 AR, with increased use of regional and Kinshasa based consultants who have been of high quality.

Summary of recommendations for 2018

Elan
The main recommendations for Elan relate to learning from (and sharing) the strong progress made to date, and where there is a trade-off between achieving sustainable market system change and achieving NAIC targets the latter should be reduced. DSU and ÉLAN should determine the ‘good enough’ quality threshold and ensure that ÉLAN’s MRM achieves this in 2018. There should also be greater attention to ensuring the longer-term impact of ÉLAN is appropriately captured and documented. There is also a strong VFM argument to continued investment from DFID to support market development within the DRC, as well as options to support ‘Markets in Crisis’, which looks to limit the damage and harness the opportunities for market systems change where there are heavy flows of humanitarian aid.

Essor
Main recommendation is to scale Essor down to a couple of effective workstreams. The programme will need better value for money by focusing on workstreams that deliver benefits, whilst reducing cross-cutting management costs. The project should also respond to recommendations for improvement.

OHADA should continue in its current direction but its impact should be more rigorously monitored.
A2E, a high risk - high potential workstream, should also continue its current intervention. It should select investors and fully package the solar projects before December 2019. The A2F inclusive insurance intervention should be closed.

Decision Support Unit (DSU)
2018 will be very important for the DSU as it takes its full responsibilities on learning and improving. This will include research, learning workshops, following through recommendations from the MTE, results verification, and support to DFID’s future direction in private sector development. The DSU should put efforts to improve its relationship and the collaboration with both Elan and Essor. This includes, but not limited to, constructive criticism and strategic discussions on learning and adapting.

A. INTRODUCTION & CONTEXT

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203161/documents
DevTracker Link to Logframe:	http://iati.dfid.gov.uk/iati_documents/5673144.XLSX

Outline of the programme

The Business Case (BC) was written on the basis that recovery of the private sector in DRC would generate vested interests in peace, expand the economic choices of women and shift political economy forces in favour of a more representative and responsive state. To date, this recovery has been hamstrung by overlapping market, government, and co-ordination failures, DFID identified four key pillars to address: Market Development, Business Environment, Corruption and Access to Finance.
Developments in the years immediately preceding and following the launch of the programme did justify some cautious optimism with high economic growth rates and some evidence of high-level political impetus on business environment reform. In 2012 in particular, DRC acceded to the OHADA organisation – a comprehensive system of harmonised business laws and institutions adopted by 17 Francophone African countries to improve legal certainty for businesses. Since 2016, however, economic and political challenges have increased, leading to falling growth and investment.
The PSD programme is currently structured around the following three components:
Market Development - ELAN: A £50m project, managed by Adam Smith International (ASI). This is a Making Markets Work for the Poor (M4P) project to stimulate income change of £88m for 1m producers by 2020 by working through the private sector to address systemic constraints preventing the poor from participating in, and benefitting from, the market. Interventions have been framed around four market functions (Agro-Inputs/Extension, Market Linkages, Business Enabling Environment and Access to finance) under six Workstreams (Agriculture: Perennial, Agriculture: Non-Perennial, Renewable Energy, Branchless Banking, SME Finance and River Transport).
Business Environment Reform/Anti-Corruption - Essor: A £35m Flexible Facility managed by PricewaterhouseCoopers (PwC) in consortium with Landell Mills, DAI, Integrity Action, and Market Share Associates. This programme is managed in close collaboration with GoDRC to support, on an as-needed basis, reforms to improve the business environment, tackle corruption and improve the architecture of the Congolese financial system. Interventions are currently framed around seven workstreams notably: OHADA, Anti-Corruption, Access to Finance, and Access to Electricity.
Decision Support Unit: A £3.48m component designed to provide ongoing performance assessment of implementing partners (reviews, results verification and evaluations), contextual analysis and support to internal programme learning and external communications. This project started in August 2016 and will run for seven years. It is managed by Oxford Policy Management Ltd (OPM).
The original BC envisaged an Access to Finance component, as a £10m contribution to a multi-donor development capital project (known as the FPM) providing access to finance through the Congolese banking sector for around 100,000 micro, and small to medium sized enterprises (MSMEs). Subsequent changes to DFID rules on investments meant it was not possible for a country office to do this. An agreement to instead provide a grant to KfW to invest further in FPM fell through when KfW had a change of strategy for DRC. In the Portfolio Quality Review of 2016 DFID DRC gave up this component, but both Elan and Essor work on financial inclusion issues.
Changes to context since the last review
In the past year the political and economic context in the DRC worsened somewhat. Elections originally scheduled for the end of 2016 and at that point postponed to late 2017 did not take place and are now scheduled for late 2018. Opposition to the continuation in power of the current regime is fragmented and has been heavily suppressed, but remains significant. Violence has increased in various parts of the country, including in the Kasais, the Kivus and Katanga. The previously stable Kasai region is now dealing with one of the world’s largest humanitarian crises, with severe problems of food insecurity and internal displacement. The national currency experienced very fast depreciation in the first half of 2017 losing about half its value in 6 months, before stabilising from July onwards. Already weak Public Financial Management systems within government largely collapsed during 2017 with no government spending following the legislated checks and balances. Political uncertainty and the apparent short-term focus of the government would appear to be contributing to reductions in private sector investment.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

Impact: Reduced poverty through (enabling) improved incomes of the poor		2016		2017
		Planned	Achieved	Planned	Achieved
Indicator 1: (Elan and indirect for Essor) Cumulative aggregate net attributable income change (NAIC) (£) among poor producers and entrepreneurs	Total	£6,450,000	£4,956,481	£18,253,150	£18,265,844[1]
	Women	£1,225,500	£1,499,206	£3,354,273	£5,005,411[2]
Indicator 2 (Elan): Outreach: cumulative number of poor people who have experienced net positive income change as a result of programme support	Total	130,000	148,512	373,469	400,660
	Women	24,700	50,314	82,163	124,054
Indicator 3: (Essor) Cumulative number of companies experiencing net positive income change as a result of Essor-supported business environment reforms, disaggregated to show cumulative number of MSMEs.	Total	N/A	N/A	3,500	10,815
	MSMEs	N/A	N/A	1,200	N/A
[1] £16,219,263 for ELAN; £2,046,581 for Essor.
[2] This achievement is only estimated from ELAN’s disaggregation of its results. Essor NAIC estimations are not disaggregated.

Outcome: The performance and position of poor people within selected market systems is substantially improved		2016		2017
		Planned	Achieved	Planned	Achieved
Indicator 1 (Elan): Performance: cumulative number of poor people who report a substantial increase in enterprise or household performance as a result of market system changes supported by the programme	Total	195,000	218,647	560,204	466,599
	Women	48,750	76,271	140,051	146,241
Indicator 2 (Elan): Cumulative number of poor women showing a progression in their role within the targeted market systems.	Total	6,175	6,700	20,541	17,803
Indicator 3 (Essor): Cumulative number of procedural changes, additions, or removals that reduce time and/or costs for MSMEs and that are supported by Essor	Total	N/A	N/A	3	2
Indicator 4 (Essor): Cumulative number of BER policy / regulatory / legislative / administrative changes made or prevented that directly benefit businesses and that are supported by Essor	Total	N/A	N/A	4	4
Indicator 5 (Essor): % of businesses in areas and sectors targeted by Essor reporting an improvement in the business environment	Total	N/A	N/A	25%	N/A

ELAN
Impact level
The project has progressed significantly during 2017 There is growing evidence and momentum around changes as the project has considerably expanded its partner base during 2017, with a large number of market actors taking up pro-poor innovations and investing in these innovations. ÉLAN has generated results which fully meet two of the three impact-level results that DFID has identified. The failure to reach the aggregate cumulative NAIC figure reflects a legacy of the shortfall in 2016 more than any weakness in performance during 2017.
Outcome level
There is robust performance at outcome level. ÉLAN is within sight of the ‘increase in enterprise performance’ and women’s economic empowerment (WEE) indicator. And, interestingly, has exceeded the market system change indicator.
ESSOR
Impact level
Workstream-specific impact modelling has been carried out across the Essor portfolio. This is a helpful exercise, but now needs significantly more attention to improve its validity noting some methodological weaknesses and issues with the plausibility of the underpinning results chains. The project needs to more clearly document what the overall benefits it expects its interventions to achieve are alongside compelling logic as to why and how such benefits could be achieved.

Outcome level

For Essor the project has not achieved its Outcome targets, taking into account the DSU’s and DFID’s revision of the results that were reported by the project. For indicator 3, the DSU’s assessment is that only two achievements of the nine reported by Essor can definitely be considered an Outcome result (as per DFID SMART Guide definitions). These relate to OHADA. AC results should be revised to an Intermediate Indicator until the project shows evidence that the change has resulted in procedural change of the agencies (either the declaration has been turned into a regulation or directive from the relevant agencies, or there is evidence that the practice has changed- as per the definition of the Logframe indicator).

For indicator 4 the reported achievement is 4 (all from the OHADA workstream) were deemed to have met the logframe indicator criteria which aims to capture change that directly benefits business. If a change has been introduced but not implemented, it does not seem possible that it could directly benefit business or represent behavioural change by beneficiaries.

For indicator 5 the data reported did not meet the high thresholds for acceptance as a result.

Has the logframe been updated since the last review?
Yes the logframe has been updated to incorporate changes to the ELAN, Essor and DSU logframes. The changes to the ELAN logframe were relatively minor, with just two indicators (Outputs 1.1.2 and 1.1.4) updating their wording. The Essor logframe was completely re-developed following the recommendations of the 2017 Annual Review. [3] And the DSU logframe was finalised and approved in late 2017. Logframe indicators for all components are included in the updated overall PSD logframe.
[3] The DSU spent ten days of staff time advising Essor on the protracted revision of the log-frame throughout 2017. This advice consisted of two main areas. First, to encourage the project to articulate its overall goals and theory of change more clearly. Second, to articulate the indicators more precisely. The DSU largely failed to gain traction in the first task. In the second, the DSU was able to engage more productively with Essor staff and so improve the quality of indicators somewhat. For the avoidance of doubt, the DSU had no role to approve the revised logframe (DFID has this responsibility) and neither did it endorse either the final choice of indicators or the means of verification
C: DETAILED OUTPUT SCORING

Aggregate output score

Aggregate component score
Component	Weight	Score	Explanation
Component 1 (Elan)	50%	A+	Moderately Exceeded Expectations
Component 2 (Essor)	40%	B	Moderately Did Not Meet Expectations
Component 3 (DSU)	10%	A	Met Expectations
Total	100%	A

Component 1: Market Development (ELAN) (50%)
Aggregate output score and description

	Weight	Score	Explanation
Output 1.1	45%	A++	Substantially Exceeded Expectations
Output 1.2	40%	A	Met Expectations
Output 1.3	15%	A+	Moderately Exceeded Expectations
	Output Score	A+	Moderately Exceeded Expectations

The overall output score is A+: outputs exceeding expectation. Output indicators across the three outputs generally exceeded or substantially exceeded the milestones for 2017 (apart from two indicators; one that matched the milestone and one that fell marginally below its target). Risk ratings for outputs did not change and neither did their risk weightings since the last AR. Impact weightings also did not change.

Output Title	Innovation: Partner market actors have successfully taken up pro-poor innovations and have invested in order to sustain these innovations independently of programme support (Adopt, Adapt)
Output number per LF		Output 1.1	Output Score	A++
Risk:		Moderate	Impact weighting (%):	45%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator		2014	2015	2016	2017
1.1.1 Cumulative number of programme partners who have invested resources in an initial pro-poor innovation as a result of direct support from the programme and intend to sustain this investment	Planned	0	5	35	75
	Achieved	0	25	65[4]	99[5]
1.1.2 Cumulative number of programme partners who continue to independently pursue activities which support the initial pro-poor innovation/change after the initial pilot has ended	Planned	0	0	1	9
	Achieved	0	0	7	11
1.1.3 Cumulative amount of investment made by programme partners in support to the initial pro-poor innovation/changes as a result of direct support from the programme.	Planned	0	200,000	1,600,000	4,500,000
	Achieved	0	728,000	2,976,683	6,143,532[6]
1.1.4 Percentage of interventions that specifically aim to provide poor women more beneficial roles.	Planned	0	n/a	10%	15%
	Achieved	0	n/a	25%[7]	21%
[4] Revised up from 57 in 2016 Annual Report
[5] Revised from 104 in Annual Report to 99 in the PWIG
[6] Revised from £6,157,913 in Annual Report to £6,143,532 in the PWIG
[7] Revised up from 17% in 2016 Annual Report

Key points
ÉLAN substantially exceeded all four output indicators and demonstrated an accelerated expansion of the project amongst increasing number and variety of partners during 2017, catalysing a significant amount of investment through these partnerships. Since 2014, ÉLAN has entered 170 partnerships across the six sectors. The wisdom of ‘casting the net wide’ in terms of piloting different types of partnerships in different sectors and geographies and with a wide range of partners, is revealed by the fact that - of these 170 partnerships entered into by ÉLAN, some 63% (or 104) have resulted in partner investment in the pilot (Output indicator 1.1.1).
Of the 76 total live interventions in the ÉLAN pipeline in mid-2017, almost half (34) had been initiated since January 2017. This is a good illustration of the adaptive nature of ÉLAN, as experience about the types of partnerships grows; the burgeoning pipeline allows the project to build this knowledge rapidly into a new tranche of partnerships. This is reflected in different types of support and more stretching performance milestones for partners. In several cases, the transition from a conventional ‘adopt’ style pilot engagement to more of a light touch ‘supported replication’ partnership is evident.
The fact that ÉLAN is exceeding the – admittedly modest - target for partner investment in pilots by about 37% is a promising sign of the commitment of partners to the pilot innovations which ÉLAN has been testing. Given that this has been achieved during a period of particular volatility in private sector markets in DRC, with declining growth and investment and purchasing power, is a significant achievement.
ÉLAN has exceeded its gender targets in terms of participation (i.e. % of interventions aiming to provide opportunities for poor women). This target is more onerous than it appears. It requires that 15% of interventions should be targeted exclusively for poor women – so excludes interventions that aim to benefit men as well as women. Beyond the fact that ÉLAN has significantly exceeded this target, the consistent performance of about 30% of beneficiaries experiencing income change being women (impact indicator 2), is evidence that ÉLAN has taken women’s economic empowerment seriously.
Output Title	Crowding in: Market actors who are competitors to those who pioneered the pro-poor innovation have copied the pro-poor changes or offered variants of it. This, along with the initial innovation, results in large numbers of poor people accessing and using improved goods or services (Expand and Outreach).
Output number per LF		Output 1.2	Output Score	A
Risk:		Major	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator:		2014	2015	2016	2017
1.2.1 Cumulative number of poor people showing significant changes in their practices as a result of market system changes supported by the programme.	Planned (women)	0 / (0)	170,000 / (42,500)	260,000 / (65,000)	746,938 (186,735)
	Achieved (women)	0 / (0)	152,263 / (n/a)	319,421 / (111,702)[8]	643,014
					(201,774)
1.2.2 Cumulative number of market actors who are competitors to the programme partners who copy and/or expand on innovations piloted by the programme	Planned	0	4	12	17
	Achieved	0	4	24	32
1.2.3 Percentage of market system changes which have resulted in market actors who are competitors to the programme partners copying and/or expanding on innovations piloted in the programme.	Planned	0	n/a	20%	40%
	Achieved	0	10%	29%[9]	45%
[8] Reported as 111,243 in 2016 Annual Report
[9] Reported as 25% in 2016 Annual Report

Key points
ÉLAN exceeded two of the output’s three milestones for 2017 - interestingly for the Output indicators (#2.2 and 1.2.3) over which ÉLAN has least control. The contextual characteristics of thin and geographically disparate markets continue to present challenges to the depths with which the markets can be expected to change in response to pilot innovations. However, the results of Output 2 do suggest that the market is beginning to ‘crowd in’ competitors around the market systems innovations that ÉLAN is supporting in pilots.
ÉLAN fell slightly below, the aggregate Output indicator 1.2.1 although the programme should be commended for exceeding their target for women. This reflects a strong commitment to gender and inclusion, and a solid technical base to operationalise the commitment.

Output Title	Market response: Non-competing market players have adjusted their own practices in reaction to the pro-poor market system change (Respond)
Output number per LF		Output 1.3	Output Score	A+
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator:		2014	2015	2016	2017
1.3.1 Cumulative number of market actors who are not competitors to the market partners who change their practices as a result of market system changes supported by the programme.	Planned	n/a	n/a	1	10
	Achieved	n/a	1	8	10
1.3.2 Percentage of market system changes which have resulted in market actors who are not competitors to the programme partners changing their practices	Planned	n/a	n/a	5%	20%
	Achieved	n/a	4%	13%[10]	45%
[10] Reported as 8% in the 2016 Annual Report

Key points
Output 1.3 is further evidence that ÉLAN is having an impact on market systems beyond the pilots which are being directly supported. This output is the response quadrant of the Adopt, Adapt, Expand and Respond M4P framework for scaling up. It is an important achievement because it is measuring a market response which is almost entirely beyond the influence of the project. For example, the copying of the Go Congo CMA (warehouse receipts) model into a much larger collateral financing project, financed by two large commercial banks in Katanga, is a notable achievement.
The fact that there are signs of scale-up a year from the end of the implementation period is encouraging because it provides empirical support that the conceptual framework underlying ÉLAN – market development – does actually work.
Component 2: Business Environment Reform (Essor) (40%)

The assessment of ESSOR was complicated by the nascent MRM system. Therefore, several rounds of reviewing the evidence, by DSU, ESSOR, and DFID needed to take place before it was clear whether or not an achievement met the requirements for inclusion. In many cases it was found that there was insufficient evidence that reported achievements met the logframe mandated requirements.
Aggregate output score and description
Based on the output indicators scores were produced that are shown in the table below besides their weighting in the final score:
	Weight	Score	Explanation
Output 2.1	20%	A	Met Expectations
Output 2.2	20%	B	Moderately Did Not Meet Expectations
Output 2.3	30%	B	Moderately Did Not Meet Expectations
Output 2.4	20%	A	Met Expectations
Output 2.5	10%	B	Moderately Did Not Meet Expectations
	Output Score	100 %	B = Moderately Did Not Meet Expectations

The projects performance on outputs has been assessed as B as only Output 2.1 and 2.4 have been assessed as meeting expectations.
Output Title	The GoDRC and private sector identify issues for reform and lobby for change
Output number per LF		Output 2.1	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		2017
2.1.1 Number of quality dialogue events held (e.g., PPDs, working group meetings) that identify BER challenges and solutions and/or lobby for change	Planned	21
	Achieved	25
	Verification Rating	Low Confidence
2.1.2 Number of technical documents prepared and published with Essor support that inform the business environment reform agenda	Planned	1
	Achieved	5
	Verification Rating	Low Confidence
2.1.3 Cumulative number of BER issues surfaced and presented to MDAs (disaggregated by the number of issues that disproportionately affect women)	Planned	15
	Achieved	19
	Verification Rating	Low Confidence
	Planned (Women)	4
	Achieved (Women)	0

Essor met expectation on this output. This included an over-achievement on indicators 2.1.1 and 2.1.2, and on the overall achievements for 2.1.3 although performance fell short on 2.1.3 women targets.
For indicator 2.1.1, the intention of the indicator is to measure dialogues between stakeholders where attempts are made to advocate for, or solve, problems. Normally this kind of indicator is used to describe dialogues between stakeholders outside the project, particularly public private dialogue, and to reflect a ToC which includes encouraging the demand side of the reform process through developing the desire for, and capacity to advocate for, reform. However, the project has interpreted this measurement more widely, including a meeting to validate the doing business reforms, and meetings between MDAs and the project, but there is no objective indication of the quality or relevance of dialogue events held. Numerous dialogue events are claimed as achievements, which are nothing more than a meeting with an MDA. Counting every such meeting, however productive, constitutes inflation of results. Given that the logframe definition sets a very high evidence threshold (four separate criteria for inclusion) many of these meetings were discounted as insufficient evidence was available in the MRM system. Greater effort should be made to assess the quality and potential impact of dialogue events. At a minimum evidence should be presented that all relevant logframe criteria have been met before a dialogue is included as an achievement.
The achievement of 68 BER issues surfaced and presented to MDAs versus 15 in the plan for Output 2.1.3 is not necessarily an indication of development effectiveness, nor does it genuinely demonstrate the robustness of the debate and engagement of stakeholders. Rather it demonstrates the success of the project in holding meetings with stakeholders and presenting issues. It is the responsibility of BER advisors to help their counterparts focus on reforms that are both achievable and likely to lead to meaningful improvements in the welfare of target populations. This long list of BER issues is evidence that Essor has not focused upon these priority reforms. Conversely, the project has separately counted issues that are closely-linked and should be considered as different components of one result. For example:
- The MSME workstream presented a list of 20 fiscal reforms, but these could be consolidated into a much smaller number. For example, Reform 10: ‘regroupement de certains taxes à même objectif (Provincial et National)’ is almost identical to Reform 11: Suppression de certaines taxes redondantes ou faisant double emploi (National & Provincial). Both of these address the problem of the multiplicity of taxation, as do Reforms 6: ‘uniformisation de la Patente et le RCCM (Provincial)’, 7: ‘création d’un guichet unique de paiement des taxes pour le PME (National), and 8: ‘extension du formulaire unique de paiements des impôts, cotisations patronales au niveau des PME (National)’. In addition, there is substantial overlap in the national and provincial MDAs that would need to be engaged in order to affect these and other reforms. Working on similar taxes with the same agency should be grouped together into one result.
- Likewise, A2F has claimed five achievements based on a note to the Central Bank that advocated reform of the Leasing Law and mentioned five articles of the law that required attention which should be grouped into one result.
	Output Title	Development of human capacity in target GoDRC ministries, departments and agencies (MDAs) and private sector organizations enables Essor-targeted reforms
	Output number per LF		Output 2.2	Output Score		B
	Risk:		Medium	Impact weighting (%):		20%
	Risk revised since last AR?		No	Impact weighting % revised since last AR?		No
Indicator(s)							2017
2.2.1 Cumulative number of people receiving capacity building that enables reform with support from Essor (disaggregated by gender)					Planned		550
					Achieved		472
					Verification Rating		Low Confidence
					Planned (Women)		150
					Achieved (Women)		319
2.2.2 "% of trained people gaining skills and knowledge in areas relevant to Essor (disaggregated by gender)					Planned		60%
					Achieved		N/A[11]
					Verification Rating		N/A
[11] No disaggregation by gender has been provided.

Essor claims that the project substantially achieved its targets for this Output. However, the MRM system does not indicate whether the delivered capacity building and training are appropriate, nor whether the people receiving training are in positions in their organisations to carry enough influence to affect reform. Based on the revision of the results we have therefore assessed performance for this output as B. The logframe assumes that all or most of the training provided under Output 2.1 is capacity building for MDAs, that these officials show an interest and find value in developing skills in areas relevant to Essor-supported reforms, and that the officials selected for training, work in areas relevant to Essor-supported reforms and have positions in their organisations that enable them to contribute to reform.
- These assumptions hold true for training content and the people trained in the OHADA workstream, for example: 1) training for 28 commercial court officers on OHADA/ Commercial law by specialist professors, organised by Amis d’OHADA in Kinshasa; 2) On the job training of 15 archivists working on the digitisation of the RCCM; or 3) Legal & software application training for 12 GUCE staff in Lubumbashi (combination of legal, archives process and software application).
- In contrast, the numbers of people trained by the AC workstream under Output 2.1 is much greater than those under OHADA, but much less relevant to Essor-supported reforms. AC trained and accompanied 24 data collectors in Goma and Lumbumbashi belonging to partner business associations in tax diary data collection and survey techniques. It also trained 40 woman trainers who then delivered training to several hundred woman micro-entrepreneurs from Lubumbashi in professional entrepreneurship, how to make a profit, savings, and working with cooperatives. Training woman micro-entrepreneurs in business principles and management skills, if done correctly, can be very useful - but it has little or no relevance to capacity building for officials of MDAs who are in positions where they can contribute to advancing reform. (- 64 results for both overall and gender disaggregated results)
- ‘Step-down trainings of trainers on female entrepreneurship skills’, delivered to 226 people, does not have an evident connection to business environment reform in an anti-corruption context, since the main focus of this training was business and financial education (developing a business idea and on budgeting, savings, credit, and financial negotiations, and relying to a considerable degree on a training module prepared by GIZ). Financial literacy is undoubtedly important for small business owners and operators, but it has limited application to anti-corruption. In addition, training of trainers through a single two-day event is rarely effective unless the trainers already have substantial knowledge of the topic. (- 226 results for both overall and gender disaggregated results).

For Output 2.2, Essor reporting shows that 90.2% of the people receiving training have gained skills and knowledge in areas relevant to Essor (versus a planned target of 60%). No gender disaggregation is provided. According to the logframe the participants would be assessed using knowledge testing questions in the evaluation sheet but the MRM system contains no evidence for this indicator. Subsequent evidence submitted indicates the use of a survey to capture satisfaction but does not include sufficient evidence on whether or not the skills learnt were useful and applied by beneficiaries (as stipulated in the logframe).

Output Title	Essor interventions are implemented in partnership with GoDRC.
Output number per LF		Output 2.3	Output Score	B
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		2017
2.3.1 Number of Essor-targeted institutions that have demonstrated commitment to reform	Planned	18
	Achieved	10
2.3.2 Progress of the listed reform interventions
3.2a Inclusive insurance		50%
3.2b. Leasing reform		100%
3.2c Reduction in taxation for MSMEs in 6 sectors in Kinshasa		100%
3.2d Improvement in public sector support to the coffee industry		100%
3.2e Reduction in taxation on coffee exports		63%
3.2f Financial and administrative burden of MSMEs in Goma and Lubumbashi is reduced		90%
3.2g Improvement in access to electricity for MSMEs		100%
3.2h Cost of corruption diagnostic		67%
3.2i Cross-border trade corruption reduction		50%
3.2j Support to development of an Inclusive financial policy		72%
3.2k Financial education modules for leasing and insurance		0%
3.2l Agreement of tax reform roadmap for Kinshasa (Component 3: Assist with reform / implementation)		0%
3.2m Development of methodology for improved practices for concessioning for PV / electricity supply		0%
3.2n Support to MoJ in indigenization of UNCAC requirements		67%
Combined score for Output Indicator 2.3.2	Planned	70%
	Achieved	75.2%
	Verification Rating	Low Confidence
2.3.3 Cumulative number of issues disproportionately affecting women targeted by Essor	Planned	3
	Achieved	6
	Verification Rating	Medium Confidence

Essor claims achievement of all Output 3 milestones in aggregate However, for indicator 2.3.1. Insufficient evidence was provided of the impact of this process, as mandated in the logframe, that a comparison of budget/action plans before and after ESSOR interventions was achieved. 10 achievements were included, even though none actually met all the logframe criteria, because there was some evidence that some of these meetings may have met some of the required outputs.
While Essor over-achieved in terms of its reported results against two of the three indicators for this Output, in more qualitative terms, the only workstream that is considered to have made significant progress in 2017 was A2E (other than OHADA which is not captured here). Parts of the A2F workstream have also made worthwhile progress (notably leasing), while other parts have not (such as insurance).
The MSME and AVC workstreams were shut down in the final quarter of the year based on the judgement that they are unlikely to achieve a significant impact, which seems to contradict indicator and measurement approaches which showed that good progress was made. Progress on the anti-corruption workstream is not satisfactory with no clear route to impact and a focus on an over-extended range of pre-reform activities. This more qualitative assessment provides an opposite conclusion to the quantitative result estimated by indicator 3.2, and indicates that the logframe is providing misleading results.
Regarding indicator 2.3.3, it is relevant to note that the Essor gender strategy has only been developed in late 2017 and its implementation in 2018 is subject to the recruitment of a gender lead which was ongoing at the time of this review. Although the anti-corruption workstream has focussed attention on issues of female economic empowerment, there is no evidence to suggest that Essor is over-achieving in terms of addressing gender issues.

Output Title	Systems and procedures in place to give force to embed OHADA Law in DRC legal framework and commercial practices
Output number per LF		Output 4	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		2017
2.4.1 Progress on deployment of the Guichet Unique (GUCE) in DRC	Planned	2 GUCE Antennas in Kinshasa operational
	Achieved	2
2.4.2 Progress on implementation of the RCCM in DRC	Planned	Quality process improved through two new software releases
	Achieved	2
	Planned	National RCCM operational for Kinshasa
	Achieved	yes
	Planned	Design completed for securities registration
	Achieved	yes
2.4.3 A mechanism for disseminating Information on OHADA law is institutionalized	Planned	Ministerial approval for l’Association des Amis de l’OHADA and governance structure agreed. Association is established and has started to operate; Readiness to hire at least 3 people in 2018 on permanent basis
	Achieved	yes
2.4.4 CNO and its associated association have had their capacity built	Planned	CNO received first elements of training on M&E and has started its self-assessment
	Achieved	yes
	Planned	Association des Amis de l’OHADA is created and has started building institutional capacity
	Achieved	yes

Essor achieved all milestones for Output 4, which exclusively comprises OHADA workstream outputs. Apart from minor delays in commissioning the GUCE antenna in Lubumbashi, the OHADA workstream has achieved its objectives according to its workplan. Although setting up the GUCE antennas is the most visible achievement of the workstream, especially because of its effect on DRC’s score in the World Bank Doing Business indicators, the impact from its digitisation of the RCCM and, especially the creation of a collateral registry, may have a more profound long-term impact on the business environment by increasing access to finance.
The project should start to review and plan for sustainability of its reforms. Ensuring financial self-sustainability for CNO and les Amis D’OHADA should be a top priority:
- Creation of les Amis d’OHADA, a private organisation that provides training to commercial court officers, is an important step towards sustainability of the OHADA reforms. But there remain serious concerns about sustainability once Essor support has ended.
- Government has declared its intention to transform the CNO. This would give CNO the ability to charge fees for services such as access to information in the collateral registry, which financial institutions would be willing to pay, and to keep business registration fees to defray its operational costs. Government, however, has yet to initiate the transformation of CNO, and if this does not occur the Essor-supported reform of business registration and the RCCM may prove unsustainable once DFID funding ends.
- Given that the corporatisation of CNO may take time, Essor and DFID should seek commitments from Government to provide financial support to the GUCE and RCCM during any transitional period.

The project should test the effectiveness of the reforms through their planned business survey, and include in their plans support to strengthen implementation and reduce the likelihood of roll back of reform (e.g. through communications and support to the Ministry).
Output Title	MSMEs have information that allows them to respond to reforms
Output number per LF		Output 2.5	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)		2017
2.5.1 Cumulative number of quality Essor-supported awareness activities informing MSMEs about business environment reform	Planned	7
	Achieved	6
	Verification Rating	Medium Confidence

Essor results claimed substantially exceeded the target for indicator 2.5.1. However, it included a questioned inclusion of five activities related to women’s economic empowerment that have no clear link to business environment reform. In addition, there is apparent double-counting of the achievement of one activity – a fiscal civic mindfulness campaign – which is registered as four separate activities in the result. (- 8 results). The indicator logframe is clear- the awareness raising activities have to (1) pertain to business environment reform, and (2) meet the quality criteria in the logframe definition. Only 6 of the achieved activities reported met both criteria.
Component 3: Decision Support Unit (DSU) (10%)

Output Title	Performance Assessment – The performance and effectiveness of the PSD programme and its component projects are regularly assessed.
Output number per LF		3.1	Output Score	A
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	Yes

Indicator(s)	2017
	Milestones	Progress
3.1.1 Number of high quality Annual Reviews conducted annually, in a timely manner and approved by DFID, in accordance with DFID standards and format for the PSD programme and its component projects	3	3
3.1.2 Number of annual verification reports, produced in a timely manner and approved by DFID, which assess the validity of results reported by the PSD programme and its component projects	2	2
3.1.3 Number of annual results reports, produced in a timely manner and approved by DFID, which estimate the results of the PSD programme's component projects after their completion.	0	0
3.1.4 Number of times IRP is convened annually. The IRP will be convened to review verification reports, post-project monitoring of results and advise DFID on payment by results.	0	0
3.1.5 Number of independently credible and rigorous evaluations undertaken, in a timely manner and approved by DFID (including EQUALS). Includes the mid-term evaluation (2017) and final evaluation (2023).	1	1

This year’s review will only assess output 1 given other outputs didn’t contain any targets for 2017.

The DSU’s performance in the first quarter of 2017, which was dominated by the ARs process, was well below expectations. Whilst the ARs were delivered on time, the quality was not of the expected standard. These issues were discussed in the previous AR in detail, which scored the project a “B”, and triggered a PIP process.

The last three quarters of the year were dominated by the PIP, the MTE, verification technical support on logframes and indicators, and planning for 2018 AR. For this period, the DSU overall made notable improvements, delivered on its objectives, mostly within deadlines. It was responsive to DFID’s feedback and priorities which made it a valuable resource for the programme.

Delivery on the PIP was successful and mostly on time. This included planning and resourcing for the 2018 AR, and a verification report which despite some challenges at the start was delivered successfully.

The MTE was successfully delivered, with a “Good” rating by EQUALS. Whilst the MTE quality was good, DFID and other partners found the tones unhelpful and not constructive which lead to wastage of time that could have otherwise been used to discuss the MTE’s content.

Despite technical support (output 3, learning and adaptation) not formally having targets for 2017, the DSU was flexible and responsive to DFID and partners requests and provided ad-hoc technical support to Elan and Essor. This included support on Essor’s logframe, a note on definitions of categories of Elan beneficiaries, and support to improve the projects value for money frameworks. The support provided was helpful, but the fact that it was done without a clearly and explicitly stated objective and without structured feedback from recipients’ means that it’s difficult to assess its quality and impact.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
Key cost drivers and performance
Overall, the PSD programme spent £16.5m in 2017 (Essor £6.6m; ELAN £9m; DSU £0.9m). This was a substantial increase from 2016, with all three projects increasing their rate of spending. In 2018, the spending rate for Essor is projected to significantly reduce as part of its PIP, the DSU’s spending is expected to marginally reduce without the major cost component of the MTE, while that for ELAN is expected to increase to £10.6m for its final year of operation.
The key cost drivers across all components of the portfolio are fees and expenses for TA. The reporting on these rates between projects is not completely standardised, which complicates a cross-portfolio analysis. Broadly speaking the average daily costs are similar to those seen in 2016
VFM performance compared to the original VFM proposition in the business case
For ELAN there is a clear embedding of VFM principles across project implementation which is reflected in an increasingly strong performance against the key VFM indicators. At the Efficiency level the project has achieved impressive leverage of external partner resources with £6.1m leveraged to date, expected to reach £10m by the end of 2018. At the effectiveness level ELAN has made major progress in 2017, ensuring increased confidence that the ambitious targets for post-project impact can be achieved.
Already by the end of 2017 ELAN had generated cumulative aggregate NAIC of £16.2m across 400,000 people, up from £5m across 150,000 people in 2016. This is an impressive already measured achievement at the Impact level, in a national context where many if not most development projects fail to demonstrate clear achievements beyond the Output level. The cost per pound of NAIC achieved is now £1.45. Should the projected NAIC target for 2020 be achieved, this cost per pound will fall to £0.77.[12] These projections are less optimistic than those originally targeted in the logframe, however, they have a far more realistic basis (indeed they may prove conservative, particularly noting that they do not incorporate indirect beneficiaries) and their achievement would still represent a major Value for Money achievement.
[12] Spend of £34m from 2014 to 2018; cumulative aggregate NAIC projection of £44.4m by 2020.

In addition, the project has made commendable efforts to support interventions where the short-term NAIC achievements are relatively modest, but which have very significant potential to achieve substantial longer term impact. Particularly strong examples of this include support to the Branchless Banking sector, leasing and the collateral management interventions. Alongside various non-estimated non-NAIC benefits, such as the social benefits associated with the expansion of the renewable energy sector in the DRC and improvements in gender empowerment, there is a good indication that DFID’s investment in ELAN is proving excellent Value for Money.

Essor updated its VFM framework following the update of its logframe in September 2017. The first report against this new framework (January 2018) was a substantial step forward from previous reporting which focused almost exclusively at the Economy level. Nevertheless, there remain major gaps in terms of finalizing the data within the report, assessing the implications of the findings as well as providing additional qualitative analysis. Workstream-specific impact modelling has been carried out across the portfolio. This is a helpful exercise, but now needs significantly more attention to improve its validity noting some methodological weaknesses and issues with the plausibility of the underpinning results chains. It also needs to be complemented by a more basic consideration of what the overall benefits of each workstream are (whether quantifiable or not), accompanied by compelling logic as to why and how such benefits could be achieved.
There continues to be some complementarity between Essor and ÉLAN to ensure that the portfolio’s value is greater than the sum of its parts. A good example is the leasing market, where two major banks are now launching products following ELAN’s direct support with these partners and Essor’s broader support on improving the regulatory framework. There was also a successful transition of expertise from Essor to ELAN with the team from Essor’s Agriculture Value Chains workstream largely being absorbed by ELAN upon its closure towards the end of 2017. Nevertheless, the analysis of the MTE makes clear the much greater potential there could have been for more dynamic collaboration, which should be considered in the design of any future phase of support to the sector.
This year was the first for DSU to report against its VFM framework (February 2018). The reports set out recommendation for improving efficiency and effectiveness, which include implementation of the MTE recommendations. Other important areas include reduction on the burden imposed on both Elan (efficiency) and Essor, and the follow up to the recommendations to Elan and Essor to ensure they improve performance of the PSD Programme (effectiveness). .
Assessment of whether the programme continues to represent value for money
Overall, there is now more confidence that ELAN is on track to deliver good VFM for DFID, thanks to impressive NAIC achievements by the end of 2017 and an improved, more realistic process for projecting NAIC to 2020. Greater capturing of the long-term impact that the project’s market system changes could achieve would further increase the evidence base for the project’s strong VFM achievements.
For Essor, two workstreams (OHADA and A2E) are making good progress and could well achieve significant benefits (although the nature of these potential benefits still needs to be more rigorously set out), however there are concerns about whether Essor overall is achieving VFM. Across other workstreams the shift to actual implementation of reforms has been slow, aside from some important progress achieved within the A2F leasing intervention. There continue to be significant weaknesses with the overall management of the project. To ensure VFM is being achieved the effectiveness of the management team needs to substantially improve, or alternatively the project should be stripped down to its most functional workstreams (OHADA and A2E, with the possible inclusion of some A2F interventions) and maintain only a minimal overarching management structure.

The DSU is performing within average on economy, but should make improvements on efficiency and effectiveness. The DSU should also ensure it develops tools and indicators to measure this.
Quality of financial management
Financial management of the projects is overall sound, although some improvements could be made on forecasting, and on the DSU’s financial planning and timely invoicing
All projects provide a forecast at the start of the financial year (baseline forecast), as well as monthly adjusted forecast. For the first two quarters of the year, spend by all projects was well below their baseline forecast, with underspend/ variance up to 20%. The projects however started making notable improvements in the third quarter. Projects were required to hold back spending in Q4 (Jan-Mar) which is likely to have a materially negative impact on project activities specifically for ELAN in the crucial first quarter of its final year of implementation.
Essor is very likely to have an under spend by its end date of January 2020. To improve project planning it is recommended that any plans for a time extension are already made explicit, and to ensure any extension is strongly contingent on a clear VFM rationale linked to improved project performance.
DFID have in discussions requested that majority of spend is prioritized in the first three quarters of the financial year (April to December). This however is not always possible for PSD projects given the majority of spend is for staffing and offices running cost.
Date of last narrative Financial Report	Essor: 31 January 2018 (2017 Financial Report) / ÉLAN: 10 February 2018 (Combined Financial Narrative and VFM report 2017) / DSU: Financial section in the annual report (31 January 2017).
Date of last Audited Annual Statement	Essor: External Audit undertaken in November 2016 covering period July 2015 to June 2016 and PwC’s financial statement as of June 2017. / ELAN’s 2017/18 audit report is currently being finalised to be submitted to DFID / DSU: Financial statement as of September 2017

E: RISK
Overall risk rating: Major
The overall risk of the PSD Programme is rated as Major
A detailed Risk Matrix for the PSD Programme is updated quarterly, using quarterly risk updates from partners (ÉLAN and Essor), as well as regular meetings between DFID and its partners. Significant risks are identified and raised with the Team Leader and if needed to the Senior Leadership Team.
ELAN undertakes additional risk mitigation through political economy and conflict analysis on a routine basis, in conjunction with a pre-partner due diligence vetting process.
Overview of programme risk
Delivery risks (major)
Political instability has grown as elections recede into the future. Frequent Cabinet reshuffles and institutional reorganisations make it difficult to maintain effective partnership with some key MDAs. Budgetary pressures, which stem from a declining economic situation, mean that many government employees may go for months without being paid, and this in turn provides fertile ground for corruption, as officials struggle to cover their household expenses. The on-going and simmering conflict in the Kivu threatens to destabilise areas where ELAN’s coffee, agriculture non-perennials and renewable energy related projects are located.
The continued downturn in the Congolese economy also poses serious risks to the programme. Reduced economic growth and increased macroeconomic instability reduce the profitability of all firms, including small businesses, reduces investment and increase uncertainty. This will make it harder for the programme to meet its targets and will increase the difficulty of planning and action.
Fiduciary risks (moderate)
There is a moderate risk of misappropriation of project funds, based on current systems and procedures applied. Due diligence assessments of implementing partners are made prior to channelling any project funds through 3rd parties. No funds are channelled directly through GoDRC systems.
Reputational risks (moderate)
There is some potential reputational risk to DFID from activities that could be seen by the political opposition and by the international press as supporting an undemocratic and corrupt government, as well as potentially giving legitimacy and support to individuals and institutions responsible for human rights violations. ELAN has undertaken Political Economy and Conflict Assessments for sensitive interventions and provinces. Essor plans to make more systematic use of Political Economy analysis in 2018.
Safeguarding (moderate)
All implementing partners under the PSD are key DFID suppliers and have therefore provided assurances on safeguarding as set out by Secretary of State on 12 March. An assessment of this evidence is not yet available. The programme team is also using current discussion on routine amendments to include specific reference to safeguarding and the code of conduct in the contracts for DSU and Elan. The next contract amendment for Essor is expected in three to six months and we will ensure text on safeguarding is also included.

Risk of exploitation and abuse: The level of risk varies between the different components from minor for DSU (small team with no presence outside Kinshasa, and no downstream partners) to moderate for Elan and Essor, given number of consultants, external stakeholders and presence outside Kinshasa including in places where vulnerability and power dynamics are apparent.

Elan’s due diligence assessments of its downstream partners doesn’t cover safeguards. DFID DRC will consider any improvements for new partnerships under the new programme starting next year.
Outstanding actions from risk assessment
The previous Annual Review stressed the importance for Essor to have enhanced and more dynamic PEA and political contingency planning, with a planned Stakeholder Working Group as an important vehicle for such analysis and planning. This has not yet happened, and the Stakeholder Working Group, meant to be established in 2017, has not materialised. These recommendations acquire additional urgency now that Essor has passed its halfway point.
The previous Annual Review also recommended Essor to appoint a Communications Lead as an important measure to address then-current weaknesses in advocacy, awareness-raising, sensitisation, information dissemination, and visibility. One year on, these weaknesses persist, and it should be an important priority to rectify them in the first half of 2018.
F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
The programme overall is behind compared to the original planned timeframe.

ÉLAN: The BC envisaged that this will be a five year component. A slower than expected start, reductions in financial allocations in 2015 and the impossibility of having a no-cost time extension means that a new phase of the project is required.
Essor was also envisaged to operate for five years. Given a slow start and continued challenges with moving forward implementation, it is behind its originally intended timeframe. For the allocated budget to be fully utilised the project would need at minimum a 12-18 month no cost time extension. This extension should however be based on confidence that continued activities would provide good VFM for DFID.
DSU: This was the last component to be contracted (due to budget cuts in 2015), but its end date is in line with the overall PSD BC (2024). Although unlikely, DFID might need to revisit the end date (if for example none of the projects are extended). Break clauses are included in the contract to allow this if needed.
Performance of partnership(s)
ELAN: Routine meetings between ÉLAN’s management team and the DFID PSD team continue to be held to ensure communication channels are clear and frequent. DFID is also required to approve partnerships between ÉLAN and actors when the value of ÉLAN’s contribution exceeds £50,000, which provides DFID with a fairly hands-on approach to managing ÉLAN’s partnership engagement processes (although has in the past had negative effects of reducing the speed with which the project can push forward its implementation plans).
Collaboration with Essor has improved in 2017, most notably with the successful partnership supporting the launch of leasing products, where Essor has assisted ELAN’s work on product development by supporting the relevant regulatory environment.
Essor: Interviews and focus groups with most of Essor’s public and private sector stakeholders indicate a positive view of Essor. They believe in Essor’s mission and purpose and respect the knowledge and capabilities of the team members with whom they have interacted, and have positive views of many of the workshops and other events in which they have participated.
At the same time, some key strategic partners have expressed concern that they are unclear as to what the Essor project is achieving overall, and in many specific cases, are unsure of the level of commitment and extent of technical and/or financial support being made available under a workstream. The views expressed by these stakeholders do not necessarily reflect the full truth of the matter, but raise questions of effective communication and information-sharing.
Essor has effectively collaborated with the ELAN project most recently on regulatory reform in connection with ELAN’s support to two of DRC’s largest commercial banks in rolling out new leasing products.
DSU’s stakeholders so far are DFID, ESSOR and Elan. The relationship with all partners was challenging in the first quarter of the year. The relationship has since improved significantly with DFID, including the relationship with the SROs of Elan and Essor. The SROs often used DSU’s advice on issues related to results and logframes. The DSU was always responsive and flexible
The relationship with the other PSD projects was mixed. Collaboration with Elan has been generally good, despite some challenges during the verification exercise, and at times over the tone of reporting. The relationship with Essor was the most challenging with issues being escalated to DFID by the two implementing partners. DFID is working with the partners to improve working relationship.
Next year will be the first when the DSU delivers under its full mandate. To maximise learning and the benefit of research it should broaden its stakeholders beyond the direct PSD projects. This could include other development agencies, and other DFID departments and programmes. Such work should be done in close collaboration with the other two projects.
Asset monitoring and control
Elan and Essor provide DFID with quarterly asset registers, which are used for annual spot checks by DFID. Any notes or issues are recorded in the delivery plan and followed upon with partners. ELAN’s VFM framework further supports asset monitoring. The last spot check was done on 28 February 2018. Few issues were raised and are being resolved. Checks in the field will carried out in the next field visit.
Elan and DFID will finalise a plan for the assets before the end of the project in December 2018. The plan it to use majority of the assets for other DFID programmes or to maintain them in storage until the start of the new phase of ELAN.
The DSU does not use any DFID assets and is not expected to
G: CONDITIONALITY
Update on partnership principles and specific conditions (if relevant)
Not applicable. The UK Partnership Principles for the DRC are not formally shared with the Congolese government. They were updated in January 2018. In the case of the PSD, no funding is channelled through Government systems, but government benefits from technical support provided by Essor. In October 2017, the UK conducted a comprehensive review of its development programming in the DRC, and the extent to which it engaged with or supports Congolese national stakeholders. This culminated in a submission to UK Ministers in 2017, with particular attention to fiduciary, human rights, and associated reputational risks.

H: MONITORING & EVALUATION
Evidence and evaluation
ELAN: The quality of evidence about the performance of interventions in ÉLAN is important for a range of reasons. At the operational level for an adaptive programme, like ÉLAN, where interventions are piloted and scaled-up, scaled-down or dropped as a result of implementation experience, it is important that the quality of evidence on which these decisions is made is robust.
A verification exercise was undertaken during 2017 to assess the extent to which ELAN’s reported results could be considered accurate reflections of reality. The overall results of the exercise were that there was at least medium confidence in the overall results reported for each logframe indicator, but only high confidence for those results reported for Output 1. As such, there was some degree of confidence in the overall results reported across all indicators, but also scope across almost all indicators to improve the validity and accuracy of these reported results. The 2018 verification exercise will need to provide an updated assessment of the validity of ELAN’s reported results data.
Although the focus of the Mid-Term Evaluation was not on the quality of the MRM system, important issues relating to the quantification of outreach, net benefit and additionality were raised at the intervention level based on primary data collection principally through case studies.
ELAN has done impressive work already in developing the WEE case study series. Case studies, stories of change, and contribution analysis are all important ways of building evidence, particularly in the spaces which lie between hard indicators. ÉLAN should continue to document WEE learnings and achievements through case studies, and these should be disseminated aggressively.
Essor: Just like ELAN, the quality of evidence about the performance of interventions in ESSOR is important for a range of reasons. At the operational level for an adaptive programme, where interventions are piloted and scaled-up, scaled-down or dropped as a result of implementation experience, it is important that the quality of evidence on which these decisions are made is robust. Furthermore, the difficulty in quantifying the results of some types of BER activity makes a robust evidence strategy and its implementation extremely important. In terms of the accountability of the project, this Annual Review being a case in point, it is also important that ESSOR is able to describe the effect that it is having on the target population accurately.
There have been some notable improvements in ESSOR’s ability to develop a functioning MMR system and begin to collect relevant data given the approved logframe. However, additional progress is needed for these efforts to reach the threshold expected of a programme of this type:
Firstly, the MRM system has to ensure that the results recorded meet all the criteria of indicators in the logframe. A technical assistance programme may engage in very fruitful discussions, and technical work. However, given the difficult to qualify nature of some of these benefits, an understandably high threshold for allowing evidence was established (the strict criteria in the logframe definitions). Unfortunately, the current MMR system has not fully operationalised these criteria and therefore, many activities which were not meeting the threshold for inclusion were being submitted as achieved results;
Secondly, in order to better capture the impact of the programme the logframe mandated the design and implementation of quite rigorous impact evaluations. Unfortunately, the time it took to begin this process has meant that many, but not all, of these impact evaluations are not feasible in their original design. Significant effort needs to be made to ensure that the remaining ones are implemented quickly and that the impact of the programme can better be captured.
Monitoring process throughout the review period
The review was conducted by the DSU team between 15 January 2018 and 2 March 2018 and consisted of a desk-based document review, and a week-long in-country visit to conduct Key Informant Interviews with both the ELAN and Essor Management Teams and DFID DRC. Following the fieldwork, a draft AR report was submitted to DFID DRC, ELAN and Essor for review and to solicit comments. All feedback from the projects and DFID was duly considered in the final draft submitted.