Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Lebanon Municipal Services Programme
Programme Value: £46.2 million		Review Date: 30/06/2017
Programme Code: 204397	Start Date: February 2014	End Date: March 2019

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	N/A	A	A	A
Risk Rating	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

The UK-supported Lebanon Municipal Services Programme is delivered through the UNDP-managed Lebanon Host Community Support Programme (LHSP). Including this financial year, the UK has provided £47.5m of funding to the LHSP since 2014. This includes £5 million in FY 14/15; £8 million in FY14/15 (of which £3m was provided from the Conflict, Stability and Security Fund); £8.2 million in FY15/16 (of which £6m was provided from the Conflict, Stability and Security Fund) The programme has improved and expanded municipal services delivery in targeted municipalities based on community‐driven needs assessments. Since the start of our support, UK funding has supported 110 municipal support projects and 33 livelihoods opportunities projects, in 51 municipalities, benefitting 445,085 vulnerable people of which 276,127 are Lebanese and 168,958 are Syrian. The projects were identified through a participatory, community-led process known as ‘Mapping of Risks and Resources (MRR)’ and covered a wide range of priority sectors such as water, energy, recreational spaces, education and health, and municipal infrastructure.

The previous Annual Review scored the programme as ‘A’ (meets expectations) and made a number of recommendations. The majority of these have been addressed following consultation and follow-up by the DFID team with UNDP. However, a number remain relevant, particularly ensuring the logframe as a management tool is kept up to date and ensuring any delays in implementation are flagged to DFID early (see recommendations).

Following the 2015 Annual Review DFID worked closely with the UNDP team in the development of ToRs for an external evaluation of LHSP which was completed in November 2016. The evaluation shows that the the project has had a positive effect on community relations and resilience: “The UK-funded projects have had an impact. They have increased the positivity of citizens in regard to services and reduced the sense of conflict/competition… reducing the tendency to “blame” refugees for inadequate services or jobs”. The evaluation corroborates the conclusion of this Annual Review which assesses overall performance as ‘A’ (meets expectations).

The programme was also reviewed by DFID’s Internal Audit Department in April 2017, as part of a broader assurance review of the CSSF. The lessons and recommendations summarised below also incorporate revelant issues flagged in the IAD report and the 2016 external evaluation.

Key lessons and recommendations

Improved communication between DFID and UNDP has supported strong programme performance and avoided some of the challenges reported in the previous Annual Review. Nevertheless, this is an area that merits continued focus. Recommendation 1: UNDP and DFID to invest time to ensure that the logframe is kept up to date and used more effectively as a programme monitoring tool. DFID to carry out more frequent, risk-based spot checks on progress of projects.

The log-frame did not include output weightings which made it hard to evaluate overall progress. Recommendation 2: UNDP and DFID to agree weighting on individual outputs in the revised logframe.

Current quarterly reporting from UNDP comes in the form of two separate reports to reflect both DFID and CSSF contributions. The narrative reports provide useful context but it is sometimes hard to clearly track performance against logframe targets. Recommendation 3: DFID should review reporting requirements with UNDP to improve efficiency and ensure that reports allow performance against logframe targets to be tracked.

The external evaluation recommended increasing the size of the programme in order to have a material impact on the issues facing host communities. This will probably require taking on larger projects and perhaps also implementing new projects in communities already covered. The Evaluation also noted that working at the cluster level is a logical way to take on large infrastructure and livelihoods projects and focusing on fewer sectors will also make it easier to reach levels where it is possible to have a material impact on priority sectors.

Whilst increased GoL involvement is extremely welcome, there needs to be a balance between GoL oversight and consultation, and timely delivery of projects as this remains a key risk to successful delivery, particularly with a move to larger, and potentially more complex projects. Recommendation 4: UNDP, with DFID support, should manage GoL engagement to ensure projects are implemented within the timeframe of the programme.

Independent evidence and discussions at municipality level suggest that employment is becoming a growing source of tension. Recommendation 5: DFID should consider whether the livelihoods component and methodology used under LHSP is the preferred modality to create jobs and to raise awareness of jobs created through this programme to counter negative perceptions.

- It is currently not clear how activities and expected outcomes of the MSS are monitored to see which conflict drivers are being addressed and how effectively. Recommendation 6: DFID to explore with UNDP how they are sequencing the next round of MSS into the MRR process in order to allow greater representation of actors who are not involved in the MRR. DFID to work with UNDP on their M&E framework to ensure that peace indicators are included and are aligned with the MSS analysis.
- UNDP have demonstrated commitment to ensuring LHSP continues to be evaluated and that lessons learnt are implemented to improve the impact of the programme. Recommendation 7: Given the number of donors now involved in the programme, it is recommended UNDP set up a donor working group to help improve coordination and to allow regular reporting on lessons and progress in implementing recommendations

Statistics on job creation have not previously been captured consistently which makes it more difficult to agree on the level of impact in the livelihoods sector. Recommendation 8: As DFID scales up its funding between 2017-19, it is recommended that the DFID team work closely with UNDP on assessment methodology to assess numbers of jobs created and the cost per additional job created across different project types.

Recommendation 9: DFID to review methodology used by UNDP on beneficiaries who benefit from municipal services projects to ensure there is no double counting. This was also a recommendation that came out of the external evaluation.

Recommendation 10: DFID to look more closely at the VfM of this programme as part of its implementation of a new VfM strategy and work closely with UNDP to ensure VfM is considered across the programme. Additional VfM indicators should be included in the revised logframe.

UNDP’s financial management of the programme has been adequate but could be strengthened. Recommendation 11: We recommend that for the next phase of the programme i) budgets should be submitted in GBP and ii) more detail should be given in financial reports, with a financial narrative included. In line with IAD recommendations, DFID will also seek verification of payments as part of regular spot checks.

Recommendation 12: UNDP and DFID to hold more regular discussions on risk, using the updated risk register as a risk management tool. Regular updating UNDP’s supply chain mapping will allow better assessment of fraud risk and potential conflicts of interest.

Recommendation 13: UNDP to review how M&E tools could better measure outcomes of the programme

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Six years into the Syrian conflict, Lebanon remains at the forefront of one of the worst humanitarian crises. The Government of Lebanon (GoL) estimates that the country hosts 1.5 million Syrians who have fled the conflict in Syria (including 1.017 million registered as refugees with the United Nations High Commissioner for Refugees (UNHCR), along with 31,502 Palestine Refugees from Syria, 35,000 Lebanese returnees, and a pre-existing population of more than 300,000 Palestine Refugees in Lebanon.

The UK’s objectives in Lebanon as set out by the National Security Council include strengthening resilience, stability and social cohesion, with refugees and host communities increasingly integrated and able to co-exist peacefully, and their resistance to extremism and radicalisation strengthened.

To help met these objectives the UK provided £9 million of funding in 2015/16 for the Lebanon Host Community Support Programme (LHSP) managed by the UN Development Programme (UNDP) which was launched in in 2013 . £4 million of this funding came from DFID’s bilateral resources and £5 million from the cross-Government Conflict, Stability and Security Fund (CSSF). In March 2016, an additional £0.3 million from the CSSF was given to UNDP to fund Social Development Centres (SDCs) of the Ministry of Social Affairs, increasing the overall budget to £9.3 million. The objective of increasing funding by £300,000 is to reinforce the capacities of 15 SDCs to deliver care services to vulnerable communities affected by the Syrian crisis, based on community needs identification. In 16/17, the UK provided £8.4 million (of which £6m was provided from the Conflict, Stability and Security Fund) and has committed a further £25 million to the LHSP programme between 2017-19 (£10 million from the CSSF and £15 milion from DFID bilateral resources).

The purpose of the DFID funded Lebanon Municipal Services Programme is is to reinforce the capacities of municipalities to respond to the increased demand for services and to reduce inter communal tensions arising from the arrival of refugees which in some places have nearly doubled the population. The UK intervention has targeted 51 municipalities in areas of high social tensions across the Bekaa, South and North of Lebanon (including Tripoli).

The programme is managed by UNDP, in close cooperation with the Government of Lebanon (GoL). GoL engagement is led by the Ministry of Social Affairs (MoSA), in close cooperation with the Ministry of Interior and Municipalities (MoIM), the Council for Development and Reconstruction (CDR) and the Office of the Prime Minister.

The expected impact of this programme is a reduction in the level of tension between refugees and host communities in target areas. The expected outcome delivered by the programme is enhanced basic services and livelihoods support in target municipalities. The most vulnerable municipalities are targeted for support under the programme. These are selected on the basis of transparent criteria including poverty rates and the ratio between inhabitants and Syrian refugees.

The original envisaged programme end date was March 2016. However this was extended to February 2017 to accommodate delays linked to Lebanese municipal elections and getting projects approved. The original LHSP log frame included milestones up to March 2016. This log frame was later revised to reflect the February 2017 end date and additional funding from CSSF for 16/17. Performance in this Annual Review is measured against this revised logframe.

How are results measured?

Project Outcome and Outputs have been measured through UNDP team and internal reports and the Lebanon Crisis Response Plan inter-agency surveys.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

We are assessing the programme against the following outcome statement ‘Enhanced municipal services and improved livelihoods conditions in targeted municipalities.’

This has been assessed through the following outcome indicators:

- Percentage of residents who took part in the municipality planning process and are "satisfied or very satisfied" with the process. (milestone 70%; achieved 91%)
- % of municipal members involved in the training who feel capacitated to better respond to the needs of their community (milestone 80%: achieved 75%)
- # of community members directly benefitting from improved water, sanitation and health conditions (milestone 29000: achieved 31200)
- # of municipalities benefitting from improved electricity supply, better visibility at night or lighting in homes (milestone 75: achieved 92)
- % of supported youth who feel their employability skills have been strengthened through the training (milestone 80%: achieved 93%)
- # of cooperatives' members benefitting from cooperative support (not reported)
- # of governmental and non-governmental social stability organisations benefitting from using the conflict mapping (milestone 900: achieved 3112)
- % of MoSA staff supported who feel their capacity to perform their duties has improved (milestone 80%; achieved 87%)

Overall, the programme is scoring well at outcome level: exceeding most outcome-level indicators. It is however recommended that DFID keeps track of how UNDP is responding to key findings from Aktis (perception survey) findings which help provide further contextual information to support the outcome assessment.

Overall output score and description

Overall, DFID has scored this programme an A based on the following Output scoring.

- Output 1: Target municipalities identify service priorities through engagement with communities, taking account of preferences based on gender, confessional group, age and Lebanese/refugee status. (weighting 20%). Score: A+
- Output 2 Municipal services and livelihoods initiatives improved Improved and/or expanded municipal services and livelihoods initiatives are delivered in target municipalities. (weighting 40%). Score: A
- Output 3: Municipal management capacities strengthened and provision of local services improved (weighting 10%). Score: A
- Output 4: Livelihood opportunities strengthened for the most vulnerable population (weighting 10%). Score: A+
- Output 5: Social stability mainstreamed through local and national channels (weighting 10%). Score: A
- Output 6: Capacities of MoSA strengthened to better respond to the Syrian crisis (weighting 10%). Score: A.

Has the logframe been updated since the last review?

Yes. Following a revision of the logframe, weightings for individual outputs were not included which made it hard to evaluate progress overall. The output weightings included above are DFID’s own assessment of outputs’ contributions to the outcome – suggested during the Annual Review. It is recommended that DFID work with UNDP to agree on output weightings in the revised logframe. (recommendation 2)

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Target municipalities consolidate their community planning.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones / 31st March 2017	Progress
1.1 Number of existing MRR-Multi-Sectorial Municipal Actions Plan updated by the Municipal Working Groups	49	141
1.2 # of Multi-Sectorial Municipal Action Plans developed at a cluster level	14	13

Key Points

This output as scored an ‘A+’ – targets have exceeded expectations.

During FY 2015/2016 the Mapping of Results and Resources (MRR) methodology was fully adopted by MoSA through a progressive process that allowed to cover the totality of the 251 vulnerable communities, producing the respective Municipal Action Plan, improving the methodology and achieving more participation of stakeholders.

Progress of output indicator 1.1 exceeded expectations (from 49 to 141 multi-sectoral action plans being updated) because the teams involved in the updating of the MRR were already mobilised and trained for the updating of the MRR phase 1 (49 municipalities). This made it possible to expand the exercise to cover an additional 92 municipalities without the need for additional resources.The methodology of the MRR has also improved in phase 3. The assessment is now led by MoSA and is implemented over a five‐day period giving the participants form the communities more time to have an in depth discussion on their risks and resources and set out their priorities. In July 2016, the MRR results were officially made available through the MoSA website, and are also accessible through the Prime Minister Office Website. This is an important indicator of GoL ownership of the methodology.
Output indicator 1.2 met expectations. The target of 14 clusters was very slightly missed (13 achieved) but with an acceptable justification. The decision for MRRs to take place at a cluster level has been to expand the scope of work of the MRR methodology and scale up the level of intervention. MoIM area coordinators, and UNDP Area Managers finalised the methodology and the criteria for the selection of the 14 clusters of municipalities to be targeted through the MRR exercise in October 2016. The initial plan was to target 14 clusters of municipalities. However, the cluster in Byblos didn’t fit the definition of ‘vulnerability’ (following the criteria of % refugees to total population, level of tensions etc.) and local stakeholders were not co-operative. Therefore, the MRR was conducted in a total of 13 clusters. A detailed action plan was put in place for the implementation of the cluster MRR exercise within the available timeframe.
Weighting the two indicators equally gives an overall score of A+.

Summary of responses to issues raised in previous annual reviews (where relevant)

One recommendation from the 2016 AR was that DFID should have been consulted on the decision to delay updating the MRR in December 2015. In response, UNDP committed to keeping DFID better informed and involved in key decision making going forward. Communication between UNDP and DFID has improved over the past year. Nevetheless, this is an area for continued focus, in order to monitor and mitigate risks of potential implementation delays in the next phase of the programme.

Recommendation for 17/18

New DFID programming for 2017-19 will include the implementation of projects that have been developed at a cluster level. Thought should be given on how DFID contributes to cluster projects in a way that strikes the balance between respecting the community/GoL planning and approval process whilst also delivering within the scope of DFID’s timeframes. Whilst increased GoL involvement is extremely welcome, there needs to be a balance between GoL oversight and consultation, and timely delivery of projects as this remains a key risk to successful delivery. UNDP, with DFID support, should manage GoL engagement to ensure projects are implemented within the timeframe of the programme. (Recommendation 4)

Output Title	Municipal services and livelihoods initiatives improved
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Proportion of municipal service projects identified in community plans which are fully completed	100%	100%
2.2 Number of direct beneficiaries of completed municipal service projects.	350,000	436,524
2.3 Number of direct beneficiaries of completed livelihoods projects	9,000	10,248

Key Points

This output has scored a ‘A: outputs met expectations’.

Of the 251 municipalities identified as most vulnerable in Lebanon, the UK has supported a total of 51 (19 in the first phase of the programme, plus an additional 32 municipalities in the Bekaa, South and North of Lebanon, including the city of Tripoli). In selecting the 51 municipalities for UK support, geographical location, confessional balance and conflict vulnerability were taken into account to ensure the best strategic fit with UK policy and objectives

Indicator 2.1 is scored ‘A’: met expectations. Originally all projects were to be completed by March 2017. The lengthy approval process following municipal elections in May 2016 meant that the original timetable was revised, with the initial target for completion of 91 projects (72 municipal services projects and 19 livelihoods projects). As of June 2017, UNDP have reported all projects have been completed.

Indicator 2.2 is scored A+: moderately exceeded expectations. UNDP have reported the number of direct beneficiares of completed municipal service projects (436,524) to be higher than the original target (350,000). However, it is not clear whether these are unique beneficiaries, or if there is some double-counting within this figure.

Output indicator 2.3 is scored A+: moderately exceeded expectations. UNDP has reported that LHSP strengthened livelihoods opportunities for farmers, host communities, and vulnerable groups through the implementation of 19 projects benefitting 10,248 vulnerable people of which 8,606 are Lebanese and 1,642 are Syrian. The projects implemented under this component were identified through the MRR and covered the agricultural sector in terms of construction works, and the agro‐food sector in terms of support to two community kitchens. Overall, the interventions employed 286 workers generating 20,277 worker days.

Weighting all indicators equally would give an overall score of A+. However, we attach greater weight to successful completion of municipal service projects and given the risk of double counting of beneficiaries under indicators 2.2 and 2.3, therefore determine that a score of ‘A’ overall is appropriate.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations from 2016 AR:

- DFID and UNDP need to invest more time in ensuring the logframe for this intervention is kept relevant and up to date. Better use of the programme logframe on both sides as a management tool could have ensured differences in expectations around delivery were identified earlier.
- Similarly, whilst increased GoL involvement is extremely welcome, a balance needs to be struck between GoL oversight and consultation, and timely delivery of projects. DFID should continue to talk with UNDP about this, and ensure timelines for project delivery are proportional.
- DFID will continue to closely monitor UNDP’s delivery of the 90 [later 91] projects under Output 2 and stress the importance of no further slippage to the timelines.

DFID have continued to monitor closely UNDP’s delivery of 91 projects on field visits and quarterly reporting and performance has been good, with all 91 projects completed by the end of the programme. Nevertheless, these recommendations remain relevant and should continue to be prioritised in the coming year.

Recommendations for 17/18:

DFID and UNDP should continue to invest time in ensuring the logframe is kept relevant and up to date. It is also recommended that DFID develop an M&E plan that includes spot checks on progress of projects. (Recommendation 1)

DFID to review methodology used by UNDP on beneficiaries who benefit from municipal services projects to ensure there is no double counting. This was also a recommendation that came out of the external evaluation. (Recommendation 9)

Output Title	Municipal management capacities strengthened and provision of local services improved
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
3.1 # of new elected municipal members trained	1200	737
3.2 # of schools and SDC rehabilitated	4	4
3.3 # low-voltage transformers installed in 50 most vulnerable municipalities	94	79
3.4 # of households benefitting from the installation of solar home systems (kits)	700	978
3.5 # of solar street lighting poles distributed in vulnerable municipalities	270	323

This output has scored a ‘A: output met expectations’. Indicators were met or exceeded in three of the five indicators, output indicators 3.1 and 3.3 were moderately under the original target. However, the explanation provided by UNDP for not meeting this target was considered reasonable. Weighting each indicator equally gives an overall score of ‘A’.
Output indicator 3.1 is scored B: moderately did not meet expectations. The capacity building programme was designed following the 2016 municipal elections to provide immediate support to the newly elected municipal bodies in key aspects of municipal work such as good governance, financial management and local development in Lebanon. 737 participants attended the training which was lower than the 1200 target figure. This was in part because UNDP’s implementing parther, the Institute of Finance (IoF), reached out to 300 municipalities but only 260 wanted to participate.

The number of participants per municipality was also lower than expected. UNDP expected an average of 4 participants per municipality, based on a previous capacity building programme conducted by IoF,. However, only an average of 3 people per municipality participated. UNDP highlighted a lesson learned for not meeting the set target was the need to review expected beneficiary numbers in rural areas where municipalities are small and the staff is very limited, particularly considering that municipal council members are volunteers.
Output indicator 3.2 is scored A: met expectations. DFID’s intervention on the rehabilitation of schools and Social Development Centres (SDC) targeted the SDCs of Syr Danniyeh, Khreybet El Jundi and Qobbeh-Tripoli and the Intermediate Public School of Halba in the North benefitting 31,301 Lebanese and Syrian in total.
Output indicator 3.3 is scored B: moderately did not meet expectations. 79 pole-mounted low voltage transformers were installed in Mount Lebanon (28 units), Akkar (22 units) and North of Lebanon (29 units), against a target of 90). 7,031 households were affected with 35,155 direct beneficiaries.
Output indicator 3.4 is scored A+: moderately exceeded expectations. 978 solar home systems were installed within some of the most vulnerable households within Danniyeh area (against a target of 700).
Output 3.5 is scored A+: moderately exceeded expectations. 323 public solar-powered street lighting poles were installed (against a target of 270), benefiting 36 villages among the most vulnerable host communities.
Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Output Title	Livelihood opportunities strengthened for the most vulnerable population
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
4.1 # of youth supported through dual vocational training programme (Disaggregated by gender and age group)	680	686
4.2 # of cooperatives that improved their assets value	5	25

This output has scored an ‘A+: outputs have moderately exceeded expectations’.
Output indicator 4.1 is scored A: met expectations. In total 686 youth have participated in dual vocational training from across the country. In order to identify the most vulnerable, UNDP use a selection criteria that looks at socio-economic vulnerability, qualifications, general employment situation and household characteristics. Selection is through two stages of a screening process under the overview of MoSA and the UNDP Area Coordinator in order to improve target selection.
Results of the evaluation questionnaire submitted to the youth enrolled in the training shows that 93% of the respondents felt that their employability skills were strengthened through the trainings and 95% of the respondents found the internship useful for future employment. MSMEs have also benefited from a two months’ internship of qualified trained skills tailored to the MSMEs needs as per the market assessment.
Output indicator 4.2 is scored A++: substantially exceeded expectations. DFID’s contribution has supported 25 cooperatives across the country, providing tools and equipment to improve their efficiency and increasing their assets value. In the identification of the cooperatives to be supported and the equipment to be provided, the results of the rapid assessment of the 5 cooperatives initially planned to be targeted showed that the needs of these cooperative cannot be tackled within the timeframe of the DFID contribution. UNDP conducted an additional assessment on a larger number of cooperatives to identify their needs and define interventions feasible to be implemented within the available timeframe, resulting in 25 cooperatives being supported instead of the 5 initially planned. Arguably, the logframe targets should have been adjusted at this stage to reflect the changed expectations.

Weighting each indicator equally gives an overall score of A+ for this output.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2016 Annual Review recommended having a strategic discussion on the split of DFID’s allocation to livelihoods vs basic service delivery projects going forward. This took place as part of discussions around the current phase of support to LHSP. It was decided to focus on basic service delivery since the DFID bilateral programme has a strong economic development and job creation focus.
Recommendation for 17/18:
Statistics on job creation have not previously been captured consistently which makes it more difficult to agree on the level of impact in the livelihoods sector. As DFID scales up its funding between 2017-19, it is recommended that the DFID team work closely with UNDP on assessment methodology to assess numbers of jobs created and the cost per additional job created across different project types (recommendation 8).

Output Title	Social stability mainstreamed through local and national channels
Output number per LF		5	Output Score
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
5.1 # of reports and studies produced and shared (disaggregated by conflict analysis reports, media monitoring reports and conflict mappings at municipal level)	5	5
5.2 n.of viewers of the CMA page (Conflict Mapping and Analysis)	350	399
5.3 # of disputes resolved by the MSS local commitees	10	10
5.4 # of activities organized by the MSS local committees	19	38
5.5 # of new and existing MSS committees sustained (disaggregated by new and existing)	30	28

This output scored an an ‘A – outputs met expectations’.
Output indicator 5.1 is scored A: met expectations. Conflict analysis reports are produced by UNDP in partnership with a local NGO, Lebanon Support, through DFID funding. This year, DFID funding contributed to 5 conflict analysis reports focusing on Sahel Akkar area in North Lebanon, Central and West Bekaa.
Output indicator 5.2 is scored A: met expectations. The Conflict Mapping and Analysis page received an average of 399 views per month over the year, against a target of 350 per month.
Output 5.3 is scored A: met expectations. UNDP has been following up on the mechanisms for social stability implemented under previous DFID funding to LHSP in 8 communities in the Bekaa and 20 in the North and Akkar. UNDP have reported 13 disputes of which 10 were resolved by the MSS local committee. UNDP note that some disputes are resolved directly by the municipality and some disputes are not reported by the committees. In addition, they note that the committees cannot intervene in all disputes instantly: they need to be a cohesive group and gain the trust of the community before being able to intervene. Many incidents were recorded to have been between Syrians and Lebanese.
Output 5.4 is scored A+: output moderately exceeded expectations. 38 activities were organised by local committees established under the Mechanisms for Social Stability (MSS) component, against a target of 19. The reason for overachievement was that the committees preferred to implement several activities/events with the available budget instead of implementing 1 activity, as originally planned.
Output 5.5 is scored B: output moderately did not meet expectations. 28 MSS commitees were established or sustained, against a target of 30 (8 in Bekaa and 20 in the North and Akkar).
Weighting each indicator equally gives an overall score of A: met expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2016 Annual Review recommended that “DFID should continue to work with UNDP to share conflict analysis findings widely with stakeholders, including MoSA, mayors and municipality members, as well as other donors and NGOs. This will include establishing how best to collate and build on analyses to date.”

DFID has worked closely with UNDP so that conflict analysis findings are shared with stakeholders. A key lesson that UNDP has highlighted is that this is a highly sensitive area and even documenting some well known facts on Lebanon’s political actors, systems and dynamics can be challenging if published with a UN Logo.

Recommendations for 17/18:
DFID to explore with UNDP how they are sequencing the next round of MSS into the MRR process which would allow greater representation of actors who are not involved in the MRR . It is also currently not clear how activities and expected outcomes of the MSS are monitored to see which conflict drivers are being addressed and how effectively. It is therefore recommended that the DFID team work with UNDP on their M&E framework to ensure that peace indicators are included and are aligned with the MSS analysis (recommendation 6).

Output Title	Capacities of MoSA strengthened to better respond to the Syrian crisis
Output number per LF		6	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
6.1 # of MoSA staff trained for the implementation of the MRR at cluster level (Disaggregated by gender)	120	127
6.2 # of staff supporting MoSA and LHSP	9	9
6.3 # of MoSA staff trained on the MSS methodology (Disaggregated by gender)	120	120

This output has scored an ‘A – outputs met expecations’. Indicators were weighted equally in assessing the overall output score.

Output indicator 6.1 is scored A: met expectations. 127 MoSA staff (particularly staff of the Social Development Centers) were trained to implementation the MRR at cluster level, against a target of 120.

Output indicator 6.2 is scored A: met expectations. A recommendation from the previous DFID AR was that UNDP recruit staff to support the MoSA team in monitoring LHSP activities. This target has been met, with 9 staff recruited against a target of 9.
Output indicator 6.3 is scored A: met expectations. A capacity building program for 120 Social Development Centre (SDC) staff from Mount Lebanon/Beirut, Baalbek/ Bekaa, Akkar, North, South and Nabatieh governorates was implemented during January and March 2017. Training sessions focused on inclusiveness and understanding conflicts. Tools such as stakeholders’ analysis, analysing positions and interests, data collection questionnaires; quantitative and qualitative interviews were all introduced and discussed.
Summary of responses to issues raised in previous annual reviews (where relevant)

UNDP identified in its 2016 proposal three lessons to improve the MRR methodology which were also highlighted in the 2016 annual review:

- Additional capacity building of MoSA staff on the MRR implementation
- Allocating more time for implementation of the MRR (from two to five days for completing the assessment, data entry and Municipal Action Plan elaboration)
- Allocating additional resources for follow up and implementation in municipalities not yet covered by the programme
With the objective of supporting the MoSA central working team in monitoring LHSP activities, additional supporting staff were recruited including a Junior Information Management Assistant, Data Revision and Quality Assurance Officer and a Driver. A Senior Policy Advisor was also recruited to support the Minister of Social Affairs.
UNDP have also reported that follow up and monthly coordination meetings take place between the LHSP central working team, MoSA area coordinators, UNDP Area Managers, the National Coordinator for LHSP and the Chief Technical Advisor of LHSP to: follow up on the implementation of the MRR and MSS activities, exchange experiences, discuss lessons learned and challenges, evaluate the methodology and tools and propose solutions for ensuring effective implementation of activities.

Recommendations for 17/18:

None

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key cost drivers are materials and labour required for construction of municipal projects, staffing costs for capacity building activities and management costs. In-country operational and running costs were particularly high in 2016/17, as noted in the DFID’s internal audit report: 15%, on top of the 8% sent to UNDP headquarters for general administration costs. This was due to the short time frame for implementation (with UNDP having to internally recruit a number of staff e.g. engineers, who they would normally have contracted through external providers). Operational costs will revert to 6% from 2017, since UNDP will have a longer lead time for planning and implementation.

Interviews conducted with partners during the Internal Audit visit suggested that VfM is primarily considered a procurement issue, and that the role of VfM in other areas (e.g. driving down administrative or staffing costs or maximising impacts) is not well understood.

VfM performance compared to the original VfM proposition in the business case

n/a

Assessment of whether the programme continues to represent value for money

It was observied during field visits that the UNDP team have worked closely with municipalities on the implementation of MRR actions plans to ensure VfM and sustainability of projects. For example, the rehabilitation of the school in Heba was implemented in two phases, with the UK-DFID contribution covering the second phase (the first phase of the project was funded by the Lebanon Recovery Fund (LRF)). Moreover, the works complement a previous intervention implemented by UNDP through the contribution of the European Union (EU), which consisted of the provision of a water treatment system, medical equipment, furniture, and IT hardware for the medical room.

On the whole, DFID still assess that the programme is representing good VfM. Through continued support and by improving the capacities of MoSA, LHSP continues to play a crucial role in strengthening our relationship with the Government of Lebanon.

DFID will look more closely at the VfM of this programme as part of its implementation of a new VfM strategy and work closely with UNDP to ensure VfM is considered across the programme. In country operational and running costs will revert to 6% (from 15% in 2016/17). Additional VfM indicators should be included in the revised logframe. (recommendation 10)

Quality of financial management

UNDP’s financial management of the programme has been adequate but could be strengthened. We recommend that for the next phase of the programme i) budgets should be submitted in GBP and ii) more detail should be given in financial reports, with a financial narrative included. In line with IAD recommendations, DFID will also seek verification of payments. (recommendation 11)

Date of last narrative financial report	29/05/17
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

The overall assessment of risk has not changed from the previous Annual Review. UNDP has delivered LHSP in Lebanon’s challenging context for almost three years. Whilst the challenging regional and domestic context mean the risks associated with this programme were high, accordingly, social and political dynamics that are key risk factors for violence in Lebanon were included in the design of the programme, with the aim of treating and mitigating some of these risks, lowering the overall risk rating to moderate.

UNDP programmes and projects are all managed through a Results Based Management (RBM) system, a customised version of PRINCE-2. The RBM approach clearly specifies that any major deviation from the approved work plan will be presented to the committee for approval. A Risk Log and an Issues Log are maintained for the project. There were no significant changes to the Programme Risk Register as presented in the original programme proposal. However, management of risk continues to be an area that merits particular focus and it is suggested that UNDP and DFID hold more regular discussions on risk, using the updated risk register as a risk management tool.

DFID has requested an updated version of UNDP’s risk register moving into the third year to ensure UNDP’s and DFID’s assessment of the risks associated with this programme are aligned. DFID have also requested that UNDP undertake supply chain mapping to better assess fraud risk and potential conflicts of interest. (recommendation 12)

Outstanding actions from risk assessment

N/A

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The planned timeframe was revised following municipal elections last year to allow more time for project approval and implementation. Delivery has remained on-track relative to the revised timeframe. Looking forward, DFID should hold discussions with UNDP to ensure expectations are aligned with the timeframe for the next phase of the programme, particularly given the shift to larger, more complex projects, involving clusters of municipalities.

Performance of partnership (s)

DFID and UNDP have developed a strong working relationship throughout the lifetime of LHSP which ensures, even as the multi donor funded programme grows, the UK has a strong voice in the direction of the programme. The previous annual review reflected a breakdown in communication regarding expectations around delivery which resulted in the logframe needing to be revised. This communication has since significantly improved, with regular meetings held between the DFID team and UNDP. This is reflected in strong programme performance this year. Nevertheless, it is important that strong communication continues to be prioritised in the coming year, in order to monitor and minimise the risk of slippage.

The programme is involved in coordination at the national level, via UNDP and LCRP structures, and at the regional level, via inter-agency LCRP working groups.

UNDP have demonstrated commitment to ensuring LHSP continues to be evaluated and that lessons learnt are implemented to improve the impact of the programme. Given the number of donors now involved in the programme, it is recommended UNDP set up a donor working group to help improve coordination and to allow regular reporting on lessons and progress in implementing recommendations (recommendation 7).

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

DFID has worked with UNDP and Aktis to survey both Lebanese and Syrians regarding their perceptions around impact of programming. The evidence base for the LHSP is based on a number of studies that continue to show the importance of municipalities as the frontline of coping with the rapid influx of the large number of Syrian refugees into Lebanon.

UNDP have contracted Aktis to undertake perception surveys using a novel methodology that involves community members telling a story about a change (positive or negative) in their community. This then enables Aktis to elicit detailed information about community concerns and changing perceptions. However, due to budget constraints, there are no ‘control’ municipalities included in the Aktis survey i.e. similar municipalities where no LHSP projects are implemented. This will make it difficult to draw conclusions about what role, if any, LHSP has played in alleviating tensions. Even with control municipalities, it would be difficult to draw conclusions on the impact of LHSP as a whole, since the survey is only being carried out in 9 out of 251 vulnerable municipalities. Nevertheless, the surveys will provide important contextual information to help inform the assessment of programme outcomes.

Recommendation: UNDP to review how M&E tools could better measure outcomes of the programme (recommendation 13)

Monitoring progress throughout the review period

Alongside formal quarterly reports, the programme team has conducted a number of visits to municipalities across the country to see first-hand work across service provision, livelihoods and mechanisms for social stability, and speak with local government officials and beneficiaries. The team visited projects in six municipalities (3 in the South; three in the North). Key points from the field visits:
- Tensions remain high with competition over jobs and pressure on services highlighted as key sources of tension;
- Municipal members and beneficiaries talked about the positive changes brought about from the various projects (including increased incomes, support to the local economy, jobs and improved social services);
- Municipal council members spoke positively about the MRR process and noted that the projects supported through the LHSP had been priorities emerging from the MRR process;
- Several projects were supplemented/complemented by support from other donors (e.g. Japan had funded a crèche next door to the UK-funded refurbishment of a Social Development Centre, with external rehabilitation work funded by USAID, and NGOs offering training courses) suggesting good coordination with other agencies and funds.
- One refurbished health centre in the North was not yet operational (despite having been completed in November 2016) as it was still subject to final checks from the Ministry of Health.
- One Mayor commented on the time-lag of getting approval for the second phase of a wastewater project (the first phase had been supported by LHSP last year; the second phase is under consideration for the latest phase of UK support) which was causing some tension between stakeholders in the community given that half the village is not benefiting from the project.
- Whilst municipality members mentioned positive changes brought about as a result of the UK investment to the programme, they also requested continued support to tackle the scale of issues faced by host communities as a result of a large number of Syrian refugees.

Conflict Sensitivity

The projects are identified through a conflict-sensitive needs assessment methodology (Maps of Risks and Resources -MRR), owned by the municipality and fully endorsed/owned by Lebanese Government’s Ministry of Social Affairs (MoSA). The MRR helps the municipality assess critical needs, identify appropriate projects to address these and and prioritise projects in a highly participatory way, involving the community. The programme then provides funding to municipalities, managed by UNDP, which allows them to finance additional public services and projects that have been identified as a priority by the municipality.

A recommendation from the external evaluation was that the conflict mapping process (MSS) should be integrated into the MRR process. This will also have the additional benefit of allowing some degree of participation of Syrians in the overall process, even if they are not involved in the actual prioritisation process. The external evaluation also suggests that the peace-building activities that are developed after the conflict mapping should be delivered through SDCs as part of a capacity development process. Particular attention should be paid to ensuring that the completed M&E framework enables strong reporting of peace-building results. (recommendation 6)

Additional indicators of effective sensitivity are the way that a project sets up its accountability systems, responds to feedback and adapts to the changing context. DFID will explore the strength of these mechanisms with UNDP as well as the feasibility of the evaluation ideas in the coming period.

Gender Sensitivity

Gender has been mainstreamed throughout all interventions and UNDP reports that women and men have been equally involved in activities as beneficiaries. Gender disaggregated data is presented in the logframe. Advocacy and capacity development support was provided to implementing partners to mainstream gender considerations throughout project implementation. Gender sensitive project communications and campaigns were also carried out to engage women as primary beneficiaries (e.g. in flyers and television clips UNDP ensured images and text did not reinforce gender stereotypes in relation to types of work and instead highlighted cases of women working in non-traditional areas, such as agricultural labour.

Through the vocational training programme, support was provided to 292 young women beneficiaries who wish to enter non-traditional fields of work (e.g. in Mount Lebanon 15 women were trained in car mechanics, car electricity and mobile repair). 42% of beneficiaries of vocational training were women. Gender sensitization for SMEs hosting interns was also conducted. In addition, a significant focus was placed on women as direct beneficiaries, particularly through the direct support to women cooperatives. Four cooperatives supported through the programme are female-headed cooperatives, whilst an additional 10 have women as members of the cooperative.   Nevertheless, women represent a small proportion of cooperative members overall: only 204 out of 3112 (7% of) beneficiaries of cooperative support were women.

The interventions supported the building of women’s negotiation capacities and the gender sensitization of men  to contribute to gender responsive conflict prevention and peacebuilding interventions. This included supporting coalition building of women’s networks to enable them to voice their priorities during decision making over recovery priorities and re-establishment of basic services (MRR, conflict prevention activities).

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process