ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Access to Family Planning Commodities
Country or region targeted	Nigeria
Type of cost extension (if applicable)	Bridge funding
Original project budget	£18m
Original project start and end dates	15 September 2011 to 30 September 2017
Cost extension value (if applicable)	£6m
New project end date (if applicable)	30 June 2019
Business Case Quest Document No.	3716678

INFORMATION
What is the project’s purpose?
The Access to Family Planning Commodities project aims to improve maternal and child health in Nigeria by ensuring that women and men have access to, and use, a mix of quality contraceptives. / Nigeria, with a projected population of 184 million (2015) and an annual population growth rate of 3.2% is set to double its population in 22 years. Family planning is central to achieving the Sustainable Development Goals in Nigeria. Without moderating fertility and population growth rates it is unlikely that living standards can be sustainably improved to a reasonable level for the majority of Nigerians. High fertility rates (the average number of births per woman) also drive high levels of maternal mortality. More than 30,000 Nigerian women (14% of the world’s total) die every year of pregnancy related causes. / DFID Nigeria launched the £18m Access to Family Planning Commodities (AFPC) programme in 2011 to ensure men and women have access to an optimum mix of family planning commodities. The programme consists of a £3 million annual contribution to a pooled fund for procurement of public sector family planning commodities, managed by the United Nations Population Fund (UNFPA). Other contributors to the pooled fund include the Government of Nigeria, Canada, and UNFPA. DFID, through this programme, currently finances around 40% of the cost of public sector contraceptive procurement. / The programme has shown strong performance, delivering 7.5 million Couple Years of contraceptive Protection (CYPs) over six years, which is estimated to have averted almost 1.6 million unintended pregnancies and 9,613 maternal deaths, exceeding business case targets. The proportion of health facilities which reported no stock-outs of contraceptives increased from 42% in 2011 to 77% in 2016. The programme has contributed to a significant increase in uptake of family planning in Nigeria in recent years (some data suggests contraceptive prevalence rates may have doubled – from a low base - over the last three years). AFPC has also helped leverage increased funding commitments and the removal of family planning user fees by the Government of Nigeria. The programme scored an A+ (outputs moderately exceeded expectation) at its last annual review. / The programme offers strong value for money. Funds have been saved by reduced clearing and freight costs as well as negotiated prices for contraceptives procured through UNFPA’s global procurement mechanism. An analysis by the USAID DELIVER project estimated annual savings of 20 – 25% of the expected cost of procurement of contraceptives for all funds in the basket. When applied to DFID funds alone the annual savings generated were between 19 – 39%. Additionally, the procurement of Long Acting Reversible Contraceptives (LARCs) contributed to a more effective mix of contraceptives, and contributed to a higher CYP at lower costs. As a result of the cost savings and improved method mix, the programme exceeded business case CYP targets and exceeded by 25% and 28% respectively the number of unintended pregnancies avoided, and maternal deaths averted. / The procurement of FP commodities by DFID was an important catalyst for actions down the supply chain. The fact that FP commodities were brought in the country resulted in a policy on free FP services in Nigeria, Government commitments on FP for the first time, an increasing numbers of partners involved inFP logistics management. In addition, new software was introduced to improve monitoring of FP commodities through the supply chain which triggered improved integrated supply chain management of essential medicines and contraceptives, and led to reproductive commodity supply meetings across the whole country, improving coordination, capacity building and awareness of family planning. / While the programme has performed well, and significant gains have been made, contraceptive usage in Nigeria remains at low levels, with surveys showing contraceptive prevalence rates of between 10 – 20% in recent years. Lessons learned from the AFPC programme indicate the need to address demand side barriers to uptake of family planning, and to target underserved groups such as married adolescents, in additional to securing commodity supply. These will be taken forward in a proposed DFID Nigeria family planning scale up programme, planned to start in late 2018. / The proposed cost-extension to the AFPC programme will act as a bridge between current DFID family planning programming in Nigeria, and the proposed scale up programme.
What is the objective of the cost extension or other changes?
To extend DFID Nigeria’s successful Access to Family Planning Commodities Programme for an additional 21 months, which will provide contraception for 1 million Nigerian couples over a two year period. As with the existing programme, the additional funding will contribute to a UNFPA managed pooled fund for procurement of contraceptives. It will help prevent stock-outs of contraceptive commodities over the period, contribute to DFID’s global target of 24 million additional users of family planning by 2020, and bridge to a new DFID Nigeria family planning scale up programme planned to start in 2018.
What is the additional and total support the UK will provide?
The UK will provide an additional £6 million to increase the programme funding from £18 million to £24 million and extend the programme by an additional 21 months to June 2019.
What are the expected results?
The cost extension will procure and deliver two million Couple Years of contraceptive Protection (CYPs) to couples across Nigeria through public health facilities. It will ensure at least 80% of family planning service delivery points experience no commodity stock-outs in the previous three months. / The cost extension will contribute 120,000 additional users of family planning to DFID’s global Family Planning 2020 target and avert an estimated 200,000 unintended pregnancies and 2,500 deaths of pregnant women.
What is the approach to implementation?
This project is implemented through an MoU with UNFPA. The cost extension will be implemented through an amendment to the existing MoU. As with the existing programme, DFID funds will contribute to the UNFPA managed pooled fund, along with funds from government of Nigeria, other development partners and UNFPA to procure and distribute contraceptives to health facilities across the country using a coordinated approach. / DFID technical coordination and direction of the programme will continue to be provided by the programme SRO/lead adviser. Project management support will be provided by a Programme Officer within the Human Development (HD) Team. / Gender Equality: Access to family planning is central to achieving gender equality. When women and couples are empowered to plan whether and when to have children, women are better enabled to complete their education; women’s autonomy within their households is increased; and their earning power is improved. This strengthens their economic security and well-being and that of their families. Cumulatively, these benefits contribute to poverty reduction and development[1].
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
Implementation of this programme so far has confirmed the validity of the original theory of change and approach. Therefore, no major changes are proposed to the original business case and theory of change during the extension period. However, evidence and lessons learned during implementation of the programme also indicates significant opportunities to secure additional benefits by addressing both supply and demand side barriers to uptake of family planning, and targeting underserved groups, such as married adolescents. These will be taken forward in the proposed DFID Nigeria family planning scale up programme planned to start in late 2018.
[1] UNFPA http://www.unfpa.org/family-planning#sthash.TJmlGhH0.dpuf