Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	23/02/2018

Title: / PATH Meningitis Vaccine Project (MVP)
Programme Code: / 202045	Start Date: / 1 November 2010	End Date: / 26 November 2017
If programme was closed >1 month early please describe in a few words why.	PATH MVP has been awarded new funding

Summary of Programme Performance

Year	2011	2012	2013	2014	2015	2016	2017
Programme Score	75/100	A	A	A	A	A	A
Risk Rating	High	High	High	High	High	Major	Major

Financial Position

Original Programme Value	£3,619,788
Extensions/ amendments	£2,170,000 / (24 February 2015)
Log-frame revisions (with dates)	May 2016 / Jan 2017
Total programme spend	£5,775,788.00

Follow up actions required following closure
The important work of the PDP will be continued in a new funding phase starting 2018. This will ensure that further necessary clinical trials can be conducted for the initial licensure and WHO Prequalification of the conjugate vaccine. Additional funding is currently being acquired for another Phase 3 trial not yet covered by the new phase of DFID funding.

Overall, the development, although still at high risk, look highly promising, given the results obtained over the funding period. If successful the conjugate vaccine could be seen as a game changer to eliminating epidemic meningococcal meningitis in the African Meningitis Belt and therefore prevent thousands of lives and disabilities.

More work could be done to showcase the early successes of MVP. The team could explore a number of avenues to highlight their progress. More information about the potential benefit to countries could help obtain funding for an additional trial that is required.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202045/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202045/documents

Outline of programme and what it has achieved
The UK has supported the Meningitis Vaccine Project (MVP), a Product Development Partnership (PDP), in its current phase since 1 November 2010. The project aimed to develop a polyvalent meningitis vaccine for Sub-Saharan Africa that will control the remaining 15% to 20% of meningococcal infections not covered by the existing meningitis A vaccine, MenAfriVac®. MenAfriVac® had been developed by the same group in an earlier phase, and, following its introduction in 2010, more than 270 million individuals have been vaccinated against group A meningococcal disease and, subsequently, Group A meningococcal disease has virtually disappeared in all countries that have immunised 1-29 year olds. This vaccine, however, does not target all the disease-causing serogroups and a new vaccine is required to prevent the remaining 15% to 20% of meningitis infections caused by other meningococcal serogroups (C, W, X and Y).

Meningitis is a deadly and debilitating disease that causes an estimated 70,000 cases/year alone in an area of sub-Saharan Africa known as the “African meningitis belt”. Despite treatment measures, meningitis kills one in ten people who are infected (and 50% of those not treated) and leaves one-quarter of survivors severely debilitated.

This investment is part of DFID’s wider approach to fund PDPs, which fill a critical research gap into essential technologies. Funding gaps in research occur where markets are not sufficiently powered to allow for funding of research through patent-development, and this is particularly true for vaccines and medicines that are designed to treat neglected diseases that affect the world’s poorest populations. Additionally, funding gaps occur where there are no current products or where those that exist are too expensive, difficult to access, no longer produced, highly toxic or ineffective. These factors have resulted in a limited research base with MVP being one of only a small number of organisations engaged in this area. MVP engages private-sector collaborators to apply their development, manufacturing, and distribution strengths to innovate technologies that would not be a private-sector priority, and therefore achieve maximum sustainable benefit for public health in developing countries.

MVP aimed for:
- Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature and meets a target-price of less than $5 per dose.
- Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrate the vaccine’s safety and immunogenicity, in partnership with the Serum Institute of India Private Ltd. (SIIPL)

Support to MVP will, in the longer term, contribute to the impact of reduced poverty through improved and affordable prevention of a common disease among the poor in the African meningitis belt.

The project has continued to demonstrate steady progress throughout the final year of this funding cycle and, indeed, throughout its lifetime. A new meningococcal conjugate vaccine covering serogroups A, C, W, X and Y (MCV-5) has been developed by SIIPL through a PATH/SIIPL partnership. Safety and immunogenicity tests were successfully completed and showed no serious adverse events and confirmed that further study phases can commence. Phase I is complete and Phase II has commenced and enrolment will be completed in March 2018, with further data available later in 2018. Delays in previous years (due to inevitable changes in the study location) have been mostly compensated by stringent and effective management and operation. Although, as with all vaccine trials, a high risks remains until larger trials have been successfully completed, the project looks set to deliver a vaccine that would not only eliminate the remaining burden of epidemic meningococcal meningitis in Africa, but will also be heat stable and be accessible in more complex circumstances and environments. Funding for continuation of this development, including 2 further clinical trials have been agreed by DFID until March 2021.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment A – Outcome met expectations

MVP has made very good progress throughout its lifetime (and in the last reporting year in particular) to meet its outcome – that is to develop a pentavalent, heat-stable meningococcal conjugate vaccine that has the potential to eliminate epidemic meningococcal meningitis from sub-Saharan Africa. Clinical trials have progressed as expected and further clinical trials are on track.

Output Score and Description

MVP has made very good progress during the final year of this funding phase. The Phase 1 clinical trial (the first in humans) is complete and showed success both in terms of safety as well as immunogenicity, implying that it is safe and effective under the very limited circumstance that a Phase 1 clinical trial allows to judge. The work is being repeated in a larger study in one of the target countries (Mali), where Phase 2 is now under way (in toddlers), with results expected by end of 2018.

Based upon a revised clinical plan, the Phase 1 study took place in the USA, conforming to high quality and regulatory standards. This new design provided potential to move directly into two parallel Phase 3 studies in Africa and India that are designed to lead to licensure and WHO prequalification. The US Food and Drug Administration (FDA) had given positive feedback on the pre-Investigational New Drug (IND) submission, required before any clinical trial can begin. PATH has been the regulatory sponsor of the Phase 1 trial.

PATH has also led a collaborative modelling team to model the cost-effectiveness of the various MCV-5 introduction strategies on meningococcal disease in the African meningitis belt. This will be a key step towards ensuring that third party donors (notably GAVI) will have the cost-effectiveness data to ensure uptake of the vaccine into regular preventive programmes.

The polyvalent meningococcal vaccine candidate against serogroups A, C, Y, W and X has the potential to eliminate meningococcal meningitis from the African meningitis belt.

During the reporting year, PATH revised the clinical plan to build safely and effectively on the success of MenAfriVac®. The new plan incorporates a Phase 1 safety and immunogenicity study in adults in the USA followed by a Phase 2 trial in African toddlers.

Lessons and how these have been shared

Over the duration of the project, it was necessary to alter the study design to conduct the first clinical trials in humans in the US with stringent conditions and regulatory approval. This work has been completed successfully allowing the continuation of Phase 2 and 3 trials, but the change of study design and approvals has taken time. The delays have now been more than compensated by the unqualified success of the Phase 1 trial.

Provided all further clinical trials will be equally successful, it is important to work towards inclusion of the pentavalent vaccine in preventive vaccination programmes to avoid any outbreaks. Cost-considerations may be an impediment, depending on resources and strategic decisions by GAVI and other stakeholders. PATH will further influence these discussions, using the cost-modelling exercise and ensuring the debate includes messages on the major health risk of the remaining burden of disease.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Refine the Pipeline of Effective vaccines for Meningitis
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	75
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
MCV-5 candidate progressed through manufacturing and preclinical testing	MCV – 5 manufactured and toxicology assessments complete by Q2 2016	Achieved in 2017: external assessment confirms MCV-5 candidate safe and well tolerated
Phase 1 study completed	Phase 1 study completed by December 2017	Achieved: Phase 1 trial successfully completed
Phase 2 study completed	Phase 2 under way in Africa	Phase 2 commenced in October 2017

Key Points

The output has met expectations. The Phase 1 clinical trial (conducted at the Center for Vaccine Development in Baltimore, University of Maryland) demonstrated clinical safety with no adverse reactions shown and immunogenicity confirmed for different preparations of the vaccine (with and without adjuvant). Immunogenicity appeared to be superior to an existing quadrivalent vaccine (Menactra). The Phase 1 was (by design) a small study, and details of the larger population trials in Africa are needed, to confirm these results.

The Phase 2 trial commenced in Mali (in African toddlers) on time (in November 2017). The Data Safety Monitoring Board met in January 2018, when there were no safety concerns. Enrolment is continuing as planned and results are expected by December 2018 (on-time).

Summary of responses to issues raised in previous annual reviews (where relevant)

The logframe targets were revised as stated above. Indicators and targets were adapted into a new logframe for future funding phase.

Recommendations for future programmes

MVP should pro-actively showcase non-sensitive early successes of their work for the polyvalent vaccine on their website.

Output Title	Develop a strategy for the use of the pentavalent vaccine, once available, in place of the existing MenAfriVac® vaccine
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1. Undertake modelling work to build evidence base about use of MCV-5 in vaccine programmes	Modelling complete by December 2017	Achieved: Modelling is complete and first manuscript has been accepted for publication.
2.2. Engage with ministries of health in relevant countries to gather support for use of MCV-5	Engagement with at least one ministry of health in the meningitis belt by Q4 2018	On track: results of clinical trials and modelling work are required prior to any engagement

Key Points

The output met expectations and is on track to meet its milestones and targets. MVP raised a risk that additional costs of the new pentavalent vaccine, that will replace MenAfriVac®, may not be viewed as cost-effective by GAVI, the Vaccine Alliance, and other funders. If MCV-5 is not used to replace MenAfriVac® and is instead used as a stockpile for reactive campaigns, meningitis outbreaks in Africa will continue, as evidenced by the 2015 meningococcal serogroup C epidemic in Niger. In mitigation, MVP is leading a collaborative mathematical modelling team with Harvard University, Yale University, Imperial College London, Cambridge University, the US Centers for Disease Control (CDC), the World Health Organisation (WHO), and the Norwegian Public Health Institute to model the cost effectiveness of various MCV-5 introduction strategies on meningococcal disease in the African meningitis belt. The study will use a cost/benefit model to evaluate four strategies (different vaccination approaches) that should lessen the meningitis burden in the African meningitis belt by 2022.

Summary of responses to issues raised in previous annual reviews (where relevant)

The logframe targets were revised. Indicators and targets were adapted into a new logframe for future funding phase.

Recommendations for future programmes

None

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Vaccine development is a high risk and costly process, particularly in the final stages leading to licensure. As vaccines progress through the pipeline, they enter successively more costly phases of development. The study was relocated from India to Africa in 2015 due to problems in attaining regulatory and ethical approvals and the impact the delays had on work-planning. The change allowed MVP to become more directly engaged in the research trials, but this came at a price due to higher operating costs. The main drivers are staff time, together with laboratory equipment and consumables. This was flagged early on by MVP, which is managing costs appropriately. Additionally, MVP has a partnership arrangement with SIIPL, who are highly experienced in vaccine development and provide cost effective approaches to developing new vaccines.

VfM performance compared to the original VfM proposition in the business case
MVP provides value for money through:

Efficiency: Responsive organisation with small core teams and open research models, to reduce operating costs; using video-conferencing and closely managing attendance at meetings/conferences, doubling up with other work commitments where possible.
Effectiveness: Building on earlier successes and learning from developing MenAfriVac®; Early go/no go decision making using expert Scientific Review Committees.
Economy: Leveraging contributions from the private sector, e.g. the very productive relationship with SIIPL; Developing partnerships with other entities to support joint activities (e.g. clinical trial site development, development and conduct of assays; MVP staff looking for better technical solutions to develop vaccines and sharing knowledge and expertise with other vaccine development colleagues.
Cost-effectiveness: Modelling work to address the issues of cost-effectiveness of using a more expensive vaccine that covers the five groups of meningococcal disease present in the meningitis belt when compared to the existing and highly successful MenAfriVac® which covers one of the serogroups (Group A). This work has shown where vaccination strategies includes a catch-up nationwide immunisation campaigns in young adults, adding MCV-5 into the expanded programme on immunisation (EPI) is cost-effective and would avert a substantial portion of meningococcal cases expected under the current WHO recommended strategy of reactive vaccination. The work highlighted the importance of a preventive campaign approach, rather than a reactive vaccination, to avoid long lead times, that risk the likelihood of many cases and lives lost.

Assessment of whether the programme represented value for money
The programme represented good value for money, despite some inevitable delays and cost increases, because of changes in study sites. The change in study sites represents overall vfm because it will lead to faster product licensure and WHO prequalification. The increased cost is due to the complex nature of the trials and because conducting clinical trials in the US and Africa is more expensive than in India. PATH has considerable expertise in conducting clinical trials in the US and Africa.

Quality of financial management during programme
Throughout the funding cycle, MVP has been responsive to requests for financial and other management information and funding requests have been submitted as agreed. Due diligence on PATH conducted by DFID considers them to be a “low risk”. They have mature systems in place that help protect donor funding and their most recent Annual Audited Statement for the period to December 2016 is unqualified. PATH provides close oversight of downstream partners ensuring that they too have effective systems to reduce the risk of misappropriation and waste. Through the subrecipient agreements, PATH monitors performance and quickly invokes (when necessary) remedial action to deal with non-compliance or poor performance. PATH has a robust policy on Fraud, Corruption and Dishonesty and in addition provides protection to informants through its Whistleblowing policy, which reflects best practice and provides funders with a high level of assurance. There have been no reported cases of fraud or misappropriation to date and PATH are confident in their internal controls and staff awareness.

Date of last narrative financial report	January 2017
Date of last audited annual statement	31 May 2017

E: RISK (½ page)

Quality of risk management over the life of the programme
MVP has reported programme risks in detail, including reporting on mitigating actions.

Most prominent risks and the reported mitigating actions over the funding period were:
1. Technical risks in product development – mitigated by partnering with SIIPL, an experienced vaccine development company with proven track record.
2. The new vaccine may not be considered cost-effective by Gavi the Vaccine Alliance – mitigated by partnering with Harvard School of Public Health and other institutions (incl. Imperial College London) to develop a cost-effectiveness model across a number of countries).
3. Increased costs of trial evaluations – mitigated by designing Phase 2 trial with various time points to provide information about the immune response to identify how many doses are needed.
4. Cost of goods – mitigated by close coordination with vaccine manufacturer, including on-site meetings, to identify and address manufacturing issues quickly.
5. Political instability of African vaccine trial sites – mitigated by including in-depth assessments of terrorist risk, media monitoring, use of information from large organisations in the field (e.g. MSF, WHO, national ministries, USAID) and use of electronic data systems, off-site monitoring and robust emergency preparedness at clinical sites.

MVP take the risks of unintended consequences, (including human rights) to ensure all relevant local and international ethical reviews comply with all the relevant laws and handle real or perceived conflicts of interest.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Changes in the timeframe were flagged early to DFID and agreed (in 2014 and 2015) following the expert recommendation to change the trial locations from India to the US and Africa. Clinical trial sites in India and later in Africa were found to be limited for the First-in-Human trials (Phase 1). The study has now successfully been carried out in the US with the subsequent Phase 2 commenced in African toddlers in Mali.

The changes of location lead to delays, but MVP has made up time against the revised plans by stringent planning and execution of trials.

Performance of partnership (s)
MVP has a productive partnership with SIIPL who have been a collaborator since the inception of this programme. MVP and SIIPL take all operational decisions jointly which helps ensure that they maintain a good working relationship. In addition this helps avoid misunderstanding of roles and ensures a coordinated approach to delivering the workplan. The DFID-MVP relationship is strong and there is regular communication on issues affecting the programme.

Asset disposal and value obtained by DFID
MVP safeguards project equipment purchased with donor funds, through spot-checks over the lifecycle of the product. In line with DFID policy, MVP maintains an asset register that lists any items purchased from donor funds with a shelf-life of more than 12 months and a value in excess of £500. MVP undertakes regular stocktakes and maintains an up to date physical inventory. MVP also undertakes spot-checks of assets allocated to downstream partners. The Inventory is reconciled to the general ledger on a monthly basis. There is one item that can be wholly attributed to the DFID contribution. This item will be required in the next phase of DFID funding. The inventory/ asset register is available to DFID on request.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Not applicable as DFID provides core funds to MVP, no support is provided through government systems

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Group A meningococcal disease has virtually disappeared in all countries that have immunised 1-29 year olds with MenAfriVac®. This has saved many lives and prevented disability resulting from meningitis. It is clear that the benefits offset development costs of the vaccine.

The importance of having a polyvalent vaccine was highlighted in July 2015, when the WHO released information about an outbreak of meningitis serogroup C in Niger where there were over 5,000 cases and 260 deaths. Whilst quadrivalent vaccines are available, they are too expensive to be used in routine immunisation programmes, and do not provide such wide coverage against all the important epidemic serogroups.

MVP launched a modelling exercise to calculate the potential costs of introducing the conjugate vaccine. While this work is still ongoing, the modelling included a calculation of an incremental cost effectiveness ratio of US$49 per disability adjusted life year (DALY) averted, if a vaccine dose could be obtained for US$4 and 91% of DALYs are averted over current reactive WHO strategy. Further cost-effectiveness calculations are under way, including analysis of vaccine use in India for high-risk groups, such as pilgrimages.

The cost-effectiveness work is important to build the investment case for Gavi, the vaccine alliance, and other global organisations, to increase the likelihood of financial support for vaccine distribution and uptake. MVP has engaged in knowledge sharing opportunities through strong professional networks.

MVP is currently fund raising for an additional Phase 3 trial in West Africa, for a recommendation for the vaccine to be used in routine EPI programmes.

Monitoring progress throughout the programme

The review was carried out by members of the Health research team in DFID’s Research and Evidence Division. Members of the review team met with MVP at the PATH headquarters in Seattle in May 2017, and at the DFID offices in London in November 2017, when MVP provided an update on recent progress. The team have had a number of teleconferences during the year, during which progress, challenges and financial issues have been discussed.

Annual Review - Summary Sheet 2014

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / PATH Meningitis Vaccine Programme 2010-2015
Programme Value: £3,619,788		Review Date: October 2014
Project Code: / 202045	Start Date: / 1 November 2010	End Date: / 31 March 2015

Summary of Programme Performance
Year	2011	2012	2013	2014
Programme Score	75/100	A	A	A
Risk Rating	High	High	High	High

Summary of progress

The Meningitis Vaccine Programme (MVP) continues to make good progress, with its work contributing to the elimination of meningitis as a public health problem in Sub-Saharan Africa.

During the reporting period funding from the Department for International Development has enabled MVP to continue the development of a vaccine designed to protect against five serogroups of the bacteria that cause meningitis, (that is, the polyvalent meningococcal vaccine) in collaboration with their partner, the Serum Institute of India Ltd (SIIL). The successful development and introduction of the polyvalent meningococcal vaccine has the potential to prevent meningitis epidemics not currently covered by MenAfriVac (a vaccine against serogroup A meningococcal bacteria) and lead to the elimination of meningococcal meningitis from Sub-Saharan Africa.

The work has progressed well and SIIL have: developed methods to increase the yield and scaled up production of the Men X polysaccharide; shown that vaccine formulations were immunogenic in animals and have selected a heat stable formulation which has similar, or better, immune responses to existing (quadravalent) licensed vaccines. The World Health Organisation (WHO) have supported the proposed product and clinical development plans.

The programme has made significant progress towards the goal of developing a vaccine that does not need to be refrigerated for an extended period of time, which can ensure major cost savings in the distribution of the vaccine. The work has included commissioning a facility dedicated to the production of the vaccine; discussion about the clinical development plan with the Drug Controller General of India (DCGI) and WHO; and planning a Good Laboratory Practice (GLP) toxicology study for early 2015. Permission to conduct a Phase 1/2 safety and immunogenicity clinical trial in adults and children will be applied for in 2015.

MVP has continued to roll out MenAfriVac, bringing the total number of vaccine recipients in the African meningitis belt to more than 151 million, since first introduced in Africa in 2010. Research published in the Lancet of a surveillance study across Chad showed reductions in meningitis incidence by 94% (http://www.path.org/news/press-room/644/).

Lessons learnt
The development of the polyvalent meningococcal conjugate vaccine (active against five serogroups) has been slowed down by a complex patent landscape. MVP and SIIL coordinated with outside patent counsel to complete a detailed patent landscape in 2011, which was updated in 2012. In addition, in 2012, the programme commissioned a freedom to operate analysis. The update provided further information on the activities of third parties in the field and identified conjugation methodologies that could be selected by MVP and SIIL, as distinct from those claimed by third parties, to allow them to move forward with no patent infringements. MVP and SIIL continue to monitor the patent activities of these selected third parties in an effort to ensure freedom to operate is maintained as the development activities advance.

Recommendations from the last review:

- MVP has adjusted its operational plan, to take into account the delays (outside their control) in development of the conjugate vaccine, described during the last reporting period.
- MVP has kept DFID up to date with developments throughout the year; through written exchanges, face to face meetings and telephone conversations. They have routinely provided details of achievements and key challenges that may affect their research activities.
- The regulatory research environment in India is still causing operational difficulties. MVP has confirmed that a Phase 1 safety trial co-funded by SIIL is likely to be moved to the Centre for Vaccine Development in Mali. The move to Africa for this initial clinical trial is designed to accelerate the overall clinical development timeline as it will include both adults and children compared with the originally planned Phase 1 trial in India that included adults only. The accelerated clinical development plan is likely to increase costs at this stage, because of the inclusion of children, but overall will result in the vaccine achieving licensure quicker and with reduced overall development costs. The programme is currently in discussion with DFID about the possibility of an extension beyond its current end in March 2015.

Annual Review - Summary Sheet 2015

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / PATH Meningitis Vaccine Project 2010-2018
Programme Value: £5,775,788		Review Date: October 2015
Programme Code: / 202045	Start Date: / 1 November 2010	End Date: / 31 March 2018

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	75/100	A	A	A	A
Risk Rating	High	High	High	High	High

Summary of progress and lessons learnt since last review

The Meningitis Vaccine Project (MVP) has continued the development of a next-generation, polyvalent meningococcal vaccine (covering serogroups A, C, W, X and Y) together with their partner, the Serum Institute of India Ltd. (SIIL). MVP is developing a thermostable, polyvalent meningococcal conjugate vaccine for use in low-resource countries, particularly those in the African meningitis belt.

During the reporting period:
- SIIL and PATH met with the World Health Organization (WHO) in early 2014 and received support for the proposed product and clinical development plans.
- SIIL renovated a manufacturing suite according to current Good Manufacturing Practice (cGMP) regulations for exclusive production of the pentavalent meningococcal conjugate vaccine (MCV-5) for clinical studies.
- SIIL successfully scaled up its production process from 2 L to 20 L (polysaccharide fermentation) and produced three GMP conjugate batches for toxicology and clinical studies. The SIIL quality assurance group officially released batches in January 2015.
- PATH and SIIL established a collaborative modelling team with Harvard University, Yale University, Imperial College, Cambridge University, the US Centers for Disease Control and Prevention (CDC), and the Norwegian Public Health Institute to model the effect of various introduction strategies of MCV-5 on meningococcal disease in the African meningitis belt.
- The PATH/SIIL team modified the clinical development plan to make up for delays and accelerate the initiation of the Phase 1 and 2 clinical studies. In early 2015, the team sought scientific advice from the Paul Ehrlich Institute (PEI) and received support for the accelerated clinical development plan and guidance that the potential benefit of inclusion of the adjuvant (aluminium phosphate) should be assessed in the clinic.

Summary of recommendations for the next year

The logframe, based on the performance framework, should be reviewed to take account of the significant achievements, with realistic goals for the programme extension period, by March 2016.

Annual Review - Summary Sheet 2016

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / PATH Meningitis Vaccine Project.
Programme Value: £5,775,788		Review Date: November 2016
Programme Code: / 202045	Start Date: / 1 November 2010	End Date: / 31 March 2018

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016
Programme Score	75/100	A	A	A	A	A
Risk Rating	High	High	High	High	High	Major

Summary of progress and lessons learnt since last review
The Meningitis Vaccine Project (MVP) has performed strongly over the reporting period. MVP has continued the development of a next-generation, polyvalent meningococcal vaccine (covering serogroups A, C, W, X and Y), known as MCV-5, together with their partner, the Serum Institute of India Private Ltd. (SIIPL). MCV-5 is being developed for use in low-resource countries, particularly those in the African meningitis belt.

During the reporting period MVP completed the manufacturing of the clinical trial material for the first-in-humans (Phase 1) study and the product quality was confirmed by three independent sources, including confirmation that MCV-5 is safe and well tolerated. Agreement has been reached that the phase 1 study will take place in the USA. The US Food and Drug Administration (FDA) has given positive feedback on the pre-Investigational New Drug (IND) submission, required before any clinical trial can begin. A decision has been made that PATH will be the regulatory sponsor of the Phase 1 trial. Planning for a Phase 2 trial (in African toddlers) is advancing well. PATH has led a collaborative modelling team to model the cost-effectiveness of the various MCV-5 introduction strategies on meningococcal disease in the African meningitis belt.

Key lessons
More than 235 million individuals have been vaccinated against group A meningococcal disease (using MenAfriVac®) and this has been an unqualified success. Group A meningococcal disease has virtually disappeared in all countries that have immunised 1-29 year olds with a strong herd immunity effect (indirect protection of unimmunised age groups). 8 countries have applied for funding to include MenAfriVac® in their national childhood immunisation programs in 2016. A polyvalent meningococcal vaccine against serogroups A, C, Y, W and X has the potential to eliminate meningococcal meningitis from the African meningitis belt

During the year PATH revised the clinical plan to build safely and effectively on the success of MenAfriVac®. The new plan incorporates a Phase 1 safety and immunogenicity study in adults in the USA followed by a Phase 2 trial in African toddlers. This design provides potential to move directly into two parallel Phase 3 studies in Africa and India that are designed to lead to licensure and WHO prequalification.

Actions on previous recommendations
The logframe was updated as recommended last year.

Summary of recommendations for the next year
The logframe should be amended, to take account of the progress made during the reporting period, by March 2017.