Annual Review - Summary Sheet

Title: Health Partnership Scheme (HPS)
Programme Value: £32.3m		Review Date: July 2017
Programme Code: 202208	Start Date: July 2011	End Date: February 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	A	A+	A++	A	A	A+
Risk Rating	L	L	L	L	Moderate	Moderate

Summary of progress and lessons learnt since last review
The Health Partnership Scheme (HPS) is a programme which supports the strengthening and sustainability of existing partnerships between UK health institutions and those in low income countries.
Programme aims are to:
- improve human resources for health and health services in developing countries through UK health institutions and professionals volunteering their time to build the capacity of their counterparts in developing countries, and
- bring benefits back to the UK through volunteer NHS staff returning with increased knowledge, improved leadership skills and a greater understanding of how to innovatively deliver healthcare with limited resources.

The HPS is managed by Tropical Health & Education Trust (THET).

Overall the programme has made very good progress towards the targets set and has had a positive impact on outcomes. Since the start of the HPS in 2011, 83,973 health workers (mostly women) have been trained, 135 health institutions supported in 34 countries in Africa and Asia, and 37 health institutions demonstrated improved health outcomes for patients. In addition, the programme is demonstrating that the volunteers also benefit from increased clinical and leadership skills. These results show the significant contribution health partnerships can make to health workforce development.

The programme was originally planned to run from July 2011 to June 2017. An 8 month independent evaluation of the programme was completed in November 2016.[1] The evaluation concluded that the scheme has “overwhelmingly demonstrated the effectiveness of the partnership and volunteering approach in supporting health worker capacity strengthening.’ and that ‘projects have contributed to health system strengthening by strengthening health worker capacity in terms of their skills, knowledge and confidence.’ A cost extension of the programme was approved in July 2017. This will sustain activities until February 2019, pending decisions on a potential successor programme.
[1] Health Partnership Scheme Evaluation Report: https://devtracker.dfid.gov.uk/projects/GB-1-202208/documents

Overall findings from the evaluation were positive and warranted a continuation of partnerships. Key lessons include:

  - HPS projects have contributed to health system strengthening by building up health worker capacity in terms of their skills, knowledge and confidence;
  - Partnerships that are able to make linkages with other initiatives, establish synergies and be more strategic are more effective;
  - THET’s input around networking and technical assistance has been well delivered, and their guidance has contributed to strengthening partnerships;
  - HPS benefits both volunteers and the UK health system.

The evaluation also pointed out areas that need further attention, including the need for greater collaboration between partnerships or with other aid programmes in host countries, stronger M&E and gender considerations.
There was a management response to the evaluation. This welcomes the evaluation findings and recommendations to consider under the current programme as well as valuable lessons and ideas for future programming.  Given that the programme’s original end date was mid-2017, DFID’s response noted the limitations to apply all recommendations and that some of these would be taken into account as part of the design of any future programming. The programme has made good progress towards addressing recommendations pertaining to the current programme, such as strengthening gender considerations.[2]
[2] The full management response to the evaluation recommendations can be found in the following link: https://devtracker.dfid.gov.uk/projects/GB-1-202208/documents

Summary of recommendations for next year in light of the programme extension

- The programme should focus on sustaining momentum but start to shift towards a more strategic approach, focussing partnerships on fewer countries and, within those countries, on areas identified by the Government as part of their overall health approach.
- The logframe needs to be revised by September 2017 to agree 2018 milestones and end of programme targets for indicators at impact, outcome and output levels. Where possible, more qualitative indicators should be identified.
- Continue the positive progress on implementing the remaining relevant recommendations from the management response to the evaluation and consider how best to take forward recommendations from the two health equity studies (gender and populations served).
- Introduce data disaggregation on disability, where possible, for both participants and beneficiaries.
- In line with DFID’s environment and climate safeguards, start to address environmental measures and opportunities to among other, contribute towards adequate waste management and improved water and sanitation at health facility level.
- Identify what factors enable or hinder the success of improvement/adoption of health policies and ways to assess quality and impact for future grants including identifying logframe indicators.
- Identify which partnerships have been most successful in terms of institutional impact, to aid a more strategic selection of partnerships during the extension period.
- DFID and THET should continue frequent reviews of workplans, budgets and activities to maximise programme grant spent and results achieved.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	HPS pre-dates DFID Business Cases
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202208/documents

DFID is providing up to £32.3m over 2011-2019 to the Health Partnership Scheme (HPS) which is managed by the Tropical Health & Education Trust (THET). The purpose of the HPS is to contribute to strengthening developing country health systems, with an emphasis on improving the performance of the health workforce. This is done through supporting partnerships between UK health institutions (e.g. NHS Trusts, universities, Royal Colleges and professional associations) and those in developing countries, building health worker capacity and sharing skills. The HPS provides grant funding and technical advice and support to partnerships. This also benefits the UK health sector as partnerships contribute to improved health professional competencies (sometimes as part of leadership schemes), motivation, health service innovations and global influence. The HPS has two main components: grants to support partnership projects in Low and Middle Income Countries (LMICs), and activities to support and develop the health partnership community in the UK and overseas.

The original programme was for £20.2m over 4 years (July 2011 – June 2015). In 2014, a £10m cost extension from June 2015 to July 2017 was approved. To sustain partnership activities and momentum until a decision on a potential successor health partnership programme is made, a final £2.1m cost extension to February 2019 was agreed in July 2017. Furthermore, in early 2016, DFID approved THET’s proposal to pilot the establishment of an office in Uganda to improve coordination of partnerships with country priorities given that a large number of health partnerships is operating in the country.

At impact level, the HPS aims to contribute to more effective and efficient health service provision and improved health outcomes. The intended outcome is more effective and efficient health systems, with an emphasis on the performance of the health workforce in participating countries and the UK. The HPS contributes in particular to Global Goal 3 (on health) but also to Goals 4 (on quality education), 5 (on gender equality), 8 (economic growth) and 17 (on partnerships for the goals), and UK commitments to tackle extreme poverty and help the world’s poorest and most vulnerable in fragile and conflict affected states.

There is a rich history of partnership approaches in health. UK and global experience demonstrate that partnerships and volunteering are effective to support DFID’s overall health goals and work to strengthen health systems, and health workers’ capacity in particular – with benefits also to the UK health system. The HPS is an important component of broader DFID investments in human resources for health in partner countries. The independent evaluation of the HPS conducted during this review period has shown that the scheme has successfully strengthened partnerships and contributed to building human resources capacity at country level.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The programme has continued to make good progress over the review period and is showing positive impact at outcome level, with the evaluation reporting that the scheme has successfully strengthened partnerships and contributed to building human resources capacity at country level.

Examples of how the programme is influencing institutional policies and improving health worker performance are provided below.

Example: An initiative by Nottingham Trent University and Makerere University School of Public Health partnership focused on strengthening the Community Health Worker (CHW) programme for health improvement in Wakiso District, Uganda. The project provided 325 training course places for CHWs and CHW supervisors, which resulted in an increased number of home visits by CHWs to provide health care, referrals and education. The partnership achieved 40,213 home visits reaching over 127,000 community members and over 19,000 children treated for malaria, diarrhoea and pneumonia by CHWs. Of the 325 training course places, 300 CHWs were assessed at least 3 months after training, and 298 demonstrated improved performance. CHW competence and motivation were assessed through quantitative and qualitative methods, including questionnaires, focus groups and interviews.

Example: The Guy’s and St Thomas’ NHS Foundation Trust and Ndola Central Hospital partnership works to improve patient safety and infection prevention control (IPC) practice in Zambia, through improved Body Fluid Exposure processes, providing Hepatitis B vaccines for staff, undertaking community awareness raising, audits, holding regular IPC Committee meetings and developing microbiology laboratory capacity building to support diagnosis. The partnership trained staff in standard operating procedures (SOPs) and four new SOPs were formally approved and implemented at Ndola Central Hospital.

Overall output score and description
Overall there has been excellent progress against programme milestones. Most output indicator targets have been met and many surpassed, showing a positive impact at outcome level. The overall output score is A+ - the programme has moderately exceeded expectations. Performance has consistently been strong over the lifetime of the programme. In addition, this review has exceeded expectations partly due to the nature of the programme, including the fact that it takes time for revised curricula and courses to get accredited and efforts have paid off over time, and the high number of live grants during the review period. There were also efficiency gains and some grants maximised training resources in anticipation of projects’ coming to an end.

Key lessons

THET has continued to improve programme and grant management throughout the lifetime of the HPS. Lessons from programme implementation include: the importance of supporting LMIC institutional leadership and capacity development; the need for sufficient investment in rigorous evaluation and research for such a complex, diverse and dynamic scheme; and the need to provide more support for volunteers to maximise learning and the application of their improved competencies and skills on their return to the UK. Additional lessons from the evaluation are included in the evidence section.

THET have shared lessons learned through webinars, learning events in the programme countries, publications on their website, social media, health events and wider networks. The HPS evaluation report has been published on the DFID website and shared widely across DFID, HMG, and UK international health networks.

Key actions

With approval of the cost extension (Jul 2017 - Feb 2019) the following activities are now underway:
- DFID and THET are mapping the delivery chain to identify all partners at each level, funding flows, risks and safeguards through to the beneficiary;
- Workplans and grant award criteria are being agreed;
- DFID is updating the due diligence assessment of THET; and
- An exit strategy is being developed.

Has the logframe been updated since last review?

The logframe was revised in September 2016 following a recommendation from the July 2016 review. To assess the added value of the Uganda office pilot, targets were increased under Outcome indicator 1 (by 20) and Output indicators 1.1 (by 40) and 3.2 (by 15). The logframe will need further revision to reflect the extension.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output 1	Improved and strengthened knowledge and capability in participating health institutions
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of training course places or other educational opportunities provided to developing country health workers (directly by project or by trainers trained in project)	77,000 / plus 40 for Uganda	83,973 (30,102 in this review period) / (41,381 female / 30,534 male / 12,058 unknown) / 54 for Uganda (all in this review period) / (20 female / 28 male / 6 unknown)
1.2 Percentage of tested trainees showing improved skills or performance immediately after training or education	92%	92% (92% in this review period 35,041/38,124 ) / (93% female / 94% male / 86% unknown)
1.3 Number of developing country institutions with improved medical equipment, ICT or health information management systems	210	233 (58 in this review period)

Key points

There has been a significant revamping of training activities towards the end of the current grants with excellent progress made. Programme performance has been consistently strong and at times exceeded expectations. Milestones have been adjusted regularly to increase or reduce ambition based on experience. As a result 2017 targets were realistic but with a high volume of live grants, longer-term relationships and maximising training opportunities, performace has been particularly strong against some milestones towards this year. Examples against each indicator are provided below.

1.1 Training course places or other educational opportunities provided
- The cumulative programme target of 77,000 was exceeded by 6,973 (9%)
- The 2017 Uganda target of 40 was exceeded by 14 (35%). The Uganda office played a significant role in facilitating connections between health partnerships and with the Ugandan Ministry of Health. This has already shown better coordination of efforts among initiatives which has led to improved efficiencies, reduced expenses and maximised participation in training/educational opportunities
- In this review period 30,102 training course places or other educational opportunities were provided, representing a 98% increase over the 15,170 places provided in the previous review period. This is due to increased capacity built up over the lifetime of the programme and a number of partnerships who made use of grant underspends to run additional or larger training courses in the remaining months of their projects

Example: The Countess of Chester Hospital NHS Foundation Trust and Church of Uganda Kisiizi Hospital partnership implemented a project to strengthen IPC systems. The project trained 4,125 medical staff and community members in Uganda. The large majority (3,790) were trained in the final year of the HPS. As staff capacity developed, in the latter months of the project local staff were able to lead training on changing patient safety culture at hospital and community health care level expanding the numbers reached.

1.2 Tested trainees showing improved skills or performance:
The cumulative target of 92% was met, with 92% achievement also in this review period.
- This target is calculated by dividing the number of health workers tested after training who show improved performance or skills by the total number of health workers who were tested, averaged over the lifetime of the HPS.
- Grant holders were required to submit a sample of completed data collection tools, so that THET could assess tools used and support assessment methods. Samples across a wide range of tools (general monitoring, educational monitoring, clinical records, and quality improvement) were found to be generally of high quality

Example: University of Edinburgh and Makerere University worked in partnership to improve palliative care in Uganda through nurse leadership. Out of 172 nurses tested, 158 reported a change in their understanding of leadership skills. Nurses were assessed using a range of methods including making a poster about their skills as a leader before the course, and then another following the course in order to map the journey to change; assessment via direct observation by the project team; and post-module evaluation forms.
1.3 Country institutions with improved medical equipment, ICT or health information management systems
- The cumulative programme target of 210 was exceeded by 23 (11%)
- The target was originally based on information provided in project workplans. However, a review of results provided in the review period in progress reports revealed that more partnerships (10 more) than indicated in workplans had improved equipment/Information. Communication Technologies (ICT) and/or Information Management Systems (IMS).

Example: During their project to strengthen diagnostic services in the Upper East Region of Ghana, the University Hospital Southampton and the Ghana Health Service partnership discovered that almost every item of x-ray equipment in institutions had technical faults. This seriously affected the provision of x-ray services in the region and meant that the Radiographic Assistant Practitioners trained through the project could not adequately implement their skills. The partnership therefore reallocated some of their budget to arrange for a maintenance engineer from the UK to visit three institutions in the region to restore vital radiography equipment and provide guidance to staff on how to maintain the equipment.

Summary of responses to issues raised in previous annual reviews (where relevant)
- The 2016 Annual Review recommended that THET develop more explicit guidance to encourage partnerships to improve data collection on gender. As a result, THET reinforced the importance of disaggregated data collection by gender and cadre through webinars, one-to-one support to grant holders, and amending reporting templates to ensure disaggregated data collection was specified in partners M&E plans.
- There was no gender data available for 14% of all the health workers trained, the same percentage as in the previous reporting period. However, given the huge increase in training course places provided during the final year of the HPS, partnerships reported disaggregated gender data for an increased number of trainees than for previous years.
Recommendations
- Disaggregate participants and beneficiaries by disability where possible
- In line with DFID’s environment and climate best practice, start to see how projects can address environmental measures and opportunities to among other; contribute towards adequate waste management and improved water and sanitation in health facilities.

Output 2	Improved and strengthened policies, protocols and curricula in participating health and health education institutions or across health systems
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of national and institutional health strategies and professional standards / protocols to which projects have contributed for development, review or update	467	516 (66 in this review period)
2.2 Number of new or improved policies and professional standards approved and signed off, by end of programme	330	350 (34 in this review period)
2.3 Number of medical education curricula to which projects have explicitly contributed for development, review or update	110	114 (10 in this review period)
2.4 Number of new and or improved medical education curricula explicitly approved for teaching	54	57 (7 in this review period)

Key points

There has been continued momentum towards strengthening policies, protocols and curricula and overall targets met or slightly surpassed. Achievement in this annual review period is on average 40% higher than the previous review period. This is partly because getting official accreditation is often a longer-term task and subject to political economy factors which are mostly beyond the control of the programme. Efforts building on established relationships with government officials has been a factor leading to this output being exceeded. Therefore, this output is overall scored as A+.

2.1 and 2.2 Number of health strategies policies and professional standards; contributed/approved
- Cumulative programme targets for Indicators 2.1 and 2.2 were both exceeded by 49 (10%) and 20 (6%) respectively
- Achievement for indicator 2.1 in this review period is 65% higher than for the last review period with many partnerships successfully updating protocols and policies in the final months of their projects.

Example: A partnership between University of Manchester and Lugina Africa Midwives Research Network supported evidence-based midwifery practice through audit in eight institutions across Kenya, Uganda, Zimbabwe and Zambia. Midwives conducted audit exercises to enable improvements in practice. The project team also worked at hospital level to garner support from managers to institutionalise the use of audits. Four out of the eight institutions have formally approved/signed off audit policies with four still in draft form.

2.3 and 2.4 Medical education curricula: contributed/approved
- Cumulative programme targets for Indicators 2.3 and 2.4 were exceeded by 4 (4%) and 3 (6%) respectively.
- Achievement for the 2 indicator targets in this review period was 25% and 75% (respectively) more than for the previous period. While not initially planned, some of the partnership projects contributed to curricula development. For example, as a result of their SAFE Obstetric Anaesthesia training project in East Africa (implemented by the Association of Anaesthetists of Great Britain and Ireland in partnership with the Association of Anaesthesiologists and the Kenyan Society of Anaesthesiologists), the SAFE course was included as part of the routine training of Anaesthetic Officers in Kenya.
Summary of responses to issues raised in previous annual reviews (where relevant)
None.

Recommendations

Given that indicator targets are very focused on numbers, this makes it difficult to assess actual impact in terms of policy or curricula uptake and use, as well as about the quality and extent of contributions to curricula. It will be important to identify alternative indicators or ways to better assess quality and impact as this programme moves to the next stage e.g. evidence of changes in national human resource policies, high-level discussions, etc.

Output 3	Stronger and more institutional and country health partnerships that promote and enable mutual learning and skills and technology transfer
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of new institutional health partnership Memoranda of Understanding or other formal written commitments	95	98 (9 in this review period)
3.2 Number of institutional health partnerships strengthened	108 / plus 15 for Uganda	118 (39 in this review period / 17 for Uganda (all in this review period)
3.3 Number of UK health professional days spent volunteering overseas + in the UK	74,190 OS / 11,578 in the UK	84,053 OS (23,097 in this review period) / 11,296 UK (4,889 in this review period)

Key points

Overall there has been good progress against this output with strong results in particular on the number of institutional partnerships strengthened[3]; a total of 56 in this review period compared to 21 in the previous review period.
[3] Partnerships were asked to self-assess during grant selection in 7 areas (including communication, joint working and learning). Following grant award, they were asked to set 3 partnership development objectives. Evidence-based progress against one or more objectives, as reported in progress reports, was counted as “strengthened”.

3.1 New institutional formal written commitments for institutional health partnerships
The cumulative programme target of 95 was exceeded by 3 (3%). With the programme due to originally end June 2017, a lower number of formal commitments between partnerships were agreed in this review period (9) than for the previous review period (17)

3.2 Health partnerships strengthened
- The cumulative programme target of 108 was exceeded by 10 (9%) with 39 partnerships counted as strengthened in this review period against 21 in the last review period. The target of 15 for Uganda was exceeded by 2 (13%)
- THET awarded grants to 128 partnerships, including 17 partnerships in Uganda, some of which were consortia that included several institution-to-institution partnerships. Therefore, the total individual partnerships are 170. Of the 170, 118 (including 17 partnerships in Uganda) reported clear evidence of strengthening working practices, including better communication, governance, and new kinds of collaboration.
- The establishment of an office in Uganda as a way to strengthen coordination of partnerships and the relationships with MoH officials is proving to be effective. For example, bottlenecks to obtaining accreditation of courses developed with support of the HPS were more easily addressed. In addition, 17 Ugandan partnerships were interviewed as part of an evaluation and reported improvements in their partnerships, including better coordination with government.

Example: A partnership between Frimley Park Hospital NHS Foundation Trust and Kitwe Central Hospital in Zambia seeks to reduce the incidence of irreversible blindness by increasing the screening and treatment of diabetic retinopathy and developing a pathway to identify patients on the screening programme who also have glaucoma. Partnership aims included strengthening communication and learning as this was sporadic (increasing only when visits were planned). Regular communication is now in place between all actors using a range of platforms, which led to better organised training courses. Via this improved communication, feedback from both UK and Zambian actors is collected and evaluated regularly to identify learning priorities, and the issues raised are now systematically addressed during training interventions. As a result, the relationship between the partners has been strengthened and training interventions have been more focussed.

3.3 UK health professional days spent volunteering
- The overseas cumulative programme target was exceeded by 9,863 (13%) whereas the UK cumulative target was slightly missed by 282 (2%)
- The large number of volunteering days in this review period (23,097 against 17,878 for the last review period) is the result of many health partnerships making use of available grant resources to expand training courses or evaluation activities, requiring more UK health worker time in LMICs, in the final year of their projects
- In spite of high levels of volunteering, some NHS staff experienced difficulties to get time off/leave to take part in health partnership activities. As shown by the evaluation, this points to the need to strengthen support for international health volunteering in the UK.
Summary of responses to issues raised in previous annual reviews (where relevant)
The 2016 Annual Review recommended that DFID and THET agree a standardised method to quantify and assess volunteers’ time spent on projects while in the UK. THET provided clear guidance to partners and ran a webinar on how to report on UK volunteer days in the UK which resulted in improved data being provided by most grant holders.
Recommendations
- Identify which partnerships have been most successful in terms of institutional impact, likely sustainability and potential to encourage a more targeted and strategic selection of partnerships during the extension period.
- Include an indicator to measure alignment and linkages with country priorities and other health system strengthening initiatives to better capture effectiveness.
- Identify if there are particular health areas/thematic areas which tend to promote stronger partnerships.
- Continue to advocate on the benefits of volunteering and consider how to improve the enabling environment for volunteering overseas.

Output 4	Effective and efficient grant funding and strategic management support to projects and health partnership community by the managing agent
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Targets	Progress
4.1 Amount of grant funding disbursed, within agreed timeframes	£21,890,645	£20,831,737
4.2 % of timely and appropriate provision of technical assistance (TA) to grant holders and other eligible stakeholders, in a 12 month period	94%	97% (36 / 37 survey respondents in this review period said they were very satisfied or quite satisfied with THET’s TA)
4.3 Number of advocacy and communication activities undertaken by THET in support of an enabling NHS environment for overseas volunteering	305	304 (53 in this review period)
4.4 Number of page views for website resource library	93,250	87,907 (29,130 in this review period)

Key points

Good progress has been made against all output indicators; especially given the added complexity and increased support grantees needed to receive from THET to finalise projects in what was originally the final year of the HPS. Although indicator 4.4. was slightly missed, this was partly due to the fact that during the final year the need to access THET’s resource library was not as big as during project design and implementation stages. As projects came to a close THET provided support via webinars and email, substituting for website views and therefore the overall output score is an A.

4.1 Amount of grant funding disbursed, within agreed timeframes
- With unused/unrequired grant funds identified following a detailed review of the HPS budget in early 2017, a revised grants budget of £21,371,433 to the original end of programme was agreed through a contract amendment. 97.4% of the revised grants budget was disbursed with just £539,695 unspent. This is a good result given the complexity and diversity of this grants programme. To remain on-track, THET ensured additional support where required and took an adaptive approach to utilisation of project funds to help maximise results for what is a large and complex grants project.
- Some partners did not spend as much as anticipated in the remaining months of their projects due to:
  - efficiency savings on flights, accommodation and training venues;
  - a national doctors and nurses’ strike in Kenya, which caused delays/cancellations in five grant projects with some volunteers returning early;
  - instability in Ethiopia, Sudan and Gaza led to delayed or cancelled activities due to travel and/or security restrictions

4.2 % of timely and appropriate provision of technical assistance to grant holders and eligible stakeholders
- The 97% result exceeds the cumulative programme target of 94% and 36 of 37 (97%) of survey respondents in this review period said they were very satisfied or quite satisfied with THET’s technical assistance
- 75 HPS grant holders were invited to complete an anonymous survey with 2 questions and space for comments. 47% (37) responded. See survey results and a sample of responses in Annex 1.
4.3 Activities undertaken by THET in support of an enabling NHS environment for overseas volunteering
The cumulative programme target of 305 was missed by 1, with 53 activities undertaken in this review period
Examples of activities include: an event entitled “Global Health Partnerships: Buzzword or Breakthrough?”, ten papers published in Globalization and Health, publication of THET’s report “In our Mutual Interest”

4.4 Number of page views on website resource library
- The cumulative target of 93,250 was missed by 5,353 (5.7%), with 29,130 page view in this review period being 13% more than for the previous review period
- During what was originally the final year of the programme, the need to access THET’s resource library was not as great as during grant project design and implementation stages. As projects came to a close, THET provided support via online webinars and shared resources directly via email to ensure both UK and overseas partners made use of the resources and to facilitate project sustainability

Summary of responses to issues raised in previous annual reviews (where relevant)

None.

Recommendations

- Recommend that DFID and THET continue frequent reviews of workplans, budgets and activities to maximise the level of grant funds spent.
- The timeliness of delivery and amount spent against planned budget together with results achieved would provide a better measurement of grant management quality.
- A more nuanced approach to understanding the value of online resources for uptake of learning should be taken – e.g. by measuring references to publications and providing examples of use of publications.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key cost drivers include inflation, exchange rates, security, and salary rates. THET overhead costs reduced from 18% to 17% in the final two years of the programme. This was due to HPS staff vacancy savings and a gradual reduction in financing costs from January 2017 as THET covered financing costs in the last stages of the HPS from its own funds. Where possible, travel was avoided through remote working and communications via video or teleconferencing facilities. Exchange rates were monitored and currency bought in advance in bulk when needed. Grant expenses were lower than planned due to savings made on flights, accommodation, subsistence, training venues and cancelled activities due to unforeseen incidents.

Project spend and progress against targets remained largely on-track against the original timescale throughout the programme. Some grant underspends were identified; refer Output Indicator 4.1 above.

VfM performance compared to the original VfM proposition in the business case

THET have undertaken extensive work to assess and continuously improve VfM in the programme. The independent evaluation found that “All of the projects reviewed…..demonstrated a high level of awareness of and commitment to the importance of economy (in particular), efficiency and effectiveness as well as sustainability, and this is driving behaviour. They applied this by economising where possible and creating high quality project inputs that produce efficient outputs and effective outcomes.” Detailed findings from THET VfM assessment and from the evaluation are provided in Annex 2.

Assessment of whether the programme continues to represent value for money

The evaluation concluded that: “The volunteering and partnerships approaches used by the HPS represent good value for money. Partners and volunteers have a high level of awareness of value for money and the creation of high-quality and effective project approaches.” In addition, programme monitoring by DFID since the evaluation and the agreement to provide a final cost-extension conclude that the programme continues to represent good value for money.

Economy: THET staff, materials, equipment and services have been procured at the best possible price and value. Costs were managed by benchmarking salaries against the sector; open tendering for consultancies, remote working, and maintaining advance travel booking and economy fare policies. Also through ongoing support to grant holders in designing and managing projects to ensure VfM and performance using webinars and remote ways of communications as far as possible. THET completed the programme within budget and programme savings were used for health partnership engagement platforms, coordination and impact studies in response to HPS evaluation recommendations.

The evaluation found that the use of expert volunteers enabled provision of specialist expertise to developing country partners at a relatively low cost. Also, that there is a strong culture and practice of cost minimisation across all projects, using low cost transport, conducting training in health facilities, and combining different cohorts of trainees to avoid extra costs. However, the diverse types of training and levels of expertise needed by projects make it challenging to compare costs per training across HPS projects. Analysis found that most training costs assessed were very low, around the £30 to £200 per person per day range, with one partner explaining that if they had conducted the same training with paid professionals the whole training would have cost them £202,404.[4]
[4] Accident and emergency health partnership between Cambridge University Hospitals and Yangon General Hospital, Myanmar.

Efficiency: THET supported UK partners to ensure experienced and qualified health volunteers delivered specific well designed training and activities in targeted, locally appropriate projects in LMICs. THET also used an adaptive management response to maximise the use of grants in the delivery of the programme. For example unused funds were used to carry out additional training and M&E activities in the final months of projects (see example below) and in a few cases underperforming projects were closed.

Example: Powys Teaching Health Board and Molo and Kuresoi Sub County Public health services partnership support community health workers and volunteers to become local community trainers in Kenya. The trainer of trainers approach enabled them to cascade the knowledge and skills learnt for effective antenatal, intrapartum and postnatal care in the community. 106 traditional birth referral agents were trained, and 16 new trainers of trainers. Following review of budget expenses and the activity plan, the partnership used £3k of unspent funds to hold refresher trainings for all previously trained trainers in order to recap training and ensure trainees could work independently of support from the UK project team. Another training was also held for hospital-based management staff in Molo and Elborgon, rather than clinical staff as originally planned, this approach proved more successful to achieving project buy-in and sustainability. Some unused funds were also used for an independent translator to assist an evaluation consultant with running focus groups which resulted in better data collection and analysis.

The evaluation found that the value of technical assistance using a partnership and volunteering approach is high compared to other comparable approaches. LMIC partner institutions and health workers value the project inputs highly and effectiveness of health workforce capacity improvements is significant. Volunteers’ demonstrated commitment to delivering high quality work and innovation and efficiency of project implementation was reported to be high by many of the evaluation country case study participants. Training and development of curricula and education systems were seen as particularly efficient and effective by both health workers and university staff interviewed. The high quality, relevant, appropriate and enjoyable nature of the training was cited by interviewees across all countries. However, this was slightly undermined in a small number of projects due to a lack of transparency between UK and LMIC partners in relation to budgets and project plans.

Effectiveness: The HPS helped strengthen the capacity of 137 LMIC health institutions. The partnership approach used is based on principles of mutual benefit and co-development to build lasting institutional partnerships beyond the programme timeframe. Approaches such as training of trainers (ToTs) also helped to standardise training and extend the sustainability and reach of skills transfer.

The evaluation found that HPS projects represent good value for money and the results show promise of lasting beyond the lifetime of the project. This is because project methodology enhances sustainability and most projects are embedded within long-term partnerships. However, it was found that HPS projects are missing the opportunity to create added value from coordination and integration with the other HPS projects and other aid programmes and recommended the following:
- developing an understanding of how value for money could be enhanced through the development of synergies with other aid programmes in key countries and between partnerships;
- continue to evolve the THET approach for strengthening partnerships in order to improve effectiveness by strengthening international development expertise, simplifying and communicating THET’s Principles of Partnership[5], and further developing guidance on institutional capacity strengthening approaches for partners.
  [5] THET Principles of Partnership: http://www.thet.org/pops/principles-of-partnership

While the evaluation found that overall effectiveness in terms of health system strengthening (HSS) may not be as scalable and sustainable as larger aid programmes that target several areas of the health system at once, there are HPS projects that show considerable promise in this respect. Further development of the partnership and volunteering approach would be advisable to understand how HSS can be maximised.

Value to UK Health Workers/system. Volunteers interviewed and surveyed by the evaluation team claimed they had strengthened technical/hard/clinical skills, increased soft skills (confidence, motivation, leadership etc.), international exposure and improved cultural awareness. On return to the UK, 67% of survey respondents stated that they had taught others in their organisation about the challenges that health workers face overseas, and that they had better cross-cultural understanding. 63% stated that they respected the NHS more, and 54% felt more confident and capable in their jobs as a result. 24% felt that they had brought back innovations which they were now using in their work in the UK. Only 8% (6 respondents) felt that their work in the UK had not changed as a result of their volunteering experience.

Comparisons of efficiency and effectiveness with other programmes. In comparison to wider aid programming, the evaluation found that the HPS has a clear VfM advantage due to the use of expert volunteers who provide specialist expertise while at the same time learning and building potential for enhancing the health system in the UK. The value accrues to the volunteer, the host country health system and the UK health system in non-monetary terms. Most other types of aid programming accrue value to the health expert in monetary terms through payment, and to the host country, but not necessarily to the UK health system. It is also true that most UK volunteers through the HPS (but not all) are paid only expenses and very low subsistence, so they cost little in terms of technical assistance. The non-monetary relationship has clear intangible advantages for both the volunteer and the host country, where commitment and relationship goes well beyond a simple economic transaction.

Equity: The evaluation found that projects reviewed tended to have limited understanding or analysis of how gender inequality and social exclusion can affect efforts to enhance human resource capacity and skills or improve people’s access to and use of health services. To help develop skills and tools to address gaps, THET conducted two studies on health equity (see details in Section H: Monitoring & Evaluation). Table 3 below sets out analysis of the data that partnerships were able to provide on populations served.

Table 3: Populations served by HPS partnership projects
Population	Projects with data	Projects proportionately reaching population	Projects disproportionately reaching population
The very poor	29	21 (72%)	15 (52%)
Women and girls	40	33 (83%)	23 (58%)
Rural people	34	15 (44%)	12 (35%)
People with disabilities	25	9 (36%)	6 (24%)

Quality of financial management
Throughout the reporting period THET have provided on-time, comprehensive and accurate narrative and financial reporting. They have competently administered monitoring and management of budgets for over 200 grants, this included conducting rolling audits of grantees financial, asset, and fraud management both in the UK and overseas and making/following up on recommendations for improvements.

An independent audit report of THET’s 2016 accounts clearly accounts for DFID funds and expenditure, including grants, and found THET’s financial systems to be true and fair.

DFID HPS Project Officer agreed with THET a detailed month-end reporting format to facilitate accurate expenditure reporting, accounting and reconciliation. This has worked well and helped to ensure updated accruals are received sufficiently in advance of DFID’s month-end financial deadlines. All expenditure is checked and reconciled against budget lines, as set out in the contract with THET, and overall expenditure has continued to remain on-track

The forecasting record for staff fees have remained within 3-5% accuracy during the reporting period.  There was a slight spike in expenses expenditure against forecast in the early part of the reporting period due to costs associated with the Symposium held with partners in Dar es Salaam but was quickly rectified and expenditure remained within overall budget.  There has also been some fluctuation with grant payment forecasts towards the end of the reporting period of approx 5-8% which was due to THET withholding grant payments until adequate reporting was provided by grantees as well as some grants being closed early.

Date of last narrative financial report	31 May 2017
Date of last audited annual statement	For year ending December 2016, received July 2017

E: RISK (½ page)

Overall risk rating: Moderate
The programme was approved with a risk rating of Low, this was re-categorised as Moderate risk with introduction of DFID’s revised risk framework in March 2016 and has remained moderate.
Overview of programme risk
Programme risks are regularly monitored and overall have remained the same as in previous Annual Reviews. Key risks that need to be managed relate to potential weak financial and programme management capacity of grantees, security issues in some contexts and lack of ownership over the programmes.
A key risk for this review period was exchange rates fluctuations. THET and grant holders successfully mitigated this by minimising in-country expenses and THET provided advice on managing exchange rate fluctuations.
Risks identified for the extension period include the following:
- As there will be a shorter implementation period to award, manage and complete grant projects during the extension period, DFID and THET will need to ensure more intensive inputs throughout; and
- Manage expectations for the extension period by agreeing clear criteria and transparency over how grants will be allocated
Management of financial risks. THET have applied robust grant award and grant management processes, including risk management procedures. These include due diligence assessment of health partnerships before grant award, followed by guidance and ongoing support on project design, budgeting, governance, financial controls, fraud management and duty of care. Grant holders provide regular detailed financial and narrative reports, with payments contingent on verification of expenditure, performance and evidence-based results. Review of programme and grants-level risk is a standing item at THET’s monthly Grant Management Group (GMG) meeting. For poor performing grants, action plans are developed in conjunction with the grantee and where grant projects failed to deliver, these were closed. Such cases were reported to DFID as issues arose (3 cases were reported to DFID in the review period). There was no incidence of fraud or corruption in this reporting period.

With the programme originally due to end July 2017, THET proactively managed staff turnover by minimising staffing gaps in key roles and ensuring they were filled by experienced/qualified staff. THET and DFID collaborated and maintained a comprehensive exit strategy and plan which included a risk matrix, management of staff resources/attrition; final monitoring and evaluation data collection and analysis requirements, grants closure processes, and activities to further enhance sustainability of partnerships.
Outstanding actions from risk assessment/due diligence

There are no outstanding actions

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
The programme has stayed on-track and has delivered against the planned timeframe. With learning from the first phase of the HPS (2011- 2015), THET worked closely with grant-holders to revise budgets where needed to maximise grant funds and results during the second phase (2015-2017). There were also minor reallocations of grant funds as projects came to an end, with some unspent funds reallocated to strengthen programme results, e.g. to Knowledge, Exchange and Sustainability Grants, establishing the THET Uganda office April 2016, contributing to the travel expenses for some developing country participants to attend the THET Annual Conference Oct 2016, and the March 2017 end of programme symposium which included a focus on sustainability.
Performance of partnership(s)
Strong productive partnerships exist between DFID, THET and the Health Partnerships being supported.
DFID and THET held quarterly catch-up meetings and engaged informally on a regular basis throughout the reporting period. DFID and THET also worked closely with the health partnership community in the UK and overseas. DFID’s Health Services Team engaged with DFID country offices on the HPS, including to update them on HPS projects operating in their countries. THET staff engaged with opinion-formers in many different contexts, such as membership of the NHS International Health Group, and co-chairmanship of the NHS International Volunteering Group.

Output 4 above provides evidence of THET’s effective relationship with UK grantees. THET also actively increased engagement and support to overseas grantees. For example: opening an office in Uganda to support the highest number of health partnerships in any one country; in-country sharing and learning events; and the symposium in Dar es Salaam, March 2017. THET’s webinar presentation series also showcases and connects partnerships working in similar thematic areas. In addition, THET developed a Principles of Partnership self-assessment tool to accredit partnerships in a more structured way in the future.
Asset monitoring and control
THET purchased office equipment in 2012 and 2013 with HPS funding, which is recorded in THET’s asset register and adjusted to reflect the portion of assets attributable to HPS. All assets are assigned serial numbers and labelled. These assets are depreciated over three years using the straight line depreciation method. Assets are located in THET’s office which is accessed by a code locked door and closed windows are reinforced by iron bars. The office is within a secured building with 24-hour security. Assets deemed to be at the end of their useful life will be disposed of by IT Green to comply with the WWE Directive ensuring hard drives are wiped and shredded. A spot check of assets was undertaken by DFID 6 July 2017; all DFID assets at the THET office were identified and found in good order.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant) N/A

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation

High level findings from the independent evaluation of the HPS include:
- HPS projects have contributed to health system strengthening by strengthening health worker capacity in terms of their skills, knowledge and confidence;
- THET’s input around networking and technical assistance has been well delivered, and their guidance has contributed to strengthening partnerships;
- HPS benefits both volunteers and the UK health systems. Most volunteers report that they gain a number of new skills, self-confidence, better cultural understanding and new levels of motivation and appreciation of the NHS.
To assist the theory-based approach for the independent evaluation, the evaluation team developed a Theory of Change (ToC) for the HPS with widespread stakeholder consultation, including THET. The ToC comprises three interconnecting change pathways: 1) partnership change; 2) volunteer and UK health system change, and 3) host country health system change, and is a useful reference for any successor programme.

The evaluation found that:
- a key strength of the HPS is that the approach has supported a large number of nascent, experimental partnerships and growing partnerships, while at the same time encouraging a development-led approach. This has resulted in some larger, more established, and possibly enduring, partnerships being strengthened that have started to impact health systems and service delivery;
- those partnerships that have linked up, established synergies with other partnership projects and aid programmes and become more strategic have been particularly effective.
- Future programming should plan more strategically by country in-line with national and international strategies and goals (SDGs and UHC) and provide longer-term funding that can enhance a range of health system changes.
- It was also found that small HPS start-up grants help early partnerships to develop their relationship and scope potential projects.

THET collected comprehensive disaggregated data throughout the programme which included:
- health workers by gender and cadre (managers, nurses, doctors, clinical officers, midwives etc);
- trainers by type (project team / volunteer or trainers trained) and number of days of training provided;
- health services and health systems strengthening by health theme and level of healthcare;
- health institutions by population served (poor, very poor, women and girls, rural, disability);
- patients disaggregated by gender.
THET also commissioned the below two studies on health equity in HPS projects:
1. The Gender equity study provides an introduction to gender inequalities in health, and analysis of data collected from two HPS supported partnerships[6]. The study found: limited data collection and analysis on gender equality; clear perceptions of gender inequality in both the health workforce and health services; identified gender-based discrimination as a barrier to women’s promotion; and identified that health workers should be more sensitive to gender, such as women and men’s different attitudes to healthcare. The report recommends that health partnership programmes consider gender explicitly, employing a gender expert to help integrate a gendered focus to grant selection, implementation, monitoring and evaluation.
[6] The Children’s Eye Care Services project (D31), by Western Health and Social Care Trust in the UK and Mbeya Referral Hospital, Tanzania; and Improving the Assessment and Treatment of Epilepsy in Children and Adolescents (D2.49) by East London NHS Foundation Trust in the UK and Mbarara University of Science and Technology (MUST) in Uganda.
2. The Populations served study analysed data collected from two HPS partnerships[7]. The data suggested that some disadvantaged populations are being reached through HPS supported partnerships, including women and girls, poor, and rural populations. This was achieved by working with mid-level health workers and community health workers, integrating health workers from rural areas and using task-sharing or task-shifting. However, in the absence of a health financing mechanism to subsidise or remove user fees, economically disadvantaged populations face major financial barriers to access health services. This is despite the availability of skilled personnel and equipment to provide a service. Therefore, health partnerships alone will struggle to improve access. Many health partnerships are collecting service-user data, but not systematically, and they are potentially underestimating their reach to disadvantaged populations. If health partnerships are to include a focus on disadvantaged populations in the future, significant considerations will be required as to how they are designed, where they are implemented, who they involve, and how impact is measured.
[7] The Accra Burn Centre Project (D2.48) by Greater Glasgow and Clyde NHS Trust in the UK and the Reconstructive Burns and Plastic Surgery Centre, Korle-Bu Hospital in Accra in Ghana; and the Establishing and building diagnostic services in the UER of Ghana project (D3) by University Hospital Southampton in the UK, the Ghana Health Service Upper East Region and the charity Afrikids.
Monitoring progress throughout the review period

It was not possible to interview overseas partners as part of the annual review but the table below lists beneficiary feedback provided during this review period.

Table 4: Beneficiary feedback
Grant	Health theme	Location	Beneficiary	Feedback
A38	Community Health Work	Ssisa sub-county, Wakiso District, Uganda	Kiyaga, Community member	I just don’t know how to thank the funders and implementers of this project. The Community Health Workers have done a tremendous job ever since they were trained which has greatly supported our villages. My grandchildren have always been treated by these CHWs hence saving me money and time that I would have spent by going to the nearest hospital which is many miles away.
D2.40	Medical equipment	Mulago National Referral Hospital, Kampala, Uganda	Dr Alex, Hospital Administrator	The project has had a good impact, especially with equipment servicing and maintenance, we are no longer losing as many equipment as before, thus saving the hospital money and resources, in turn saving human lives.
F6	Patient Safety	Gondar Hospital, Ethiopia	Alemeyahu Derse	After I have got the training from Occupational Health & Safety and Infection Prevention & Control project trainers, I now have a plan to supervise my staff to follow the principles, especially how to dispose of waste to protect themselves and patients from the sharps injury.
A33	Mental Health	Butabika Hospital, Uganda	Laurence Okello, Peer support worker	We have received a very good training, which has helped us to bridge the gap between patients and hospital staff. The training has reduced stigma from most members and they are able to express themselves openly without fear, which is a sign of acceptance and moving forward.

DFID has held quarterly catch-up meetings with key THET staff to review progress reports, progress against the logframe, financial management and expenditure in addition to frequent informal engagement. Formal progress reports in December 2016 and April 2017 were jointly reviewed and remedial actions agreed.

THET supported health partnerships to plan, monitor, evaluate and report on their projects. DFID and THET visited seven projects in Ethiopia in July 2016 and THET made monitoring visits to seven African countries during this review period. These visits included reviews of activities, impact and partnership working and financial audits.

The DFID Senior Responsible Owner (SRO) joined the end of programme Symposium (Dar es Salaam, March 2017), attended by 90 global health actors including health partnership representatives from 14 countries in Africa, Asia and the UK as well as the Government of Tanzania, INGOs and the multilateral and donor community. The 2 day event provided an opportunity to reflect on partnerships’ successes and challenges, to learn from other actors and to identify what could be improved in the future. Sessions looked at different areas of health systems strengthening, partnership approaches, and sustainability in diverse country contexts and circumstances. Practical sessions on resource mobilisation, financial management, monitoring and evaluation where held. THET’s Principles of Partnership and the recommendations of the HPS evaluation were also discussed to help partners think about their next steps.
Methodology
This review was led by the SRO for the programme with support from the global health policy adviser. It included discussions with THET staff including reviewing each output to assess progress, discussions with programme stakeholders in the UK, and with both UK and LMIC partners at the March Symposium, a desk-review of results, monitoring reports, and commissioned studies (gender, populations). It also drew substantially from the HPS evaluation report and case studies.

Annex 1

Box 1: THET provision of technical assistance survey results
Q1. How satisfied are you with the quality of THET’s technical assistance in the last twelve months? / 46% very satisfied, 51% quite satisfied, 0% quite unsatisfied, 3% very unsatisfied. (The respondent may have selected this option by mistake, because it is at odds with their comment – the first one below.) / Sample comments: / THET have grown significantly as an organisation over the course of the Health Partnership Scheme. They are able to offer superb support to UK and overseas health institutions who wish to undertake health systems strengthening programmes using the health partnership model. / While the templates provided by THET have significantly improved over the course of HPS, they are still somewhat cumbersome and sometimes do not provide space for deep reflection on the running of the project. THET are always extremely helpful when asked for advice, however we have had several changes of project officer on this project and understandably the understanding of our project has suffered. / I really like project planning and I am very supportive of good monitoring and evaluation. However, it has been more onerous than necessary for a relatively small project. / Q2. How satisfied are you with the timeliness of THET’s technical assistance in the last twelve months? / 49% very satisfied, 49% quite satisfied, 3% quite unsatisfied, 0% very unsatisfied. / Sample comments: / THET are always available and accommodating as much as possible. / There were problems at the start of the Project due to delays in forwarding the funding THET has been very focused on closing down the programme and this has resulted in lack of flexibility and vision for what partnerships may need to continue after funding is finished.