 Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2018

Title: Urban crises programme
Programme Code: 204273	Start Date 01 October 2014	End Date: 31 December 2017
If programme was closed >1 month early please describe in a few words why.	Not applicable

Summary of Programme Performance

Year	2015	2016	2018
Programme Score	A	A	A+
Risk Rating	Moderate	Moderate	Moderate

Financial Position

Original Programme Value	Initial total = £3,523,593.03, of which £540,000 was for International Rescue Committee (IRC), £2,591,908 to the International Institute for Environment and Development (IIED) and £391,685.03 for critical administration and co-ordination costs.
Extensions/ amendments	The IRC component of the programme was originally due to end on 31 December 2016. It was extended for one year for IRC to support the ongoing establishment and sustainability of the Global Alliance for Urban Crises. The extension also aligned the IRC end date with that of the IIED component. This allowed for continued engagement between the two partners, in particular the dissemination of learning arising from IIED-funded research. A cost extension was granted to IRC of £250,000 up to 31 December 2017, taking the total budget of the programme to £3,773,593.03.
Log-frame revisions (with dates)	The IIED logframe was amended in July 2017, in order to push back the target date to align with the programme end date, therefore shifting the end line from September to December 2017. / A new IRC logframe was created to align with the programme extension and was finalised in July 2017. The outputs were changed to shift the focus of the programme from stakeholder engagement at a regional level to city-level outcomes. This ensured the recommendations coming out of the programme were being taken up at practitioner level.
Total programme spend	£3,685,327.94

Follow up actions required following closure

Ensure that key lessons and recommendations continue to feed into future humanitarian programming, within DFID, IRC, IIED and beyond, as well as being taken up by urban development actors.

Ensure that IIED continue to promote the outputs produced under this grant to contribute to ongoing strengthening of good practice in urban crises, through the Global Alliance for Urban Crises and engagement in other international fora. This includes advancing key messages on the need to broaden understanding and resources for new ways of working in urban settings within the major inter-governmental policy forums in 2018, notably the Global Compact for Refugees and Migrants, the World Urban Forum and the Commonwealth Heads of Government meeting.

Ensure that IRC’s and IIED’s membership in the Global Alliance for Urban Crises continues to drive change in humanitarian response, so that it is adapted to an urban world.

DFID to follow up with IRC in March 2018 and IIED in June 2018 on their latest Annual Audited Statements.

DFID to finalise on asset disposal plan with IRC. IIED have no DFID funded assets with this programme.

A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204273/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204273/documents

Outline of programme and what it has achieved

This programme was established in response to the 2011 Humanitarian Emergency Response Review’s identification of urban contexts as increasingly frequent locations of crises, and the need to support the capacity of the humanitarian system in this area.

The main purpose of this programme was to increase DFID’s, its partners’, and the humanitarian system’s confidence, understanding and capability to respond to humanitarian crises taking place in urban contexts. The definition of urban crises includes natural disasters impacting on urban areas, large flows of refugees and internally displaced people (IDPs) into towns and cities and urban areas directly affected by conflict.

The programme has generated outcomes in three core areas:

- Learning on how urban systems are impacted by humanitarian crises and how responses can best be tailored to the urban context.
- Increased operational capability to work in urban areas, due to the development of tools and promotion of learning from best practice.
- Evidence-based high-level policy engagement on system reform for improved response to urban crises.

The programme had 2 components. Component 1 was an advocacy and learning partnership with the International Rescue Committee (IRC). Component 2, managed by the International Institute for Environment and Development (IIED), was a capability fund that managed grants to support documentation of and learning from good practice, and the development of practical tools. The team have ensured compliance with the International Development Act (Gender Equality) 2014 across the two components, including the development of research products with an explicit focus on gender and consideration of gender equality in the recruitment of research teams.

Component 1
IRC’s contribution to the programme had two outputs:

1. IRC’s advocacy output worked to broaden the range of actors involved in responding to urban crises and encouraged key stakeholders to develop, review and enhance their policies on urban contexts and their implementation. To this end, IRC implemented a programme of policy engagement focused on the preparations for the World Humanitarian Summit (WHS) and Habitat III (the United Nations Conference on Housing and Sustainable Urban Development) both held in 2016. IRC also engaged with the UN system and member states in New York to introduce text on urban crises into humanitarian resolutions, and worked bilaterally with UN agencies, the Red Cross, international NGOs and academia to raise the profile of the urban crises agenda. IRC supported these actors’ own development of policy and operational responses to the urbanisation of emergencies. In 2017, advocacy work built on the progress achieved at the Summit and Conference and engaged with the processes set up to deliver Global Compacts on Refugees and Migrants. Over the course of the programme IRC produced a range of advocacy materials, ranging from policy-focused briefs, think pieces published in newspapers and on specialist websites, and practitioner-oriented peer reviewed journal articles.

2. IRC’s learning output worked to improve humanitarian and other actors’ understanding of how crises impact urban contexts and how to programme effectively in towns and cities. With a particular focus on working with local authorities and on cash and livelihoods programming, the partnership has generated evidence-based knowledge products that draw on IRC’s and other organisations’ operational experience in crisis-affected towns and cities. IRC has disseminated lessons learned and good practice.

IRC’s DFID-funded Advocacy and Learning programme was originally due to end on 31 December 2016 while the IIED research programme was due to continue through 2017. As recommended in DFID’s 2016 Annual Review, the IRC component was extended into 2017 to enable IRC to support the consolidation and institutionalisation of the Global Alliance for Urban Crises. The Alliance had been launched at the WHS as a direct result of IRC’s advocacy output. IRC’s support for the Alliance has ensured its sustainability post 2017. In a departure from usual practice, a new logframe was created for IRC’s 2017 work, and so this review reflects on what was achieved across the 2014-2016 logframe and the 2017 logframe (hence there are more outputs than usually expected in a project completion review.)

Component 2
IIED’s contribution to the programme has been to generate a considerable body of evidence on approaches to humanitarian response in urban contexts, to strengthen the understanding of, and inform practice by, national and international humanitarian actors, local and national governments, and donors. It has addressed gaps in knowledge, technical capacity and skills in order to provide a better basis on which to prepare for and respond to humanitarian crises in urban areas. IIED worked with researchers, humanitarian practitioners, urban practitioners, local government officials and civil society representatives, through research projects and international and local workshops and conferences. The work by IIED had three mutually reinforcing outputs:

Coordinating two ‘learning partnerships’ of leading international organisations (including NGOs, multilateral agencies, and academic institutions) working in the field of urban humanitarian response, in order to document best practices, generate tools, and develop innovative operational working methods. The Stronger Cities partnership (led by IRC) generated 9 toolkits and guidance notes for working in urban settings, with a particular focus on displacement crises, whilst the Urban Crises Learning Partnership (UCLP, led by Habitat for Humanity) generated 12 pieces of research and documentation relating to disaster preparedness, response and recovery.

1. Managing a competitive ‘learning fund’ and ‘responsive small scale research and documentation fund’ to support innovative thematic and regional research on key issues shaping humanitarian responses in urban areas. This learning fund has enabled 31 distinct research projects to be carried out in Asia, Africa, the Middle East and Latin America. These research projects have led to the production of 29 policy briefing papers and 32 working papers in English, French, Arabic and Croatian, as well as peer-reviewed academic papers and online opinion pieces. A special issue of the journal Environment and Urbanization on urban humanitarian response was also released.
2. Coordinating learning events and networking activities in order to disseminate best practices, discuss policy changes, and build the capacity of key actors. In partnership with IRC, IIED hosted 3 workshops for municipal officials, civil society representatives and humanitarian agency workers for the Middle East, Asia and East Africa regions, respectively, as well as city-specific workshops in Amman and Kampala. IIED led side events at the World Humanitarian Summit and Habitat III, as well as organising an international conference on urban crises.

Output 3 also included the establishment and coordination of a Strategic Steering Group (SSG); monitoring, evaluation and learning (MEAL) activities; and review and disbursement of funds to successful Learning Fund applicants.

The SSG was formed in the early months of the initiative, composed of 5 non-IIED members with a background in humanitarian practice or research and a demonstrated interest in urban humanitarian response specifically. The members were selected on the recommendations of DFID advisors and researchers working in the sector – the SSG members were not remunerated for their participation. The SSG met on a 6-monthly basis. Its role was to review progress of the programme, advise on thematic focus areas for activities, and approve shortlisted proposals from the competitive calls for proposals for the Learning Fund. The SSG also played an essential role in the qualitative assessment of the programme’s outcomes as per the logframe, which set out qualitative indicators for each of the 3 outputs. Accordingly, SSG members were interviewed independently by a member of IIED’s M&E team to provide their assessment of the logframe targets – the key project staff from IIED were not involved in this process so as not to influence the results. Four of the five SSG members were available for these interviews and the full report of this qualitative assessment is available in Annex A.

Please note that the IIED elements of this PCR which reference ‘IRC Stronger Cities’ refers to activities funded via IIED’s learning consortia (output 1). Reference to ‘IRC’ relates to activities funded directly by DFID where IIED and IRC have collaborated.

The third strand of the programme was the secondment of a DFID advisor to IRC in order to work specifically on urban crisis. The advisor was based in New York in order to facilitate engagement with the work of IRC’s Head Office and establish working relationships with a range of relevant actors in New York and Washington DC. This position ensured that policy development on this critical issue was informed by high-quality technical advice, giving DFID a strong voice in international policy arenas. This arrangement also served to strengthen the institutional relationship between IRC and DFID.

## B: PERFORMANCE AND CONCLUSIONS
Overall Outcome Assessment
The intended outcome of this programme was:
Humanitarian and development actors have improved understanding and enhanced policy and operational commitment to respond to the challenges and opportunities presented by urban crises, to meet the immediate needs of the city and its inhabitants, foster recovery and encourage sustainable development.

During the development of the separate logframe for the one year 2017 IRC extension, a revised outcome statement was included for that specific work. The review team consider that this should be considered as a sub-outcome to the overarching programme outcome (as above) and so it is against the original outcome that progress has been assessed.

This programme has introduced the concept of Urban Crises to a broad range of humanitarian and urban development actors. At the time the programme began, debates on how to improve response to crises in urban areas were largely absent from international forums. Levels of understanding of how urban areas are affected by crises were low, and there was very limited evidence on how best to respond to emergency situations in the urban environment. By convening a wide range of actors, and combining policy engagement and support for research, the programme has opened space for discussion on urban crises at the international level. It has also informed these discussions with a range of evidence, learning and advocacy products and operational guidance. The programme has exceeded expectations in terms of the number and type of actors who are now aware/better informed of the urban crises agenda. The recommendations that have been generated by the programme – through convening of actors and through research – have now reached a level of maturity whereby they are being translated into operational practice on the ground.

A significant achievement was the institutionalisation of the Global Alliance for Urban Crises which has successfully engaged beyond academia, development and humanitarian actors to include networks of municipal authorities, architects, engineers and planners. IRC has recently secured funding for the Alliance from European Civil Protection and Humanitarian Aid Operations (ECHO), which means that much of IRC’s work on policy engagement and advocacy will continue beyond the life of this programme, and that there is a mechanism in place for the continued dissemination of IIED supported research, evidence and tools.

Both IIED and IRC were able to stimulate considerable interest in the urban crises agenda. As a result, alongside meeting original targets for producing written documents and organising learning or advocacy-focused events, both organisations have also achieved much further reaching but also less tangible results. These are hard to quantify and attribute. Anecdotal evidence would suggest that a number of international agencies (including United Nations Childrens Fund (UNICEF), United Nations Development Programme (UNDP), and the International Committee of the Red Cross (ICRC)) are reviewing their work in urban areas affected by crises and have been influenced by the outputs of the urban crises programme. This influence is more obviously apparent in the policy discussions on urban displacement currently being led by UNHCR (explained in full below). Several of the largest international non-governmental organisations (NGO) (including the Norwegian Refugee Council (NRC), Habitat for Humanity, World Vision and Oxfam) have been involved in the production of operational tools and guidance through the programme, and are therefore likely to be integrating the lessons generated into their work on the ground. The full impact of the programme may only be seen in later years – changes in operations can be slow to materialise. But key recommendations stemming from the programme on, for example, managing urban displacement, developing area-based approaches and deploying urban expertise to emergencies, may in future become standard practice in urban crises situations.
IRC contribution to the outcome
In the period 2014-16 the IRC targeted a range of institutions and processes that it assessed as having the potential to bring positive change to the way that urban crises are addressed. Major successes included influence over the preparations, agendas and official outputs for the WHS and Habitat III in 2016, the introduction of urban language in to a number of key humanitarian resolutions at the UN and the creation of the Global Alliance for Urban Crises. The programme also brought a range of new actors in to debates on urban crises (networks of local government, and international organisations of planners, engineers and architects) and forged new partnerships between these actors as a result. The recent decision by the World Bank to join the Global Alliance is a further indication of the way in which the IRC’s work has generated a broad movement for change in the way that urban crises are addressed.
This represents an overall strong achievement of the outcome given that a new set of municipal authorities are now more prepared and knowledgeable of appropriate urban humanitarian response than when the Urban Crises programme began.

IIED contribution to the outcome

IIED has delivered more than double the originally specified number of outputs, thereby providing urban response actors with evidence on a wider range of contexts and issues than was originally anticipated and meeting a broader range of potential needs. IIED has made concerted efforts to ensure local, municipal-level stakeholders have been engaged throughout the course of the initiative, either through their participation in research or in international and local events.

Through the research it has generated, and in line with the outcome, IIED has also sought to influence international processes to promote urban concerns in humanitarian crises preparedness and response. Achieving this will inevitably require time for the findings to be absorbed and integrated in humanitarian practice. Progress was assessed through independent evaluation interviews in the closing months of the project, with members of the Strategic Steering Group (SSG) who acted as strategic advisors over the course of the project. Their combined assessment is that the programme is likely ‘to have succeeded in influencing international processes to promote urban concerns in humanitarian crises preparedness and response’ (scoring 4.25 on a Likert scale where 5 = very likely and 1 = very unlikely).

A selection of further comments offering opinions as to the outcomes of the initiative are available in Annex A.

Output Score and Description

Overall the programme scored an ‘A+’ – outputs moderately exceeded expectations. This is calculated using the scores and weightings assigned to each output. There were a number of areas across the outputs where targets were substantially exceeded, such as IIED’s number of research grants allocated and the knowledge products that were thereafter produced from these funds. It could be argued that the targets were not ambitious enough for some outputs, especially under the IIED component; although it is difficult at the outset to know what realistic targets are, these should perhaps have been reconsidered during the programme implementation. The only output where the programme did not deliver well was under IRC’s number of knowledge products produced on programming effectively in urban contexts. That said, the target was later met, but after the original target date of December 2016.

Lessons and how these have been shared

This programme has focused on generating and sharing of lessons to improve urban humanitarian response. The detail of learning products and dissemination activities are provided in the sections on outputs. A short overview is provided here:

Lessons for policy-makers

During the 18-month preparatory period for the WHS, the IRC co-convened the Urban Expert Group and co-led an in-depth consultation that drove the development of a set of recommendations for the humanitarian sector. These were adopted as the Global Alliance’s Urban Crises Charter and served as a basis for a range of events in Europe and the US targeted at international policy makers. This included (but were not limited to) an event at UN Headquarters in New York titled ‘City Haven’ in 2016 at which IRC President David Miliband gave a keynote address, a day-long workshop for donors at Ditchley Park in 2015, a briefing for UN member states at the UK Mission in 2015, and side events held yearly throughout the Programme at the ECOSOC Humanitarian Affairs segment. IRC urban crises team members (including the DFID Secondee) regularly addressed policy audiences through their participation at panel discussions at conferences and events organised by, amongst others, ALNAP, Interaction, OCHA and the Red Cross Movement. As mentioned above, the World Humanitarian Summit (WHS) and Habitat III were key moments for the Urban Crises programme which the IRC and IIED used to amplify lessons that were emerging from the Urban Crises Programme. This involved organising a range of side events as well as sessions on the main agendas of both events.

David Dodman from IIED held a seminar with DFID advisers at their request on the 14th November 2017, to share the key policy lessons from the research.

Lessons for practitioners

To complement and inform participation at these events, both partners also shared lessons through a series of publications. These were targeted mainly at urban development and humanitarian response practitioners. The generation and dissemination of lessons was the main focus of IIED’s contribution to the programme and of the IRC’s learning component, and full details are provided in the outputs sections below. It should be noted, however, that IIED published 60 papers (against a target of 25) that have been downloaded more than 57,000 times (against a target of 5000). The DFID secondee also published articles in peer reviewed practitioner-oriented journals and think pieces on websites targeted at humanitarian and urban development actors. She also worked with the IRC’s communications team to draft an article on the Guardian’s Cities page that was authored by David Miliband.

The partners held an end of programme event held on 15-16 November in London with IIED and IRC. Participants from across multiple sectors including local government, UN agencies, civil society, built environment professionals, academics and humanitarian agencies actively participated in discussions of the research findings. The IIED and IRC’s knowledge products were disseminated during the conference and the IRC hosted a parallel session on building urban resilience following displacement.

Lessons for municipal authorities and other local actors

Local government officials and local civil society were exposed to a range lessons arising from the programme in a series of regional (Middle East, Asia and East Africa) and city-level workshops (Amman and Kampala). IIED has worked with IRC throughout the programme to ensure that there have been opportunities for local engagement and sharing of evidence and knowledge around urban response practice. Additionally, many of the research outputs under IIED’s Output 2 have involved the participation of local researchers, practitioners, and local government, in the research process.

Also at the local level, the IRC has supported the work of 100 Resilient Cities, an initiative of the Rockefeller Foundation which has a strong influence on resilience planning in 100 cities globally. IRC has shared lessons from working in urban areas to encourage the inclusion of refugee integration within concepts of urban resilience. Through engagement and contributions to three context analyses with 100 Resilient Cities, IRC has been able to influence the resilience planning of a number of focus cities for the Rockefeller initiative. IRC has also influenced the approach that 100 Resilient Cities is applying to resilience planning globally.

Lessons for future advocacy programming

This programme has also generated lessons for advocacy focused initiatives. It could be argued that the original targets for the programme were not ambitious enough. However, the ability to achieve change through research and advocacy is contingent upon a number of factors that are beyond the control of researchers or advocates. Implementing partners are unlikely, in these types of programmes, to be willing to set themselves up for failure by setting clear targets for changes in practice that will arise as a result of their efforts. Trying to make these types of predictions in advance is inherently difficult, and might prevent partners from responding flexibly to changing circumstances. Effective advocacy must be reactive in nature, taking advantage of the emergence of new coalitions and new forums, global events or political changes. The design of future programming within DFID in support of advocacy and/or focused on changing policy and practice should be informed by best practice from specialist organisations particularly in terms of how indicators are developed and progress measured.

C: DETAILED OUTPUT SCORING

Output Title	Advocacy: Key stakeholders are encouraged to develop, review and enhance their policies on urban contexts and better operationalise them
Output number per LF		(IRC 2014-2016) 1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	22%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of advocacy products produced with actionable policy recommendations that address how humanitarian, development and urban stakeholders can improve response in urban contexts and disseminated at regional and global advocacy and policy events and through online downloads.	By December 2015: 3 papers / By December 2016: At least 6 advocacy products (papers, reports and briefings) have been published or electronically circulated over the course of 2 years	The total number of advocacy products produced by the programme is 8, please see Annex B for detail.
Number of events at which evidence based advocacy messages are shared (side events, high-level panel events).	By December 2015: 4 events / By December 2016: At least 6 events where advocacy messages are shared	The programme co-hosted or organised 12 events in total, please see Annex B for detail.
Number of targeted stakeholders (including humanitarian, urban and development) briefed by IRC on the specificities of urban crises and key recommendations.	By December 2015: All Ditchley Park attendees in Group A have had at least 2 follow-up meetings and 30% of Group A have sent representatives to other IRC events. Initial meetings held or other forms of institutional engagement with Group B stakeholders / By December 2016: Engagement maintained with all Group A organisations and follow-ups with Group B. Briefings extended to five additional high-level stakeholders (donors, international multilateral agencies or INGOs)	The target was exceeded to a significant degree. All Group A stakeholders had at least 2 follow-up meetings, and 76% sent representatives to other IRC events (UN High Commissioner for Refugees (UNHCR), United Nations Officer for the co-ordination for Humanitarian Affairs (OCHA), UNDP, International Federation of the Red Cross (IFRC), ICRC, International Organisation for Migration (IOM), UN-Habitat, World Bank, ECHO, DFID, Danida, Swedish International Development Cooperation Agency (SIDA), World Food Programme (WFP) /FAO food security working group). IRC also initiated and maintained communication with 3 additional governments (Germany, Switzerland and the Netherlands). Institutional systematic engagement was also maintained with all Group B stakeholders through December 2016. / Outreach to well beyond 5 additional stakeholders was achieved through sustained advocacy activities. The culmination of these efforts led the launch of the Global Alliance for Urban Crises. The Alliance now has more than 70 members. This has exposed a large number of new actors, including associations of urban professionals, Member States and municipal authorities, to messages developed by the IRC and other Alliance members on the intersections between urbanisation and humanitarian action.

Key Points

This output was moderately exceeded, scoring an A.

In 2015 and 2016, the Urban Crises programme saw the successful uptake of messages related to improved urban humanitarian response at key events. These included City Haven in New York, the launch of the Global Alliance for Urban Crises during the World Humanitarian Summit, and the subsequent visibility of Alliance members and their unified voice during Habitat III. Each event was an opportunity to advocate to a different audience. At City Haven, senior staff from UN OCHA, the IRC, and UN Habitat, among others, highlighted the need for increased attention on the plight of urban refugees to a largely UN audience. The launch of the Global Alliance at WHS showed the importance of collaborative urban humanitarian response to the humanitarian community, while Habitat III brought the same message to the international community of urban professionals, local governments, and urban development practitioners. With accompanying policy briefs and early growth and convening of Global Alliance membership, 2015 and 2016 was a turning point for the international discourse on urban humanitarianism.

An example of the ongoing influence of the Urban Crises Programme can be seen in the policy development of the European Commission. ECHO released “The Urban Amplifier” in 2018 and makes specific mention of the IRC as a humanitarian partner that has “gained experience and capacity to operate in urban settings.”

Output Title	Learning: Humanitarian and other actors supported to have greater understanding of how urban contexts are impacted by crises and how to programme effectively for the urban context.
Output number per LF		(IRC 2014-2016) 2	Output Score	B
Risk:		Moderate	Impact weighting (%):	11%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of knowledge products produced on how urban contexts are impacted by crises and how to programme effectively for the urban context.	By December 2015: / 1 knowledge product produced / By December 2016: At least 3 additional knowledge products produced based on evidence and lessons learnt from IRC urban programming and other non-IRC urban humanitarian and development programming over life of project.	The programme only produced 2 out of the 4 knowledge products by December 2016. A total of 5 knowledge products was produced by December 2017, exceeding the original indicator target of 4 knowledge products, but outside of the planned timeframe: / Finding economic opportunity in the city: lessons from IRC's cash and livelihoods programs in cities within Lebanon and Jordan (August 2016) / Learning from Lesbos: Lessons from the IRC's emergency response in the urban areas of Lesbos (November 2016) / The Right to the City for Urban Displaced (January 2017) / Violence in the City: A Systematic Review of the Drivers of Violence against Displaced Populations in Urban Crisis and Post-crisis Settings (January 2017) / Public service delivery in contexts of urban displacement (December 2017)
Number of Regional Practitioner Workshops delivered independently or jointly with IIED on how urban contexts are impacted by crises and to promote exchange of knowledge on how to programme effectively in urban areas.	By December 2015: / 1 Regional Practitioner Workshop delivered by IRC in collaboration with IIED. / By December 2016: / 3 Regional Practitioner Workshops delivered by IRC or jointly with IIED.	The Programme delivered jointly with IIED the following Practitioners’ Workshops: / ‘Meeting needs in a context of protracted urban displacement in the Middle East and North Africa’ (September 2015) / ‘Meeting needs in a context of protracted urban displacement in the Horn and East Africa’ (May 2016) / Meeting needs in a context of protracted urban displacement in Asia (January 2017)

Key Points

This output was not fully achieved in the planned timeframe, scoring a B.

On the learning side, the Urban Crises programme in 2015 and 2016 held three regional urban practitioner workshops which included practitioners from 18 countries in total. Coupled with four knowledge products written or published during that time frame, covering the humanitarian topics of livelihoods, protection, social cohesion, and emergency response, the programme established a robust base of primary research applicable to a large portion of the humanitarian community. From this base, several practitioners, including the IRC and its peer agencies, have begun to shift their practices towards more appropriate urban responses to humanitarian crisis. For example, the catholic relief agencies CAFOD, CRS, and CWS recently solicited the IRC’s expertise on interventions related to urban violence based on their reading of the Violence in the City knowledge product. The targets for IRC’s learning component were reached in early 2017, later than originally planned (December 2016). This can be attributed to the 6-month delay in hiring the learning manager at the start of the programme. IRC’s hiring at the time was affected by senior staff turnover and the finalisation of a new strategy.

The successes on both the advocacy and learning sides of the Urban Crises programme in 2015 and 2016 were significant in bringing about a change in behaviour both at the global and local levels that we are seeing today. While ECHO is reaching out to IRC for assistance in shaping their Global Urban Displacement Strategy, the Kampala Capital City Authority is incorporating IRC recommendations into their forthcoming strategy on meeting the needs of refugees within their city. These specific examples would not have been possible within the wide reach of advocacy and learning efforts during the first two years of the Urban Crises programme.

Output Title	The Global Alliance for Urban Crises is operational and effectively functioning the end of 2017
Output number per LF	(IRC 2017) 1	Output Score	A
Risk:	Moderate	Impact weighting (%):	9%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
1.1: Priority working groups of the Global Alliance supported with advice on policy and practice	Target: 3 WGs operational/meeting regularly / Achieved: Yes	The target milestone of 3 Alliance Working Groups operational and meeting regularly was exceeded. All 4 Alliance working groups are operational and have funding to sustain themselves through 2018.
1.2: Preliminary findings from Alliance activities and working groups are amplified by the Steering Group and informing global advocacy and policy messages	Target: End of programme event in partnership IIED amplifying messages from all priority working groups, the Steering Group and the Urban Crises Programme / Achieved: Yes	The end of programme event was held in November 2017 and was attended by over 100 participants from academic institutions, UN and donor agencies, INGOs, state governments, and local municipal authorities.
1.3: Steering Group well established, including its secretariat, and lessons from the Urban Crises Programme amplified	Target: Secretariat and Steering Group can function without additional support from IRC / Achieved: Yes	The Steering Group is now well established, and has continued to meet after the conclusion of the grant period approximately every 4-6 weeks. The Steering Group held a meeting in February 2018. The next planned meeting of the SG is for March 2018.

Key Points

The output delivery met expectations, scoring an A.

The Global Alliance for Urban Crises activities have funding for 2018 and its initiatives are being undertaken by 4 working groups representing dozens of members committed to implementing Alliance-related activities by the end of the calendar year. Both the Alliance’s Secretariat and Steering Group are well established and staffed, with clear roles and responsibilities between the Secretariat, the Steering Group, and the working groups. The IRC no longer needs to provide additional support beyond its usual presence on the Steering Group and working groups. The Steering Group revised its Terms of Reference in 2017 and has rotated its membership so as to maintain dynamism. It will also have a rotating Chair. The Secretariat now has one full-time staff member with funds from a Steering Group member and the Norwegian government through UN Habitat. The Secretariat is actively fundraising for an additional senior staff member. Alliance members will continue to advocate on tailoring humanitarian response to the urban context to disseminate lessons generated by the Urban Crises programme. Alliance members recently successfully advocated for key urban messages to be considered in the Global Compact for Migration. The Zero Draft of the Global Compact for Refugees has also been influenced by this project. This was achieved by joint hosting of a Brookings Event during the UN General Assembly, bilateral engagement, policy briefings and participation in key influencing fora in Geneva. As a result, the document includes three references to recommendations devised by Alliance members and specific reference to the Global Alliance itself.

Summary of responses to issues raised in previous annual reviews (where relevant)

One of DFID’s 2017 Annual Review recommendations focused on the development of the Global Alliance and ensuring it would be consolidated and institutionalised after the closure of the programme. The IRC component of the programme was extended and a new logframe was designed to focus specifically on these areas. The outputs and key points above reflect this change in focus.

The recommendations also highlighted the need for IRC to focus on specific aspects of policy and practice where it wanted to see change over the remainder of the project. While the initial stakeholder engagement was broad, over the past year IRC in partnership with the Global Alliance has taken a more focused approach. IRC’s UK Head of Policy developed a targeted approach focusing on:
- Global Compact on Refugees
- Global Compact on Migration
- European Commission policy
- World Bank policy (as evidenced by the World Bank committing to joining the Global Alliance during the 9th session of the World Urban Forum. While this took place after the conclusion of the urban crises programme, it is the result of advocacy undertaken during the grant.)
Another recommendation focused on the need for IRC to document and share its successes to inform future programming. Internally, IRC has documented the approaches that have been successful in working in urban areas. This has led to an internal working document entitled “Working in Cities”, which IRC will apply to future programme design.

Recommendations for future programmes

During the design of the programme, DFID evaluation advisers did not recommend an evaluation, and the advocacy and learning programme did not have a budget for M&E. Attempts were made to capture influence, by tracking verbal and written communications by key stakeholders that referenced core concepts or documents developed by the Programme, and by making note of the creation of teams or strands of work on urban crises within agencies targeted by advocacy activities. However, this was done in an ad hoc manner. Continual monitoring and textual analysis of policy documents and announcements by key stakeholders, combined with a series of interviews or questionnaires with the same actors during the course of the programme, would have served to give a better picture of the influence of the programme, and the most effective methods it had employed to raise awareness, understanding and capacity to address urban crises.

Output Title	Global Alliance vision and priorities translated to city level where cities are affected by displacement
Output number per LF	(IRC 2017) 2	Output Score	A
Risk:	Moderate	Impact weighting (%):	8%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
2.1: Number of city practitioner workshops held that involve at least 4 members that represent non-traditional humanitarian actors (professional networks, local authorities, academics)	Target: 2 total city workshops held / Achieved: Yes	The IRC successfully hosted two city workshops, titled Urban Practitioner Workshops, in Amman (May 2017) and Kampala (September 2017). Each workshop was co-hosted with the local municipal authority and resulted in clear commitments under Outcome Indicator 2 for many stakeholders in each city.
2.2: Number of case studies published and disseminated documenting at least one example of collaboration in each network	Target: 4 total case studies published and disseminated / Achieved: Yes	The IRC published or disseminated six case studies of collaboration over the course of the grant, with an additional case study published under the programme but after the grant’s formal end date. They include case studies of humanitarian-local authority partnerships in Amman, Athens, Kampala, Maiduguri, Paros and two in Lebanon with several municipal authorities or ‘unions of municipalities’ involved.
2.3: Number of city-wide reports published and disseminated on collaboratively working towards recovery and resilience in response to urban crises	Target: 1 joint report - shared or accessed by at least 150 users / Achieved: Published in February 2018	The report, From Response to Resilience, details the long term plans of Amman and Kampala to address urban displacement. Publication was delayed in order to receive sign-off for co-publication with relevant municipalities and 100 Resilient Cities.

Key Points

Performance against this output met expectations, scoring an A.

The IRC has translated the Alliance’s vision and priorities in Amman and Kampala. Both cities have new plans that include actions around the needs of displaced and marginalised residents and incorporating these population groups into future sustainability and urban resilience planning. The IRC has entered into a formal partnership agreement with the Greater Amman Municipality and is exploring partnership agreements with the Kampala Capital City Authority to provide programmatic and technical support to municipally-led activities around urban displacement.
The efforts taken by the IRC and its partners to move from a humanitarian response to displacement towards an approach that builds resilience and integrates refugees in Amman and Kampala are described in detail in the From Response to Resilience report. While not published within the scheduled time frame (it was published in February 2018), the additional time has allowed the IRC to secure 100 Resilient Cities, the Greater Amman Municipality, and the Kampala Capital City Authority as co-publishers of the report. It is being disseminated through the international and local networks of each partner.
Replicating the partnerships in Amman and Kampala in other refugee-hosting cities would help to ensure an approach to refugees that is more inclusive and sensitive to their needs. The IRC is joining Alliance members in actively pursuing funding towards this end.

Summary of responses to issues raised in previous annual reviews (where relevant)

A recommendation from DFID’s 2017 Annual Review was that IRC should ensure that its knowledge products have a clear aim and are not duplicating existing guidance. It was also recommended that IRC undertake rigorous evidence-based analyses as much as possible.

In order to ensure this was taken in to consideration, the last two knowledge products applied a robust methodology as outlined below.

For the 4th knowledge product on Urban Violence, the IRC conducted a systematic review of academic and grey literature sources, 23 publications met the eligibility criteria of including an urban crisis or post-crisis setting and being related to interpersonal or community violence. Results related to the drivers of violence were organised using the social ecological model (SEM)* as a framework, categorising drivers at the individual, familial, community, and structural/policy levels.

For the 5th knowledge product on Service Delivery, the methodology including (1) a comprehensive literature review of public service delivery issues in urban displacement contexts, especially the roles humanitarian actors can play in supporting local service
delivery networks; (2) 19 Key informant interviews with researchers, humanitarian and development actors, as well as municipal authorities whose localities are receiving humanitarian support; (3) A review of 30 case studies for improving public service delivery networks and local governance in urban humanitarian contexts.

DFID also recommended that IRC should ensure ongoing collaboration with many different actors, including international and national peer organisations, non-humanitarian NGOs, and municipal governments. Throughout 2017, IRC continued to collaborate with a wide range of actors at both the global and local level. At the global level, the events organized aimed to bring together a variety of organisations that do not normally work together. Similarly, at a city level, the two practitioner workshops engaged a wide range of actors, many of whom had never been in the same room together, to develop a holistic approach to urban crisis issues in their city. For example in Kampala, the Kampala Capital City Authority is now reconvening a broad range of key stakeholders, including UNHCR and IOM, to present the launch of their refugee integration strategy.

Recommendations for future programmes

Although the styles and approaches of the two implementing partners are different and complementary, there is some overlap in functions on research and learning. This came about due to a lack of clarity in terms of reference for the IRC learning manager. While the programme partners have worked well together and have avoided duplication, the division of roles and staffing across the programme could have been thought through more carefully at the outset.
On a Country-level, it is encouraged that Urban response projects are developed to be:
  1. Area-based
  2. Multi-year
  3. Work along a continuum from emergency response to recovery and development
  4. Monitoring that focuses on contribution to a response rather than attribution
  5. Flexible and relying on adaptive designs that allow for co-creation and co-design with local stakeholders

## C: DETAILED OUTPUT SCORING

Output Title	Effective practices documented, tools generated and innovative operational working methods developed by the learning consortium.
Output number per LF		(IIED) 1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1: Number of tools and knowledge products co-produced by partners within the two consortia	Target: A total of 9 tools and knowledge products (including research papers, briefing papers, advocacy notes, guidebooks) co-produced by consortia; SSG assess knowledge and information needs to be better met by existing tools and products / Achieved: Exceeded- total 23	The IRC-led Stronger Cities consortium produced a total of 9 tools, and 2 desk reviews. / The Habitat-led Urban Crises Learning Partnership (UCLP) produced 12 knowledge products.
1.2: Number of learning events jointly delivered by partners within the two consortia.	Target: A total of 4 events held and jointly organised by consortia; Learning Consortia (LC) lead to better communication between humanitarian sectors in urban areas as assessed by SSG and LC members / Achieved: Exceeded	IIED held a Habitat for Humanity event that was organised at Habitat III in November 2016. / The Stronger Cities consortium organised a two-day conference in London in June 2017 with more than 100 registered participants. A further event was organised in Washington DC in October 2017 bringing together participants from 36 US-based organisations including the World Bank. / The UCLP organised workshops in its two focus countries: a two-day May 2017 earthquake simulation in Bangladesh, with a total of 56 participants from local government, civil society, international NGOs and international organizations; a one day workshop in Haiti in October 2017 attended by NGOs, local government and university researchers.

Key Points

Performance against this output moderately exceeded expectations, scoring an A+.

While originally the intention was to establish one consortium, on the strong steer of the SSG two Learning Consortia were established with the vision that having two smaller (in funding) consortia would allow a greater range of organisations and actors to be involved, and a larger variety of crises and geographies to be covered. The intention was that there would be regular opportunities for cross-learning and engagement between the two. IIED organised six-monthly meetings of the two consortia which enabled this to happen. Together, the two consortia led to a range of tools and guidance kits (Stronger Cities), and documentation of past responses and preparedness needs (Urban Crises Learning Partnership (UCLP)). This led to the fostering of new partnerships between international NGOs and researchers (internationally and locally) to build a greater understanding of the components of effective urban response.

The Urban Crises Learning Fund (2015-2017) managed by IIED aimed to contribute to urban and humanitarian stakeholders increasing their knowledge, technical capacity, and commitment to working in partnerships. This included providing appropriate institutional support in order to be better able to meet the immediate needs of cities and urban residents affected by crises (including the way these shape and are shaped by gender relations), to foster recovery and sustainable development in their aftermath, and to strengthen preparedness for future events. The programme involved new research, documentation of past experiences, development of tools and guidelines, and shared learning across humanitarian actors and other urban stakeholders.

The IRC-led Stronger Cities Initiative delivered all its planned outputs on schedule, including dissemination events. The Habitat for Humanity-led UCLP faced delays in its activities, and outputs were published in February 2018. However, IIED will continue to ensure the dissemination of the research outputs and their findings beyond the lifetime of the project, for example through conference panels on urban crises, through other research projects and activities by IIED related to this topic. As part of IIED standing capacity, the IIED communications teams and project staff will work closely together to promote outputs and publications. This will be done through available social media platforms, such as blogs, twitter, mailing lists (Active Learning Network for Accountability and Performance in Humanitarian Action (ALNAP)’s Urban Response Community of Practice, and Global Alliance for Urban Crises)), Facebook, newsletters, promoting publications during relevant international “days” or events to put the work in context. The project staff and communications team will where possible, group publications by theme or sector and promote them to specific stakeholders via these platforms for more tailored dissemination. Where relevant stakeholders are identified, IIED will post publications on request. This is done on an ongoing basis for all IIED projects even after the life of a project.

IIED used the learning consortia as a monitoring and evaluation (M&E) case study, using the M&E methodology of an in-depth social network analysis of both consortia and their ways of working – examining the relationships between the different actors in each consortia and the effectiveness of the consortium approach. This provided valuable insight into the different ways of structuring a consortium which consists of different types of organisation (research, humanitarian) and what is most effective as a structure for achieving the desired activities. The consortium members were active participants in the social network analysis process. The M&E report will be finalised in March 2018, and will include process tracing of the Stronger Cities initiative activities and impacts in Amman, Jordan.

Summary of responses to issues raised in previous annual reviews (where relevant)

One recommendation for IIED from the latest Annual Review was that DFID would welcome further details on the specific objectives and progress of both consortia. This information was thereafter provided by IIED in the quarterly reports produced in 2017.

As IRC wwere receiving DFID funds both directly and through IIED for work on urban crises, one recommendation was for IIED and IRC to ensure clarity in allocation of activities and outputs . In this report, reference to IRC Stronger Cities refers to activities funded via IIED’s learning consortia (output 1). Reference to IRC relates to activities funded directly by DFID.

Recommendations for future programmes

Allowing more time for training, uptake, analysis and refinement of tools (ideally an iterative process) that were developed would ensure that they are fully adapted to use on the ground.

With regards to the ways of operating, allowing more time and resources for interaction with the consortia through both formal and informal spheres could be helpful, for example with in-country consortium members.

Another suggestion is ensuring that the key staff members in the consortia are fully embedded in organisations (e.g. hiring specific project managers for consortia can cause delays).

Output Title	Innovative thematic and regional research produced through a learning fund and small scale research and documentation fund.
Output number per LF		(IIED) 2	Output Score	A++
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1: Number of research grants allocated through the learning fund and the small-scale research fund	Target: A total of 25 research grants allocated / Achieved: Exceeded	A total of 23 grants were awarded from 4 competitive calls for proposals. In addition, a further 8 research grants were awarded from the ‘discretionary’ fund – a total of 31 research grants.
2.2: Number of knowledge products produced from both funds and disseminated at events and through online downloads	Target: At least 25 working and briefing papers produced; At least 5000 internet downloads and products disseminated at a further 3 events / Achieved: Exceeded	As of 31 December 2017, 77 papers (working papers and briefing papers, including Learning Partnership outputs) were available for download from the IIED website – with a further 10 in final production. / By 31 December 2017, 57,094 downloads of publications had been made from the IIED website (this includes the Stronger Cities outputs), of which 18,312 came from the global south. Some papers remain in the final production stage in January 2018 and thus are not included in these download figures. / In addition, other outputs such as two online ‘long reads’, an opinion piece on the IRIN News website and articles on The Conversation were published.
2.3: Effective and relevant knowledge products are produced (including products with particular focus on needs of different groups and gender relations)*	Target: The products are assessed to have had a strategic impact by SSG members in global and local platforms. / Achieved: Yes	A number of research outputs had an explicit focus on gender, children and needs of marginalised groups such as religious minorities, speaking to population groups with particularly strong protection needs. / The download figures (described above) strongly suggest that there was a strong demand for the work, including in the global south, and that the findings were relevant to a large number of people and organisations. The significant number of downloads may allay any concerns around the take-up expressed by the SSG members (who were deliberately not provided with this information before their interviews).

Key Points

Performance against this output substantially exceeded expectations, scoring an A++.
IIED has managed the production of 77 distinct outputs, with a further 10 in final production stages – delivering significantly beyond the originally planned number. IIED funded a variety of research teams and sought to encourage collaborative approaches to research on the ground, for example research teams including local government or local NGOs, rather than solely led by UK academics. As a result, there is a diversity of researchers and practitioners (from local government, INGOs and NGOs) involved in the authorship of the outputs – representing different nationalities, host institutions, career stages and genders. The outputs also cover a significant scope and range of topics and geographies (21 countries in Asia, Africa, MENA and Latin America). Both crises resulting from conflict and displacement, and natural disasters, are covered. A number of outputs are also directly or indirectly focused on gender issues in the context of urban crises, particularly the seven research outputs produced under the ‘protection’ call for research proposals of the Learning Fund.

All of these outputs are available for free download on the IIED website, linked on the ALNAP urban portal, and regularly disseminated through IIED, ALNAP and Global Alliance for Urban Crises social media and newsletters.

Of the working papers and briefing papers, the top 5 downloads from the IIED site were for the following papers (from date of publication to 31 December 2017):

Urban planning following humanitarian crises: Supporting local government to take the lead in the Philippines following super typhoon Haiyan	769
A review of needs assessment tools, response analysis frameworks, and targeting guidance for urban humanitarian response (Stronger Cities)	1,113
Responding to the Syrian crisis in Lebanon: collaboration between aid agencies and local governance structures	1,392
A review of evidence of humanitarian cash transfer programming in urban areas	1,876
Humanitarian response to urban crises: a review of area-based approaches	1,973

IIED developed and published a special issue of the journal Environment and Urbanization on Urban Humanitarian response (released October 2017). This special issue included 7 papers, of which 4 emerged from the Urban Crises initiative. The editorial, by Diane Archer and David Dodman, was downloaded 1,051 times between October and December. Overall, publications in this journal have significant reach and influence which typically lasts for several years – in 2017 there were more than 330,000 full text downloads of papers from the journal.

The type of outputs produced have been diverse. There were more than ten blogs on the IIED website, two long reads (The future of humanitarian crises is urban; Five fundamentals to keep Lebanon’s water flowing), a short film, and an opinion piece on the IRIN website. Some authors of research pieces also ensured dissemination of findings through different avenues such as an article on The Conversation.

A full list of outputs is appended in Annex B.

Recommendations for future programmes

The initiative would have benefited from more time for a synthesis of the outputs that have been produced and their findings. Given the time necessary to initiate, conduct, and document high-quality research, many of the outputs were produced in the final months of the programme. Additional timing and allocated (even if not additional) budget for purely synthesis-based activities would have been valuable, to truly capture all the findings that have emerged over the last 3 years. As a steering group member stated in the evaluation:

- ‘it would be useful to have one or more synthesised documents (e.g. regional basis or thematically) to bring together the [research findings and] lessons learned and the messages that come out – consolidation of what we now know based on what has come out of the studies. That would be a very valuable contribution’.
- ‘Maybe for £50,000 to do this kind of [research] synthesis. Probably about three months’ work and would be a very good investment’.

There would have been benefit from allowing more scope for on-the-ground engagement with local actors, to support further research dissemination and uptake of the research findings in practice. The process of networking and relationship building with local stakeholders can also take place without distinct associated outputs such as events. As stated in the steering group evaluation:

‘If the assumption is that it’s business as usual,[by the humanitarian sector] then many tools will meet the needs of actors. But if we wanted to see a change in their roles, then the evidence to build a change in those roles or the development of tools to play a different role may not have been well met, but it might be a second stage of the work.’
‘It’s a shame that there wasn’t more funding or gearing of the project towards regional workshops or even country-based workhops… I feel the face-to-face kind of workshop with mayors and city planners and getting the city preparedness teams together, would be useful… would have been a very powerful way of disseminating what the programme was trying to do’.

This type of engagement requires investment in the time to identify and develop local partnerships with key actors in humanitarian responses on the ground, to enable deeper engagement around the topic. While time-heavy, the time spent developing such in-depth partnerships with key stakeholders in specific cities, can ensure that any outputs produced are then usefully put in practice on the ground.

Output Title	Best practices disseminated, policy changes discussed and capacity of key actors built through learning events, networking, and effective project management.
Output number per LF		(IIED) 3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1: Number of different types of events organised (webinars, workshops) and number of participants attending the events, with feedback from participants indicating that they plan to make use of workshop content in their work	Target: A total of 4 learning events; each attended by at least 20 people, with representation from different sectors, attend events, and indicate that contents will be used to inform their work. / Achieved: Exceeded- total 7	In November 2017 a two-day Cities in Crises conference was organised in London, attended by around 100 people from research and practice, including local government. / In May 2017 and September 2017 city-level workshops were co-organised with IRC in Amman and Kampala respectively, with city government representatives, NGOs, international organisations and researchers.
3.2: Number of events at which research outputs shared	Target: Research outputs shared at a total of 6 events / Achieved: Exceeded- total 8	The key event for dissemination of outputs was the two-day November 2017 flagship event. Copies of relevant publications were taken to the Kampala and Amman city workshops and the June 2017 Stronger Cities symposium, as well as an additional symposium hosted by members of the Stronger Cities consortium in Washington, DC, in November 2017. Additionally, research outputs and findings were shared through lectures on Masters-level courses by IIED staff at Oxford University and University College London.
3.3 Chances of reaching the most relevant people are maximised and information that is most useful to them is shared to them	Target: An assessment by SSG finds that events have been targeted at the most relevant actors / Achieved: Difficult to confirm, but indications are positive.	IIED made an effort to ensure that representatives from municipalities affected by crises were given a platform at all events, including international conferences and regional workshops. There was very clear targeting of the most relevant stakeholders in crisis level in the city-level workshops - beyond local government to include civil society and local research groups.

Key Points

Performance against this output moderately exceeded expectations, scoring an A+.

IIED has been committed to engaging a range of stakeholders throughout the life of the project, including local government actors, international and local humanitarian agencies, other practitioners, and researchers. It recognised that different approaches to engagement are required to effectively reach different audiences, hence it organised a range of events over the course of the project, partnering effectively with IRC to organise both regional (in Bangkok, Nairobi and Istanbul for Asia, East Africa and MENA regions respectively) and city-level workshops (in Amman and Kampala), with more direct engagement of local government and local and international NGOs operating in the area of urban humanitarian crises. These events have been vital for facilitating take-up of findings and evidence into practice, by exposing local actors to the lessons learnt from other urban humanitarian response contexts.

IIED has been an active participant in the Global Alliance for Urban Crises since its inception, with David Dodman (Group Director at IIED’s Human Settlements Group) sitting on the steering committee, and events organised by IIED at HABITAT III and the World Humanitarian System under the banner of the Global Alliance. While the Global Alliance represents individuals and organisations committed to more effective urban humanitarian response, IIED has been able to contribute evidence for its messaging. It has also linked in new communities and networks, such as community organisations actively organising around disaster risk reduction (e.g. bringing Nepali representatives of an NGO working with community organisations on disaster management committees to speak at a WHS event).

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable.

Recommendations for future programmes

The best means of engaging with national and local actors is directly at the local level in cities and towns. Whilst all the products are freely available for download online, it is important to recognise there need to be other more direct forms of engagement in order to achieve meaningful results, and these require funds and time e.g. to engage directly with the local community of practice or local government through workshops and involving them directly in the research and forming partnerships locally. This will also require having the necessary local language skills. This local level engagement is also an entry point for involving national-level actors. As recorded by the SSG evaluation:

- ‘Greater impact could have been achieved by convening events/workshops around particular themes and at the regional level… The regional events would be where the national-level administrators might have engaged with the messages of the project’.
- ‘There’s limited uptake in key actors. Some of this we can’t control, but there’s also a lesson for how we design these programmes – you really need the right people around the table to foster ownership’.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers for the IRC element of the project remain predominantly as staffing, travel, events and publications. Almost all IIED costs have been staffing costs, grants (including bank charges) and travel (including meetings).

VfM performance compared to the original VfM proposition in the business case

The original business case notes that IRC has strong internal policies and procedures to monitor and manage delivery and financial risks, most notably fraud, bribery and corruption.
During 2016 the IRC has set up a new Ethics and Compliance Unit and revised the reporting procedures around Fraud, Bribery and Corruption Policy. This was presented to DFID’s Counter Fraud Unit in June 2016.

The IRC has employed the following approaches to ensure Value for Money.
- IRC procurement policies for flights and hotels - IRC books flights and hotels at charity fares, which has allowed for significant savings on flight costs needed to join panels or global events.
- Joint events and leveraging existing fora – Key influencing events were often done in partnership with other organizations to make the best use of resources. This included jointly hosting the Urban Humanitarian Response Symposium in London, Cities in Crises event in London, and Brookings Institute Refugees in the City event in New York. Such joint activities helped to both increase the effectiveness of the influencing while reducing the costs.
- Engagement with Municipalities leveraged existing IRC resources – To complement support through this grant, the IRC leveraged existing staff time and financial resources to conduct the context analyses.

Demonstrating effectiveness, the IRC was able to secure complementary funding from ECHO which allowed the Stronger Cities initiative to increase the number of activities and conduct joint dissemination activities such as the Urban Humanitarian Response Symposium in London and the Humanitarian Action in an Urban World event in Washington, DC.

The original business case notes that each bid to IIED would be assessed on value for money by the IIED internal fund management board /strategic steering group. This was established at the start of the initiative, consisting of non-IIED humanitarian experts (including DFID staff). The process for assessing proposals was to do an overall shortlist with reserve options, based on criteria specified in the call document. The steering committee’s advice was then taken regarding the selection. Financial considerations included looking at budgets in terms of rate of proportion of staff costs from total and specifically at day rate and number of days, levels of travel costs, amount and justification for any institutional overhead, minimising any miscellaneous or contingency budget lines, and checking overall for a realistic estimate of costs to complete the work intended.

Demonstrating efficiency, IIED delivered more than double the outputs than originally budgeted – all research grants were reviewed by the SSG before approval to ensure that the most relevant topics and geographies were being covered, and budget ceilings were imposed for open calls for proposals. The process of SSG review and budget ceilings for grants ensured where possible an optimum balance between quality and cost of work.

Final outputs and briefing papers were carefully reviewed with authors to ensure the effectiveness of the work in addressing the original call and quality of the research. Beyond commissioning research, IIED through this process supported partners in building their research and writing capacities for future work.

On the strong steer of the SSG, IIED decided to fund two smaller learning consortia rather than one bigger one, as this would allow coverage of a greater range of crises, geographies, and involvement of a broader mix of organisations, producing a mix of outputs. As a result, they ended up with 9 toolkits/guidance notes, 2 desk reviews, and 12 pieces of research and documentation, which represents a significant number of outputs, and more organisations have been engaged in working on this topic over the two years (ie delivering a more effective programme).

Given that this programme has exceeded its targets on many of the outputs, and that there are indications that it has delivered a greater impact than initially anticipated, such as with the establishment of the Global Alliance, we can conclude that it has delivered better value for money than the initial business case anticipated.

Assessment of whether the programme represented value for money

The Urban Crises Programmes was designed against a backdrop of extremely wasteful, unsustainable and potentially damaging responses by the international humanitarian community to urban crises – notably the Haiti earthquake in 2010, and early interventions in Lebanese and Jordanian towns and cities to the influx of Syrian refugees.

At the time it was designed, only one UN agency operating in humanitarian contexts had an urban policy (UNHCR), and by its own admission, it was not being implemented. Not only was there an almost complete void in policy discussion on the need to tailor humanitarian approaches to urban contexts (i.e. to work with urban systems and engage municipal and other local actors) there was very little evidence on good practice. Existing evidence was to be found mainly in evaluations, and documented what had gone wrong. Tools and guidance to support the work of humanitarian actors unfamiliar with urban contexts, or to promote partnerships with urban development actors – particularly municipal authorities – were almost entirely lacking.

As the world becomes increasingly urbanised, so emergencies will happen more frequently in towns and cities. The adoption of learning and good practice generated by the Urban Crises Programme has the potential to greatly improve the effectiveness and relevance of crisis response in urban areas. While it is difficult to assess value for money of the Urban Crises Programme, it should noted that the humanitarian sector is now equipped with a wealth of evidence from a wide range of crisis-affected towns and cities, alongside comprehensive toolkits and guidance to ensure humanitarian response is appropriately targeted and implemented. In addition, a large number of humanitarian actors have been exposed to advocacy messages around the need to tailor their approaches, and have been made aware of the existence of good practice and guidance. Anecdotal evidence would suggest that the products generated by the Urban Crises Programme are being taken up by internal working groups on urbanisation and task teams developing urban policies in a number of UN agencies and international NGOs.

Quality of financial management during programme

IRC provided comprehensive quarterly financial reports and gave clear explanations for any variance between forecast and actual spend. IRC fully spent the allocated budget within the timeframe.
With IIED the quality of financial management was satisfactory, although an underspend was only confirmed near to the end of the programme. This underspend reflects an underspend from one of the learning partnerships. This partnership was required to report on a 6-monthly basis. The second to last financial report and budget narrative sent to IIED noted delays but did not flag any potential underspend. The budget narrative showed that the unutilised funds would be spent in in the final 6 months of the project. In November 2017, IIED was made aware that there would be an underspend of around 50,000 GBP. This was due to much less travel than planned and lower staff costs than anticipated. However, the partnership was still able to deliver its planned outputs.

Date of last narrative financial report	31/03/2018
Date of last audited annual statement	07/12/2017

E: RISK

Quality of risk management over the life of the programme

The DFID programme team held quarterly risk meetings, however, it is recognised that overall more attention should have been given to risks around research findings not being taken up and lack of traction within DFID. Having said that, there were some good examples of risk management such as managing the risk around conflict of interest with the DFID-secondee by ensuring a separate DFID advisor reviewed the project and decision making.
Overall, however, there could have been better coordinated processes across the programmes different elements.

For IRC there were some risks in maintaining regular communication between Steering Group (SG) calls, however this was mitigated through bilateral outreach to SG members. There was also active engagement from the SG to update the terms of reference and discussing representation and functions going forward in 2018.

For IRC the risks were tracked on a quarterly basis through Project Review Meetings. At the meetings the risks flagged in the Quarterly Reports would be discussed amongst the project team and decisions taken in order to mitigate this risk.

For example, a key risk that was flagged was the issue related to the functioning of the Global Alliance SG. As a result, the IRC’s Head of Policy took actions to revise the Terms of Reference to increase the level of engagement required of the SG and held new nominations in early 2018. Similarly, a key risk to the Alliance was securing funding to implement activities. The IRC’s Head of Policy was able to successfully engage key donors, notably ECHO, to secure funding for Alliance activities through 2019.

Another example was a risk that the Regional Practitioner workshops were not leading to concrete changes at the city-level. To mitigate the risk, the IRC decided to focus the cost-extension period on engagement at the city-level to ensure concrete changes were happening and that the influencing activities were leading to action. The subsequent commitments of Amman and Kampala to include refugee-focused projects in their city plans and to seek out the IRC as an implementing partner are evidence that this strategy was effective.

IIED project management policy supports managing risk both before and during the life of a project. IIED has for all partners a minimum standard of financial due diligence before contracting. Additionally, IIED assesses the risk profile of the partner to determine the level additional assurances and due diligence that are required, if any. This will also depend on the amount of funds contracted. This allows IIED to manage supporting small partner and NGOs while managing the level of risk exposure.

Additionally, as per IIED policy, due to the project size, it has undergone bi-annual risk reviews. Project staff met with the head of finance to discuss the project, potential risks, and how these needed to be addressed or mitigated. The reviews considered partner risks, non-delivery, quality of work, financial risks and risks associated with geographical location of work.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The Urban Crises Programme delivered against the planned timescale and logframe following the approval of a cost extension for the IRC component of the project.

Performance of partnership (s)

The performance of the partnership has been good with regular contact between relevant parties. IRC and DFID are in regular contact resolving any project issues as and when they occur. IRC also reported quarterly on progress though narrative reports, and DFID and IRC met to discuss these each quarter.

IIED and IRC were in regular contact throughout, from meetings in the inception phase to agree a common theory of change, to organising all the regional and city workshops together. They also collaborated on the events at Habitat III and the World Humanitarian Summit. IRC helped to review some of the research outputs from IIED, and vice versa, and IIED has fed into IRC advocacy pieces. Both have benefited from a mutually-beneficial working relationship.

IIED also worked closely with the IRC Stronger Cities lead, who was involved in many of the events mentioned above.

IRC’s latest Due Diligence report was conducted by DFID in June 2015 where the overall risk rating was found to be low. Actions from this report were followed up although the review team considers that a spot check part way through the programme could have been useful to check all processes and systems continued to operate as expected.

In December 2017 IRC and IIED provided DFID with Delivery Chain Mapping of all partners they worked with throughout the Urban Crises programme. IIED ensure that their partners also comply with appropriate due diligence. IRC did not work with any downstream partners in this programme.

Asset disposal and value obtained by DFID

DFID have assessed the asset disposal proposal from IRC UK in line with best value for money considerations and have agreed to transfer ownership to IRC UK for future use on urban related issues. IIED have no assets associated with the programme.

G: CONDITIONALITY

Partnership principles assessment

N/A

H: MONITORING & EVALUATION

Evidence and evaluation

The assumptions in the business case theory of change and the IIED/IRC joint theory of change still hold. A monitoring and evaluation process initiated by IIED is near conclusion which focuses on the Learning Partnership, with the intention of using the findings to implement any necessary changes in the project’s approaches and ways of working.

IIED have involved the IIED Monitoring Evaluation and Learning (MEL) team for an assessment of the Learning Partnerships around social network analysis and process tracing. This was beyond any project requirements, but intended to generate additional and independent learning to assess the effectiveness of this work and to support future activities of this type. This MEL report will be available in March 2018. The M&E focus is twofold: looking at the influence of the learning partnership on the ways of working of humanitarian actors in urban contexts (i.e. effectiveness) and what the implications are for the ways of working for IIED in managing a consortium model.

There was enthusiasm on behalf of members of both consortia in participating in the social network analysis, and the process tracing has focused on IRC-led activities and uptake of consortium tools in Amman.One aspect of this is a case-study of the ‘City Analysis Toolkit’, developed by the IRC-led consortium, demonstrating that the toolkit had been successfully used to influence the Amman Resilience Strategy.

IIED also engaged a member of the IIED MEL team, independent of the Human Settlements team delivering the programme, to carry out interviews with the SSG for a thorough assessment of achievements as per the logframe. The summary of their responses is appended.
Monitoring progress throughout the programme

The project has been monitored through a set of nested Excel-based logframes, which have informed annual reviews by DFID.

The IRC used a spreadsheet as an ‘outreach tracker’ for the advocacy component of the programme. Staff made regular notes of meetings that had been held with key advocacy targets, and recorded updates on the engagement of stakeholder institutions in policy discussions, plus progress within these institutions on policy and programme development.

The IRC also made note of papers, briefings and events that referenced the key messages of the Urban Crises programme.

Results have been disaggregated by sex and age therefore supporting our commitments around gender equality.

This Project Completion Review was conducted by DFID’s project team consisting of the Senior Responsible Officer, programme manager and advisor. IRC and IIED provided written assessments, which were used alongside quarterly reports and meetings with both organisations.
Annex A

Responses from Steering Group Evaluation of UCLF on logframe indicators
The responses in this document are provided by four of the five SSG members of the Urban Crises Learning Fund based on the background information provided by IIED about the results of the Programme.
Key urban and humanitarian stakeholders to be reached by the activities of the UCLF:

SSG member 1:
Humanitarian agencies, local and international, donors, academics.
Local government, local stakeholders, local responders, local organisations.
SSG member 2:
NGOs, Red Cross movement, UN agencies, government agencies, especially disaster management agencies, municipal authorities in host countries.
Donors e.g. DFID
SSG member 3: One of my concerns is that there’s been a very narrow focus on INGOs, not even necessarily UN organisations, large areas of the RCRC, but more narrowly Anglophone international NGOs. In that regard, my understanding this was humanitarian crises, - including risk and response, and the protracted period of stabilization and recovery. There’s been a narrow focus on humanitarian response and humanitarian actors, in terms of the participation and the target.
Other stakeholders not well engaged with:
Reconstruction and recovery actors, e.g. the WB, the IDB, EU departments (not only ECHO), USAID (not only OFDA), I’d have liked to have seen a better connection to other phases of humanitarian crises and the stakeholders concerned. Many crises are protracted and involve more active role of development and reconstruction stakeholders. There’ve been significant efforts to bridge between the two, but that doesn’t come out through this programme.
There’s been quite a focus on local authorities and municipalities, which follows a pattern set by the Global Alliance, but there are key ministries in most countries that are also particularly involved, not only local authorities. I’m not seeing so much the civil service or the national authorities, whether for economic development, social welfare, urban planning, housing etc.
Because it’s urban, there’s a fashion to focus on the city level, but I think we need to add national authorities in.
Media – how crises are communicated, how the causes, symptoms, impact and response, and recovery is covered in media. How things are forgotten and politicised. Educating the media is a very good opportunity – well-covered by the Guardian in Houston, and Hurricane Irma.
International NGOs seem disproportionately important in this programme – or an assumption that they’re the most important actor, which in my opinion they’re not.
Academia
SSG member 4 (In order of priority):
City and municipal governments / administrations
National governments, ministries and sectoral parts that deal with urban affairs
NGOs
Civil society organisations – local community-based organisations
Private sector – entrepreneurs, business at urban and national levels
International organisations and stakeholders, Intergovernmental orgs and INGOs
Wasn’t sure whether to differentiate between practitioners and political stakeholders – very different. The programme is geared mostly towards the practitioner and policy-maker side. Maybe there’s a gap in terms of dealing with politics.

Annex B
IIED Urban Crises Learning Fund – Full list of publications and other outputs
Contact – Diane Archer, diane.archer@iied.org, www.iied.org/urbancrises

Publications and authorship – all papers can be found here

	Study title and region	Study lead/team	Status	Contact
	Call 1 – local collaboration
1	An assessment of collaboration between local and humanitarian actors in Colombia, South Sudan and the Philippines	Futureproof consulting	Working paper / Companion piece / Briefing paper / Blog	Furat Al-Murani furatalmurani@gmail.com
2	Local government management and response to Syrian refugees transiting in Croatian border towns	Institute for International Urban Development (I2UD)	Working paper / Briefing paper 1 / Briefing paper 2 / Croatian briefing / Blog	Maren Larsen marenmlarsen@gmail.com
3	La gestion humanitaire des inondations dans une commune de Niamey, Niger (Humanitarian management of floods in a district of Niamey)	LASDEL - Laboratoire d’études et recherches sur les dynamiques sociales et le développement local, Niger	Working paper	Oumar Hamani / hamani@lasdel.net
4	Typhoon Haiyan response in Tacloban, the Philippines	Gerald Paragas, Television producer and Licensed Environmental Planner	Film online / Working paper / Briefing paper	Gerald Paragas geraldparagas@gmail.com
5	The collaboration mechanisms in addressing the Syrian refugee crisis in urban settings in Lebanon	UN HABITAT Lebanon	Working paper / Briefing paper	Marwa Boustani Marwa.Boustani@unhabitat.org
6	Civilian Protection in Urban Sieges- capacities and practices of first responders: A cross-country analysis in Aleppo, Syria and Gaza, OPT	Centre for Trust, Peace & Social Relations (CTPSR), Coventry University	Briefing paper / Blog / Working paper	Chas Morrison, Research Fellow in Reconstruction / ab1224@coventry.ac.uk
	Call 2 - protection
7	Promoting the protection of children on the / move in urban contexts through including / and strengthening locally-developed child / protection practices in the humanitarian / response – in Timbuktu and Gao, Mali	Terre des Hommes Mali	Working paper (French) / Working paper (English) / Briefing paper (French) / Briefing paper (English)	Annabel Debakre annabel.debakre@tdh.ch / Salimatou Traore salimatou.traore@tdh.ch
8	Implications of humanitarian responses in the long-term: Case of Chennai	IIHS, India	Working paper / Briefing paper	Garima Jain gjain@iihs.ac.in
9	Idea Lab for Fostering Protection of Displaced Persons in Urban Areas of Northern Nigeria	Bayero University Kano, Department of Urban and Regional Planning, Nigeria	Working paper / Briefing paper	Aliyu Barau aliyubarau1@yahoo.co.uk
10	Tackling gender based violence in Gaza	IDS at University of Sussex	Briefing paper / Working paper	Catherine Mueller c.mueller@ids.ac.uk / Jean-Pierre Tranchant JP.Tranchant@ids.ac.uk
11	Hidden refugees in Egypt	American University of Cairo	Briefing paper / Working paper	Nourhan Abdel Aziz nabdelaziz@aucegypt.edu
12	Protecting IDPs in Mogadishu	Somali Disaster Resilience Institute	Working paper / Briefing paper	Mohamed Osman Mohamoud othmansom@gmail.com
13	Non-state forms of protection	Oxfam Haiti	Working paper (French) / Briefing paper (French)	Emily Bauman EBauman@oxfam.org.uk
	Call 3 – local markets
14	Urban Refugee Economies in Addis Ababa, Ethiopia	Cardiff University	Briefing paper / Working paper	Alison Brown BrownAM@cardiff.ac.uk / Peter MacKie MackieP@cardiff.ac.uk
15	Refugee and IDP participation in local markets in urban Uganda	University of East Anglia with Makerere University, Kampala	Briefing paper / E&U paper / Blog	William Monteith / William.monteith@iied.org
16	Impacts of Humanitarian Cash and Voucher Aid on Women’s Paid Work and Unpaid Care Work in Kathmandu	Social Development Direct	Working paper Blog	Zahrah Nesbitt-Ahmed Zahrah@sddirect.org.uk
17	Impact of the Syrian Crisis on Urban Food Markets in Mafraq Governorate, Northern Jordan	Centre of Agroecology, Water and Resilience (CAWR), Coventry University	Working paper / Briefing paper	Andrew Adam-Bradford ab3805@coventry.ac.uk
18	Influences of the delivery of voucher aid in the two Syrian cities of Darkoush and Salquin	Bridging Peoples (Timor Leste) and Trust Consultancy (Turkey)	Briefing paper / Working paper / Working paper (Arabic) / Briefing paper (Arabic)	Deborah Cummins deb@bridgingpeoples.com
	Call 4 – humanitarian and development nexus
19	Humanitarian response for development: Lessons from Tropical Cyclone Winston	University of Technology Sydney	Working paper / Briefing paper	Keren Winterford Keren.Winterford@uts.edu.au
20	When the humanitarian response requires urban development policies: IDPs in Bangui and sustainable responses	Groupe URD, France	Working paper (French) / Briefing paper (French) / Briefing paper (English) / Presentation given	Anne Burlat aburlat@urd.org
21	Refugee (self-)support in the city: Exploring where humanitarian norms meet development needs. A New Delhi case study.	OP Jindhal Global University, Delhi	Working paper 1 / Working paper 2 / Briefing paper / The Conversation article	Dr. Jessica Field jfield@jgu.edu.in
22	Exploring the nexus between humanitarian and development goals during on-going conflict – an Aleppo case study	Saagarika Dadu Brown, independent consultant	Working paper / Briefing paper	Saagarika Dadu-Brown saagarika.brown@gmail.com
23	Rebuilding health workforces in crisis: The case of the Syrian health workforce	University of Cambridge and Imperial College London	Working paper / Briefing paper	Adam P. Coutts apc31@cam.ac.uk

	Study title	Study lead/team	Status
	Discretionary fund
24	Review of area-based approaches	V Maynard	Working paper	Victoria Maynard victoria.c.maynard@gmail.com
25	Review of cash transfers	L Mohiddin	Working paper / Annexes / Briefing paper	Lili Mohiddin lilimohiddin@gmail.com
26	For my son (film)	RYOT	HuffPo
27	Haiti Urban Response: Learning from Community Planning	Maggie Stephenson, Darren Gill	Working paper	Maggie Stephenson maggie@mestephenson.org / Darren Gill darrensgill@gmail.com
28	Water programming in the MENA region	WSUP, London	Briefing paper / Working paper / Blog	Loan Diep ldiep@wsup.com
29	Empowerment outcomes of Urban Humanitarian Responses	SLURC, Freetown	Working paper	Joseph Macarthy jm72macarthy@yahoo.com
30	Urban planning following humanitarian crises: Supporting local actors to take the lead	Beth Parker	Working paper 1 / Working paper 2 / Blog / Blog 2 / E&U paper / Briefing paper	elizabeth elizabethruthparker@hotmail.com
31	Towards an inclusive urban reconstruction policy development process in Nepal	Jennifer Duyne and Patrick Daly	Working paper / E&U paper	Patrick Daly PatrickDaly@ntu.edu.sg

Others
Editorial: The urbanization of humanitarian crises by Diane Archer, David Dodman, Environment and Urbanization
Long read: The future of humanitarian crises is urban, by Diane Archer
Long read: Five fundamentals to keep Lebanon's water flowing by Anna Walnycki
IRIN opinion piece: Urban crisis response needs a humanitarian sector shake-up by Diane Archer

Coping with forced displacement: lessons from cities	May 2017	Blog
Write up of Urban Crises events at Habitat III	November 2016	Blog
Introducing the Global Alliance for Urban Crises	May 2016	Blog
Introducing the work of the IRC Stronger Cities learning consortium	November 2016	Blog
Write up of Nairobi IRC-IIED workshop	May 2016	Blog
Write up of Istanbul IRC-IIED workshop	September 2016	Blog
Ten urban planning principles every humanitarian should know	November 2015	Blog

Stronger cities consortium
All of the outputs remain available on the project website as follows:
Basedow, J, Westrope, C and Meaux, A (2017) Urban stakeholder engagement and coordination. Guidance note for humanitarian practitioners. IIED, London.

Sitko, P (2017) Enacting urban cash for work programmes in Lebanon in response to the Syrian refugee crisis. Guidance note for humanitarian practitioners. IIED, London.

Norwegian Refugee Council (2017) Security of tenure in urban areas. Guidance note for humanitarian practitioners. IIED, London.

Mohiddin, L, Smith, G and Phelps, L (2017) Urban multi-sector vulnerability assessment tool for displacement contexts (UMVAT). Guidance note for humanitarian practitioners. IIED, London.

International Rescue Committee (2017) Urban context analysis toolkit. Guidance note for humanitarian practitioners. IIED, London.

Bermudez, LG (2017) Integrating livelihoods and protection for displaced persons in urban humanitarian response. Guidance note for Humanitarian Practitioners. IIED, London.

Smith, G Mohiddin, L and Phelps, L (2017) Targeting in urban displacement contexts. Guidance note for humanitarian practitioners. IIED, London.

Mohiddin, L, Smith, G and Phelps, L (2017) Urban Response Analysis Framework (URAF). Guidance note for humanitarian practitioners. IIED, London.

Sanderson, D and Sitko, P (2017) Urban area-based approaches in post-disaster contexts. Guidance note for Humanitarian Practitioners. IIED, London

Implementing area-based approaches (ABAs) in urban post-disaster contexts, Environment and Urbanization

Urban Crises Learning Partnership consortium
Emergent groups and spontaneous volunteers in urban disaster response, Environment and Urbanization